NT10BIX5570148 | 2012 | Q4 | Q4 - 2012 | Finished the pedestrian cultural survey on Badger Creek Road on the Blackfeet Reservation. Transport electronics have been installed in Missoula, Arlee, St. Ignatius, Ronan and Pablo. Solarwinds software and Dell servers have been installed at the Missoula fiber hotel and the Network operations center is now fully operational, monitoring the part of the network that has been installed. Finished the redundant loop fiber installation from St. Ignatius to Ronan. Upgraded 60 existing wireless customers in Arlee and added 10 new ones, for a total of 70. | 121 | 797 | 106 | 0 | 121 | 1 | 0 | 7 | Projected 264. Work stoppage on the Blackfeet and schedule slippage by our contractor both have impacted miles planned for completion. | Projected 321 | Projected 106, no variance (106 in kind fiber match) | Projected 0 | Projected 264. Work stoppage on the Blackfeet has impacted miles planned for completion. | Projected 4. Wireless is scheduled for the end of the middle mile build, so project slippage has impacted it. | N/A | Projected 17. Seattle, Missoula, Arlee, St. Ignatius, Ronan, Santa Rita, and Pablo. Overall project slippage has impacted the number of connection points. | 3 | 1 | 12 | Cablevision (Bresnan)...dark fiber Cutthroat Communications...bandwidth Montana Skynet...bandwidth | We have executed a contract with Bresnan for a 20-year prepaid IRU for 2 dark fibers. They will prepay in a lump sum when installed and accepted. We have executed a contract with Cutthroat Communications for the provision of 2Gb ethernet from Missoula to Seattle for a monthly recurring charge of $5600, term of 36 months. | The Montana West system's Network Operations Center is now fully operational, and monitors all electronics and links presently installed. | 0 | 2 | 1 | 4 | Projected 0 | Projected 4. Project delays have impacted this projection. Montana Skynet and Cutthroat Communications | Projected 0. Bresnan has executed an IRU agreement with Montana West for dark fiber when available. Originally scheduled for August 2012, now scheduled for next quarter (April 2013) | 100Mb, 1Gb, 2Gb, dark fiber 100Mb (1), 2Gb (1), dark fiber (1) | 0 | 0 | 0 | 2 | Projected 32. Blackfeet work stoppage and contractor slippages have impacted our ability to provide planned service. | Projected 0. | Projected 32. Blackfeet work stoppage and contractor slippages have impacted our ability to provide planned service. | 100Mb and 1Gb | 190 | 70 | 0 | 0 | 3 | Projected 1210. Overall project slippage has impacted this planned provision of services. | Projected 318. Overall project slippage has impacted this planned provision of services. 70 wireless customers in Arlee, 60 upgraded and 10 new customers. | Projected 42. Overall project slippage has impacted this planned provision of services. | Projected 276. Overall project slippage has impacted this planned provision of services. | 1.5Mb, 2.5Mb, 4Mb 1.5Mb (55), 4Mb (15) | 12 | 0 | 0 | 0 | 4 | Projected 171. Overall project slippage has impacted this planned provision of services. | Projected 67. Overall project slippage has impacted this planned provision of services. | Projected 22. Overall project slippage has impacted this planned provision of services. | Projected 45. Overall project slippage has impacted this planned provision of services. | 10Mb, 20Mb, 50Mb, 100Mb | We do not anticipate any special offerings other than wholesale bandwidth and Internet connectivity to other providers and to businesses and anchor institutions. | FALSE | N/A | Negotiations will complete with the Blackfeet and work will start again on the Blackfeet Reservation. Wireless services will be completed to Arlee and Elmo. Fiber backbone will be completed to Browning and East Glacier on the Blackfeet. Northern section of the Western network will be completed. Additional 1Gb upstream will be obtained from Seattle. An ISP in Kalispell will sign up for service. Number of miles planned for next quarter: Blackfeet 37 Number of CAI's planned for next quarter: 18 Number of broadband wholesaler/last mile provider agreements planned for next quarter: 2 | Ronan Telephone Co. | The Blackfeet Tribe stopped the project on the Blackfeet Reservation on August 3. Negotiations have been ongoing since then. BTOP program management has been involved in direct discussions with the Tribe to effect a resolution. Due to the work stoppage the remaining time left in the grant has been reduced to the point that alternative Internet delivery methods are being examined...potentially microwave to reach the outlying areas in order to complete the grant in the time allotted. | --AAR for a project modification for a route change from the west shore of Flathead Lake to the East shore will require assistance from BTOP with a short time frame due to contractor schedule slippages. --AAR for route change and fiber to microwave on the Blackfeet, if we can get the Tribe to give us a go ahead...will need help on both the AAR and the contract negotiations. | TRUE
NT10BIX5570148 | 2013 | Q1 | Q1 - 2013 | Negotiations were completed with the Blackfeet Tribe and construction resumed. Middle mile fiber route with all electronics between Pablo and Missoula was completed, tested and fully operational. This enabled delivery of one half of the service (the southern route) contracted for with Bresnan. Fiber has been completed and tested between Cut Bank and Browning. An additional 1Gb upstream transport has been contracted for in Seattle. Peering has started in Seattle with 21 content providers now peering with Montana West. | 143 | 797 | 106 | 0 | 143 | 1 | 0 | 7 | Projected 264. Work stoppage on the Blackfeet and schedule slippage by our contractor both have impacted miles planned for completion. | Projected 321. | Projected 106. No variance | Projected 0 | Projected 264. Work stoppage on the Blackfeet has impacted miles planned for completion. | Projected 4. Wireless is scheduled for the end of the middle mile build, so project slippage has impacted this schedule. | N/A | Projected 17. Overall project slippage has impacted the number of connection points. | 3 | 1 | 12 | Cablevision (Bresnan) Cutthroat Communications Montana Skynet | Bresnan: 20 Year prepaid IRU for 2 dark fibers Cutthroat Communications: 2Gb ethernet Missoula to Seattle, $5600 per month. Montana Skynet: 200Mb Internet, $18/Mb/Mo, $200/Mo/Port | Montana West operates its own network with a network operations center. | 0 | 2 | 1 | 4 | Projected 0 | Projected 4. Project delays have impacted this projection. | Projected 1. Prepaid IRU with Bresnan for dark fiber. | (1) 100Mb, 1Gb, (1) 2Gb, (1) dark fiber | 0 | 0 | 0 | 2 | Projected 32. Blackfeet work stoppage and contractor slippages have impacted our ability to provide this planned service. | Projected 0 | Projected 32. Blackfeet work stoppage and contractor slippages have impacted our ability to provide this planned service. | 100Mb and 1Gb | 190 | 70 | 0 | 0 | 3 | Projected 1210. Overall project slippage has impacted this planned provision of services. | Projected 318. Overall project slippage has impacted this planned provision of services. 70 wireless customers in Arlee, 60 upgraded and 10 new customers. | Projected 42. Overall project slippage has impacted this planned provision of services. | Projected 276. Overall project slippage has impacted this planned provision of services. | (55) 1.5Mb, 2.5Mb, (15) 4Mb | 12 | 0 | 0 | 0 | 4 | Projected 171. Overall project slippage has impacted this planned provision of services. | Projected 67. Overall project slippage has impacted this planned provision of services. | Projected 22. Overall project slippage has impacted this planned provision of services. | Projected 45. Overall project slippage has impacted this planned provision of services. | 10Mb, 20Mb, 50Mb, 100Mb | We do not anticipate any special offerings other than wholesale bandwidth and Internet connectivity to other providers and to businesses and anchor institutions. | FALSE |  | Once our CAI list passes the Environmental Assessment, we will install or upgrade 17 CAI's. We plan to install 45 miles of fiber on the Blackfeet, and 42 miles of fiber between Kalispell and Polson. | Ronan Telephone Co. | Work stoppage continued on the Blackfeet Reservation through this quarter until mid February. Once negotiations were completed and the Tribe authorized the project to restart, it took 3 to 4 weeks to engage a contractor and for mobilization of the work force before we could start again. Budget modifications were made this quarter that fall below the 10% threshhold: Moved $250,000 out of the equipment budget. Added $50,000 to the legal budget--Blackfeet issues. Added $10,530 to Network Testing to pay for the test equipment. Added $1328 to Permits to correct the over budget situation. Added $188,142 to Network Design to pay for network hardware. | EA approval for the CAI's may cause slippages in the schedule. Our contractor has slipped his schedule numerous times, and we may need help in leveraging resources to finish on time. The Blackfeet is a challenge to get right of ways to finish...we may need to go to microwave if we cant get the easements necessary to get to St. Mary and Babb. | TRUE
NT10BIX5570148 | 2013 | Q2 | Q2 - 2013 | Electronics were installed in Santa Rita and Browning and testing between Missoula and Santa Rita was completed. Fiber installation was completed between Cut Bank and Browning and between Browning and East Glacier Park. Permits were obtained from MDOT for the fiber route between Browning and Hwy89 for the St. Mary/Babb route. Cultural survey was completed for the Horn Ridge microwave site and the access road to it, for wireless service to Heart Butte. | 143 | 797 | 106 | 0 | 143 | 1 | 0 | 17 | Projected 295, Work stoppage on the Blackfeet and schedule slippage by our contractor both have impacted miles planned for completion. | Projected 321 | Projected 106, no variance | Projected 0 | Projected 295, Work stoppage on the Blackfeet and schedule slippage by our contractor both have impacted miles planned for completion. | Projected 4, Wireless is scheduled for the end of the middle mile build, so project slippage has impacted this schedule. | N/A | Projected 18. Overall project slippage has impacted the number of connection points. | 3 | 1 | 12 | Bresnan Cutthroat Communications Montana Skynet | Bresnan: 20 Year prepaid IRU for 2 dark fibers Cutthroat Communications: 2Gb ethernet Missoula to Seattle, $5600 per month. Montana Skynet: 200Mb Internet, $18/Mb/Mo, $200/Mo/Port | Montana West operates its own network with a network operations center. | 0 | 2 | 1 | 4 | Projected 0 | Projected 4, Project delays have impacted this projection. | Projected 1, Prepaid IRU with Bresnan for dark fiber | (1) 100mb, 1Gb, (1) 2Gb, (1) dark fiber | 0 | 0 | 0 | 2 | Projected 33, Blackfeet work stoppage and EA review have slipped this planned service provision. | Projected 0 | Projected 33, Blackfeet work stoppage and EA review have slipped this planned service provision. | 100mb and 1Gb | 190 | 70 | 10 | 60 | 3 | Projected 1810. Overall project slippage has impacted the planned provision of services. | Projected 468. Overall project slippage has impacted the planned provision of services. 70 wireless customers in Arlee, 60 upgraded and 10 new customers. | Projected 51. Overall project slippage has impacted the planned provision of services | Projected 417. Overall project slippage has impacted the planned provision of services | (55) 1.5Mb, 2.5Mb, (15) 4Mb | 12 | 0 | 0 | 0 | 4 | Projected 186. Overall project slippage has impacted the planned provision of services | Projected 67. Overall project slippage has impacted the planned provision of services | Projected 22. Overall project slippage has impacted the planned provision of services | Projected 45. Overall project slippage has impacted the planned provision of services | 10Mb, 20Mb, 50Mb, 100Mb | We do not anticipate any special offerings other than wholesale bandwidth and Internet connectivity to other providers and to businesses and anchor institutions. | FALSE | Our network management practices have not changed. | We plan to install 45 miles of fiber on the Blackfeet, and 42 miles of fiber between Kalispell and Polson. We will begin providing backhaul to Oki Communications in Browning, and will deliver service to Blackfeet Tribal Headquarters. We will make service available to 17 CAI's upon receiving EA approval. Total cumulative new miles deployed will be 230 (143+45+42). We expect to sign an additional broadband wholesaler/last mile provider next quarter for a cumulative total of 4. | Ronan Telephone Co. | Moved balance of Equipment Budget to Construction--$168,191. The budget modifications to date are still under the 10% thresh hold. Expenses in Equipment category were miscoded. We moved them to the Construction category. It took time to research rights of way issues on the St. Mary/Babb route, and it was decided to obtain consents from signature companies in preparation for a fiber build instead of microwave. It was decided to build microwave to support Heart Butte, based on the difficulties in obtaining owner consents on the two routes to that community for fiber. | EA review for the CAI's is impacting our schedule. Contractor building the northern route to Kalispell has slipped the delivery date almost every month since last August. Latest estimate for delivery is by the end of September. We have applied for an extension as a result of both contractor slippages and work stoppages on the Blackfeet. | TRUE
NT10BIX5570148 | 2013 | Q3 | Q3 - 2013 | July August September---Montana West was granted a one-year extension until August 31, 2014. This was necessary due to delays to the schedule brought about by difficulties in obtaining rights of way. 54 new miles of fiber were deployed, mostly by blowing in fiber to conduit that was placed last quarter. Progress has also been made during this quarter in obtaining rights of way for access to and location of a microwave site on Horn Ridge, which will be used to provide high speed Internet to the community of Heart Butte on the Blackfeet Reservation. Wireless Internet has been provided to Elmo/Big Arm. | 197 | 797 | 106 | 0 | 197 | 2 | 0 | 17 | Projected 295. 54 new miles were deployed this quarter. We were working on getting easements on the Blackfeet reservation and the contractor building fiber between Kalispell and Pablo had delays in their schedule. | Projected 321 | Projected 106, no variance | Projected 0 | Projected 295. 54 new miles were deployed this quarter. We were working on getting easements on the Blackfeet reservation and the contractor building fiber between Kalispell and Pablo had delays in their schedule. | Projected 4, added Elmo/Big Arm wireless this quarter. Remaining wireless is scheduled for the end of the middle mile build, so overall project slippage has impacted this schedule. | N/A | Projected 18. Overall project slippage has impacted the number of connection points. | 3 | 1 | 12 | Bresnan Cutthroat Communications Montana Skynet | Bresnan: 20 Year prepaid IRU for 2 dark fibers Cutthroat Communications: 2Gb ethernet Missoula to Seattle, $5600 per month. Montana Skynet: 200Mb Internet, $18/Mb/Mo., @1400/Mo/Port | Montana West operates its own network with a network operations center. | 0 | 2 | 1 | 4 | Projected 0 | Projected 4, Project delays have impacted this projection. | Projected 1, prepaid IRU with Bresnan for dark fiber | 100Mb (1), 1Gb , 2Gb (1), dark fiber (1) | 0 | 0 | 0 | 2 | Projected 33, Difficulties in obtaining rights of way has impacted the project schedule, and EA review have slipped this planned service provision. | Projected 0 | Projected 33, Difficulties in obtaining rights of way has impacted the project schedule, and EA review have slipped this planned service provision. | 100Mb and 1Gb | 190 | 96 | 36 | 60 | 3 | Projected 1810. Overall project slippage has impacted the planned provision of services. | Projected 468. Overall project slippage has impacted the planned provision of services. 96 wireless customers in Arlee, 60 upgraded and 36 new customers. | Projected 51. Overall project slippage has impacted the planned provision of services. | Projected 417. Overall project slippage has impacted the planned provision of services. | 1.5Mb (66), 2.5Mb, 4Mb (30) | 12 | 0 | 0 | 0 | 4 | Projected 186. Overall project slippage has impacted the planned provision of services. | Projected 67. Overall project slippage has impacted the planned provision of services. | Projected 22. Overall project slippage has impacted the planned provision of services. | Projected 45. Overall project slippage has impacted the planned provision of services. | 10Mb, 20Mb, 50Mb, 100Mb | We do not anticipate any special offerings other than wholesale bandwidth and Internet connectivity to other providers and to businesses and anchor institutions. | FALSE | Our network management practices have not changed. | Once the northern route to Kalispell is delivered by the contractor, and we receive our route change approval, we expect to be able to offer service from Missoula all the way through both the Mission and Flathead valleys to Kalispell. We expect to complete the requirements necessary to obtain EA approval of our CAI builds and will aggressively pursue these builds. We will have completed builds to 6 CAI's by the end of this quarter. We do not have any planned sales to additional broadband/wholesaler/last mile providers for this quarter. We plan on completing the microwave build to Heart Butte, and will start delivering wireless broadband to that community on the Blackfeet Reservation. Total cumulative miles deployed will be 197 + 42 (Kalispell to Pablo) + 31 (Microwave to Heart Butte) or 270 network miles. | Ronan Telephone Co. | g. Site Work on "The Infrastructure Budget Execution Details" went down due to a refund from Mission Valley Power on the electrical requirements for the Big Arm site. We experienced some delays waiting for response from Native American Tribes regarding Cultural concerns on the Blackfeet Reservation. The contractor building the fiber route on the east shore of Flathead Lake delayed their progress for a variety of reasons, which impacted our construction schedule. | EA approval of our project modifications regarding route changes, and the CAI builds are the only issues that could potentially impact our schedule. Weather is always a factor in our area, however we expect to finish both the western side of the network and the microwave build to Heart Butte this next quarter, hopefully before the snow flies and the ground freezes. | TRUE
NT10BIX5570148 | 2013 | Q4 | Q4 - 2013 | The Northern route around Flathead Lake on Hwy 35 between Polson and Kalispell was completed and accepted as a route change by the Program Office. This completed the build on the Western side of the project. We received EA approval for our CAI builds and have completed upgrades or builds to 13 of the 33 in our schedule. A Master Services Agreement was executed with the Confederated Salish and Kootenai Tribes for service to 48 tribal departments, offices and tribal affiliated entities on the reservation. Landowner consents and surveys have been obtained for easements for the microwave facilities to serve the community of Heart Butte on the Blackfeet reservation. The consent process has been started for the fiber route between Browning and St. Mary/Babb on the Blackfeet reservation. | 254 | 797 | 106 | 0 | 254 | 2 | 0 | 23 | Projected 295. 57.41 new miles were deployed this quarter. This was the completion of the northern route between Polson and Kalispell. 63.6 miles remain (42.6 fiber and 21 microwave miles) on the Blackfeet reservation. | Projected 321 | Projected 106, no variance | Projected 0 | Projected 295. 57.41 new miles were deployed this quarter. This was the completion of the northern route between Polson and Kalispell. 63.6 miles remain (42.6 fiber and 21 microwave miles) on the Blackfeet reservation. | Projected 4. Overall project slippage has impacted this task. | N/A | Projected 18...surpassed projections | 3 | 1 | 12 | Bresnan Cutthroat Communications Montana Skynet | Bresnan: 20 Year prepaid IRU for 2 dark fibers Cutthroat Communications: 2Gb ethernet Missoula to Seattle, $5600 per month. Montana Skynet: 200Mb Internet, $18/Mb/Mo., @1400/Mo/Port | Montana West operates its own network with a network operations center. | 0 | 2 | 1 | 5 | Projected 0 | Projected 4, Project delays have impacted this projection. | Projected 0, prepaid IRU with Bresnan for dark fiber | 100Mb (0), 200Mb (1), 1Gb (0), 2Gb (1), dark fiber (1) | 13 | 1 | 12 | 2 | Projected 33. Overall project delays with rights of way and EA review has slipped this schedule. | Projected 0 | Projected 33, 11 upgrades plus Mission Valley Power | 100Mb (13), 1Gb (0) | 1210 | 112 | 52 | 60 | 4 | Projected 1810. Project delays impacted this projection. | Projected 468. Project delays impacted this projection. | Projected 51. Surpassed this projection. | Projected 417. Project delays impacted this projection. | 1.5Mb (28), 2.5Mb (5), 4Mb (76), 100Mb (3) | 160 | 5 | 0 | 5 | 4 | Projected 186. Project delays impacted this projection. | Projected 67. Project delays impacted this projection. | Projected 22. Project delays impacted this projection. | Projected 45. Project delays impacted this projection. | 10Mb (0), 20Mb (0), 50Mb (2), 100Mb (3) | We do not anticipate any special offerings other than wholesale bandwidth and Internet connectivity to other providers and to businesses and anchor institutions. | FALSE | Out network management practices have not changed. | We plan to complete installation to a total of 27 of the 33 CAI's. (14 additional over the 13 already installed or upgraded) We plan to install the microwave site to support wireless to Heart Butte, pending on AAR approval of the route change, easements, and as always depending on the weather. We also plan on acquiring easements for the fiber route to St. Mary/Babb. We do not expect to complete any miles of fiber or microwave installation in the next quarter due to the severe weather on the Blackfeet in the winter. We do not anticipate signing any additional wholesale or last mile agreements during the next quarter. | Ronan Telephone Co. | A particularly harsh winter in December halted some construction. No other significant challenges presented themselves. | We need approval for our consolidated route change AAR. Acquisition of easements is a complex process on the Blackfeet. We have engaged the services of an expert to assist us in this effort, and he is currently identifying landowners on the Duck Lake Road route and obtaining signatures for consent to move forward. This requires at least 51% of the landowners consent in order to move forward with surveying, appraisals and finally application for approval from the BIA. Along with the weather, this will be our most significant challenge next quarter. | TRUE
NT10BIX5570150 | 2010 | Q4 | Q4 - 2010 | Worked with fiber vendor to finalize fiber route paths and produce route maps with sufficient detail to support environmental assessment requirements. Provided maps and project detail to program office for dissemination to appropriate agencies for environmental assessment. Researched and retained environmental consulting firm to conduct and draft required environmental assessment report. Began data gathering and discussions with appropriate federal and state agencies relative to the environmental assessment. Began review and updating of overall network design to accommodate any changes since application submission and incorporate changes in technology. Validate address and contact information for all Community Anchor Institutions. Submit necessary reports and baseline project plans as required by the grant award conditions. Attended the Round Two Post-Award Recipient workshop in Herndon, Virginia. Obtained approval for 6 Month Expenditure Plan and budget reclassification request. Due to the Special Award Condition limiting project activities to non-construction initiatives, the project milestones pertaining to equipment procurement, network build, equipment deployment and network testing were not addressed during this reporting period. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not started due to Environmental Assessment requirements | N/A | Not started due to Environmental Assessment requirements | N/A | Not started due to Environmental Assessment requirements | N/A | N/A | Not started due to Environmental Assessment requirements | 0 | 0 | 0 | None at this time | Not planned in this project | N/A | 0 | 0 | 0 | 0 | Zero variance | Zero variance | N/A | 10 Mbps - 0 subscribers at this time 100 Mbps - 0 subscribers at this time | 0 | 0 | 0 | 0 | Project has not begun construction phase | Zero variance | Zero variance | 100 Mbps - 0 subscribers at this time 1000 Mbps - 0 subscibers at this time | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None planned at this time | FALSE | No changes | Finish environmental assessment data gathering and provide to consultant for report inclusion. Environmental consultant to finalize environmental assessment report and submit to program office as required. Once submitted, obtain final approval and Finding of No Significant Impact (FONSI). Finalize network design and obtain approval for any necessary changes. | Department of Administration Services Bureau of Enterprise Systems & Technology | A minor challenge faced was longer than anticipated report and Award Action Request approval time frames. While this did not affect overall milestone completion percentage objectives from a work effort basis, it did make accomplishing these milestones more difficult than planned and it has delayed receiving and paying several invoices until next quarter. | None at this time | TRUE
NT10BIX5570150 | 2011 | Q1 | Q1 - 2011 | Continued to work with fiber vendor to validate fiber route paths and support data gathering for the submission of the Environmental Assessment. Worked with Environmental Assessment consultant and relevant State and Federal agencies to complete required Environmental Assessment consultations and project reviews. Obtained required input and comments from consulted agencies for inclusion in the Environmental Assessment submission. Submitted final draft of Environmental Assessment to appropriate National Telecommunications and Information Administration resources and systems for review and approval. Continued review and updating of overall network design to incorporate changes and efficiencies that have occurred since application submission and grant award. Worked with fiber and equipment vendors to further refine implementation planning and scheduling of site work. Incorporated these updates into the overall project plan timelines. Obtained approval for extension of the 6 Month Expenditure plan to accommodate anticipated delay in receiving approval of the Environmental Assessment and lifting of the Environmental Assessment Special Award Condition. Due to the Special Award Condition limiting project activities to non-construction initiatives, the project milestones pertaining to equipment procurement, network build, equipment deployment and network testing are not addressed during this reporting period. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started due to Environmental Assessment requirements | N/A | Not Started due to Environmental Assessment requirements | N/a | Not Started due to Environmental Assessment requirements | N/A | N/A | Not Started due to Environmental Assessment requirements | 0 | 0 | 0 | None at this time | Not planned in this project | N/A | 0 | 0 | 0 | 0 | Zero Variance - Deployment activities have not begun | Zero Variance - Deployment activities have not begun | N/A | 10 Mbps - 0 at this time 100 Mbps - 0 at this time | 0 | 0 | 0 | 0 | Project has not begun deployment activities | Project has not begun deployment activities | Project has not begun deployment activities | 10 Mbps - 0 at this time 100 Mbps - 0 at this time | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None planned at this time | FALSE | No changes | The State expects to receive approval for the submitted Environmental Assessment and a Finding of No Significant Impact (FONSI) this quarter. This will allow lifting of the Environmental Assessment Special Award Condition and for the project to proceed with implementation and deployment activities. These activities include equipment procurement, network build, equipment deployment and network testing. Additionally, the final network design and operational configuration parameters will be finalized this quarter. We anticipate that approximately 75 Community Anchor Institutions and significant portions of the fiber backbone to be completed during this quarter. | Department of Administration Services Bureau of Enterprise Systems & Technology | Vendor invoices are not being received as quickly as anticipated and therefore not reflected in draw down or expenditure activities as planned. We expect this issue to diminish once implementation and deployment activities begin next quarter. | Later than anticipated receipt of FONSI (40+ days) will delay starting of deployment activities as previously planned and submitted in the Baseline Report. It is anticipated that these delays will be compensated for over the next 2 quarters and the project back on schedule prior to close of 3Q2011. This will allow all other goals and objectives to be met as planned. | TRUE
NT10BIX5570150 | 2011 | Q2 | Q2 - 2011 | Received signed copy of Finding of No Significant Impact (FONSI) regarding the submitted Environmental Assessment and satisfaction of Special Award Condition (SAC) 11 on April 27, 2011. This notification has allowed the project to move forward into the deployment and activation phases. The project began site surveys and site preparation for equipment installation at core and edge sites. Equipment was ordered for the sites planned for this quarter. The project deployed 36 miles of off-net and 747 strand miles of on-net fiber, completing optical spans to 59 core sites. During this quarter, the project did not have to implement any of the specified pre-approved protocols required by the Environmental Assessment Special Award Conditions. Equipment was installed and activated at 59 core sites. Continue fiber deployment to remaining core sites and begin deployment of fiber to edge sites. | 36 | 0 | 747 | 0 | 783 | 0 | 0 | 59 | Later than anticipated receipt of FONSI delayed starting of deployment activities. | N/A | Later than anticipated receipt of FONSI delayed starting of deployment activities. | N/A | Later than anticipated receipt of FONSI delayed starting of deployment activities. | N/A | N/A | Later than anticipated receipt of FONSI delayed starting of deployment activities. | 0 | 0 | 0 | None at this time | Not planned in this project | N/A | 0 | 0 | 0 | 0 | Zero Variance | Zero Variance | Zero Variance | 10 Mbps - 0 Subscribers 100 Mbps - 0 Subscibers | 59 | 59 | 0 | 59 | Later than anticipated receipt of FONSI delayed starting of deployment activities. | Later than anticipated receipt of FONSI delayed starting of deployment activities. | Zero Variance | 10 Mbps - 0 at this time 100 Mbps - 0 at this time 1000 Mbps - 59 at this time Later than anticipated receipt of FONSI delayed starting of deployment activities. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None planned at this time | FALSE | No changes | Planned deployment of an additional 150 miles of off-net fiber and an additional 1800 strand miles of on-net fiber. Ordering of equipment for this quarter. Installation of equipment and connectivity to an additional 80 CAI locations. | Department of Administration Services Bureau of Enterprise Systems & Technology | Later than anticipated receipt of FONSI and lifting of Environmental Assessment SAC 11 delayed project implementation and deployment activities by approximately 65 days. Additionally, new SAC requirements specified in the FONSI institutes time-of-year work restrictions in specific areas and has necessitated adjustments to the planned deployment schedule. These factors have the net effect of reducing the deployment related anticipated completion percentage milestones planned for this quarter as well as for Q3 and Q4 of 2011. However, these delays and adjustments have been incorporated into the overall project plan and the project anticipates being back on schedule by the end of Q1 of 2012. From a budget perspective, because the reporting shows only actual expense expenditures for the quarter and does not include encumbered amounts, some milestones may show less than actual due to vendor invoice timing. | Later than anticipated receipt of FONSI has delayed deployment activities. Project anticipates being back on schedule by end of Q1-2012. | TRUE
NT10BIX5570150 | 2011 | Q3 | Q3 - 2011 | This quarter activities included deployment of an additional 170 miles of off-net and 1751 miles of on-net fiber, bringing the total deployed fiber for the project to 206 miles of off-net and 2498 miles of on-net fiber. Received and installed equipment at 59 additional core sites (project total now at 118 sites). Continued fiber deployment and optical span activation to edge sites as planned for this quarter. Continued remediation and site survey tasks at edge sites as required. Ordered necessary equipment and materials to support next 2 quarter planned deployment schedule. Continue to conduct project and status review meetings with all project teams and stakeholders. Collect and assemble information surrounding key project metrics. Produce and file appropriate reports relative to the project status and financial performance with the necessary entities and stakeholder groups. | 206 | 0 | 2498 | 0 | 206 | 0 | 0 | 118 | On schedule | N/A | Ahead of schedule | N/A | On schedule | N/A | N/A | Later than anticipated start of deployment reduced number of projected POI completed this quarter. (Note that in this project, POI's are located at the CAI locations) | 0 | 0 | 0 | None at this time | Not planned in this project | N/A | 0 | 0 | 0 | 0 | Zero Variance from plan | Zero Variance from plan | Zero Variance from plan | 10 Mbps - 0 Subscribers 100 Mbps - 0 Subscribers | 118 | 118 | 0 | 3 | Later than anticipated start of deployment reduced number of projected CAI completed this quarter | Later than anticipated start of deployment reduced number of projected CAI completed this quarter | Zero Variance from plan | 10 Mbps - 0 at this time 100 Mbps - 0 at this time 1000 Mbps - 118 at this time Later than anticipated start of deployment reduced number of projected CAI completed this quarter | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None planned at this time | FALSE | N/A | Continued deployment of fiber, currently projected to include 100 miles of off-net fiber and 500 strand miles of on-net fiber. Continued receipt and deployment of equipment for planned CAI locations. Provide connections into an additional 80 CAI locations. | Department of Administration Services Bureau of Enterprise Systems & Technology | Previous quarter impacts from delayed FONSI, additional SAC requirements and delayed start of deployment are affecting this quarter performance projections. These factors are expected to continue for Q4-2011 and Q1-2012. However, these delays and requirements have been incorporated into the overall project plan and project is anticipated to be back on schedule by end of Q1-2012. During this quarter, 8 planned locations were subject to additional SAC requirements. 6 of these locations are still being reviewed by the appropriate environmental agencies and no work has been started. 2 of the locations fell within the predetermined protocols (blocked existing conduit required ground disturbance that did not extend beyond a 5 foot radius of existing utility poles or underground conduits) and were successfully mitigated as required and all SAC requirements were complied with. | Winter months and weather conditions may adversely affect fiber deployment. Additional SAC compliance for selected sites may be subject to delay depending upon appropriate agencies review timing. | TRUE
NT10BIX5570150 | 2011 | Q4 | Q4 - 2011 | This quarter's activities included deployment of an additional 81 miles of off-net (new) and 1092 miles of on-net (upgraded) fiber, bringing the total deployed fiber for the project to 287 miles of off-net and 3590 miles of on-net fiber. Completed installation at 18 additional sites. Received and installed equipment at 80 additional sites. However, due to an engineering inaccuracy, one specific part for each of those sites was incorrectly ordered, thereby preventing installation completion as planned and listing of those sites as completed in this reporting period. Replacement parts have been ordered and are anticipated to be received in early Q1-2012, at which point they will be installed and those sites officially completed. Continued fiber deployment and optical span activation to edge sites as planned for this quarter. Continued remediation and site survey tasks at edge sites as required. Completed equipment ordering requirements to support planned deployments for Q2-2012. Conducted project and status review meetings with all project teams and stakeholders. Interviewed and selected candidates for additional program support staff to begin in Q1-2012. Collect and assemble information surrounding key project metrics. Produce and file appropriate reports relative to the project status and financial performance wit the necessary entities and stakeholder groups. | 287 | 0 | 3590 | 0 | 287 | 0 | 0 | 136 | On schedule | N/A | Ahead of schedule | N/A | On schedule | N/A | N/A | Equipment and fiber were installed at 80 additional sites this quarter. However, a mis-ordered part prevented these sites to be fully completed and reported. | 0 | 0 | 0 | None at this time | Not planned in this project | N/A | 0 | 0 | 0 | 0 | Zero Variance | Zero Variance | Zero Variance | Zero Variance | 136 | 136 | 0 | 3 | Equipment and fiber were installed at 80 sites this quarter. However, a mis-ordered part prevented these sites to be fully completed and reported. Therefore, the total subscribers served was affected. | Equipment and fiber were installed at 80 sites this quarter. However, a mis-ordered part prevented these sites to be fully completed and reported. Therefore, the total subscribers served was affected. | Zero variance from plan | 10 Mbps - 0 at this time 100 Mbps - 0 at this time 1000 Mbps - 136 at this time Equipment and fiber were installed at 80 sites this quarter. However, a mis-ordered part prevented these sites to be fully completed and reported. Therefore, the total subscribers served was affected. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None planned at this time. | FALSE | N/A | Continue deployment of fiber, currently projected to be an additional 100 miles of off-net fiber and 500 strand miles of on-net fiber. Continued receipt and deployment of equipment to planned CAI locations, currently projected to be 180 (100 new plus 80 partially completed during this quarter). Connection of CAI into network. Addition of 2 project staff for project management and administrative support. | Department of Administration Services Bureau of Enterprise Systems & Technology | Previous quarter impacts from delayed FONSI, additional SAC requirements and delayed start of deployment activities have affected this quarter milestone projections. These factors are expected to continue through the end of Q1-2012. Additionally, the mis-ordered part did not allow the planned sites to be reported as completed. Both of these factors are anticipated to be fully remediated during Q1-2012. During this quarter, SAC requirements for 6 sites were successfully mitigated following approved protocols as required and no new instances of EA compliance were necessary. | Winter months and weather conditions may adversely affect fiber deployment. Additional SAC compliance for selected sites may be subject to delay depending upon appropriate agencies review timing. | TRUE
NT10BIX5570150 | 2012 | Q1 | Q1 - 2012 | The activities for this quarter included deployment of an additional 212 miles of off-net (new) and 1289 miles on-net (upgraded) fiber bringing the total deployed fiber for the project to 499 of off-net and 4879 of on-net fiber. Completed activation of portions of the network backbone, allowing 306 sites to receive improved access. Completed installations at 99 additional sites. Continued fiber deployment and optical span activation to core and edge sites as planned for this quarter. Continued site remediation and site survey tasks at edge sites as required. Completed equipment ordering to meet planned deployment schedules. Added two (2) project staff members (Project Manager and Project Administrator). Conducted weekly project and status review meetings with all project teams and management stakeholders. Collect and assembled information surrounding key project metrics. Produce and file appropriate reports relative to the project and financial status with the necessary entities and stakeholder groups. | 499 | 0 | 4879 | 0 | 499 | 0 | 0 | 235 | Ahead of schedule | N/A | Ahead of schedule | N/A | Ahead of schedule | N/A | N/A | Slightly behind planned schedule. Later than anticipated start of project due to initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 0 | 0 | 0 | None at this time | None planned in the project | N/A | 0 | 0 | 0 | 0 | Zero Variance | Zero Variance | Zero Variance | Zero Variance | 541 | 235 | 306 | 3 | Slightly behind planned schedule. Later than anticipated start of project due to initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | Slightly behind planned schedule. Later than anticipated start of project due to initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | The number of subscribers to receive improved access was originally estimated to be 342. The total number has been adjusted downward to reflect the actual number of subscribers. This downward change was due to subscribers choosing to utilize an alternate provider as well as location utilization requirements changing and no longer requiring connectivity. | 10 Mbps - 306 100 Mbps - 39 1000 Mbps - 196 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None planned at this time | FALSE | N/A | Continued deployment of fiber miles. Completion and submittal of a Route Change Request and supporting environmental assessment documentation. Continued receipt and deployment of equipment to planned sites. Addition of a Project Administrator to support ongoing site coordination activities. The project is anticipating completing an additional 100 miles of off-net (new) and 700 miles of on-net (upgraded) fiber connectivity during this quarter as well as completing installations at an additional 100 sites. | Department of Administration Services Bureau of Enterprise Systems & Technology | Previous quarter impacts from delayed initial FONSI receipt, additional SAC requirements and delayed start of deployment activities continue to affect originally planned milestone projections. Additionally, coordination of site visits for installation and testing are taking longer than anticipated. We are in the process of adding program staff to assist in the coordination efforts. It is anticipated that these schedule variances from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | A Route Change Request will be submitted along with appropriate environmental assessment documentation to NTIA for review. Depending on the approval timing or potential requests for more information, this may have an impact on affected sites to be completed. Additionally, as some of the affected sites are in a "ring" topology that affect other "non-changed" sites, delays may have an impact on those sites as well. | TRUE
NT10BIX5570150 | 2012 | Q2 | Q2 - 2012 | The activities for this quarter included deployment of an additional 303 miles of off-net (new) and 1765 miles on-net (upgraded) fiber bringing the total deployed fiber for the project to 802 miles of off-net and 6644 miles of on-net fiber. Completed installations at 95 additional sites. This was less than originally planned due to delayed shipment of some site equipment components. A remediation plan was put into place to resolve the delay prior to the end of Q3-2012. Continued fiber deployment and optical span activation to core and edge sites as planned for this quarter. Continued site remediation and site survey tasks at edge sites as required. Submitted Route Modification request and supporting documentation for approval. Completed equipment ordering to meet planned deployment schedules. Conducted weekly project and status review meetings with all project teams and management stakeholders. Collect and assembled information surrounding key project metrics. Produce and file appropriate reports relative to the project and financial status with the necessary entities and stakeholder groups. | 802 | 0 | 6644 | 0 | 802 | 0 | 0 | 636 | Ahead of schedule | N/A | Ahead of schedule | N/A | Ahead of schedule | N/A | N/A | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. Additionally, an equipment delivery issue reduced the number of sites deployed this quarter. A remediation plan is in place to address this issue and will be resolved during Q3-2012. | 0 | 0 | 0 | None at this time. | None planned in this project. | N/A | 0 | 0 | 0 | 0 | Zero Variance | Zero Variance | Zero Variance | Zero Variance | 636 | 330 | 306 | 3 | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | The number of subscribers to receive improved access was originally estimated to be 342. The total number has been adjusted downward to reflect the actual number of subscribers. This downward change was due to subscribers choosing to utilize an alternate provider as well as location utilization requirements changing and no longer requiring connectivity. | 10 Mbps - 306 100 Mbps - 84 1000 Mbps - 246 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None planned at this time. | FALSE | N/A | Continued deployment of fiber miles. Anticipate approval of submitted Route Change Request. Continued receipt and deployment of equipment to planned sites. The project is anticipating deploying an additional 100 miles of off-net (new) and 400 miles of on-net (upgraded) fiber during this quarter as well as completing installations and connectivity at an additional 80 Community Anchor Institutions. No wholesale or last mile provider agreements are planned at this time. | Department of Administration Services Bureau of Enterprise Systems & Technology | Previous quarter impacts from delayed initial FONSI receipt, additional SAC requirements and delayed start of deployment activities continue to affect originally planned milestone projections. Additionally, coordination of site visits for installation and testing are taking longer than anticipated. It is anticipated that these schedule variances from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. Additionally, an equipment delivery issue affected the total number of sites completed this quarter. A remediation plan was put into place to address this and it will be fully mitigated during Q3-2012. | A Route Change Request has been submitted along with appropriate environmental assessment documentation to NTIA for review. Depending on the approval timing or potential requests for more information, this may have an impact on affected sites to be completed. Additionally, as some of the affected sites are in a "ring" topology that affect other "non-changed" sites, delays may have an impact on those sites as well. | TRUE
NT10BIX5570150 | 2012 | Q3 | Q3 - 2012 | The activities for this quarter included deployment of an additional 121 miles of off-net (new) and 623 miles on-net (upgraded) fiber bringing the total deployed fiber for the project to 923 miles of off-net and 7267 miles of on-net fiber. Completed installations at 109 additional sites. Continued fiber deployment and optical span activation to core and edge sites as planned for this quarter. Continued site remediation and site survey tasks at edge sites as required. Received approval for submitted Route Modification request. Completed equipment ordering to meet planned deployment schedules. Conducted weekly project and status review meetings with all project teams and management stakeholders. Collect and assembled information surrounding key project metrics. Produce and file appropriate reports relative to the project and financial status with the necessary entities and stakeholder groups. | 923 | 0 | 1987 | 0 | 923 | 0 | 0 | 745 | Ahead of schedule | N/A | Ahead of schedule | N/A | Ahead of schedule | N/A | N/A | Slightly ahead of schedule | 0 | 0 | 0 | None at this time. | None planned in this project at this time. | N/A | 0 | 0 | 0 | 0 | Zero Variance | Zero Variance | Zero Variance | Zero Variance | 745 | 439 | 306 | 3 | Slightly ahead of schedule | Slightly ahead of schedule | Zero Variance | 10 Mbps - 306 100 Mbps - 104 1000 Mbps - 335 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None planned at this time. | FALSE | N/A | Continued deployment of fiber miles. Continued receipt and deployment of equipment to planned sites. The project is anticipating deploying an additional 50 miles of off-net (new) and 300 miles of on-net (upgraded) fiber during this quarter as well as completing installations and connectivity at an additional 60 Community Anchor Institutions. No wholesale or last mile provider agreements are planned at this time. | Department of Administration Services Bureau of Enterprise Systems & Technology | Previous quarter impacts from delayed initial FONSI receipt, additional SAC requirements and delayed start of deployment activities continue to affect originally planned milestone projections. Additionally, a substantial Route Modification was approved late in the quarter. It is anticipated that these schedule variances from the baseline will be fully mitigated by the end of Q4-2012. Additionally, an equipment delivery issue that affected the total number of sites completed in the previous quarter was remediated. | The Route Change request was approved late in Q3-2012. As such, some sites that were originally planned to be completed have been delayed slightly. This may have a potential impact on sites to be completed during Q4-2012. Additionally, as the winter months approach, unexpected weather conditions may impact fiber deployment and sites completed. | TRUE
NT10BIX5570150 | 2012 | Q4 | Q4 - 2012 | The activities for this quarter included deployment of an additional 37 miles of off-net (new) and 98 miles on-net (upgraded) fiber bringing the total deployed fiber for the project to 960 route miles of off-net and 2085 route miles of on-net fiber. Completed installations at 97 additional sites. Continued fiber deployment and optical span activation to core and edge sites as planned for this quarter. Continued site remediation tasks at edge sites as required. Completed equipment ordering to meet planned deployment schedules. Conducted weekly project and status review meetings with all project teams and management stakeholders. Collect and assembled information surrounding key project metrics. Produce and file appropriate reports relative to the project and financial status with the necessary entities and stakeholder groups. | 960 | 0 | 2085 | 0 | 960 | 0 | 0 | 842 | Ahead of schedule | N/A | Ahead of schedule | N/A | Ahead of schedule | N/A | N/A | Slightly ahead of schedule | 0 | 0 | 0 | None at this time. | None planned in this project at this time. | N/A | 0 | 0 | 0 | 0 | Zero Variance | Zero Variance | Zero Variance | Zero Variance | 840 | 519 | 321 | 3 | Slightly ahead of schedule | Slightly ahead of schedule | Zero Variance | 10 Mbps - 304 100 Mbps - 111 1000 Mbps - 425 Note: Number of 10Mbps subscribers was reduced by 2 (306 to 304) from last reporting period after determining that those 2 locations did not fit the BTOP definition of a CAI. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None planned at this time | FALSE | N/A | Continued deployment of fiber miles. Continued receipt and deployment of equipment to planned sites. The project is anticipating deploying an additional 40 route miles of off-net (new) and 75 route miles of on-net (upgraded) fiber during this quarter as well as completing installations and connectivity at an additional 33 Community Anchor Institutions. No wholesale or last mile provider agreements are planned at this time. | Department of Administration Services Bureau of Enterprise Systems & Technology | Project continues to progress on schedule. No significant challenges or issues we encountered during this quarter. | With the winter months during this quarter, unexpected weather conditions may impact fiber deployment and sites completed. | TRUE
NT10BIX5570150 | 2013 | Q1 | Q1 - 2013 | The activities for this quarter included deployment of an additional 65 miles of off-net (new) and 110 miles on-net (upgraded) fiber bringing the total deployed fiber for the project to 1025 route miles of off-net and 2195 route miles of on-net fiber. Completed installations at 46 additional sites. Continued fiber deployment and optical span activation to core and edge sites as planned for this quarter. Continued site remediation tasks at edge sites as required. Completed equipment ordering to meet planned deployment schedules. Conducted weekly project and status review meetings with all project teams and management stakeholders. Collect and assembled information surrounding key project metrics. Produce and file appropriate reports relative to the project and financial status with the necessary entities and stakeholder groups. | 1025 | 0 | 2195 | 0 | 1025 | 0 | 0 | 888 | On schedule | N/A | On schedule | N/A | On schedule | N/A | N/A | On schedule | 0 | 0 | 0 | None at this time. | None planned in this project at this time. | N/A | 0 | 0 | 0 | 0 | Zero variance | Zero variance | Zero variance | Zero variance | 886 | 565 | 321 | 3 | On schedule | On schedule | Zero variance | 10 Mbps - 304 100 Mbps - 111 1000 Mbps - 471 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | It is currently anticipated that the project will finish deployment of all fiber miles required for the project during this quarter. As such, the project is anticipating deploying an additional 28 route miles of off-net (new) and 98 route miles of on-net (upgraded) fiber during this quarter which will bring the total deployed fiber route miles to 1053 off-net (new) and 2293 on-net (upgraded). The project is also anticipating completing installations and connectivity at an additional 49 Community Anchor Institutions, leaving only 5 sites remaining to be completed for the entire project. Our hope is that the 49 planned sites will proceed ahead of schedule, thereby allowing the remaining 5 sites to be completed during this quarter as well. No wholesale or last mile provider agreements are planned at this time. | Department of Administration Services Bureau of Enterprise Systems & Technology | Project continues to progress on schedule. No significant challenges or issues were encountered during this quarter. | None anticipated at this time. | TRUE
NT10BIX5570150 | 2013 | Q2 | Q2 - 2013 | The activities for this quarter included deployment of an additional 23 miles of off-net (new) and 32 miles on-net (upgraded) fiber bringing the total deployed fiber for the project to 1048 route miles of off-net and 2227 route miles of on-net fiber. Completed installations at 29 additional sites. Continued fiber deployment and optical span activation to core and edge sites as planned for this quarter. Continued site remediation tasks at edge sites as required. Completed equipment ordering to meet planned deployment schedules. Conducted weekly project and status review meetings with all project teams and management stakeholders. Collect and assembled information surrounding key project metrics. Produce and file appropriate reports relative to the project and financial status with the necessary entities and stakeholder groups. | 1048 | 0 | 2227 | 0 | 1048 | 0 | 0 | 917 | On Schedule | N/A | On Schedule | N/A | On Schedule | N/A | N/A | On Schedule | 0 | 0 | 0 | None at this time. | None planned in this project at this time. | N/A | 0 | 0 | 0 | 0 | Zero Variance | Zero Variance | Zero Variance | Zero Variance | 915 | 594 | 321 | 3 | Zero Variance | Zero Variance | Zero Variance | 10 Mbps - 304 100 Mbps - 111 1000 Mbps - 500 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | As August 31 marks our award end date, all activities related to this project will be completed as required. This will include completion of all fiber installation and strand activation. This will bring the total deployed fiber to 1053 route miles of off-net (new) and 2293 route miles of on-net (existing) for a combined total of 3346 route miles. Additionally, the completion of network deployment to remaining 25 sites will bring the total connected CAI's to 940. At this point, the network will be deemed fully "production ready". As allowed under the grant, we will continue to work on completion of required close-out documentation within the time frames allowed. | Department of Administration Services Bureau of Enterprise Systems & Technology | Project continues to proceed on schedule. Temporary site access delays reduced the projected number of completed sites for this quarter from 49 to 29. However, these delays have been addressed, are being corrected and the project does not see any issues that will prevent the remaining 25 sites to be completed within the grant period as planned. | None anticipated at this time. | TRUE
NT10BIX5570150 | 2013 | Q3 | Q3 - 2013 | The activities for this quarter included deployment of the final 5 miles of off-net (new) and 66 miles on-net (upgraded) fiber bringing the total deployed fiber for the project to 1053 route miles of off-net and 2293 route miles of on-net fiber for a combined total of 3346 route miles. Completed installations at final 25 sites. Completed final fiber deployment and optical span activation to core and edge sites as planned for this quarter. Completed site remediation and testing tasks at edge sites as required. Conducted weekly project and status review meetings with all project teams and management stakeholders. Collect and assembled information surrounding key project metrics. Produce and file appropriate reports relative to the project and financial status with the necessary entities and stakeholder groups. In summary, the completed project deployed 1053 route miles of off-net (new) fiber and 2293 route miles of on-net (upgraded) encompassing a total of 22,427 strand miles of fiber to many previously under or non-served areas throughout the entire state of Connecticut. This project allowed a total of 940 Community Anchor Institutions to be connected to a cohesive high speed fiber optic network and provides the base springboard for further expansion. Of these 940 locations, 619 previously did not have access to broadband speed network connections while 321 locations received upgraded connectivity, going from DSL or T-1 speeds to 100 Mbps or higher speeds. These new or increased connectivity speeds have enabled advanced services such as large file transfers or downloads, videoconferencing, distance learning, etc. to be utilized by the connected entities. Looking forward, expansion of the network is soon to be underway that includes connecting another 168 Municipal locations. Many of these locations will utilize the network to improve sharing of services and applications between the locations creating regional uses and shared resource opportunities. Additionally, we have received considerable interest from public and private entities for connectivity to the network for data transport and are reviewing these for technological feasibility and costs. In closing, many innovative applications and uses have been enabled by this network that would have been impossible or too expensive to implement otherwise. Interest in connectivity to the network remains high and we anticipate this to continue or increase going forward, especially once other "success stories" from connected entities become well known. | 1053 | 0 | 2293 | 0 | 1053 | 0 | 0 | 940 | Zero variance | N/A | Zero Variance | N/A | Zero variance | N/A | N/A | Zero variance | 0 | 0 | 0 | None at this time | None planned in this project at this time | N/A | 0 | 0 | 0 | 0 | Zero variance | Zero variance | Zero variance | Zero variance | 940 | 619 | 321 | 3 | Zero variance | Zero variance | Zero variance | 10 Mbps = 304 100 Mbps = 111 1000 Mbps = 525 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None planned at this time | FALSE | N/A | As the project is in close-out as of 8/31/13, no further activities other than Grant close-out documentation will occur. | Department of Administration Services Bureau of Enterprise Systems & Technology | None | None as the grant is now in close-out. | TRUE
NT10BIX5570153 | 2010 | Q4 | Q4 - 2010 | Ocean State Higher Education Economic Development and Administrative Network began the network design of the Beacon 2.0 Node and Community Anchor Institution sites. A bid was released for the 10Gbps Network Upgrade, the vendor was chosen and equipment ordered. A fiber RFP was issued and tentative awards granted. Several Beacon 2.0 contractors were selected as the result of a competitive bid. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Ocean State Higher Education Economic Development and Administrative Network will complete the network design of the Beacon 2.0 Node and Community Anchor Institution sites. Site Preparation for the 4 Massachusetts Nodes will commence. The 10Gbps Equipment ordered for the Network upgrade will be received, configured and installed. Several Beacon 2.0 contractors will be selected as the result of a competitive bid. | Ocean State Higher Education Economic Development Administrative Network | N/A | N/A | TRUE
NT10BIX5570153 | 2011 | Q1 | Q1 - 2011 | For the period, 1/1/2011- 3/31/2011, Ocean State Higher Education Economic Development Administrative Network completed the following. Network Design For the network design, Ocean State Higher Education Economic Development Administrative Network hired a Fiber Project Engineer and a Traffic Systems Management Contractor. The design for the four Massachusetts Optical Nodes, six Rhode Island Optical Nodes, and Community Anchor Institutions is complete. Site Preparation The site preparation for both the four Massachusetts Optical Nodes and six Rhode Island Optical Nodes has commenced. Equipment Procurement Ocean State Higher Education Economic Development Administrative Network received its 10G Backbone Upgrade Equipment. A Request for Proposal for Beacon 2.0 Optical Equipment was issued in March. Responses are due April 8, 2011. Network Build Ocean State Higher Education Economic Development Administrative Network hired a Field Project Engineer. An IRU was executed with Cox Communications in Rhode Island and Sidera Networks in Massachusetts. As part of the RFP process, a definitive project plan was determined to ensure that all milestones are met. Community Anchor Institution negotiations have commenced based on the schedule defined. Equipment Deployment The Cogent 10G Router Equipment, Level3 10G Router Equipment, and Safe Harbor 10G Router Equipment were all configured and installed. Community Outreach Ocean State Higher Education Economic Development Administrative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | Zero new network miles leased during this period | Zero existing network miles upgraded during this period | N/A | Zero miles of new fiber leased during this period | N/A | N/A | Zero new or upgraded interconnection points during this perion points during this period | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero subscribers served during this period | Zero subscribers received new access during this period | Zero subscribers received improved access during this period | No subscribers were served during this period | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | For the period, 4/1/2011- 6/30/2011, Ocean State Higher Education Economic Development Administrative Network is projected to complete the following. Network Design Review and finalize analysis of a Traffic Systems Management study to identify existing rights of way and conduit for public safety efforts across the state. Determine and document network changes required to accommodate the increased Community Anchor Institution connections. Site Preparation The site preparation for the Massachusetts node locations will be completed. Equipment Procurement Ocean State Higher Education Economic Development Administrative Network shall award a fiber vendor with the Beacon 2.0 Optical Equipment contract. Optical equipment needs will be finalized and the ordering of equipment will commence. Network Build Ocean State Higher Education Economic Development Administrative Network will continue contract negotiations with Community Anchor Institutions. The installation of backbone fiber and CAI laterals in Providence County, Rhode Island will commence. Community Outreach Ocean State Higher Education Economic Development Administrative Network community outreach efforts will include a Kick Off Event on May 9, 2011 and continued public presentations to local, regional, and national groups. | Ocean State Higher Education Economic Development Administrative Network | None. | None. | TRUE
NT10BIX5570153 | 2011 | Q2 | Q2 - 2011 | Network Design The Networks design for Beacon 2.0 is complete, save any change orders that may be required for minimal alterations to proposed Community Anchor Institution laterals, and minor backbone route adjustments. Site Preparation Ocean State Higher Education Economic Development Administrative Network hired Bridgewater Communications to perform the site prep work required for two of the Massachusetts Optical node locations. The site preparation work at the third Massachusetts node location is complete, and only a single cross-connect is required at the fourth site. In Rhode Island, site preparations for two Optical node locations are complete, and orders have been placed for the work required at the remaining four sites. Equipment Procurement On April 29, 2011, Ocean State Higher Education Economic Development Administrative Network issued a notice of tentative award to Atrion Networking Corporation for the procurement of CISCO 10G optical equipment. The network engineers and technicians from both OSHEAN and Atrion dedicated May and June to designing the network and defining the exact equipment list required to light the network and connect the Community Anchor Institutions. The Bill of Materials was finalized at the end of June, 2011. Equipment orders will commence in July, 2011. Network Build In Rhode Island, forty (40) miles of backbone fiber have been installed by Cox Communications. In Massachusetts, all required applications have been submitted by Sid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | Zero new network miles leased during this period | Zero existing network miles upgraded during this period | N/A | Zero miles of new fiber leased during this period | N/A | N/A | Zero new or upgraded interconnection points during this perion points during this period | 0 | 0 | 0 | N/A | N/A3 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero subscribers served during this period | Zero subscribers received new access during this period | Zero subscribers received improved access during this period | No subscribers were served during this period | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Network Design Networks design for Beacon 2.0 will be completed, save any change orders that may be required for minimal alterations to proposed Community Anchor Institution laterals, and minor backbone route adjustments. Site Preparation All Optical Node site preparation is slated for completion. Equipment Procurement On April 29, 2011, Ocean State Higher Education Economic Development Administrative Network issued a notice of tentative award to Atrion Networking Corporation for the procurement of CISCO 10G optical equipment. The network engineers and technicians from both OSHEAN and Atrion dedicated May and June to designing the network and defining the exact equipment list required to light the network and connect the Community Anchor Institutions. The Bill of Materials was finalized at the end of June, 2011. Equipment orders will commence in July, 2011. Network Build In Rhode Island, one hundred (100) miles of backbone fiber will be installed by Cox Communications. Cox Communications will also begin the lateral installations for Community Anchor Institutions. In Massachusetts, all required applications have been submitted by Sidera Networks will perform the necessary walk-outs at Community Anchor Institution sites and follow-up on applications and permits that have been submitted for fiber installation. Community Anchor Institution site visits will continue in both states. Other In August, the OMB Circular A-133 audit will commence, with completion scheduled f | Ocean State Higher Education Economic Development Administrative Network | None. | None. | TRUE
NT10BIX5570153 | 2011 | Q3 | Q3 - 2011 | Network Design The network design for Beacon 2.0 is complete, save any change orders that may be required for minimal alterations to proposed Community Anchor Institution laterals, and minor backbone route adjustments. Site Preparation Site preparation at the four Massachusetts Optical node locations is complete. In Rhode Island, site preparations for four Optical node locations are complete; rack orders were placed for the two remaining sites. Delivery and installation of the racks is expected in 2011 Q4, at which time all site preparation efforts will be complete. Equipment Procurement Ocean State Higher Education Economic Development and Administrative Network (OSHEAN) executed its optical equipment contract with Atrion Networking Corporation. On July 29, a $3.4M order was placed for Optical node equipment; $2.2M of the order was received and verified in late September, 2011; the remaining $1.2M of equipment will be received in 2011 Q4. Network Build In Rhode Island, one hundred fifty eight (158) miles of backbone fiber have been installed by Cox Communications. The fiber for fifteen (15) Community Anchor Institution (CAI) laterals has been installed. Grounding and testing of the CAI laterals is scheduled for 2011 Q4. OSHEAN does not recognize fiber miles and laterals as complete until the 158 miles of fiber and 15 CAI laterals are tested, test results are approved by OSHEAN, and the fiber is handed off by Cox. In Massachusetts, all required applications have be | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | Zero new network miles leased during this period | Zero existing network miles upgraded during this period | N/A | Zero miles of new fiber leased during this period | N/A | N/A | Zero new or upgraded interconnection points during this perion points during this period | 0 | 0 | 0 | N/A | N/A3 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/a | 0 | 0 | 0 | 0 | Zero subscribers served during this period | Zero subscribers received new access during this period | Zero subscribers received improved access during this period | Zero new subscribers served during this period | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Network Design The network design for Beacon 2.0 will be complete, save any change orders that may be required for minimal alterations to proposed Community Anchor Institution laterals, and minor backbone route adjustments. Site Preparation Site preparation efforts are scheduled to be 100% complete. Equipment Procurement Ocean State Higher Education Economic Development and Administrative Network expects to order its Phase II optical equipment which shall include Cisco CPT 50 technology for CAI lateral connections. Network Build In Rhode Island, approximately two hundred (200) miles of backbone fiber are expected to be deployed by Cox Communications. The fiber for forty (40) Community Anchor Institution (CAI) laterals are scheduled for deployment. Testing of the Providence County IRU fiber is scheduled for testing. In Massachusetts, all required applications have been submitted by Sidera Networks, and walk-outs have commenced. Community Anchor Institution site visits continue in both states. | Ocean State Higher Education Economic Development Administrative Network | None | None. | TRUE
NT10BIX5570153 | 2011 | Q4 | Q4 - 2011 | Network Design The network design for Beacon 2.0 is complete, save any change orders that may be required for minimal alterations to proposed Community Anchor Institution (CAIs) laterals, and minor backbone route adjustments. Site Preparation Site preparation at the four Massachusetts Optical node locations is complete. In Rhode Island, site preparation for five Optical node locations are complete; a power distribution unit was ordered for the final node location. Delivery and installation of the power distribution unit is expected in 2012 Q1, at which time all site preparation efforts will be complete. Equipment Procurement Ocean State Higher Education Economic Development and Administrative Network executed its optical equipment contract with Atrion Networking Corporation. During the quarter, OSHEAN received the DWDM optical equipment required for its optical nodes. In November, a second equipment order as placed for the CPT50 optical gear required for CAI connectivity. As of the close of the quarter, approximately fifty (50) percent of the CPT50 optical equipment was received. Network Build In Rhode Island, two hundred forty six (246) miles of backbone fiber have been installed by Cox Communications. In Providence County, one hundred seventy four (174) miles of the 246 miles were tested and accepted by OSHEAN. The remaining seventy two (72) miles were installed in Kent County. These miles of fiber are expected to be tested and turned over to OSHEAN in 2012 Q1. The fiber for thirty (38) Community Anchor Institution (CAI) laterals has been installed. OSHEAN has tested and accepted the fiber for two (2) of those CAIs. Grounding and testing of the remaining thirty six (36) CAI laterals is scheduled for 2012 Q3. In Massachusetts, Sidera Networks completed the licensing and make-ready work required for the fiber installation. Community Anchor Institution site visits continue in both states. | 0 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | Priority has been placed on leased (IRU) fiber deployment. In Providence County, RI, 174 miles were tested and accepted by OSHEAN. | Zero existing network miles upgraded during this period due to a minimal delay in optical equipment delivery. This has no impact on major milestones required by the grant. | N/A | Zero miles of new fiber during this period. Priority has been placed on leased (IRU) fiber deployment. | N/A | N/A | Zero new or upgraded interconnection points during this period due to a minimal delay in optical equipment delivery. This has no impact on major milestones required by the grant. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 2 | 0 | 2 | 2 | Subscriber connections are ahead of the baseline schedule because Rhode Island fiber deployment is ahead of schedule. | Zero subscribers received new access during this period | Subscriber connections are ahead of the baseline schedule because Rhode Island fiber deployment is ahead of schedule. | Subscribers will have access to 1GigE and 10GigE speed tiers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None. | FALSE | N/A | Network Design The network design for Beacon 2.0 will be complete, save any change orders that may be required for minimal alterations to proposed Community Anchor Institution laterals, and minor backbone route adjustments. Site Preparation Site preparation efforts are scheduled to be 100% complete. Equipment Procurement Ocean State Higher Education Economic Development and Administrative Network (OSHEAN) expects to complete all equipment procurement efforts. Network Build In Rhode Island, seventy two (72) miles of Kent County backbone fiber are expected to be tested and accepted by OSHEAN. Cox is scheduled to begin the Washington County fiber installation. The connections for fifteen (15) Community Anchor Institution (CAI) laterals are scheduled. Testing of the Providence County IRU fiber is scheduled for testing. In Massachusetts, Sidera is expected to being pulling fiber in Plymouth and Bristol counties. Equipment Deployment. OSHEAN expects to deploy the Cisco 15454 optical equipment at its node locations. | Ocean State Higher Education Economic Development Administrative Network | None | None. | TRUE
NT10BIX5570153 | 2012 | Q1 | Q1 - 2012 | Network Design The network design for Beacon 2.0 is complete, save any change orders that may be required for minimal alterations to proposed Community Anchor Institution (CAIs) laterals, and minor backbone route adjustments. Site Preparation All site preparation is complete except for some additional splice and fiber testing required at two of the MA node locations. Equipment Procurement During the quarter, OSHEAN received all of the CPT50 equipment required to light the CAI sites. Equipment Installation The Optical Nodes for Providence (AP3) and Cambridge have been deployed. Network Installation In Rhode Island, three hundred twenty (320) miles of backbone fiber have been installed by Cox Communications. In Kent County, seventy two (72) miles of the 320 miles were tested and accepted by OSHEAN. Sixty five (65) miles were installed in Washington County and nine (9) miles were installed in Newport County. The fiber for twenty five (25) Community Anchor Institution (CAI) laterals has been installed. In Massachusetts, Sidera Networks has completed the licensing and make-ready work required for the fiber installation. Community Anchor Institution site visits continue in both states. | 0 | 246 | 0 | 0 | 0 | 0 | 0 | 2 | N/A | In Providence County and Kent County, RI, 246 miles were tested and accepted. | The equipment delay delayed the lighting of the existing network miles; these miles will be upgraded during 2012 Q2. | N/A | Zero new miles of fiber during this period. | N/A | N/A | Equipment was installed to upgrade two Beacon 2.0 interconnection points | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 3 | 0 | 3 | 3 | While OSHEAN has accepted three Community Anchor Institution laterals from Cox Communications as of 3/31/12, the backbone fiber was not lit during the period. Therefore, the three subscribers cannot yet be served. | Zero subscribers received new access during this period | While OSHEAN accepted two Community Anchor Institution laterals from Cox Communications during 2012 Q1, the backbone fiber was not lit during the period. Therefore, the three subscribers cannot yet receive improved access. | Subscribers will have access to 1GigE and 10GigE speed tiers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None | FALSE | N/A | Network Design The network design for Beacon 2.0 is complete. Site Preparation Site preparation efforts are scheduled to be 100% complete. Equipment Procurement Ocean State Higher Education Economic Development and Administrative Network (OSHEAN) expects to complete all equipment procurement efforts. Network Installation In Rhode Island, Cox is scheduled to complete the backbone fiber installation in Washington County, and continue backbone fiber installation in Newport County. Cox is also scheduled to begin backbone fiber installation in Bristol (RI) County. three hundred seventy (370) miles of backbone fiber are expected to be constructed in total. The connections for twenty(20) additional Community Anchor Institution (CAI) laterals are scheduled, which will result in a cumulative total of forty five (45). Sidera is expected to being pulling fiber in Plymouth County and Bristol County in Massachusetts. OSHEAN expects to "light" the Providence County and Kent County backbone fiber in May and light its first CAI by the close of June. Equipment Deployment. OSHEAN expects to deploy the Cisco 15454 optical equipment at its node locations, and begin deployment of the CAI CPT50 equipment. | Ocean State Higher Education Economic Development Administrative Network | Delays with the delivery of equipment were experienced primarily because the Cisco equipment selected for the CAI sites (CPT50 equipment) was brand new. Cisco lagged on some of the deliverable dates promised because the brand new technology for the CPT50 equipment was not ready. These delays will not impact the project as a whole. In Massachusetts, Sidera Networks has also experienced delays in gaining the rights to several poles required for the backbone fiber installation. Sidera is in the process of resolving these issues with the pole owners. | OSHEAN anticipates a firm resolution to the Cisco CPT50 equipment delay. Sidera Networks expects to have gained the pole rights by the close of the quarter. No significant challenges are foreseen. | TRUE
NT10BIX5570153 | 2012 | Q2 | Q2 - 2012 | Network Installation Recognition of network miles is pending a project modification request. Fifteen Community Anchor Institution (CAI) laterals were installed. OSHEAN lit its Providence County and Kent County sub-ring, and began providing service to its first CAI in June. Equipment Deployment. OSHEAN deployed Cisco 15454 optical equipment at the majority of its optical node sites. The installation of CPT50 at CAI sites commenced. | 0 | 246 | 401 | 0 | 0 | 0 | 0 | 6 | N/A | In Providence and Kent County, RI, 246 miles were tested and approved. Additional new network miles leased are subject to a modification request pending. | Baseline = 522 miles. 401 miles have been upgraded. 36 lateral miles and 85 backbone miles have not been upgraded due to a minor delay at two optical node locations. This delay will not affect the overall project time line. | N/A | Zero new miles of fiber during this period. | N/A | N/A | Equipment was installed to upgrade six Beacon 2.0 interconnection points | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 18 | 12 | 6 | 18 | While OSHEAN has accepted eighteen Community Anchor Institution laterals from Cox Communications as of 6/30/12, only two subscribers were being served as of 6/30/12 | While OSHEAN accepted twelve Community Anchor Institution laterals from Cox Communications during 2012 Q2, no subscribers have received new access. | While OSHEAN accepted three Community Anchor Institution laterals from Cox Communications during 2012 Q2, only two subscriber have received improved access. | 1Gbps (7 subscribers) and 10Gbps (11 subscribers) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None. | FALSE | N/A | Network Installation Recognition of network miles is pending a project modification request. A minimum of twenty CAI laterals are expected to be installed. OSHEAN will continue to connect CAIs at 1Gbps and 10Gbps speeds. Equipment Deployment. OSHEAN will complete the deployment of Cisco 15454 optical equipment at its optical node sites. The installation of CPT50 at CAI sites will continue. | Ocean State Higher Education Economic Development Administrative Network | Delays with the delivery of equipment were experienced primarily because the Cisco equipment selected for the CAI sites (CPT50 equipment) was brand new. Cisco lagged on some of the deliverable dates promised because the technology to support the CPT50 equipment at 1Gbps and 10Gbps levels was not ready. These delays are not projected to impact the project as a whole. In Massachusetts, Sidera Networks has also experienced delays in gaining the rights to several poles required for the backbone fiber installation. Sidera has made great progress during the quarter and expects to begin backbone installation during 2012 Q3. | Resolution with Cisco and the CPT50 equipment is anticipated. | TRUE
NT10BIX5570153 | 2012 | Q3 | Q3 - 2012 | Fiber Cox Communications has completed the installation of backbone fiber in the following counties: Providence, Kent, Washington, and Bristol. Cox has completed the majority of backbone fiber deployment in Newport County. Total fiber miles deployed = 410. Sidera is continuing its licensing and make ready efforts in Massachusetts. As of 9/30/12, sixty (60) Community Anchor Institution (â€œCAIâ€) laterals had been installed. Equipment As of August 23, 2012, the optical node equipment in Providence, Kent, Washington, Newport and Bristol Counties was fully deployed, and the Rhode Island Beacon 2.0 fiber network was lit. CPT50 equipment continues to be deployed at CAI locations. As of 9/30/12, sixteen (16) CAIs were â€œlitâ€ and receiving service. | 0 | 410 | 401 | 0 | 811 | 0 | 0 | 8 | N/A | Baseline = 275. Increase in mileage due to backbone deployment being ahead of schedule and total baseline/lateral miles increasing per a post award modification. | Baseline = 522. Total miles contingent on pending post award modification. | N/A | Baseline = 749. Number of miles of new fiber are ahead of baseline schedule. | N/A | N/A | Baseline = 10. The final two interconnection points required additional site prep. The two sites are expected to be upgraded prior to 12/31/2012. | 0 | 0 | 0 | N/A | N/A | OSHEAN contracts to Atrion (Contractor) for Network Operations and call center support which includes support on all equipment (i.e. Optical, MPLS Switches, Routers). Atrion 125 Metro Center Warwick, RI 02886 Contact: John Pyle Email: jpyle@atrion.net Phone: 401-736-6400 Cox Communications is a contractor of OSHEAN and provides support the the fiber optic cable. Cox is contracted to respond and repair any physical fiber issues. CoxCom INC 9 James P Murphy Hwy West Warwick, RI Contact: Marc Lataille Email: marc.lataille@cox.com Phone: 401-615-1425 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 60 | 50 | 10 | 60 | While OSHEAN accepted 60 CAI laterals as of 9/30/12, only 16 subscribers were being served as of 9/30/12. | 11 of the 50 subscribers were receiving lit service as of 9/30/12. | 6 of the 10 subscribers were receiving lit service as of 9/30/12. Total subscribers are slightly below the 13 projected in the baseline because of a shift in the subscriber lateral installation schedule, which increased the number of "subscribers receiving new access" for the period. This will have no impact on the overall project schedule. | >1Gbps (27 subscribers) 1Gbps (16 subscribers), 10Gbps (17 subscribers) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None. | FALSE | N/A | Fiber Recognition of additional networks miles is pending a project modification request. OSHEAN projects the installation of fiber laterals at five (5) additional CAI sites. Equipment OSHEAN expects to complete the deployment of Cisco 15454 equipment at its remaining optical node sites. The installation of CPT50 equipment will continue at CAI sites. Nine (9) additional CAIs are projected to receive â€œlitâ€ service. | Ocean State Higher Education Economic Development Administrative Network | None. OSHEAN has resolved with Cisco the issue it held with CPT50 equipment. | None anticipated. | TRUE
NT10BIX5570153 | 2012 | Q4 | Q4 - 2012 | Fiber Cox Communications has completed the installation of backbone fiber in Rhode Island. Sidera is continuing its licensing and make ready efforts in Massachusetts. Two (2) Community Anchor Institution (â€œCAIâ€) laterals were installed this quarter, bringing the total to sixty-two (62). Equipment CPT50 equipment continues to be deployed at CAI locations. | 0 | 359 | 401 | 0 | 760 | 0 | 0 | 8 | N/A | Variance due to an approved route modification. 410 network miles were incorrectly reported on the 9/30/2012 PPR. 359 network miles is correct for the 12/31/2012 reporting period. | Variance due to an approved route modification | N/A | Variance due to an approved route modification. Because new network miles leased were incorrectly reported on the 9/30/2012 PPR, the number of miles of new fiber was also incorrectly reported. 760 miles of new fiber is correct for the 12/31/2012 reporting period. | N/A | N/A | Baseline = 10. The two remaining interconnection points required additional site prep. The two sites are expected to be upgraded in January, 2013. As part of a post award modification, four additional points of interconnection will be added. | 0 | 0 | 0 | N/A | N/A | OSHEAN contracts to Atrion (Contractor) for Network Operations and call center support which includes support on all equipment (i.e. Optical, MPLS Switches, Routers). Atrion 125 Metro Center Warwick, RI 02886 Contact: John Pyle Email: jpyle@atrion.net Phone: 401-736-6400 Cox Communications is a contractor of OSHEAN and provides support the the fiber optic cable. Cox is contracted to respond and repair any physical fiber issues. CoxCom INC 9 James P Murphy Hwy West Warwick, RI Contact: Marc Lataille Email: marc.lataille@cox.com Phone: 401-615-1425 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 62 | 51 | 11 | 62 | Greater than baseline due to an increase in project CAIs via a project modification | 14 of the 51 subscribers were receiving lit service as of 12/31/12. Greater than baseline due to an increase in project CAIs via a project modification | 9 of the 11 subscribers were receiving lit service as of 12/31/12. Total subscribers are slightly below the baseline projection ibecause of a shift in the subscriber lateral installation schedule, which increased the number of "subscribers receiving new access" for the period. This will have no impact on the overall project schedule. | 1Gbps (44 subscribers); 10Gbps (18 subscribers) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None. | FALSE | N/A | Fiber Sidera Networks is projected to complete at least 75% of the installation of backbone fiber in Massachusetts. OSHEAN also expects to execute an IRU with Taunton Municipal Light Plant and and IRU with Lightower Fiber Networks. The installation of fiber laterals to twenty three (23) CAIs is anticipated for the quarter. Projected backbone miles total 55. Equipment OSHEAN expects to complete the deployment of Cisco 15454 equipment at its remaining optical node sites. The installation of CPT50 equipment will continue at CAI sites. | Ocean State Higher Education Economic Development Administrative Network | No specific challenges were faced during the quarter. | None anticipated. | TRUE
NT10BIX5570153 | 2013 | Q1 | Q1 - 2013 | Fiber Sidera Networks completed 75% of the fiber miles for the Massachusetts portion of the project. Cox Communications completed laterals to (5) Community Anchor Institutions (CAIs) this quarter, bringing the total to sixty-six (66). A total of 19 new leased miles in MA and 18 new leased miles in RI were completed this quarter, bringing the overall total of leased miles for the project to 396. Equipment CPT50 equipment continues to be deployed at CAI locations. | 0 | 396 | 401 | 0 | 0 | 0 | 0 | 10 | N/A | Variance from baseline due to approved route modifications from recent post award modification. | Variance from baseline due to approved route modifications from recent post award modification. | N/A | N/A | N/A | N/A | Approved route modifications from recent post award modification will result in a total number of new and/or upgraded interconnection points of 14. | 0 | 0 | 0 | N/A | N/A | OSHEAN contracts to Atrion (Contractor) for Network Operations and call center support which includes support on all equipment (i.e. Optical, MPLS Switches, Routers). Atrion 125 Metro Center Warwick, RI 02886 Contact: John Pyle Email: jpyle@atrion.net Phone: 401-736-6400 Cox Communications is a contractor of OSHEAN and provides support the the fiber optic cable. Cox is contracted to respond and repair any physical fiber issues. CoxCom INC 9 James P Murphy Hwy West Warwick, RI Contact: Marc Lataille Email: marc.lataille@cox.com Phone: 401-615-1425 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 66 | 52 | 14 | 66 | Number consistent with recently approved post award modification. Note: There was an error in a previous report on the total subscribers served, resulting in one too many subscribers being listed previously. (The CAI for 2000 Post Rd, Warwick for the RI Divsion of IT, one of a number of DoIT sites on the project, was inadvertently reported as complete on the 9/30/12 PPR.) With the addition of 5 CAIs this quarter, the correct total is 66. | 36 of the 52 subscribers were receiving lit service as of 3/31/13. Consistent with recently approved post award modification. | 14 of the 14 subscribers were receiving lit service as of 3/31/13. | 1 Gbps (48 subscribers); 10Gbps (18 subscribers) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None. | FALSE | N/A | Fiber Sidera Networks is projected to complete the 6 remaining fiber miles in Massachusetts. TMLP is projected to complete 100% of its 4 fiber miles in Massachusetts. Cox Communications is projected complete 9.5 miles next quarter, representing the majority of the outstanding laterals to CAIs in Rhode Island based on the post award project modification. OSHEAN expect to complete execution of the IRU with Lightower to provide 46 fiber miles. Total fiber miles planned to be deployed next quarter: 65.5 miles CAIs An additional 32 CAIs are planned to be connected via laterals next quarter, for a total of 98 for the project to date. Equipment OSHEAN will continue with the installation of CPT50 equipment at the CAI sites. Equipment is planned to be installed at 44 additional CAI locations next quarter. | Ocean State Higher Education Economic Development Administrative Network | No specific challenges were faced during the quarter. | Legal reviews and final signatures on Lightower and TMLP IRUs have taken longer than anticipated and delay the delivery of the associated leased fiber miles. We are working to speed up this process so as not to negatively impact the overall project schedule. Also, because of number of new CAI laterals added to the project that were held until formal acceptance of the post award budget modification, the construction of the final laterals in Rhode Island is occurring later in the schedule than previously anticipated. We are working with our vendor to ensure completion of the work in time to perform the equipment installation before the project award deadline. | TRUE
NT10BIX5570153 | 2013 | Q2 | Q2 - 2013 | Fiber Sidera Networks completed the remaining 6 fiber miles for the Massachusetts portion of the project, bringing the Sidera portion of the project to 100% completion, totalling 25 miles of 24-strand fiber. The IRU agreement with Taunton Municipal Lighting Plant was completed in June and the construction of the 4 new miles of fiber included in the agreement is in progress. Cox Communications completed laterals to thirty-one (31) CAIs this quarter, bringing the total to ninety-seven (97). A total of 8 new leased miles in MA and 8 new leased miles in RI were completed this quarter, bringing the overall total of leased miles to 412 out of 478.5. Equipment CPT equipment continues to be deployed at CAI locations. Thirty-one (31) CPT installations were completed this quarter at CAI locations. | 0 | 412 | 401 | 0 | 0 | 0 | 0 | 12 | N/A | Variance from baseline due to approved route modifications from recent post award modification. After route modification, the new total for network miles leased is 478.5. | Variance from baseline due to approved route modifications from recent post award modification. After route modification, the new total for existing miles upgrades is 432. | N/A | N/A | N/A | N/A | 12 of the 14 total interconnection points have been completed. Two interconnection points (at Stonehill and Wheaton) were completed this quarter. | 0 | 0 | 0 | N/A | N/A | OSHEAN contracts to Atrion (Contractor) for Network Operations and call center support which includes support on all equipment (i.e. Optical, MPLS Switches, Routers). Atrion 125 Metro Center Warwick, RI 02886 Contact: John Pyle Email: jpyle@atrion.net Phone: 401-736-6400 Cox Communications is a contractor of OSHEAN and provides support the the fiber optic cable. Cox is contracted to respond and repair any physical fiber issues. CoxCom INC 9 James P Murphy Hwy West Warwick, RI Contact: Marc Lataille | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 97 | 78 | 19 | 97 | Variance from baseline due to approved post award modification to increase the total number of CAis. After the modification the total number of approved CAIs is 124. | 62 of the 78 subscribers were receiving lit service as of 6/30/13. 26 of the 78 subscribers receiving new access were installed in Q2 2013. | 19 of the 19 subscribers were receiving lit service as of 6/30/13. 5 of the 19 subscribers receiving improved access were installed in Q2 2013. | 1 Gbps (71 subscribers); 10Gbps (26 subscribers) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None. | FALSE | N/A | Next quarter will mark the completion of our BTOP project. The fiber in MA under the TMLP and Lightower IRUs will be fully constructed / deployed, and the remaining RI laterals being constructed by Cox will be completed. The remainder of the CPT equipment will be installed at CAI locations. All remaining project installation and technical documentation activities will be completed by August 31st, and closeout documentation will be underway. We anticipate submitting a rebudget in Q3 2013 to shift funds between categories as to bring the percentages in line with the baseline for the final project as indicated below. | Ocean State Higher Education Economic Development Administrative Network | Finalizing the legal language on outstanding IRUs with Lightower and TMLP presented a challenge this quarter, as work on installing or provisioning the resulting fiber was delayed until contracts could be signed. These have been resolved and the vendors will be able to catch up on the project schedule. Also, as we near the end of the project, ensuring the laterals will be completed by the vendors on time are requiring additional efforts. We expect this to be resolved. | Challenges for next quarter will be completing all the remaining activities that remain to be done prior to the 8/31/13 project end, and initiating the closeout documentation. We will need to ensure all lateral work is completed with sufficient time to be able to install the associated network equipment. A budget modification is in progress to categorize unexpected program revenue and adjust the budget categories to be closer to the expected totals. The process to document any CAI sites that cannot be completed (due to issues with physical cable access, building moves, or change in CAI plans for broadband service from start of project) will need to be addressed. | TRUE
NT10BIX5570153 | 2013 | Q3 | Q3 - 2013 | All remaining fiber and network equipment included in the scope of the project was completed. Fiber Taunton Municipal Lighting Plant completed construction of the 4 new miles of fiber and splicing of 32 existing miles of fiber provided to OSHEAN under the previously signed IRU agreement. Cox Communications completed laterals to thirteen (13) CAIs in the final quarter, bringing the total to one hundred ten (110). A total of 36 new leased miles in MA and 26.8 new miles in RI were completed this quarter, bringing the final overall total of leased miles to 474.8. Equipment All remaining network equipment was deployed this quarter. Twenty-nine (29) CPT equipment installations were completed at CAI locations, bringing the final total to 110. | 0 | 475 | 432 | 0 | 0 | 0 | 0 | 14 | N/A | Final new miles leased: 474.8 based on approval of August memo to remove several CAIs for which laterals could not be completed. | After final approved route modification, the new total for existing miles upgraded is 432. | N/A | N/A | N/A | N/A | 14 of the 14 total interconnection points have been completed. Two interconnection points (at the TMLP POP in Taunton, MA and the OpenCape interconnection in Bridgewater, MA) were completed this quarter. | 0 | 0 | 0 | OSHEAN has no current signed agreements with wholesale and last mile providers. | OSHEAN makes available leased dark to wholesale providers, but at present no providers have requested formal pricing for the wholesale leased fiber service. The service is based on a per mile-per fiber lease rate across our available fiber capacity, and we are at present finalizing the rate to ensure it is competitive with comparable dark fiber lease rates in the region. OSHEAN stands prepared to provide pricing and availability on a timely basis to any wholesalers who inquire about our service. | OSHEAN contracts to Atrion (Contractor) for Network Operations and call center support which includes support on all equipment (i.e. Optical, MPLS Switches, Routers). Atrion 125 Metro Center Warwick, RI 02886 Contact: John Pyle Email: jpyle@atrion.net Phone: 401-736-6400 Cox Communications is a contractor of OSHEAN and provides support the the fiber optic cable. Cox is contracted to respond and repair any physical fiber issues. CoxCom INC 9 James P Murphy Hwy West Warwick, RI Contact: Marc Lataille | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 110 | 91 | 19 | 110 | Variance from post award modification total due to approved request to remove some CAIs for which connections were not able to be built due to physical or timing issues, or because of change in need by the CAIs. After this request, the final total of CAIs is 110. | 25 of the 91 subscribers receiving new access had service installed in Q3 2013. | None of the 19 subscribers receiving improved access were installed this quarter. | 1 Gbps (84 subscribers); 10Gbps (26 subscribers) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None. | FALSE | N/A | All final closeout documentation will be completed and submitted during the next quarter. | Ocean State Higher Education Economic Development Administrative Network | The challenges for the past quarter consisted primarily of getting the final fiber laterals completed and tested, and obtaining and installing the final equipment prior to the project end date. In addition, getting the final vendor invoices reviewed and in process in order to complete reporting and begin the closeout in a timely manner proved to be a challenge. Notes on current quarter budget details: 1. Certain past expenses reported in the Administrative and Legal category were recategorized as Architectural/Engineering to more accurately reflect the nature of the expenditures. This resulted in the Federal Funds total for Q3-2013 being slightly lower than the same figure reported in Q2-2012, with that reduction being added to the Architectural/Engineering category. 2. In re-examining a past expense reported in the Site Work category, an adjustment reducing the Federal Funds total was made to accurately reflect the correct amount. This reduced in the total Federal Funds for Q3-2013 being slightly lower than the same figure reported in Q2-2012. | Challenges next quarter will be to complete all of the project closeout documentation correctly and in a timely manner. | TRUE
NT10BIX5570156 | 2010 | Q4 | Q4 - 2010 | In the fourth quarter of 2010, one of the top priorities was to complete the Grantee Substitution request from the Centennial Board of Cooperative Educational Services (CBOCES) to the new entity, EAGLE-Net Alliance (EAGLE-Net). In order to make this transition as smooth as possible, no funds were spent and no federal funds were requested by the CBOCES for this grant in the fourth quarter. In our communications with the NTIA, it has been indicated to us and we expect the Grantee Substitution request to be fully completed in January 2011. At that time, as EAGLE-Net, we will begin to spend the necessary funds and fully expect to catch up to our budgeted completion estimates in the first quarter of 2011. As soon as the request has been approved, we have a core staff ready to be hired by EAGLE-Net as well as our business and operational support systems ready to be implemented, we have our Environmental Consultant selected and they are awaiting our word to begin work, and we have our Project Management/Network Design Team selected and ready to begin work. Although the above paragraphs might not sound like "accomplishments", the three important positives are that the Grantee Substitution is almost complete, we refrained from spending money under the CBOCES name to make the process easier and more clear-cut to follow the grant expenditures, and we laid the groundwork for the EAGLE-Net organization to begin and are ready to go with our Environmental and Network Design consultan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Due to the previously described delays in the Network Design, no new network miles were deployed. Therefore, we are behind our baseline target of 117 new deployed miles. | Due to the previously described delays in the Network Design, no new network miles were leased. Therefore, we are behind our baseline target of 148 new leased miles. | Due to the previously described delays in the Network Design, no new network miles were upgraded. Therefore, we are behind our baseline target of 19 upgraded miles. | n/a Consistent with the baseline report. | Due to the previously described delays in the Network Design, no new fiber miles were deployed. Therefore, we are behind our baseline target of 102 fiber miles. | Due to the previously described delays in the Network Design, no new wireless links were installed. Therefore, we are behind our baseline target of 9 new wireless links. | Due to the previously described delays in the Network Design, no new towers were constructed. Therefore, we are behind our baseline target of 10 new towers. | Due to the previously described delays in the Network Design, no new fiber miles were deployed. Therefore, we are behind our baseline target of 102 fiber miles. Due to the previously described delays in the Network Design, no new wireless links were installed. Therefore, we are behind our baseline target of 9 new wireless links. Due to the previously described delays in the Network Design, no new towers were constructed. Therefore, we are behind our baseline target of 10 new towers. Due to the previously described delays in the Network Design, no new or upgraded interconnection points were completed. Therefore, we are behind our baseline target of 11 new interconnection pointsd delays in the Network Design, no new fiber miles were deployed. Therefore, we are behind our baseline target of 102 fiber miles. Due to the previously described delays in the Network Design, no new wireless links were installed. Therefore, we are behind our baseline target of 9 new wireless links. Due to the previously described delays in the Network Design, no new towers were constructed. Therefore, we are behind our baseline target of 10 new towers. Due to the previously described delays in the Network Design, no new or upgraded interconnection points were completed. Therefore, we are behind our baseline target of 11 new interconnection points. | 0 | 0 | 0 | n/a There are no agreements signed through the fourth quarter, which is consistent with our baseline target. | n/a As no build has yet been completed, no services were being provided by this project in the fourth quarter. Therefore, there is no pricing list attachment, no services were being provided by this project in the fourth quarter. Therefore, there is no pricing list attachment. | n/a No build has yet been completed so there is no network operation. | 0 | 0 | 0 | 0 | Consistent with the baseline target. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a No operating network so no speed tiers. | 0 | 0 | 0 | 0 | Due to the previously described delays in the Network Design, no subscribers were being served in the fourth quarter. Therefore, we are behind our baseline target of 259 subscribers. | Due to the previously described delays in the Network Design, there were no subscribers receiving new access in the fourth quarter. Therefore, we are behind our baseline target of 54 subscribers receiving new access. | Due to the previously described delays in the Network Design, there were no subscribers receiving improved access in the fourth quarter. Therefore, we are behind our baseline target of 205 subscribers receiving improved access. | n/a No operating network so no speed tiers. | 0 | 0 | 0 | 0 | 0 | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | 0 | 0 | 0 | 0 | 0 | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a No services being provided yet. | FALSE | n/a | The number one accomplishment will be the completion of the Grantee Substitution from CBOCES to EAGLE-Net. This will allow us to begin appropriate expenditures and request reimbursements. EAGLE-Net will hire its core staff and set up its business and operational support systems. We will also engage the selected consultants to begin the Environmental Assessment and the Network Design work. During the quarter as these tasks are underway, we will be able to initiate site preparation and begin some equipment procurement, deployment and testing for peering sites. These items will be substantially complete during the next quarter. | Centennial Board of Cooperative Educational Services | Although listed under accomplishments, the time involved in the Grantee Substitution process obviously had an impact on our project's timeline. Our NTIA Federal Program Officer has been very helpful throughout the process and and while this process was not completed during the fourth quarter we anticipate it will be complete in January 2011. | Once the Grantee Substitution process has been completed, we will expedite things to the best of our ability while still making sure that we adhere to good business procedures and decisions. We are confident that because of the groundwork and preparation that was laid this quarter, we will be able to catch up in the near future. | TRUE
NT10BIX5570156 | 2011 | Q1 | Q1 - 2011 | The top priority has been to complete the Grantee Substitution request from the Centennial Board of Cooperative Educational Services (CBOCES) to the new entity, EAGLE-Net Alliance (EAGLE-Net). In order to make this transition as smooth as possible, no funds were spent and no federal funds were requested by the CBOCES for this grant in the first quarter. In our communications with the NTIA, it has been indicated to us and we expect the Grantee Substitution request to be fully completed in February 2011. At that time, as EAGLE-Net, we will begin to spend the necessary funds and fully expect to catch up to our budgeted completion estimates in the first quarter of 2011. As soon as the request has been approved, we have a core staff ready to be hired by EAGLE-Net as well as our business and operational support systems ready to be implemented, we have our Environmental Consultant selected and they are awaiting our word to begin work, and we have our Project Management/Network Design Team selected and ready to begin work. PLEASE NOTE: This report is being created after the transfer request, per our Federal Program Officer. It is meant to show activity for the period of January 1 - January 31, 2011. There was no financial spend activity during this time, so the comparison is to the baseline results for the end of the December 31, 2011 time period. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Due to the previously described delays in the Network Design, no new network miles were deployed. Therefore, we are behind our baseline target of 117 new deployed miles. | Due to the previously described delays in the Network Design, no new network miles were leased. Therefore, we are behind our baseline target of 148 new leased miles. | Due to the previously described delays in the Network Design, no new network miles were upgraded. Therefore, we are behind our baseline target of 19 upgraded miles. | n/a Consistent with the baseline report. | Due to the previously described delays in the Network Design, no new fiber miles were deployed. Therefore, we are behind our baseline target of 102 fiber miles. | Due to the previously described delays in the Network Design, no new wireless links were installed. Therefore, we are behind our baseline target of 9 new wireless links. | Due to the previously described delays in the Network Design, no new towers were constructed. Therefore, we are behind our baseline target of 10 new towers. | Due to the previously described delays in the Network Design, no new or upgraded interconnection points were completed. Therefore, we are behind our baseline target of 11 new interconnection points. | 0 | 0 | 0 | n/a There are no agreements signed through the fourth quarter, which is consistent with our baseline target. | n/a As no build has yet been completed, no services were being provided by this project in the fourth quarter. Therefore, there is no pricing list attachment. | n/a No build has yet been completed so there is no network operation. | 0 | 0 | 0 | 0 | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a No operating network so no speed tiers. | 0 | 0 | 0 | 0 | Due to the previously described delays in the Network Design, no subscribers were being served in the fourth quarter. Therefore, we are behind our baseline target of 259 subscribers. | Due to the previously described delays in the Network Design, there were no subscribers receiving new access in the fourth quarter. Therefore, we are behind our baseline target of 54 subscribers receiving new access. | Due to the previously described delays in the Network Design, there were no subscribers receiving improved access in the fourth quarter. Therefore, we are behind our baseline target of 205 subscribers receiving improved access. | n/a No operating network so no speed tiers. | 0 | 0 | 0 | 0 | 0 | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | 0 | 0 | 0 | 0 | 0 | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a No services being provided yet. | FALSE | n/a | The number one accomplishment will be the completion of the Grantee Substitution from CBOCES to EAGLE-Net. This will allow us to begin appropriate expenditures and request reimbursements. EAGLE-Net will hire its core staff and set up its business and operational support systems. We will also engage the selected consultants to begin the Environmental Assessment and the Network Design work. During the quarter as these tasks are underway, we will be able to initiate site preparation and begin some equipment procurement, deployment and testing for peering sites. These items will be substantially complete during the next quarter. | Centennial Board of Cooperative Educational Services | Although listed under accomplishments, the time involved in the Grantee Substitution process obviously had an impact on our project's timeline. Our NTIA Federal Program Officer has been very helpful throughout the process and and while this process was not completed during the fourth quarter we anticipate it will be complete in February 2011. | Once the Grantee Substitution process has been completed, we will expedite things to the best of our ability while still making sure that we adhere to good business procedures and decisions. We are confident that because of the groundwork and preparation that was laid this quarter, we will be able to catch up in the near future. | TRUE
NT10BIX5570157 | 2010 | Q4 | Q4 - 2010 | The primary accomplishments during the quarter were centered on the process of formally accepting the grant and establishing the necessary policies, procedures and practices to manage the grant and successfully implement the project. Key accomplishments included releasing a Request for Proposal for the required environmental services to complete the Environmental Assessment (EA) and selecting a vendor. Additionally, we began to develop the required Intergovernmental Agreements between the prime-recipient and all sub-recipients that will be required to begin development. Work on the initial fiber network design was also started. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/a | N/A | FALSE | N/A | During the first quarter of 2011 we hope to achieve several key milestones related to the successful implementation of the Public Safety Broadband Network. We intend to complete our work on the Environmental Assessment (EA), which is currently on schedule for submission by the March 31st deadline. We will release our Competitive Cost Proposal for the LTE related equipment and services in early January 2011 with the intention of having a vendor selected by the end of March. Additionally, we plan to begin implementing the in-kind fiber optic network elements that will begin the process of connecting our Community Anchor Institutions. We also plan to release our Competitive Cost Proposal for the installation of the remaining new fiber required for the network. | Adams County Communications Center, Inc. | N/A | The primary challenges for this quarter will be finalizing the Intergovernmental Agreements with the sub-recipients and the completion of the Environmental Assessment. The primary roadblock to completing the EA would be unexpected weather that could lead to delays. | TRUE
NT10BIX5570157 | 2011 | Q1 | Q1 - 2011 | During this quarter ADCOM 911 successfully completed and submitted the draft Environmental Assessment by the March 31st deadline. Additionally, we released a Request for Competitive Cost Proposal (RFCCP) for the equipment and services required for the wireless LTE portion of the project. We received 4 qualified responses and from those identified 2 semi-finalists. We began to purchase the required fiber-optic and networking equipment to implement the existing fiber-optic cable that will be used for the underlying backhaul network. Negotiations with both sub-recipients continued towards the Intergovernmental Agreements required to purchase and implement equipment and services. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | During the 4th quarter, ADCOM anticipates receiving our Finding of No Significant Impact (FONSI) allowing us to proceed with full project development activities. We will sign the contract for LTE related services and equipment and begin development of the network. As part of this, we anticipate beginning all site work and hope to finish a few key sites. ADCOM hopes to release the Request for Competitive Cost Proposal for fiber-construction services for the West Tower/Thornton fiber run. We plan to install and configure 2 of the 3 fiber aggregation points to be used for the underlying network as well. | Adams County Communications Center, Inc. | N/A | N/A | TRUE
NT10BIX5570157 | 2011 | Q2 | Q2 - 2011 | During the second quarter of 2011 ADCOM 911 achieved two significant milestones toward the overall project. We received our Finding of No Significant Impact (FONSI) and we finalized negotiations with our selected LTE systems integrator Raytheon. In addition to these accomplishments we continued to make progress on the underlying back haul network by beginning to install the required network equipment at existing IT sites to turn up the in-kind fiber that already exists. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance | N/A | No Variance | N/A | No Variance | No Variance | The revised site configuration will only require one new tower construction, a 70 foot monopole to be developed. This site will be developed soon and will not cause delays in the project. | No Variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | Network not yet in service | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | During the third quarter of 2011 we anticipate significant progress on site preparation and a finalization of all rights. We should begin the process of lighting up and configuring the in-kind fiber that will begin the development of the underlying fiber back haul network. Additionally, we hope to begin receiving initial LTE equipment toward the end of the quarter. | Adams County Communications Center, Inc. | As discussed, the time to receive our FONSI after initial EA submission was much longer than anticipated which caused significant delays. Additionally, the contract negotiations with our selected vendor took a bit longer than anticipated. Both of these issues were resolved at the end of June and we anticipate to be on full project schedule by the end of next quarter. Additionally, ADCOM 911 and Denver International Agreement (DIA) were unable to reach an agreement to distribute the specified sub-recipient funds. The primary roadblock to the agreement were conflicts between Federal Aviation Administration (FAA) requirements that DIA must adhere to and the requirements of the BTOP program. Specifically, the issue of security interest in grant purchased property and the useful life requirements were the sources of conflict. | With the LTE contract finalized and the EA completed we should be able to ramp up deployment and construction quickly. | TRUE
NT10BIX5570157 | 2011 | Q3 | Q3 - 2011 | During the third quarter of 2011 ADCOM made significant steps toward the LTE system development. The contract with Raytheon Corporation was signed in July and immediately began working on the overall network design. The initial draft of the network design was completed in late July and all equipment required for the eNodeB and EPC site(s) were ordered. ADCOM received the EPC equipment beginning in late august and an initial eNodeB in September. By the end of September, ADCOM had successfully completed an "Initial Capability" test in which we were able to transfer data through the system to a laptop using a USB dongle UE device. Additionally, we successfully testing the basic functionality of our CAD application through the network and successfully testing the process of failing over from our network to a commercial network using middleware software. In addition to the wireless activities, ADCOM continued to install the equipment required to activate the existing fiber-optic infrastructure to serve as the backbone of the backhaul network. ADCOM also began the site construction and tower strengthening work that will be required for the eNodeB sites. | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 3 | Based on changes in NTIA guidelines, existing dark fiber that was being utilized is now considered upgraded fiber rather than new deployment. See Existing miles upgraded for additional details on fiber deployment. | N/A | Based on changes in NTIA guidelines, existing dark fiber that was being utilized is now considered upgraded fiber rather than new deployment. For baseline numbers related to network miles please refer to new network miles in baseline report. We were delayed in placing equipment at one of our Community Anchor Institutions due to work they were doing in their IT room. This pushed back the process of turning-up one segment. This issue has since been resolved and we do not expect any delays in the overall project. | N/A | Based on changes in NTIA guidelines, existing dark fiber that was being utilized is now considered upgraded fiber rather than new deployment. See Existing miles upgraded for additional details on fiber deployment. | No Variance | The revised site configuration will only require one new tower construction, a 70 foot monopole to be developed. This site will be developed soon and will not cause delays in the project. | No Variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 3 | 0 | 3 | 3 | During this quarter, we decided to revisit our logical network design and re-work some routing and other specifications. Due to this, we delayed the installation of some network equipment until final decisions had been made. The design work has been completed and the fiber is available at the remaining CAI's. We will be working to install the required equipment at these CAI's during the next quarter. | No Variance | During this quarter, we decided to revisit our logical network design and re-work some routing and other specifications. Due to this we delayed the installation of some network equipment until final decisions had been made. The design work has been completed and the fiber is available at the remaining CAI's. We will be working to install the required equipment at these CAI's during the next quarter. | CAI's will receive either 10GB/sec or 1GB/sec | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | During the next quarter we hope to finalize the majority of technical design requirements for the LTE system. We will continue to make significant progress on all site preparation and tower hardening as well. In addition, we plan to turn-up additional CAI's on our fiber route and potentially activate additional miles of fiber. The specific estimates (cumulative) are: New network miles deployed: 25 New network miles leased: N/A Total number of CAI's: 8 Number of agreements: N/A The reason for the lower number of network miles deployed is due to the delay in implementing the microwave backhaul portion of the network due to delays in the EA process. | Adams County Communications Center, Inc. | As mentioned, ADCOM submitted a reprogram/rebudget request to reflect changes to cost categories now that the final LTE contract has been signed. We anticipate these revised budgetary numbers will reflect the actual progress better. Additionally, there are key changes to the implementation in our contract to those anticipated in the Initial Baseline report; however, the project is anticipated to go live during the Spring of 2012, before the final deadline. In regards to the discrepancy in the Activity Based Expenditures section 1d, ADCOM had anticipated the tower studies commissioned (for approx. $15,000) to be invoiced during this quarter. While the work was done, ADCOM 911 had not received an invoice as of September 30th, therefore, showed no expenditures. Based on the initial report, we anticipate the required tower strengthening to take place during the last quarter of the year, and expending the $75,000 allocated. There is a chance, with difficult weather, that the work will not be full completed during the quarter. | The primary activities for the next quarter will be site preparation and final system design. Our primary challenge during this period would be weather patterns as unseasonable cold or snow may delay some construction activities. | TRUE
NT10BIX5570157 | 2011 | Q4 | Q4 - 2011 | During this quarter ADCOM 911 focused on site work required for the installation of the eNodeB sites. We successfully installed 3 new generators at key sites, 2 new UPS units and did extensive electrical work at the primary ADCOM 911 facility in order to handle the EPC and fiber aggregation point to be located here. We successfully installed two of the key fiber aggregation points and began passing data over the fiber connection between three of our CAI's. ADCOM 911's revised budget was approved by the NTIA during this quarter as well. | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 1 | The initial direction on the baseline report was to consider dark, in-kind fiber as new miles. We have subsequently received instructions to count this as upgraded fiber and are reporting accordingly. | N/A | The initial direction on the baseline report was to consider dark, in-kind fiber as new miles. We have subsequently received instructions to count this as upgraded fiber and are reporting accordingly. The miles upgraded to date represent some of this dark fiber that has been turned-up between two key aggregation points, both of which are CAI's. | N/A | The initial direction on the baseline report was to consider dark, in-kind fiber as new miles. We have subsequently received instructions to count this as upgraded fiber and are reporting accordingly. | No Variance | The revised site configuration will only require one new tower construction, a 70 foot monopole to be developed. The initial foundation for this site has been completed and will be installed during the second quarter of 2012. | At the time of the baseline report, we did not have a final network design. We have since implemented a model that will has one key interconnection points where multiple public safety and local government agencies will connect their networks to be used for multiple purposes. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 4 | 0 | 4 | 4 | Changes to the fiber route and overall network design caused some delays in fiber implementation. The design has been completed and we are identifying the final fiber route. We do not expect any delays in the overall project. | No Variance | Changes to the fiber route and overall network design caused some delays in fiber implementation. The design has been completed and we are identifying the final fiber route. We do not expect any delays in the overall project. | CAI's will receive either 10GB/sec or 1GB/sec | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | For the 1st quarter of 2012 ADCOM 911 plans to continue the site work and preparation for the eNodeB installation. We anticipate to receive updated EPC software releases from our vendor as well. We should begin receiving the eNodeB equipment in March. ADCOM 911 hopes to release the RFP for the final fiber route during this quarter as well. | Adams County Communications Center, Inc. | While there are some delays from the original baseline, the project remains on schedule based on the project plan developed with the LTE vendor. Our biggest challenge has been adapting the project to some of the unknown issues that have arisen (zoning issues, changing fiber routes, etc). Delays from various equipment manufactures have caused us to alter priorities but again, the overall project remains on track. | During the winter and spring weather is always a primary challenge for site work and preparation. Finalizing, and getting an RFP for the final fiber paths will be a primary focus as well. | TRUE
NT10BIX5570157 | 2012 | Q1 | Q1 - 2012 | During the first quarter of 2012 ADCOM 911 maintained its focus on site development and backhaul network development. ADCOM 911 submitted a route change request and associated environmental analysis to modify one of the primary fiber routes as well as some LTE site changes due to zoning and tower requirements. ADCOM 911 installed all the required generators, finished initial tower strengthening and shelter modifications. ADCOM 911 successfully installed the one approved monopole at Fire Station 11. ADCOM 911 continued to install and configure the fiber network to be used for LTE backhaul and CAI connection. ADCOM 911 also began receiving the eNodeB's to be used for the final network. The RFP for the (proposed) 120th fiber installation was released. | 20 | 0 | 20 | 0 | 0 | 0 | 1 | 3 | The initial baseline report anticipated the installation of some microwave sites before the eNodeB sites. The final design and installation plan assumes the microwave will be installed at the same time as the eNodeB's. We anticipate most of these sites to be completed by Fall of 2012. | N/A | No Variance | N/A | This is less than the projected deployment from our baseline report. This is due to the fact that we had to revise our Environmental Assessment, to change the fiber route in the ground from one path to another. The EA was not received prior to the end of the quarter, so we were not able to start the bid or build process for the additional fiber. | No Variance | This is less than the projected deployment from our baseline report. This is due to the fact that we had to revise our Environmental Assessment, to change some of the sites housing tower facilities. The EA was not received prior to the end of the quarter, so we were not able to start the bid or build process for the additional tower sites. | No Variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 4 | 0 | 4 | 4 | Changes to the fiber route and overall network design caused some delays in fiber implementation. The design has been completed and we are identifying the final fiber route. We do not expect any delays in the overall project. Additionally, some of the CAI's have not had the appropriate space ready for us in their equipment rooms. | N/A | Changes to the fiber route and overall network design caused some delays in fiber implementation. The design has been completed and we are identifying the final fiber route. We do not expect any delays in the overall project. Additionally, some of the CAI's have not had the appropriate space ready for us in their equipment rooms. | Changes to the fiber route and overall network design caused some delays in fiber implementation. The design has been completed and we are identifying the final fiber route. We do not expect any delays in the overall project. Additionally, some of the CAI's have not had the appropriate space ready for us in their equipment rooms.Each fiber link is operating at 1 Gbps, with connection to an Aggregation Point. The connections between Aggregation Points are operating at 10 Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | ADCOM 911 hopes to begin the process of installing the final eNodeB's and start testing the overall network. At this time ADCOM 911 has received verbal notice that all LTE related activities will be suspended. ADCOM 911 believes continuing with the eNodeB installation is in the best interest of both ADCOM 911 and FirstNet. ADCOM 911 will continue to finalize all site work and hopes to receive final approval of the route change so we can begin installation of the 120th fiber and the Station 54 monopole. | Adams County Communications Center, Inc. | With the passing of the legislation allocating the D-block and creating FirstNet ADCOM 911 has been notified of potential complications with our project development. ADCOM 911 continues to move forward with the overall development of the network, currently focusing on infrastructure development and awaits further instructions from NTIA. | Based on the verbal direction provided by NTIA we believe the future of the project is in flux and can not estimate the challenges until further direction is provided. | TRUE
NT10BIX5570157 | 2012 | Q2 | Q2 - 2012 | During the second quarter of 2012 ADCOM911 maintained its focus on site development and backhaul network development. ADCOM911 successfully established connectivity to another CAI - City of Commerce City. A microwave link was installed to another CAI - Southwest Adams County Fire. That link is still pending further network configuration before it is activated. We also received approval of the route change request made in the previous quarter. ADCOM received additional LTE equipment from our vendor, which was ordered and paid for earlier in the project. This includes several ENodeB units, 50 USB Dongles, and 50 trunk mounted Mobile Modems. Testing continued with the existing Core and ENodeB mounted at the ADCOM911 site. Technicians were scheduled to begin additional deployment of equipment, both LTE and network related, to additional sites. ADCOM911 received the partial suspension order on May 11th, 2012, and all site and network development was placed on hold. The remainder of the quarter was spent providing a detailed accounting of funds spent through 5/11, and evaluating how to move forward with the project with the partial suspension in effect. While completing the expense audit, it was discovered some expenses were booked to the wrong line item in previous PPR reports. The categorized totals under Infrastructure Budget now coincide with the expense audit, the SF-425, and the ARRA report. Because of this, some categories will show less expenses than previous quarters, while some show more. | 30 | 0 | 25 | 0 | 3 | 1 | 1 | 4 | One microwave link was installed to another CAI - Southwest Adams County Fire, and is undergoing testing at this time. Further equipment configuration will need to be completed prior to production use of the link. Additional microwave and fiber optic infrastructure will be deployed once the project plan is revised. | N/A | The City of Commerce City link was placed into production during the quarter. | N/A | This is less than the projected deployment from our baseline report. This is due to the fact that we had to revise our Environmental Assessment, to change the fiber route in the ground from one path to another. Approval was received on the revised EA just prior to receipt of the suspension letter. One segment of a larger run was completed to connect to our 3rd major aggregation point. ADCOM911 is currently asking for vendor bids to install two additional fiber paths. | One microwave link was installed to Southwest Adams County Fire. | This is the above mentioned link to Southwest Adams County Fire. This is less than the projected deployment from our baseline report. This is due to the fact that we had to revise our Environmental Assessment, to change some of the sites housing tower facilities. Approval was received on the revised EA just prior to receipt of the suspension letter, so we were not able to start the bid or build process for the additional tower sites. | The City of Commerce City link will serve as an intermediary hub to additional fiber and/or microwave connections. This link is now active and in use by the CAI. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 6 | 2 | 4 | 4 | 4 subscribers currently have equipment installed and configured. 3 of them are actively using the connection today. The fourth is scheduled to begin use of the new link within the 3rd quarter 2012. The two remaining have fiber installed, but do not have equipment installed yet. One is waiting for additional expansion of the network to a new endpoint, and one is waiting for the site owner to prepare the room to house equipment. | Adams County Government Center and City of Brighton previously had no access. Fiber is now run to their facility, though no equipment is installed or configured, as noted above. | City of Commerce City formerly used an outdated microwave link. They are now actively using the new fiber optic network. Southwest Adams County Fire currently uses an internet based VPN, limited to 1 Mbps. Once their link is activated, they will begin using improved access as noted above. | Each fiber link is operating at 1 Gbps, with connection to an Aggregation Point. The connections between Aggregation Points are operating at 10 Gbps. Since most individual links will carry more than one subscriber, each subscriber is provided 100 Mbps back to the aggregation points. Currently 2 subscribers are using 100 Mbps, and one subscriber is using 10 Gbps. The fourth will be using 100 Mbps when activated. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | ADCOM911 plans to continue deployment of the microwave and fiber optic networks that were part of the original plan and provide additional use besides the LTE system. For example, sites that will connect CAIs to the server applications housed at ADCOM911, sites that can be used for LMR and NextGen 911 backhaul, etc. ADCOM911 is hopeful the FCC will grant a temporary STA to deploy additional LTE sites within the area, according to the original plan. If the STAs are not granted, ADCOM911 will potentially re-scope the project to deploy additional broadband access which was not part of the original project plan. | Adams County Communications Center, Inc. | The largest challenge faced was receipt of the partial suspension notice. ADCOM911 had to place all efforts on hold. A full accounting of all expenses up to the suspension notice was required. Internal resources were redirected to complete the audit in a timely fashion. Further guidance was received, indicating that expansion of the broadband network was an acceptable use of the BTOP funds. However, ADCOM911 suspended any further technical work to provide time to assess our strategy moving forward. If ADCOM911 redirects all remaining funds toward network expansion, there will be no funds left to configure and deploy the LTE equipment we have already procured. However, additional benefit can be realized by expanding the transport network further than originally planned. Discussions continue between ADCOM911, NTIA, the FCC, and other community partners to further develop our strategy moving forward. | The biggest challenge for the upcoming quarter is the future direction of the project as a whole. ADCOM911 will evaluate whether to re-scope the project to provide additional broadband access beyond the original plan, or to build the network as originally designed and wait for direction related to the LTE system. If it is decided to deploy additional broadband access, the project plan will need to be revised, along with the budget. Additional EA work will need to be performed, and potentially new agreements established. If it is decided to wait for direction related to the LTE system, the overall progress of the project will slow significantly. Additional startup costs may be incurred from our vendors to get the project moving forward again, if approval is received to continue LTE development. Existing agreements may need to be revised in anticipation of delayed deployment. | TRUE
NT10BIX5570157 | 2012 | Q3 | Q3 - 2012 | During the third quarter of 2012 ADCOM911 maintained its focus on site development and backhaul network development. ADCOM911 finalized the configuration of network equipment to another CAI - Southwest Adams County Fire. That link is now ready to be used, and is waiting for the CAI to integrate their own network connectivity to it. Three additional microwave links were upgraded at the Cherokee, LadyBird, and Hoyt sites, which will provide backhaul from remote areas of the County back to the ADCOM 911 Fiber Network. At the Brighton Administration building, additional network equipment was installed which will allow us to connect another microwave link to remote areas of the County once the microwave equipment has been installed. A soil engineering report was completed for another remote site (Fire Station 54), and the parts and materials required to install a monopole at that site were delivered to our primary contractor. One of the prime sites (Cherokee) has been undergoing various site improvements - structural and electrical - and a significant portion of the work was completed this quarter. This work is a pre-requisite to installing and activating the network equipment at the site, because the original structure and infrastructure could not support additional equipment. Finally, ADCOM 911 completed the installation of a new run of fiber optic cable, from our Cherokee Site to the corner of 120th Ave. and Grant Street in Northglenn, as part of our in-kind contribution. This section of fiber will tie into another section to be constructed along 120th Ave. as part of the overall project. When the 120th Ave. construction is complete, we will have connectivity through fiber as a primary path to Cherokee and the existing fiber aggregation points. The construction completed during this quarter was the first phase of that overall fiber run. | 32 | 0 | 90 | 0 | 5 | 1 | 1 | 4 | One segment of fiber was installed - from 112th and Cherokee to 120th and Grant - or just under 2 miles. This run will be part of a larger fiber optic network build to be completed later in the project. | N/A | Three existing microwave links were upgraded with new microwave equipment, providing much greater bandwidth in the overall transport network. From ADCOM 911 to Cherokee - 5 miles. From Cherokee to LadyBird - 30 miles. From LadyBird to Hoyt, 30 miles. | N/A | This is less than the projected deployment from our baseline report. This is due to ongoing uncertainty with the overall status of the LTE project. We will proceed with caution toward the project and funding until we ascertain if we will move forward with LTE, or Broadband connectivity alone. However, a new segment was installed as noted above, and was just under 2 miles of new fiber construction. | This is less than the projected deployment from our baseline report. This is due to ongoing uncertainty with the overall status of the LTE project. We will proceed with caution toward the project and funding until we ascertain if we will move forward with LTE, or Broadband connectivity alone. The microwave links noted above were existing links that were upgraded. | The project plan has been modified since the baseline report was first submitted, and we will be utilizing many existing towers instead of building as many new towers as first projected. This is still less than the projected deployment from our baseline report. This is due to ongoing uncertainty with the overall status of the LTE project. We will proceed with caution toward the project and funding until we ascertain if we will move forward with LTE, or Broadband connectivity alone. | This is less than the projected deployment from our baseline report. This is due to ongoing uncertainty with the overall status of the LTE project. We will proceed with caution toward the project and funding until we ascertain if we will move forward with LTE, or Broadband connectivity alone. While 3 microwave links were upgraded, they are still pending the installation/configuration of the network equipment. And while 1 new network switch was installed, it is still pending the installation/configuration of the microwave. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 6 | 2 | 4 | 4 | 4 subscribers currently have equipment installed and configured. 3 of them are actively using the connection today. The fourth is ready to begin use of the new link when they have integrated the link with their existing network. Two remaining sites have fiber installed, but do not have equipment installed yet. One is waiting for additional expansion of the network to a new endpoint, and one is waiting for the site owner to prepare the room to house equipment. | Adams County Government Center and City of Brighton previously had no access. Fiber is now run to their facility, though no equipment is installed or configured, as noted above. | City of Commerce City formerly used an outdated microwave link. They are now actively using the new fiber optic network. Southwest Adams County Fire currently uses an internet based VPN, limited to 1 Mbps. Once their link is activated, they will begin using improved access as noted above. | Each fiber link is operating at 1 Gbps, with connection to an Aggregation Point. The connections between Aggregation Points are operating at 10 Gbps. Since most individual links will carry more than one subscriber, each subscriber is provided 100 Mbps back to the aggregation points. Currently 2 subscribers are using 100 Mbps, and one subscriber is using 10 Gbps. The fourth will be using 100 Mbps when activated. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | ADCOM911 plans to continue deployment of the microwave and fiber optic networks that were part of the original plan and provide additional use besides the LTE system. For example, sites that will connect CAIs to the server applications housed at ADCOM911, sites that can be used for LMR and NextGen 911 backhaul, etc. ADCOM911 is hopeful the FCC will grant a temporary STA to deploy additional LTE sites within the area, according to the original plan. If the STAs are not granted, ADCOM911 will potentially re-scope the project to deploy additional broadband access which was not part of the original project plan. | Adams County Communications Center, Inc. | The suspension notice received in May 2012 came at a critical juncture in the ADCOM 911 project. Most of the LTE equipment was purchased prior to the suspension, and the majority has since been received at our facility. We had many discussions with the NTIA throughout the quarter to try and determine if the LTE project would move forward. If it was approved to move forward, then we would continue with the project as originally planned. If we were not allowed to move forward, we would need to reassess our plans and use the remaining grant funds to further expand and develop the Broadband network in areas previously unplanned. As such, we were very cautious moving forward so no funds were wasted before a decision could be made. At the end of the 3rd Quarter, we have still not received a definitive answer as to whether LTE will move forward or not. Both the NTIA and FCC have to approve our application to do so, and additional guarantees are required from our vendor. Since this decision is still pending, our progress was slowed, and we have only worked on those parts of the Broadband Network that can be used whether LTE moves forward or not. We will continue with this cautious approach until a final determination is made. | ADCOM911 is hopeful the FCC will grant a temporary STA to deploy additional LTE sites within the area, according to the original plan. If the STA application is granted, ADCOM 911 will need to redirect some amount of funds and staff time to the restart of the contract and project. However, the overall project would then be able to proceed according to the original plan, though project timelines will shift outside the original scope. If the STAs are not granted, ADCOM911 will need to re-scope the project to deploy additional broadband access which was not part of the original project plan. If this occurs, the project plan will need to be revised, along with the budget. Additional EA work will need to be performed, potentially new agreements established, and existing agreements may need to be revised in anticipation of delayed deployment. Additional delays will occur until a decision regarding LTE deployment is reached. | TRUE
NT10BIX5570157 | 2012 | Q4 | Q4 - 2012 | During the fourth quarter of 2012 ADCOM911 maintained its focus on site development and backhaul network development. ADCOM911 installed a broadband microwave from the Brighton City Hall to the Hilltop site. Once configured, this link will replace an outdated microwave, and will carry voice traffic for the LMR system. It will also serve as a redundant path that can be used should the fiber network in the northern area be cut. We continued the remodel at one of our primary network aggregation sites, the Cherokee site. This site is key to our Broadband, LMR, and LTE networks, and the remodel will fortify it for years of ongoing use. The construction at the Fire Station 54 site continued, and a foundation was poured to use for the base of the monopole that will be installed there. At the ADCOM site our contractor installed the gas line used to provide service to our broadband-specific backup generator. We applied for the frequency coordination and FCC licensing to increase the 11 Ghz Broadband Microwave licenses from 40 Mhz to 80 Mhz bandwidth, effectively doubling the data throughput in each microwave. Additionally, the high speed microwave installed in Q3 between the ADCOM and Cherokee sites was placed into production service. This link replaced an older 45 Mbps microwave with the new 500 Mbps microwave capability. Both the ADCOM and Cherokee sites are major aggregation hubs in the overall network, and this link will serve as the primary path between them for the short term. Once the fiber network is extended to the Cherokee site, the microwave will then act as a backup path in case of a fiber cut in the southern area. | 40 | 0 | 90 | 0 | 5 | 2 | 1 | 5 | A new microwave link was installed between the City of Brighton and the Hilltop Radio Site - approximately 8 miles. | N/A | This differs from the baseline report because the original intention was to use BTOP funds to install fiber cabling between locations. However, it was later determined to use existing cabling and use BTOP funds to purchase the network equipment instead. | N/A | This is less than the projected deployment from our baseline report. This is due to ongoing uncertainty with the overall status of the LTE project. We will proceed with caution toward the project and funding until we ascertain if we will move forward with LTE, or Broadband connectivity alone. | This is less than the projected deployment from our baseline report. This is due to ongoing uncertainty with the overall status of the LTE project. We will proceed with caution toward the project and funding until we ascertain if we will move forward with LTE, or Broadband connectivity alone. However, 1 new micrwowave link to two sites was installed. | The project plan has been modified since the baseline report was first submitted, and we will be utilizing many existing towers instead of building as many new towers as first projected. This is still less than the projected deployment from our baseline report. This is due to ongoing uncertainty with the overall status of the LTE project. We will proceed with caution toward the project and funding until we ascertain if we will move forward with LTE, or Broadband connectivity alone. | This is less than the projected deployment from our baseline report. This is due to ongoing uncertainty with the overall status of the LTE project. We will proceed with caution toward the project and funding until we ascertain if we will move forward with LTE, or Broadband connectivity alone. While the microwave was installed connecting the Brighton City Hall to the Hilltop Site, only the Brighton side has a network switch connected and configured. No additional network equipment was deployed for the new fiber until the larger fiber connection is complete. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 6 | 2 | 4 | 4 | 4 subscribers currently have equipment installed and configured. 3 of them are actively using the connection today. The fourth is ready to begin use of the new link when they have integrated the link with their existing network. Two remaining sites have fiber installed, but do not have equipment installed yet. Both are waiting for the site owner to prepare the room to house equipment. | Adams County Government Center and City of Brighton previously had no access. Fiber is now run to their facility, though no equipment is installed or configured, as noted above. | City of Commerce City formerly used an outdated microwave link. They are now actively using the new fiber optic network. Southwest Adams County Fire currently uses an internet based VPN, limited to 1 Mbps. Once they have integrated the link to their own network, they will begin using improved access as noted above. | Each fiber link is operating at 1 Gbps, with connection to an Aggregation Point. The connections between Aggregation Points are operating at 10 Gbps. Since most individual links will carry more than one subscriber, each subscriber is provided 100 Mbps back to the aggregation points. Currently 2 subscribers are using 100 Mbps, and one subscriber is using 10 Gbps. The fourth will be using 100 Mbps when activated. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | ADCOM911 plans to continue deployment of the microwave and fiber optic networks that were part of the original plan and provide additional use besides the LTE system. For example, sites that will connect CAIs to the server applications housed at ADCOM911, sites that can be used for LMR and NextGen 911 backhaul, etc. ADCOM911 is hopeful FirstNet will grant use of the spectrum and resolve questions pertaining to the proposed conditions. If so, our project can proceed according to the original plan. If not, ADCOM911 will potentially re-scope the project to deploy additional broadband access which was not part of the original project plan. | Adams County Communications Center, Inc. | We are at a difficult juncture in our overall project, forcing us to a near standstill. We have enough money remaining in the grant to either finish our original LTE project, or repurpose the funds to expand additional Broadband connectivity throughout the County. If we repurpose the funds for Broadband expansion and are later notified we can proceed with LTE, we wonâ€™t have the funds needed to finish the LTE project. Because of this, we are waiting to hear the status of our LTE deployment, and we are only working on those aspects of the Broadband network that could be used whether LTE moves forward or not. As of December 31st, 2012, we still have not received any indication from the NTIA if our original LTE grant project will move forward. The NTIA has indicated that we must be granted use of the LTE spectrum before they will permit us to move forward, but only FirstNet can grant us permission to use the spectrum. We met with representatives of the FirstNet Board in December 2012, and are hopeful we will have some indication in Q1 2013. NTIA also proposed new conditions which both ADCOM 911 and our Vendors must conform to. During the meeting with the FirstNet Board members, it was indicated that these conditions may be changed by FirstNet to better satisfy their goal of a Nationwide Public Safety Broadband Network. Therefore, we are also waiting for further direction from the FirstNet Board to determine if these conditions will be modified or stand as proposed by NTIA. | ADCOM911 is hopeful the FirstNet Board will grant use of the spectrum, and resolve the outstanding questions regarding the conditions. If so, ADCOM 911 will need to redirect some amount of funds and staff time to the restart of the contract and project. However, the overall project would then be able to proceed according to the original plan, though project timelines will shift outside the original scope. If not, ADCOM911 will need to re-scope the project to deploy additional broadband access which was not part of the original project plan. If this occurs, the project plan will need to be revised, along with the budget. Additional EA work will need to be performed, potentially new agreements established, and existing agreements may need to be revised in anticipation of delayed deployment. Additional delays will occur until a decision regarding LTE deployment is reached. | TRUE
NT10BIX5570157 | 2013 | Q1 | Q1 - 2013 | During the first quarter of 2013 ADCOM911 maintained its focus on site development and backhaul network development. We completed the remodel at one of our primary network aggregation sites, the Cherokee site. This site is key to our Broadband, LMR, and LTE networks, and the remodel will fortify it for years of ongoing use. The construction at the Fire Station 54 site was completed, and a new monopole was installed. We also installed and aligned the microwave between Station 54 and the Brighton Water Tank site. At the ADCOM site we finished the start up process for the generator powering the broadband equipment shelter, and that generator is now online. We have solicited bids to complete the fiber installation at our Cherokee site, from the street pull box into the equipment building. Once in place this fiber will serve as the primary link for the Cherokee site to reach Adcom and the rest of the network, and the microwave will become the backup link. We have been working with representatives of Jefferson County in order to plan for expansion of fiber infrastructure into further areas of the Denver metro area. If we re purpose our grant funds solely for broadband expansion, we can pursue these options to interconnect additional Community Anchor Institutions for the purposes of Public Safety cooperation. Finally we have been in negotiation with FirstNet representatives to obtain a lease of the 700 Mhz Public Safety Broadband Spectrum. These negotiations are ongoing as of the end of the 1st Quarter, 2013. | 43 | 0 | 90 | 0 | 5 | 3 | 2 | 5 | A new microwave path was installed between Station 54 and the Brighton Water Tank | N/A | This differs from the baseline report because the original intention was to use BTOP funds to install fiber cabling between locations. However, it was later determined to use existing cabling and use BTOP funds to purchase the network equipment instead. We have not upgraded any existing network miles this quarter. | N/A | We have not installed any new fiber in the 1st quarter of 2013 | This is less than the projected deployment from our baseline report. This is due to ongoing uncertainty with the overall status of the LTE project. We will proceed with caution toward the project and funding until we ascertain if we will move forward with LTE, or Broadband connectivity alone. However, 1 new micrwowave link to two sites was installed. | During the 1st quarter of 2013 we finished the installation of a new monopole at Station 54. The project plan has been modified since the baseline report was first submitted, and we will be utilizing many existing towers instead of building as many new towers as first projected. This is still less than the projected deployment from our baseline report. This is due to ongoing uncertainty with the overall status of the LTE project. We will proceed with caution toward the project and funding until we ascertain if we will move forward with LTE, or Broadband connectivity alone. | This is less than the projected deployment from our baseline report. This is due to ongoing uncertainty with the overall status of the LTE project. We will proceed with caution toward the project and funding until we ascertain if we will move forward with LTE, or Broadband connectivity alone. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 6 | 2 | 4 | 4 | 4 subscribers currently have equipment installed and configured. 3 of them are actively using the connection today. The fourth is ready to begin use of the new link when they have integrated the link with their existing network. Two remaining sites have fiber installed, but do not have equipment installed yet. Both are waiting for the site owner to prepare the room to house equipment. | Adams County Government Center and City of Brighton previously had no access. Fiber is now run to their facility, though no equipment is installed or configured, as noted above. | City of Commerce City formerly used an outdated microwave link. They are now actively using the new fiber optic network. Southwest Adams County Fire currently uses an internet based VPN, limited to 1 Mbps. Once they have integrated the link to their own network, they will begin using improved access as noted above. | Each fiber link is operating at 1 Gbps, with connection to an Aggregation Point. The connections between Aggregation Points are operating at 10 Gbps. Since most individual links will carry more than one subscriber, each subscriber is provided 100 Mbps back to the aggregation points. Currently 2 subscribers are using 100 Mbps, and one subscriber is using 10 Gbps. The fourth will be using 100 Mbps when activated. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/a | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | ADCOM911 plans to continue deployment of the microwave and fiber optic networks that were part of the original plan and provide additional use besides the LTE system. For example, sites that will connect CAIs to the server applications housed at ADCOM911, sites that can be used for LMR and NextGen 911 backhaul, etc. ADCOM911 is hopeful FirstNet will grant use of the spectrum and resolve questions pertaining to the proposed conditions. If so, our project can proceed according to the original plan. If not, ADCOM911 will potentially re-scope the project to deploy additional broadband access which was not part of the original project plan. | Adams County Communications Center, Inc. | We are at a difficult juncture in our overall project, forcing us to a near standstill. We have enough money remaining in the grant to either finish our original LTE project, or repurpose the funds to expand additional Broadband connectivity throughout the County. If we repurpose the funds for Broadband expansion and are later notified we can proceed with LTE, we wonâ€™t have the funds needed to finish the LTE project. Because of this, we are waiting to hear the status of our LTE deployment, and we are only working on those aspects of the Broadband network that could be used whether LTE moves forward or not. We have begun negotiation with FirstNet to obtain a lease for the use of the 700 Mhz spectrum, Firstnet began group negotiations with the 7 original BTOP recipients in order to determine a set of common terms and conditions for use of the spectrum. Firstnet, along with the 7 BTOP recipients formulated a rough draft spectrum lease agreement. Currently each of the BTOP recipients are negotiating independently with Firstnet to finalize an agreement specific to each project. Until this negotiation process is complete we cannot request that NTIA remove the suspension of the funds related to LTE. | ADCOM911 is hopeful the FirstNet Board will grant use of the spectrum, and resolve the outstanding questions regarding the conditions. If so, ADCOM 911 will need to redirect some amount of funds and staff time to the restart of the contract and project. However, the overall project would then be able to proceed according to the original plan, though project timelines will shift outside the original scope. If not, ADCOM911 will need to re-scope the project to deploy additional broadband access which was not part of the original project plan. If this occurs, the project plan will need to be revised, along with the budget. Additional EA work will need to be performed, potentially new agreements established, and existing agreements may need to be revised in anticipation of delayed deployment. Additional delays will occur until a decision regarding LTE deployment is reached. Adcom will also need to complete and submit the paperwork necessary to extend the grant timeline. | TRUE
NT10BIX5570157 | 2013 | Q2 | Q2 - 2013 | During the second quarter of 2013 ADCOM911 maintained its focus on site development and backhaul network development. We completed power installation for the new monopole and equipment installed at the Station 54 microwave site. At the Cherokee aggregation site, we have been in talks with the City of Northglenn to obtain the easements needed to pull the existing fiber from the street into the equipment building. These talks are proceeding well, and we expect the easement to be granted at the next City Council meeting. We solicited bids from 3 companies to provide security systems at the three tower sites operated by ADCOM911. The Justice Center site has had fiber installed for some time, but the site owner did not have rack space or power available for our equipment. During the quarter, the site owner completed both requirements, so our fiber aggregation router was installed and configured. This router will provide service to the CAI located at the site, and will serve as an interconnection point for several additional microwave links. In addition, we began discussions with Weld County which borders Adams County directly to the North about the possibility of connecting their broadband network to ours using the above mentioned router. We have also been working with representatives of Jefferson County in order to plan for expansion of fiber infrastructure into further areas of the Denver metro area. If we repurpose our grant funds solely for broadband expansion, we can pursue both of these options to interconnect additional Community Anchor Institutions for the purposes of Public Safety cooperation. Finally our negotiations with FirstNet representatives continued throughout the quarter to obtain a lease of the 700 Mhz Public Safety Broadband Spectrum. These negotiations were still ongoing by the close of the quarter. We intend to complete negotiations early in the third quarter, so we can submit a revised project plan and budget to move forward with our project. | 43 | 0 | 90 | 0 | 5 | 3 | 2 | 6 | No variance from previous quarter report. | N/A | No variance from previous quarter report. | N/A | No variance from previous quarter report. | No variance from previous quarter report. | No variance from previous quarter report. | The aggregation router was installed at the Justice Center site, and will allow for additional connectivity using both fiber and microwave paths. This is less than the projected deployment from our baseline report. This is due to ongoing uncertainty with the overall status of the LTE project. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 7 | 3 | 4 | 4 | 4 subscribers currently have equipment installed and configured and are actively using the connection today. 2 of the subscribers have equipment installed, and will be ready to begin use of the new link when they have integrated the link with their existing network. One remaining site has fiber installed, but does not have equipment installed yet. We are waiting for the site owner to prepare the room to house equipment. | Adams County Government center has fiber installed, though no equipment has been installed as noted above. The City of Brighton and the Adams County Justice Center now have fiber and routing equipment installed, where they had no access previously. | City of Commerce City formerly used an outdated microwave link. Brighton Police formerly used a T1 line. Southwest Adams County Fire currently uses an internet based VPN, limited to 1 Mbps. Once they have integrated the link to their own network, they will begin using improved access as noted above. | Each fiber link is operating at 1 Gbps, with connection to an Aggregation Point. The connections between Aggregation Points are operating at 10 Gbps. Since most individual links will carry more than one subscriber, each subscriber is provided 100 Mbps back to the aggregation points. Currently 2 subscribers are using 100 Mbps, and one subscriber is using 10 Gbps. The remainder will be using 100 Mbps when activated. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | ADCOM911 plans to continue deployment of the microwave and fiber optic networks that were part of the original plan and provide additional use besides the LTE system. For example, sites that will connect CAIs to the server applications housed at ADCOM911, sites that can be used for LMR and NextGen 911 backhaul, etc. ADCOM911 will conclude the SMLA negotiations with FirstNet, and will either resume the deployment of the Public Safety LTE network, or modify the grant toward additional broadband. If we modify the grant, we have already had preliminary discussions with surrounding counties to interconnect our networks, and further expand access among and between Public Safety CAI locations. | Adams County Communications Center, Inc. | We are at a difficult juncture in our overall project, forcing us to a near standstill. We have enough money remaining in the grant to either finish our original LTE project, or repurpose the funds to expand additional Broadband connectivity throughout the County. If we repurpose the funds for Broadband expansion and are later notified we can proceed with LTE, we wonâ€™t have the funds needed to finish the LTE project. Because of this, we are waiting to hear the status of our LTE deployment, and we are only working on those aspects of the Broadband network that could be used whether LTE moves forward or not. We continued negotiations with FirstNet to obtain a lease for the use of the 700 Mhz spectrum. By the close of the quarter, the negotiations were still ongoing. | ADCOM911 plans to conclude our negotiations with FirstNet regarding the SMLA early in Q3 2013. If the negotiation is successful, ADCOM911 will need to redirect some amount of funds and staff time to the restart of the contract and project. However, the overall project would then be able to proceed according to the original plan, though project timelines will shift outside the original period of performance. If the negotiations are unsuccessful, ADCOM911 will modify the project plan and budget for the remaining grant funds exclusively toward further expansion of a Public Safety broadband network in the metropolitan area that will service numerous Public Safety and Government facilities. In either case, ADCOM911 will submit a revised project plan and budget to the grants office for consideration to extend the original award period. The extension request may or may not be granted, and will take a minimum of 30 days to complete. Therefore, some activity may be stalled until the determination is made. | TRUE
NT10BIX5570157 | 2013 | Q3 | Q3 - 2013 | During the third quarter of 2013 ADCOM911 maintained its focus backhaul network development. We installed microwaves at the Adams County Justice Center, Front Range Airport, and the Hoyt Tower site. These microwaves will add additional network miles to our existing broadband network, providing new broadband service at the three locations. Additionally during the third quarter ADCOM911 concluded negotiations with FirstNet without coming to an amicable resolution regarding the language of the SMLA. Recently FirstNet has reached out to ADCOM911 again with the desire to further negotiate the terms of the SMLA. ADCOM911 is awaiting further information from FirstNet representatives. ADCOM911 requested an extension from the NTIA to move forward with the broadband portions of the BTOP Grant. The extension was granted on Sept. 11th 2013, and ADCOM911 began work to submit a route modification, revised budget, and revised project plan. | 91 | 0 | 90 | 0 | 5 | 6 | 2 | 6 | We installed 48 new network miles in the form of high speed microwaves during Q3 of 2013. | N/A | No variance from previous quarter report. | N/A | No variance from previous quarter report. | We installed 3 new microwave hops during Q3 of 2013. | No variance from previous quarter report. | No variance from previous quarter report. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 7 | 3 | 4 | 4 | 4 subscribers currently have equipment installed and configured and are actively using the connection today. 2 of the subscribers have equipment installed, and will be ready to begin use of the new link when they have integrated the link with their existing network. One remaining site has fiber installed, but does not have equipment installed yet. We are waiting for the site owner to prepare the room to house equipment. | Adams County Government center has fiber installed, though no equipment has been installed as noted above. The City of Brighton and the Adams County Justice Center now have fiber and routing equipment installed, where they had no access previously. | City of Commerce City formerly used an outdated microwave link. Brighton Police formerly used a T1 line. Southwest Adams County Fire currently uses an internet based VPN, limited to 1 Mbps. Once they have integrated the link to their own network, they will begin using improved access as noted above. | Each fiber link is operating at 1 Gbps, with connection to an Aggregation Point. The connections between Aggregation Points are operating at 10 Gbps. Since most individual links will carry more than one subscriber, each subscriber is provided 100 Mbps back to the aggregation points. Currently 2 subscribers are using 100 Mbps, and one subscriber is using 10 Gbps. The remainder will be using 100 Mbps when activated. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | ADCOM911 plans to complete the route modification, revised budget, and revised project plan and submit those documents to the NTIA for review. Assuming a timely acceptance of those plans ADCOM911 anticipates the release of an RFP, and the award of a contract for fiber optic construction, as well as microwave installation during the fourth quarter of 2013. ADCOM911 also plans to award a contract for site security, and hope to have that work completed during the fourth quarter of 2013. | Adams County Communications Center, Inc. | The SMLA negotiations with FirstNet, as well as the looming deadline of the BTOP Grant, presented a challenging landscape for ADCOM911 during the third quarter of 2013. Much of the planned work was put on hold until we had a solid understanding of the availability of funds moving forward. | While the LTE portion of the Grant was suspended during the third quarter of 2013 ADCOM911 focused it's efforts on developing plans to utilize the remaining Broadband funds to connect additional CAI's, and add additional network miles to our Broadband Network. At this juncture ADCOM911 is proceeding with plans to expend Grant funds for use in the Broadband Network. We will need to work closely with representatives of the NTIA to accomplish these goals. In particular in formulating a revised project plan, route modification, and a revised budget. | TRUE
NT10BIX5570157 | 2013 | Q4 | Q4 - 2013 | During the fourth quarter of 2013 ADCOM911 successfully concluded negotiations with FirstNet regarding the SMLA which will allow ADCOM911 to use the LTE spectrum, and operate the LTE network within Adams County. The agreement has been signed by both parties, and ADCOM911 began some preliminary work in ramping the LTE portion of our project back up. With this in mind ADCOM911 drafted a revised budget, and finalized the route modification needed to complete the project. ADCOM911 also selected a vendor to configure and install an upgraded security system, which will cover our location, as well as several of our key sites. This work will be completed in the 1st quarter of 2014. | 91 | 0 | 90 | 0 | 5 | 6 | 2 | 6 | No change since Q3. | N/A | No Change from Q3. | N/A | No Change from Q3. | No Change from Q3. | No Change from Q3. | No Change from Q3. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 8 | 3 | 5 | 4 | This is a change from Q3 2013, as one of the CAI's listed in the addendum (Adams County Sheriffs Office) had not been reported in previous PPR or APR's. The link had been established in 2011. I am unsure as to why the discrepancy exists, but that CAI was also not listed in the 2012 APR addendum. I have corrected that mistake and it will be accounted for in future reports. | No Change from Q3 | This is a change from Q3 2013, as one of the CAI's listed in the addendum (Adams County Sheriffs Office) had not been reported in previous PPR or APR's. The link had been established in 2011. I am unsure as to why the discrepancy exists, but that CAI was also not listed in the 2012 APR addendum. I have corrected that mistake and it will be accounted for in future reports. | No Change from Q3 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | ADCOM911 plans to complete the site security work here at our location, and several of the sites. We anticipate the release of the RFP for the fiber optic construction along E 120th Ave, and we also anticipate the selection of a vendor and the award of the contract. We hope to also select a vendor to bring the LTE system up to date with software revisions, and to begin the process of deploying the LTE antennas. We do not anticipate adding any new CAI's or network miles in the first quarter of 2014. | Adams County Communications Center, Inc. | ADCOM911 did not face any significant challenges during the 4th quarter of 2013, other than the planning and preparation for completing the LTE network. | ADCOM911 is confident that we can complete the project by the end of 2014, however there is a significant amount of work to be done to complete the project. ADCOM911 will need to work closely with representatives of the BTOP program in order to accomplish this task, in particular on the budget, the route modification, and any environmental work which may need to be completed. | TRUE
NT10BIX5570158 | 2010 | Q4 | Q4 - 2010 | LA-RICS Authority completed the Environmental Assessment procurement for the LASafetyNet Project. The LA-RICS Authority also received proposals from vendors in response to an RFP addendum that provided additional technical specifications for the broadband network. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zero variance. | N/A | Zero variance. | Zero variance. | N/A | Zero variance. | Zero variance. | Zero variance. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero variance. | Zero variance. | Zero variance. | Speeds not available because no system is not deployed | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Execute EA Agreement; initiate procurement for LTE engineering firm; complete evaluations for system RFP (vendor selection); initiate contract negotiations with vendor for system; submit draft EA to grantor. | Los Angeles Regional Interoperable Communications System Authority | N/A | N/A. | TRUE
NT10BIX5570158 | 2011 | Q1 | Q1 - 2011 | The LA-RICS Authority executed its Environmental Assessment (EA) contract on January 6, 2011, and the selected contractor, Ultrasystems Environmental, immediately began working on the EA for 260 sites. Procurement was initiated for the LTE engineering firm, with an RFP released on February 9, 2011, proposals received by February 23, 2011, evaluated, and a vendor was recommended to the JPA Board on March 3, 2011. Negotiations were initiated and are ongoing. Evaluations were completed for the system RFP, and negotiations ensued with the highest rated vendor. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | zero variance | N/A | zero variance | zero variance | N/A | zero variance | zero variance | zero variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero Variance | Zero Variance | Zero Variance | System is not yet deployed | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The Authority executive team will complete negotiations with an LTE system design/ build contractor and will forward a contract to the Board of Directors for review and approval. | Los Angeles Regional Interoperable Communications System Authority | N/A | N/A | TRUE
NT10BIX5570158 | 2011 | Q2 | Q2 - 2011 | The LA-RICS Authority submitted the Environmental Assessment on April 11, 2011. Negotiations continued with the highest rated vendor, including the services of our LTE Engineering contractor, Televate, who's contract was executed on April 18, 2011. Towards the end of the quarter, the County Counselâ€™s Office notified the LA-RICS Authority staff that they were conducting an evaluation of its procurement process. At this time, negotiations have been put on hold until County Counsel completes its evaluation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zero variance | N/A | Zero variance | Zero variance | N/A | Zero variance | Zero variance | Zero variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero variance | Zero variance | Zero variance | System is not yet deployed | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The Authority executive team will complete negotiations with an LTE system design/build contractor and will forward a contract to the Board of Directors for review and approval. The Authority will also issue a Request for Proposals for CEQA/Environmental Services as well as Project Management services. | Los Angeles Regional Interoperable Communications System Authority | Towards the end of the quarter, the County Counselâ€™s Office notified the LA-RICS Authority staff that they were conducting an evaluation of its procurement process. At this time, negotiations have been put on hold until County Counsel completes its evaluation. | Towards the end of the quarter, the County Counselâ€™s Office notified the LA-RICS Authority staff that they were conducting an evaluation of its procurement process. At this time, negotiations have been put on hold until County Counsel completes its evaluation. | TRUE
NT10BIX5570158 | 2011 | Q3 | Q3 - 2011 | On July 28, 2011, the LA-RICS Authority Board of Directors passed a motion to cancel the existing procurement. Per Counselâ€™s review, the original procurement for a turn-key system was not in compliance with California Public Contracts Code. On August 4, 2011, the Board directed staff to prepare a new Request for Proposal. Concurrent with the Boardâ€™s discussion regarding the procurement approach, the County of Los Angeles sponsored legislation, California Assembly Bill 946, to allow the Authority to use a solicitation process to award a contract for the design, construction and delivery of the system through a turn-key procurement. Assembly Bill 946 was approved in both the California Assembly and Senate and signed into law by the Governor on October 3, 2011. On October 6, 2011, the Board approved the release of a new RFP with the condition that legal counsel and a subcommittee of the Board review and approve the final version before it is issued. At this time, staff is making final changes to the RFP to present to legal counsel and the subcommittee for approval. We anticipated issuing the new LA-RICS RFP in the next couple weeks. In addition, the Authority issued a RFP for preparation of environmental documents in compliance with the requirements of the California Environmental Quality Act (â€œCEQA") (Public Resources Code Â§ 21000 et seq.) and the National Environmental Policy Act ("NEPA") (42 U.S.C. Â§ 4321 et seq.) on September 7, 2011. Proposals are due for t | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zero variance. | N/A | Zero variance. | Zero variance. | N/A | Zero variance. | Zero variance. | Zero variance. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero variance. | Zero variance. | Zero variance. | System is not deployed yet. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Next quarter, the LA-RICS Authority will have issued the Telecommunications Request for Proposal and the Project Management Request for Proposals. In addition, there will be a new contract for environmental documentation services. | Los Angeles Regional Interoperable Communications System Authority | As stated above, the existing procurement was canceled due to legal issues. | We do not anticipate any further challenges next quarter. | TRUE
NT10BIX5570158 | 2011 | Q4 | Q4 - 2011 | The Authority released a new Request for Proposal (RFP) for the Telecommunications System on November 8, 2011, which completely recast the site selection process for the LTE Broadband Mobile Data Network. Vendors interested in submitting proposals were required to only use the sites provided in the Site Selection List. On November 17, 2011, the Authority received proposals in response to the Environmental Documentation Services RFP released on September 7, 2011. The Authority completed evaluation and selected an environmental firm to present to the Board for contract approval. On December 6, 2011, the Authority released an RFP for Project and Construction Management Services. Proposals are due January 19, 2012. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Due to canceled procurement. | N/A | Due to canceled procurement. | Due to canceled procurement. | N/A | Due to canceled procurement. | Due to canceled procurement. | Zero variance. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero variance. | Zero variance. | Zero variance. | System not deployed yet. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The LA-RICS Authority anticipates: 1) Completion of Telecommunications System RFP evaluation; 2) Initiation of Telecommunications System negotiations; 3) Selection, negotiation and contract execution for a project management firm; 4) Environmental site analysis/studies. | Los Angeles Regional Interoperable Communications System Authority | As discussed in the last quarter report, the Authority canceled its procurement process on July 28, 2011 due to noncompliance with the California Public Contracts Code. In order to remedy the compliance issues, the County sponsored State legislation. In addition, the Authority pursued a prescriptive approach in the new RFP after discussions with NTIA. By using a prescriptive approach in the new RFP, project staff will be able to work on the NEPA/CEQA documents and permitting process concurrent with the Telecommunications System procurement process. This will greatly enhance efficiency and decrease the time required to complete the NEPA/CEQA process. | We do not anticipate any further challenges next quarter. | TRUE
NT10BIX5570158 | 2012 | Q1 | Q1 - 2012 | The LA-RICS Authority received proposals for the Telecommunications System RFP on January 3, 2012. The Evaluation Team has completed its review of the proposals and the LA-RICS Authority initiated negotiations on contract terms and conditions on March 20, 2012. The LA-RICS Authority also received proposals on January 19, 2012 in response to the Project and Construction Management Services RFP. After completing evaluations and negotiations, the LA-RICS Authority executed a contract with a project and construction management firm on March 29, 2012. The selected firm will monitor and manage all aspects of the LA-RICS project including schedules, budgets, system architecture, contractors and site related activities. The additional project management expertise and experienced staff will help ensure that the LA-RICS project meets all critical milestones and deadlines. The LA-RICS Authority is also making progress on the environmental assessment of sites. This past quarter, the LA-RICS Authority completed field visits to collect data for 255 sites; provided NTIA with a draft project description; commenced outreach to local jurisdictions; and compiled a site database for analysis and preparation of technical reports. Preliminary drafts of technical reports are currently being prepared. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Due to canceled procurement | N/A | Due to canceled procurement | Due to canceled procurement | N/A | Due to canceled procurement | Due to canceled procurement | Zero variance. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero variance. | Zero variance. | Zero variance. | System not deployed yet. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | On April 2, 2012, Assistant Secretary Larry Strickling notified LA-RICS that NTIA will issue a suspension on the purchase of LTE equipment. LA-RICS has suspended negotiations until further notice from NTIA and is currently analyzing the impacts of this information. | Los Angeles Regional Interoperable Communications System Authority | On February 22, 2012, HR 3630 became law. The LA-RICS Authority is reviewing the legislation to determine potential impacts given the establishment of FirstNet by August 22, 2012. | LA-RICS anticipates addressing issues that arise from the suspension in equipment purchases. At this time, LA-RICS is waiting for formal written notification. | TRUE
NT10BIX5570158 | 2012 | Q2 | Q2 - 2012 | No significant updates at this time. The LA-RICS Authority has placed the procurement on hold in order to address the partial suspension from the NTIA on LTE related equipment purchases. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Procurement process on hold. | N/A | Procurement process on hold. | Procurement process on hold. | N/A | Procurement process on hold. | Procurement process on hold. | Procurement process on hold. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero variance. | Zero variance. | Zero variance. | System not deployed yet. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The LA-RICS Authority is currently considering different procurement options to address the partial suspension on LTE-related equipment purchases. We anticipate releasing an addendum or a new Request for Proposal in the next quarter to address the changes in our proposed specifications. | Los Angeles Regional Interoperable Communications System Authority | On February 22, 2012, President Barack Obama signed into law the Middle Class Tax Relief and Jobs Initiative of 2012 (HR 3630). In light of this legislation, on April 2, 2012, verbal notification was received from the Department of Commerce (DOC) indicating a freeze on the LA-RICS Authorityâ€™s ability to spend Broadband Technology Opportunity Program (BTOP) grant funds pending a determination of FirstNet system architecture for the Nationwide Public Safety Broadband Network. Written notice was sent to both proposers on April 4, 2012, informing them of the suspension of negotiations. On May 11, 2012, formal notification was received from the DOC clarifying their April 2nd directive. The suspension was further continued on May 11, 2012, based on the written notification from DOC. The LA-RICS Authority is continuing to work with DOC to clarify what portions of the LTE broadband project may proceed and which portions must remain suspended. At this time, the LA-RICS procurement is still on hold until the LA-RICS Authority determines the best option in moving forward with the procurement process. | The LA-RICS Authority is determining the best strategy in moving forward with the procurement. The Board of Directors may decide to issue an addendum or a new Request or Proposal to address the LTE-related equipment that was included in the proposed system specifications which now is affected by the partial suspension from DOC. | TRUE
NT10BIX5570158 | 2012 | Q3 | Q3 - 2012 | No significant project accomplishments at this time. The LA-RICS Authority canceled its System procurement in August 2012 in order to address the significant changes mandated by H.R. 3630, and subsequently opted for issuance of separate procurements for the LMR and LTE system components; a new Request for Proposal (RFP) for the LMR system will be released on October 25, 2012 while the RFP for the LTE system remains in draft mode, pending FirstNet's determination of how the BTOP projects can support the development of the nationwide public safety broadband network. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Procurement process on hold. | N/A | Procurement process on hold. | Procurement process on hold. | N/A | Procurement process on hold. | Procurement process on hold. | Procurement process on hold. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero variance | Zero variance | Zero variance | System not deployed yet | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | With the suspension of LTE equipment purchase still in place, LA-RICS will continue working on drafting of the RFP for the LTE system and evaluation of LTE sites for environmental requirements. | Los Angeles Regional Interoperable Communications System Authority | The LA-RICS staff recently began the preparation of the RFP for the LTE system and is anticipating guidance from FirstNet on the system architecture for the Nationwide Public Safety Broadband Network. | The progress of the RFP preparation for the LTE system relies on guidance from FirstNet to comply with the system architecture for the Nationwide Public Safety Broadband Network. | TRUE
NT10BIX5570158 | 2012 | Q4 | Q4 - 2012 | As reported previously, the LA-RICS Authority decided to cancel the second procurement for a telecom contractor. Separate procurements will be conducted for the Long Term Evolution (LTE) and Land Mobile Radio (LMR) systems. LA-RICS staff immediately started working on the RFP draft for the LTE system and it should be substantially complete for FirstNet review by Feb, 2013. The RFP for the LMR system was completed and released in October, 2012 and proposals are currently being evaluated. Negotiations should be completed by May, 2013 and a contract is expected by Jun, 2013. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Procurement process on hold. | N/A | Procurement process on hold. | Procurement process on hold. | N/A | Procurement process on hold. | Procurement process on hold. | Procurement process on hold. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero variance | Zero variance | Zero variance | System not deployed yet | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The RFP for the LTE system should be substantially complete and ready for FirstNet review by Feb, 2013, and available for industry review by the first week of March, 2013. | Los Angeles Regional Interoperable Communications System Authority | N/A | The progress of the RFP preparation for the LTE system may be impacted if FirstNet's nationwide system design is not released by Feb, 2013. | TRUE
NT10BIX5570158 | 2013 | Q1 | Q1 - 2013 | FirstNet released in February, 2013 a draft of the lease agreement for the use of the public safety broadband spectrum. LA-RICS participated with other BTOP grantees in reviewing with FirstNet the draft terms and conditions. The agreement's final terms and conditions will be incorporated in the RFP for the LTE system that is currently being developed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | Procurement process on hold. | Procurement process on hold. | N/A | Procurement process on hold. | Procurement process on hold. | Procurement process on hold. | Procurement process on hold. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero variance | Zero variance | Zero variance | System not deployed yet | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | LA-RICS will continue to seek NTIA approval for separate submission of CEQA documents which can help fast track the environmental review process. After the spectrum lease agreement is executed, preparation of the RFP-LTE system should proceed faster. LA-RICS will submit a request to extend the performance deadline of its BTOP grant, as well as request the lifting of the partial suspension on BTOP funds. | Los Angeles Regional Interoperable Communications System Authority | The LA-RICS environmental team has been seeking ways to expedite the review process and got a big boost when AB 1486 was approved. The new law grants statutory CEQA exemption on sites LA-RICS plans to use in its LTE network. This is a unique opportunity to save precious time so LA-RICS reached out to NTIA with a modified approach to submit CEQA documents separately from the NEPA documents. LA-RICS also requested more discussions on the merits of its proposal but the quarter ended without a decision from NTIA. | Planned progress will be impacted by the following: 1. NTIA denial of LA-RICS modified CEQA/NEPA approach 2. If the spectrum lease agreement is not executed within the 90-day period set by FirstNet | TRUE
NT10BIX5570158 | 2013 | Q2 | Q2 - 2013 | The NTIA denied the LA-RICS proposal for a separate environmental process and gave instructions to complete the CEQA process first before proceeding with NEPA. This may prove problematic because if any of the proposed 255 LTE sites requires any kind of a CEQA process, the process is put on hold, thus putting NEPA on hold. To avoid this scenario, LA-RICS re-examined the site list to identify which sites may delay CEQA and dropped them from the list. This reduced the site list to 232. However, LA-RICS staff needs to conduct new studies to determine how the revised site list is going to affect network coverage and if replacement sites will need to be located. During this quarter, LA-RICS completed the final draft of the site access agreement it needed to execute with cities owning potential LTE sites. The LA-RICS Joint Powers Authority (JPA) Board approved the draft and authorized the initiation of consultation with the cities. Also, LA-RICS concluded negotiations with FirstNet for the Spectrum Management Lease Agreement and finalized a draft agreement. The LA-RICS Joint Powers Authority and the FirstNet Board approved the draft agreement in their separate meetings. The agreement is scheduled to be executed in the next quarter. The draft of the Request for Proposal (RFP) for the LTE system is in the final stages and is expected to be completed early in the next quarter. After the LA-RICS JPA Board approves release of the RFP, the procurement process will soon follow. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | Procurement process on hold | Procurement process on hold | N/ N/A | Procurement process on hold | Procurement process on hold | Procurement process on hold | Procurement process on hold | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero variance | Zero variance | Zero variance | System not deployed yet | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | During the next quarter, LA-RICS plans to accomplish the following: â€¢Complete execution of the Spectrum Management Lease Agreement with FirstNet Provide all required documentation for the NTIA to lift the suspension on the BTOP award and extend the performance period of the grant â€¢ Complete the final draft of the RFP for the LTE system and begin the procurement process â€¢ Begin consultation with cities for site access agreements for LTE sites | Los Angeles Regional Interoperable Communications System Authority | After the solution proposed by LA-RICS to expedite the environmental process was denied, the timeline to complete the project within the grant performance period became even more challenging. | Staff needs to conduct more studies on how the reduced site locations will affect network system coverage; replacement sites may have to be identified, preferably CEQA compliant locations. Please note: In the next section for Infrastructure Budget Execution Details, under the column for Actuals from Project Inception, the Matching Funds for Administrative and legal expenses amount of $1,973,913 is lower than the amount of $2,067,680 reported in the previous quarter. This is caused by an adjustment to reclassify previously reported expenditures from Administrative and legal expenses into Architectural and engineering fees. | TRUE
NT10BIX5570158 | 2013 | Q3 | Q3 - 2013 | On July 1, 2013, LA-RICS executed a Spectrum Management Lease Agreement with FirstNet. This was followed by the NTIA lifting of the partial suspension on the BTOP award on August 9, 2013. On the procurement for the LTE system contractor, LA-RICS completed preparation of its RFP #008. The RFP was released on August 13, 2013, followed by a proposers' conference on August 22, 2013. LA-RICS accepted questions from proposers until August 29, 2013 and set the deadline for submitting proposals on October 2, 2013. Preparation for the upcoming proposal evaluation process began with the orientation of subject matter experts. Drafts of site access agreements were distributed to City Managers relating to respective LTE sites. Initial meetings and language negotiations relating to site access agreements are in progress. As part of community outreach work, meetings were held with representatives of 30 communities. Presentations were made followed by productive discussions, which gave communities a better understanding of the LA-RICS project. Environmental assessment, including discussions with the federal environmental team are ongoing. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Procurement delays and suspension of LTE activities caused the variance from the baseline plan; however, a new procurement is nearing completion and the suspension has been lifted. | Procurement delays and suspension of LTE activities caused the variance from the baseline plan; however, a new procurement is nearing completion and the suspension has been lifted. | Zero variance | Pending system deployment. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | During the next quarter, LA-RICS plans to accomplish the following: Complete the evaluation of vendor proposals Begin negotiation with selected vendor Continue outreach with cities and agencies for site access agreements for LTE sites. Complete and submit award action requests for budget modification and route modification plan. | Los Angeles Regional Interoperable Communications System Authority | Upon successful negotiations with FirstNet for the SMLA, and lifting of the partial suspension by NTIA, LA-RICS moved forward expeditiously for release of the LTE RFP, as required by the aggressive timeline resulting from the performance period of our grant. | N/A | TRUE
NT10BIX5570158 | 2013 | Q4 | Q4 - 2013 | The procurement for the construction and deployment of the LTE system is proceeding well. After the October 2, 2013 deadline for submitting proposals expired, the LA-RICS team worked expeditiously to begin the evaluation process. The lead bidder's proposal was compared with the LA-RICS cost estimate and compliance analyses were conducted. On November 25, 2013, negotiations with the lead bidder began. The procurement process is expected to be completed early in the next quarter. Progress continue to be made in consultations with cities on site access agreements; comments and edits were incorporated into the working draft of the agreement. To address the question of cost participation for subscribers, a team of consultants began working on developing a funding plan. Questionnaires were sent to members to determine, among other things, frequency uses current system in place, the number of radios and data usage. Workshops were also conducted to cover additional questions and requests for clarification. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | Pending contract execution with selected LTE contractor. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Procurement delays and suspension of LTE activities caused the variance from the baseline plan; however, a new procurement is nearing completion. | Procurement delays and suspension of LTE activities caused the variance from the baseline plan; however, a new procurement is nearing completion. | Zero variance. | Pending system deployment. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | uring the next quarter, LA-RICS anticipates concluding negotiations with the lead bidder and presenting to the Board a contract for approval. After the LA-RICS Board approves the contract, a notice to proceed will be issued to the vendor and work on the LTE system project can finally begin. | Los Angeles Regional Interoperable Communications System Authority | The BTOP team has been providing guidance on eligible expenditures discussed during negotiations with the lead bidder and this is an area where continued assistance will be helpful. | In anticipation of executing a contract with the lead bidder and subsequent start of the LTE project, the BTOP program could help by upgrading the award from its current "agency review" status; this would enable LA-RICS to drawdown advance funds to help meet the expected increase in cash expenditures. | TRUE
NT11BIX5570001 | 2010 | Q3 | Q3 - 2010 | The grant for the CBOCES/EAGLE-Net was officially announced on September 13, 2010. Due to the timing of the award, there were no requests for federal funds during the quarter ended September 30, 2010. Key milestones for specific areas include: OVERALL PROJECT: â€¢ The EAGLE-Net website (www.co-eaglenet.net) was immediately updated with the award information, BTOP related activities, and additional information available to the community and vendors. Public relations and outreach activities were conducted to share the news of the award as well as informing partners, customers, and supporters. Activities included a press conference with news media, and a variety of calls and meetings with groups such as the Colorado Department of Education, the Colorado Education Association, Colorado School Board Association, Colorado Association of School Executives, Colorado BOCES Association, and the Rotary Club. â€¢ Meetings were held with project management, consulting, and engineering firms to begin the process of engaging a firm to conduct the Environmental Assessment. â€¢ As outlined in the grant, an Intergovernmental Agreement was executed creating EAGLE-Net as a free standing intergovernmental agency. A resolution transferring the grant from Centennial Board of Cooperative Educational Services (CBOCES) to EAGLE-Net was approved by the CBOCES Board. The NTIA transfer process was initiated and we are awaiting completion of this process. â€¢ EAGLE-Net continues to develop and revie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | The next quarterâ€™s activities will continue to focus on development of the organization resources required for implementation of the grant as well as completing RFPs and the finalization of contracts with vendors. Federal expenditures during the next quarter reporting period are estimated at $6,000,000 to pay for professional services associated with the activities described below. Key milestones for specific areas include: OVERALL PROJECT: â€¢ Completion of the NTIA name transfer is a key activity, along with the development of the organizational structure of EAGLE-Net to accommodate grant implementation activities, reporting, and other compliance requirements. â€¢ Community Outreach to inform partners, supporters, customers, and potential customers of the projectâ€™s progress will continue to be a key activity. A newsletter targeting school districts will be developed. NETWORK DESIGN: â€¢ The Environmental Assessment is the key activity on which weâ€™ll be focusing. The requirements are being completed with a consulting/engineering firm and a contract will be completed this quarter. â€¢ Vendor selection and finalization of contracts to begin Project Management, Network Architecture and Design, Site and Route Surveys, and Network Equipment Design will continue to be a major focus this quarter. SITE PREPARATION: â€¢ Site and route surveys will begin as sections of the Environmental Assessment are completed. EQUIPMENT PROCUREMENT: â€¢ Equipment Procurement is anticipat | Eagle-Net Alliance | n/a | n/a | TRUE
NT11BIX5570001 | 2010 | Q4 | Q4 - 2010 | In the fourth quarter of 2010, one of the top priorities was to complete the Grantee Substitution request from the Centennial Board of Cooperative Educational Services (CBOCES) to the new entity, EAGLE-Net Alliance (EAGLE-Net). In order to make this transition as smooth as possible, no funds were spent and no federal funds were requested by the CBOCES for this grant in the fourth quarter. In our communications with the NTIA, it has been indicated to us and we expect the Grantee Substitution request to be fully completed in January 2011. At that time, as EAGLE-Net, we will begin to spend the necessary funds and fully expect to catch up to our budgeted completion estimates in the first quarter of 2011. As soon as the request has been approved, we have a core staff ready to be hired by EAGLE-Net as well as our business and operational support systems ready to be implemented, we have our Environmental Consultant selected and they are awaiting our word to begin work, and we have our Project Management/Network Design Team selected and ready to begin work. Although the above paragraphs might not sound like "accomplishments", the three important positives are that the Grantee Substitution is almost complete, we refrained from spending money under the CBOCES name to make the process easier and more clear-cut to follow the grant expenditures, and we laid the groundwork for the EAGLE-Net organization to begin and are ready to go with our Environmental and Network Design consultan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Due to the previously described delays in the Network Design, no new network miles were deployed. Therefore, we are behind our baseline target of 117 new deployed miles. | Due to the previously described delays in the Network Design, no new network miles were leased. Therefore, we are behind our baseline target of 148 new leased miles. | Due to the previously described delays in the Network Design, no new network miles were upgraded. Therefore, we are behind our baseline target of 19 upgraded miles. | n/a Consistent with the baseline report. | Due to the previously described delays in the Network Design, no new fiber miles were deployed. Therefore, we are behind our baseline target of 102 fiber miles. | Due to the previously described delays in the Network Design, no new wireless links were installed. Therefore, we are behind our baseline target of 9 new wireless links. | Due to the previously described delays in the Network Design, no new towers were constructed. Therefore, we are behind our baseline target of 10 new towers. | Due to the previously described delays in the Network Design, no new fiber miles were deployed. Therefore, we are behind our baseline target of 102 fiber miles. Due to the previously described delays in the Network Design, no new wireless links were installed. Therefore, we are behind our baseline target of 9 new wireless links. Due to the previously described delays in the Network Design, no new towers were constructed. Therefore, we are behind our baseline target of 10 new towers. Due to the previously described delays in the Network Design, no new or upgraded interconnection points were completed. Therefore, we are behind our baseline target of 11 new interconnection pointsd delays in the Network Design, no new fiber miles were deployed. Therefore, we are behind our baseline target of 102 fiber miles. Due to the previously described delays in the Network Design, no new wireless links were installed. Therefore, we are behind our baseline target of 9 new wireless links. Due to the previously described delays in the Network Design, no new towers were constructed. Therefore, we are behind our baseline target of 10 new towers. Due to the previously described delays in the Network Design, no new or upgraded interconnection points were completed. Therefore, we are behind our baseline target of 11 new interconnection points. | 0 | 0 | 0 | n/a There are no agreements signed through the fourth quarter, which is consistent with our baseline target. | n/a As no build has yet been completed, no services were being provided by this project in the fourth quarter. Therefore, there is no pricing list attachment, no services were being provided by this project in the fourth quarter. Therefore, there is no pricing list attachment. | n/a No build has yet been completed so there is no network operation. | 0 | 0 | 0 | 0 | Consistent with the baseline target. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a No operating network so no speed tiers. | 0 | 0 | 0 | 0 | Due to the previously described delays in the Network Design, no subscribers were being served in the fourth quarter. Therefore, we are behind our baseline target of 259 subscribers. | Due to the previously described delays in the Network Design, there were no subscribers receiving new access in the fourth quarter. Therefore, we are behind our baseline target of 54 subscribers receiving new access. | Due to the previously described delays in the Network Design, there were no subscribers receiving improved access in the fourth quarter. Therefore, we are behind our baseline target of 205 subscribers receiving improved access. | n/a No operating network so no speed tiers. | 0 | 0 | 0 | 0 | 0 | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | 0 | 0 | 0 | 0 | 0 | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a Consistent with the baseline report. | n/a No services being provided yet. | FALSE | n/a | The number one accomplishment will be the completion of the Grantee Substitution from CBOCES to EAGLE-Net. This will allow us to begin appropriate expenditures and request reimbursements. EAGLE-Net will hire its core staff and set up its business and operational support systems. We will also engage the selected consultants to begin the Environmental Assessment and the Network Design work. During the quarter as these tasks are underway, we will be able to initiate site preparation and begin some equipment procurement, deployment and testing for peering sites. These items will be substantially complete during the next quarter. | Eagle-Net Alliance | Although listed under accomplishments, the time involved in the Grantee Substitution process obviously had an impact on our project's timeline. Our NTIA Federal Program Officer has been very helpful throughout the process and and while this process was not completed during the fourth quarter we anticipate it will be complete in January 2011. | Once the Grantee Substitution process has been completed, we will expedite things to the best of our ability while still making sure that we adhere to good business procedures and decisions. We are confident that because of the groundwork and preparation that was laid this quarter, we will be able to catch up in the near future. | TRUE
NT11BIX5570001 | 2011 | Q1 | Q1 - 2011 | In the first quarter of 2011, the grantee substitution process was completed on February 22 to transfer the grant from the Centennial Board of Cooperative Educational Services (CBOCES) to EAGLE-Net Alliance. While this was our single largest accomplishment, it has to be tempered with the fact that it had been a five month process, a long time frame that neither we nor the NTIA anticipated. In order to keep the process as clean as possible for both EAGLE-Net and the CBOCES, it was determined that no grant dollars would be spent until after the process was completed. Ultimately a new grant number was issued and the old grant number was able to be closed with no dollars spent, and all expenditures and project performance goals are now being tracked against the new grant number . The unexpected delay related to the transfer and new grant number issuance put us behind both our baseline milestones as well as our projections on the previous Performance Progress Report. Once the transfer was complete and we could spend grant funds, accomplishments included: -starting to hire our core staff; 11 employees were hired in March -leasing office space to accommodate our current staff as well as future growth -officially hiring our Environmental Assessment, Project Management and Logical Network Design consultants to begin work -formalizing and implementing our management process and controls (e.g. change control, risk management, issues management) -submitting and receiving approv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Due to the previously described delays in the Network Design, no new network miles were deployed. Therefore, we have not achieved our baseline target of 272 new deployed miles. | Due to the previously described delays in the Network Design, no new network miles were leased. Therefore, we have not achieved our baseline target of 345 new leased miles. | Due to the previously described delays in the Network Design, no existing network miles were upgraded. Therefore, we have not achieved our baseline target of 44 upgraded network miles. | n/a. Consistent with baseline report | Due to the previously described delays in the Network Design, no new fiber miles were deployed. Therefore, we have not achieved our baseline target of 237 new fiber miles. | Due to the previously described delays in the Network Design, no wireless links were deployed. Therefore, we have not achieved our baseline target of 22 wireless links. | Due to the previously described delays in the Network Design, no towers were constructed. Therefore, we have not achieved our baseline target of 23 new towers. | Due to the previously described delays in the Network Design, no new fiber miles were deployed. Therefore, we have not achieved our baseline target of 237 new fiber miles. Due to the previously described delays in the Network Design, no wireless links were deployed. Therefore, we have not achieved our baseline target of 22 wireless links. Due to the previously described delays in the Network Design, no towers were constructed. Therefore, we have not achieved our baseline target of 23 new towers. Due to the previously described delays in the Network Design, no new or upgraded interconnection points were completed. Therefore, we have not achieved our baseline target of 26 new interconnection pointsd delays in the Network Design, no new fiber miles were deployed. Therefore, we have not achieved our baseline target of 237 new fiber miles. Due to the previously described delays in the Network Design, no wireless links were deployed. Therefore, we have not achieved our baseline target of 22 wireless links. Due to the previously described delays in the Network Design, no towers were constructed. Therefore, we have not achieved our baseline target of 23 new towers. Due to the previously described delays in the Network Design, no new or upgraded interconnection points were completed. Therefore, we have not achieved our baseline target of 26 new interconnection points. | 0 | 0 | 0 | n/a. There are no agreements signed through this quarter, which is consistent with the baseline report. | n/a. As no build has yet been completed, no services were being provided by this project in this quarter. Therefore, there is no pricing list attached, no services were being provided by this project in this quarter. Therefore, there is no pricing list attached. | n/a. No build has yet been completed, so there is no network operation in this quarter. | 0 | 0 | 0 | 0 | Due to the previously described delays in the Network Design, there are no signed agreements for new access. Therefore, we have not achieved our baseline target of 2 signed agreements. | n/a. Consistent with baseline report. | n/a. Consistent with baseline report. | n/a. | 0 | 0 | 0 | 0 | Due to the previously described delays in the Network Design, no subscribers were being served in this quarter. Therefore, we are behind our baseline target of 331 subscribers. However, as soon as the FONSI is received, we will have 345 subscribers with new and/or improved service. | Due to the previously described delays in the Network Design, no subscribers receiving access in this quarter. Therefore, we are behind our baseline target of 126 subscribers receiving new access. | Due to the previously described delays in the Network Design, no subscribers were receiving improved access in this quarter. Therefore, we are behind our baseline target of 205 subscribers receiving improved access. | n/a. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. | n/a. No services being provided yet. | FALSE | n/a. | The next quarter will be very important to catch up to many of the Baseline milestones. Activities will include: -Hiring of additional personnel to reach anticipated staff levels shown on the organizational chart -Submission of the Environmental Assessment Special Award Condition draft and anticipated approval within the quarter -Submission of the Overlap Special Award Condition paperwork and anticipated approval within the quarter -Submission of a re-programming Award Action Request to re-apportion match contributions and purchase the EAGLE-Net "legacy" network from the Centennial Board of Cooperative Educational Services -Transfer of accounting structure and historical data from the CBOCES to our financial management system -Completion of a Grants file structure in Google-Docs to allow easy online access along with secured access and authorizations -Completion of documentation and approval sheets for all required federal reporting -Completed contracts with school districts and other Community Anchor Institutions for new and upgraded services -Completion of the procurement process to obtain and sign a contract with a design/build firm to begin detailed design activity -Completion of the procurement process to begin purchase of network equipment based on the logical network design -Continuing outreach programs including a new edition of the EAGLE-Net newsletter, upgrades to the EAGLE-Net website, creating a "leave behind" brochure for local community visits, and es | Eagle-Net Alliance | Our main challenge was the extensive time taken to complete the Grantee Substitution process from the Centennial Board of Cooperative Educational Services to EAGLE-Net. We had anticipated that this process would be completed in January, but it was not officially signed until February 22nd. In fact, part of the process was to actually award us an entirely new grant number, which we did not expect. As a result, there were technical difficulties setting us up in the ASAP (Automated Standard Application for Payment) system, and we were not able to actually draw grant funds until the end of March, which was the end of this quarter. These factors prevented us from spending much money during the quarter, and put us behind in trying to make up time toward our baseline milestones as well as our prior Performance Progress Report expectations for this quarter. | The biggest challenge in the next quarter will be accelerating our progress to meet our baseline milestones. Regarding areas of assistance, our Environmental Assessment draft will be submitted in early May, so a quick response to review it and return it for modifications so that it can be approved as soon as possible would be a huge help to our timeline. Receiving our FONSI will be key to us making rapid progress to catch up to our baseline milestones. It will allow us to deploy equipment and immediately connect 345 community anchor institutions with new and/or improved service, as well as to begin the other build phases of our project. A second challenge will be the procurement of our design/build contractor. As of the end of the quarter, we are currently writing the requirements for this hire, but because of the size and complexity of this portion of the project, this hire may not be completed during the next quarter. However, we are working hard to coordinate the contracting of the design/build contractor with the receipt of the FONSI. Once the FONSI has been received and this contract is complete, we are confident that running concurrent activities in different parts of the state (the capability to do this will be one of the requirements of any contractor hired) will allow us to catch up to the baseline build milestones. A third challenge for the next quarter will involve the the completion of the procurement of network equipment purchases. The RFP is currently b | TRUE
NT11BIX5570001 | 2011 | Q2 | Q2 - 2011 | During the second quarter of 2011, significant accomplishments included: -Continuing to hire our core staff; 7 new employees were hired during this quarter. -Significant progress in our Environmental Assessment (EA). While we did not achieve our goal of a FONSI by the end of the quarter, all EA work was completed including a programmatic agreement (PA), although awaiting final approvals on the PA meant that the final EA was not submitted until July 6. -An NTIA site visit was successfully completed. -Both the logical network design and project schedule were substantially completed during this quarter. -Several Community Outreach programs were accomplished, including attending 11 conferences with higher education associations, meetings with community, education and business groups, the creation of a community outreach brochure, and two articles published in local newspapers, including the Denver Business Journal. Because of this success, our VP of Community Outreach and VP of Business Development were asked to lead a BTOP Best Practices call on EAGLE-Net's community outreach strategy and segmentation plan. -Completion of documentation and approval sheets for our required quarterly Federal reports. -Creation of a file structure in GoogleDocs for easy but secured online access to all grant related documents. All employees were trained on this system, and are migrating documents to the server. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Due to the previously described delays in the Network Design, no new network miles were deployed. Therefore, we have not achieved our baseline target of 525 new deployed miles. | Due to the previously described delays in the Network Design, no new network miles were leased. Therefore, we have not achieved our baseline target of 66 new leased miles. | Due to the previously described delays in the Network Design, no existing network miles were upgraded. Therefore, we have not achieved our baseline target of 86 upgraded existing miles. | n/a. Consistent with baseline report. | Due to the previously described delays in the Network Design, no new fiber miles were deployed. Therefore, we have not achieved our baseline target of 457 new fiber miles. | Due to the previously described delays in the Network Design, no new wireless links were deployed. Therefore, we have not achieved our baseline target of 42 new wireless links. | Due to the previously described delays in the Network Design, no new towers were constructed. Therefore, we have not achieved our baseline target of 44 new towers. | Due to the previously described delays in the Network Design, no new or upgraded interconnection points were completed. Therefore, we have not achieved our baseline target of 50 new interconnection points. | 0 | 0 | 0 | n/a. There are no signed agreements through this quarter. | n/a. As no build has net been completed, no services were being provided by this project in this quarter. Therefore, there is no pricing list attached. | n/a. No build has yet been completed, so there is no network operation in this quarter. | 0 | 0 | 0 | 0 | Due to the previously described delays in the Network Design, there are no signed agreements for new access. Therefore, we have not achieved our baseline target of 3 signed agreements. | n/a. Consistent with baseline report. | n/a. Consistent with baseline report. | n/a. | 0 | 0 | 0 | 0 | Due to the previously described delays in the Network Design, no subscribers were being served in this quarter. Therefore, we have not achieved our baseline target 448 total subscribers. | Due to the previously described delays in the Network Design, no subscribers were receiving new access in this quarter. Therefore, we have not achieved our baseline target 243 subscribers receiving new access. | Due to the previously described delays in the Network Design, no subscribers were receiving improved access in this quarter. Therefore, we have not achieved our baseline target of 205 subscribers receiving improved access. | n/a. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. | n/a. No services being provided yet. | FALSE | n/a. | There were several accomplishments that we were close to completing in June, but were extended into July. These, in addition to other planned accomplishments in the next quarter include: - Completion of Environmental Assessment and issuance of FONSI - Awarding of Design/Build Contract - Purchase of "Legacy" network from Centennial BOCES - Upgrade of legacy network to provide service to over 400 CAIs - Transfer of accounting structure and historical data from CBOCES to our financial management system, with upgrades for that system installed and implemented - Completion of IRU agreement with Platte River Power Authority; other IRUs in negotiation with some to be completed this quarter - Issuance of RFP and award of bid on layer 2/3 equipment - Continuing community outreach activities including meetings with county commissioners of several counties, attendance and participation in many professional meetings and conferences, development of a pre-launch/launch business development schedule coordinated with build schedule and creation of related communications templates, and tailoring of market segment communications for business development - Hiring of additional staff according to organizational plan - Moving into permanent office space | Eagle-Net Alliance | Our main challenge during the quarter was trying to complete the Environmental Assessment so that we could receive our FONSI. Many resources were used, including significant time from both our environmental consultant as well as EAGLE-Net personnel. While we tried as hard as possible to complete this by the quarter end of June 30, after submissions and reviews, we actually just received the FONSI clearance memo as this report was being submitted on July 29. | The biggest challenge is the wait for our FONSI to be issued. We have been moving forward with pre-FONSI activities as much as possible; e.g. design work with our Design/Build Contractor is well underway, IRUs are being negotiated, and equipment has been purchased to upgrade the legacy system. So the next major step is to begin the build phase of the project once the FONSI has been issued. With our start delayed about 5 months, our main challenge will then be to accelerate our progress to meet our baseline milestones. This will be planned with our design/build contractor, and that plan will begin to be implemented this quarter as soon as we receive the FONSI. | TRUE
NT11BIX5570001 | 2011 | Q3 | Q3 - 2011 | We achieved several significant accomplishments the last quarter, including: - The approval of our Environmental Assessment (EA) and issuance of our Finding of No Significant Impact (FONSI). - The awarding of the Design/Build contract to G4S Technology. - The purchase of the "legacy" network from the Centennial BOCES (Board of Cooperative Educational Services). This existing network serves as the platform from which the statewide network will grow. - The upgrade of the legacy network with new equipment which provided additional bandwidth to the network. - The connection of five new customers including four school districts, which added a total of 215 new CAIs. - The signing of three IRUs totaling 510 miles. These agreements are with the City of Longmont, Platte River Power Authority, and Tri-State Generation and Transmission Association. - The issuance by G4S Technology of two Requests for Information (RFI) for dark fiber and telecommunications network infrastructure in the state. - The issuance by G4S Technology of a Request for Proposal (RFP) for the purchase of optical fiber. This RFP was awarded to Draka Prysmian. - The awarding of the Layer 2-3 network equipment to IBM as the distributor of Cisco equipment. - The completion of the installation of the upgraded Financial System. - The hiring of three new EAGLE-Net Alliance core staff; one Project Manager and two accounting personnel. - Significant efforts in community outreach which included contact with all of our gran | 0 | 412 | 170 | 0 | 0 | 0 | 0 | 3 | No new network miles have yet been deployed This is behind our baseline projection of 798 miles because of the delays encountered with the grant transfer and in achieving the FONSI. | The 412 new network miles leased (via capital IRU) is behind our baseline projection of 1,011 miles because of the delays encountered with the grant transfer and in achieving the FONSI. Two RFIs were issued this quarter with the intent of specifically discovering existing fiber available to begin the procurement process of securing IRUs for those miles. | The 170 existing miles upgraded is ahead of the baseline projection of 130 miles because the legacy network was upgraded at one time instead of in stages. | n/a. Consistent with baseline report. | This is behind our baseline target of 695 new fiber miles as construction has not yet started due to the delays encountered with the grant transfer and achieving the FONSI. | This is behind our baseline target of 63 new wireless links because of delays encountered with the grant transfer and achieving the FONSI. | This is behind our baseline target of 66 new towers because of delays encountered with the grant transfer and achieving the FONSI. | This is behind our baseline target of 695 new fiber miles as construction has not yet started due to the delays encountered with the grant transfer and achieving the FONSI. This is behind our baseline target of 63 new wireless links because of delays encountered with the grant transfer and achieving the FONSI. This is behind our baseline target of 66 new towers because of delays encountered with the grant transfer and achieving the FONSI. This is behind our baseline target of 75 new interconnection points because of delays encountered with the grant transfer and achieving the FONSIt of 695 new fiber miles as construction has not yet started due to the delays encountered with the grant transfer and achieving the FONSI. This is behind our baseline target of 63 new wireless links because of delays encountered with the grant transfer and achieving the FONSI. This is behind our baseline target of 66 new towers because of delays encountered with the grant transfer and achieving the FONSI. This is behind our baseline target of 75 new interconnection points because of delays encountered with the grant transfer and achieving the FONSI. | 0 | 0 | 0 | This is behind our baseline target of five projected providers because of delays encountered with the grant transfer process and achieving the FONSI. | While we are not providing wholesale services yet, as part of the project we do intend to offer services including IP transport and adddrop capability at Peering Points and selected POIs to be used primarily for Internet service backhaule services yet, as part of the project we do intend to offer services including IP transport and adddrop capability at Peering Points and selected POIs to be used primarily for Internet service backhaul. | n/a. No third party is operating our network. | 0 | 0 | 0 | 0 | This is behind our baseline target of five projected providers because of delays encountered with the grant transfer process and achieving the FONSI. We should be caught up to the baseline projections by the second quarter of 2012. | n/a. Consistent with baseline report. | n/a. Consistent with baseline report. | n/a. | 539 | 215 | 324 | 1 | We are a little behind our baseline projection of 574 CAIs. This is due to the delays encountered by the grant transfer process and the resulting delays achieving our FONSI. | We are behind our baseline projection of 369 CAIs. This is due to the delays encountered by the grant transfer process and the resulting delays achieving our FONSI. | We are ahead of our baseline projection of 205 CAIs. | 1GB speed is available for each anchor institution. The network is capable of providing multiple 1GB or 10GB connections if requested. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | We are not providing any special offerings at this time. | FALSE | n/a. | The next quarter will see a flurry of activity toward the build of the network. This will include: - The closing of a Request for Information (RFI) asking for responses regarding state-wide infrastructure and resources. Based on the responses to this RFI, there will be Requests for Proposals (RFPs) issued as well as direct negotiations for resources in areas with only one respondent. The RFI responses will also aid G4S and EAGLE-Net in determining a more final design by identifying areas where build will be required because of the lack of existing infrastructure in certain parts of the state. So, design, RFPs and direct negotiations for Indefeasible Rights of Use (IRU) will all move ahead during this quarter. - The purchase of the network layer 2 and 3 equipment will begin. We will begin testing equipment in preparation for deployment. - The purchase of fiber for the fiber network build will begin. - Although ground will be broken in December, we don't anticipate deploying any new network miles this quarter. - We will have signed IRUs for an additional 250 leased network miles during this quarter. - We will provide service to 40 new CAIs during the quarter. - Due to the previously described delays, we don't anticipate having any signed agreements with broadband wholesalers or last mile providers during this quarter. - We will move to EAGLE-Net's permanent office space. The additional space will allow us to continue hiring according to our approved staffing plan as the | Eagle-Net Alliance | The biggest challenges were still related to the delays in obtaining the grant transfer and the approval of our statewide Envronmental Assessment. This five month delay caused a corresponding five month delay in receiving our FONSI and release from our environmental Special Award Condition (SAC), which was finally obtained on August 3. Many resources were used to reach this milestone, both within EAGLE-Net Alliance and from our vendors, but now with the FONSI issuance we can focus on catching up to our baseline projections. | The biggest challenge will be accelerating our progress to make up for the five month delay caused by the grant transfer process and the statewide Environmental Assessment approval process which resulted in a delay of our FONSI issuance. This next quarter will be a time of much designing, planning, negotiating and outreach in preparation for the main part of the physical build which will be in full force in subsequent quarters due to Colorado's winter weather. | TRUE
NT11BIX5570001 | 2011 | Q4 | Q4 - 2011 | Accomplishments in the 4th Quarter included: - Closing of RFI asking for statewide infrastructure and resources. - Issuance of 6 major RFPs based on RFI responses. - Completion of a new IRU agreement for 511 miles of dark fiber with the Zayo Group. - First purchase and receipt of layer 2 - 3 equipment. - First purchase and receipt of 100 miles of fiber. - Identification of warehouse/lab space for equipment storage and testing; lease to be signed in January. - Moved into our permanent office space. - Continued to hire and reorganize staff according to staffing plan; five new positions were filled this quarter, including a Project Manager, a System Administrator, a Grants Analyst, a Communications Coordinator and an Order Processing Coordinator. - Significant Community Outreach activities, including continuation of individual visits to CAIs across the state, continued partnerships with sister grants and other key programs in the state to cross-promote and support each others' efforts, collaborations with the State Office of Information Technology, the IT department of the Secretary of State, the Colorado Government Association for Information Technology and several other organizations, and the finalizing of a pilot program with the Rotary Club to enable them to assist local schools throughout the state with content flow through EAGLE-Net connectivity. | 0 | 923 | 170 | 0 | 0 | 0 | 0 | 3 | No new network miles have yet been deployed. This is behind our baseline projection of 973 miles because of the delays encountered with the grant transfer and in achieving the FONSI. | The 923 new network miles leased (via capital IRU) is behind our baseline projection of 1,233 miles because of the delays encountered with the grant transfer and in achieving the FONSI. While one new IRU was signed this quarter, 4 RFPs have just closed and new IRUs will be awarded shortly. | The 170 existing miles upgraded is ahead of of the baseline projection of 159 miles because the legacy network was upgraded at one time instead of in stages. | n/a. Consistent with baseline report. | This is behind our baseline target of 847 new fiber miles as construction has not yet started due to the delays encountered with the grant transfer and achieving the FONSI. | This is behind our baseline target of 77 new wireless links because of delays encountered with the grant transfer and achieving the FONSI. | This is behind our baseline target of 80 new towers because of the delays encountered with the grant transfer and achieving the FONSI. | This is behind our baseline target of 92 new interconnection points because of the delays encountered with the grant transfer and achieving the FONSI. | 0 | 0 | 0 | There are currently no agreements, which is behind our baseline target of six projected providers because of delays encountered with the grant transfer process and achieving the FONSI. | While we are not providing wholesale services yet, as part of the project we do intend to offer services including IP transport and add-drop capability at Peering Points and selected POIs to be used primarily for Internet service backhaul. | n/a. No third party is operating our network. | 0 | 0 | 0 | 0 | This is behind our baseline target of six projected providers because of delays encountered with the grant transfer process and achieving the FONSI. | n/a. Consistent with baseline report. | n/a. Consistent with baseline report. | n/a. | 467 | 206 | 261 | 1 | In our previous PPR we reported 539 CAIs, but that number has been adjusted to 467. The 539 CAIs originally reported included local government connections that we originally understood should be counted in this report. No new connections were made during this quarter. This number is behind our baseline projection of 656 CAIs due to the delays encountered by the grant transfer process and the resulting delays in achieving our FONSI. | In our previous PPR we reported 215 CAIs, but that number has been adjusted to 206 for the reason stated above. This is behind our baseline projection of 451 due to the delays encountered by the grant transfer process and the resulting delays in achieving our FONSI. | In our previous PPR we reported 324 CAIs, but that number has been adjusted to 261 for the reason stated above. This is ahead of our baseline projection of 205 CAIs. | The network is capable of providing 1 Gbps, multiple 1Gbps, and 10 Gbps connections based on the anchor institution requests. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | We are not providing any special offerings at this time. | FALSE | n/a. | Projected network accomplishments for the next quarter include: - The completion of 3 new IRUs based on awarded RFPs totalling about 550 miles. - A new RFP issued for infrastructure in the southeast quadrant of the state. - New RFPs issued and awarded for builds on the western slope and the southern portion of the state. - Awarding of the RFP contract for the build along I25 North. - Ground breaking and the start of construction on the I25 corridor. - Peering site deployments to begin. - A second order for layer 2 - 3 equipment. - Our focus will be on building out our peering sites, so don't anticipate connections to any new CAIs this quarter. - Due to the previously described delays, we don't anticipate having any signed agreements with broadband wholesalers or last mile providers during this quarter. Community Outreach activities for the next quarter will include: - A newly designed and more user-friendly website. - New communication and educational materials targeted to different segments of our CAIs; Education, Libraries, Government and Healthcare. - Hiring of Regional Community Representatives for many outreach sessions in different regions of the state. This includes community planning with with regional authorities, economic development councils, Department of Local Affairs, etc. - Coordinating efforts with other grants offering their services over our peering site connections. - Increased communications via webinar and remote presentations across all CAI segments. | Eagle-Net Alliance | The last quarter was one of playing catch-up due to the delays in obtaining the grant transfer and the approval of our statewide Environmental Assessment and FONSI, which was finally obtained on August 3. The timing of issuing an RFI and then 6 corresponding RFPs for state infrastructure, and then integrating that knowledge into our design was time consuming during a period when we were trying to make up lost time. However, we did have quite a bit of success, and continue to move forward and closer to our projections. | It's well documented that there were delays that occurred because of the grant transfer process and the statewide Environmental Assessment approval, and these delays challenge our timing when looking at the original Baseline Report projections. However, we have completed our planning and scheduling to ensure that we achieve all Project milestones. Our challenge is to stay on target with that schedule, and by doing so, we will complete the build on schedule and on budget. | TRUE
NT11BIX5570001 | 2012 | Q1 | Q1 - 2012 | Project accomplishments for the first quarter of 2012 included: - The issuance of 10 new Request for Proposals (RFPs) that were primarily for infrastructure solutions as well as for network construction. Six of these were awarded while the others are in the process of being finalized. Three different construction companies out of over thirty different respondents were awarded infrastructure and lateral build RFPs. - The signing of five new Indefeasible Rights of Use (IRUs) that added a total of 585 miles of dark fiber to the statewide fiber peering ring. The Zayo Group, FiberLink and AboveNet Communications were all awarded RFPs for existing infrastructure and all signed 20 year IRUs. - The continuing receipt of Layer 2 and 3 equipment from previously awarded RFPs. - The leasing of warehouse space for the storage, testing and staging of the Layer 2 and 3 equipment. Equipment was readied for April installation to the peering ring sites. - Many permits being obtained in preparation for the start of April construction. - Contracts signed with 19 new school districts for the next school year. These will be connected and the associated Community Anchor Institutions (CAIs) counted in the third quarter of the year. - Continuing community outreach activities including revamping the EAGLE-Net website to improve information availability and to make it more user friendly, meetings with Colorado Governor Hickenlooper and the staffs of the U.S. Senators and Representatives in addition to state Senators and Representatives, and more meetings with CAIs, local governments, local technology groups, and other interested parties. We also hosted visits from NTIA senior officials to discuss our project. | 0 | 1508 | 170 | 0 | 0 | 0 | 0 | 3 | No new network miles have yet been deployed. This is behind our baseline projection of 1,168 miles because of the delays encountered with the grant transfer and in achieving the FONSI. However, construction is on track to begin in April with an accelerated summer build schedule. | The 1,508 new network miles leased (via capital IRU) are ahead of our baseline projection of 1,480 leased miles. These miles constitute the majority of our network peering ring. | The baseline projection is for 190 miles through this quarter, so we are slightly behind that total. Work will be completed and we will be caught up in the next quarter. | n/a. Consistent with baseline report. | This is behind our baseline projection of 1,016 new fiber miles because of the delays encountered with the grant transfer and in achieving the FONSI. | This is behind our baseline projection of 92 new wireless links because of the delays encountered with the grant transfer and in achieving the FONSI. | This is behind our baseline projection of 95 new towers because of the delays encountered with the grant transfer and in achieving the FONSI. | This is behind our baseline projection of 110 new interconnection points because of the delays encountered with the grant transfer and in achieving the FONSI. | 0 | 12 | 0 | There are currently no agreements, which is behind our baseline projection of eight projected providers because of the previously described delays. However, now that we are near construction, we are in negotiations with 12 broadband wholesalers or last mile providers on Master Service Agreements. | While we are not providing wholesale services yet, as part of the project we do intend to offer services including Internet Protocol (IP) transport and add-drop capability at Peering Points and selected Points of Interconnect (POIs) to be used primarily for Internet service backhaul. | n/a. No third party is operating our network. | 0 | 0 | 0 | 0 | This is behind our baseline projection of 8 signed agreements because during this quarter we did not have network availability due to the delays encountered with the grant transfer and FONSI process. However, negotiations with providers have begun, and we anticipate having two signed service orders in the next quarter. | n/a. Consistent with baseline report. | n/a. Consistent with baseline report. | n/a. | 467 | 206 | 261 | 0 | No new subscribers were added this quarter, although several will be coming on board as we build to them in the third quarter. The 467 subscriber total is behind the baseline projection of 746, which is due to the holdup in building our infrastructure because of the delays encountered by the grant transfer process and the resulting delays in achieving our FONSI. | This is behind the baseline projection of 541 subscribers receiving new access due to the delays described above. | This is ahead of our baseline projection of 205. | The network is capable of providing 1 Gbps, multiple 1 Gbps, and 10 Gbps connections based on the anchor institution requests. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | We are not providing any special offerings at this time. | FALSE | n/a | Accomplishments in the 2nd quarter of 2012 will include: - The activation of all peering sites except for Cheyenne. - The start of physical construction consecutively in 5 parts of the state. These are I25 north, the Denver metro area, the Colorado Springs area, NorthEast Colorado, and along highway 160 and into the San Luis Valley. - The installation of layer 2-3 equipment at peering sites as well as at some CAIs. - The upgrade of 84 existing fiber miles with new equipment. - The purchase of a long term lease for 359 miles of dark fiber. - The new construction of an estimated 200 miles of new fiber. - Although agreements are signed, there will be 0 CAIs added in the next quarter as both turn-up and agreement dates will be for the third quarter of the year (July 1 or later). - The signing of Master Service Agreements with broadband wholesalers/last mile providers with at least two service orders to begin services in the third quarter. - Continued community outreach activities including a "Construction Kick Off" event at the state capital on April 16. Presenters included Colorado Governor John Hickenlooper, other state and NTIA officials and EAGLE-Net CEO Randy Zila. | Eagle-Net Alliance | The challenge has been trying to catch up after our initial delays. The size and the multifaceted nature of this project have made it difficult to make up the time that was lost waiting for the grant transfer and achieving the FONSI. Keeping to our aggressive schedule has been essential to insure that we hit our upcoming milestone of 2/3 complete by August 31, 2012. | The main issues will be the logistics of ramping up the physical construction simultaneously in several parts of the state. Obviously, this quarter and the next are key construction periods in Colorado to take advantage of mild weather. So far, we are moving according to our schedule with no unforeseen challenges. | TRUE
NT11BIX5570001 | 2012 | Q2 | Q2 - 2012 | Project accomplishments for the second quarter of 2012 included: - The deployment and activation of the main peering ring from which the statewide network will be connected. - The start of construction concurrently in several areas of the state, including along northern I-25 from Denver to Wyoming, the San Luis Valley, along southern highway 285 between Monte Vista and Saguache, parts of highway 160, and in the cities and towns of Denver, Aurora, Thornton, Colorado Springs, Fort Morgan, Walsenburg, La Veta, Calhan, Flagler, Bethune and others. - All RFPs for construction through the end of 2012 have been awarded. These will result in construction of both new fiber and wireless miles. - The signing of three new Indefeasible Rights of Use (IRU) agreements for a total of 71.3 miles. The agreements were with the Zayo Group, KenTec Communications and RebelTec Communications in three urban areas of the state. - Fiber being purchased on the existing contract to supply our build needs for the remainder of the year. - The initial order of the Layer 2 and 3 equipment was received and tested at our lab/warehouse space. The remaining contracted equipment has been ordered and will be arriving during the next quarter. - The continuation of team members driving across the state to meet with CAIs, regional and local governments, local technology groups and other interested parties. - Continuing to complete our staffing with the hiring of Regional Community Representatives who live in more rural areas outside of the Denver Metro area to represent EAGLE-Net and continue community outreach to local communities in their quadrants of the state. - The signing of 12 Master Service Agreements with local providers which are the framework to provide services and give them expanded bandwidth as construction is completed to their areas. - Hosting a scheduled NTIA site visit to discuss the status of our project. | 12 | 1579 | 254 | 0 | 12 | 0 | 0 | 31 | Although this is obviously far behind out baseline projection of 1440 miles, construction has now started in earnest and there were more than 150 miles of conduit laid this quarter. Fiber miles will be increasing dramatically during the next quarter. | Leased fiber miles are slightly behind the baseline projection of 1825 miles as 2 IRUs are currently in negotiation, but were not completed by the end of the quarter. | This amount is higher than our baseline projection of 235 miles. | n/a. Consistent with baseline report. | This is behind our 1254 baseline projection as conduit is now being laid and significant mile of new fiber will be completed during the next quarter. | This is behind our baseline projection of 114 new wireless links because of the initial delays encountered with the grant transfer and in achieving the FONSI. Wireless construction will begin in the next quarter. | This is behind our baseline projection of 116 new towers because of the delays encountered with the grant transfer and in achieving the FONSI. | This is behind our baseline projection of 136 new interconnection points because of the delays encountered with the grant transfer and in achieving the FONSI. However, significant number of new interconnection points will be added in the next quarter. | 12 | 10 | 0 | We have signed Master Service Agreements with 12 wholesale and last mile providers. The MSAs provide the framework for actual service agreements, of which we should have several in the next quarter as the network is built out. However, as of the end of June, there were no specific service orders from those agreements, which is behind our baseline projection of 10 for this quarter. | While we are not providing wholesale services yet, as part of the project we do intend to offer services including Internet Protocol (IP) transport and add-drop capability at Peering Points and selected Points of Interconnect (POIs) to be used primarily for Internet service backhaul. | n/a. No third party is operating our network. | 0 | 0 | 0 | 0 | Although we have providers primed to sign service agreements once construction is completed in their areas, due to the network construction delays, no service is currently being provided. This is behind our baseline projection of 10 signed service agreements. | n/a. Consistent with the baseline report. | n/a. Consistent with the baseline report. | n/a. | 467 | 206 | 261 | 0 | No new subscribers were added this quarter, leaving us behind our baseline projection of 872. The delays are due to the holdup in building our infrastructure because of the delays encountered by the grant transfer process and the resulting delays in achieving our FONSI. We do have several signed contracts that start service during the next quarter. | This is behind the baseline projection of 667 subscribers receiving new access due to the delays described above. | This is ahead of our baseline projection of 205. | The network is capable of providing 1 Gbps, multiple 1 Gbps, and 10 Gbps connections based on the anchor institution requests. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | We are not providing any special offerings at this time. | FALSE | n/a. | The next quarter will be key as network construction is now in full swing. Accomplishments should include: - The signing of 5 new IRUs signed for a total of at about 760 miles. - 1,017 network miles under construction with at least 450 completed with fiber and equipment installed. - 185 wireless miles completed and connected to the network. - Approximately 70% of our CAIs having access to the network. - Signed agreements with 10 more wholesale and last mile providers. - Signed agreements with 15 more CAI school districts. - Continuing presence throughout the state for community outreach activities. | Eagle-Net Alliance | Permitting has slowed progress in a few areas as the complexity and quantity of required permits has impacted the schedule. The good news is that so far, weather and the severe fires throughout the state have not had an impact. We are continuing our aggressive schedule to ensure that we achieve our upcoming milestone of 2/3 complete by August 31, 2012. | Although on track, permitting can always become a potential issue in a large project like ours. However, we don't anticipate any serious problems going forward. Also, in the next quarter we will be submitting a budget reprogram to more accurately reflect the cost categories and progress of the project as we move forward. | TRUE
NT11BIX5570001 | 2012 | Q3 | Q3 - 2012 | During the third quarter, there was significant progress in the build and implementation of the network, including: -The signing of two new Indefeasible Rights of Use (IRU) agreements for a total of 137.3 miles. -The deployment of up to 33 construction crews working in the state, creating a job FTE of 203.06. -Construction continued throughout the state and a total of 543 miles of conduit and 352 miles of fiber have been laid. -Level 2 and 3 equipment installed at 15 new peering sites. -60 new CAIs connected. -20 new contracts signed with school districts. -The signing of 9 new Master Service Agreements which are the framework to provide services as well as 6 service orders as a result of these agreements. -Continuing community outreach activities with CAIs, state, regional and local governments, local technology groups and other interested parties. | 352 | 1717 | 263 | 0 | 352 | 0 | 0 | 46 | Although behind our baseline projection of 1693 deployed miles, construction is moving forward rapidly. Conduit was laid for an additional 191 miles through September. | New leased fiber is behind our baseline projection of 2145 miles, as three IRUs were in negotiation last quarter, but only two were completed by the end of September. | This amount is slightly behind our baseline projection of 276 miles. Note that this is a correction of 254 miles previously reported. | n/a. Consistent with baseline report. | This is behind our baseline projection of 1474 miles. Construction is continuing on laying new fiber miles, and an area of wireless build will be completed next quarter. | Although there are several wireless links that were in the process of being deployed this quarter, none were completed by September 30. This is behind our baseline projection of 134 new wireless links. | This is behind our baseline projection of 134 new towers. | This is behind our baseline projection of 160 interconnection points due to the previously described delays in construction. | 6 | 16 | 6 | We have signed Master Service Agreements (MSAs) with 21 wholesale and last mile providers. The MSAs provide the framework for actual service agreements of which there were six executed in the last quarter. Our baseline projection was for twelve agreements, so we are behind that estimate. However, as we continue our build into other providers' areas, the MSAs signed will lead to service agreements. | We are providing transport to the IP transport for these providers. | n/a. No third party is operating our network. | 6 | 0 | 0 | 0 | Although behind our baseline projection of 12 signed agreements for service, we have the framework for several more agreements in place once we've completed out build to those specific areas. | n/a. Consistent with the baseline report. | n/a. Consistent with the baseline report. | n/a. | 527 | 266 | 261 | 0 | Sixty new CAIs were added this quarter. Although some of these CAIs are our contracted subscribers, others now have the access ability to connect if they choose to purchase service from us. We are still behind our baseline projection of 989 due to the holdup in building our infrastructure because of the delays encountered by the grant transfer process and the resulting delays in achieving our FONSI. | This is behind our baseline projection of 784 subscribers receiving new access due to the delays described above. | This is higher than our baseline projection of 205. | The network is capable of providing 1 Gbps, multiple 1Gbps and 10 Gbps connections based on the anchor institution requests. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | We are not providing any special offerings at this time. | FALSE | n/a. | Accomplishments during the fourth quarter will include: - Connection to more than 370 new CAIs. - Approximately 185 miles and 41 links of the wireless system connected to the network. - Approximately 650 total miles of fiber built. - The signing of one IRU for 72 additional miles. - Signed Master Service Agreements with 10 additional last mile providers throughout the state. - Continuing community outreach activities with CAIs, state, regional and local governments, local technology groups and other interested parties. | Eagle-Net Alliance | As in the previous quarter, permitting has slowed progress in a few areas as the complexity and quantity of required permits has impacted the schedule. As noted in the narrative, we have submitted and are awaiting approval on a budget reprogram that contains the same total project build amount, but reallocates the dollars between the various budget categories. This revised budget gives a clearer picture of the actual build costs as we move forward. Also, we wanted to note that if we were allowed to use accrued expenses in our percentage calculations, as of September 30 we were actually at 66% completion of the project. | The major impact will be the approval of our submitted reprogrammed budget. This approval is key to allow us to keep on schedule so that the project is complete by August 31, 2013. | TRUE
NT11BIX5570001 | 2012 | Q4 | Q4 - 2012 | Fourth quarter accomplishments included: -The deployment of up to 39 construction crews working in the state, creating a job FTE of 169.44. -Construction of 185 miles of conduit during the quarter, for a total of 728 miles. -Construction of 308 miles of fiber during the quarter, for a total of 660 new network fiber miles. -The deployment of 24 active cabinets with equipment. -Completion of an IRU for 242 wireless miles. -Connection of 37 new CAIs during the quarter, for a total of 104 CAIs connected (see section 6 for description of revised CAI listing). -Continuing community outreach activities with CAIs, state, regional and local governments, local technology groups and other interested parties. | 660 | 1959 | 263 | 0 | 660 | 24 | 0 | 54 | The total miles deployed are behind our baseline projection of 1,829 total new miles. With the initial delays in the grant transfer and receiving the FONSI and the construction suspension in early December, we continue to be behind our baseline estimate. This difference is also partially due to the route modifications that have been submitted to NTIA which include more fiber miles and less wireless miles than originally projected. | The total miles equal 1,717 leased fiber miles as well as 242 leased wireless miles from local, regional and national Colorado providers. However, these miles are behind our baseline projection of 2,318 leased miles. While we are exceeding the original projection of leased fiber miles, we are behind the projection for leased microwave miles. | The baseline report projected 298 miles to be upgraded by this quarter, and 317 miles by the end of the project. However, all existing miles have been upgraded, so although the total mileage is at 263 miles, this upgrade of all existing network miles has been completed. | n/a. Consistent with baseline report. | This is behind our baseline projection of 1592 miles of new fiber due to the previously described construction delays. | This is behind our baseline projection of 145 wireless links. | Although the baseline projection is for 145 new towers by this quarter and 154 new towers by the end of the project, the route modification request shows that no new towers will be built for the project, so the new towers will remain at zero. This route modification has been submitted to NTIA. | This is behind the baseline projection of 173 interconnection points due to the previously described delays in construction. | 5 | 12 | 8 | We have signed Master Service Agreements (MSAs) with 21 wholesale and last mile providers. The MSAs provide the framework for actual service agreements of which there have been 5 executed so far. Our baseline projection was for 14 agreements so we are slightly behind that estimate. However, we have additional service agreements ready which can be executed once construction resumes. | We are providing transport to the ISP or intra-state transport for the wholesale providers' customers. | n/a. No third party is operating our network. | 5 | 0 | 0 | 0 | We actually have more agreements ready to be executed to provide new access to wholesalers and last mile providers, but with the construction suspension, only 5 of those are connected, with the others tp be connected shortly after construction resumes. | n/a. Consistent with the baseline report. | n/a. Consistent with the baseline report. | n/a. | 104 | 92 | 12 | 0 | During this quarter, we were asked by the NTIA to change CAI count methodology from counting individual schools to counting school districts. This is in line with our original application as well as the CAIs posted on our website. In this conversion we went from a total of 1106 CAIs to 223 CAIs. So, in a project to date view, we are now connected to 104 of 223 CAIs, with 37 added this quarter. With the current construction stoppage, we were very close to completing but unable to finish connections to an additional 39 CAIs. While some of these CAIs are our contracted subscribers, others now have the access ability to connect if they choose to purchase service from us. | These are new CAI connections from either built fiber, leased fiber, or microwave connections. | These are upgraded CAI connections from the original Centennial BOCES network. | The network is capable of providing 1 Gbps, multiple 1 Gbps and 10 Gbps connections based on the anchor institution requests. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | We are not providing any special offerings at this time. | FALSE | n/a. | The major accomplishment will be to receive approval for our supplemental Environmental Assessment to have the construction suspension lifted. Once this is completed, we will be able to move forward with construction. At the time of the construction suspension, there were several routes close to completion, so being able to complete those quickly and to connect those related CAIs will be our number one priority. However, having established the lifting of the suspension as our main goal for the quarter, the Planned Percent Complete calculations below, based on actual dollars spent, are based on the conservative assumption that we will only be able to draw $1,500,000 this quarter for actual project payments. | Eagle-Net Alliance | On December 6, EAGLE-Net received notice to suspend all construction activities due to selected route modifications that had not been covered or approved in the initial approved state-wide Environmental Assessment. Therefore, all construction activities were stopped at that time, and EAGLE-Net has submitted revised and updated environmental documentation that is now being reviewed by the NTIA. Federal funds for construction have also been temporarily suspended pending approval of the environmental documentation. EAGLE-Net is working closely with the NTIA to facilitate an expedited review and approval of the routes in order to lift the suspension. | With the assumption that we'll receive approval of our supplemental Environmental Assessment, the biggest challenge will be ramping construction activities back up quickly so that we can still complete the network by August 31. The construction suspension happened during winter, which is slower time for construction, but we still must be ready to begin as soon as approval had been given. We were also set back financially as customer that might have connected during this period were not, so we must optimize our route selection to ensure that any potential customers are quickly connected. | TRUE
NT11BIX5570001 | 2013 | Q1 | Q1 - 2013 | First quarter accomplishments included: -Hiring a new President to lead the organization going forward. -Environmental reviews and submissions in order to complete the process to obtain a new "Finding of No Significant Impact" (FONSI) and have the temporary suspension lifted. The final supplemental EA was submitted on March 19, 2013. -The awarding of several E-Rate contracts to provide service to school districts for the 2013-2014 school year. -Continuing community outreach activities with CAIs, state, regional and local governments, local technology groups, the press, and other interested parties. There were many questions raised publicly with the suspension, so it was important to increase our community outreach efforts. | 660 | 1960 | 263 | 0 | 660 | 24 | 0 | 54 | The total miles deployed are unchanged from last quarter due to our temporary construction suspension, and are behind our baseline projection of 1,907 miles. We are awaiting approval of our route modifications that have been submitted to the NTIA which include more fiber miles and less wireless miles, resulting in less total miles than originally projected. | This total leased miles amount includes 1,718 leased fiber miles as well as 242 leased wireless miles from local, regional and national Colorado providers. While we are exceeding the original projection for leased fiber miles, we are behind the projection for leased microwave miles, leaving us in total behind the baseline projection of 2,417 leased miles. | The baseline report projected 311 miles to be upgraded by this quarter, and 317 miles by the end of the project. However, all existing miles have been upgraded and completed at 263 total miles. | n/a. Consistent with the baseline report. | This is behind our baseline projection of 1,660 miles of new fiber due to the early construction delays with the grant transfer and in achieving the FONSI. | This is behind our baseline projection of 151 wireless links. | Although the baseline projection is for 151 new towers by this quarter, the submitted route modification request shows that no new towers will be build for the project, so the number of new towers will remain at 0. | This is behind the baseline projection of 180 intercommection points due to the previously described delays in construction. | 5 | 17 | 8 | [REDACTED] | We are providing transport to the ISP or intra-state transport for the wholesale providers' customers. | n/a. No third parting is operating the EAGLE-Net network. | 5 | 0 | 0 | 0 | Although only 5 wholesalers and last mile providers are currently receiving service, we have several other agreements ready to be executed once construction resumes and routes are completed. | n/a. Consistent with the baseline report. | n/a. Consistent with the baseline report. | The network is capable of providing 1 Gbps, multiple 1 Gbps and 10 Gbps connections based on the subscribers' requests. | 104 | 92 | 12 | 0 | We are connected to 104 of the potential 223 CAIs in our project, or 47%. With the temporary construction stoppage, we were unable to continue builds to several others that are close to completion, however these will be connected once construction resumes. While some of these CAIs are our contracted subscribers, others now have the access ability to connect if they choose to purchase service from us. | These are new CAI connections from either build fiber, leased fiber, or microwave connections. | These are upgraded CAI connections from the original Centennial BOCES network. | The network is capable of providing 1 Gbps, multiple 1 Gbps and 10 Gbps connections based on the anchor institution requests. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | We are not providing any special offerings at this time. | FALSE | n/a. | The one essential planned accomplishment is to receive the new FONSI and to have the temporary suspension lifted. This will allow us to pay our contractors for their work performed and resume the construction necessary to finish the network. As stated earlier, there are several routes that were close to completion before the suspension, so these will be completed and those CAIs will be connected in the coming months. However, since the physical deployment of resources will take some time, we anticipate that by the end of the next quarter, we will have completed eight new fiber miles and have connections for two new CAIs. Because of the limited completion of routes by June 30, we anticipate having two new agreements with open access providers completed. | Eagle-Net Alliance | The biggest issue has been the temporary construction suspension that EAGLE-Net had been under since December 6. Challenges have included the time and effort to provide all of the requested data by the various agencies to obtain the new FONSI, the temporary suspension of funds that have prevented contractors from being paid for work already completed, and the lost time to finish partially built routes, many of them close to completion at the time of the suspension. In addition, although we did win several new contracts with school districts for the new school year, we also lost out on some contracts because of the perceived uncertainty of our situation, even though our proposals offered the lowest cost along with the best technology solutions. | Challenges will include obtaining the FONSI and having the temporary construction suspension lifted very quickly. Once this is done, we will need to pay our contractors as soon as possible so that they can quickly deploy to complete the remaining routes and connect to the remaining CAIs. Because of the many delays, both at the beginning of the project as well as the recent construction delays, catching back up to complete the network by August 30 will be a real challenge. Because of this, we do anticipate submitting an application for extension of time to complete the project. Also, because of lost or delayed revenue opportunities during the recent suspension, we will have to put extra effort into executing new service agreements as soon as construction on targeted routes and segments are complete. We do have several opportunities to sell open access agreements to several interested carriers, so we will need to quickly follow up with those potential customers. Also, please note that we anticipate the new budget reprogram to be approved in the next quarter. As part of that reprogram, the budget category amounts have changed, and the NTIA has asked that we use those new category amounts on the "Infrastructure Budget Execution Details" page (the last page) of this report for the "Anticipated Actuals" for the next quarter. | TRUE
NT11BIX5570001 | 2013 | Q2 | Q2 - 2013 | Accomplishments during the quarter included: - Completing and having approved the new statewide Supplemental Environmental Assessment (EA) and receiving a new FONSI. - Beginning construction once the temporary construction suspension was lifted. Eight new miles and connections to one new CAI via a local provider/partner were completed this quarter. - Winning 14 new e-rate contracts to be delivered in the 2013-2014 school year. - Completing a contract with one new local provider. - Purchasing a new IRU for 4 miles near Craig, Colorado. - Having a new budget re-program approved by the NTIA. Please note that the milestones of Percent Complete shown below in section 2 are based on the Baseline Report, which did not change. However, the various expense category amounts did change in the newly approved budget. See the last page of this report for an update of the new approved budget. | 668 | 1947 | 263 | 0 | 668 | 24 | 0 | 56 | The total miles deployed increased by only 8 miles due to the temporary construction suspension that was just lifted during the quarter. Therefore, construction activities didn't resume until the second week of June. The baseline projection was for the project to be complete at 1,946 new network miles, however, because of design changes, including the change from wireless to fiber in many routes, and changes in routes deployed, the revised project goals are for a total of 1,070 new network miles deployed. | The total leased miles increased by 4 miles this quarter, however, a correction of from Quarter 4, 2012 reduced the leased miles by 17 miles for a leg was not needed for the network, for a net reduction of 13 miles, and a total of 1,705 leased fiber miles and 242 leased wireless miles from local, regional and national Colorado providers. This is behind the baseline total network projection of 2,466 leased miles as the number of wireless leases was decreased. However, the revised project goals are for a total of 2,020 leased miles, so we are closing in on that total. | The baseline projection was for 317 miles to be upgraded by the end of the project, however all existing miles have been upgraded and completed at 263 miles, 73 wireless and 190 fiber. | n/a. Consistent with the baseline report. | Please note that the guidance for this metric has changed from total fiber miles in the baseline report (projected to be 1,694 constructed, leased and upgraded fiber miles) to only newly constructed fiber miles, which is the 668 reported here. | The baseline projection was for 154 new wireless links. However, the revised project goals will total 37 wireless links, as the network has transitioned from a primarily wireless network to a primarily fiber network. | The baseline projection was for 154 new towers. However, the revised project goals will total 0 new towers, as the network has transitioned from a primarily wireless network to a primarily fiber network. | The baseline projection was for 184 new interconnection points. However, the revised project goal will total 78 new interconnection points. | 6 | 8 | 6 | [REDACTED] | We are providing middle mile transport/backhaul to ISPs and other providers. | n/a. No third party is operating the EAGLE-Net network. However, during this quarter we began an Invitation to Negotiate (ITN) process to select a partner/network operator to operate the network in the future. This selection process will continue into the third quarter. | 6 | 0 | 0 | 3 | Although only 6 wholesalers and last mile providers are currently receiving service, we have several other agreements close to being executed once construction is completed. | n/a. Consistent with the Baseline Report. | n/a. Consistent with the Baseline Report. | Provider speed tiers include 2 at 100 Mbps, 2 at 300 Mbps, and 2 at 600 Mbps. Speed tiers available are up to 1 Gbps. | 105 | 93 | 12 | 4 | We added one new connection to school districts via a local provider in June. So, we are connected to 105 of the potential 223 CAIs in our project, or 47%. In addition, although not directly connected, we are providing service through local partners to 7 of the 10 school districts that we took off of our list because of BIP overlap issues (these are not included in the 105 connections). We are supplying these schools' local providers with backhaul service. | These are new CAI connections from either built fiber, leased fiber, microwave connections or agreements with local last mile providers. | These are upgraded CAI connections from the original Centennial BOCES network. | The customers to whom we are providing service fall into 4 tiers: 10-49 Mbps = 12 50-99 Mbps = 6 100-499 Mbps = 12 500 Mbps-1Gbps = 4 | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | We are not providing any special offerings at this time. | FALSE | n/a. | We hope to complete three major accomplishments during the next quarter. The first is to submit an extension request and have it approved through December, 2014. This is the time that it will take us to complete the Silverton build. The second is to have some route changes approved, as we have been able to work out agreements with some local providers to purchase IRUs rather than to build to a few CAIs. The third is to complete our process to select a partner/network operator so that we can complete our build and while still administering the network, have an experienced entity take over the day to day operations of the network. In addition, we expect to have completed the build of 165 new fiber miles, to have purchased an additional 35.6 miles of an IRU, and to have connected 12 new CAIs, 4 of which we'll immediately be providing service to via e-rate contracts. We also plan to have seven new signed agreements with wholesale providers providing new income during the next quarter. | Eagle-Net Alliance | The biggest challenge was the work involved in providing all documentation to get off of the temporary construction suspension on which we'd been placed since December. Since we weren't allowed to perform any construction related activities, once the suspension was released, we had to quickly make schedule and design changes so that we could begin deployment as soon as possible. So, although the suspension was released on April 29, actual construction was not re-started until the second week in June. One other consequence of the suspension was that we lost potential customers as part of the e-rate process. There were situations where, even though we offered the best technology at the lowest price, we were not awarded the contract because of the suspension. In other cases, the suspension put us behind the original build schedule, so that we were unable to offer service at the beginning of the contract year, July 2013. However, the NTIA worked with us to complete the lifting of the suspension and to complete a new budget and schedule so that we can get back to building the statewide network as quickly as possible. | Challenges during the next quarter will be to ensure approval of our extension submission to complete our network build past the 8/31/2013 deadline. With the previous delays in our project, we will not be able to complete the approved network in the previous time allotted. In addition, we are still negotiating with several local providers on some routes which may necessitate that route changes be submitted and approved. The challenge will be to ensure that our submissions for both of these processes are complete and to try to expedite approval as much as possible. | TRUE
NT11BIX5570001 | 2013 | Q3 | Q3 - 2013 | Significant accomplishments during this quarter included: - Approval of our extension request to continue construction up to December 31, 2014. - Completion of 74 newly constructed fiber miles in the San Luis Valley and Southwest areas of the state. - Connection provided to 3 new CAIs, 2 of which are receiving service from EAGLE-Net. In addition, there was the addition of 3 CAIs that had been connected in prior periods, but had not been included on the report. - Service provided to 2 previously connected CAIs in Widefield and Elbert school districts. - Service agreement signed and service begun to 1 new wholesale service provider. - Selection of Network Operator "final candidate" completed, and negotiations started on a definitive agreement. - Presentation made to Colorado State Legislative Audit Committee. - Continued efforts to work with local service providers on potential deals to share similar routes. - Despite the recent catastrophic flooding in Colorado, we experienced only one service outage on the network. The outage was on one of our IRUâ€™d fiber routes where an overhead fiber path that crossed a river was damaged. Working with the service provider, the service was able to be restored by being routed to an alternate facility prior to the school district reopening. | 742 | 1947 | 263 | 0 | 742 | 24 | 0 | 56 | This quarter, 74 new fiber miles were completed, for a total of 742 new network miles. The baseline projection was for the project to be complete at 1,946 new network miles, however, because of design changes, including the change from wireless to fiber in many routes, and changes in routes deployed, the revised project goals are for a total of 1,070 new network miles deployed. | The total leased miles did not change this quarter as no new IRUs were completed, although a few are in negotiations. This gives a total of 1,705 leased fiber miles and 242 leased wireless miles from local, regional and national Colorado providers. This is behind the original baseline total network projection of 2,466 leased miles as the number of wireless leases was decreased. However, the revised project goals are for a total of 2,020 leased miles, so we are closing in on that total. | The baseline projection was for 317 miles to be upgraded by the end of the project, however all existing miles have been upgraded and completed at 263 miles, 73 wireless and 190 fiber. | n/a. Consistent with the baseline report. | Please note that the guidance for this metric has changed from total fiber miles in the baseline report (projected to be 1,694 constructed, leased and upgraded fiber miles) to only newly constructed fiber miles, which is the 742 reported here. | The baseline projection was for 154 new wireless links. However, the revised project goals will total 37 wireless links, as the network has transitioned from a primarily wireless network to a primarily fiber network. | The baseline projection was for 154 new towers. However, the revised project goals will total 0 new towers, as the network has transitioned from a primarily wireless network to a primarily fiber network. Although no new towers will be built, there will be some leased space on existing towers as part of the approved design plan. | The baseline projection was for 184 new interconnection points. However, the revised project goal will total 78 new interconnection points. | 7 | 19 | 6 | [REDACTED] | We are providing middle mile transport/backhaul to ISPs and other providers. | n/a. No third party is operating the EAGLE-Net network. However, during this quarter we continued our Invitation to Negotiate (ITN) process by selecting the "final" candidate and beginning negotiations on an agreement to operate the network sometime during the next quarter. The definitive agreement will be completed and the announcement will be made in the fourth quarter 2013. | 7 | 0 | 0 | 3 | Although only 7 wholesalers and last mile providers are currently receiving service, we have several other agreements close to being executed once construction is completed. | n/a. Consistent with the Baseline Report. | n/a. Consistent with the Baseline Report. | Provider speed tiers include 2 at 100 Mbps, 3 at 300 Mbps, and 2 at 600 Mbps. Speed tiers available are up to 1 Gbps. | 109 | 97 | 12 | 4 | We performed a review of the APR list of connected CAIs and found four errors; two CAIs that were on the list and should not have been, and two CAIs that were not on the list and should have been. So, the total number of connected CAIs remained at 104 as of 12/31/2012. In the 2013 second quarter PPR, we added one CAI, Genoa-Hugo, However, there should have been a second CAI added, Woodlin, also connected via a partner. This quarter we added two new connections to school districts, Hoehne and Meeker, as well as to the Meeker Regional Library, so we are connected to 109 of the potential 223 CAIs in our project (these four new CAIs, in addition to the two that were missed in 2012, Mapleton and Falcon, have been added to the CAI list in #9 below). In addition, although not directly connected, we are providing service through local partners to 8 of the 10 school districts that we took off of our list because of BIP overlap issues (these are not included in the 109 connections). We are supplying these schools' local providers with backhaul service. | These are new CAI connections from either built fiber, leased fiber, microwave connections or agreements with local last mile providers. | These are upgraded CAI connections from the original Centennial BOCES network. | The 37 school district customers and 2 BOCES customers to whom we are providing service fall into 4 tiers: 10-49 Mbps = 15 50-99 Mbps = 7 100-499 Mbps = 13 500 Mbps-1Gbps = 4 | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | We are not providing any special offerings at this time. | FALSE | n/a. | Accomplishments will include: - Finalizing a definitive agreement with a network operator. - Construction of 2 miles of new fiber. - IRUs for 40.9 miles of leased fiber. - Connection to 13 new CAIs, including providing service to 4 of these school districts. - Providing service to 3 new wholesale providers as well as the signing of 19 new master service agreements to lay the parameters for future service agreements. | Eagle-Net Alliance | Now that we have received approval of our extension request, we have been trying to finalize potential cooperative agreements with local providers. To the extent that we reach agreements, these will result in submitting route changes, as our approved FONSI stipulated that we build the approved routes and we had received environmental approval for those exact routes. If any route is changed because of a partnership agreement or for any other reason, there may be extra time required to submit and receive approval of the route change. We also had some impact from the major flooding in Colorado, as some construction was delayed and crews and personnel had to be focused on clean up and repair work to the existing network during this time rather than new network deployment. | The biggest challenges will be finalizing the agreement with the new Network Operator, and beginning the transition for that entity to begin the daily management of the network. Also, as winter begins, construction will be slowed for the next few months, leaving much of the wireless construction as well as the Silverton build to be completed in 2014. | TRUE
NT11BIX5570001 | 2013 | Q4 | Q4 - 2013 | Significant accomplishments during the quarter ending 12/31/2013 include: - The selection and signed agreement with a Network Operator, Affiniti. This agreement will ensure EAGLE-Net's sustainability with Affiniti taking over the cost of network operations, will add to the network build to more schools with a minimum $11.5m capital contribution over the next five years, and will ensure that all contracted CAIs receive excellent support for all of their broadband needs going forward. - Completing connections to ten new CAIs. - The completion of 67 new miles of fiber build. - Obtaining approval from the NTIA to allow the finalization of a Facilities Exchange agreement with an incumbent provider. This agreement will add 26.7 miles to the EAGLE-Net network over the next nine months. - Presentation made to Colorado State Legislative Audit Committee. - Continued efforts to work with local service providers on potential deals to share similar routes. | 809 | 1947 | 263 | 0 | 809 | 24 | 0 | 58 | This quarter, 67 new fiber miles were completed, for a total of 809 new network miles. The baseline projection was for the project to be complete at 1,946 new network miles, however, because of design changes, including the change from wireless to fiber in many routes, and changes in routes deployed, the revised project goals are for a total of 1,070 new network miles deployed. | The total leased miles did not change this quarter as no new IRUs were completed, although a few are in negotiations. This gives a total of 1,705 leased fiber miles and 242 leased wireless miles from local, regional and national Colorado providers. This is behind the original baseline total network projection of 2,466 leased miles as the number of wireless leases was decreased. However, the revised project goals are for a total of 2,020 leased miles, so we are closing in on that total. | The baseline projection was for 317 miles to be upgraded by the end of the project, however all existing miles have been upgraded and completed at 263 miles, 73 wireless and 190 fiber. | n/a. Consistent with the baseline report. | Please note that the guidance for this metric has changed from total fiber miles in the baseline report (projected to be 1,694 constructed, leased and upgraded fiber miles) to only newly constructed fiber miles, which is the 809 reported here. | The baseline projection was for 154 new wireless links. However, the revised project goals will total 37 wireless links, as the network has transitioned from a primarily wireless network to a primarily fiber network. | The baseline projection was for 154 new towers. However, the revised project goals will total 0 new towers, as the network has transitioned from a primarily wireless network to a primarily fiber network. Although no new towers will be built, there will be some leased space on existing towers as part of the approved design plan. | The baseline projection was for 184 new interconnection points. However, the revised project goal will total 78 new interconnection points. | 8 | 33 | 6 | [REDACTED] | We are providing middle mile transport/backhaul to ISPs and other providers. | During this quarter, an agreement was reached with Affiniti Colorado, LLC to be the overall network operator for the EAGLE-Net statewide network. This agreement commenced as of October 1, 2013 and is a 25 year agreement. Affiniti has been approved by the NTIA as sub recipient and will provide all operations activities for the network, with EAGLE-Net continuing ownership and managerial oversight for the network. Affiniti's headquarters are located at: 9208 Waterford Centre Blvd, Suite 150 Austin, Texas 78758-7682. | 8 | 0 | 0 | 4 | Although only eight wholesalers and last mile providers are currently receiving service, we have several other agreements close to being executed once construction is completed. | n/a. Consistent with the Baseline Report. | n/a. Consistent with the Baseline Report. | Provider speed tiers include 2 at 100 Mbps, 3 at 300 Mbps, 2 at 600 Mbps and 1 at 1 Gbps. | 119 | 107 | 12 | 4 | Ten new CAIs were connected this quarter, consisting of one library, one BOCES, and eight K-12 school districts (see the list of new connections in #9 below). These new connections result in a total of 119 connected CAIs. Of the total CAIs, EAGLE-Net is providing service to 63, either through direct contracts or via partnership agreements. | These are new CAI connections from either built fiber, leased fiber, microwave connections or agreements with local last mile providers. | These are upgraded CAI connections from the original Centennial BOCES network. | The 53 school district customers and 5 BOCES customers to whom we are directly providing service fall into 4 tiers: 10-49 Mbps = 30 50-99 Mbps = 11 100-499 Mbps = 13 500 Mbps-1Gbps = 4 | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | 0 | 0 | 0 | 0 | 0 | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | n/a. We are a BTOP project with no last mile component. | We are not providing any special offerings at this time. | TRUE | As described in 5d above, we have engaged a network operator to be responsible for all operations of the statewide network. While in a transitional state during this quarter, day to day responsibilities of network operations, and some decisions concerning those operations are being handed over to Affiniti. While EAGLE-Net retains ownership and managerial oversight of the grant and the network, operational decisions will now be managed by Affiniti. | Significant accomplishments for the next quarter include: - Completing a budget reprogram to ensure that all costs for the approved remaining projects are allocated correctly to the appropriate cost classifications. - Completion and issuance of our annual audit. - Bid awards to contractors and completion of engineering for the Silverton network build. - Continuation of build of the wireless sections of the network; approximately 80 miles of wireless will be built. - Completion of one new fiber mile built and one new fiber mile leased (IRU). - Build completions to five new CAIs. - The addition of signed contracts with three new wholesale or last mile providers. - Finalization of the network operations transition to Affiniti. | Eagle-Net Alliance | One main challenge was the continuing negotiations with incumbent providers to find shared solutions to connect CAIs and to limit the amount of actual construction that we need to complete. Generally, these negotiations move much more slowly than we would like given our limited timeframe to complete the grant, and have sometimes fallen apart after many weeks or months of proposals. So, some of these negotiations slow us down at a critical time in the project. We also had issues with our wireless build, as tower space that had been represented to us as being available either were not completed or did not meet our requirements. Therefore, we have been looking for alternate wireless solutions at a two CAIs, which again has slowed us down. Any changes in towers from our original approved design will require approved route changes to complete. | There is a potential for weather to be a challenge during the first quarter of 2014. There are certain build milestones that we would like to meet, despite the possibility of winter weather. | TRUE
NT12BIX5570001 | 2012 | Q1 | Q1 - 2012 | This grant was originally awarded to Zayo Bandwidth, LLC. under award # NT10BIX5570025. Following the wind-up of a corporate merger in late 2011, the government approved a transfer in March 2012 and awarded the grant to the current recipient who is a Zayo affiliate under Award # NT12BIX5570001. A seamless transition period is expected because the purpose and goals of the original grant have not changed, key project staff will remain intact, and we anticipate very little, if any, impact on the project implementation schedule. You can see the previous reports under the original award number above. The numbers below reflect the total current numbers for the whole project. The numbers in section 2 through the Budget Execution Details on the last page of this report are based on the numbers transferred forward from the original grant. Current aerial miles constructed is 440 of 568 total. Current underground miles constructed is 71 of 100 total. Total miles currently constructed is 511 of 668 for the total project for a total percentage of ~76% complete. Miles not yet constructed but all permits received is 82. We have currently purchased 0 Wireline IRU miles. Interconnection points installed 1348 of 413 for a total of 935 more that in our baseline. Zayo leaves a slack loop for tie in purposes every 2,000 feet. This is what we label as interconnection points. We have currently connected 17 CAI's of the 21 CAI's for the whole project for a total percentage of ~81% complete. We currently have 38 Railroad ROW permits of 45 total for a total of 84% complete. We currently have 107 City Permits of 120 total for a total of 89% complete. We currently have 68 County Permits of 73 total for a total of 93% complete. We currently have 224 State Permits of 230 total for a total of 97% complete. There are currently a total of 437 required permits, we currently have 468 total for a total of 93% of all permits. We have made 2 Land Purchases of 2 total for a total of 100% complete. We currently have 530 miles of Aerial Poles Make Ready completed of 568 total for a total percentage of 93% complete. | 511 | 0 | 0 | 0 | 511 | 0 | 0 | 1348 | This is 134 miles behind our baseline. This is based on permitting and EA change delays. | N/A | N/A | N/A | This is 134 miles behind our baseline. This is based on permitting and EA change delays. | N/A | N/A | This is 935 ahead of our baseline. Zayo is exceeding our expected number of interconnection points because we are installing more than originally calculated. | 10 | 53 | 399 | I-Light, Enhanced Telecom Corporation, Smithville Digital, Perry-Spencer Telephone, Internet Communications, Inc. | I-Light colocation- two @ $710 monthly per site and one dark fiber segment @ $2676 monthly, Smithville Digital â€“ Co-Location at $1,000 monthly, 3 dark fiber segments, one @ $1664 monthly, one @ $2048 monthly, one @ $1056 monthly, ETC â€“ dark fiber segment @ $3200 monthly, Internet Communications, Inc â€“ GigE transport, $2000 monthly, Perry-Spencer Communications â€“ GigE transport - $3425 monthly. | N/A | 2 | 0 | 2 | 0 | Perry-Spencer, Internet Communications, Inc. | N/A | I-Light, Smithville, ETC | 10meg to 100gig | 17 | 17 | 0 | 0 | This is 17 above baseline. | This is 17 above baseline. | N/A | 10meg to 100gig | 0 | 0 | 0 | 0 | 0 | This is on target, this is a middle mile project. | This is on target, this is a middle mile project. | This is on target, this is a middle mile project. | This is on target, this is a middle mile project. | This is on target, this is a middle mile project. | 0 | 0 | 0 | 0 | 0 | This is on target, this is a middle mile project. | This is on target, this is a middle mile project. | This is on target, this is a middle mile project. | N/A | N/A | None | FALSE | N/A | Zayo should be very close to wrapping up our original 648 miles if we get approval of our EA addendum in time. | Zayo Group, LLC | Zayo has submitted an Environmental Assessment (EA) Amendment Request to allow us to go from aerial to underground in some areas so that we can avoid excessive pole change out and make ready costs. We are currently waiting on Government approval. | We are currently awaiting an EA Addendum as discussed in section 1 above. Delays in getting this issued could cause delays in meeting our target date for completion. | TRUE
NT12BIX5570001 | 2012 | Q2 | Q2 - 2012 | This grant was originally awarded to Zayo Bandwidth, LLC. under award # NT10BIX5570025. Following the wind-up of a corporate merger in late 2011, the government approved a transfer in March 2012 and awarded the grant to the current recipient who is a Zayo affiliate under Award # NT12BIX5570001. The numbers below reflect the total current numbers for the whole project. The numbers in section 2 through the Budget Execution Details on the last page of this report are based on the numbers transferred forward from the original grant. Current aerial miles constructed is 440 of 568 total. Current underground miles constructed is 71 of 100 total. Total miles currently constructed is 511 of 668 for the total project for a total percentage of ~76% complete. "In-Kind" Contribution is 198 miles. Miles not yet constructed but all permits received is 82. We have currently purchased 0 Wireline IRU miles. Interconnection points installed 1348 of 413 for a total of 935 more that in our baseline. Zayo leaves a slack loop for tie in purposes every 2,000 feet. This is what we label as interconnection points. We have currently connected 17 CAI's of the 21 CAI's for the whole project for a total percentage of ~81% complete. We currently have 38 Railroad ROW permits of 45 total for a total of 84% complete. We currently have 107 City Permits of 120 total for a total of 89% complete. We currently have 68 County Permits of 73 total for a total of 93% complete. We currently have 224 State Permits of 230 total for a total of 97% complete. There are currently a total of 437 required permits, we currently have 468 total for a total of 93% of all permits. We have made 2 Land Purchases of 2 total for a total of 100% complete. We currently have 530 miles of Aerial Poles Make Ready completed of 568 total for a total percentage of 93% complete. | 568 | 0 | 0 | 0 | 568 | 0 | 0 | 1348 | This is 134 miles behind our baseline. This is based on permitting and EA change delays. | N/A | N/A | N/A | This is 134 miles behind our baseline. This is based on permitting and EA change delays. | N/A | N/ N/A | This is 935 ahead of our baseline. Zayo is exceeding our expected number of interconnection points because we are installing more than originally calculated. | 12 | 18 | 60 | I-Light, Enhanced Telecom Corporation, Smithville Digital, Perry-Spencer Telephone, Internet Communications, Inc., Verizon, T-Mobile, ETC | I-Light colocation- two @ $710 monthly per site and one dark fiber segment @ $2676 monthly, Smithville Digital â€“ Co-Location at $1,000 monthly, 3 dark fiber segments, one @ $1664 monthly, one @ $2048 monthly, one @ $1056 monthly, ETC â€“ dark fiber segment @ $3200 monthly, Internet Communications, Inc â€“ GigE transport, $2000 monthly, Perry-Spencer Communications â€“ GigE transport - $3425 monthly, Verizon Wireless â€“ 50 and 100meg Ethernet â€“ multiple sites, average $1000 per site, T-Mobile â€“ 50 and 100meg Ethernet â€“ multiple sites, average $1,000 per site. | N/A | 5 | 2 | 3 | 0 | Perry-Spencer, Internet Communications, Inc., Smithville Digital, I-Light, ETC | T-Mobile, Verizon Wireless | I-Light, Smithville, ETC | 10meg to 100gig | 17 | 17 | 0 | 0 | This is 4 behind our baseline. This is because of sites waiting on equipment. | This is 4 behind our baseline. This is because of sites waiting on equipment. | N/A | 10meg to 100gig | 0 | 0 | 0 | 0 | 0 | This is on target, this is a middle mile project. | This is on target, this is a middle mile project. | This is on target, this is a middle mile project. | This is on target, this is a middle mile project. | This is on target, this is a middle mile project. | 0 | 0 | 0 | 0 | 0 | This is on target, this is a middle mile project. | This is on target, this is a middle mile project. | This is on target, this is a middle mile project. | N/A | N/A | None | FALSE | N/A | Zayo should have 610 miles built by next quarter. Zayo should have 18 CAI's connected by next quarter. Zayo should have 10 last mile providers signed by next quarter. | Zayo Group, LLC | None. | Zayo is not anticipating any issues next quarter. We should be very close to being done. | TRUE
NT12BIX5570001 | 2012 | Q3 | Q3 - 2012 | Current aerial miles constructed is 544 of 568 total. Current underground miles constructed is 99 of 100 total. Total miles currently constructed is 643 of 668 for the total project for a total percentage of 96% complete. "In-Kind" Contribution is 198 miles. Miles not yet constructed but all permits received is 25. We have currently purchased 0 Wireline IRU miles. Interconnection points installed 1549 for 935 more than the 413 projected in our baseline report. Zayo leaves a slack loop for tie in purposes every 2,000 feet. This is what we label as interconnection points. We have currently connected 17 CAI's of the 21 CAI's for the whole project for a total percentage of ~80% complete. We currently have 44 Railroad ROW permits of 45 total for a total of 99% complete. We currently have 120 City Permits of 120 total for a total of 100% complete. We currently have 73 County Permits of 73 total for a total of 100% complete. We currently have 230 State Permits of 230 total for a total of 100% complete. There are currently a total of 468 required permits, we currently have 468 total for a total of 100% of all permits. We have made 2 Land Purchases of 2 total for a total of 100% complete. We currently have 558 miles of Aerial Poles Make Ready completed of 568 total for a total percentage of 98% complete. | 643 | 0 | 0 | 0 | 643 | 0 | 0 | 1549 | This is actual build. | N/A | N/A | N/A | This is actual build. | N/A | N/A | This is way ahead of our baseline. | 16 | 61 | 40 | AT&T, Comcast Cable, Level 3, TW Telecom, Verizon Business, CenturyLink, Earthlink Business, ExteNet Networks, I-Light, KDL, Internet Communications, ETC, Smithville Digital, Perry-Spencer Telephone, Verizon Wireless, Wide Open West | ark Fiber, Ethernet, Dedicated Internet. | N/A | 16 | 2 | 3 | 16 | Most of the providers have signed for multiple sites/segments/routes. | T-Mobile, Verizon Wireless, This is 15 behind our baseline. This is because or baseline was a plan and this is based on actuals. | I-Light, Smithville, ETC | The dark fiber is limited only by the equipment, so can run 10meg to 100gig. | 17 | 17 | 0 | 0 | This is based on actuals. This is four behind our baseline of 21 because of delays connecting our anchor institutions. We will be caught up next quarter. | This is based on actuals. | N/A | 10meg to 100gig - ENA (100meg - 200meg, 1 gig), UDWI - 10meg, CMN - 1000meg, | 0 | 0 | 0 | 0 | 0 | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | 0 | 0 | 0 | 0 | 0 | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | N/A | FALSE | N/A | Zayo should be completed with construction by next quarter. That means 568 miles deployed next quarter. We should have 21 CAIs connected by the end of next quarter. We should have 20 broadband wholesaler/last mile provider agreements signed through the end of next quarter. | Zayo Group, LLC | Even though Zayo is ahead of schedule and under budget, we have exceeded spending in our A and E line item and will need to move funds from our Construction budget to our A and E budget. Zayo needs to submit an AAR Request to BTOP to move funds from the construction line item and put it in our Architecture and Engineering budget. This will cover inspectors and as builts. | Zayo should be done with construction by the end of next quarter. | TRUE
NT12BIX5570001 | 2012 | Q4 | Q4 - 2012 | I-Light Current aerial miles constructed is 565 of 568 total. Current underground miles constructed is 99.5 of 100 total. Total miles currently constructed is 665 of 668 for the total project for a total percentage of 96% complete. "In-Kind" Contribution is 198 miles. Miles not yet constructed but all permits received is 3. We have currently purchased 0 Wireline IRU miles. Interconnection points installed 1649 for 935 more than the 413 projected in our baseline report. Zayo leaves a slack loop for tie in purposes every 2,000 feet. This is what we label as interconnection points. We have currently connected 21 CAI's of the 21 CAI's for the whole project for a total percentage of ~99% complete. We currently have 45 Railroad ROW permits of 45 total for a total of 100% complete. We currently have 120 City Permits of 120 total for a total of 100% complete. We currently have 73 County Permits of 73 total for a total of 100% complete. We currently have 230 State Permits of 230 total for a total of 100% complete. There are currently a total of 468 required permits, we currently have 468 total for a total of 100% of all permits. We have made 2 Land Purchases of 2 total for a total of 100% complete. We currently have 565 miles of Aerial Poles Make Ready completed of 568 total for a total percentage of 99% complete. | 665 | 0 | 0 | 0 | 665 | 0 | 0 | 1649 | This is actual build. | N/A | N/A | N/A | This is actual build. | N/A | N/A | Zayo leaves a slack loop for tie in purposes every 2,500 feet. This is what we label as an interconnection point. | 21 | 13 | 60 | AT&T, ATMInternet, CenturyLink, CMN-RUS, Comcast Cable, Earthlink Business, ExteNet, FBN Indiana, Great Lakes ComNet, KDL, Level 3, Lightbound, Perry-Spencer Communications, Smithville Digital, Sunman Telephone, Time Warner, TransWorld, TW Telecom, Verizon Wireless, Wide Open West. | Dark fiber leases and IRUs, lit services from 10meg to 100gig. | N/A | 3 | 7 | 11 | 21 | Most of the providers have signed for multiple sites/segments/routes. | This is based on actuals. | This is based on actuals. | The dark fiber is limited only by equipment, so can run 10meg to 100gig. | 21 | 21 | 0 | 21 | This is based on actuals. | This is based on actuals. | N/A | The dark fiber is limited only by equipment, so can run 10meg to 100gig. | 0 | 0 | 0 | 0 | 0 | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | 0 | 0 | 0 | 0 | 0 | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | N/A | FALSE | N/A | Zayo should have this project completed by next quarter. We will complete the remaining two Ivy Tech connections, Bloomington and Connersville by the end of the third week in January 2013 That means 668 miles deployed next quarter. | Zayo Group, LLC | N/A | Zayo will be done with construction by the end of next quarter. | TRUE
NT12BIX5570001 | 2013 | Q1 | Q1 - 2013 | Current aerial miles constructed is 545 of 545 total. Current underground miles constructed is 100 of 100 total. Total route miles currently constructed is 645 (668)_total fiber miles constructed for the total project for a total percentage of 100% complete. "In-Kind" Contribution is 198 fiber 99 route miles x 2 strands. Interconnection points include 5 collocation facilities but further more include 1651 for 935 more than the 413 projected in our baseline report. Zayo leaves a slack loop for tie in purposes every 2,000 feet. This is what we label as interconnection points. All 21 CAI's of the 21 CAI's for the whole project for a total percentage of ~100% complete. We currently have 45 Railroad ROW permits of 45 total for a total of 100% complete. We currently have 120 City Permits of 120 total for a total of 100% complete. We currently have 73 County Permits of 73 total for a total of 100% complete. We currently have 230 State Permits of 230 total for a total of 100% complete. There are currently a total of 468 required permits, we currently have 468 total for a total of 100% of all permits. We have made 2 Land Purchases of 2 total for a total of 100% complete. | 645 | 0 | 0 | 99 | 645 | 0 | 0 | 1651 | This is based on Route miles. (668 Fiber miles) | This is based on actual build. | This is based on actual build. | This is "In-Kind" Contribution. 99 miles x 2 strands | This is based on Route miles. (668 fiber miles) | This is based on actual build. | This is based on actual build. | 5 Colo locations and 1,651 slack loops | 29 | 16 | 60 | AT&T, Anexeon, ATMineternet, CenturyLink, CMN-RUS, Comcast Cable, Earthlink Business, ENA, ExteNet, FBN Indiana, Great Lakes ComNet, I-Light, KDL, Level 3, Lightbound, Only Internet, Perry-Spencer Communications, Single Digits, Smithville Digital, Sunman Telephone, Time Warner, TransWorld, Trellegborg, TW Telecom, Verizon Wireless, Verizon Business, Wide Open West. Two providers have more than one agreement. | Dark fiber leases and IRU's, lit services from 10meg to 100meg. See Q1 2013 PPR Attachment 1. | N/A | 5 | 9 | 13 | 27 | Most of the providers have signed for multiple sites/segments or routes. See Attachment 1 to this report. | This is based on actual build. | This is based on actual build. | Dark fiber is limited by equipment, so can run 10meg to 100gig | 21 | 21 | 0 | 21 | This is based on actual build. | This is based on actual build. | This is based on actual build. | The dark fiber is limited only by equipment, so can run 10meg to 100gig. | 0 | 0 | 0 | 0 | 0 | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | 0 | 0 | 0 | 0 | 0 | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | N/A | FALSE | N/A | Zayo completed this award on schedule and approximately $3.4 under budget. The network expanded our Indiana network by approximately 30%. This has enabled us to work with Community Anchor Institutions, enterprises and wholesales customers. Connectivity has been provided to 21 campuses for higher education, as well as K-12 schools, energy providers, and telecomm providers. The increases in bandwidth has enabled users of both wireline and wireless devices and network to expand their use of internet and wide area network connectivity. This includes access to Internet 2 and National Lambda Rail, enabling enhanced research between and among all levels of educational users. It has also provided opportunities to users of internet access in rural areas with increased bandwidth. | Zayo Group, LLC | Zayo is complete with this project and is approximately 27 % under budget. | None. Project was completed on 1/31/2013. | TRUE
NT12BIX5570002 | 2012 | Q1 | Q1 - 2012 | This grant was originally awarded to Zayo Bandwidth, LLC, under award # NT10BIX5570071. Following the wind-up of a corporate merger in late 2011, the government approved a transfer in March 2012 and awarded the grant to the current recipient who is a Zayo affiliate under Award # NT12BIX5570002. A seamless transition period is expected because the purpose and goals of the original grant have not changed, key project staff will remain intact, and we anticipate very little, if any, impact on the project implementation schedule. The numbers below reflect the actual numbers to date based on the entire project. The numbers below in Section 2 through the Infrastructure Budget Execution Details on the last page of this report reflect the percentages of the the money moved forward with this award. Current aerial miles constructed is 28 of 94 total. Current underground miles constructed is 58 of 175 total. Total miles currently constructed is 86 of 269 for the total project for a total percentage of ~32% complete. Miles not yet constructed but all permits received is 61. Interconnection points installed 233 of 625 for a total of ~37% complete. Zayo leaves a slack loop for tie in purposes every 2,000 feet. This is what we label as interconnection points. We have currently connected 8 CAI's of the 145 CAI's for the whole project for a total percentage of ~5.5% complete. We currently have 15 Railroad ROW permits of 17 total for a total of 88% complete. We currently have 15 City Permits of 32 total for a total of 47% complete. We currently have 14 County Permits of 32 total for a total of 44% complete. We currently have 16 State Permits of 24 total for a total of 67% complete. We currently have 4 DNR Permits of 12 total for a total of 33% complete. We currently have 1 Corp of Engrs Permits of 4 total for a total of 25% complete. We currently have 65 permits of 121 total for a total of 54% Complete for all permits. We currently have 1550 miles of Aerial Poles Make Ready completed of 1710 total for a total of 91% complete. | 86 | 0 | 0 | 0 | 86 | 0 | 0 | 15 | Based on actual build, we are 19 miles ahead of our baseline. | N/A | N/A | N/A | We are 19 miles ahead of our baseline. | N/A | N/A | This is 30 behind our baseline. This is because we are equally spacing all interconnection points. | 0 | 2 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | This is in line with our baseline. | This is 8 in line with our baseline. | N/A | 45Mpbs, 155Mbps, 620Mbps, 2,480Mbps, 50Mbps, 100Mbps, 100Mbps, 2,480Mbps, 10,000Mbps, Dark Fiber. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None. | FALSE | N/A | Zayo currently has approved permits for several miles ~40 that we will be able to construct once we receive approval of our requested EA Addendum. Depending on how soon we get approval, we should be able to finish this project well ahead of schedule. | Zayo Group, LLC | Zayo has applied for an addendum to our Environmental Assessment (EA) to allow us to go from aerial to underground in certain areas to allow us to avoid excessive pole change out and make ready fees. | Once we have our EA addendum approved we are not expecting any further challenges or issues. | TRUE
NT12BIX5570002 | 2012 | Q2 | Q2 - 2012 | This grant was originally awarded to Zayo Bandwidth, LLC, under award # NT10BIX5570071. Following the wind-up of a corporate merger in late 2011, the government approved a transfer in March 2012 and awarded the grant to the current recipient who is a Zayo affiliate under Award # NT12BIX5570002. The numbers below reflect the actual numbers to date based on the entire project. The numbers below in Section 2 through the Infrastructure Budget Execution Details on the last page of this report reflect the percentages of the the money moved forward with this award. Current aerial miles constructed is 48 of 94 total. Current underground miles constructed is 154 of 175 total. Total miles currently constructed is 202.73 of 269 for the total project for a total percentage of 75% complete. Miles not yet constructed but all permits received is 29. Interconnection points installed 428 of 625 for a total of 68% complete. Zayo leaves a slack loop for tie in purposes every 2,500 feet. This is what we label as interconnection points. We have currently connected 38 CAI's (no electronics, not ready for use) of the 145 CAI's for the whole project for a total percentage of 26.2% complete. We currently have 17 Railroad ROW permits of 17 total for a total of 100% complete. We currently have 31 City Permits of 35 total for a total of 88.5% complete. We currently have 29 County Permits of 38 total for a total of 76.3% complete. We currently have 27 State Permits of 28 total for a total of 96.4% complete. We currently have 11 DNR Permits of 14 total for a total of 78.5% complete. We currently have 1 Corp of Engrs Permits of 4 total for a total of 25% complete. We currently have 116 permits of 134 total for a total of 86.5% Complete for all permits. We currently have 1550 miles of Aerial Poles Make Ready completed of 1710 total for a total of 91% complete. | 202 | 0 | 0 | 0 | 202 | 0 | 0 | 428 | Based on actual build, we are 94 miles ahead of our baseline. | N/A | N/A | N/A | Based on actual build, we are 94 miles ahead of our baseline. | N/A | N/A | This is 348 ahead of our baseline. This is because we are equally spacing all interconnection points. | 0 | 2 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | This is 65 behind our baseline because we have not turned any sites up yet. | N/A | N/A | 0 | 0 | 0 | 0 | This is in line with our baseline. | This is in line with our baseline. | N/A | 45Mpbs, 155Mbps, 620Mbps, 2,480Mbps, 50Mbps, 100Mbps, 100Mbps, 2,480Mbps, 10,000Mbps, Dark Fiber. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Number of miles you plan to deploy next quarter - 230 Miles Number of CAIs you plan to connect by the end of the next quarter - 0 these will not be turned up until after the network is completed and lit. Number of broadband wholesaler/last mile provider agreements you plan to sign through the end of next quarter- 0 This will coincide with the lighting of the network after the build is complete. Zayo plans to stay ahead of schedule. | Zayo Group, LLC | Zayo is ahead of schedule. | Zayo plans to stay ahead of schedule. | TRUE
NT12BIX5570002 | 2012 | Q3 | Q3 - 2012 | Current aerial miles constructed is 56 of 84 total. Current underground miles constructed is 173 of 192 total. Total miles currently constructed is 229.49 of 276 for the total project for a total percentage of 85% complete. Miles not yet constructed but all permits received 29. Interconnection points installed 483 of 625 for a total of 78% complete. Zayo leaves a slack loop for tie in purposes every 2,500 feet. This is what we label as interconnection points. We have currently connected (run the dark fiber to) 102 CAI's (no electronics, not ready for use) of the 145 CAI's for the whole project for a total percentage of 72.2% complete OSP. 3 have Equipment installed which brings the total connected to 105. We currently have 17 Railroad ROW permits of 17 total for a total of 100% complete. We currently have 34 City Permits of 35 total for a total of 97.1% complete. We currently have 37 County Permits of 38 total for a total of 97.3% complete. We currently have 27 State Permits of 28 total for a total of 96.4% complete. Currently we Need 1 DNR/Fish & Wildlife Permit anticipated news by Nov 4th 2012. We currently have 24 DNR Permits of 28 total for a total of 85.5% complete. We currently have 1 Corp of Engrs Permits of 2 total for a total of 50% complete. We currently have 139 permits of 148 total for a total of 86.5% Complete for all permits. We currently have 1550 miles of Aerial Poles Make Ready completed of 1710 total for a total of 91% complete. | 229 | 0 | 0 | 0 | 229 | 0 | 0 | 483 | This is based on actual build. | N/A | N/A | N/A | This is based on actual build. | N/A | N/A | This is because we are equally spacing all interconnection points. | 0 | 4 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zayo is not connected to sites yet and needs to before we can sell or improve connections. Zayo expects to match our baseline by the end of the project timeline. | Zayo is not connected to sites yet and needs to before we can sell or improve connections. Zayo expects to match our baseline by the end of the project timeline. | Zayo is not connected to sites yet and needs to before we can sell or improve connections. Zayo expects to match our baseline by the end of the project timeline. | The dark fiber is limited only by the equipment, so can run 10meg to 100gig. | 0 | 0 | 0 | 0 | This is because we have not connected the passed institutions yet. | This is based on actuals to date. | This is based on actuals to date. | 10meg to 100gig - ENA (100meg - 200meg, 1 gig), UDWI - 10meg, CMN - 1000meg, | 0 | 0 | 0 | 0 | 0 | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | 0 | 0 | 0 | 0 | 0 | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | None | FALSE | N/A | Zayo plans to be complete ahead of schedule and under budget by the end of next quarter. Zayo should have all 276 miles constructed by next quarter. Zayo should have 145 CAIs connected by the end of next quarter. Zayo should have 2 last mile agreements executed by next quarter with the rest by the end of the award period. | Zayo Group, LLC | Zayo is ahead of schedule and below budget and plans to stay that way. | Zayo is ahead of schedule and plans to stay that way. | TRUE
NT12BIX5570002 | 2012 | Q4 | Q4 - 2012 | Current aerial miles constructed is 58 of 84 total, 70%. Current underground miles constructed is 184 of 192 total, 95%. Total miles currently constructed is 242.00 of 276 for the total project for a total percentage of 88% complete. Miles not yet constructed but all permits received 12 miles. Interconnection points installed 598 of 625 for a total of 96% complete. Zayo leaves a slack loop for tie in purposes every 2,500 feet. This is what we label as interconnection points. We have currently connected (run the dark fiber to) 140 CAI's (no electronics, not ready for use) of the 145 CAI's for the whole project for a total percentage of 97.0% complete OSP. 12 have Equipment installed, 9% Complete Equipment Installation. We currently have 17 Railroad ROW permits of 17 total for a total of 100% complete. We currently have 41 City Permits of 41 total for a total of 100% complete. We currently have 39 County Permits of 40 total for a total of 98.0% complete. We currently have 28 State Permits of 28 total for a total of 100% complete. Currently we Need 1 DNR/Fish & Wildlife Permit anticipated news by Jan 30th 2013. We currently have 29 DNR Permits of 30 total for a total of 97.0% complete. We currently have 2 Corp of Engrs Permits of 2 total for a total of 100% complete. We currently have 156 permits of 157 total for a total of 99.0% Complete for all permits. We currently have 1580 miles of Aerial Poles Make Ready completed of 1710 total for a total of 93% complete. | 242 | 0 | 0 | 0 | 242 | 0 | 0 | 685 | This is based on actual build. | N/A | N/A | N/A | This is based on actual build. | N/A | N/A | Zayo leaves a slack loop for tie in purposes every 2,500 feet. This is what we label as an interconnection point. | 1 | 10 | 60 | ComNet | N/A | N/A | 1 | 0 | 0 | 1 | This is a middle mile project and Zayo has not lit the network yet. Zayo should meet our baseline by the end of the project. | This is a middle mile project and Zayo has not lit the network yet. Zayo should meet our baseline by the end of the project. | This is a middle mile project and Zayo has not lit the network yet. Zayo should meet our baseline by the end of the project. | 10meg to 100gig - ENA (100meg - 200meg, 1 gig), UDWI - 10meg, CMN - 1000meg, | 1 | 1 | 0 | 1 | Zayo has only connected one site to date. Zayo expects to match our baseline by the end of the project timeline. We will connect and light fiber after the build. | Zayo has only connected one site to date. Zayo expects to match our baseline by the end of the project timeline. We will connect and light fiber after the build. | This is based on actuals to date. | 10meg to 100gig - ENA (100meg - 200meg, 1 gig), UDWI - 10meg, CMN - 1000meg, | 0 | 0 | 0 | 0 | 0 | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | 0 | 0 | 0 | 0 | 0 | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | None | FALSE | N/A | Complete all Outside Plant Construction, Equipment Installation and Testing and Turn up of all 145 sites. | Zayo Group, LLC | The only challenge to date has been with permitting. The Fish and Wildlife permit process has been a 5-6 month process, but we should have our last permit by January 31, 2013. | Zayo does not anticipate any challenges for the next quarter with the exception of weather delays. | TRUE
NT12BIX5570002 | 2013 | Q1 | Q1 - 2013 | Current Aerial and underground route miles constructed is 245.2 of 250 total, 98.8%. Miles not yet constructed but all permits received 3 miles. Interconnection points installed 685 of 685 for a total of 100 % complete. Zayo leaves a slack loop for tie in purposes every 2,500 feet. This is what we label as interconnection points. We have currently connected 142 CAI's of the 145 CAI's for the whole project for a total percentage of 97.8 % complete OSP. 142 have Equipment installed, 98.7 % Complete Equipment Installation. CAI break down as follows 130 CAI's and 15 Water Towers providing service to city entities and law enforcement radio systems. We currently have 17 Railroad ROW permits of 17 total for a total of 100% complete. We currently have 41 City Permits of 41 total for a total of 100% complete. We currently have 40 County Permits of 40 total for a total of 100.0% complete. We currently have 28 State Permits of 28 total for a total of 100% complete. We currently have 30 DNR Permits of 30 total for a total of 100.0% complete. We currently have 2 Corp of Engrs Permits of 2 total for a total of 100% complete. We currently have 157 permits of 157 total for a total of 100.0% Complete for all permits. We currently have 1550 poles of Aerial Poles Make Ready completed of 1550 (1710) total. (100% complete). Note: 1710 poles is the estimate in the initial engineering stages. 1550 current total reported on the XCEL APA's, final tabulation of the As-built will be completed when they become available from the engineers at that time final number of poles will be determined. | 245 | 0 | 0 | 0 | 245 | 0 | 0 | 685 | This is based on actual build. | N/A | N/A | N/A | This is based on actual build. | N/A | N/A | Zayo leaves a slack loop for tie in purposes every 2,500 feet. This is what we label as an interconnection point. | 0 | 3 | 60 | N/A | N/A. Wholesale services are based on mileage and equipment used as well as fiber availability. These will all vary from customer to customer. | N/A | 0 | 0 | 1 | 1 | This is a middle mile project and Zayo has not lit the network yet. Zayo listed 145 in our baseline, but this was a mistake and copied over from the number of CAI's we would be connecting, not last mile providers. | This is a middle mile project and Zayo has not lit the network yet. Zayo should meet our baseline by the end of the project. | Currently providing 12 Dark Fibers to Anoka County per Master Services Agreement with Zayo. | 10meg to 100gig - ENA (100meg - 200meg, 1 gig), UDWI - 10meg, CMN - 1000meg, please refer to the CAI addendum. Speeds are indicated on each CAI. | 142 | 142 | 0 | 1 | Zayo has only connected 142/145 sites to date. Zayo has turned over facilities to the CAI's for service as well as testing. | Zayo has only connected 142/145 sites to date. Zayo expects to match our baseline by the end of the project time line. | This is based on actuals to date. | 10meg to 100gig - ENA (100meg - 200meg, 1 gig), UDWI - 10meg, CMN - 1000meg, please refer to the CAI addendum. Speeds are indicated on each CAI. | 0 | 0 | 0 | 0 | 0 | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | 0 | 0 | 0 | 0 | 0 | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | This is a middle mile project. | None | FALSE | N/A | We should have the final 5 miles built by the end of next quarter. We should also be preparing closeout documentation to finalize project. Zayo initial baseline/target of 286 miles was based on estimates derived from measurements off of a preliminary proposed route on a google map. As can be expected, this method would be at least a +/- 10% margin of error, based on this the Zayo Planner used 260 miles plus a 10% contingency which equates to 286 miles. As engineering of the actual routes are documented the miles are firmed up and more accurate. The miles changes for several reasons, permit agencies, government entities and route changes due to environmental groups. During fiber construction it is common practice to report footages from Fiber Cable Sequential Readings on the cable, this is recorded as total cable placed. Final as-built drawings will provide an accurate tabulation of the constructed route, at the time Zayo will have a final number of miles to report. As of this quarter 142 CAI's of the 145 CAI's Zayo has turned over facilities to the CAI's for service as well as testing. The final 3 CAI's are scheduled to be turned up by May 31, 2013. CAI break down is as follows 130 CAI's and 15 water towers providing service to city entities and law enforcement radio system. Last Mile Wholesale Providers - Zayo Sales Group has proposed services to several Last Mile Providers and no agreements have been signed this quarter. Zayo expects to match our baseline by the end of the project. | Zayo Group, LLC | Zayo's only issues this last quarter have been weather related. Delays due to snow. | We should have the final 5 miles constructed this quarter. As you can see below, Zayo went $152,177.00 over budget on A&E (Line D). As we finish next quarter, Zayo will have to move money from Construction to A&E to cover this overrun. This should not be an issue as Zayo is projecting to come in ~$1M under budget. | TRUE
NT12BIX5570002 | 2013 | Q2 | Q2 - 2013 | Zayo completed the construction of the middle mile project on time and below budget, delivering a scalable and future proof fiber optic network infrastructure system to over 130 public facilities or community anchor institutions that included schools, universities, libraries, police, fire and other first responder facilities, and numerous administrative agencies. The network is a dark fiber network that has enabled the county to become a last mile provider that has installed its own optronix to light up the fiber and provide service as they desire to the CAI's and others. Those service capabilities include Ethernet, direct Internet, private line and similar services. It also enables the County to upgrade to higher transmission and bandwidth capacities as new optronix equipment becomes available from various manufacturers. The network further serves to provide the terrestrial infrastructure necessary for the County to make a significant step in implementing the NTIA's FirstNet, first responders initiative. Benefits to the County agencies, by way of example overnight data backups used to take 10 hours every night, often still in process when agencies opened for business in the mornings, frustrating many citizens, now the entire back up process takes only about 30 to 60 minutes during the night. Another example of new efficiencies and cost savings, the City of Findley has reported savings of $ 987 per month or approximately $ 12,000 per year on its telephone bill by utilizing Voice over Internet Protocol (VoIP) service over traditional copper line POTS. | 215 | 0 | 0 | 0 | 236 | 0 | 0 | 685 | This is based on actual build. | N/A | N/A | N/A | Variance from network miles is slack & vertical (pole) lengths. | N/A | N/A | Zayo leaves a slack loop for tie in purposes every 2,500 feet. This is what we label as an interconnection point. | 1 | 0 | 60 | Anoka County. Zayo provides dark fiber infrastructure to Anoka County. Anoka County then acts as a last mile provider, installing its own optronix to light the fiber and provide whatever services it chooses to offer to the Community Anchor Institutions and to whomever else it desires to provide service to. | Wholesale services are custom quoted for each new project, and are based on a considerable number of variables including but not limited to mileage, equipment used, fiber availability, engineering and construction costs, costs of underlying rights and myriad other costs. Each new project undergoes an IRR & other financial analysis to determine its profitability or loss it may result in. Due to the complex nature of such custom built projects it is not possible to maintain such a list with any reasonable accuracy. | N/A | 131 | 0 | 1 | 1 | Actual dark fiber agreement is with Anoka County, MN, who provides lit services and bills for the lit service, to the 131 CAIs listed in the addendum hereto. | This is a dark fiber middle mile project. | Anoka County, MN. This is a dark fiber network. | No speed tiers offered, providing dark fiber only. Speed tiers are dependent on whatever optronix the customer (Anoka County, MN) installs. | 131 | 131 | 131 | 0 | Zayo has turned over facilities to Anoka County for service as well as testing. Zayo built to the CAIs, but Anoka County provides the lit services and bills the CAIs. | Zayo has turned over facilities to Anoka County for service as well as testing. Zayo built to the CAIs, but Anoka County provides the lit services and bills the CAIs. | Zayo has turned over facilities to Anoka County for service as well as testing. Zayo built to the CAIs, but Anoka County provides the lit services and bills the CAIs. | No speed tiers offered, providing dark fiber only. Speed tiers are dependent on whatever optronix the customer (Anoka County, MN) installs. | 0 | 0 | 0 | 0 | 0 | N/A. This is a middle mile project. | N/A. This is a middle mile project. | N/A. This is a middle mile project. | N/A. This is a middle mile project. | N/A. This is a middle mile project. | 0 | 0 | 0 | 0 | 0 | N/A. This is a middle mile project. | N/A. This is a middle mile project. | N/A. This is a middle mile project. | N/A. This is a middle mile project. | N/A. This is a middle mile project. | Not applicable. This is a middle mile project. | FALSE | N/A | Zayo is complete with construction. Overall Project 12% under budget. Environmental Assessment 100% on budget. Network Design 100% on budget. Equipment Procurement 87% under budget. Network Build 1% under budget. | Zayo Group, LLC | Zayo had no issues this last quarter. | None. Zayo has completed all construction. | TRUE

## CCI_MileStones_Actuals
award_num | Year_Desc | Quarter_Cd | YearQuarter | Milestone_Id | PPRMain_Id | Complete_Ind | ProjOverall_Prcnt_Amt | ProjOverall_Narrtv_Desc | OtherMilstone_Prcnt_Amt | OtherMilstone_Specify_Desc | OtherMilstone_Narrtv_Desc | EnvmntAssessmnt_Prcnt_Amt | EnvmntAssessmnt_Narrtv_Desc | NetworkDesign_Prcnt_Amt | NetworkDesign_Narrtv_Desc | RightsofWay_Prcnt_Amt | RightsofWay_Narrtv_Desc | ConstructPermit_Prcnt_Amt | ConstructPermit_Narrtv_Desc | SitePreprtn_Prcnt_Amt | SitePreprtn_Narrtv_Desc | EquipProcurmnt_Prcnt_Amt | EquipProcurmnt_Narrtv_Desc | NetworkBuild_Prcnt_Amt | NetworkBuild_Narrtv_Desc | EquipDeploy_Prcnt_Amt | EquipDeploy_Narrtv_Desc | NetworkTest_Prcnt_Amt | NetworkTest_Narrtv_Desc | Created_Date | Modified_Date | Created_Person_Id | Modified_Person_Id | Recipient | April 11, 2014 Cutoff Date
NT10BIX5570003 | 2010 | Q2 | Q2 - 2010 | 39 | 1278 | FALSE | 10 |  |  |  |  | 100 |  | 100 |  | 100 |  | 100 |  | 20 |  | 25 |  | 5 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2010 | Q3 | Q3 - 2010 | 433 | 1483 | TRUE | 17 | N/A | 0 | N/A | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 25 | N/A | 55 | A significant amount of equipment was ordered ahead of planned milestones when the baseline was initially completed. | 5 | Construction and overall project is lagging milestones as Projected in the Baseline Report. The Environmental approval was originally forecasted one quarter prior to actual receipt. | 15 | Construction and overall project is lagging milestones as Projected in the Baseline Report. The Environmental approval was originally forecasted one quarter prior to actual receipt. | 0 | 0 | 2010-11-29 11:46 | 2010-11-29 11:46 | 5446 | 5446 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2010 | Q4 | Q4 - 2010 | 1391 | 2407 | TRUE | 27 | An aggressive schedule for the last quarter fell short of our milestone when weather caused us to slow construction toward the end of the quarter. | 0 | N/A | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 42 | Site preparation has proceeded without any delays and we are currently exceeding our milestone in this category. | 62 | Partial equipment orders were extended into the next quarter causing some gap in milestone baseline achievement. | 10 | Although construction has fallen short of our projected milestones, additional miles have been implemented with fiber placement scheduled for the first half of this next calendar year. The project made minimal progress during the current quarter because of inclement weather. The intention is to advance the project once the weather passes for the season. | 50 | Equipment deployment has fallen short of milestone as a result of some construction not completed, we are anticipating reaching this by end of Q3, 2011. | 10 | The lack of equipment deployed and shortfall in network build have caused network testing to be short of baseline projection for this timeframe. We are confident that this category will be brought up to baseline within the next year. | 2011-02-28 16:12 | 2011-02-28 16:12 | 5446 | 5446 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2011 | Q1 | Q1 - 2011 | 1959 | 2725 | TRUE | 28 | Weather, as anticipated, slowed construction and expenditures in this quarter. | 0 | N/A | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 45 | Limited site preparation took place but the project continues to exceed projections in this category. | 62 | Minimal equipment purchases were anticipated this quarter as originally forecasted. Purchases planned prior to this time frame that will be made up before year end, will bring the project in line with Baseline Projections. | 20 | Additional miles were added to bring the project closer in line with projections earlier forecasted. This milestone will be the focus of 2011 as we commit to meeting the Broadband Technology Opportunities Program guidelines. | 50 | Equipment originally projected for installation has been moved out in the project timeline. This does not effect our build or potential subscribers. | 10 | Network testing is behind baseline projections, indicative of the lag in construction based upon original projections. | 2011-05-12 09:37 | 2011-05-12 09:37 | 5446 | 5446 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2011 | Q2 | Q2 - 2011 | 3001 | 3258 | TRUE | 41 | Aggressive Baseline projections have left this metric short of forecast, but thirteen percent above last quarter actuals. Additional expenditures in the next quarter will continue to bring this number in line with the Baseline. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 65 | No variance. | 75 | No variance. | 26 | The Network Build will continue to lag Baseline projections into 2012. Based on a later start to the construction of the project than originally forecasted, this metric will miss forecast. Additional resources have been allocated and the project will be completed as outlined in the Broadband Technology Opportunities Program guidelines. | 68 | Equipment Deployment although slightly behind Baseline currently will exceed the planned metric in the next quarter. | 20 | Testing is currently lagging Baseline projections due to Network Build progress. This metric will lag until the middle of 2012. | 2011-08-10 17:24 | 2011-08-10 17:24 | 5446 | 5446 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2011 | Q3 | Q3 - 2011 | 4229 | 3963 | TRUE | 59 | An aggressive Baseline projection has left this metric short of forecast by twenty two percent. Some of this shortfall will be made up over the next two quarters as we originally only projected a five percent increase for the same time period. Additional crews were added to accommodate this lag. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 85 | No Variance. | 75 | No Variance. | 50 | The Network Build milestone will continue to lag into the final year of the project. Components of this metric will continue to be incorporated into the project as construction activities take place. | 90 | Exceeding Baseline. Deployment and addition of some equipment will take place in this and following quarters. | 35 | Network Testing is currently lagging Baseline projections with the anticipation of making up some of this over the next two quarters. A smaller increase in the Baseline will allow for some 'catch up'. | 2011-11-22 15:39 | 2011-11-22 15:39 | 5445 | 5445 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2011 | Q4 | Q4 - 2011 | 5279 | 4949 | TRUE | 76 | An aggressive Baseline projection has left this metric short of forecast by seventeen percent. Some of this shortfall will be made up over the next two quarters as we originally only projected a five percent increase for the same time period. Additional crews were added to accommodate this lag. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 90 | No Variance. | 95 | Equipment procurement should be completed by end of quarter one in 2012. | 79 | The Network Build milestone will continue to lag into the final year of the project. Components of this metric will continue to be incorporated into the project as construction activities take place. | 90 | Exceeding Baseline. Deployment and addition of some equipment will take place in this and following quarters. | 60 | Testing of Network Equipment is currently meeting Baseline projections and will be completed by mid 2012. | 2012-02-27 10:37 | 2012-02-27 10:37 | 5445 | 5445 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2012 | Q1 | Q1 - 2012 | 6033 | 5616 | TRUE | 81 | An aggressive Baseline projection leaves this metric slightly behind planned progress. Necessary crews and goals have been established for the remaining months to insure the project meets the completion date as outlined in the requirements. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 95 | No Variance. | 100 | No Variance. | 83 | There is minimal lag in this metric as we continue to build network miles and expand the project to the initial plans. This metric will be met during the final months of the project timeline. | 100 | Exceeding Baseline. | 65 | No Variance. | 2012-05-11 08:32 | 2012-05-11 08:32 | 5445 | 5445 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2012 | Q2 | Q2 - 2012 | 6959 | 6107 | TRUE | 87 | An aggressive Baseline projection coupled with a longer than anticipated Environmental process has continued to see us lag in original Baseline projections. Minimal mileage remains to be built and will reach the end of construction in Q3 with final administrative tasks being completed in Q4 2012. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 95 | The Network build is nearing completion with final lateral routes still remaining with anticipation of completing construction in Q3 2012. | 100 | No Variance. | 80 | Once construction is completed and final subscriber connections are made, testing will be completed with an anticipated date sometime in the fourth quarter of 2012. | 2012-08-09 11:27 | 2012-08-09 11:27 | 5445 | 5445 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2012 | Q3 | Q3 - 2012 | 7851 | 6630 | TRUE | 90 | The majority of the project has been completed with only minimal construction remaining. The project is scheduled to be completed by the end of October with some remaining splicing and connections to Community Anchor Institutions left to complete as well. | 0 | N/A | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance | 100 | No Variance. | 100 | No Variance. | 95 | With the approval of an additional route this metric basically remained the same although additional miles were constructed this quarter. The build is scheduled to be completed by the end of October with minimal connections and splicing being completed in November. | 100 | No Variance. | 90 | Final Network testing will be completed as routes are finished and construction is wrapped up. | 2012-11-13 17:24 | 2012-11-13 17:24 | 5445 | 5445 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2012 | Q4 | Q4 - 2012 | 9037 | 7806 | TRUE | 100 | No Variance | 100 |  | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-02-27 16:34 | 2013-02-27 16:34 | 5445 | 5445 | South Dakota Network, LLC | TRUE
NT10BIX5570004 | 2010 | Q2 | Q2 - 2010 | 40 | 1335 | FALSE | 25 |  | 0 |  |  | 100 |  | 80 |  | 70 |  | 0 |  | 20 |  | 25 |  | 3 |  | 5 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2010 | Q3 | Q3 - 2010 | 299 | 1416 | TRUE | 22 | Project delayed due to pending EA approval | 0 |  | N/A | 85 | EA revisions to include Last Mile build caused delays | 70 | EA revisions to include Last Mile build caused delays | 70 | N/A | 0 | N/A | 10 | Project delayed due to pending EA approval | 10 | Project delayed due to pending EA approval | 0 | Project delayed due to pending EA approval | 0 | N/A | 0 | N/A | 2010-11-01 14:35 | 2010-11-01 14:35 | 5444 | 5444 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2010 | Q4 | Q4 - 2010 | 863 | 1898 | TRUE | 23 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 0 | N/A | N/A | 99 | Final approval received January 3, 2011. | 80 | Last Mile design will not be completed until the core and middle mile are completed. At that time last mile customers will have been determined. | 80 | Last Mile design will not be completed until the core and middle mile are completed. At that time last mile customers will have been determined. | 34 | N/A | 20 | N/A | 15 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. No contracts could be issued until after final environmental clearance. | 0 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 0 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 0 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 2011-01-28 17:51 | 2011-01-28 17:51 | 5444 | 5444 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2011 | Q1 | Q1 - 2011 | 1939 | 2715 | TRUE | 4 | Previous reports based on actual work complete not funds expended. Percent complete now reflects total funds expended versus total budget. The next quarter will reflect additional funds expended for equipment, core and middle mile fiber construction. | 0 | N/A | N/A | 100 | Environment Assessment Complete and fully expended. | 80 | Previous reports based on actual work complete not funds expended. Percent complete now reflects total funds expended versus total budget.Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts have been started and last mile construction is projected to begin in third quarter 2011. | 90 | Previous reports based on actual work complete not funds expended. Percent complete now reflects total funds expended versus total budget.Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts have been started and last mile construction is projected to begin in third quarter 2011. | 45 | Construction Permits and Other Approvals are 45 percent complete in first quarter 2011 which meets the baseline milestones. | 20 | Previous reports based on actual work complete not funds expended. Percent complete now reflects total funds expended versus total budget.The initial site preparation that was completed prior to the end of 2010 was all that was needed prior to the beginning of the construction. Construction of fiber plant began last week of March, 2011. We do anticipate an increase in site preparation in the second quarter of 2011. | 30 | Previous reports based on actual work complete not funds expended. Percent complete now reflects total funds expended versus total budget.An additional $5,000,000 has been specified, quote requested, approved for purchase, contracts executed, material not received at this time. Expenditure should be completed in second quarter 2011. | 1 | Previous reports based on actual work complete not funds expended. Percent complete now reflects total funds expended versus total budget.Construction of fiber plant began last week of March, 2011. Plan for all core and middle mile fiber construction to be completed by third quarter 2011. IRU negotiations are ongoing and should be completed by end of second quarter 2011. | 0 | Previous reports based on actual work complete not funds expended. Percent complete now reflects total funds expended versus total budget.Equipment procurement is complete but not received for core and middle mile fiber, SPOP/CPOP equipment, last mile equipment. Equipment deployment will begin in second quarter 2011 and we are projecting to meet our third quarter 2011 milestone.. | 10 | Testing is 10 percent complete in first quarter 2011 which meets the baseline milestones. | 2011-05-11 11:41 | 2011-05-11 11:41 | 5751 | 5751 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2011 | Q2 | Q2 - 2011 | 3031 | 3273 | TRUE | 8 | Third quarter will reflect additional funds expended for equipment, core and middle mile fiber construction and last mile deployment. | 0 | N/A | N/A | 100 | Environment Assessment Complete and fully expended. | 80 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts have been started and last mile construction is projected to begin in third quarter 2011. | 90 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts have been started and last mile construction is projected to begin in third quarter 2011. | 50 | Construction Permits and Other Approvals are 50 percent complete in second quarter 2011 which meets the baseline milestones. | 35 | The initial site preparation that was completed prior to the end of 2010 was all that was needed prior to the beginning of the construction. Construction of fiber plant began last week of March, 2011. Site Preparation will continue with the installation of core and middle mile fiber and last mile construction. We do anticipate an increase in site preparation in the third quarter of 2011. | 50 | An additional $5,000,000 has been specified, quote requested, approved for purchase, contracts executed, material not received at this time. Expenditure should be completed in third quarter 2011. | 15 | Over one hundred thirteen miles of core fiber completed through second quarter. Plan for all core and middle mile fiber construction to be completed by third quarter 2011. IRU negotiations are ongoing and should be completed by end of third quarter 2011. | 15 | Equipment procurement is complete but not received for core and middle mile fiber, SPOP/CPOP equipment, last mile equipment. Equipment deployment will begin in third quarter 2011 and we are projecting to meet our third quarter 2011 milestone. | 15 | Testing is 15 percent complete in second quarter 2011 which meets the baseline milestones. | 2011-08-11 18:25 | 2011-08-11 18:25 | 7129 | 7129 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2011 | Q3 | Q3 - 2011 | 4205 | 3951 | TRUE | 30 | Fourth quarter will reflect additional funds expended for equipment, core and middle mile fiber construction and last mile deployment. We do expect to be sixty-seven percent complete which will meet our baseline milestones. | 0 |  | N/A | 100 | Environment Assessment Complete and fully expended. | 85 | Last mile design will not be completed until after the core and middle mile construction is completed. After that time most of the last mile customer will have been determined. Last mile marketing efforts have continued and last mile construction began the last week of September 2011. | 90 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts continued and last mile construction began the last week of September 2011. | 58 | Construction Permits and Other Approvals are 58 percent complete in third quarter 2011 which meets the baseline milestones. | 48 | The initial site preparation that was completed prior to the end of 2010 was all that was needed prior to the beginning of the construction. Construction of fiber plant began last week of March, 2011 and last mile construction began the last week of September. Site Preparation will continue with the installation of core and middle mile fiber and last mile construction. | 53 | Additional material has been specified, quotes requested, approved for purchase, materials not received at this time. Expenditures should be completed in fourth quarter 2011. | 25 | Over 277 miles of core, middle and last mile fiber completed through third quarter. Plan for all core and middle mile fiber construction to be completed by fourth quarter 2011. IRU negotiations are ongoing with contracts in hand and should be completed by end of fourth quarter 2011. | 40 | Equipment procurement is complete but not received for core and middle mile fiber, SPOP/CPOP equipment, last mile equipment. Equipment deployment began the end of September 2011 and we are projecting to meet our fourth quarter 2011 milestone. | 25 | Testing is 25 percent complete in third quarter 2011 which meets the baseline milestones. | 2011-11-21 21:31 | 2011-11-21 21:31 | 5751 | 5751 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2011 | Q4 | Q4 - 2011 | 5203 | 4874 | TRUE | 65 | First quarter 2012 will reflect additional funds expended for core, middle and last mile deployment. We do expect to be seventy-five percent complete which will meet our baseline milestones. | 0 |  | N/A | 100 | Environment Assessment Complete and fully expended. | 88 | Last mile design will not be completed until after the core and middle mile construction is completed. After that time most of the last mile customer will have been determined. Last mile marketing efforts will continue until the end of the project. | 92 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts will continue until the end of the project. | 67 | Meets baseline report | 67 | Meets baseline report | 67 | Meets baseline report | 50 | Meets baseline report | 60 | Meets baseline report | 35 | Meets baseline report | 2012-02-23 10:23 | 2012-02-23 10:23 | 5751 | 5751 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2012 | Q1 | Q1 - 2012 | 6317 | 5761 | TRUE | 67 | Second quarter 2012 will reflect additional funds expended for core, middle and last mile deployment. We do expect to be eighty-four percent complete which will meet our baseline milestones. | 0 | N/A | N/A | 100 | Environment Assessment Complete and fully expended. | 91 | Last mile design will not be completed until after the core and middle mile construction is completed. After that time most of the last mile customer will have been determined. Last mile marketing efforts will continue until the end of the project. | 95 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts will continue until the end of the project. | 75 | Meets baseline report | 75 | Meets baseline report | 75 | Meets baseline report | 55 | Meets baseline report | 75 | Meets baseline report | 45 | Meets baseline report | 2012-05-29 12:11 | 2012-05-29 12:15 | 7129 | 7129 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2012 | Q2 | Q2 - 2012 | 7099 | 6177 | TRUE | 74 | Third quarter 2012 will reflect additional funds expended for core, middle and last mile deployment. We do expect to be ninety-two percent complete which will meet our baseline milestones. Invoices from contractors were not received until July so they were unable to be paid by June 30. | 0 | N/A | N/A | 100 | Environment Assessment Complete and fully expended. | 94 | Last mile design will not be completed until after the core and middle mile construction is completed. After that time most of the last mile customer will have been determined. Last mile marketing efforts will continue until the end of the project. | 97 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts will continue until the end of the project. | 83 | Meets baseline report | 83 | Meets baseline report | 83 | Meets baseline report | 75 | Meets baseline report | 80 | Meets baseline report | 55 | Meets baseline report | 2012-08-15 18:51 | 2012-08-15 18:51 | 7129 | 7129 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2012 | Q3 | Q3 - 2012 | 7665 | 6512 | TRUE | 85 | Fourth quarter 2012 will reflect additional funds expended for middle and last mile deployment. We do expect to be 100 percent complete. Invoices from contractors were not received until October so they were unable to be paid by September 30. | 0 | N/A | N/A | 100 | Environment Assessment Complete and fully expended. | 97 | Last mile design will not be completed until after the core and middle mile construction is completed. After that time most of the last mile customer will have been determined. Last mile marketing efforts will continue until the end of the project. | 99 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts will continue until the end of the project. | 92 | Meets baseline report | 92 | Meets baseline report | 92 | Meets baseline report | 85 | Meets baseline report | 90 | Meets baseline report | 75 | Meets baseline report | 2012-10-30 19:10 | 2012-10-30 19:10 | 7129 | 7129 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2012 | Q4 | Q4 - 2012 | 9175 | 8008 | TRUE | 100 | Meets baseline report | 0 | N/A | Meets baseline report | 100 | Meets baseline report | 100 | Meets baseline report | 100 | Meets baseline report | 100 | Meets baseline report | 100 | Meets baseline report | 100 | Meets baseline report | 100 | Meets baseline report | 100 | Meets baseline report | 100 | Meets baseline report | 2013-04-12 14:31 | 2013-04-12 14:31 | 5751 | 5751 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570006 | 2010 | Q2 | Q2 - 2010 | 41 | 1311 | FALSE | 15 |  |  |  |  | 100 |  | 100 |  | 100 |  | 35 |  | 10 |  | 10 |  | 10 |  |  |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Biddeford Internet Corp. | TRUE
NT10BIX5570007 | 2010 | Q2 | Q2 - 2010 | 42 | 1314 | FALSE | 8.47 |  | 53.85 |  |  | 100 |  | 100 |  | 16.72 |  | 12.9 |  | 2.41 |  | 11.23 |  | 3.95 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | ION HOLDCO, LLC | TRUE
NT10BIX5570009 | 2010 | Q2 | Q2 - 2010 | 43 | 1283 | FALSE | 20 |  | 30 |  |  | 99 |  | 60 |  | 60 |  | 20 |  | 10 |  | 30 |  | 2 |  | 5 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2010 | Q3 | Q3 - 2010 | 343 | 1438 | TRUE | 15 | Given the below comments the primary challenge we face is coordinating work all the types of agencies and working through the proper avenues of approval. | 30 | Staffing | None Noted | 100 | None Noted | 60 | None Noted | 75 | The reason we're not 90% is that final CAD necessary for applications is not available yet from TKNS. We do have most pole attachment agreements in place, though. | 40 | None Noted | 0 | Given the proper permits are not in place we have note been given the proper clearances to move forward. | 0 | Merit will have selected a vendor, but we have changed our purchasing strategy to "just in time". Our baseline plan assumed that equipment would be purchased in advance with a 90-day lead time and warehoused. | 0 | None Noted | 0 | None Noted | 0 | None Noted | 2010-11-18 08:37 | 2010-11-18 08:37 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2010 | Q4 | Q4 - 2010 | 1345 | 2363 | TRUE | 30 | Give the previous quarter's challenges we may not be able to catch up at this point but plan to within the next quarter and the quarter after that. | 40 | Staffing | None Noted. | 100 | None Noted | 85 | None Noted | 85 | Given that the CAD necessary for applications was not provided from our engineering firm until the middle of December Merit has not received all of the responses from the proper agencies. | 45 | Our engineering consultant has submitted over 100 permits with errors. The permits are getting fixed and we have set a process in place to detect these errors in the in future. | 10 | Site preparation is still one quarter behind due to permitting problems addressed above. | 10 | Merit has received equipment from the selected vendor for multiple locations but Merit has not been billed for the equipment at this point. Merit anticipates deployment in the next quarter after the equipment is properly tested. | 1 | Permitting has been slower that originally anticipated; therefore, we have not had access to construct as much as originally reported. | 0 | The equipment that has been purchased but not deployed due to timeing issues. Merit feels the equipment will be deployed early next quarter. | 0 | The Network has not been tested considering the Equipment has not be deployed. | 2011-02-23 15:52 | 2011-02-23 15:52 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2011 | Q1 | Q1 - 2011 | 2265 | 2878 | TRUE | 9 | Based on the more specific guidance issued by the NTIA regarding the percentage calculation, we need to report a lower number in this category than had previously been reported. The combination of delays in several milestone categories has resulted in significantly less spending than we projected; however, once construction is fully underway, we anticipate closing the gap between our current status and the Baseline Plan. | 42 |  | We are slightly under budget in this category because engineering staff have not completed the installation training. | 100 | The Environmental Assessment (EA) is actually at 375% of budget, and continues to grow slowly. Since our Finding of No Significant Impact (FONSI) was issued, we have needed and will continue to need to work with our environmental consulting firm on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the significant overrun, we do not anticipate revising the budget as reported on Form 424C; the EA is a component of the Engineering budget, and we are significantly under budget in that category at this time. We are confident that the Engineering budget will be able to absorb the current overrun, as well as the additional EA costs between now and completion, estimated at 732%. | 16 | Engineering has cost significantly less than originally budgeted. This is offset by the EA subcategory (split out separately for the purpose of reporting), which has cost significant more than anticipated. The percent complete number, when based solely on financials, does not reflect that network design for the fiber optic backbone is complete aside from occasional route changes required by permit kickbacks. Also, based on the more specific guidance issued by the NTIA regarding the percentage calculation, we need to report a lower number in this category than had previously been reported. | 100 | We have exceeded our budget for rights-of-way permitting (we are at 172%), however, work still remains to be done. We estimate the percentage at completion will be 180%, and the funds will come out of the construction budget. There are several municipalities who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution (CAI) builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for construction permitting (we are at 172%), however, work still remains to be done. We estimate the percentage at completion will be 180%, and the funds will come out of the construction budget. There are several pole owners who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution (CAI) builds and route changes necessitated by schedule or engineering. | 0 | We are in the middle of the procurement process for selecting a contractor to perform the site preparation work; we are also still in the process of finalizing central office and community anchor routes. We will be catching up by prepping the site prior to the arrival of the backbone fiber to the anchor, allowing us to get more site preparation complete in a short time frame. Wherever possible, we will save time by purchasing existing entrances to the central office facilities. | 10 | We have begun procuring optical equipment. Merit does not want to deploy optical equipment until we are closer to the fiber installation date. Due to a lack of storage capacity in our business office, we feel it is wasteful to order more equipment at this time than we are ready to deploy. | 2 | We are slightly behind on the network build because we are still waiting for the Davis Bacon Act wage determinations to be issued. We have temporarily secured the services of an underground construction firm so that we could begin some construction, but Merit cannot enter into a contract with a construction firm without attaching the applicable wage determinations. We anticipate bringing on several construction crews and beginning aerial construction in the quarter after next (2011 Q3) | 0 | Merit has just hired an engineer to deploy and test optical equipment; we anticipate being routinely under budget in this category, since it comprises 36 months of salary. We are so early in the deployment process, it is difficult to assess whether or not the difference will be made up by the end of the project, but I believe that we will be at or close to budget by completion. | 0 | Merit has just hired an engineer to deploy and test optical equipment; we anticipate being routinely under budget in this category, since it comprises 36 months of salary. We also have not incurred expense for testing equipment at this time. We are so early in the deployment process, it is difficult to assess whether or not the difference will be made up by the end of the project, but I believe that we will be at or close to budget by completion. | 2011-05-24 09:26 | 2011-05-24 09:26 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2011 | Q2 | Q2 - 2011 | 3029 | 3272 | TRUE | 14 | The combination of delays in several milestone categories has resulted in significantly less spending than we projected; however, once construction is fully underway, we anticipate closing the gap between our current status and the Baseline Plan. | 65 | Staffing, Misc. | We are slightly over budget in this category because legal fees were higher than projected. We believe the difference will be eliminated next quarter, since we are not yet at projected staffing levels. | 100 | The Environmental Assessment is actually at 387% of budget.Since our Finding of No Significant Impact was issued, we have needed to work with our environmental consulting firm on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the overrun, we do not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and we are significantly under budget in that category at this time. We are confident that the Engineering budget will be able to absorb the current overrun, as well as the additional Environmental Assessment costs between now and completion, estimated at 400%. | 17 | Engineering has cost significantly less than originally budgeted. This is offset by the Environmental Assessment subcategory (split out separately for the purpose of reporting), which has cost significant more than anticipated. The percent complete number, when based solely on financials, does not reflect that network design for the fiber optic backbone is complete aside from route changes required by permit kickbacks. | 100 | We have exceeded our budget for rights-of-way permitting (we are at 196%), however, work still remains to be done. We estimate the percentage at completion will be 200%, and the funds will come out of the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for construction permitting (we are at 196%), however, work still remains to be done. We estimate the percentage at completion will be 200%, and the funds will come out of the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 0 | We selected a contractor to perform the site preparation work; we are also still in the process of finalizing central office and community anchor routes. We will be catching up by prepping the site prior to the arrival of the backbone fiber to the anchor, allowing us to get more site preparation complete in a short time frame. Wherever possible, we will save time by purchasing existing entrances to the central office facilities. | 15 | We have begun procuring optical equipment. Merit does not want to deploy optical equipment until we are closer to the fiber installation date. Due to a lack of storage capacity in our business office, we feel it is wasteful to order more equipment at this time than we are ready to deploy. | 8 | We are slightly behind on the network build because of the wait for the Davis Bacon Act wage determinations to be issued. However, we now have contracts with seven construction firms, and we anticipate bringing on several construction crews and beginning aerial construction next quarter. | 0 | We have not incurred expense for equipment deployment at this time. Merit has not completed enough construction to warrant placing equipment in the field during this quarter. We are early in the deployment process, but Merit will be most likely be at or close to budget by completion. | 0 | We have not incurred expense for testing equipment at this time. Merit has not completed enough construction to do network testing in this quarter. We are early in the deployment process, but Merit will be most likely be at or close to budget by completion. | 2011-08-11 16:39 | 2011-08-11 16:39 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2011 | Q3 | Q3 - 2011 | 3947 | 3812 | TRUE | 22 | Permitting (both construction and environmental) delays have resulted in less spending than originally projected. Once multiple construction deployments commence (which will occur in the very near future) we anticipate closing the gap between our current status and the Baseline Plan. | 75 |  | We hired a full-time project manager for the entire project as well as a mapping specialist and grants clerk. We are also in the process of hiring another full-time permit coordinator and an additional engineer to conduct site visits and site preparation. We are slightly over budget this quarter due to unforeseen legal expenses. | 100 | The Environmental Assessment is actually at 427% of budget.Since our Finding of No Significant Impact was issued, we have needed to work with our environmental consulting firm on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the overrun, we do not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and we are significantly under budget in that category at this time. We are confident that the Engineering budget will be able to absorb the current overrun. There are no known additional Environmental Assessment charges. | 21 | While the engineering expense cost less than anticipated, we have had significant delays in getting our environmental clearances. The current percent complete does not accurately reflect that network design for fiber optic backbone is complete. The route changes occurred due to changes required by permitting entities. | 100 | We have exceeded our budget for rights-of-way permitting (we are at 237%), however, work still remains to be done. We estimate the percentage at completion will be 250%, and the funds will come out of the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for construction permitting (we are at 237%), however, work still remains to be done. We estimate the percentage at completion will be 250%, and the funds will come out of the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 0 | We have almost completed the process of finalizing central office and community anchor institution routes. Last quarter we selected a contractor to perform site preparation work and they are diligently conducting site visits. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 15 | We have continued to purchase equipment and have recently opened a 50,000 square foot warehouse in Waters, Michigan to house our equipment. We have also hired a full-time employee to manage the warehouse, receive deliveries and deploy equipment to contractors as necessary. | 19 | We have contracts with seven construction firms, each with multiple construction crews and have begun aerial construction in the Southern region. Other areas of aerial construction are planned to start in the very near future as permits are being approved. We are currently over 60% complete on all Round 1 permits, of which there are 1,256 needed. | 0 | We have not incurred expense for equipment deployment at this time. Merit has not completed enough construction to warrant placing equipment in the field. As we are early in the deployment process, Merit will most likely be at or close to budget by completion. | 1 | We have incurred a minimal expense for testing equipment this quarter. We are still early in the deployment process, but Merit will likely be close or at budget at completion. | 2011-11-10 07:48 | 2011-11-10 07:52 | 5485 | 5485 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2011 | Q4 | Q4 - 2011 | 5319 | 4990 | TRUE | 36 | Permitting (both construction and environmental) delays have resulted in less spending than originally projected. Multiple construction deployments have commenced this quarter, but have not yet been invoiced, so we anticipate closing the gap between our current status and the Baseline Plan in subsequent quarters. | 81 |  | Spending in this category has evened out, and is only 1% above the Baseline Projection, largely due to unforeseen legal expenses. We anticipate being at budget by project completion. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with our environmental consulting firm and the Michigan Department of Environmental Quality (MDEQ) on ways to minimize our project's impact in sensitive areas and remain in compliance. We also needed to do additional work to obtain environmental approval from the NTIA for route changes. Despite the overrun, we do not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and we are significantly under budget in that category at this time. We are confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 24 | Engineering has so far cost far less than anticipated, and we have had significant delays in getting our environmental clearances. The current percent complete does not accurately reflect that network design for fiber optic backbone is complete. Final CADs cannot be produced until construction is complete, so we anticipate seeing a significant portion of the budget funds expended in the third and fourth quarters of 2012. | 100 | We have exceeded our budget for rights-of-way permitting (266%), however, some work still remains to be done. We estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for construction permitting (266%), and some work still remains to be done. We estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 0 | We have almost completed the process of finalizing central office and community anchor institution routes. Last quarter we selected a contractor to perform site preparation work and they are diligently conducting site visits. Some work has been completed this quarter, but Merit was not invoiced during the reporting period. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 20 | Most of the dense wave division multiplex (DWDM) equipment was ordered this quarter. It arrived in December, and we anticipate being invoiced next quarter. The procurement process for routers and switches was nearly completed, with contracts being in the final stages of negotiation at the close of the reporting period. Merit anticipates being at budget by project completion. | 36 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 0 | Merit has not incurred expense for equipment deployment at this time, because not enough construction has been completed to warrant ordering and placing equipment in the field. However, with construction actively underway, spending in this category will increase, and Merit will be at or close to budget by completion. | 52 | Test equipment has been purchased; once more construction is complete, testing will be performed, and the percent complete is projected to be at budget by project completion. | 2012-02-27 17:13 | 2012-02-27 17:13 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2012 | Q1 | Q1 - 2012 | 6119 | 5662 | TRUE | 44 | Permitting (both construction and environmental) delays have resulted in less spending than originally projected. Multiple construction deployments have commenced this quarter, but have not yet been invoiced, so Merit anticipates closing the gap between our current status and the Baseline Plan in subsequent quarters. | 94 | Staffing, Miscellaneous | Spending in this category has evened out, and we anticipate being at budget by project completion. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with our environmental consulting firm and the Michigan Department of Environmental Quality (MDEQ) on ways to minimize our project's impact in sensitive areas and remain in compliance. Merit also needed to do additional work to obtain environmental approval from the NTIA for route changes. Despite the overrun, Merit does not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and Merit is under budget in that category at this time. Merit is confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 32 | Engineering has so far cost less than anticipated, and we have had some delays in getting our environmental clearances. The current percent complete does not accurately reflect that network design for fiber optic backbone is complete. Final CADs cannot be produced until construction is complete, so Merit anticipates seeing a significant portion of the budget funds expended in the third and fourth quarters of 2012. | 100 | Merit has exceeded our budget for rights-of-way permitting (269%), however, some work still remains to be done. Merit estimates the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, Merit may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | Merit has exceeded our budget for construction permitting (269%), and some work still remains to be done. Merit estimates the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, Merit may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 0 | Merit has almost completed the process of finalizing central office and community anchor institution routes. A contractor has been selected to perform site preparation work and they are diligently conducting site visits. Some work has been completed this quarter, but Merit was not invoiced during the reporting period. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 46 | The procurement process for routers and switches was completed, and Merit plans to order this equipment in Q2 2012. Merit anticipates being at budget by project completion. | 42 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 0 | Merit has not incurred expense for equipment deployment at this time, because not enough construction has been completed to warrant ordering and placing equipment in the field. However, with construction actively underway, spending in this category will increase, and Merit will be at or close to budget by completion. | 52 | Test equipment has been purchased; once more construction is complete, testing will be performed, and the percent complete is projected to be at budget by project completion. | 2012-05-16 09:10 | 2012-05-16 09:10 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2012 | Q2 | Q2 - 2012 | 6949 | 6102 | TRUE | 55 | Permitting (both construction and environmental) delays Merit encountered early in the project has resulted in less spending to date than originally projected. Construction is fully underway and Merit is awaiting invoicing for the construction being completed, so Merit anticipates closing the gap between our current status and the Baseline Plan in subsequent quarters. | 100 | Staffing, Miscellaneous | Spending in this category has reached 104% of budget. Merit anticipates that there should be minimal expenses in this category over the remainder of the project. Surplus funds from the Network Testing Category will cover the cost overruns for staffing and miscellaneous expenses. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with our environmental consulting firm and the Michigan Department of Environmental Quality (MDEQ) on ways to minimize our project's impact in sensitive areas and remain in compliance. Merit also needed to do additional work to obtain environmental approval from the NTIA for route changes. Despite the overrun, Merit does not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and Merit is under budget in that category at this time. Merit is confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 35 | Engineering has so far cost less than anticipated, and we have had some delays in getting our environmental clearances. The current percent complete does not accurately reflect that network design for fiber optic backbone is complete. Final CADs cannot be produced until construction is complete, so Merit anticipates seeing a significant portion of the budget funds expended in the third and fourth quarters of 2012. | 100 | Merit has exceeded our budget for rights-of-way permitting (276%), however, some work still remains to be done. Merit estimates the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, Merit may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | Merit has exceeded our budget for construction permitting (276%), and some work still remains to be done. Merit estimates the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, Merit may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 0 | Merit has almost completed the process of finalizing central office and community anchor institution routes. A contractor has been selected to perform site preparation work and they are diligently conducting site visits. Some work has been completed this quarter, but Merit was not invoiced during the reporting period. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner | 67 | All optical hardware has been procured and invoiced, and the procurement process for routers and switches was completed this quarter. Merit anticipates being at budget by project completion. | 53 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant spending rate in this budget category, and will be at budget by project completion. | 0 | Merit has not incurred expense for equipment deployment at this time, because not enough construction has been completed to warrant ordering and placing equipment in the field. However, with construction actively underway, spending in this category will increase, and Merit will be at or close to budget by completion. Major deployments are scheduled for the second half of the third quarter. | 52 | Test equipment has been purchased; once more construction is complete, testing will be performed. However, due to the scheduling and staffing efficiencies achieved by combining deploying equipment, site preparation, and testing the network on single runs, this category is projected to be under budget by project completion. | 2012-08-09 09:17 | 2012-08-09 09:17 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2012 | Q3 | Q3 - 2012 | 8035 | 6724 | TRUE | 71 | The construction and environmental permit delays Merit experienced at the outset of the project has resulted in less spending to date than originally projected. Construction is fully underway and Merit is working quickly towards completing project construction. Merit anticipates having the build completed during the fourth quarter. | 100 | Staffing, Miscellaneous | Spending in this category has reached 107% of the budgeted amount. Merit anticipates that there should be minimal expenses in this category over the remainder of the project. Surplus funds from the Network Testing and Network Design categories will cover this cost overrun. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with the environmental consulting firm and the Michigan Department of Environmental Quality on ways to minimize our projectâ€™s impact and remain in compliance. Merit also needed to do additional work to obtain environmental approval from the National Telecommunications & Information Administration for route changes. Despite the overrun Merit does not anticipate revising the budget as reported on Form 424C. The Environmental Assessment is a component of the Engineering budget and Merit is currently under budget in that category. Merit is confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 40 | The percentage of completion does not accurately reflect that the network design for fiber optic backbone is complete. Final CADs cannot be produced until construction is complete, so Merit anticipates seeing a significant portion of the budget funds expended in the fourth quarter of 2012. At this point, the engineering costs have been far less than anticipated. | 100 | Merit has exceeded our budget for the rights-of-way permitting (285%). However, some work still remains to be done. Merit estimates the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, Merit may need to submit additional permit applications for Community Anchor Institution builds and route changes necessitated by the schedule or engineering. | 100 | Merit has exceeded our budget for the rights-of-way permitting (285%). However, some work still remains to be done. Merit estimates the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, Merit may need to submit additional permit applications for Community Anchor Institution builds and route changes necessitated by the schedule or engineering. | 0 | Merit has completed the process of finalizing central office and Community Anchor Institution routes. A contractor has been selected to perform site preparation work and they are diligently conducting site visits. Some work has been completed this quarter, but Merit was not invoiced during the reporting period. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner | 92 | All optical hardware has been procured and invoiced, and the procurement process for routers and switches was completed this quarter. Merit anticipates being at budget by project completion. | 72 | Merit has contracts with seven (7) construction firms. The seven (7) firms have multiple construction crews that are performing aerial and underground construction across the funded network. Merit anticipates being at budget by the end of the fourth quarter. | 0 | Merit has not incurred expenses for equipment deployment at this time. However, with construction actively underway spending in this category will increase. Merit will be at or close to budget by completion. Major deployments are scheduled during the fourth quarter as construction is completed. | 52 | Test equipment has been purchased. As construction is completed testing will be performed. This category is projected to be under budget by project completion due to the scheduling and staffing efficiencies achieved in deploying equipment, site preparation, and testing the network on single runs. | 2012-11-26 12:38 | 2012-11-26 12:38 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2012 | Q4 | Q4 - 2012 | 8973 | 7754 | TRUE | 90 | The construction and environmental permit delays Merit experienced at the outset of the project has resulted in less spending to date than originally projected. Merit made great progress with construction during the 2012 fourth quarter and is wrapping up the remaining construction to complete the project. Merit anticipates having all construction completed by early 2013. | 100 | Staffing, Miscellaneous | Spending in this category has reached 107% of the budgeted amount. Merit anticipates that there should be minimal expenses in this category over the remainder of the project. Surplus funds from the Network Testing and Network Design categories will cover this cost overrun. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with the environmental consulting firm and the Michigan Department of Environmental Quality on ways to minimize our projectâ€™s impact and remain in compliance. Merit also needed to do additional work to obtain environmental approval from the National Telecommunications & Information Administration for route changes. Despite the overrun Merit does not anticipate revising the budget as reported on Form 424C. The Environmental Assessment is a component of the Engineering budget and Merit is currently under budget in that category. Merit is confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 44 | The percentage of completion does not accurately reflect that the network design for fiber optic backbone is complete. Final CADs cannot be produced until construction is complete, so Merit anticipates seeing a significant portion of the budget funds expended as the project wraps up, and will also contain costs relating to site preparation as well as absorb some of the Environmental Assessment costs. | 100 | Merit has exceeded our budget for the rights-of-way permitting (288%). However, some work may still remain. Merit estimates the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, Merit may need to submit additional permit applications for Community Anchor Institution builds and route changes necessitated by the schedule or engineering. | 100 | Merit has exceeded our budget for the rights-of-way permitting (288%). However, some work may still remain. Merit estimates the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, Merit may need to submit additional permit applications for Community Anchor Institution builds and route changes necessitated by the schedule or engineering. | 0 | Based on the way we have been categorizing expenses, site preperation items have been placed in the Network Design category. | 100 | All optical hardware has been procured and invoiced, and the procurement process for routers and switches was completed. Merit anticipates being at budget by project completion. | 98 | Merit has contracts with seven (7) construction firms. The seven (7) firms have multiple construction crews that are performing aerial and underground construction across the funded network. Merit anticipates being at budget by the end of the next quarter. | 62 | Merit anticipates rounding out spending in the next quarter as equipment is finished being placed and fiber is lit. | 52 | Test equipment has been purchased. As construction is completed testing will be performed. This category is projected to be under budget by project completion due to the scheduling and staffing efficiencies achieved in deploying equipment, site preparation, and testing the network on single runs. | 2013-02-26 14:18 | 2013-02-26 14:18 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2013 | Q1 | Q1 - 2013 | 10001 | 8545 | TRUE | 96 | The construction and environmental permit delays Merit experienced at the outset of the project has resulted in less spending to date than originally projected. Merit has completed construction and is now working on and completing final testing and any repairs that are necessary. | 100 | Staffing, Miscellaneous | Spending in this category has reached 120% of the budgeted amount. Merit anticipates that there should be minimal expenses in this category over the remainder of the project. Surplus funds from the Network Testing and Network Design categories will cover this cost overrun. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with the environmental consulting firm and the Michigan Department of Environmental Quality on ways to minimize our projectâ€™s impact and remain in compliance. Merit also needed to do additional work to obtain environmental approval from the National Telecommunications & Information Administration for route changes. Despite the overrun Merit does not anticipate revising the budget as reported on Form 424C. The Environmental Assessment is a component of the Engineering budget and Merit is currently under budget in that category. Merit is confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 45 | The percentage of completion does not accurately reflect that the network design for fiber optic backbone is complete. Final CADs cannot be produced until construction is complete, so Merit anticipates seeing additional budget funds expended as the project wraps up, and will also contain costs relating to site preparation as well as absorb some of the Environmental Assessment costs. | 100 | Merit has exceeded our budget for the rights-of-way permitting (288%). However, some work may still remain. Merit estimates the percentage at completion will be under 300%. | 100 | Merit has exceeded our budget for the rights-of-way permitting (288%). However, some work may still remain. Merit estimates the percentage at completion will be under 300%. | 1 | Based on the way we have been categorizing expenses, most site preparation items have been placed in the Network Design category. | 100 | Equipment procurement is currently at 102%. All optical hardware has been procured and invoiced, and the procurement process for routers and switches was completed. | 100 | Merit has contracts with seven (7) construction firms. The seven (7) firms have multiple construction crews that are perfored aerial and underground construction across the funded network. Merit is currently at 108% of the Network Build budget and will have final contractor invoices coming in over the next quarter. | 100 | Merit is at 129% of the budget amount in this category but anticipates minimal spending in the following quarter as all equipment has been placed. | 53 | Construction is completed and some testing has occurred so far. Additional testing will take place over the following quarter. | 2013-05-30 07:28 | 2013-05-30 07:28 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2013 | Q2 | Q2 - 2013 | 10523 | 8915 | TRUE | 99 | The construction and environmental permit delays Merit experienced at the outset of the project has resulted in less spending to date than originally projected. Merit has completed construction and is now working on and completing final testing and any repairs that are necessary. | 100 | Staffing, Miscellaneous | Spending in this category has reached 178% of the budgeted amount. Merit anticipates that there should be minimal expenses in this category over the remainder of the project. Surplus funds from the Network Testing and Network Design categories will cover this cost overrun. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with the environmental consulting firm and the Michigan Department of Environmental Quality on ways to minimize our projectâ€™s impact and remain in compliance. Merit also needed to do additional work to obtain environmental approval from the National Telecommunications & Information Administration for route changes. Despite the overrun, Merit is under budget in other areas and should be able to absorb the overage in those categories. | 47 | The percentage of completion does not accurately reflect that the network design for fiber optic backbone is complete. Final CADs are being produced now that construction is complete, so Merit anticipates seeing additional budget funds expended as the project wraps up, and will also contain costs relating to site preparation as well as absorb some of the Environmental Assessment costs. | 100 | Merit has exceeded our budget for the rights-of-way permitting (294%). However, some work may still remain. Merit estimates the percentage at completion will be under 300%. | 100 | Merit has exceeded our budget for the rights-of-way permitting (294%). However, some work may still remain. Merit estimates the percentage at completion will be under 300%. | 1 | Based on the way we have been categorizing expenses, most site preparation items have been placed in the Network Design category. | 100 | Equipment procurement is currently at 102%. All optical hardware has been procured and invoiced, and the procurement process for routers and switches was completed. | 100 | Merit has contracts with seven (7) construction firms. The seven (7) firms have multiple construction crews that are perfored aerial and underground construction across the funded network. Merit is currently at 109% of the Network Build budget and will have final contractor invoices coming in over the next quarter. | 100 | Merit is at 129% of the budget amount in this category but anticipates minimal spending in the following quarter as all equipment has been placed. | 53 | Construction is completed and some testing has occurred so far. Additional testing will take place over the following quarter. | 2013-08-08 14:06 | 2013-08-08 14:06 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2013 | Q3 | Q3 - 2013 | 12677 | 10991 | TRUE | 100 | Merit has completed the REACH-3MC Project. | 100 | Staffing, Miscellaneous | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 2015-02-04 09:08 | 2015-02-04 09:08 | 7981 | 7981 | Merit Network Inc. | TRUE
NT10BIX5570011 | 2010 | Q2 | Q2 - 2010 | 44 | 1298 | FALSE | 8 |  | 0 |  |  | 100 |  | 100 |  | 25 |  | 25 |  | 0 |  | 15 |  | 10 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | 2010 | Q3 | Q3 - 2010 | 383 | 1458 | TRUE | 8 | N/A | 0 |  | N/A | 100 | N/A | 72 | 887 miles were projected in the baseline in the project. 197 were part of an existing IRU, 223 from IRU's to be obtained, and 467 from new construction. 197 miles has been acquired under new executed IRU's that have been completed, and 199 miles designed totaling 593 miles (including the initial 197 IRU miles). An IRU with Morris was communicated to NTIA that will replace 50 miles of new build. Of the 887 miles, 593 has been obtained or designed, approximately 72% of the total. The remaining 28% are scheduled to be complete by end of next quarter. | 2 | We have applied for approximately 48% of the required ROW's but as of quarter end had not received all back. We were delayed somewhat in our application for these by not yet having received the FONSI. We expect to receive all that have been applied for by end of next quarter to be back on track and apply for more as formal engineering is completed. | 2 | We have applied for approximately 48% of the required ROW's but as of quarter end had not received completed all back. We were delayed somewhat in our application for these by not yet having received the FONSI. We expect to receive all that have been applied for by end of next quarter to be back on track and apply for more as formal engineering is completed. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-23 11:38 | 2010-11-23 11:38 | 5748 | 5748 | MCNC | TRUE
NT10BIX5570011 | 2010 | Q4 | Q4 - 2010 | 1169 | 2204 | TRUE | 15 | We got a slower start to construction than planned due to delay in encroachment issues and finalizing contracts with construction vendors. We however believe we will be back on schedule by end of Y2Q1. | 0 |  | Not Applicable | 100 | EA done, FONSI received. Amendment for required network reroute due by February. | 97 | NCDOT rejected initial encroachment request on US Hwy 264 due to controlled access and suggested moving to Business Hwy 264. MCNC notified design firm to go out and complete an EA and to re-engineer the route. MCNC notified NTIA of the required change and submitted supporting documentation to the FPO. | 97 | NCDOT rejected initial encroachment request on US Hwy 264 due to controlled access and suggested moving to Business Hwy 264. MCNC notified design firm to go out and complete an EA and to re-engineer the route. MCNC notified NTIA of the required change and submitted supporting documentation to the FPO. | 23 | As rights of way were applied for, approvals have been received. A later start to this process due to delays with engineering contribute to the slight variance, but will be offset by Y2Q1. | 0 | Not Applicable at this time. | 25 | We procured equipment for 200 miles of IRU fibers we already owned and the expenditures track to about 25% of the original forecasted budget. | 45 | We have formalized agreements and/or built 403 miles of the 887 forecasted miles of our project. 197 are via IRU's from FRC and ERC, 197 from an existing IRU, and 7 miles constructed. | 0 | Deployment did not commence by end of quarter as was anticipated on the planned routes but began in early January of Y2Q1. | 22 | We are testing the fibers we build as they are constructed, or as they are obtained and ready to put in to service. At the end of the quarter, we had tested 197 of the 887 miles to be deployed | 2011-02-16 08:18 | 2011-02-16 08:18 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2011 | Q1 | Q1 - 2011 | 1883 | 2687 | TRUE | 35 | Given where we're at in the execution of contracts, agreements, and conduit placed in the ground, we believe our project is performing slightly ahead of the schedule communicated in the baseline relative to deployment of the mileage forecasted. However, due to the lack of fibers actually placed, we will only report equal to the baseline from a completeness standpoint. | 0 | na | Not applicable. | 100 | During the quarter we received confirmation that a required approximate 30 mile reroute had gained clearance. In addition we filed a second shorter approximately 2 mile reroute request that was still having EA work completed at quarter end. | 100 | All engineering activities related to the fiber construction of the project are completed, including the approximately 2 mile reroute spoke about in the environmental assessment. The only lingering issue is the EA review of that segment. | 100 | All right's of way required on the project have now been applied for. | 94 | At this point we only lack encroachment agreements from NC DOT in two counties, seven railroads, and United States Forest Service for the Croatan Forest across the entire footprint of the project. Together these areas represent approximately 25 miles of the entire 414 miles to be constructed as part of the project. All other areas have required construction/encroachment or equivalent permits. Note we've previously communicated 407 miles of new construction. With the required reroutes previously referenced, the number of engineering miles is now 414. | 0 | Not applicable at this time. | 63 | We have placed orders for equipment for all segments that total approximately 461 of the engineered miles. Relative to all operated miles that reflects 51%. However, in terms of the procurements to dollars in the budget, and what we will report, we're at $1.6M of commit or actually received on equipment, or about 63%. | 52 | We have formalized agreements and/or built 461.5 miles of the 894 (adjusted to reflect reroute) forecasted miles of our project. 197 are via IRU's from FRC and ERC, 197 from an existing IRU, 61 from the new IRU with Morris Broadband, and 6.5 miles constructed. If you factor in the miles of conduit completed, the number would be 581.5 miles. For the purpose of this report and the percentage noted, we will use the lower value of 461.5 or 52% complete, which still tracks ahead of our 30% forecast in the baseline. If to the higher number we would be at 66%. | 22 | Due to delays in getting started on construction by approximately two quarters, this milestone will lag by about one quarter in reporting. We base the deployment number at 197 miles now operated of the 887 reflecting the placement of equipment between Raleigh and Wilmington. Originally we would have expected to have had Mocksville/Asheville and Rocky Mount/Greenville deployed as well, but the delay in construction did not allow. These spans likely will deploy in late summer and may not make the Y2Q2 report either, but we have no concerns at this point with being back on schedule no later than Y2Q3. | 52 | We are testing the fibers we build as they are constructed, or as they are obtained and ready to put in to service. At the end of the quarter, we had tested 461.5 of the 887 miles to be deployed. | 2011-05-04 13:28 | 2011-05-04 13:28 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2011 | Q2 | Q2 - 2011 | 2945 | 3230 | TRUE | 53 | Given where we're at in the execution of contracts, agreements, and conduit placed in the ground, we believe our project is performing slightly ahead of the schedule communicated in the baseline relative to deployment of the mileage forecasted. With 75% of the conduit placed and 25% of the fiber placed, and all significant permits and agreements obtained, we feel we are nearing 75% complete. We will remain conservative at 50%. | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | All right's of way required on the project have now been applied for. | 98 | At this point, we only lack encroachment agreements/permits from five railroads and the United States Forest Service for the Croatan across the entire footprint of the project. Together these areas represent approximately 5 miles of the entire 413 miles to be constructed as part of the project. All other areas have required construction/encroachment or equivalent permits. | 0 | N/A | 81 | We have placed orders for equipment for all segments that are priority in nature, or approximately $2M of the $2.6M in the original budget and thus are ahead of the projection in the baseline. | 66 | We have formalized agreements for IRU and built a total of 593 miles of the 901 forecasted miles of our project. 197 are via IRU's from FRC and ERC, 197 from an existing IRU, 61 from the IRU with Morris Broadband, 33 from the IRU's with Balsam and Plateau, and 105 miles constructed. If you factor in the miles of conduit completed, the number would be 798 miles. For the purpose of this report and the percentage noted, we will use the lower value of 593 or 66% complete, which still tracks ahead of our 40% forecast in the baseline. If to the higher number we would be at 88%. | 22 | Due to delays in getting started on construction by approximately two quarters, this milestone will lag by about one quarter in reporting. We base the deployment number at 197 miles now operated of the 901 reflecting the placement of equipment between Raleigh and Wilmington. Originally we would have expected to have had Mocksville/Asheville and Rocky Mount/Greenville deployed as well, but the delay in construction did not allow. These spans likely will deploy in late summer and we will be back on track by Y2Q3. | 66 | We are testing the fibers we build as they are constructed, or as they are obtained and ready to put in to service. At the end of the quarter, we had tested 593 of the 901 miles to be deployed. | 2011-08-08 09:45 | 2011-08-08 09:45 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2011 | Q3 | Q3 - 2011 | 4223 | 3960 | TRUE | 58 | Relative to the original budget spent, we are 58% complete. Given where we are in the execution of contracts, agreements, and conduit placed in the ground (i.e. the work of the project itself), we believe our project is performing ahead of the schedule presented in the baseline relative to deployment of the mileage forecasted and approximately 75% of the total body of work original funded to complete. | 0 |  | NA | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 0 | N/A | 100 | All major components to operate the backbone as designed have been ordered by end of this quarter. While there may be a small item or two like a fiber jumper, power breaker, etc., all major elements are now in possession. | 51 | Relative to the construction portion of the original project budget, we are at 51% complete for the project. Relative to the projected spend rate for construction due to savings we are at 61% complete. These numbers are also lower relative to actual completion due to timings on invoices from contractors. Relative to the actual network to be constructed, we have formalized agreements for IRU and built a total of 693 miles of the 901 forecasted miles of our project. 197 are via IRU's from FRC and ERC, 197 from an existing IRU, 61 from the IRU with Morris Broadband, 33 from the IRU's with Balsam and Plateau, and 205 miles constructed. If you factor in the miles of conduit completed, the number would be 883 miles. Relative to the work related to the miles to be built or acquired in the approved project, we are at 77% complete. | 41 | Due to delays in getting started on construction by approximately two quarters, this milestone has lagged by about one quarter in reporting until now. We base the deployment percentage complete on number of optical miles lit. With 368 miles now operational of the 901 reflecting the placement of equipment between Raleigh and Wilmington, Rocky Mount and Greenville and Mocksville to Hickory, we consider ourselves 41% complete, slightly ahead of the 40% projection. The delay in construction did not allow for the deployment of Hickory to Asheville as we had anticipated by now. This segment is expected to become operational during the October - December 2011 quarter. Other spans will likely deploy in late fall, and in no case do we expect deployment of equipment to carry on beyond Y3Q1 (March 2012). | 77 | We are testing the fibers that we build as they are constructed, or as they are obtained and ready to put in to service. At the end of the quarter, we had tested 693 of the 901 miles to be deployed, ahead of the 33% projection. | 2011-11-22 15:05 | 2011-11-22 15:05 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2011 | Q4 | Q4 - 2011 | 4969 | 4645 | TRUE | 68 | Relative to the original project budget, we are approximately 68% complete. We are lower to baseline due to savings realized in costs during execution of the project, as well as some of our contractors not billing us upon completion of sub-segments as timely as they could be. Relative to the defined project scope of work we are roughly 85% complete. | 0 | NA | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 61 | Relative to the construction portion of the original budget, we are at 61% completion. Variances to budget are due to savings in the construction process, as well as the timing of billings from our contractors. Relative to the actual network being built, we are at 94% completion as we have formalized Indefeasible Rights to use for fibers or built fibers totaling 845 of 901 forecasted miles of our project. | 54 | Due to delays in construction start, and then with difficulties in the mountains of North Carolina slowing down construction to Sylva from Asheville, we are slightly behind deployment schedule. We did deploy equipment to another POP in this quarter and began operating another segment between Hickory and Asheville. Remaining efforts to deploy equipment had commenced at the end of the quarter, but the facilities enabled by those deployments were not complete as fiber was still being built. We forecast full completion of the equipment deployment in the March reporting quarter. | 82 | We are testing the fibers as they are acquired or built and spliced. More fiber was placed at the end of the quarter than had had final splicing performed on. Due to this we don't report much more over last quarter, but still ahead of baseline schedule. | 2012-02-13 12:40 | 2012-02-13 12:40 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2012 | Q1 | Q1 - 2012 | 6227 | 5716 | TRUE | 78 | Relative to the project budget, we are at 78%. However, relative to what we were funded to do in the original project, we are at 100% complete. | 0 | NA | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 70 | Relative to the construction portion of the original budget, we are at 70% completion. Variances to budget are due to savings in the construction process, as well as the timing of billings from our contractors. Relative to what were funded to do in the original project, we are at 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 2012-05-21 12:48 | 2012-05-21 12:48 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2012 | Q2 | Q2 - 2012 | 7137 | 6196 | TRUE | 84 | As the project was initially outlined and funded, we are 100% complete from a deployment perspective. The spend rate relative to the now approved budget with the additional builds sits at 84% | 0 | N/A | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 44 | All original equipment outlined to operate the network have been ordered and deployed as the project was originally funded. Items relative to supporting the additional builds to the CAI's and 100G infrastructure that were approved is ongoing and should complete in the September reporting quarter. | 95 | Relative to the additional miles added to the project during the quarter to the overall number now to be built, we stand at 88% complete. As it relates to dollars spent on the project, we are at 95%. | 90 | All original equipment outlined in the original proposal has been deployed. Equipment related to the additional CAI's is pending and will occur toward the end of the September reporting period and in to the start of the December reporting period. | 94 | Relative to the additional miles added to the project during the quarter to the overall number initially funded in the project and now in operation, we stand at 94% complete, and thus 94% tested. | 2012-08-20 07:32 | 2012-08-20 07:32 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2012 | Q3 | Q3 - 2012 | 8105 | 6760 | TRUE | 91 | As the project was initially outlined and funded, we are 100% complete from a deployment perspective. The spend rate relative to the now approved budget and partial completion of those tasks associated with the additional builds we are at 91% complete. | 0 |  | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 96 | All original equipment outlined in the original proposal has been deployed. Equipment related to the additional CAI's and 100G upgrades is nearing completion. | 89 | As it relates to dollars spent on the project, we are at 89% complete. Last quarter's number was reported at 95% in error, as that was based on miles. Last quarter's number based on dollars should have been 88%. The total number of new miles being built in the project is 444 and the total number of miles to be acquired is 314. With newly built miles and newly acquired miles considered, we are at 728 miles complete of 758 miles, or 96% complete. | 90 | All original equipment outlined in the original proposal has been deployed. Equipment related to the additional CAI's is pending and will occur toward the end of the calendar year. | 95 | Relative to the additional miles added to the project during the quarter to the overall number initially funded in the project and now in operation we stand at 95% complete, and thus 95% tested. | 2012-11-28 12:24 | 2012-11-28 12:24 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2012 | Q4 | Q4 - 2012 | 9031 | 7802 | TRUE | 98 | As the project was initially outlined and funded, we are 100% complete from a deployment perspective. The spend rate relative to the now approved budget and partial completion of those tasks associated with the additional builds we are at 98% complete. | 0 |  | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 95 | All elements of the project as initially funded and then approved during the course of the grant period have been completed. We show less than 100% here at this time to reflect the additional equipment approved at the end of the quarter for procurement and deployment during the extension period. | 99 | As it relates to dollars spent on the project, we are at 99% complete. The total number of miles built in the project is 444 and the total number of miles acquired was 314, for an overall total of 758 miles. | 95 | All elements of the project as initially funded and then approved during the course of the grant period have been completed. We show less than 100% here at this time to reflect the additional equipment approved at the end of the quarter for procurement and deployment during the extension period. | 100 | This task is 100% complete | 2013-02-27 16:17 | 2013-02-27 16:17 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2013 | Q1 | Q1 - 2013 | 9903 | 8493 | TRUE | 98 | As the project was initially outlined and funded, we are 100% complete from a deployment perspective. | 0 |  | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 95 | All elements of the project as initially funded and then approved during the course of the grant period have been completed. We show less than 100% here at this time to reflect the additional equipment approved at the end of the quarter for procurement and deployment during the extension period. | 99 | As it relates to dollars spent on the project, we are at 99% complete. The total number of miles built in the project is 444 and the total number of miles acquired was 314, for an overall total of 758 miles. | 95 | All elements of the project as initially funded and then approved during the course of the grant period have been completed. We show less than 100% here at this time to reflect the additional equipment approved at the end of the quarter for procurement and deployment during the extension period. | 100 | N/A | 2013-05-24 15:58 | 2013-05-24 15:58 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2013 | Q2 | Q2 - 2013 | 10539 | 8924 | TRUE | 99 | We are 100% complete from a deployment perspective, as the project was initially outlined and funded. The variance here is due to the pending completion of the additional components of the project. | 0 |  | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 99 | As it relates to dollars spent on the project, we are at 99% complete. The total number of miles built in the project is 444 and the total number of miles acquired was 314, for an overall total of 758 miles. | 95 | All elements of the project as initially funded and then approved during the course of the grant period have been completed. We show less than 100% here at this time to reflect the additional equipment approved at the end of the quarter for procurement and deployment during the extension period. Procurement has been completed, but due to timing of delivery relative to the end of the quarter, deployment has not yet occurred. | 100 | This task is 100% complete. | 2013-08-09 15:12 | 2013-08-09 15:12 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2013 | Q3 | Q3 - 2013 | 10939 | 9176 | TRUE | 100 | This task is 100% complete. | 0 |  | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 2013-10-25 08:17 | 2013-10-25 08:17 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570016 | 2010 | Q2 | Q2 - 2010 | 45 | 1331 | FALSE | 10 |  |  |  |  | 100 |  | 100 |  | 80 |  | 50 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2010 | Q3 | Q3 - 2010 | 185 | 1359 | TRUE | 2 | Awaiting approval of EA, PA & USCOE permits before beginning construction activities. Our contingency plan is to hire additional contract construction forces to complete project on time. | 0 |  | N/A | 95 | Had to wait for USFWS approval & preparation of PA | 30 | Network design delayed due to PA requirements & additional time to review & execute EF&I contracts. Plan to finish by end of 4th quarter. | 80 | No information to add | 70 | No information to add | 0 | No information to add | 0 | Ordered generators (2) in August, but not invoiced | 0 | No information to add | 0 | No information to add | 0 | No information to add | 2010-10-28 11:51 | 2010-10-28 11:51 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2010 | Q4 | Q4 - 2010 | 809 | 1845 | TRUE | 4 | Awaiting approval of EA before starting construction | 0 |  | N/A | 95 | Awaiting National Forest Service approval before submission of final EA | 100 | N/A | 100 | N/A | 85 | Awaiting permit approval from National Forest Service & VAMRC | 0 | N/A | 5 | Ordered huts in December; not invoiced. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-01-28 15:52 | 2011-01-28 15:52 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2011 | Q1 | Q1 - 2011 | 2125 | 2808 | TRUE | 16 | Final EA approval has delayed construction start. Now scheduled for Y2Q2. | 0 |  | N/A | 95 | Awaiting SHPO consultation approval before submission of final EA, now scheduled for Y2Q2. | 100 | N/A | 100 | N/A | 100 | N/A | 0 | Awaiting EA approval and RFP award. Now scheduled for Y2Q2. | 30 | Ordered switching equipment, but not invoiced. Will be paid in Y2Q2. | 0 | Awaiting EA approval/FONSI, now scheduled for Y2Q2. | 0 | N/A | 0 | N/A | 2011-05-18 12:00 | 2011-05-18 12:00 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2011 | Q2 | Q2 - 2011 | 3065 | 3290 | TRUE | 23 | EA approval pushed scheduled start date back by approximately 6 months. New project complete date to be Y3Q2. | 0 |  | N/A | 100 | FONSI issued on 5-17-2011. | 100 | N/A | 100 | N/A | 100 | N/A | 0 | Bid has been awarded. Vendor is to start 7-18-2011. Completion is scheduled for Y2Q3. | 100 | All equipment is ordered and received. | 16 | Construction started on 5-23-2011. Delay in EA approval will push construction complete back by approximately 6 months to Y3Q1. | 0 | Deployment delayed by site preparation bidding. Equipment deployment to start to start in Y2Q3 and complete in Y2Q4. | 0 | N/A | 2011-08-12 17:32 | 2011-08-12 17:32 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2011 | Q3 | Q3 - 2011 | 4033 | 3857 | TRUE | 40 | Delayed EA approval pushed scheduled start date approximately 6 months. New completion date is Y3Q2. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 30 | Wet weather and unforeseen construction challenges have delayed completion to Y2Q4. | 100 | Complete | 45 | Site preparation and wet weather have hampered our attempt to make construction gains. Estimated completion date is Y2Q4. | 0 | Equipment deployment has been delayed because of the delay in site preparation. Deployment will begin in Y2Q4 and be completed in Y3Q1. | 0 | Network testing has been delayed because of the delay in site preparation. Testing will begin in Y2Q4 and be completed in Y3Q2. | 2011-11-14 15:43 | 2011-11-14 15:43 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2011 | Q4 | Q4 - 2011 | 4881 | 4574 | TRUE | 53 | Start date approximately 6 months delayed due to EA approval; pushed schedule back. New completion date in Y3Q2 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 80 | Both huts on site. Wet weather delayed placing power. To complete in Y3Q1. | 100 | Complete | 82 | Completed 41 miles in Y2Q4 for a total of 86 miles | 20 | Completed PemTel co-location. Remainder delayed until Y3Q1 due to delay in site preparation | 15 | Delayed until Y3Q1 due to delay in construction completion | 2012-02-06 12:11 | 2012-02-06 12:11 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2012 | Q1 | Q1 - 2012 | 6077 | 5638 | TRUE | 67 | Start date delayed approximately 6 months due to EA approval. New completeion date is Y3Q2 | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 91 | Completed 10 miles in Y3Q1 for a total of 91% complete | 40 | Installation continues at New Castle and East Park | 40 | Testing complete from Bedford to EastPark. Tom complete remainder by Y3Q2. | 2012-05-15 05:23 | 2012-05-15 05:23 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2012 | Q2 | Q2 - 2012 | 6873 | 6063 | TRUE | 73 | Final billing and retainage to be completed on initial build-out. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 93 | New node & 11 mile IRU to be built under approved route modification | 85 | Installation continues at New Castle & Eastpark | 100 | Complete | 2012-08-06 22:26 | 2012-08-06 22:26 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2012 | Q3 | Q3 - 2012 | 7887 | 6648 | TRUE | 87 | Awaiting completion of route modification. Expected completion 12-15-12. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Original build is 100% complete. Awaiting completion of site prep for Price Fork (route modification). Four (4) sites are completed of the five (5) proposed. | 100 | Complete | 96 | Route modification node to be completed in Y3Q4 | 95 | Awaiting completion of equipment installation for Price's Fork (route modification). | 100 | Complete | 2012-11-14 21:12 | 2012-11-14 21:12 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2012 | Q4 | Q4 - 2012 | 8659 | 7483 | TRUE | 94 | Submitted a no-cost project extension on 12-21-2012 to extend the project completion date to 6-30-2013. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 80 | Original build 100%, work to start January 2013 on Prices Fork. Four (4) of five (5) sites completed. Percent Complete decreased from last quarter as a result of the approved route modification and associated revised budget. A node was added and additional funding was reallocated to Site Preparation budget. | 100 | Complete | 96 | Extension requested to complete route modification. Submitted no-cost project extension on 12-21-2012 to extend the project completion end-date to 6-30-2013 | 95 | Awaiting completion of node to complete equipment installation | 96 | Awaiting completion of equipment installation. Percent Complete decreased from last quarter as a result of the approved route modification and associated revised budget. Additional equipment (for the new node) was added to the scope of work. Once this equipment is deployed, it needs to be tested. | 2013-02-06 20:38 | 2013-02-06 20:38 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2013 | Q1 | Q1 - 2013 | 9651 | 8358 | TRUE | 95 | Approved Route Modification and no-cost project extension extended project completion to 6-30-2013 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 80 | Site preparation delayed due to wet weather conditions | 100 | Complete | 99 | Approved Route Modification and no-cost project extension extended project completion to 6-30-2013 | 97 | Awaiting completion of node to complete equipment installation | 99 | Awaiting completion of note to complete testing | 2013-05-08 23:58 | 2013-05-08 23:58 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2013 | Q2 | Q2 - 2013 | 12439 | 10628 | TRUE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-08-19 15:49 | 2014-08-19 15:49 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570017 | 2010 | Q2 | Q2 - 2010 | 46 | 1319 | FALSE | 8 |  |  |  |  | 100 |  | 90 |  | 95 |  | 5 |  | 5 |  | 50 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2010 | Q3 | Q3 - 2010 | 389 | 1461 | TRUE | 3 | Based upon the project construction schedule recently submitted by the vendor for the 68 backbone sites, we have projected overall completion to be 3%. This is a revision downward We expect to be able to catch up during Q2 and Q3 of 2011. It took longer than expected to get all purchasing documents processed and no infrastructure installation started during Q3. | 30 | Customer Acquisition, Support and Billing | We have issued a purchase order to Alcatel-Lucent for a portal based asset management tool to assist in tracking the service subscriptions as well as billing of customers. While the initial design and hardware requirements have been determined, the final look of the product has yet to be finalized and may be influenced by the first customers to sign onto the service. | 95 | The Commonwealth received the Environmental Assessment or Finding Of No Significant Impact (FONSI) from NTIA on August 12, 2010. After receiving the Assessment, we were notified by the Wyandotte Tribe with a concern. We have initiated an investigation to address their concerns and are expecting a favorable outcome. | 60 | Network vendor started process of delivering a high-level and low-level network switching design. Project includes 43 point to point and point to multipoint wireless connections to anchor institutions and last mile providers. Although a preliminary design included an array of 110 potential locations and environmental assessments, the final network design will be based upon customer requirements. The current status will not cause delays to backbone construction and network design will be completed by end of Q2 2011. | 65 | Commonwealth is ensuring that every site permission document is finalized with all required technical amendments. There are master license agreements in place for all site and tower owners. This issue is related to the installation of any customer equipment at project sites but will not delay backbone construction. | 0 | No Construction activities have started and most construction permits, if required, will be requested in Q4 of 2010 or Q1 of 2011. Permits could be needed at the 14 locations where the commonwealth is building a new communications tower or adding a new communications shelter, depending on local ordinances. The remaining 54 sites will typically not require permits. | 0 | No site activity has commenced. | 54 | The Commonwealth has issued purchase orders for all equipment required for backbone construction, but equipment purchases for anchor institution connections are pending. Although completion is ahead, there are still milestones for delivery of equipment and ordering of equipment for wireless links to backbone. | 0 | No build activity has commenced. | 0 | No equipment deployment has commenced. | 0 | No network testing has commenced. | 2010-11-23 16:29 | 2010-11-23 16:29 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2010 | Q4 | Q4 - 2010 | 1171 | 2205 | TRUE | 6 | By the end of the fourth quarter, we have reached 6 percent of overall project completion. We believe that we are at about six percent of completion due to the completion of three hops of microwave equipment upgrades as well as the issuance of a total of twenty purchase orders for equipment and services. The lower percent of progress as compared to our baseline report is the result of a longer than expected time frame for purchase orders to flow through the approval process. Now that we have initiated all of the purchase orders to cover the cost of equipment, shelters and towers as well as site work and construction, we expect to catch up during Q2 and Q3 of 2011. | 22 | Customer Acquisition, Support and Billing | We are working toward the completion of the initial design documentation for the billing system but have finalized design documentation for the asset management portion of the project. Training and implementation of the system is expected to occur within Q2 of 2011. This is a downward adjustment to progress in this category due to a restructuring of our metrics. in this category. | 100 | We received our Finding of No Significant Impact (FONSI) in August of 2010, but we also received a request from the Wyandotte tribe to do additional research on four of the five new tower sites. The additional study that was performed resulted in a satisfactory result from the requesting tribe. Only minor delays were experienced with the additional research and we fully expect to remain on schedule. | 90 | We have completed the initial documentation phase of our network as well as both the high level and low level design documentation for the backbone portion of the network. Design documentation for the wireless connections remain and may be determined by the initial customers. | 68 | We received additional permissions documents back fully executed during the quarter; however, there are still a few that remain to be received. While this item is taking longer than expected, we do not anticipate that it will delay our project. | 0 | Construction permits have taken longer than initially expected due to the time necessary in researching what permits were going to be necessary as well as receiving confirmation from the appropriate entities. Now that we are aware that we will only need permits for the new towers, we are preparing complete sets of drawings for each tower to start the process. The drawings will be submitted during Q1 and we expect to be able to get the permits back within the same quarter. We do not believe that this will cause any delays to the project. | 21 | Geotech studies have been completed at three of the sites that will receive significant modifications as a part of this project. | 73 | We have issued purchase orders for all of the equipment that we have deemed to be necessary other than what might be needed for the wireless connections and customer sign on as each customer's needs may be different. All new towers and shelters have been ordered. | 1 | We have installed equipment to upgrade three of the seventy-one hops in the backbone of our project to be capable of handling broadband. Additionally, modifications have been completed to eight of our existing towers to allow for new coax cabling to be routed into the shelters for connection to existing equipment. As noted above, we were delayed in Q3 of 2010 with our purchase orders moving more slowly than anticipated through the approval process which slowed the order of equipment and therefore pushed back the date at which we could begin the installation of the equipment.. During Q4 we did however begin to install equipment and have a plan in place to catch up to what was reported on the baseline report submitted at the start of our project. It is expected that we will catch up to the baseline by Q3 of 2011 for the category of network build. | 2 | Three hops have received equipment upgrades by the close of Q4. With the completion of equipment purchase orders in Q3 and Q4 of 2010, we expect to see the deployment of those items within Q2 and Q3 of 2011. | 4 | All upgraded hops have been tested. | 2011-02-16 08:29 | 2011-02-16 08:29 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2011 | Q1 | Q1 - 2011 | 2395 | 2943 | TRUE | 4 | According to the guidance from the NTIA and direction from our current Federal Program Officer, our current overall project progress would be gaged at only 4% of progress. Expenditures for the Commonwealth of Pennsylvania are one of the final elements of any project. The commonwealth requires that any goods or services are delivered/performed and quality control checked prior to the invoicing by the vendor. Once an invoice is received, it is generally paid within 30 days of receipt. Using this method to measure progress will make catching up to the baseline extremely difficult since our project's baseline is based upon the same factors as our internal method of progress measurement, and is not expenditure based. Our internal method of progress measurement has been documented for our Federal Program Officer. As of the close of Q1, our project has reached 14% of completion according to our own internal measurements. We have completed 15 microwave connection upgrades as well as | 0 | Customer Acquisition, Support and Billing | According to the guidance from the NTIA and direction from our current Federal Program Officer, our current progress for this milestone would be gaged at 0% of completion. Expenditures for the Commonwealth of Pennsylvania are one of the final elements of any project. The commonwealth requires that any goods or services are delivered/performed and quality control checked prior to the invoicing by the vendor. Once an invoice is received, it is generally paid within 30 days of receipt. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we have reached 37% of completion for this milestone. During Q1, we completed the initial design of the billing and provisioning system as well as determined how we will integrate the automated billing that it will provide, into the Commonwealth's current billing system. | 100 | According to the guidance from the NTIA and direction from our current Federal Program Officer, our progress on this milestone would be gaged at 100% of progress. All invoices have been received and paid for work associated with our project's environmental assessment. We completed this milestone as of the close of Q4 according to our own internal measurements. Our Finding of No Significant Impact (FONSI) was issued in Q3 of 2010; however, we received an additional inquiry after receiving the FONSI. As a result, we performed research to satisfy the request we had received from the Wyandotte tribe. By the close of Q4, we had received notification of a satisfactory result of our research. | 44 | According to the guidance from the NTIA and direction from our current Federal Program Officer, our progress for this milestone would be at 44% based solely on expenditures. We have completed the initial documentation phase of our network as well as the high and low level design documentations for the backbone portion of the project. The final design documentation for the wireless connections may be determined by the needs of the initial customers. We anticipate being able to begin to close the gap between our current percent completion and the baseline report during Q2 of 2011 with the completion of our wireless design for the first customers of the project. According to our own internal tracking we are at 90% of project completion. | 0 | According to guidance from the NTIA and direction from our current Federal Program Officer, our progress for this milestone is not to be tracked and is listed as 0% due to there being no expenditures for this milestone. The commonwealth has internally used the rights of way milestone to track the execution of signature documents with our project. Considering that our network is already in existence and is being enhanced as part of the broadband middle mile project, the actual rights of way documents are in place. Permissions documents are used to update the owner of our intent to change a detail in the current set up. These documents are trickling in and we anticipate a larger push to catch up with our baseline report within Q2 of 2011. According to our own internal measurements for this milestone, we are currently at 76% completion. | 0 | According to guidance from the NTIA and direction from our current Federal Program Officer, our progress for this milestone is not to be tracked and is listed as 0% due to there being no expenditures for this milestone. The commonwealth has internally used the Construction Permits and other Approvals milestone to track our project's completion in obtaining the necessary permits and approvals even though they do not have an expenditure attached to them. Upon submission of the drawings for our five new towers, it was determined that a building permit will not be required for the towers due to language in the Uniform Construction Code which exempts public service agencies requesting to install, alter or repair generation, transmission, distribution, metering or other related equipment under its ownership from acquiring a permit. This has been confirmed by the Pennsylvania Department of Labor and Industry. We will however, be required to obtain zoning permits for the two towers in | 0 | According to guidance from the NTIA and direction from our current Federal Program Officer, our progress for this milestone is at 0% due to the lack of any expenditures posting to date as of the close of Q1. As with the other milestones, we internally have tracked our progress using items of accomplishment other than expenditures. During the first quarter of 2011, we poured foundations for three shelters which are now curing in preparation for the new structure that will be installed there. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we have reached 21% of completion for this milestone. | 0 | According to the guidance from the NTIA and direction from our current Federal Program Officer, our current progress for this milestone would be gaged at 0% of completion due to the lack of any expenditures at this point in the project. Expenditures for the Commonwealth of Pennsylvania are one of the final elements of any project. The commonwealth requires that any goods or services are delivered/performed and quality control checked prior to the invoicing by the vendor. Once an invoice is received, it is generally paid within 30 days of receipt. According to our own internal measurements, we have reached 74% of project completion on this milestone. Our method of measurement includes the actual procurement, ordering and delivery of the equipment as well as invoicing. We recently issued a purchase order to acquire equipment that will drastically reduce the downtime experienced during the transition between equipment cabinets and larger shelters. We have also deployed and insta | 0 | According to the guidance from the NTIA and direction from our current Federal Program Officer, our current progress for this milestone would be gaged at 0% of completion. Expenditures for the Commonwealth of Pennsylvania are one of the final elements of any project. The commonwealth requires that any goods or services are delivered/performed and quality control checked prior to the invoicing by the vendor. Once an invoice is received, it is generally paid within 30 days of receipt. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we have reached 4% of completion for this milestone. We have continued to install microwave equipment to upgrade a total of fifteen of the 71 connections at this point in our project. Additionally, modifications to nine of our existing towers has occurred enabling new coax cabling to be routed into the shelters for connection to existing equipment. As of the close of Q1, foundations to three | 0 | According to the guidance from the NTIA and direction from our current Federal Program Officer, our current progress for this milestone would be gaged at 0% of completion. Expenditures for the Commonwealth of Pennsylvania are one of the final elements of any project. The commonwealth requires that any goods or services are delivered/performed and quality control checked prior to the invoicing by the vendor. Once an invoice is received, it is generally paid within 30 days of receipt. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we have reached 11% of completion for this milestone. By the close of Q1, fifteen microwave radio connections have received equipment upgrades. The installation of switching equipment has been delayed due to a change necessitated by one component included in our initial order becoming discontinued. We have taken steps to avoid any significant delays to the project as a result of this change | 0 | According to the guidance from the NTIA and direction from our current Federal Program Officer, our current progress for this milestone would be gaged at 0% of completion. Expenditures for the Commonwealth of Pennsylvania are one of the final elements of any project. The commonwealth requires that any goods or services are delivered/performed and quality control checked prior to the invoicing by the vendor. Once an invoice is received, it is generally paid within 30 days of receipt. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we have reached 4% of completion for this milestone. Microwave testing will be performed in conjunction with testing of the switching equipment for a more efficient use of field technician resources. The testing schedule has been revamped to allow us to proceed on that basis. We do not expect this to delay our project. | 2011-05-31 08:55 | 2011-05-31 08:55 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2011 | Q2 | Q2 - 2011 | 3129 | 3322 | TRUE | 8 | Based upon project expenditures, our overall project progress is at 8%. Expenditures only occur after the goods or services are received/provided and installed/quality control checked. As a result, our project does not appear to be progressing as quickly as it would with other methods of gauging progress. As the structures begin to be delivered and installed, or constructed on the site, mostly during the second and third quarters of 2011, our progress should begin to catch up to the baseline due to the realization of those expenditures. | 0 | Customer Acquisition, Support and Billing | Based upon expenditures for this milestone, we are at zero percent of completion. We recently completed the asset management portion of this milestone and expect to receive an invoice for that equipment and services within the first month of the third quarter which will allow us to show some progress. The other main components to this milestone include the provisioning and billing tools which trail behind the asset management portion. We expect to complete the remaining portions of this milestone by the close of 2011 but may not have received all of the appropriate invoices until early 2012. While we continue to progress in this category, we will likely not catch up to our baseline until early in 2012 due to the fact that our baseline report was not figured upon expenditures as a method of gauging progress. Prior to the the receipt of an invoice, our vendors are required to deliver the goods and services as well as install any equipment and have it quality control checked. | 100 | This milestone is complete. | 50 | We have completed the engineering, site audit services and documentation of all of the changes that we are making to the northern tier sites included in the broadband project and expect to receive the final invoices for the services recently completed, early in the third quarter. While we continue to progress in this category, we will likely not catch up to our baseline until early in 2012 due to the fact that our baseline report was not figured upon expenditures as a method of gauging progress. Prior to the the receipt of an invoice, our vendors are required to deliver the goods and services as well as install any equipment and have it quality control checked. | 0 | N/A The rights of way milestone has no cost associated with it as part of our project therefore it's progress will not be tracked within the quarterly PPR. | 0 | N/A The construction permits and other approvals milestone has no cost associated with it as part of our project therefore it will not be tracked within the quarterly PPR. | 0 | We have completed the construction of one of our new towers as well as five of the new shelters by the close of the second quarter of 2011. Our progress for this milestone is shown as zero percent completed due to a lack of expenditures in this category. We will begin to show expenditures in the third quarter of 2011 with the payment of invoices for the completed tower and shelters. We expect to catch up to the baseline for this milestone during the fourth quarter of 2011 when we have received all of the expected invoices. | 3 | As of the close of the second quarter, we have only recognized expenditures for 3% of the total expense for equipment. As our project continues to complete equipment installations and have those installations quality control checked, we will start to realize increased expenditure based progress. Taking into consideration that our baseline report was not based upon expenditures, we may not catch the baseline's projected progress in this milestone until the second quarter of 2012. | 0 | The network build milestone includes expenditures for the construction of our five new towers and our ten new shelters included within the project. Prior to the close of the second quarter, we had completed one tower and five shelters; however, we had not received or paid any invoices for that work. We expect that we should be able to catch our baseline report's progress for this milestone by the close of the calendar year. | 5 | The equipment deployment milestone includes the installation of the microwave radio upgrades that have continued to progress through the second quarter of 2011. Unfortunately, we only received our first invoices for this work after the close of the second quarter. This milestone also includes installation of the wireless portions of the network that will be determined by our first customers and the installation of the switching equipment that has not been completed to date. With the project schedule in mind, we expect to catch up to our baseline report for this milestone in the early quarters of 2012. | 23 | We have tested all of the completed microwave connections. The progress on this milestone is in agreement with our baseline. | 2011-08-16 15:53 | 2011-08-16 16:03 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2011 | Q3 | Q3 - 2011 | 4063 | 3875 | TRUE | 21 | Our percent complete, based upon expenditures, as required by the project leadership, trails that of our baseline due to the safeguards built into our payment system. Invoices are only paid after the goods are received, installed, quality assurance tested, approved and an invoice submitted by the vendor. Despite the percentage complete being at only 21 percent, our project remains on schedule and expects to make significant progress as payment for invoices of completed shelters, towers and equipment are made. We expect our progress to catch that of our baseline report in early 2012 as we receive and pay invoices for multiple towers and shelter structures that were built in the third quarter of 2011. | 16 | Customer Acquisition, Support and Billing | Due to the realization of a potential weakness in the network, we were forced to put the development of our billing and provisioning software on hold to allow us to time to determine the correct course of action. Now that we have made the decision of which equipment we will deploy to harden the network, we are able to once again move forward with the billing and customer support portion of the project. Additionally, we have decided that it is in our best interest and in the best interest of our future customers that we gain experience in the sale of broadband services. In order to do so, we will begin a pilot project in the fourth quarter that will allow us to gain the valuable experience that will enable us to make intelligent decisions regarding the sales of our new broadband capacity. We expect our progress to catch that reported in our baseline early in 2012. | 100 | Our environmental assessment is complete. | 69 | We have completed the network design for all areas of our network with the exception of the connection to our Community Anchor Institutions and last mile service providers. This portion of our project will become the focus of our attention early in 2012. We expect to move closer to our baseline in the fourth quarter but do not expect to catch up completely until 2012 when we are able to finalize the plans of our interconnection with Community Anchor Institutions and Last mile service providers. | 0 | The rights of way milestone has no cost associated with it as part of our project; therefore, it is not being tracked within the quarterly PPR. | 0 | The construction permits and other approvals milestone has no cost associated with it as part of our project; therefore, it is not being tracked within the quarterly PPR. | 21 | The site preparation milestone tracks our project's progress on the work completed to prepare sites for the new equipment, shelter and/or tower that is planned for that radio tower site. Because of our internal requirements that installation, quality assurance testing and approval are necessary prior to invoicing, this milestone does not show the true progress of the project. We expect to catch the progress predicted in our baseline report within the fourth quarter of 2011. | 21 | Our equipment procurement milestone currently shows the percentage of equipment that we have paid for so far in the project and is not an accurate reflection of the true progress in this area. As of the close of the third quarter, we had completed a total of 32 of the 71 microwave radio connections. We expect to catch our baseline report by the middle of 2012. | 32 | Our network build milestone includes expenditures for our towers and shelters, most of which were completed within the third quarter. The percentage of progress shown is reflective of expenditures which are delayed by the requirement that the commonwealth has put upon our vendors that the construction has to be completed, the work quality assurance tested, approved and invoiced. As of the close of the third quarter, we had completed four of the five towers with the final tower expected to be completed early in the fourth quarter. We have also completed construction on nine equipment shelters. We expect to catch the baseline for this milestone within the next quarter (Q4, 2011.) | 5 | While we have deployed equipment at 32 of our 71 microwave radio connections, our vendor has not billed us for any of the work associated with that deployment to date due to those services being connected to the installation of the switching equipment as well. Since we expect the switching equipment to be installed in early 2012, we expect to receive invoices for this work in the first and second quarters of 2012. We expect to catch our baseline report in the first half of 2012 with the roll out of switching equipment and the expenditures that they will create. | 25 | As sections of our microwave network are completed, we have them tested for quality assurance. As of the end of the third quarter, we are only showing 25 percent complete due to not receiving the invoices for July and August until late in September. Due to the time necessary to process, payment of these invoices will not happen until early in the fourth quarter. We will continue to work with this vendor to get invoices in a timely manner and expect to begin catching up early in 2012. | 2011-11-16 11:59 | 2011-11-16 11:59 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2011 | Q4 | Q4 - 2011 | 5295 | 4965 | TRUE | 42 | The project, when measured by expenditure alone, is behind due to the safeguards built into the Commonwealth's payment system. Goods and/or services must be provided and approved, then quality assurance checked and invoiced. Project progress based upon completion of work is on schedule at 72% of completion. Upon payment of invoicing for the equipment installation and integration services, expenditure based progress will make a dramatic surge towards agreement with the baseline report which is expected to occur in the third quarter of 2012. | 39 | Customer Acquisition, Support and Billing | Payment for an asset management system to track the assets procured as part of this project has been made. The Service Portal application to provision bandwidth and priority rating on the network has also been invoiced and paid. The Billing portion of the project remains in progress as we await customers to test the application. Upon receipt and payment of an invoice for the billing portion of the project, our expenditure based progress will catch up to the baseline. It is expected that the invoice for this portion will be paid in Q3, 2012. | 100 | This milestone is complete. | 72 | The project remains on schedule with the exception of the final determination for the last mile connections. With the issuance of a Request for Information in Q1, 2012, we anticipate finalizing the remaining design work within the first half of 2012. | 0 | N/A. This milestone does not apply to our project. | 0 | N/A. This milestone does not apply to our project. | 68 | This milestone remains on schedule. | 39 | 54% of microwave equipment expenditures have been realized. 14% of MPLS switching equipment invoices have been received and paid. 0% of invoices for WiMAX equipment has been paid to date. The project remains on schedule. Engineering and configuration of switching equipment continued allowing for the deployment in Q2, 2012. | 95 | This milestone remains on schedule. | 8 | 8% of invoices for the services to install equipment have been received and paid to date. On this project, the payments for services at the network sites are contingent upon both microwave and switching equipment to be installed prior to payment; therefore, invoices have not been submitted. Due to the scheduled installation of switching equipment to be performed in Q2, 2012, it is expected that expenditures will catch up to the baseline report in Q3, 2012. | 50 | This milestone remains on schedule. | 2012-02-27 15:35 | 2012-02-27 15:35 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2012 | Q1 | Q1 - 2012 | 6005 | 5602 | TRUE | 44 | When measured by expenditures, the overall project percentage complete is only 44%; however, the project is actually on schedule. Due to the structure of our purchasing documents with the main vendor on the project, microwave radio installations as well as switching equipment installations were quoted together per site. As a result, our vendor is unable to invoice us for services rendered until both the microwave radio and the switching equipment have been installed at each site. According to the current project schedule, a majority of the switching equipment installations are scheduled to be completed within the second and early third quarters, as a result, we expect this percent complete to increase exponentially to show agreement with the baseline in the third quarter of 2012. | 39 | Customer Acquisition, Support and Billing | The Customer Acquisition, Support and Billing milestone trails the progress anticipated within the baseline report submitted at the start of the project; however, we expect to make significant progress within the second quarter of 2012. As we have moved closer to determining the connections to the last mile providers and community anchor institutions, we have been able to move forward in providing the necessary specifications to our vendor for the business support component of the project allowing for final configuration, invoicing and payment of those portions of the project. We anticipate making marked progress on this expenditure during the second and third quarters of 2012. | 100 | This milestone is complete. | 73 | Our Network Design milestone remains at 73% of completion as a result of tasks added to this indicator. During the first quarter we requested additional tower analyses and path surveys as part of a route change which alters the progress in this category. These path surveys and tower analyses are anticipated to be complete within the second quarter. Additionally the final design for the connections to our last mile providers and community anchor institutions are yet to be finalized due to line of sight challenges experienced during the pilot program's final engineering. The final design for the connection to last mile and community anchor institutions is expected to be determined early within the second quarter of 2012 as we evaluate alternate routes to connect with last mile service providers. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 70 | This milestone remains on schedule. | 41 | Our Equipment Procurement milestone trails that of the baseline report submitted at the start of the project. Microwave radio equipment upgrades have been paid to date. We anticipate the receipt of invoices for the switching equipment following installation and configuration which is expected to occur within the second and third quarters of 2012 allowing this milestone to come into agreement with the baseline in the third quarter. | 100 | This milestone is complete. | 9 | Our Equipment Deployment milestone also trails that of the baseline report. This milestone shows a lack of significant progress due to the fact that the vendor providing the service to install both the microwave radio and switching equipment had quoted the services together on a site by site basis allowing them only to invoice once each site is upgraded with both types of equipment. At this point in the project all microwave radio installations that have been completed have not been able to be invoiced because the switching equipment installations/configurations have not been completed. According to the project schedule, these switching equipment upgrades will be completed within the second and early third quarters of 2012 allowing the project to make dramatic progress and catch the baseline report in the third quarter. | 62 | This milestone remains on schedule. | 2012-05-10 11:34 | 2012-05-10 11:34 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2012 | Q2 | Q2 - 2012 | 6935 | 6095 | TRUE | 48 | When measured by expenditures, the overall project percentage complete is only 48%; however, the project is actually on schedule. Due to the structure of our purchasing documents with the main vendor on the project, microwave radio installations as well as switching equipment installations were quoted together per site. As a result, our vendor is unable to invoice us for services rendered until both the microwave radio and the switching equipment have been installed at each site. According to the current project schedule, a majority of the switching equipment installations are scheduled to be completed within the second and early third quarters, as a result, we expect this percent complete to increase exponentially to show agreement with the baseline in the third quarter of 2012. | 39 | Customer Acquisition, Support and Billing | The Customer Acquisition, Support and Billing milestone trails the progress of the baseline report. This milestone was largely completed near the end of the second quarter; however, the invoice was not received early enough to have been counted within the quarter, due to its receipt falling past the commonwealth's fiscal year end deadlines. It is expected that this milestone will catch up to the progress predicted in the baseline within the third quarter of 2012. | 100 | This milestone is complete. | 73 | Our network design milestone remains at 73% of completion for the second quarter. Multiple tasks within this indicator are currently in progress and will likely be completed and invoiced within the third quarter. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 87 | This milestone remains on schedule. | 49 | Our equipment procurement milestone trails that of the baseline report submitted at the start of the project. Microwave radio equipment upgrades have been paid to date. We anticipate the receipt of invoices for the switching equipment following installation and configuration which is expected to continue into the third quarter of 2012. The payment of these invoices will bring this milestone into agreement with the baseline in Q3, 2012. | 100 | This milestone is complete. | 10 | Our equipment deployment milestone trails the progress predicted in our baseline report. This milestone shows a lack of significant progress due to the quotation received from our equipment vendor. When quoted, the vendor listed the services for installation of microwave radio upgrades along with MPLS switching equipment installations/configurations on a site by site basis. Until both types of equipment are installed at each site, this vendor is unable to invoice the commonwealth. Testing for the deployment of the switching equipment was commenced during the second quarter and will continue into the third quarter. With the scheduled installations and configuration of this switching equipment in the third quarter, we expect to make significant progress on this milestone. | 67 | The network testing milestone progress trails that which is indicated on our baseline report. The network testing is being completed as elements of the project are finished. With the completion of the MPLS switching upgrades largely in the third quarter, it is anticipated that this indicator will catch up to the baseline at that time. | 2012-08-08 16:07 | 2012-08-08 16:07 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2012 | Q3 | Q3 - 2012 | 7821 | 6614 | TRUE | 53 | When measured by expenditures alone, our overall project percent complete is only 53%; however, the project remains on schedule. Due to the structure of our purchasing documents with the main vendor on our project, microwave radio upgrades as well as switching equipment installations were quoted together on a site by site basis. As a result, the vendor is not able to invoice for services rendered until both the microwave radio and switching equipment have been installed at each site. According to the current project schedule, which takes into account the longer than anticipated review process for our requested route change as well as the extended acceptance testing on the switching equipment deployment, we anticipate that we will be able so show significant progress with the fourth quarter report. | 81 | Customer Acquisition, Support and Billing | Our customer acquisition, support and billing milestone trails the progress that was predicted on our baseline. As of the close of the third quarter, the acceptance testing remains to be completed. Once complete, this milestone will also be complete. | 100 | This milestone is complete. | 90 | This milestone is on schedule. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 96 | This milestone remains on schedule. | 56 | Our equipment procurement milestone continues to trail that of the baseline submitted at the start of the project. With the completion of the acceptance testing of the deployment of our switching equipment, we will be able to receive and pay invoices for this equipment. By the close of the fourth quarter, we believe that we will be in agreement with the baseline report. | 100 | This milestone is complete. | 13 | Our equipment deployment milestone continues to trail the progress predicted in the baseline report. Due to the lack of final acceptance testing and completion of the switching equipment upgrades, we were not able to receive and pay the invoices for that equipment as well as for the services to install all of the microwave and switching equipment deployed to date. At this point, we believe that much of this invoicing will now occur within the fourth quarter allowing us to catch up to the baseline in January of 2013. | 67 | Due to the switching equipment acceptance testing not being completed as well as the longer than anticipated response on the requested route changes, there was little network testing completed within the third quarter. We anticipate that we will be able to catch up to the baseline within the fourth quarter on this milestone. | 2012-11-09 15:24 | 2012-11-09 15:24 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2012 | Q4 | Q4 - 2012 | 8777 | 7574 | TRUE | 60 | Our project was able to make substantial progress within the fourth quarter of 2012 as will be shown upon receipt and payment of the resulting invoices. We completed acceptance testing on the switching equipment portion of the project which will allow our vendor to submit invoices for not only this equipment but also for the services to install the switches and microwave radios included within the project. Due to our structured payment process, we will likely be able to report these expenditures within the first quarter of 2013. | 81 | Customer Acquisition, Support and Billing | Our customer acquisition, support and billing milestone trails the progress that was predicted on our baseline. As of the close of the fourth quarter, the acceptance testing of the entire network remains to be completed. Once complete, this milestone will also be complete. | 100 | This milestone is complete. | 90 | This milestone is on schedule. The network design that remains to be completed is in regard to the connections to our last mile service providers and Community Anchor Institutions. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 96 | This milestone remains on schedule. | 67 | Our equipment procurement milestone continues to trail the progress predicted in our baseline report; however, we believe that we will be in agreement within the first quarter of 2013. The completion of acceptance testing on the switching equipment portion of the project in mid December will allow our equipment vendor to begin to invoice us for this equipment as well as for the services to install the equipment. | 100 | This milestone is complete. | 16 | Our equipment deployment milestone continues to trail the progress predicted in the baseline report. Due to acceptance testing of the switching equipment that occurred in mid December, we anticipate receipt and payment for this equipment and its installation to occur within the first quarter of 2013. We believe that we will catch the progress predicted in the baseline report within the first quarter. | 69 | Acceptance testing for our switching equipment was completed in mid December. With the completion of this testing, we anticipate receipt of invoices for this work early in the first quarter of 2013. The payment of these invoices will allow us to catch up to the baseline within the first quarter. | 2013-02-14 14:14 | 2013-02-14 14:14 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2013 | Q1 | Q1 - 2013 | 9773 | 8421 | TRUE | 86 | Our project made significant progress during the first quarter with the receipt and payment of invoices for the switching equipment as well as the services to install a majority of the equipment purchased as part of the project. The payment of these invoices allowed us to get to 86% complete for the overall project. | 81 | Customer Acquisition, Support and Billing | The remaining task within this milestone is dependent upon our final end to end test of the system which is scheduled for May of 2013. With successful completion of the test, the final invoice for the customer support and billing system will be received and paid. | 100 | This milestone is complete. | 90 | This milestone is on schedule. The network design that remains to be completed is in regard to the connections to our last mile service providers and Community Anchor Institutions. The design for those connections has been determined; however, until they are complete and the invoices paid, we are unable to show an increase in progress. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 96 | This milestone remains on schedule. | 92 | During the first quarter of 2013, we made significant progress on the Equipment Procurement milestone. With the completion of our switching equipment upgrades, we were able to receive and pay a significant number of invoices. The items remaining in this category are for connections to the last mile service providers and community anchor institutions. This milestone is on schedule. | 100 | This milestone is complete. | 84 | With the completion of our switching equipment upgrades, a majority of the invoices for services were received and then paid allowing us to show 84% completion of this milestone. The remaining expenditures in this category are for the installation of switching hub equipment as well as the installation of equipment to support our connections to last mile service providers and community anchor institutions. | 86 | With the receipt and payment of invoices for the acceptance testing of our switching equipment, we were able to make progress on this milestone. The remaining items within this milestone are expected to be completed within the second quarter. The expenditures that follow will likely fall near the end of the second quarter or early third quarter. | 2013-05-16 14:59 | 2013-05-16 14:59 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2013 | Q2 | Q2 - 2013 | 10621 | 8971 | TRUE | 91 | Our project continues to make progress toward completion. The upgrade of the final two links of the microwave backbone are underway and testing of the complete network has been engineered and planned to take place in July. The project is on schedule for a successful completion in August. | 100 | Customer Acquisition, Support and Billing | This milestone is complete. | 100 | This milestone is complete. | 90 | This milestone is on schedule. Invoices for work completed in June are expected within the month of July allowing us to complete this milestone. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 98 | This milestone remains on schedule. The final invoice for this category is expected within the month of July allowing us to complete this milestone. | 94 | The items remaining in our Equipment Procurement category are related to the connection of last mile service providers and community anchor institutions which are currently in progress. | 100 | This milestone is complete. | 90 | The items remaining in our Equipment Deployment category are related to the connection of last mile service providers and community anchor institutions which are currently in progress. | 94 | The items remaining in our Network Testing category are related to the final end to end testing of the network scheduled for mid July. Upon successful completion of the end to end test, this milestone will be complete. | 2013-08-16 14:28 | 2013-08-16 14:28 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2013 | Q3 | Q3 - 2013 | 11303 | 9451 | TRUE | 100 | The upgrade of the final two links of the microwave backbone was completed during the third quarter. Successful testing of the complete network was completed within September. Invoices for this work will be received early in the closeout period. | 100 | Customer Acquisition, Support and Billing | This milestone is complete. | 100 | This milestone is complete. | 100 | This milestone is on schedule. Invoices for the final design of the switching network will be received early in the closeout period allowing this milestone to reach 100% of progress. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 100 | This milestone is complete. | 100 | This milestone is on schedule. The remaining items are related to the connection of last mile service providers and community anchor institutions that were completed in September. | 100 | This milestone is complete. | 100 | This milestone is on schedule. The remaining items are related to the connection of last mile service providers and community anchor institutions that were completed in September. | 100 | This milestone is on schedule. The remaining items are related to the connection of last mile service providers and community anchor institutions that were completed in September. | 2013-11-20 10:48 | 2013-11-20 10:48 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570018 | 2010 | Q3 | Q3 - 2010 | 453 | 1493 | TRUE | 2 | No significant variance from baseline | 0 |  | N/A | 100 | Satisfied EA Requirement in First Reporting Quarter | 22 | Resulting from delays in recruitment. | 15 | No significant variance from baseline | 0 | N/A | 2 | Variance due to delays in recruitment and employment commencement dates. | 2 | Manufacturer delivery delays. Equipment will arrive in the next quarter. | 0 | No significant variance from baseline | 2 | No significant variance from baseline | 0 | No significant variance from baseline | 2010-11-30 11:27 | 2010-11-30 11:27 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2010 | Q4 | Q4 - 2010 | 1353 | 2369 | TRUE | 85 | No variance from baseline. | 0 |  | N/A | 100 | Satisfied EA requirement in first reporting quarter. | 47 | No variance from baseline. | 63 | Rights of way ahead of schedule by 47% due to key rooftop acquistion completed at end of this quarter. Originally was scheduled to be completed at beginning of next quarter. | 0 | N/A | 19 | Recruitment Delay of Network Analyst reflected in expenditures. (3% variance from baseline). | 5 | 46% variance from baseline because funds were not disbursed in this quarter as anticipated. However, procurement which was scheduled to be completed to-date has been completed. Disbursement of funds for procurement will be made in Q1-2011. | 99 | No variance from baseline. | 6 | Recruitment delays of Network Analyst reflected in expenditures (5% variance from baseline) | 0 | Recruitment delays of Network Analyst reflected in expenditures (4% variance from baseline) | 2011-02-24 08:16 | 2011-02-24 08:16 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2011 | Q1 | Q1 - 2011 | 2411 | 2951 | TRUE | 87 | No variance from baseline. | 0 |  | NA | 100 | No variance from baseline. | 55 | Variance of 2% due to delays in staff recruitment. | 63 | Variance of 7% due to disbursement/invoicing delays, primarily for legal fees. | 0 | NA | 52 | Variance of 35% due to finalization of legal agreements for terrestrial network tower sites. | 42 | Variance of 25% due to finalization network design for RF terrestrial portion. Upon completion, we will issue RFP for equipment. | 99 | No variance from baseline. | 10 | Variance of 10% due to delays in staff recruitment and equipment procurement. | 4 | Variance of 5% due to delays in staff recruitment and equipment procurement. | 2011-05-31 16:37 | 2011-05-31 16:37 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2011 | Q2 | Q2 - 2011 | 2441 | 2966 | TRUE | 90 | Variance of 2.5% from baseline, no variance from revision last quarter. | 0 |  | N/A | 100 | No variance from baseline. | 66 | No variance from baseline. | 63 | Variance of 14% from baseline due to delays in finalization of legal agreements for terrestrial network tower sites. | 0 | N/A | 63 | Variance of 30% from baseline due to delays in finalization of legal agreements for terrestrial network tower sites. | 44 | Variance of 32% from baseline due to delays in finalization of legal agreements for terrestrial network tower sites. | 99 | No variance from baseline. | 17 | Variance of 15% from baseline due to delays in finalization of legal agreements for terrestrial network tower sites. | 10 | Variance of 7% from baseline due to delays in finalization of legal agreements for terrestrial network tower sites. | 2011-07-11 18:21 | 2011-07-11 18:21 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2011 | Q3 | Q3 - 2011 | 4037 | 3859 | TRUE | 90 | No variance from revised projections | 0 |  | N/A | 100 | No variance from baseline | 73 | No significant variance from revised projections | 64 | Variance of 30% from revised projections due to route change preparations & negotiations for wireless sites. | 0 | N/A | 92 | Variance of 11% from revised projections, 3% from baseline due to route change preparations & negotiations for wireless sites. | 54 | Variance of 7% from revised projections, 28% from baseline due to route change preparations & negotiations for wireless sites. | 99 | No variance from projections or baseline | 24 | Variance of 2% from revised projections, 18% from baseline due to route change preparations & negotiations for wireless sites. | 13 | Variance of 3% from revised projections, 12% from baseline due to route change preparations & negotiations for wireless sites. | 2011-11-14 16:14 | 2011-11-14 16:14 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2011 | Q4 | Q4 - 2011 | 4961 | 4635 | TRUE | 93 | 2% variance from baseline | 0 |  | NA | 100 | No variance from baseline | 83 | 1.8% variance from baseline due to redesign and engineering of network and preparation of route change. | 100 | Actual Milestone Value: 101.78%. Exceeded 100% due to expansion of network route in approved route change and acquisition of additional tower sites. | 0 | NA | 92 | 4% variance from baseline due to pending route change approval. | 55 | 33% variance due to hold on equipment procurement pending route change approval. | 99 | No variance from baseline | 38 | 15% variance due to pending route change approval. | 22 | 13% variance due to pending route change approval. | 2012-02-13 10:38 | 2012-02-13 10:38 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2012 | Q1 | Q1 - 2012 | 6177 | 5691 | TRUE | 94 | Variance of 2% from baseline | 0 |  | N/A | 100 | No variance from baseline | 92 | Variance of 5% due to redesign of network in accordance with approved route change. | 100 | Actual Milestone Value: 101.96%. Exceeded 100% due to expansion of network route in approved route change and acquisition of additional tower sites. | 0 | N/A | 94 | Variance of 3% from baseline due to pending FCC license issuance | 61 | Variance of 33% from baseline due to pending FCC license issuance | 99 | No significant variance from baseline | 45 | Variance of 18% from baseline due to pending FCC license issuance | 34 | Variance of 12% from baseline due to pending FCC license issuance | 2012-05-18 11:07 | 2012-05-18 11:07 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2012 | Q2 | Q2 - 2012 | 6925 | 6090 | TRUE | 96 | No significant variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 95 | Variance of 4% due to redesign of network in accordance with approved route change. | 100 | Actual 101.99%. Exceeded 100% due to expansion of network route in approved route change and acquisition of additional tower sites. | 0 | N/A | 96 | Variance of 2% from baseline due to delays in FCC license issuance | 82 | Variance of 15% from baseline due to delays in FCC license issuance | 99 | No significant variance from baseline | 54 | Variance of 18% from baseline due to delays in FCC license issuance | 50 | Variance of 6% from baseline due to delays in FCC license issuance | 2012-08-08 14:34 | 2012-08-08 14:34 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2012 | Q3 | Q3 - 2012 | 7811 | 6609 | TRUE | 98 | No significant variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 95 | No significant variance from baseline | 100 | Actual 101.99% Exceed budget due to approved network route change and acquisition of additional tower sites. | 0 | N/A | 97 | No significant variance from baseline | 92 | Variance of 8% due to challenges with 2 POIs, which will be addressed in Oct2012 Route Change | 99 | No significant variance from baseline | 64 | Variance of 17% due to original FCC delays. However, milestones are tied with salary expenditures. Deployment is on target to meet 3/31/13 deadline. | 55 | Variance of 15% due to original FCC delays. However, milestones are tied with salary expenditures. Deployment is on target to meet 3/31/13 deadline. | 2012-11-09 11:20 | 2012-11-09 11:20 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2012 | Q4 | Q4 - 2012 | 8715 | 7520 | TRUE | 99 | No variance | 0 |  | NA | 100 | No variance | 100 | No variance | 100 | No variance | 0 | NA | 99 | No variance | 97 | No variance | 99 | No variance | 69 | Variance due to delays in issuance of FCC licenses. Currently pending 2 licenses. | 74 | Variance due to delays in issuance of FCC licenses. Currently pending 2 licenses. | 2013-02-12 08:50 | 2013-02-12 08:50 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2013 | Q1 | Q1 - 2013 | 9879 | 8478 | TRUE | 99 | Extension received in February 2013 to permit expansion of project to include PRBI-TU segment | 0 |  | NA | 100 | No variance | 100 | Actual 102%, due to new design work on PRBI-TU segment | 100 | No variance | 0 | NA | 100 | No variance. We anticipate this will exceed 100% as well, as we will incur costs related to expanded PRBI-TU segment which was not included in original baseline. | 98 | Variance due to expansion of project. | 99 | Variance due to expansion of project. | 78 | Variance due to expansion of project. | 79 | Variance due to expansion of project. | 2013-05-23 08:42 | 2013-05-23 08:42 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2013 | Q2 | Q2 - 2013 | 10707 | 9017 | TRUE | 99 | Extension received in Feb 2013 to permit expansion of project to include PRBI-TU segment. | 0 |  | NA | 100 | No variance | 100 | Actual 102%, due to new design work on PRBI-TU segment | 100 | No variance | 0 | NA | 100 | Actual 101%, due to project expansion to include PRBI-TU segment | 98 | Variance due to expansion of project | 99 | Variance due to expansion of project | 87 | Variance due to expansion of project | 84 | Variance due to expansion of project | 2013-08-23 11:19 | 2013-08-23 11:19 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2013 | Q3 | Q3 - 2013 | 11631 | 9752 | TRUE | 100 | Successful project completion as of September 30 2013 | 0 |  | NA | 100 | Successful project completion as of September 30 2013 | 100 | Successful project completion as of September 30 2013 | 100 | Successful project completion as of September 30 2013 | 0 | NA | 100 | Successful project completion as of September 30 2013 | 100 | Successful project completion as of September 30 2013 | 100 | Successful project completion as of September 30 2013 | 100 | Successful project completion as of September 30 2013 | 100 | Successful project completion as of September 30 2013 | 2014-01-21 11:27 | 2014-01-21 11:27 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570019 | 2010 | Q2 | Q2 - 2010 | 47 | 1289 | FALSE | 10 |  |  |  |  | 100 |  | 80 |  | 90 |  | 50 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2010 | Q3 | Q3 - 2010 | 297 | 1415 | TRUE | 3 | Awaiting approval of EA before beginning construction activities. Our contingency plan is to hire additional construction forces to complete the project on time. | 0 |  | N/A | 95 | Awaiting USFWS approval. | 55 | Design to be completed by Y2Q1. Additional time needed to review & execute EF&I contracts & wait for EA approval. | 90 | No Information to add at this time. | 50 | No Information to add at this time. | 0 | N/A | 0 | Ordered Generators in August (4). | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-01 11:20 | 2010-11-01 11:20 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2010 | Q4 | Q4 - 2010 | 1129 | 2168 | TRUE | 7 | VAMRC permitting requirements delay in obtaining Environmental Assessment approval. | 0 |  | N/A | 100 | PA assessment have to be reported to NTIA & SHPO | 70 | Design took longer than anticipated due to the Design teams verifying SHPO sites to be completed in Y2Q1. | 95 | Awaiting approval of two (2) RailRoad permits | 90 | Awaiting approval of VDOT Memorandum of Usage, City of Petersburg permit, VA Corp of Engineers, VAMRC | 0 | Awaiting final permit approval on two (2) site for approval of EA was on 12-7-10. | 0 | Ordered huts in December | 0 | Construction could not start until after EA approval & satisfaction of PA & VAMRC to start in 1-11. | 0 | N/A | 0 | N/A | 2011-02-14 11:43 | 2011-02-14 11:43 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2011 | Q1 | Q1 - 2011 | 2093 | 2792 | TRUE | 19 | PA approval delayed construction start until March 2011 | 0 |  | N/A | 95 | Addendum needed | 87 | Two routes to be redesigned | 100 | Completed | 95 | Awaiting approval of VMRC & USACE permits | 0 | RFP's drafted to send out in April 2011.The delay in the EA contributed to the delay, but we also decided, after much discussion, to bid the site work, instead of using our normal vendor that handles our site work. We had to prepare the RFP, distribute the RFP, obtain responses and evaluate the bids. We should complete in 2011, quarter 2 and then proceed with construction. | 13 | Network Equipment ordered in March 2011 | 10 | Construction started in March 2011 | 0 | Expect delivery in Y2Q2. Awaiting hut installation in Y2Q2 & Y2Q3. This equipment is housed in huts that have to be constructed as detailed in the site preparation section above. Therefore, the delay in the EA/PA process delayed the equipment deployment. We have ordered the equipment to be available when the site work and huts are completed. | 0 | N/A | 2011-05-17 15:09 | 2011-05-17 15:09 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2011 | Q2 | Q2 - 2011 | 2989 | 3252 | TRUE | 25 | PA approval delayed construction start until March, 2011. This quarter we have moved from 19% complete to 25% complete. | 0 |  | N/A | 95 | Addendum needed. To be submitted by 7-29-11. | 95 | Two routes had to be redesigned. One is complete; the other one is 50% complete. Should be complete by 7-31-11. | 100 | N/A | 97 | Awaiting final VDOT approval on re-route design. Expected approval date is 9-1-11. | 0 | Site work was delayed due to preparing RFP and bidding out the work. | 16 | Equipment has been ordered. 16% has been received. We expect to receive the remaining equipment by the end of Y2Q3. | 38 | Completed 116 miles this quarter. Construction was delayed due to the PA delay. | 0 | Delay in site preparation for huts has delayed some equipment installation. However, all of the ordered equipment has not been delivered. The expected delivery complete date is 9-30-11. Therefore equipment installation will be started in 8-2011 and should be complete by 11-30-11. | 0 | N/A | 2011-08-09 16:54 | 2011-08-09 16:54 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2011 | Q3 | Q3 - 2011 | 4003 | 3841 | TRUE | 40 | PA approval delayed construction start until March 2011. This quarter moved from 25% complete to 40%. | 0 |  | N/A | 95 | Addendum submitted. Expect approval 10/2011. | 100 | Complete | 100 | Complete | 100 | Complete | 50 | Site preparation slowed by wet weather. Remaining 2 sites to be completed by 12/2011. | 90 | Expect to receive remaining equipment by 11/2011. | 61 | Completed 98 miles this quarter. Awaiting EA addendum approval for part of segments 5 & 6. | 0 | Equipment deployment to start for 2 completed sites by 11/1/2011. All deployment to be completed by 2/2012. | 10 | Some completed legs off of backbone have been tested. Expected to complete testing by 3/2012. | 2011-11-14 09:00 | 2011-11-14 09:00 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2011 | Q4 | Q4 - 2011 | 4865 | 4565 | TRUE | 53 | Moved from 40% to 53% complete. EA approval delayed the start date to March 2011 | 0 |  | N/A | 99 | EA addendum under review. Expect approval in January 2012 | 100 | Complete | 100 | Complete | 100 | Complete | 75 | Wet weather has hampered efforts to complete 4th unit. To be completed in January 2012 | 100 | Complete | 80 | Completed 81 miles this quarter | 20 | Equipment deployment delayed due to delay in site work | 30 | Testing underway in Segments 2, 3, 6. Complete in Y3Q3. | 2012-02-03 14:37 | 2012-02-03 14:37 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2012 | Q1 | Q1 - 2012 | 5965 | 5582 | TRUE | 62 | Moved from 53% to 62% complete. EA approval delay and VDOT approval delayed start of segment 5 reroute. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 94 | Completed 61 miles this quarter | 40 | Equipment deployment continues after completion of interconnection points to be completed in Y3Q3. | 60 | Testing underway in Segment 1; complete in segments 2,3 & 6. Project testing complete in Y3Q3. | 2012-05-08 14:24 | 2012-05-08 14:24 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2012 | Q2 | Q2 - 2012 | 6951 | 6103 | TRUE | 73 | Moved from 62% to 73% complete. VDOT approvals have delayed start of 2nd & 3rd work orders for segment 5 (Petersburg Reroute) | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 96 | Completed 13 miles this quarter | 70 | Equipment deployment continues after completion of nodes | 80 | Testing underway in 3 segments to be completed Y3Q3 | 2012-08-09 09:27 | 2012-08-09 09:27 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2012 | Q3 | Q3 - 2012 | 7753 | 6571 | TRUE | 84 | Project moved from 73% to 84% this quarter. Project to be complete by end of Y3Q4 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 66 | Four (4) out of six (6) sites completed. (Two sites on route modification to be built) | 100 | Complete | 96 | Construction was halted awaiting material & permit approval for route modification | 85 | Awaiting completion of route modification | 95 | Awaiting completion of route modification & segment 5 construction completion | 2012-11-01 13:35 | 2012-11-01 13:35 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2012 | Q4 | Q4 - 2012 | 8665 | 7487 | TRUE | 88 | Project moved from 84% to 88% complete this quarter. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 97 | Moved from 413 to 421 miles placed. Eight (8) miles placed this quarter. Awaiting route modification approval. | 85 | Awaiting completion of remainder of cable. | 95 | Awaiting completion of equipment installation. | 2013-02-07 16:14 | 2013-02-07 16:14 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2013 | Q1 | Q1 - 2013 | 9607 | 8335 | TRUE | 92 | Approved route modification which allowed for placing additional cable which is underway | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 99 | Completion of route modification additions to complete 6-30-13 | 95 | Awaiting completion of route modification | 99 | Awaiting completion of route modification | 2013-05-06 09:59 | 2013-05-06 09:59 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2013 | Q2 | Q2 - 2013 | 12309 | 10483 | TRUE | 100 | Complete; 95% of Grant amount spent | 0 |  | N/A | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 2014-07-18 15:24 | 2014-07-18 15:24 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570023 | 2010 | Q3 | Q3 - 2010 | 12013 | 10177 | TRUE | 15 | As a result of the re-evaluation of the design approach, the complexity of the specifications for procurement and the modified requirements for the capacity delivery under the IRU are responsible for the resultant delay in the purchase of equipment, progress payments to Level 3, and the execution of commercial tower leases. | 25 | In-Kind Contribution | On Target | 0 | Exempt | 80 | Network Design on schedule | 0 | N/A | 5 | The Project Management Office is in the process of contacting county agencies to establish permitting procedures for each county and to streamline the overall permitting process. | 30 | Site preparation follows final design parameters and equipment procurement/selection of vendors in order to determine specific site preparation requirements. The delay is due to the re-evaluation of the engineering design from the previous quarter. This milestone will get back on schedule in subsequent quarters as equipment procurement moves forward and final design parameters are resolved. | 30 | Delay is due to the re-evaluation of engineering design and the addition of more engineering resources in previous quarters. Network redesign allowed greater participation from vendors, more potential capacity, and higher reliability. Equipment procurement underway and should be largely complete next quarter. | 15 | Master IRU with Level 3 for fiber capacity executed. Work orders initiated. Interim DNS servers in place. Level 3 engineering and provisioning is in progress. Level 3â€™s network plan was revisited due to revised network configuration and design. | 0 | Procurement specifications and timeline have been developed. Delay is due to the re-evaluation of engineering design and the addition of more engineering resources in previous quarters for reasons noted above. Should be back on schedule Q1 2011. | 0 | Not yet ready for testing- elements will be tested as deployed and the network will undergo extensive testing prior to lanch of formal service. | 2014-03-31 22:18 | 2014-03-31 22:18 | 6524 | 6524 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2010 | Q4 | Q4 - 2010 | 1351 | 2367 | TRUE | 15 | The re-evaluation of the network design approach that began in previous quarters and continued through this reporting quarter resulted in an overall project delay and has impacted most major milestone categories, including site preparation, equipment procurement, network build, equipment deployment, network testing, and in-kind lease agreements, where further progress was originally anticipated according the Baseline Report. Final design to be finalized in March 2011. In addition, the modified requirements for the capacity delivery under the IRU that began in previous quarters delayed the anticipated progress payments to Level 3. However, upstream IRU design configuration was completed this reporting period. Circuit delivery is on schedule, and prep work for data center equipment began during this reporting period at Level 3â€™s Tampa co-location facility. Execution of commercial tower leases is also on hold pending Grants Office review and approval of tower lease language. We are | 35 | IN-KIND | On-target. We are checking for previous / duplicate federal funding for targeted in-kind assets, per the Grants Officeâ€™s request. | 0 | Exempt | 85 | Network design is back on schedule. Final structural assessments are pending. | 0 | N/A | 30 | County agencies were contacted to establish and streamline permitting procedures for each county. Tower companies were also contacted to identify their certification requirements and application procedures. | 35 | Site preparation follows final design parameters and equipment procurement/selection of vendors in order to determine specific site preparation requirements. The delay is due to the re-evaluation of the engineering design from previous quarters that carried into this current reporting period. Also, execution of commercial tower leases is on hold pending Grants Office review and approval of tower lease language. However, final engineering design is near completion, equipment vendors have been selected, and initial equipment purchase orders were executed during this reporting period. Therefore, we anticipate that this milestone will get back on schedule in subsequent quarters as equipment procurement continues to move forward and final design parameters are resolved. | 30 | Delay is due to the re-evaluation of engineering design and the addition of more engineering resources in previous quarters that carried into this current reporting period. The network redesign allowed for greater participation from vendors, more potential capacity, and higher reliability. Equipment RFPs were released, equipment vendors were selected and approved, and initial equipment purchase orders were executed during this current reporting period. Therefore, we anticipate equipment procurement to be on schedule by the end of next quarter. | 30 | Upstream IRU design configuration complete. Circuit delivery is on schedule, and Level 3â€™sTampa gateway / co-location facility was prepped for data center equipment installation. Execution of commercial tower leases is on hold pending Grants Office review and approval of tower lease language. We are also checking for previous / duplicate federal funding for targeted in-kind assets, per the Grants Officeâ€™s request. | 5 | Delay is due to the re-evaluation of engineering design and the addition of more engineering resources in previous quarters that carried into this current reporting period. Equipment RFPs were released, equipment vendors were selected and approved, and initial equipment purchase orders were executed during this reporting period. We anticipate this milestone to get back on schedule by the end of Q1 2011. | 5 | Not yet ready for testing. Network elements will be tested as equipment is deployed, and the network will undergo extensive testing prior to launch of formal service. As referenced above, the delay is due to the re-evaluation of engineering design and the addition of more engineering resources in previous quarters that carried into this current reporting period. We anticipate this milestone to get back on schedule by the end of Q1 2011. | 2011-02-24 07:24 | 2011-02-24 07:24 | 5502 | 5502 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2011 | Q1 | Q1 - 2011 | 2215 | 2853 | TRUE | 15 | The variance for Overall Project progress from the estimated Baseline Plan is the continued result of the network design re-evaluation that began in previous quarters. Please see Section 1, Item #3 for a more detailed explanation of the project's variance from the Baseline plan. The network design was finalized this quarter, with the exception of possible modifications that will be determined by the status of remaining tower structural assessments. As part of our efforts to catch up to the Baseline Plan, we are moving forward with equipment procurement--executing purchase orders, managing inventory, conducting bench tests, and staging equipment in advance of network deployment. With the execution of individual commercial tower site license agreements and the engagement of civil and installation contractors underway, we anticipate that the overall project completion schedule will be back in line with Baseline Plan projections in subsequent quarters. | 0 | In-Kind Tower Licenses | The variance for Network Testing from the Baseline Plan is the continued result of the network design re-evaluation that began in previous quarters. Please see Section 1, Item #3 for a more detailed explanation of the project's variance from the Baseline plan. In previous Performance Progress Reports, progress reporting for this milestone category was previously based on work completed, such as identification of in-kind vertical assets in the core network design, engagement of in-kind asset owners, and development of a master in-kind site license agreement. From this point forward, however, for this category (and for all milestone categories) we will report milestone completion percentages based on budget expenditures, incorporating both Federal funds and non-Federal share matching in-kind contributions in the milestones calculation, per the Additional Guidance instructions. Site license agreements for in-kind vertical assets have not been executed yet. However, as part of our eff | 0 | N/A. Categorically exempt from Environmental Assessment. | 88 | On schedule, but the percent complete reported here is less than the Actuals for Engineering fees reported in Cost Classifications d. and e. in the Infrastructure Budget Execution Details section of this report. As noted in Section 1, Item #3, we are in the process of preparing a budget reallocation Award Action Request to reconcile or adjust our SF-424C budget categories that were originally based on the turnkey link network design project plan. In the original budget allocation, costs for professional and deployment services associated with the original turnkey links network design were originally allocated to the Equipment category. Upon approval of the Award Action Request, these costs will be reallocated to the Engineering categories (d. and e.). As also noted in Section 1, Item #3, we are also preparing an Award Action Request for Network Route / Design Change to establish that our network design has changed from the original Turnkey Link Spur Network design to our current in | 0 | N/A | 50 | On schedule. | 0 | Progress reported for this milestone category in previous Performance Progress Reports was attributed to the progress of work associated with the development of the Request for Quotes procurement document for Civil and Electrical Site Work. As noted in Section 1, Item #3, we are in the process of preparing a budget reallocation Award Action Request to reconcile or adjust our SF-424C budget categories that were originally based on the turnkey link network design project plan. Upon approval of the Award Action Request, the budget amount originally allocated for Site Preparation will be re-allocated to other Cost Classification categories. | 11 | The variance for Equipment Procurement from the Baseline Plan is the continued result of the network design re-evaluation that began in previous quarters. Please see Section 1, Item #3 for a more detailed explanation of the project's variance from the Baseline plan. Progress reported for this milestone category in previous Performance Progress Reports was attributed to the progress of work associated with the development of the Request for Proposals procurement documents for network equipment, the subsequent review of submitted network equipment proposals, and the selection of equipment vendors. The progress reported in this report is based on line item budget expenditures in the Equipment Cost Classification category, and the budget amount for the Equipment Cost Classification category is based on the original turnkey link network design plan. However, as noted in Section 1, Item #3, we are in the process of preparing a budget reallocation Award Action Request to reconcile or adju | 7 | The variance for Network Build from the Baseline Plan is the continued result of the network design re-evaluation that began in previous quarters. Please see Section 1, Item #3 for a more detailed explanation of the project's variance from the Baseline plan. Progress reported for this milestone category in previous Performance Progress Reports was attributed to progress of work instead of budget expenditures for the Land, Structures, Right-of-Ways Cost Classification category (b.), and the budget amount for this Cost Classification category is based on the original turnkey link network design plan. However, as noted in Section 1, Item #3, we are in the process of preparing a budget reallocation Award Action Request to reconcile or adjust our SF-424C budget categories that were originally based on the turnkey link network design project plan. Upon approval of the Award Action Request, a portion of the budget amount originally allocated for Land, Structures, Right-of-Ways Cost Classi | 0 | The variance for Equipment Deployment from the Baseline Plan is the continued result of the network design re-evaluation that began in previous quarters. Please see Section 1, Item #3 for a more detailed explanation of the project's variance from the Baseline plan. Progress reported for this milestone category in previous Performance Progress Reports was attributed to the progress of work associated with the solicitation of Civil and Equipment Installation contractors, the implementation of equipment inventory management and staging procedures. The progress reported in this report is based on line item budget expenditures in the Equipment Cost Classification category, and the budget amount for the Equipment Cost Classification category is based on the original turnkey link network design plan. As noted in Section 1, Item #3, we are in the process of preparing a budget reallocation Award Action Request to reconcile or adjust our SF-424C budget categories that were originally based o | 0 | The variance for Network Testing from the Baseline Plan is the continued result of the network design re-evaluation that began in previous quarters. Please see Section 1, Item #3 for a more detailed explanation of the project's variance from the Baseline plan. Progress reported for this milestone category in previous Performance Progress Reports was attributed to the receipt and testing of sample equipment cabinets, sample microwave radios, and initial gateway datacenter equipment. The progress reported in this report is based on line item budget expenditures in the Equipment Cost Classification category, and the budget amount for the Equipment Cost Classification category is based on the original turnkey link network design plan. As noted in Section 1, Item #3, we are in the process of preparing a budget reallocation Award Action Request to reconcile or adjust our SF-424C budget categories that were originally based on the turnkey link network design project plan. In the original | 2011-05-20 14:13 | 2011-05-20 14:13 | 6621 | 6621 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2011 | Q2 | Q2 - 2011 | 3215 | 3369 | TRUE | 17 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. We had anticipated a significant expenditure for this reporting period for the delivery of upstream circuits for our Indefeasible Right of Use. However, we are still waiting for final fiber connections and testing to be completed at our four Point of Presence sites and also our two datacenter locations. Payment is tied | 1 | In-Kind Contributions | We have received in-kind contributions in the form of donated professional services. The variance from the Baseline Plan is the continued result of the network design re-evaluation and re-engineering process that began in previous quarters. Please see Section 1, Item #3 for a more detailed explanation of the project's variance from the Baseline plan. In previous Performance Progress Reports (submitted prior to the Performance Progress Report for 1st Quarter 2011), progress reporting for this milestone category was previously based on work completed, such as identification of in-kind vertical assets in the core network design, engagement of in-kind asset owners, and development of a master in-kind site license agreement. However, per the Additional Guidance instructions provided by the Grants Office in April 2011 and beginning with the Performance Progress Report submitted for the last quarter, we are now reporting milestone completion percentages based on budget expenditures (incor | 0 | N/A. Categorically exempt from Environmental Assessment. | 91 | On schedule, but the percent complete reported here is less than the Actuals for Engineering fees reported in Cost Classifications d. and e. in the Infrastructure Budget Execution Details section of this report. As noted in Section 1, Item #3, we prepared a draft budget reallocation to be submitted in upcoming quarter as an Award Action Request to reconcile or adjust our SF-424C budget categories that were originally based on the turnkey link network design project plan. In the original budget allocation, costs for professional and deployment services associated with the original turnkey links network design were originally allocated to the Equipment category. Upon submittal and approval of the Award Action Request, these costs will be reallocated to the Engineering categories (d. and e.). As also noted in Section 1, Item #3, at the Project Officer direction, we also prepared a draft Award Action Request for Network Route / Design Change and submitted to the Program Office for revie | 0 | N/A | 60 | On schedule. | 0 | In previous Performance Progress Reports (submitted prior to the Performance Progress Report for 1st Quarter 2011), progress reported for this milestone category was attributed to the engagement of tower owners, the negotiation of master commercial tower lease terms, and the initial draft development of the procurement document for civil and site electrical work. A 3 month delay in getting the Davis-Bacon wage decisions prevented issuance of RFP's for any site work until received. RFP's were issued within a week of receipt. As noted in Section 1, Item #3, we prepared a draft budget reallocation to be submitted as an Award Action Request following Program Office review and comment, to reconcile or adjust our SF-424C budget categories that were originally based on the turnkey link network design project plan. Upon approval of the Award Action Request, the budget amount originally allocated for Site Preparation will be re-allocated to other Cost Classification categories. | 14 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011; and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. In previous Performance Progress Reports (submitted prior to the Performance Progress Report for 1st Quarter 2011), progress reported for this milestone category was attributed to work associated with the development of the Request for Proposals procurement documents for network equipment, the subsequent review of submitte | 7 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. In previous Performance Progress Reports (submitted prior to the Performance Progress Report for 1st Quarter 2011), progress reported for this milestone category was attributed to progress of work instead of budget expenditures for the Land, Structures, Right-of-Ways Cost Classification category (b.), and the budget amoun | 0 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up. In previous Performance Progress Reports (submitted prior to the Performance Progress Report for 1st Quarter 2011), progress reported for this milestone category was attributed to the progress of work associated with the solicitation of Civil and Equipment Installation contractors, the implementation of equipment inventory management and stag | 0 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. In previous Performance Progress Reports (submitted prior to the Performance Progress Report for 1st Quarter 2011), progress reported for this milestone category was attributed to the receipt and testing of sample equipment cabinets, sample microwave radios, and initial gateway datacenter equipment. The progress reported | 2011-08-18 18:34 | 2011-08-18 18:34 | 5502 | 5502 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2011 | Q3 | Q3 - 2011 | 4357 | 4035 | TRUE | 42 | With our disbursements to date, approved open (unpaid) expenditures (as defined per form SF-270), and our recipient match, overall project completion is at 42% for this reporting period. If we are allowed to report progress toward our recipient match contributions based on the signed letters of commitment and resolutions received from our member governments for their in-kind contributions, then overall project completion would be at 65% for this reporting period. Variance from Baseline during this period is primarily the result of (1) the use of resources to prepare a Corrective Action Plan, as directed by the Program and Grants Offices; (2) the suspension of payments under the Grant Award, effective August 18, 2011; and (3) the suspension of the Grant Award effective September 21, 2011. According to our estimates, the project would otherwise have been Substantially Complete by the end of this reporting period (four months ahead of the Federal deadline for Substantial Completion). | 2 | In-Kind Contributions | We confirmed our inventory of committed in-kind assets for our Federal match requirement. We streamlined our site acquisition process for in-kind assets, and we have compiled legal descriptions, parcel identification numbers, and other legal data necessary to formally execute site lease agreements with in-kind asset owners. If we are allowed to report progress toward our in-kind recipient match contributions based on signed letters of commitment and resolutions from our local member governments who have committed their in-kind contributions to this project, then the completion percentage for this category would be at 100% for this reporting period. As noted above, we put everything in place (legal descriptions, parcel identification numbers, etc.) so that in-kind lease agreements could be executed before the end of this reporting period, which would have enabled us to report corresponding progress for this period. However, compliance with the directive to prepare a Corrective A | 0 | N/A. Categorically exempt from Environmental Assessment. | 93 | There was marginal change from the previous quarter because relatively few approved expenditures were applied toward this Milestone category. As part of our efforts to realign the project with its Baseline plan, Jacobs Telecommunications has been engaged to perform network design quality assurance reviews, which includes checking engineering deliverables to ensure that they meet industry and Federal program standards. | 0 | N/A | 70 | This Milestone category remains on schedule. | 100 | As noted in our previous quarterly Performance Progress Reports, we prepared a draft budget reallocation to be submitted as an Award Action Request following Program Office review and comment, to reconcile or adjust our SF-424C budget categories that were originally based on the turnkey link network design project plan. Upon approval of the Award Action Request, the budget amount originally allocated for Site Preparation will be re-allocated to other Cost Classification categories. | 67 | As significant expenditures for equipment procurement continue to be accrued, we expect that this Milestone category will be realigned with the Baseline plan by the end of next quarter. | 51 | Variance from Baseline is primarily the result of (1) the use of resources to prepare a Corrective Action Plan, as directed by the Program and Grants Offices; (2) the suspension of payments under the Grant Award, effective August 18, 2011; and (3) the suspension of the Grant Award effective September 21, 2011. Prior to this suspension, a substantial delay was also incurred awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011). Following reinstatement of Federal funding, we expect to reach our Baseline projections for this Milestone category by next reporting period. | 34 | Significant progress was made in the field due to the efforts of our deployment contractors this past quarter. Variance from Baseline is primarily the result of (1) the use of resources to prepare a Corrective Action Plan, as directed by the Program and Grants Offices; (2) the suspension of payments under the Grant Award, effective August 18, 2011; and (3) the suspension of the Grant Award effective September 21, 2011. According to our estimates, we could have reached our Baseline goal if deployment had not been interrupted by this suspension. Substantial delays in deployment were also incurred awaiting Davis Bacon wage-rate determinations (more than 3 months), which delayed the procurement of our equipment installation contractors; awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (sub | 15 | Variance from Baseline is primarily the result of (1) the use of resources to prepare a Corrective Action Plan, as directed by the Program and Grants Offices; (2) the suspension of payments under the Grant Award, effective August 18, 2011; and (3) the suspension of the Grant Award effective September 21, 2011. Network testing follows closely behind equipment deployment. As noted above, substantial delays in deployment were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (submitted for comment in March 2011, AAR submitted in July 2011, still awaiting response). Upon reinstatement of Federal funding, bench testing and "burn-in" testing will continue for network equipment as it continues to be received and inventoried. Site | 2011-11-30 16:32 | 2011-11-30 16:32 | 6621 | 6621 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2011 | Q4 | Q4 - 2011 | 5383 | 5058 | TRUE | 60 | Total expenditures plus allowable in-kind match provides 60% complete. Variance from the baseline resulted from a series of delays that NFBA encountered during this reporting period, including the suspension of the Grant Award, the development of a Corrective Action Plan (CAP), and preparation and implementation of a Transition Plan to execute the CAP. In addition, NFBA encountered additional delays associated with transferring equipment from the Wachula warehouse to the Lake City NFBA warehouse, re-evaluation of existing network configurations, and the transfer of responsibilities to NFBA employees from contract staff, as well as the termination of NFBA's relationships with several key vendors. NFBA is on track to complete the project funded by the Grant Award before the end of the Award period. NFBA will be submitting a separate Memorandum to the BTOP Program Office reiterating this commitment. | 55 | In-kind | While the Transition Plan was being executed, NFBA focused on finalizing its non-federal, in-kind (match) contributions to the project. During 2011, NFBA operated under a proportionality waiver. By the December 31, 2011, expiration of that waiver, NFBA had booked matching contributions reflecting the same general rate of expenditure of federal funds, in compliance with this Award requirement. These assets are now being worked into the build schedule accordingly. | 0 | N/A; Categorically exempt from Environmental Assessment. | 100 | NFBA has transferred additional network engineering and construction responsibilities to the new engineering firm. During this transition, it has become apparent that certain changes to the NFBA network topology are necessary. As a result of the transition and these changes, additional resources will be required going forward. NFBA is preparing a request to reallocate its project budget to accommodate the additional required expenditures. | 0 | N/A | 100 | The transfer of permits to the new General Contractor pursuant to the Transition Plan is near completion. | 100 | Budget reallocation is underway to adjust allocation of funds to cover the additional expenditures. | 80 | NFBA's equipment expenditures are nearing completion. NFBA is preparing a request to reallocate budget surplus in this category to other areas of need. | 90 | Network build is behind schedule as a result of the issues NFBA encountered during this reporting period identified in Item 2a. NFBA has overcome these issues and expects to make rapid and efficient progress in this area during 2012. | 34 | Progress was delayed during the suspension of the Award and the development and implementation of the Transition Plan, including as a result of delays in the transfer of previously purchased equipment from NFBA's prior contractor. NFBA expects that its new contractor will begin installing equipment during 1st quarter 2012. | 15 | Progress was delayed during the suspension of the Award and the development and implementation of the Transition Plan, including as a result of delays in the transfer of previously purchased equipment from NFBA's prior contractor. NFBA expects that its new contractor will begin equipment testing during 1st quarter 2012. | 2012-02-29 07:30 | 2012-02-29 07:30 | 7368 | 7368 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2012 | Q1 | Q1 - 2012 | 6075 | 5637 | TRUE | 71 | With our total expenditures plus allowable in-kind contributions for recipient match, overall project completion is at 70.6% for this reporting period. As a result, we reached our Substantial Completion milestone during this past quarter. Variance from the baseline plan is largely the result of issues that began in previous quarters and carried over into this reporting period. These include the delays and difficulties associated with our efforts to gain access and custody of previously-purchased network equipment, the discovery of purchasing errors for previously-ordered tower hardware, the discovery of FCC license application errors that delayed the build-out of one of our Fiber Access Point sites, and the discovery of a design specification error with our field equipment cabinets that manifested itself during end-to-end field tests when equipment operating temperatures exceeded manufacturer recommendations. Please see Section 3 below for additional information regarding these is | 79 | In-Kind Contributions for Recipient Match | We continued to book contributed in-kind assets through this past quarter to maintain proportionality with federal expenditures as required, and we are continuing to work these assets into our network roll-out schedule as planned lateral extensions of our core network. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | We transferred network design responsibilities to our new engineering firm and implemented a strategy for network performance upgrades that will be necessary to accommodate anticipated customer demand. We finalized and submitted our Budget Reallocation Award Action Request and await approval. | 0 | N/A | 100 | We completed the transfer of permits to our new General Contractor. | 100 | We finalized and submitted our Budget Reallocation Award Action Request to address additional expenditures incurred in this category as a result of corrective actions and related transition processes that began in previous quarters. Once our Budget Reallocation request is approved, we will be able to adjust the budget number for this category and, accordingly, establish a realistic benchmark to measure against for reporting cost and schedule performance for site preparation. | 90 | The progress reported is measured against the original baseline budget. We completed and submitted our Budget Reallocation Award Action Request, which will reallocate the budget surplus in this category to other areas of need and represent a realistic benchmark to measure against for equipment procurement progress. We are behind our original baseline target for Equipment Procurement as a result of the issues discussed in Item 2a above and further described in Section 3 below. We completed an inventory assessment of previously-purchased network equipment that we transferred from Wauchula to our new warehouse in Lake City. We subsequently identified remaining equipment purchasing requirements and took appropriate action to finalize remaining procurement activities for core network equipment. | 95 | We are behind our original baseline target for Network Build as a result of the issues discussed in Item 2a above and further described in Section 3 below. Our resources are fully engaged to work through these issues, and we are on target to complete remaining Network Build activities by the end of next quarter. We completed and submitted our Budget Reallocation Award Action Request, which will reallocate the budget surplus in this category to other areas of need and represent a realistic benchmark to measure against for network build progress. | 35 | Equipment Deployment is behind our baseline target for this reporting period as a result of the issues discussed in Item 2a above and further described in Section 3 below. We have taken appropriate action to mitigate the impact of these issues while maintaining the progress that was re-established this quarter for equipment deployment. We are on target to complete deployment activities for all of our core network tower sites and fiber access points by the end of next quarter. | 20 | Network Testing is also behind our baseline target for this reporting period as a result of the issues discussed in Item 2a above and further described in Section 3 below. We are on target to complete end-to-end testing and interoperability testing by the end of next quarter. | 2012-05-14 21:46 | 2012-05-14 21:46 | 6621 | 6621 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2012 | Q2 | Q2 - 2012 | 7189 | 6222 | TRUE | 79 | With our total expenditures plus allowable in-kind contributions for recipient match, overall project completion is at 79% for this reporting period. Variance from the baseline plan is largely the result of unique challenges experienced this quarter in addition to residual effects from transition-related issues that began in previous quarters. Please see Section 3 below for more details. | 88 | In-Kind Contributions for Recipient Match | We continued to book contributed in-kind assets through this past quarter to maintain proportionality with federal expenditures as required, and we are continuing to incorporate these assets into our roll-out schedule as planned lateral extensions of our core network. | 0 | N/A. Categorically exempt from Environmental Assessment. | 75 | Percent complete variance from the baseline plan reflects the increase to the cost classification budget category associated with this milestone per our approved Budget Reallocation Award Action Request. Progress is reported against our approved revised budget, resulting in the completion percentage being decreased for this milestone category in comparison to our previous Performance Progress Report. Our core network design is functionally complete. We are continuing to work with demand forecasts to drive the implementation our network design enhancement plan, which addresses performance and capacity limitations that we discovered following a value-engineering / quality assessment of our pre-transition network design. The reallocation of budget funds to this milestone's budget category effectively addresses the cost impacts associated with this process. | 0 | N/A | 98 | Progress is reported against our approved revised budget, resulting in the completion percentage being decreased for this milestone category in comparison to our previous Performance Progress Report. Transfer of permits to our new General Contractor is complete. However, a few local permitting agencies required us to resubmit our permit applications for three of our core network tower sites. Permits for all remaining core network tower sites are approved and in-hand, and we remain on track with our baseline projection for this milestone. | 97 | Progress is reported against our approved revised budget, resulting in the completion percentage being decreased for this milestone category in comparison to our previous Performance Progress Report. Civil and electrical site work is substantially complete at 89 out of 92 core network commercial tower sites and at our Fiber Access Points in Branford, Monticello, Chiefland, and Live Oak. | 98 | Equipment procurement is complete for our data centers in Tampa and Orlando, all of our core network commercial tower sites, and our Fiber Access Points in Branford, Monticello, Chiefland, and Live Oak. | 98 | Site acquisition is complete for our data centers in Tampa and Orlando, all of our core network commercial tower sites, and our Fiber Access Points in Branford, Monticello, Chiefland, and Live Oak. | 90 | Equipment deployment is complete at our core datacenters, 87 out of 92 core network commercial tower sites, and at our Fiber Access Points in Branford, Monticello, Chiefland, and Live Oak. | 90 | Network testing is complete for our data centers in Tampa and Orlando and for our Fiber Access Points in Branford, Monticello, Chiefland, and Live Oak. We continue to see positive results with link alignment and end-to-end testing at our core network tower sites as we deploy network paths outward from our Fiber Access Points. | 2012-08-21 14:47 | 2012-08-21 14:47 | 7368 | 7368 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2012 | Q3 | Q3 - 2012 | 7951 | 6681 | TRUE | 86 | With our total expenditures plus allowable in-kind contributions for recipient match, overall project completion is at 86% for this reporting period. Variance from the baseline plan is the result of challenges experienced this quarter in addition to residual effects from transition-related issues that began in previous quarters. Please see Section 3 below for more details. | 96 | In-Kind Contributions for Recipient Match | We continued to book contributed in-kind assets through this past quarter to maintain proportionality with federal expenditures as required, and we are continuing to incorporate these assets into our roll-out schedule as planned lateral extensions of our core network. | 0 | N/A. Categorically exempt from Environmental Assessment. | 90 | We are continuing to work with demand forecasts to drive the implementation our network design enhancement plan, which addresses performance and capacity limitations that we discovered following a value-engineering / quality assessment of our pre-transition network design. | 0 | N/A | 100 | Remaining core network permitting issues have been resolved. | 99 | Civil and site electrical work is complete at 91 out of 92 core network tower sites. We resolved a site drawing issue and related permitting issue at our last remaining tower site, and we are on schedule to complete site preparation work at this site by the end of next quarter. | 99 | Equipment procurement is complete for our core network network tower sites. As part of our our network enhancement strategy, we are procuring additional licensed microwave radios and antennas to ensure that network performance is aligned with anticipated customer demand. | 99 | Site acquisition is complete for our core network datacenters, fiber access points, and core tower sites. We currently exploring options and conducting cost/benefit analysis for increasing the quantity of fiber access points at strategic areas of our core network. | 96 | Network equipment installation and path alignment activities are complete at 91 out of 92 core network tower sites. These activities are expected to be completed at our last remaining tower site by the end of next quarter. | 96 | Network testing is complete at 91 out of 92 core network tower sites. This activity is expected to be completed at our last remaining tower site by the end of next quarter. | 2012-11-19 10:31 | 2012-11-19 10:31 | 7368 | 7368 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2012 | Q4 | Q4 - 2012 | 9071 | 7846 | TRUE | 95 | With our total expenditures plus allowable in kind contributions for recipient match, overall project completion is at 95.4% for this reporting period. Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. Please see Section 3 below for more details. | 100 | In-Kind Contributions for Recipient Match | We continued to book contributed in kind assets through this past quarter to maintain proportionality with federal expenditures as required, and we are continuing to incorporate these assets into our roll-out schedule as lateral extensions of our core network to reach our target customers and connecting Community Anchor Institutions. | 0 | N/A. Categorically exempt from Environmental Assessment. | 98 | Core network design is functionally complete. We continued to implement our network design enhancement plan this past quarter to address pre-transition network design performance and capacity limitations that we identified through our comprehensive design review that we conducted in previous quarters to ensure that our network will accommodate projected demand. This enhancement plan also includes additional link design and engineering as required to integrate our new Fiber Access Point into the core network and to build out our in kind tower assets as lateral extensions of our core network to reach our target customers and connecting Community Anchor Institutions. | 0 | N/A | 100 | Core network permitting is complete. | 100 | Core network site preparation work is complete. | 100 | Core network equipment procurement is complete. We are continuing to procure additional licensed microwave radios and antennas as necessary to ensure that network performance and capacity requirements are aligned with forecasted customer demand. | 100 | Site acquisition is complete for our core network fiber access points and tower sites. As part of our network enhancement plan, we are continuing to explore options for increasing the quantity of fiber access points at strategic areas of our core network. | 98 | Network equipment installation and path alignment activities are complete at all core network sites. As part of our network enhancement plan, we are continuing to install additional licensed microwave radios and antennas at key wireless links to ensure that network performance and capacity requirements are aligned with forecasted customer demand. | 98 | Network testing is in the final stages at the core network tower sites . Testing activities will continue as additional links are brought online to integrate our new Fiber Access Point and our in-kind towers. | 2013-02-28 13:09 | 2013-02-28 13:09 | 7368 | 7368 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2013 | Q1 | Q1 - 2013 | 9747 | 8408 | TRUE | 99 | With our total expenditures plus allowable in kind contributions for recipient match, overall project completion is at 98.64% for this reporting period. As noted above, we received approval this past quarter for an Award Action Request to extend our grant period to September 30, 2013. Milestone percent complete quantities reported for this quarter may therefore vary from our original baseline plan projections, as these were based on percent complete estimates that anticipated the original January 31, 2013 project completion date. | 100 | In-Kind Contributions for Recipient Match | We continued to book contributed in kind assets through this past quarter to maintain proportionality with federal expenditures as required, and we are continuing to incorporate these assets into our roll-out schedule as lateral extensions of our core network to reach our target customers and to connect Community Anchor Institutions. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | Core network design is functionally complete. We continued to implement our network design enhancement plan this past quarter, which included design activities associated with integrating our new fiber access point in Palatka into the core network. | 0 | N/A | 100 | Core network permitting is complete. We applied for additional permits this quarter for the build-out of our new Fiber Access Point in Palatka (Putnam County), which includes the provisioning of an associated fiber connection to a communications tower in nearby San Mateo. | 100 | Core network site preparation work is complete. We performed additional site preparation this past quarter for the build-out of our new Fiber Access Point in Palatka. | 100 | Core network equipment procurement is complete. As we extend the core network out to reach customers and community anchor institutions, we are continuing to procure additional licensed microwave radios and antennas as necessary to ensure that network performance and capacity requirements are aligned with forecasted customer demand. | 100 | Site acquisition is complete for our core network fiber access points and tower sites. We also completed site acquisition activities this quarter for the build-out of our new Fiber Access Point in Palatka and its associated communications tower in nearby San Mateo. | 98 | Network equipment installation and path alignment activities continued this quarter for the build-out of our new Fiber Access Point in Palatka. | 98 | Network testing activities continued this quarter for the build-out of our new Fiber Access Point in Palatka. | 2013-05-15 16:39 | 2013-05-15 16:39 | 7368 | 7368 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2013 | Q2 | Q2 - 2013 | 12011 | 10176 | TRUE | 99 | With our total federal expenditures plus allowable in-kind contributions for recipient match, overall project completion is at 99.9% for this reporting period. | 100 | In-Kind Contributions for Recipient Match | We continued to book contributed in kind assets through this past quarter to maintain proportionality with federal expenditures as required, and we continued to incorporate these assets into our roll-out schedule as lateral extensions of our core network to reach target customers and to enable connectivity to community anchor institutions. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | Core network design is functionally complete. We also successfully implemented our network design enhancement plan to ensure network capacity for anticipated customer demand. | 0 | N/A | 100 | Core network permitting is complete, and we obtained the necessary permits for the build-out of our new Fiber Access Point in Palatka (Putnam County). | 100 | Core network site preparation work is complete. We completed site prep activities this past quarter for the build-out of our new Fiber Access Point in Putnam County and for the build-out our in-kind tower infrastructure in Hamilton, Lafayette, Putnam, and Levy counties. | 100 | Core network equipment procurement is complete. We continued to procure additional licensed microwave radios and antennas for the ongoing build-out our in-kind tower infrastructure. | 100 | Site acquisition is complete for our core network fiber access points and tower sites, and we successfully negotiated an Indefeasible Right of Use for upstream bandwidth to increase our network capacity in order to serve more customers in the eastern portion of our network footprint. | 99 | Network equipment installation and path alignment activities continued this quarter for the build-out of our in-kind tower infrastructure. | 99 | Network testing activities continued this quarter for the build-out of our in-kind tower infrastructure. | 2014-03-31 22:13 | 2014-03-31 22:13 | 6524 | 6524 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2013 | Q3 | Q3 - 2013 | 11445 | 9564 | TRUE | 100 | The project is 100% complete, as determined by total federal expenditures plus allowable in-kind contributions for recipient match. | 100 | In-Kind Contributions for Recipient Match | We continued to book contributed in kind assets through this past quarter to maintain proportionality with federal expenditures as required, and we continued to incorporate these assets into our roll-out schedule as lateral extensions of our core network to reach target customers and to enable connectivity to community anchor institutions. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | Core network design is functionally complete, and we successfully implemented our design enhancement plan to complete the network engineering design and to increase network capacity for anticipated customer demand. | 0 | N/A | 100 | Core network permitting is complete. | 100 | Core network site preparation work is complete. | 100 | Core network equipment procurement is complete, and we continued to procure additional licensed microwave radios and antennas for the ongoing build-out our in-kind tower infrastructure. | 100 | Site acquisition is complete for our core network fiber access points and tower sites. | 100 | Core network equipment deployment is complete. Equipment installation and path alignment activities continued this quarter for the build-out of our in-kind tower infrastructure. | 100 | Core network equipment testing is complete. Network testing activities continued this quarter for the build-out of our in-kind tower infrastructure. | 2013-12-06 14:31 | 2013-12-06 14:31 | 6524 | 6524 | North Florida Broadband Authority | TRUE
NT10BIX5570024 | 2010 | Q2 | Q2 - 2010 | 48 | 1330 | FALSE | 12 |  | 0 |  |  | 100 |  | 100 |  | 40 |  | 40 |  | 20 |  | 30 |  | 10 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570024 | 2010 | Q3 | Q3 - 2010 | 333 | 1433 | TRUE | 27 | The U of U/UEN project overall remains on schedule. Completing the Environmental Assessment and Telecommunications Provider contracts remain our top priority. The U of U/UEN, with the assistance of NTIA and BTOP representatives, is on schedule to complete these two activities in the fourth quarter. We are planning to launch the implementation phase of the project beginning quarter one of project year two. | 0 |  | N/A | 90 | Per the NTIA's recommendation, the U of U/UEN needs additional review on all designs by the State Historic Preservation Office and the Army Corps of Engineers. This consultation and work is currently underway. This milestone is on schedule for completion in the fourth quarter. | 95 | Telecommunication Partner's and internal designs are complete. The U of U/UEN has been meeting with Anchor Institutions on the review and their final approval of the network designs. This milestone is on schedule for completion in the fourth quarter. | 0 | The Right of Way process will begin when the Environmental Assessment is approved and all vendor contracts are signed. The U of U/UEN anticipates approval of the Environmental Assessment in the fourth quarter allowing Telecommunication Partners to submit requests for Rights of Way. This milestone is on schedule to begin in the first quarter of project year two. | 0 | The Construction Permit process will begin when the Environmental Assessment is approved and vendor contracts are signed. The U of U/UEN anticipates approval of the Environmental Assessment in the fourth quarter allowing Telecommunication Partners to submit requests for construction permits. This milestone is on schedule to begin in the first quarter of project year two. | 0 | Site Preparations will begin when the Environmental Assessment is approved and vendor contracts are signed. The U of U/UEN anticipates approval of the Environmental Assessment in the fourth quarter allowing the site survey and site improvement process to commence. This milestone is on schedule to begin in the first quarter of project year two. | 0 | Equipment Procurement will begin when the Environmental Assessment is approved and vendor contracts are signed. The U of U/UEN anticipates approval of the Environmental Assessment in the fourth quarter allowing equipment procurement to commence. This milestone is on schedule to begin in the first quarter of project year two. | 0 | Network Build out will begin when the Environmental Assessment is approved and vendor contracts are signed. The U of U/UEN anticipates approval of the Environmental Assessment in the fourth quarter allowing Telecommunication Partners to begin network build out. This milestone is on schedule to begin in the first quarter of project year two. | 0 | Equipment Deployment will begin when the Environmental Assessment is approved and vendor contracts are signed. The U of U /UEN anticipates approval of the Environmental Assessment in the fourth quarter allowing Telecommunications Partners to begin shipping equipment. This milestone is on schedule to begin in the first quarter of project year two. | 0 | Network Testing will begin as the Network Build and Equipment Deployment is proceeding. These two milestones are pending the approval of the Environmental Assessment. The U of U/UEN anticipates approval of the Environmental Assessment in the fourth quarter. Network Testing is on schedule to begin in the first quarter of project year two. | 2010-11-17 11:08 | 2010-11-17 11:08 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2010 | Q4 | Q4 - 2010 | 1051 | 2090 | TRUE | 36 | The U of U/UEN BTOP project overall is on schedule. Working in cooperation with our Federal Program Officer, the U of U/UEN has been able to complete all grant requirements needed to move into the implementation phase of the project.There are three reasons the U of U/UEN has expended only 1 % of the funds, yet overall project is 36% complete. First, The U of U/UEN reimburses their sub recipient after the Community Anchor Institutions (CAI) installation and turn up is complete. The design work is 85% complete, but the U of U/UEN has not been billed by their sub recipient. Secondly, the U of U/UEN has not processed personnel expenditures because they are waiting for a letter from our Grants Office stating the disallowance of F&A expenditures to the U of U/UEN when the grant was accepted. We are currently working with our Federal Program Officer to get this letter. The Third reason is that through the competitive bidding process we have received prices than originally budgeted. | 0 |  | N/A | 100 | The NTIA approved the U of U/UEN Environmental Assessment and issued a FONSI in November of 2010. | 85 | This milestone is behind schedule and was projected to be completed by the end of the fourth quarter of project year one. The U of U/UEN is pending signatures on seven Telecommunications Partner contracts. These remaining contracts constitute 15 percent of the total project effort. These remaining contracts are in review and expected to be completed within the month of January. Although the Network Design work is 85% complete, billing for this portion of the project will not occur until the Community Anchor Institution (CAI) installations and turn ups are complete. | 0 | This milestone is on schedule and will begin the first quarter of project year two. | 0 | This milestone is on schedule and will begin the first quarter of project year two. | 0 | This milestone is on schedule and will begin the first quarter of project year two. | 0 | This milestone is on schedule and will begin the first quarter of project year two. | 0 | This milestone is on schedule and will begin the first quarter of project year two. | 0 | This milestone is on schedule and will begin the first quarter of project year two. | 0 | This milestone is on schedule and will begin the first quarter of project year two. | 2011-02-10 14:47 | 2011-02-10 14:47 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2011 | Q1 | Q1 - 2011 | 2073 | 2782 | TRUE | 2 | The overall percentage of completion for the U of U/UEN BTOP project is behind schedule due to multiple reasons. Although significant project progress has been made the amount of funds spent to date is less than projected in the Baseline Report. The higher cost project activities, such as those associated with outside plant construction, is behind schedule which is reflected in the number of CAIs turned up to date. The U of U/UEN is expecting this rate of installation and turn up to increase significantly in the upcoming quarters. Additionally, the U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow the completion of project construction activities and the invoicing of work completed by sub recipients. The U of U/UEN experienced some delays in the turn up of CAIs during this quarter which was due in part to obstacles and subsequent delays encountered during the review and approval | 0 |  | N/A | 100 | The NTIA approved the U of U/UEN Environmental Assessment and issued a Finding Of No Significant Impact (FONSI) in November of 2010. | 100 | All network designs and contracts with Telecommunications Partners have been completed. | 20 | This milestone is on schedule. The U of U/UEN has over twenty six (26) active CAI construction projects underway with Rights of Way and Permits in hand. These projects in addition to the nine (9) completed in the first quarter and those completed so far in the second quarter exceed the total of forty (40) CAIs, which is the accumulative second quarter projected milestone for this task. | 20 | This milestone is on schedule. The U of U/UEN has over twenty six (26) active CAI construction projects underway with Rights of Way and Permits in hand. These projects in addition to the nine (9) completed in the first quarter and those completed so far in the second quarter exceed the total of forty (40) CAIs, which is the accumulative second quarter projected milestone for this task. | 2 | This milestone is behind schedule. Although significant project progress has been made the amount of funds spent to date is less than projected in the Baseline Report. The higher cost project activities, such as those associated with outside plant construction, is behind schedule which is reflected in the number of CAIs turned up to date. | 17 | This milestone is on schedule. The U of U/UEN has over twenty six (26) active CAI construction projects underway and has ordered, received and inventoried the needed hardware to complete these installs. | 2 | The U of U/UEN is behind schedule on this milestone. Although significant project progress has been made the amount of funds spent to date is less than projected in the Baseline Report. The higher cost project activities, such as those associated with outside plant construction, is behind schedule which is reflected in the number of CAIs turned up to date. | 2 | The U of U/UEN is behind schedule on this milestone. Although significant project progress has been made the amount of funds spent to date is less than projected in the Baseline Report. The higher cost project activities, such as those associated with outside plant construction, is behind schedule which is reflected in the number of CAIs turned up to date. | 2 | The U of U/UEN is behind schedule on this milestone. Although significant project progress has been made the amount of funds spent to date is less than projected in the Baseline Report. The higher cost project activities, such as those associated with outside plant construction, is behind schedule which is reflected in the number of CAIs turned up to date. | 2011-05-17 10:15 | 2011-05-17 10:15 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2011 | Q2 | Q2 - 2011 | 3299 | 3412 | TRUE | 8 | The overall percentage of completion for the U of U/UEN BTOP project is behind schedule which is due primarily to billing and invoicing processes. Although significant project progress has been made the federal funds expended is less than projected in the Baseline Report. The U of U/UEN billing policy does not require prepayment by sub recipients for work performed. As such, the draw down of Federal Funds is delayed and will follow the completion of construction and network build out activities. | 0 |  | N/A | 100 | The NTIA approved the U of U/UEN Environmental Assessment and issued a Finding of No Significant Impact (FONSI) in November 2010. | 100 | All network designs and contracts with Telecommunications Partners have been completed. | 40 | This milestone is on schedule. The U of U/UEN has over fifteen (15) CAI construction projects underway with Rights of Way and Permits in hand. These projects in addition to the forty four (44) CAI already completed exceed the projections in the Baseline Report. | 40 | This milestone is on schedule. The U of U/UEN has over fifteen (15) CAI construction projects underway with Rights of Way and Permits in hand. These projects in addition to the forty four (44) CAI already completed exceed the projections in the Baseline Report. | 8 | This milestone is behind schedule. Although significant project progress has been made the amount of funds spent to date is less than projected in the Baseline Report. This is due to the fact that most of the higher cost projects with larger outside plant construction requirements will not be started until the third quarter of 2011 and that the draw down of Federal Funds doesn't occur until we are invoiced for completed work. | 34 | This milestone is on schedule. The U of U/UEN has over fifteen (15) active CAI construction projects underway in addition to the forty four (44) already completed and has ordered, received and inventoried the needed hardware to complete these installations. | 8 | This milestone is behind schedule. Although significant project progress has been made the amount of funds spent to date is less than projected in the Baseline Report. This is due to the fact that most of the higher cost projects with larger outside plant construction requirements will not be started until the third quarter of 2011 and that the draw down of Federal Funds doesn't occur until we are invoiced for completed work. | 8 | This milestone is behind schedule. Although significant project progress has been made the amount of funds spent to date is less than projected in the Baseline Report. This is due to the fact that most of the higher cost projects with larger outside plant construction requirements will not be started until the third quarter of 2011 and that the draw down of Federal Funds doesn't occur until we are invoiced for completed work. | 8 | This milestone is behind schedule. Although significant project progress has been made the amount of funds spent to date is less than projected in the Baseline Report. This is due to the fact that most of the higher cost projects with larger outside plant construction requirements will not be started until the third quarter of 2011 and that the draw down of Federal Funds doesn't occur until we are invoiced for completed work. | 2011-08-24 17:52 | 2011-08-24 17:52 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2011 | Q3 | Q3 - 2011 | 4151 | 3924 | TRUE | 14 | The overall percentage of completion for the U of U/UEN BTOP project is behind schedule which is due primarily to billing and invoicing processes. Although project build out and implementation is on schedule the federal funds expended is less than projected in the Baseline Report. The U of U/UEN billing process does not require prepayment by sub recipients for work performed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 0 |  | N/A | 100 | The NTIA approved the U of U/UEN Environmental Assessment and issued a Finding of No Significant Impact (FONSI) in November 2010. | 100 | All network designs and contracts with Telecommunications Partners have been completed. | 60 | This milestone is on schedule. The U of U/UEN has over 20 (twenty) CAI construction projects underway with Rights of Way and Permits in hand. These projects in addition to the 65 (sixty five) already completed exceed the projections in the Baseline Report. | 60 | This milestone is on schedule. The U of U/UEN has over 20 (twenty) CAI construction projects underway with Rights of Way and Permits in hand. These projects in addition to the 65 (sixty five) already completed exceed the projections in the Baseline Report. | 14 | This milestone is behind schedule. Although significant project progress has been made the amount of funds spent to date is less than projected in the Baseline Report. This is due primarily to billing procedures that delay the draw down of federal funds until the U of U/UEN is invoiced for work completed. Additionally, the U of U/UEN has not yet been invoiced for the larger builds in the project and expects this to happen before the end of the year. | 51 | This milestone is on schedule. The U of U/UEN has over fifteen (15) active CAI construction projects underway in addition to the sixty five (65) already completed and has ordered, received and inventoried the needed hardware to complete these installations. | 14 | This milestone is behind schedule. Although significant project progress has been made the amount of funds spent to date is less than projected in the Baseline Report. This is due primarily to billing procedures that delay the draw down of federal funds until the U of U/UEN is invoiced for work completed. Additionally, the U of U/UEN has not yet been invoiced for the larger builds in the project and expects this to happen before the end of the year. | 14 | This milestone is behind schedule. Although significant project progress has been made the amount of funds spent to date is less than projected in the Baseline Report. This is due primarily to billing procedures that delay the draw down of federal funds until the U of U/UEN is invoiced for work completed. Additionally, the U of U/UEN has not yet been invoiced for the larger builds in the project and expects this to happen before the end of the year. | 14 | This milestone is behind schedule. Although significant project progress has been made the amount of funds spent to date is less than projected in the Baseline Report. This is due primarily to billing procedures that delay the draw down of federal funds until the U of U/UEN is invoiced for work completed. Additionally, the U of U/UEN has not yet been invoiced for the larger builds in the project and expects this to happen before the end of the year. | 2011-11-18 17:35 | 2011-11-18 17:35 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2011 | Q4 | Q4 - 2011 | 4949 | 4628 | TRUE | 28 | The overall percentage of completion for the U of U/UEN BTOP project is behind schedule. This is primarily due to billing and invoicing processes. Although project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow pre-payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 0 | N/A | N/A | 100 | The NTIA approved the U of U/UEN Environmental Assessment and issued a Finding of No Significant Impacct (FONSI) in November of 2010. | 100 | All network designs and contracts with Telecommunication Partners have been completed. | 82 | This milestone is on schedule. The U of U/UEN has over twenty (20) CAI construction projects underway with Rights of Way and Permits in hand. These projects in addition to the ninety-five (95) already completed exceed the projections in the Baseline Report. | 82 | This milestone is on schedule. The U of U/UEN has over twenty (20) CAI construction projects underway with Rights of Way and Permits in hand. These projects in addition to the ninety-five (95) already completed exceed the projections in the Baseline Report. | 28 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not allow pre-payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 90 | This milestone is on schedule. The U of U/UEN has ordered, received and inventoried nearly all equipment for the140 CAIs and the fiber for the Salt Lake and Logan Middle Mile segments. The U of U/UEN has received partial shipment of the Optronics for the middle mile projects and is expecting to receive the remaining components by the end of the quarter, which will complete this activity for the project. Invoicing for some equipment is pending the shipment of these final components. | 28 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not allow pre-payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 28 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not allow pre-payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 28 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not allow pre-payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 2012-02-10 16:38 | 2012-02-10 16:38 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2012 | Q1 | Q1 - 2012 | 6331 | 5768 | TRUE | 41 | The overall percentage of completion for the U of U/UEN project is behind schedule. This is due to billing and invoicing processes. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 0 | N/A | N/A | 100 | The NTIA approved the U of U/UEN Environmental Assessment and issued a Finding of Non Significant Impact (FONSI) in November of 2010. | 100 | All network designs and contracts with Telecommunication Partners have been completed. | 100 | All Rights of Way for this project have been approved and build out is underway. | 100 | All Construction Permits have been granted and build out is underway. | 41 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 90 | This milestone is on schedule. The U of U/UEN has ordered, received and inventoried all end site equipment needed to complete connectivity to the one hundred forty (140) CAIs and the fiber and Optronics needed to complete the Salt Lake Middle Mile segment. The only outstanding equipment order is the Optronics for the Logan Middle Mile segment. | 41 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 41 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 41 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 2012-05-29 16:00 | 2012-05-29 16:00 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2012 | Q2 | Q2 - 2012 | 6905 | 6079 | TRUE | 48 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 0 |  | N/A | 100 | The NTIA approved the U of U/UEN Environmental Assessment and issued a Finding of No Significant Impact (FONSI) in November of 2010. | 100 | All network designs and contracts with Telecommunication Providers have been completed. | 100 | All Rights of Way for this project have been approved and build out is underway. | 100 | All Construction Permits have been granted and build out is underway. | 48 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 90 | This milestone is behind schedule. A Re-budget Request submitted by the U of U/UEN this past April was approved by the NTIA in May and included one additional Optical Amplifier the for Logan Middle Mile segment and one hundred (100) gigabit optics for connecting the Salt Lake Middle Mile segment to the Internet 2 National Backbone. The U of U/UEN is expecting to take delivery of this equipment in the third (3rd) quarter completing all equipment procurement. | 48 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 48 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 48 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 2012-08-07 16:40 | 2012-08-07 16:40 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2012 | Q3 | Q3 - 2012 | 7329 | 6294 | TRUE | 56 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 0 | N/A | N/A | 100 | The NTIA approved the U of U/UEN Environmental Assessment and issued a Finding of No Significant Impact (FONSI) in November of 2010. | 100 | All network designs and contracts with Telecommunication Providers have been completed. | 100 | All Rights of Way for this project have been approved and build out is underway. | 100 | All Construction Permits have been granted and build out is underway. | 56 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 90 | This milestone is behind schedule. A Re-budget Request submitted by the U of U/UEN this past April was approved by the NTIA in May and included one additional Optical Amplifier the for Logan Middle Mile segment and one hundred (100) gigabit optics for connecting the Salt Lake Middle Mile segment to the Internet 2 National Backbone. The U of U/UEN is expecting to take delivery of this equipment in the fourth (4th) quarter completing all equipment procurement. | 56 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 56 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 56 | This milestone is behind schedule. Although project implementation is on schedule the amount of funds spent to date is less than projected. The U of U/UEN billing process does not permit payment to sub-recipients until work is completed. For this reason the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 2012-10-12 15:30 | 2012-10-12 15:30 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2012 | Q4 | Q4 - 2012 | 8655 | 7481 | TRUE | 58 | This milestone is behind schedule. Although project implementation is near completion the amount of federal funds spent to date is less than the completed network build out indicates. The U of U/UEN billing process does not permit pre-payment and invoicing by sub-recipients is not made until all work is completed. For this reason the draw down of federal funds is delayed and follows behind the completion of construction and network build out activities. | 0 | 0 | N/A | 100 | The NTIA approved the U of U/UEN Environmental Assessment and issued a Finding of No Significant Impact (FONSI) in November of 2010. | 100 | All network designs and contracts with Telecommunication Providers have been completed. | 100 | All Rights of Way for this project have been approved and build out is underway. | 100 | All Construction Permits have been granted and build out is underway. | 58 | This milestone is behind schedule. Although project implementation is near completion the amount of federal funds spent to date is less than the completed network build out indicates. The U of U/UEN billing process does not permit pre-payment and invoicing by sub-recipients is not made until all work is completed. For this reason the draw down of federal funds is delayed and follows behind the completion of construction and network build out activities. | 100 | All equipment procurement for this project is completed. | 58 | This milestone is behind schedule. Although project implementation is near completion the amount of federal funds spent to date is less than the completed network build out indicates. The U of U/UEN billing process does not permit pre-payment and invoicing by sub-recipients is not made until all work is completed. For this reason the draw down of federal funds is delayed and follows behind the completion of construction and network build out activities. | 58 | This milestone is behind schedule. Although project implementation is near completion the amount of federal funds spent to date is less than the completed network build out indicates. The U of U/UEN billing process does not permit pre-payment and invoicing by sub-recipients is not made until all work is completed. For this reason the draw down of federal funds is delayed and follows behind the completion of construction and network build out activities. | 58 | This milestone is behind schedule. Although project implementation is near completion the amount of federal funds spent to date is less than the completed network build out indicates. The U of U/UEN billing process does not permit pre-payment and invoicing by sub-recipients is not made until all work is completed. For this reason the draw down of federal funds is delayed and follows behind the completion of construction and network build out activities. | 2013-02-06 18:01 | 2013-02-06 18:01 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2013 | Q1 | Q1 - 2013 | 10033 | 8567 | TRUE | 66 | This milestone is behind schedule. Although project implementation is near completion the amount of federal funds spent to date is less than the completed network build out indicates. The U of U/UEN billing process does not permit pre-payment and invoicing by sub-recipients is not made until all work is completed. For this reason the draw down of federal funds is delayed and follows behind the completion of construction and network build out activities. | 0 | N/A | N/A | 100 | The NTIA approved the U of U/UEN Environmental Assessment and issued a Finding of No Significant Impact (FONSI) in November of 2010. | 100 | All network designs and contracts with Telecommunication Providers have been completed. | 100 | All Rights of Way for this project have been approved and build out is underway. | 100 | All Construction Permits have been granted and build out is underway. | 66 | This milestone is behind schedule. Although project implementation is near completion the amount of federal funds spent to date is less than the completed network build out indicates. The U of U/UEN billing process does not permit pre-payment and invoicing by sub-recipients is not made until all work is completed. For this reason the draw down of federal funds is delayed and follows behind the completion of construction and network build out activities. | 100 | All equipment procurement for this project is completed. | 66 | This milestone is behind schedule. Although project implementation is near completion the amount of federal funds spent to date is less than the completed network build out indicates. The U of U/UEN billing process does not permit pre-payment and invoicing by sub-recipients is not made until all work is completed. For this reason the draw down of federal funds is delayed and follows behind the completion of construction and network build out activities. | 66 | This milestone is behind schedule. Although project implementation is near completion the amount of federal funds spent to date is less than the completed network build out indicates. The U of U/UEN billing process does not permit pre-payment and invoicing by sub-recipients is not made until all work is completed. For this reason the draw down of federal funds is delayed and follows behind the completion of construction and network build out activities. | 66 | This milestone is behind schedule. Although project implementation is near completion the amount of federal funds spent to date is less than the completed network build out indicates. The U of U/UEN billing process does not permit pre-payment and invoicing by sub-recipients is not made until all work is completed. For this reason the draw down of federal funds is delayed and follows behind the completion of construction and network build out activities. | 2013-05-31 15:46 | 2013-05-31 15:46 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2013 | Q2 | Q2 - 2013 | 12233 | 10405 | TRUE | 100 | The U of U/UEN completed Utah's Broadband Technologies Opportunity Program project, Utah Anchors: A Community Broadband Project on May 31st, 2013. This percentage for overall completion represents actual expenditures. | 0 | N/A | N/A | 100 | The NTIA approved the U of U/UEN Environmental Assessment and issued a Finding of No Significant Impact (FONSI) in November of 2010. | 100 | All network designs and contracts with Telecommunication Providers have been completed. | 100 | All Rights of Way for this project have been approved and build out is underway. | 100 | All Construction Permits have been granted and build out is completed. | 100 | All Site Preparations for the project are completed. | 100 | All equipment procurement for this project is completed. | 100 | The Network Build Out for the project is completed. | 100 | All project equipment and hardware for the project is installed and in operation. | 100 | All Network Testing was successfully completed prior to production implementation. | 2014-05-23 16:31 | 2014-05-23 16:31 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570025 | 2010 | Q2 | Q2 - 2010 | 49 | 1286 | FALSE | 68 |  |  |  |  | 100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | 2010 | Q3 | Q3 - 2010 | 335 | 1434 | TRUE | 1 | Draft Environmental Assessment is done | 0 |  | N/A | 100 | Draft Environmental Assessment submitted 9/28/10 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-17 12:17 | 2010-11-17 12:17 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | 2010 | Q4 | Q4 - 2010 | 1135 | 2174 | TRUE | 3 | N/A | 0 |  | N/A | 100 | N/A | 35 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Zayo is still in the network design phase and we are not at a point where we need to buy equipment yet. | 0 | N/A | 0 | We have not bought any equipment yet to deploy. | 0 | N/A | 2011-02-14 15:50 | 2011-02-14 15:50 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | 2011 | Q1 | Q1 - 2011 | 1899 | 2695 | TRUE | 5 | This is behind our baseline because of delays in permitting and ordering materials. Even though we are ahead overall on permitting, we cannot build a segment until we have all of the permits for a segment. | 0 |  | N/A | 100 | This is in line with our baseline. | 85 | Zayo is ahead of our baseline on this. This is because Zayo has hired 3 Engineering Firms and they are moving very quickly. | 40 | Zayo is ahead of our baseline on this because we combined this with our engineering. | 20 | Zayo is ahead of our baseline on this because we combined this with our engineering. | 0 | Zayo is behind on this because this ties into engineering and selecting the required sites. Now that Zayo is getting permits, this will take place next quarter. | 2 | Zayo has started purchasing fiber. This was already competitively bid and awarded. Zayo has started ordering. We are behind from our baseline because we are just now awarding our contract for other required materials. | 0 | N/A | 0 | Zayo is behind because of the delay in awarding the materials contract sited in 2g above. | 0 | N/A | 2011-05-05 20:35 | 2011-05-05 20:35 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | 2011 | Q2 | Q2 - 2011 | 3399 | 3463 | TRUE | 15 | This is 13% behind our submitted baseline. A big part of the reason for this is because of costs savings from competitively bidding out the project. | 0 |  | N/A | 100 | Zayo is on track here because we have our FONSI. We may have more EA work required as we submit site changes requested by our customer. | 85 | Zayo is 5% ahead of our baseline on this. This is because we awarded this work to more than one contractor. This allowed us to step up our schedule. | 55 | Zayo is 55% ahead of our baseline on this. This is because we have been very aggressive with our Engineering and applying for our ROW's and lucky in getting a quick turnaround on some of our permits. Zayo has done some reroutes because of changes requested by our customer. | 55 | Zayo is 55% ahead of our baseline on this. This is because of a quick turnaround with some of our permitting agencies. | 20 | Zayo is 80% behind on our baseline on this. This is because we just secured a consultant to help us with site acquisition and hut placement. We were delayed because of reroutes and site changes requested by our customer as outlined above. Zayo plans to be back on target by the end of next quarter. | 15 | Zayo is 65% behind on this. This is because we just sent out our RFP for most of our route construction. Zayo has a warehouse and has been procuring materials, but we have not been moving to aggressively here because we are waiting to start construction so that materials are moving. | 10 | Zayo is right on target here. We have started construction on one segment and we have about 65 miles of our 645 miles built so far. | 10 | Zayo is 80% behind here from our baseline. This is because of our delay in starting building. As you can see, this number matches up with our network build percentage above. | 0 | This is right in line with our baseline. | 2011-08-31 16:58 | 2011-08-31 16:58 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | 2011 | Q3 | Q3 - 2011 | 4195 | 3946 | TRUE | 26 | This is 42% under from our baseline. This is because of delays Zayo had encountered in our permitting phase. Zayo has run into excessive pole change out costs and is looking at dipping underground in areas where there is a large quantity of poles to avoid these costs. Zayo is also currently under budget compared to our baseline. While we are financially at 26% of our baseline budget, in actual completion of our project, we are at about 45% completion. | 0 |  | This is in line with our baseline. | 100 | This is on target with our baseline. | 100 | This is on target with our baseline. | 60 | This is on target with our baseline. | 80 | This is 29% above our baseline. This is because we have made headway with our network design. | 26 | This is 74% behind our baseline. This is because of delays in finding the appropriate hut sites. Zayo has hired a consultant to help with this. | 0 | Zayo is 100% behind on this because of our delays in getting our huts. We should be caught up in 2 quarters. We need to procure our huts, set them up and put the electronics in them. | 21 | Zayo is 49% behind our baseline on this because of our permitting delays as discussed above in 2a. | 0 | Zayo is behind on this because of the delays in getting our huts and in securing our equipment. We will be caught up in 2 quarters as discussed in 2g. | 0 | This is in line with our baseline. | 2011-11-21 17:00 | 2011-11-21 17:00 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570026 | 2010 | Q2 | Q2 - 2010 | 50 | 1267 | FALSE | 6 |  | 0 |  |  | 100 |  | 50 |  | 50 |  | 15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2010 | Q3 | Q3 - 2010 | 341 | 1437 | TRUE | 5 | . | 0 |  | . | 100 | . | 25 | Due to issues with our current contractor's ability to secure a performance bond, KINBER has started the RFP process to obtain a new contractor (s) to design and build the network. | 0 | Due to issues with our current contractor's ability to secure a performance bond, KINBER has started the RFP process to obtain a new contractor (s) to design and build the network. | 0 | Due to issues with our current contractor's ability to secure a performance bond, KINBER has started the RFP process to obtain a new contractor (s) to design and build the network. | 0 | . | 0 | . | 0 | . | 0 | . | 0 | . | 2010-11-17 13:22 | 2010-11-17 13:22 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2010 | Q4 | Q4 - 2010 | 1303 | 2332 | TRUE | 5 | Due to having to complete the RFP process and change construction vendors, the project is slightly behind originally anticipated progress. | 0 |  | n/a | 100 | EA is complete. FONSI received. | 25 | Due to having to complete the RFP process and change construction vendors, the project is slightly behind originally anticipated progress. | 0 | Due to having to complete the RFP process and change construction vendors, the project is slightly behind originally anticipated progress. | 0 | Due to having to complete the RFP process and change construction vendors, the project is slightly behind originally anticipated progress. | 0 | . | 0 | . | 0 | . | 0 | . | 0 | . | 2011-02-22 15:28 | 2011-02-22 15:28 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2011 | Q1 | Q1 - 2011 | 1943 | 2717 | TRUE | 1 | Construction work has begun, the project is slightly behind the baseline schedule due to a change in construction vendors in 2010. Some construction has begun, however as of the end of the quarter, KINBER had not yet received any invoices. | 0 | n/a | n/a | 100 | EA complete FONSI received, $19,250 in construction related expenses were reported to pay for the EA | 0 | Much of the design has been completed however we have not been invoiced for this work and therefore haven't had any expenditures by 3/31/11. It is projected that all design work will be completed in Q2 2011. | 0 | 23% is actually complete, representing 400 miles of overlash fiber, however we have not been invoiced for this and did not drawndown any federal funds in Q1 2011. | 0 | Due to the reissuing of a construction RFP, the project is slightly behind the originally projected progress. Some pole permits have been submitted and await approval. No funds have been invoiced. | 0 | Due to the reissuing of a construction RFP, the project is slighlty behind the originally projected progress. No funds have been invoiced. | 0 | RFP for equipment was prepared and will be released Q2 2011. | 0 | Project is on schedule. | 0 | Project is on schedule. | 0 | Project is on schedule. | 2011-05-11 13:25 | 2011-05-11 13:25 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2011 | Q2 | Q2 - 2011 | 3075 | 3295 | TRUE | 22 | The project is slightly behind schedule due to changing the construction vendor (3-6 month time loss) and the required submission of a revised environmental assessment due to route changes. It is expected that the project will be back on schedule in 11Q4. | 100 | Fiber procurement | KINBER has received 1,030 miles of fiber and has dedicated factory time and delivery dates for the remaining fiber necessary to construct the PennREN project. | 100 | FONSI was received on initial EA submission. Due to vendor and slight route changes, a revised EA was submitted and is awaiting approval. (See #3 below) | 80 | 80% of the pole and conduit application have been submitted. This milestone is slightly behind schedule due to the lengthy approval process necessary to finalize the design and the need to submit a revised EA for areas of the network that had to be altered. It is anticipated that this milestone will be complete in 11Q3. | 23 | The ROW for 400 miles of fiber overlash have been approved. 295 additional ROW requests have been submitted. This milestone is behind projections due to the lengthy process to receive approvals. Currently there are three dedicated ROW agents working full-time on rights of way permitting and related issues. | 40 | 80% of all make ready requests have been submitted and await approvals. Although KINBER has no control over the approval process, it is anticipated that this milestone will catch up to projects in 11Q4. | 0 | This milestone is behind due to the lag in construction realized with changing vendors in December 2010. Site preparation activities will begin in Q3, 2011. | 0 | RFP for equipment and related professional services was released in Q2 2011. Selection will be made in Q3, 2011 | 0 | Project is on schedule. | 0 | Project is on schedule. | 0 | Project is on schedule. | 2011-08-15 10:53 | 2011-08-15 10:53 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2011 | Q3 | Q3 - 2011 | 4047 | 3866 | TRUE | 27 | Project is slightly behind due to changing construction vendors in Q4,2010 as well as weather related delays in Q3, 2011. | 100 | Fiber procurement | KINBER has received 1,030 miles of NZD fiber and has secured dedicated factory time for the production of the remaining fiber necessary to construct the PennREN project. | 100 | Project is on Schedule | 100 | Project is on schedule | 36 | 102 of the 284 identified right of way permits have been submitted but KINBER is experiencing delays in the approval process which has delayed successful completion as projected on this milestone. | 45 | 90% of the pole and conduit applications have been submitted | 45 | 28 of the 62 building entrances have been completed | 10 | Selection of a vendor for equipment was made in Q3,2011. All equipment has been ordered with an expectation that it will be delivered in Q4, 2011. | 0 | Project is on schedule | 0 | Project is on schedule | 0 | Project is on schedule | 2011-11-15 16:11 | 2011-11-15 16:11 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2011 | Q4 | Q4 - 2011 | 5097 | 4768 | TRUE | 53 | Overall project is being reported as slightly behind due to the deliverable based billing nature of our construction contract. The project will be over 70% complete in Q1 2012. | 100 | Fiber Procurement | KINBER has received over 1,030 miles of NZD fiber and has secured dedicated factory time to manufacture the remaining fiber necessary to build the network. It is anticipated that sufficient quantities of fiber will be ordered and delivered well in advance of their need. | 100 | Project is on schedule. | 100 | Project is on schedule. | 97 | Project is on schedule. | 90 | We are awaiting conduit approvals related to a change in route related to the Zito project overlash. | 75 | Project is ahead of schedule. | 79 | The optical equipment has been ordered and received. It is currently being tested and configured. Additional equipment is ordered. | 15 | Project is on schedule. | 0 | It was decided to hold equipment in intermediary staging facilities rather than deliver it to the various node sites across the state until fiber terminations were available in each location for appropriate setup and testing. It is expected that 40% of the equipment will be deployed in Q1 2012. | 0 | Equipment deployment has not yet taken place but will begin in Q1 2012. | 2012-02-17 14:38 | 2012-02-17 14:38 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2012 | Q1 | Q1 - 2012 | 5989 | 5594 | TRUE | 72 | Although the project is slightly behind schedule; it met the substantially complete obligation in February 2012. The project continues to move forward and is actually ahead of schedule in many milestone categories. The allocation of funds is behind due to the deliverable based nature of KINBER's fixed-price construction contract billing. | 100 | Fiber Procurement | KINBER has received all of the fiber necessary to build the network. | 100 | Milestone is complete. | 100 | Milestone is complete. | 97 | Project is on schedule. | 93 | We are waiting on a few permits to be released for construction activities to commence. Many of these permits are on small sections of segments, delaying segment completion. This will not delay the project. | 75 | Project is on schedule. | 86 | Project is on schedule. | 50 | Project is on schedule. | 26 | Equipment has been deployed at six (6) of twenty-three (23) sites requiring equipment. Equipment has been received for most of the other locations and staged at a secure facility awaiting deployment. | 0 | Although fiber and equipment have been deployed in many sites on the network, connectivity has not been established and the network does not yet have a lit segment to test the network. | 2012-05-09 16:18 | 2012-05-09 16:18 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2012 | Q2 | Q2 - 2012 | 6969 | 6112 | TRUE | 72 | Project is slightly behind due to make-ready approvals and related work. Also the fixed price contract only allows KINBER to pay its construction vendor for completed milestones; not proportionally to the work completed. This results in an artificially low completion percentage. | 100 | Fiber Procurement | KINBER has received all of the fiber necessary to build the network. | 100 | Milestone is complete. | 100 | Milestone is complete. | 99 | Project is slightly behind due to length of time it takes to get approvals. | 97 | Project is slightly behind due to length of time it takes to get approvals. | 95 | 59 of 62 sites are completed | 100 | All network equipment has been procured. | 75 | Project is on schedule. | 61 | Equipment has been deployed at 14 of 23 sites | 6 | Although fiber and equipment have been deployed in many sites on the network, connectivity has not been established and the network does not yet have a lit segment to test the network. The project schedule has been slowed by small portions of fiber in early segments that can not be connected to light the entire segment. KINBER is addressing this milestone by delivering and configuring equipment to sites prior to the fiber being complete and tested. We will deploy more crews, as necessary to catch up on progress on this milestone once the fiber segments are complete. | 2012-08-09 13:38 | 2012-08-09 13:38 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2012 | Q3 | Q3 - 2012 | 7799 | 6602 | TRUE | 82 | Project is slightly behind due to permitting and ROW delays as well as the fixed price nature of the contract. KINBER only spends funds based on deliverable completion and does not make partial payments. Therefore, more work has been completed than funds drawn due to this payment schedule. | 100 |  | KINBER has received all of the fiber necessary to build the network. | 100 | Milestone is complete | 100 | Milestone is complete | 99 | Project is waiting for a few additional ROW approvals. | 97 | KINBER is waiting for a few remaining permits | 97 | This slight delay is related to pending permits and ROW approvals | 100 | Milestone is complete. | 90 | Project is on schedule. | 96 | Equipment has been deployed at 22 of 23 sites. | 33 | Although fiber and equipment have been deployed to much of the network, connectivity has not been fully established. There are five segments lit and in test status, and one segment (B) is in production status. Other segment lighting and testing has been slowed due to small fiber segments that have not been connected due to something like a bridge crossing or other construction or permit related delay. KINBER has to deployed all equipment at 22/23 node sites and awaits final connectivity to be able to light the segments as soon as possible. | 2012-11-08 10:14 | 2012-11-08 10:14 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2012 | Q4 | Q4 - 2012 | 8691 | 7505 | TRUE | 92 | Project is slightly behind due to extreme weather in October 2012 (superstorm Sandy) and the deployment of make-ready crews to deal with emergency repairs in other states. | 100 | Fiber Procurement | KINBER has received all of the fiber necessary to build the network. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 99 | We are awaiting one final approval for a bridge crossing over a railroad. | 100 | Milestone is complete. | 100 | Milestone is complete. | 95 | Project is slightly behind due to weather related construction delays. | 100 | Milestone is complete. | 67 | 10 of the 15 segments have been lit are in various stages of testing. This milestone has been delayed due to a 60-day construction schedule impact to the project caused by Superstorm Sandy. | 2013-02-11 07:44 | 2013-02-11 07:44 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2013 | Q1 | Q1 - 2013 | 9609 | 8336 | TRUE | 95 | Construction of the network is complete. KINBER is holding the remaining 5% of funds until all proper documentation is complete for closeout. | 100 | Fiber Procurement | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 2013-05-06 11:38 | 2013-05-06 11:38 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2013 | Q2 | Q2 - 2013 | 11787 | 9954 | TRUE | 100 | Project is complete. | 100 | Fiber Procurement | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 2014-02-03 17:10 | 2014-02-03 17:10 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570027 | 2010 | Q2 | Q2 - 2010 | 51 | 1328 | FALSE | 1 |  |  |  |  | 100 |  | 100 |  |  |  | 100 |  | 10 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2010 | Q3 | Q3 - 2010 | 221 | 1377 | TRUE | 1 | No variance to baseline. | 0 | N/A | N/A | 100 | Complete. | 100 | Complete. | 0 | N/A | 90 | All construction permits have been requested from the NMDOT. Expecting to receive all permits in Quarter 4. | 0 | The FONSI was signed and issued on September 30th, therefore we were not able to begin construction or break ground until it had been obtained. | 0 | No new progress. | 0 | No new progress. | 0 | No new progress. | 0 | No new progress. | 2010-10-29 12:17 | 2010-10-29 12:17 | 5496 | 5496 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2010 | Q4 | Q4 - 2010 | 565 | 1586 | TRUE | 3 | Milestone progress for the past quarter has been affected by several factors including the delay in receiving the FONSI, the procurement process taking longer than expected and the extensive analysis and review of equipment manufacturer qualifications as a part of the vendor selection process. Since vendor selection will be close to complete this next quarter and the project will begin implementation ENMR-Plateau is expecting to catch up to projected milestones in subsequent quarters. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 99 | All permits received from NMDOT. Currently waiting on one permit change request with NMDOT due to moving fiber route from one side of the street to another. Also waiting on permit related to railroad crossing. This is not affecting progress as of now. | 0 | Site preparation was one of the milestones that was pushed back due to the delay in receiving the FONSI. ENMR-Plateau is currently in the process of bidding the construction of the equipment building facilities and expects to have a contractor begin site work by the end of March. | 0 | Due to the additional amount of time required to complete the final EA and have the FONSI issued the schedule was pushed back two months. In addition the procurement process is taking longer than anticipated. We are estimating to have the equipment procurement well under way by the middle to end of Q1 2011 and catch up the milestone in subsequent quarters. | 0 | No variance. | 0 | Equipment deployment was also affected by the addtional time required for the completion of the environmental assessment. Currently in the process of receiving RFP responses and selecting vendors for each equipment type. Procurement is estimated to get under way in Q1 2011 and estimated to catch up to milestones in subsequent quarters. | 0 | No variance. | 2011-01-26 18:30 | 2011-01-26 18:30 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2011 | Q1 | Q1 - 2011 | 2027 | 2759 | TRUE | 7 | As discussed in previous PPRs progress for milestones have been affected by the delay in the FONSI, length of time required for proper procurement processes and extensive review and analysis conducted on equipment manufacturers. As of 4/30 vendor selection for all aspects of project have been complete. Currently negotiating or finalizing contracts and expect to catch up to projected milestones in subsequent quarters. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 0 | As of the end of the quarter still evaluating the contractor proposals. Awarded building contractor on 4/11 and auxiliary equipment vendor on 4/11. | 0 | Selected DWDM vendor on 2/22; haven't finalized contract negotiations as of 3/31. Selected Access Equipment vendor on 3/9; also currently working on contract negotiations. | 6 | No variance. | 0 | Pushed back due to equipment procurement schedule. Waiting for contract negotiations and scheduling to be finalized for DWDM Equipment; deployment of DWDM Equipment is expected to begin next quarter. | 0 | Pushed back due to equipment deployment schedule. | 2011-05-13 16:17 | 2011-05-13 16:17 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2011 | Q2 | Q2 - 2011 | 3307 | 3416 | TRUE | 33 | As discussed in previous PPRs progress for milestones have been affected by the delay in the FONSI, length of time required for proper procurement processes and extensive review and analysis conducted on equipment manufacturers. As of 6/30 vendor selection and contract execution for all parts of the project has been completed. Expect to catch up to projected milestones in subsequent quarters. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 10 | Contractor selected and contract executed. Contractor expected to begin work next quarter. | 50 | Contract negotiations with all equipment vendors have been finalized. Contracts have been executed and procurement is underway. | 35 | No variance. Construction progress proceeding on schedule. | 50 | Equipment deployment is under way. Deployment schedule was pushed back due to equipment procurement schedule. | 25 | Equipment testing is under way. Testing schedule was pushed back due to equipment deployment schedule. | 2011-08-25 10:45 | 2011-08-25 10:45 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2011 | Q3 | Q3 - 2011 | 4187 | 3942 | TRUE | 56 | Variance of 2%. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 45 | Site construction and building set at one location. Site construction complete at second location. | 60 | Equipment is being procured as we are able to install it. The equipment installers are able to install and turn up equipment very quickly. | 53 | No variance. | 60 | Equipment deployment follows equipment procurement. | 50 | Network testing follows equipment procurement and deployment. | 2011-11-21 15:54 | 2011-11-21 15:54 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2011 | Q4 | Q4 - 2011 | 4923 | 4604 | TRUE | 79 | Positive variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 95 | Site construction complete, DC power approximately 95% complete. Waiting on connection to commercial power from electric company. Anticipate 100% completion by the end of Q1 2012. | 83 | Positive variance. | 75 | Positive variance. | 83 | Positive variance. | 75 | Positive variance. | 2012-02-09 11:24 | 2012-02-09 11:24 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2012 | Q1 | Q1 - 2012 | 5977 | 5588 | TRUE | 91 | Positive variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 90 | Equipment procurement expected to be complete next quarter (Q2 2012). | 90 | Positive variance. | 90 | Equipment deployment follows procurement. Expected to be complete next quarter (Q2 2012). | 90 | Testing follows equipment deployment and network build. Expected to be complete next quarter (Q2 2012). | 2012-05-08 17:26 | 2012-05-08 17:26 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2012 | Q2 | Q2 - 2012 | 6933 | 6094 | TRUE | 94 | Positive variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 92 | Equipment procurement expected to be complete next quarter. Awaiting final inspections and acceptance testing. | 95 | Positive variance. | 92 | Equipment deployment follows procurement. Expected to be complete next quarter. | 92 | Testing follows deployment and procurement. Expected to be complete next quarter. | 2012-08-08 15:47 | 2012-08-08 15:47 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2012 | Q3 | Q3 - 2012 | 7561 | 6439 | TRUE | 96 | Positive variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 95 | Equipment procurement expect to be complete next quarter. | 96 | Network build expect to be completed next quarter. Finalizing splicing and reconciling final invoicing. | 95 | Equipment deployment follows procurement. Expect to be complete next quarter. | 95 | Testing follows deployment and procurement. Expect to be complete next quarter. | 2012-10-30 11:56 | 2012-10-30 11:56 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2012 | Q4 | Q4 - 2012 | 8989 | 7769 | TRUE | 96 | Waiting for final invoicing on construction, equipment and installation, which should be received and paid in January 2013. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 99 | Please see above. | 99 | Please see above. | 99 | Please see above. | 100 | No variance. | 2013-02-26 16:59 | 2013-02-26 16:59 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2013 | Q1 | Q1 - 2013 | 10021 | 8560 | TRUE | 100 | No variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 2013-05-31 11:04 | 2013-05-31 11:07 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570028 | 2010 | Q2 | Q2 - 2010 | 52 | 1313 | FALSE | 2 |  | 0 |  |  | 30 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Administration, Wisconsin Department of | TRUE
NT10BIX5570028 | 2010 | Q3 | Q3 - 2010 | 387 | 1460 | TRUE | 2 | N/A | 0 | N/A | N/A | 30 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-23 14:36 | 2010-11-23 14:36 | 5375 | 5375 | Administration, Wisconsin Department of | TRUE
NT10BIX5570028 | 2010 | Q4 | Q4 - 2010 | 1021 | 2066 | TRUE | 4 | Baseline and last progress report estimated 15% completion at the end of quarter. Did not attain that target due to the fact project has not completed discussion of special award conditions or extension of operating contract (mentioned in #1). | 0 |  | N/A | 90 | Baseline and last progress report estimated 100% completion at the end of quarter. Did not attain that target due to the fact project has not completed discussion of special award conditions or extension of operating contract (mentioned in #1). | 0 | Baseline and last progress report estimated 5% completion at the end of quarter. Did not attain that target due to the fact project has not completed discussion of special award conditions or extension of operating contract (mentioned in #1). | 0 | Baseline and last progress report estimated 5% completion at the end of quarter. Did not attain that target due to the fact project has not completed discussion of special award conditions or extension of operating contract (mentioned in #1). | 0 | Baseline and last progress report estimated 5% completion at the end of quarter. Did not attain that target due to the fact project has not completed discussion of special award conditions or extension of operating contract (mentioned in #1). | 0 | Baseline and last progress report estimated 5% completion at the end of quarter. Did not attain that target due to the fact project has not completed discussion of special award conditions or extension of operating contract (mentioned in #1). | 0 | Baseline and last progress report estimated 35% completion at the end of quarter. Did not attain that target due to the fact project has not completed discussion of special award conditions or extension of operating contract (mentioned in #1). | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-09 14:02 | 2011-02-09 14:02 | 5375 | 5375 | Administration, Wisconsin Department of | TRUE
NT10BIX5570028 | 2011 | Q1 | Q1 - 2011 | 1449 | 2438 | TRUE | 5 | Baseline and last progress report estimated 15% completion at the end of quarter. Did not attain that target due to the fact project did not complete discussion of special award conditions and the project was terminated as mentioned in #1. | 0 |  | N/A | 100 | N/A | 0 | Baseline and last progress report estimated 5% completion at the end of quarter. Did not attain that target due to the fact project did not complete discussion of special award conditions and the project was terminated as mentioned in #1. | 0 | Baseline and last progress report estimated 5% completion at the end of quarter. Did not attain that target due to the fact project did not complete discussion of special award conditions and the project was terminated as mentioned in #1. | 0 | Baseline and last progress report estimated 5% completion at the end of quarter. Did not attain that target due to the fact project did not complete discussion of special award conditions and the project was terminated as mentioned in #1. | 0 | Baseline and last progress report estimated 5% completion at the end of quarter. Did not attain that target due to the fact project did not complete discussion of special award conditions and the project was terminated as mentioned in #1. | 0 | Baseline and last progress report estimated 35% completion at the end of quarter. Did not attain that target due to the fact project did not complete discussion of special award conditions and the project was terminated as mentioned in #1. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-04-20 11:27 | 2011-04-20 11:27 | 5375 | 5375 | Administration, Wisconsin Department of | TRUE
NT10BIX5570028 | 2011 | Q2 | Q2 - 2011 | 2469 | 2983 | TRUE | 1 | As noted earlier in the report,project terminated for convenience | 0 | N/A | N/A | 100 | N/A | 0 | Project terminated | 0 | Project terminated | 0 | Project terminated | 0 | Project terminated | 0 | Project terminated | 0 | N/A | 0 | N/A | 0 | N/A | 2011-07-20 09:41 | 2011-07-20 09:41 | 5373 | 5373 | Administration, Wisconsin Department of | TRUE
NT10BIX5570029 | 2010 | Q2 | Q2 - 2010 | 53 | 1282 | FALSE | 5 | [6 empty] | 35 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Education Networks of America, Inc. | TRUE
NT10BIX5570029 | 2010 | Q3 | Q3 - 2010 | 353 | 1443 | TRUE | 5 | Delay in key vendor contract encountered secondary to new Federal regulations regarding security interest. ENA, vendor and National Telecommunications and Information Administration are currently working to address this issue. | 0 |  | N/A | 0 | N/A | 15 | Vetting Wave 2 sites to verify service need. | 0 | See item #2a above | 0 | See item #2a above | 0 | See item #2a above | 0 | See item #2a above | 0 | See item #2a above | 0 | See item #2a above | 0 | See item #2a above | 2010-11-19 13:15 | 2010-11-19 13:15 | 5509 | 5509 | Education Networks of America, Inc. | TRUE
NT10BIX5570029 | 2010 | Q4 | Q4 - 2010 | 819 | 1854 | TRUE | 5 | Delay in securing primary vendor contract because during the fourth quarter our vendor was in the process of undergoing an acquisition and that significantly affected their ability to negotiate or enter into new service contracts. | 0 |  | N/A | 0 | N/A | 15 | Vetting Wave 2 sites to verify service need. | 0 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 2011-01-28 16:07 | 2011-01-28 16:07 | 5509 | 5509 | Education Networks of America, Inc. | TRUE
NT10BIX5570029 | 2011 | Q1 | Q1 - 2011 | 1397 | 2411 | TRUE | 0 | Grant termination due to unforeseen changes in the end-user market within our PFSAs. | 0 |  | N/A | 0 | N/A | 0 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 2011-03-10 15:57 | 2011-03-10 15:57 | 5508 | 5508 | Education Networks of America, Inc. | TRUE
NT10BIX5570030 | 2010 | Q2 | Q2 - 2010 | 54 | 1269 | FALSE | 18 |  |  |  |  | 100 |  | 100 |  | 75 |  | 85 |  |  |  | 20 |  | 15 |  | 15 |  | 15 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2010 | Q3 | Q3 - 2010 | 445 | 1489 | TRUE | 12 | Sole source ordinance and public/private agreements have taken longer to negotiate and draft than anticipated. In the baseline report, we had estimated completion by Q6. We now anticipate substantial completion by Q8 and full completion by Q12. DeKalb Fiber Optics has committed to additional resources necessary to complete the project on schedule. | 0 |  | N/A | 100 | Environmental assessment special award condition satisfied in Q3. | 100 | Completed network design. | 50 | Contingent on private/public agreements. North part of route in-hand. South part of route to be acquired when north route is underway. Target was 100% at this point but delayed in order to concentrate on agreement preparation. | 75 | Contingent on private/public agreements. Efforts this quarter have been redirected to getting the agreements completed. When construction is underway, permitting for the south part of the route will be restarted. Target was 100% at this point but delayed in order to concentrate on agreements preparation. | 0 | N/A | 0 | Contingent on private/public agreements. No equipment needed immediately due to construction not started. Target was 20% at this point but delayed in order to work on NIU Outreach agreement. | 0 | Contingent on private/public agreements. DeKalb Fiber Optics is prepared to start work immediately upon signing of agreements and has committed to additional resources necessary to complete the project on schedule. Target was 10% at this point but delayed due to lack of agreements that would allow construction to start. | 0 | Contingent on private/public agreements. Equipment purchase and deployment will follow start of construction. Target was 20% at this point but delayed due to lack of agreements are needed in order for construction to start and equipment to be deployed. | 0 | Contingent on private/public agreements. Network testing will be performed as segments are constructed. Target was 20% at this point but delayed due to lack of agreements that are needed in order for construction to start and testing to take place. | 2010-11-29 17:52 | 2010-11-29 17:52 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2010 | Q4 | Q4 - 2010 | 1315 | 2341 | TRUE | 15 | Original Baseline indicated 45% at this point which was revised to 15% in Q3. Construction work started later in quarter than expected but progress with anchor institutions and equipment procurement progress has allowed project to keep pace with Q3 updated expectation. | 0 | N/A | N/A | 100 | Previously completed | 100 | Previously completed | 60 | Rights of Way are in place for the segments to be completed in Q5. Work continues to acquire rights of way for work segments to be constructed in future quarters. We had expected to be 100% complete as of Q4 but resources were shifted to mobilizing construction activities. | 70 | Permits are in-place for segments to be constructed in Q5 and work continues to acquire permits for future quarters. Permits were expected to be 100% complete at this point but construction delayed. | 0 | N/A | 15 | Network build equipment is either on-site or being shipped. Northern Illinois University Outreach has completed needs surveys at all Community Anchors that are expected to receive fiber in Q5. The procurement process for equipment to be placed at community anchor locations is underway. This equipment is expected to be competitively bid in Q5. Equipment procurement was projected to be 50% complete as of Q4 but construction delayed. | 1 | Completed duct only amounting to 5351 lf. in Q4 in DeKalb. Fiber to be installed starting in Q5. Expected to be 45% at this point but IRU was not signed until late in Q4 which delayed construction from what was projected. | 1 | Deployed network build equipment for 11,477 in Q4. Expected to be 40% at this point but delayed due to IRU not signed until late in Q4 which delayed construction from what was projected. | 0 | No fiber installed. Expected to be 40% at this point but delayed due to IRU was not signed until late in Q4 which delayed construction from what was projected. | 2011-02-22 17:08 | 2011-02-22 17:08 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2011 | Q1 | Q1 - 2011 | 2071 | 2781 | TRUE | 20 | Baseline predicted 60% at this point. The project was behind schedule early due to difficulty getting Indefeasible Right of Use and Locating, Maintenance and Repair agreements with DeKalb Fiber Optics, LLC in place. Project has been moving well since 1/1/11. | 0 |  | N/A | 100 | Previously Completed | 100 | Previously Completed | 65 | Baseline predicted 100%. The project was behind schedule early due to difficulty getting agreements in place. Right of Way agreements are in place for north part of route and work there is underway. Agreements are in place for State and County Roads project-wide. Baseline had predicted 100% for Quarter 5. We estimate the project will be 100% complete with ROW in December, 2011 (nine additional months). Based on detailed production schedule. ROW for all State and County Roads in hand. Need ROW for individual communities only. These are being acquired a few months in advance of construction for that area as opposed to obtaining all at the front end of the project that was envisioned in the baseline. | 75 | Baseline predicted 100% at this point. The project was behind schedule early due to difficulty getting agreements in place. Rail crossing permits are filed for the north part of the route. Baseline had predicted 100% for Quarter 5. We estimate the project will be 100% complete with permits in December, 2011 (nine additional months). Based on detailed production schedule. Rail crossing permits process is underway and ongoing. | 0 | N/A | 30 | Baseline predicted 75% at this point. Network build equipment is being received as production schedule dictates. Community Anchor switches were competitively bid. The project was behind schedule early due to difficulty getting agreements in place. Backbone equipment is being prepared to bid. 911 equipment is being prepared to bid. Baseline had predicted 75% for Quarter 5. We estimate the project will be 75% complete with equipment procurement in August, 2011 (five additional months). Based on award and delivery schedule for CAI switches. | 15 | Baseline predicted 60% at this point. The project was behind schedule early due to difficulty getting agreements in place. Project is ahead of last quarter projection due to good construction conditions.Baseline had predicted 60% for Quarter 5. We estimate the project will be 60% complete with network build between August and September, 2011 (five-Six additional months). Based on detailed construction schedule and estimate provided by contractors | 1 | Baseline predicted 50% at this point. The project was behind schedule early due to difficulty getting agreements in place. Community Anchor switches were bid in Quarter 5, but not yet installed. | 9 | Baseline predicted 50% at this point. The project was behind schedule early due to difficulty getting agreements in place. All segment one fiber has been tested. Baseline had predicted 50% for Quarter 5. We estimate the project will be 50% complete with testing in September, 2011 (six additional months). Based on detailed construction schedule and estimate provided by contractors. | 2011-05-17 09:18 | 2011-05-17 09:18 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2011 | Q2 | Q2 - 2011 | 2949 | 3232 | TRUE | 29 | Baseline predicted 80% completed at this point. The project was behind schedule early due to difficulty getting indefeasible right to use and locating, repair and relocation agreements with DeKalb Fiber Optics, LLC in place. Project has been moving well for last two quarters. | 0 |  | N/A | 100 | Previously completed. There was no budget for Environmental Assessment therefore the cost of $89,500 will need to be offset with savings in other areas such as rail and pipeline crossings which are costing less than expected. | 100 | Previously completed within budget. | 58 | Baseline predicted 100%. The project was behind schedule early due to difficulty getting agreements in place. Difficulty getting right of way (row) agreement for one parcel in Genoa necessitated requesting and receiving a route revision. There are no known row issues with the north or central part of the route. In the south part of the route, the number of landowner and township row agreements needed is greater than anticipated, requiring additional time. Additional personnel and legal resources have been allocated to row acquisition. Row permits are in-hand for State and County Roads. Six of twelve municipal utility agreements are either in-hand or expected soon. We estimate the project will be 100% completed with row by December, 2011 (nine additional months). This is on target with what was predicted in the last report period. Expenditures are expected to be within budget. | 80 | Baseline predicted 100% at this point. All eighteen rail crossing permits have been submitted; nine have been approved; nine are under review. Expenditures are expected to be within budget. | 0 | N/A | 15 | Baseline predicted 100%. The project was behind schedule early due to difficulty getting agreements in place. Community anchor switches were received, inventoried and paid in Q2. Backbone equipment was bid and ordered. When backbone equipment is paid (Q8), equipment budget will be 60% spent. Expenditures are expected to be within budget. | 27 | Baseline predicted 80% complete at this point. The project was behind schedule early due to difficulty getting agreements in place. Build has been at a good pace for past two quarters. We estimate the network build will be at 80% between October and November, 2011 (4-5 additional months). Based on detailed construction schedule and estimate provided by contractors. Expenditures are expected to be within budget. Contractor is being paid on a monthly basis from federal and local funds. | 1 | Baseline predicted 75% at this point. The project was behind schedule early due to difficulty getting agreements in place. Switches for Community Anchors have been received but not deployed. Backbone equipment has been ordered but not received, deployed or paid. | 4 | Baseline predicted 70% at this point. The project was behind schedule early due to difficulty getting agreements in place. Route change approval process delayed completion of fiber path and testing in Genoa area. We estimate the project will be 75% complete with testing in November, 2011 (five additional months). Based on detailed construction schedule and estimate provided by contractors. | 2011-08-08 11:44 | 2011-08-08 11:44 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2011 | Q3 | Q3 - 2011 | 4019 | 3850 | TRUE | 47 | Baseline predicted 95% complete at this point. The project was behind schedule early due to getting indefeasible right to use agreement and locating, repair and relocation agreements with DeKalb Fiber Optics in place. Project has been moving well past three quarters showing completion percentages of 20, 29 and 47 percent respectively. The budget for the project overall is within parameters. | 0 |  | N/A | 100 | Previously completed. There was no budget for environmental assessment included in the project, therefore the $89,500 cost for the environmental assessment must be offset with savings in other areas. The costs for rail and pipeline crossings are expected to be less than budgeted. | 100 | Previously completed within budget. | 70 | Baseline predicted 100%. The project was behind schedule early due to difficulty getting agreements in place. In the south part of the route, the number of landowner and township row agreements needed is greater than anticipated, requiring additional time. Additional personnel and legal resources have been allocated to row acquisition. Despite best efforts, we are forced to request a route revision to avoid properties whose owners either will not agree, refuse to negotiate or insist on being paid for the row. Row permits are in-hand for State and County Roads. Eight of fourteen municipal utility agreements are either in-hand or expected soon and the others are in active negotiation/ approval process. We estimate the row acquisition will be 100% completed with row by April, 2012 (twelve additional months). This assumes route change is approved by 1/1/12. Expenditures are expected to be within budget. | 90 | Baseline predicted 100% at this point. All eighteen rail crossing permits are approved and in-hand; one of one interstate highway crossing permit is approved and in-hand. No other construction permits are expected to be needed. We will continue to pay for permit expenses into Quarter 8 as construction activities covered under the approved permits are completed. | 0 | N/A | 17 | Baseline predicted 100%. The project was behind schedule early due to difficulty getting agreements in place. Fiber back haul equipment for E-911 system was bid in Q3. When backbone equipment is paid (Q8), equipment budget will be 60% spent. Still need to order GPON and downtown wireless equipment. Expenditures are expected to be within budget. Expect to be at 100% in Q11 (12 additional months). | 50 | Baseline predicted 100% complete at this point. The project was behind schedule early due to difficulty getting agreements in place. Build has been at a good pace for past three quarters. We estimate the approved network build will be at 100% in June, 2012 (9-12 additional months). Based on detailed construction schedule and estimate provided by contractors. Expenditures are expected to be within budget. Contractor is being paid on a monthly basis from federal and local funds. | 1 | Baseline predicted 100% at this point. The project was behind schedule early due to difficulty getting agreements in place. Switches for Community Anchors have been received and configuration started but not deployed. Backbone equipment has been ordered and 50% received; it has not been deployed or paid. Fiber back haul equipment has been bid but not awarded, deployed or paid. Deployment of backbone and anchor switches equipment will start in Q8. Backbone deployment will be complete in Q10 (nine additional months) and anchor switch deployment will continue through Q11 (twelve additional months). | 4 | Baseline predicted 100% at this point. The project was behind schedule early due to difficulty getting agreements in place. Route change approval process delayed completion of fiber path and testing in Genoa area and row acquisition delayed construction (and testing) in south part of route. We estimate the project will be 100% complete with testing in Q10 (nine additional months). Based on detailed construction schedule and estimate provided by contractors. | 2011-11-14 12:37 | 2011-11-14 12:37 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2011 | Q4 | Q4 - 2011 | 5115 | 4785 | TRUE | 62 | Baseline predicted 98% complete at this point. The project was behind schedule early due to problems getting the indefeasible right to use and locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Since January, 2011, the project has been moving ahead well showing completion percentages of 20, 29, 47 and 62% respectively for the previous four quarters. The overall budget for the project is within parameters. | 0 | N/A | N/A | 100 | Previously completed. There was no budget for environmental assessment, therefore the $89,500 cost of the assessment must be offset with savings in other areas. The costs for rail and pipeline crossings are less than anticipated and the cost of the assessment will be covered by savings in those areas. | 100 | Previously completed within budget. | 100 | Baseline predicted 100% complete with rights of way at this point. The project was behind schedule early due to problems getting the indefeasible right to use and locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. In the south part of the route, the number of landowner and township row agreements is greater than anticipated, requiring additional time. Additional personnel and legal resources have been allocated to the row issue. Despite best efforts, the project had no alternative other than to request a route change around areas of unattainable row. This route change request was submitted to NTIA in December, 2011. Row permits are in-hand for all State and DeKalb County roads. Nine of 14 municipal utility agreements are approved and the remaining five are in active negotiation and/ or approval process. Two private row acquisitions need to be finalized. La Salle County row permits are in final approval stages. We estimate row approval will be 100% compl | 95 | Baseline predicted 100%. All 18 rail crossing permits are in-hand. Four crossings remain to be completed in municipalities with which utility agreements are still being negotiated. Some inspection expenses remain to be paid as those crossings are made. One interstate crossing permit was received and the crossing made and paid for in Q4-11. No other permits are anticipated. | 0 | N/A | 21 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor premise equipment has been purchased, paid, and configuration is complete. Backbone equipment has been received, partially paid and configuration started. Fiber back haul equipment has been ordered, partially paid, and partially deployed. Remaining equipment to be procured consists of GPON, wireless access points and City of DeKalb downtown wireless, all of which are in active engineering design. Expect to be at 100% in Q11 (12 additional months). | 70 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Duct is at 84% complete and fiber is at 65% complete. Acquired 144 strand miles of fiber from Northern Illinois University. Acquired 12.84 miles of duct space from DeKalb Fiber Optics and an in-kind contribution to the project. Acquired collocation space in four telephone company offices. We estimate the network will be complete in June, 2012 (twelve additional months from baseline and six additional months from date of report). | 5 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community Anchor equipment deployment is expected to commence in January, 2012 and continue into Q11. Network backbone equipment deployment will start in January, 2012 and continue into Q10. Deployment of the fiber back haul equipment was started in December, 2011 and will continue into April, 2012. Deployment of GPON, wireless access points and downtown wireless depends on procurement, but probably will take place in Q10 (May, 2012). All deployment is expected to be complete in Q11 (12 additional months). | 8 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Areas of row acquisition challenges have prevented testing because a complete optical route was not available. Testing has now been completed on 52,000 feet of fiber from Kirkland to the south edge of Genoa. | 2012-02-17 17:07 | 2012-02-17 17:07 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2012 | Q1 | Q1 - 2012 | 6037 | 5618 | TRUE | 70 | Baseline predicted 100% complete at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Since January, 2011, the project has been moving well showing quarterly completion percentages or 20, 29, 47, 62, and 70 per cent respectively for the past five quarters. The project met its substantial completion deadline and is on target to meet the final completion deadline. Overall, the budget is within parameters. Some line items have been exceeded but savings in other areas are expected to offset those overages. | 0 |  | N/A | 100 | Previously completed. There was no budget provided for the environmental assessment, therefore the $89,500 cost of the environmental assessment must be offset with savings in other areas. The costs for rail and pipeline crossings are less than anticipated and the cost of the environmental assessment will be covered by savings in those areas. | 100 | Previously completed within budget. | 100 | Baseline predicted 100% completed at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. In the south part of the route, the number of landowner and township row agreements needed is greater than anticipated, requiring additional time. Additional personnel and legal resources have been allocated to row acquisition. Many row acquisition issues were resolved when the route change was approved in January, 2012. That route was immediately constructed. Ten of fourteen municipal row agreements are in hand and those parts of the route have been constructed. Two private row acquisitions remain. La Salle County permits were received and those segments constructed. All outstanding row acquisition (municipal and private) are in active negotiation process. We now expect row acquisition to be complete by June, 2012 (fifteen additional months from baseline a | 95 | Baseline predicted 100% at this point. All 18 rail crossing permits are in hand, 14 have been made and four remain in municipalities with which row agreements are being negotiated. Some flagmen and inspection costs remain to be paid when those crossings are made. No other permit costs are expected. | 0 | N/A | 24 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor premise equipment has been received and paid. Backbone equipment has been received and partially paid. Fiber back haul equipment has been received and paid. Remaining equipment to be procured is for GPON (under engineering design and feasibility study), wireless access points for libraries (to be bid in Q10) and downtown wireless (under engineering design). Expect to be completed in Q11 (12 additional months from baseline). | 75 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Duct is 86% complete and fiber is 80% complete. All leased fiber is complete. All duct provided by DeKalb Fiber Optics has been received and overridden with fiber. We estimate the network will be completed in September, 2012 (15 additional months from baseline). | 25 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor equipment deployment started in January, 2012 and is complete in Genoa, Kingston and Kirkland. Backbone equipment deployment started in January, 2012 and four node locations were installed in Q9 (Genoa Frontier Central Office, Northern Illinois University [NIU] network operations center, NIU central office, and DeKalb Frontier central office.) Fiber back haul equipment deployment started in Q9. Remaining community anchor equipment deployment, backbone equipment, fiber back haul equipment, GPON and downtown wireless will continue into Q10 and expected to be complete in Q11 (12 additional months from baseline). | 33 | Baseline predicted 100%.The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. 85,000 feet (16.1 miles) of fiber was tested from the south side of Genoa to Northern Illinois University Wellness and Life Building and 92,000 feet (17.42) miles was tested from Wellness and Life to Hinckley in Q9 of award. Total now tested is 229,000 feet (43.37 miles) of 127 miles for project. | 2012-05-11 10:17 | 2012-05-11 10:17 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2012 | Q2 | Q2 - 2012 | 7237 | 6246 | TRUE | 75 | Baseline predicted 100% complete at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. Since January, 2011, the project has been moving well showing completion percentages of 20, 29, 47, 62, 70, and 75 percent respectively for the past six quarters. The project met its substantial completion deadline and is on track to meet final completion deadline. Overall, the budget is within parameters. Some line items have been and/or will be exceeded but savings in other areas are expected to offset those overages. | 0 |  | N/A | 100 | Previously completed. There was no budget provided for the environmental assessment, therefore the $89,500 cost of the environmental assessment must be offset from savings in other budget areas. The costs for rail and pipeline crossings are anticipated to cost less that budgeted so the cost of the assessment can be covered from savings in that area. | 100 | Previously completed within budget. | 100 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. One right-of-way issue and three municipality agreements were resolved in Q10. There remains one right-of-way issue and one municipal utility agreement to resolve. Those processes are well along and are expected to be completed in Q11 of award. All rights-of-way issues should be resolved in July of 2012 (sixteen months additional from baseline and one additional month from date of this report). Costs for rights-of-way are expected to exceed budget due to payment for previously completed duct that was budgeted in "Construction" but was properly paid from "Rights-of-Way" line item. | 95 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. Baseline predicted 100% at this point. All 18 rail crossing permits are in hand, 14 have been made and four remain in municipalities with which row agreements are being negotiated. Some flagmen and inspection costs remain to be paid when those crossings are made. No other permit costs are expected. All crossings are expected to be completed in Q11 of award. Submitted permit application and detailed construction drawings to Illinois Department of Transportation for State Route 30 from Kane County line to Big Rock, IL. | 0 | N/A | 27 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor premise equipment has been received and paid. Backbone equipment has been received and partially paid and we expect to pay for the majority of the backbone equipment in Q11 of award. Fiber back haul equipment has been received and paid. Wireless access points for libraries have been received and paid. Remaining equipment to be procured is for 10Gig "ring" modules (under engineering design), and downtown wireless (under engineering design). Expect to be completed in Q11 (12 additional months from baseline). | 80 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Duct is 87% complete and fiber is 87% complete. All leased fiber is complete. All duct provided by DeKalb Fiber Optics has been received and overridden with fiber. We estimate the network will be completed in November, 2012 (17 additional months from baseline). | 30 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor equipment deployment started in January, 2012 and is complete in Genoa, Kingston and Kirkland. Backbone equipment deployment started in January, 2012 and one additional node location was installed in Q10 (Hinckley central office) Fiber back haul equipment deployment continued in Q10. Remaining community anchor equipment deployment, backbone equipment, fiber back haul equipment, and downtown wireless will continue into Q11 and expected to be complete in Q12 (15 additional months from baseline). | 33 | Baseline predicted 100%.The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. No new fiber was tested this quarter due to gaps in the fiber path due to row and utility agreement issues. Total now tested is 229,000 feet (43.37 miles) of 127 miles for project. | 2012-08-24 12:50 | 2012-08-24 12:50 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2012 | Q3 | Q3 - 2012 | 7923 | 6666 | TRUE | 83 | Baseline predicted 100% complete at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. Since January, 2011, the project has been moving well showing completion percentages of 20, 29, 47, 62, 70, 75 and 83 percent respectively for the past seven quarters. The project met its substantial completion deadline and is on track to meet final completion deadline. Overall, the budget is within parameters. Some line items have been and/or will be exceeded but savings in other areas are expected to offset those overages. | 0 |  | N/A | 100 | Previously completed for original project scope. Additional environmental assessment work is on-going for proposed route changes. There was no budget provided for the environmental assessment, therefore the $89,500 cost of the environmental assessment must be offset from savings in other budget areas. The costs for rail and pipeline crossings are anticipated to cost less that budgeted so the cost of the assessment can be covered from savings in that area. | 100 | Previously completed within budget. | 100 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. One right-of-way issue and one municipality agreement was resolved in Q11. All rights-of-way and municipal utility agreement issues needed for the project are now resolved. Costs for rights-of-way are expected to exceed budget due to payment for previously completed duct that was budgeted in "Construction" but was properly paid from "Rights-of-Way" line item. | 100 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. Baseline predicted 100% at this point. All 18 rail crossing permits are in hand, 16 have been made and 2 remain in municipalities with which row agreements were recently received. Some flagmen and inspection costs remain to be paid when those crossings are made. No other permit costs are expected. All crossings are expected to be completed in Q12 of award. Received permit from Illinois Department of Transportation for State Route 30 from Kane County line to Big Rock, IL. in Q3-12 | 0 | N/A | 64 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor premise equipment has been received and paid. Backbone equipment has been received and paid. Fiber back haul equipment has been received and paid. Wireless access points for libraries have been received and paid. Remaining equipment to be procured is for 10Gig "ring" modules (being bid early in Q4-12), and fire walls for libraries (to be ordered early in Q4-12). Expect to be completed in Q12 (15 additional months from baseline). Equipment procurement is 64% complete when compared to budget. Project total is expected to be under budget. Equipment procurement is 91% complete when compared to expected end of project. | 95 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Duct is 97% complete and newly constructed fiber is 95% complete. All leased fiber is 100 complete. All duct provided by DeKalb Fiber Optics has been received and overridden with fiber. We estimate the network will be completed in November, 2012 (17 additional months from baseline). | 75 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor equipment deployment started in January, 2012 and is complete in Genoa, Kingston, Kirkland, Sycamore, Hinckley, Big Rock, Waterman and Shabbona. Backbone equipment deployment started in January, 2012 and four of five node locations are deployed. Fiber back haul equipment deployment continued in Q11. Remaining community anchor equipment deployment, backbone equipment and fiber back haul equipment will be complete in Q12 (15 additional months from baseline). | 69 | Baseline predicted 100%.The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. 44.23 additional miles of fiber fiber were tested this quarter. Total now tested is 87.6 miles of 127.6 miles of newly constructed fiber for project. | 2012-11-16 14:02 | 2012-11-16 14:02 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2012 | Q4 | Q4 - 2012 | 8741 | 7538 | TRUE | 92 | Baseline predicted 100% complete at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. Since January, 2011, the project has been moving well showing completion percentages of 20, 29, 47, 62, 70, 75 and 83 percent respectively for the past eight quarters. Overall, the budget is within parameters. Some line items have been and/or will be exceeded but savings in other areas are expected to offset those overages. When calculating overall current completion as a percentage of projected final project expenditures, the project is currently more than 96% complete. | 0 |  | N/A | 100 | Previously completed for original project scope. Additional environmental assessment work is on-going for proposed route changes. There was no budget provided for the environmental assessment, therefore the $89,500 cost of the environmental assessment must be offset from savings in other budget areas. The costs for rail and pipeline crossings are anticipated to cost less that budgeted so the cost of the assessment can be covered from savings in that area. | 100 | Previously completed within budget. | 100 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. One right-of-way issue and one municipality agreement was resolved in Q11. All rights-of-way and municipal utility agreement issues needed for the project are now resolved. Costs for rights-of-way are expected to exceed budget due to payment for previously completed duct that was budgeted in "Construction" but was properly paid from "Rights-of-Way" line item. | 100 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. Baseline predicted 100% at this point. All rail crossings are complete but some flagmen costs remain to be paid in 2013-Q1. | 0 | N/A | 65 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor premise equipment has been received and paid. Backbone equipment, fiber back haul equipment, wireless access points and fire walls for libraries have been received and paid. Remaining equipment to be procured is for 10Gig "ring" modules (has been bid, awarded and ordered). Expect to be completed in 2013-Q1, (16 additional months from baseline). Equipment procurement is 65% complete when compared to budget. Project total is expected to be under budget. Equipment procurement is 90% complete when compared to expected end of project. | 100 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Approved duct and fiber is 100% complete. All leased fiber is 100 complete. All duct provided by DeKalb Fiber Optics has been received and overridden with fiber. Completed in December, 2012 (18 additional months from baseline). When route changes are approved, an additional 1.5 miles of duct and fiber will be constructed and an additional 2.975 miles of network will be acquired by IRU or bill of sale. | 95 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor equipment deployment started in January, 2012 and is complete for the project with the exception of three approved locations. Additional locations will need to be deployed when the route changes are approved. Backbone equipment deployment started in January, 2012 and all five node locations are now deployed. Fiber back haul equipment deployment continued in 2012-Q4. Remaining community anchor equipment deployment for approved locations, and fiber back haul equipment will be complete in 2013-Q1 (16 additional months from baseline). | 100 | Baseline predicted 100%.The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Testing was completed for all fiber on the approved network in December, 2012. | 2013-02-13 10:44 | 2013-02-13 10:44 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2013 | Q1 | Q1 - 2013 | 9817 | 8445 | TRUE | 92 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use agreement and locating, maintenance and repair agreements with DeKalb Fiber Optic, LLC in place. Since January, 2011, project has been moving well showing completion percentages of 20, 29, 47, 62. 70, 75, 83 and 92% for the previous eight quarters. Since December, 2012, when the approved route was completed, there has been little progress as we await approval of pending route changes. | 0 |  | N/A | 100 | Previously completed for original project scope. Additional environmental assessment work is on-going for proposed route changes. | 100 | Previously completed within budget. | 92 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. All rights-of-way and municipal utility agreement issues needed for the project are now resolved. Previous quarter reported 100% complete. Budget modification approved in January increased budgeted amount which lowered actual percentage complete. Additional in-kind to be received when prospective route changes are approved. | 100 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. Baseline predicted 100% at this point. | 0 | N/A | 87 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor premise equipment has been received and paid. Backbone equipment, fiber back haul equipment, wireless access points and fire walls for libraries have been received and paid. 10Gig "ring" modules have been received and paid. Expect to be completed in 2013-Q2, (19 additional months from baseline). | 98 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Previous quarter reported 100% compete. Approved route changes added additional network remaining to be completed which lowered actual percentage complete. Approved duct and fiber is 100% complete. All leased fiber is 100 complete. All duct provided by DeKalb Fiber Optics has been received and overridden with fiber. Completed in December, 2012 (18 additional months from baseline). Retroactive route change approval authorized 1.88 miles of contributed duct and fiber to be added to the network. When prospective route changes are approved, an additional 1.26 miles of duct and fiber will be constructed and an additional 1.9 miles of network will be acquired by IRU or bill of sale. | 95 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor equipment deployment started in January, 2012 and is complete for the project with the exception of one approved location. Additional locations will need to be deployed when the prospective route changes are approved. Backbone equipment deployment started in January, 2012 and all five node locations are now deployed. Fiber back haul equipment deployment continued in 2013-Q1. Remaining community anchor equipment deployment for approved locations, and fiber back haul equipment will be complete in 2013-Q2 (19 additional months from baseline). | 98 | Baseline predicted 100%.The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Previous quarter reported 100% compete. Approved route changes added additional network remaining to be tested which lowered actual percentage of completed testing.Testing was completed for all fiber on the approved network in December, 2012. No new fiber was constructed in 2013-Q1. Testing for 1.26 miles of additional fiber will need to be completed when the prospective route changes are approved and that additional fiber is installed. | 2013-05-20 10:44 | 2013-05-20 10:44 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2013 | Q2 | Q2 - 2013 | 10489 | 8896 | TRUE | 93 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use agreement and locating, maintenance and repair agreements with DeKalb Fiber Optic, LLC in place. Since January, 2011, project has been moving well showing completion percentages of 20, 29, 47, 62. 70, 75, 83, 92 and 93% for the previous nine quarters. Since December, 2012, when the approved route was completed, there was little progress as we awaited approval of pending route changes. All route changes are now approved and we are building the remainder of the network. | 0 |  | N/A | 100 | Previously completed for original project scope. Additional environmental assessment work was completed, submitted and approved for retroactive and prospective route changes. | 100 | Previously completed within budget. | 95 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. All rights-of-way and municipal utility agreement issues needed for the project are now resolved. All in-kind duct and fiber provided by DeKalb Fiber Optics has been received. | 100 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. Baseline predicted 100% at this point. | 0 | N/A | 98 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor premise equipment has been received and paid. Backbone equipment, fiber back haul equipment, wireless access points and fire walls for libraries have been received and paid. 10Gig "ring" modules have been received and paid. The only remaining equipment is what may be needed to connect the locations authorized by the prospective route changes. Expect to be completed in 2013-Q3, (19 additional months from baseline). | 99 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. All leased fiber is 100 complete. All duct provided by DeKalb Fiber Optics has been received and overridden with fiber. All approved network was completed in December, 2012 (18 additional months from baseline). Additional 1.27 miles of duct and fiber will be constructed as authorized by prospective route changes. | 98 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor equipment deployment started in January, 2012 and is complete. Additional locations authorized by the prospective route changes are now being deployed. Backbone equipment deployment started in January, 2012 and all five node locations are now deployed. Fiber back haul equipment deployment was completed in 2013-Q2. Equipment deployment for all approved locations will be complete in 2013-Q3 (22 additional months from baseline). | 99 | Baseline predicted 100%.The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Testing was completed for all fiber on the approved network in December, 2012. No new fiber was constructed in 2013-Q2. Testing for 1.28 miles of additional fiber will need to be completed when that additional fiber is installed which is expected to be completed early in 2013-Q3. | 2013-08-06 10:52 | 2013-08-06 10:52 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2013 | Q3 | Q3 - 2013 | 11465 | 9580 | TRUE | 100 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use agreement and locating, maintenance and repair agreements with DeKalb Fiber Optic, LLC in place. Since January, 2011, project has been moving well showing completion percentages of 20, 29, 47, 62. 70, 75, 83, 92, 93 and 94% for the previous nine quarters. The network is 100% complete. The equipment purchase from the Northern Illinois University project was completed in 2013-Q3. Completed project at 97% of authorized budget. | 0 |  | N/A | 100 | Completed for original project scope and for additional route changes. | 100 | Previously completed within budget. | 100 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. All rights-of-way and municipal utility agreement issues needed for the project have been received. All in-kind duct and fiber provided by DeKalb Fiber Optics has been received. | 100 | Baseline predicted 100% at this point. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC in place. | 0 | N/A | 100 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. All community anchor premise equipment has been received and paid. Backbone equipment, fiber back haul equipment, wireless access points and fire walls for libraries have been received and paid. 10Gig "ring" modules have been received and paid. The purchase of redundant ring equipment was completed in 2013-Q3 and funds have been withdrawn. Equipment procurement is complete. | 100 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. All leased fiber is 100 complete. All components of the network are complete. | 100 | Baseline predicted 100%. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Community anchor equipment deployment for locations authorized by the prospective route changes is now complete. Backbone equipment deployment is complete. Fiber back haul equipment deployment is complete | 100 | Baseline predicted 100%.The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Testing is complete for the network. | 2013-12-10 11:08 | 2013-12-10 11:08 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570031 | 2010 | Q2 | Q2 - 2010 | 55 | 1287 | FALSE | 10 |  |  |  |  | 90 |  | 30 |  | 60 |  | 60 |  | 30 |  | 40 |  | 15 |  | 15 |  | 5 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2010 | Q3 | Q3 - 2010 | 321 | 1427 | TRUE | 10 | N/A | 0 | N/A | N/A | 75 | N/A | 30 | N/A | 50 | Ahead of project by 25% | 25 | N/A | 0 | N/A | 15 | N/A | 0 | N/A | 15 | N/A | 0 | N/A | 2010-11-15 16:48 | 2010-11-15 16:48 | 5491 | 5491 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2010 | Q4 | Q4 - 2010 | 1147 | 2186 | TRUE | 20 | Awaiting FONSI for project kick-off/construction to begin. | 0 |  | N/A | 75 | EA submitted. Provided additional maps to USF&W. Awaiting FONSI | 30 | The pending FONSI is the only hold up in this area from the baseline. | 50 | Awaiting FONSI for project kick-off/construction to begin. | 25 | The pending FONSI is the only hold up in this area from the baseline. | 0 | Awaiting FONSI for project kick-off/construction to begin. | 35 | Awaiting FONSI for project kick-off/construction to begin. | 0 | Awaiting FONSI for project kick-off/construction to begin. | 15 | 1064 Routers are deployed in the fact that they have been delivered (deployed) to the host community anchor for installation when FONSI complete. | 0 | Awaiting FONSI for project kick-off/construction to begin. | 2011-02-15 12:13 | 2011-02-15 12:13 | 5745 | 5745 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2011 | Q1 | Q1 - 2011 | 2117 | 2804 | TRUE | 19 | Receipt of FONSI was just awarded, so we are behind projections. We plan to be on target within the next two quarters. The % includes draw down March 29 in the amount of $13,415.25. Per GEO Fiscal Officer, this transaction was completed before close of business 03/31/2011. | 0 |  | N/A | 1 | The actual percenage of funds spent on EA is less than 1% of the total grant amount (.027%). Items remain to be resolved directly related to programmatic agreement. There is now a physical plan in place to immediately overcome this shortfall. | 60 | This completion is on track to be accomplished to complete the grant on time. The 10% lag will be overcome during the upcoming reporting period. | 85 | Rights of Way is on target at 85% completion for all towers. The remaining 15% is for rights of way directly related to CAI, which will be completed on schedule per the baseline. | 45 | As construction now commences, this number will dynamically increase and we are set to be on target within the next two quarters. | 10 | The FONSI award and PA directly related to towers is now in place. The Community Anchor Institution construction has commenced. Two of the twelve towers have site construction ongoing. We will be on target with the overall plan within the next two quarters. | 45 | This is 5% below target; however, within the next quarter we will be on target. Currently tower steel, buildings, generators, and other hardware is being coordinated, released, etc., from the respective vendors. | 5 | Although this percentage is 20% below goal, as construction began at the end of this quarter, with programmatic agreement issues being worked out, we are set to move up to target goals. | 25 | The last week of March 2011the deployment of routers has begun to the 1064 anchor tenants. Programming and installation has commenced. This number will meet targeted goals within the next two quarters. | 5 | Vendor bench testing has been completed on the tower portion of the project; hovever, testing could not commence prior to this date due to inability to physically construct. With release to begin construction, the testing will directly follow installation. | 2011-05-18 10:06 | 2011-05-18 10:06 | 5745 | 5745 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2011 | Q2 | Q2 - 2011 | 2973 | 3244 | TRUE | 37 | A very rainy late spring/early summer hindered start-up of tower construction (about 3 weeks behind schedule) and a shortage of fiber slowed the fiber build out of community anchor institutes (about 7 weeks behind schedule). A hot/dry summer is making the tower construction initiative make up for lost time. We expect that within six weeks the towers will be on schedule. Frontier found a suitable and reliable substitute vendor for the cable shortfall, and we believe that the community anchor build out will be on schedule within 90 days. | 0 | N/A | n/a | 3 | The actual percentage of funding spent on environmental remains low due to environmental invoices held up in the administrative paper flow. During quarter 3, paperwork and related invoices will be processed and paid to bring the environmental to about 50%. During quarter 4, with new potential community anchors, the observatory build out, and Historic Preservation actions complete, we will be close to 85% complete in this area. | 75 | Network design is rapidly coming to a full close and conclusion. After field testing and programming of microwave radios during August, we expect to be on schedule to complete design work by close of the calendar year. | 90 | Rights of Way for the towers continue to be on track and for the community anchors. However, until completion of the engineering for the National Radio Astronomy to WVU link is fully designed/engineered, there may be additional rights of way to be developed and contracted. Engineering for this section will be complete during 3d or 4th quarter and we should be on track by end of the calendar year to close out all rights of way. | 60 | This area improved by 15% during this quarter. As we move through the 3d and 4th quarter of 2011, we should approach 100%. This increase will be fostered by completion of engineering, memorandums of agreement/understanding, and actual progress on the overall project. | 30 | Due to vastly dryer weather, tower site preparation is rapidly progressing. As we complete engineering and begin construction of the National Radio and Astronomy Observatory to West Virginia link, we will begin site preparation for that 64 miles of fiber. Most likely we will move to approximately 65 to 70 percent by calendar year end. There will be a slowdown of preparation during middle to late winter with a dramatic increase in spring 2012. | 50 | This is 15% below budget; however, we actually ordered 19mil of microwave radios that should be invoiced in either August or September. The receipt and subsequent payment of this invoice, when coupled with other ongoing equipment purchases, will enable this area to reach goal by calendar year end. | 30 | The towers continue to progress and we will be on schedule at the next reporting period for them. However, due to the noted fiber shortage, we remain sluggish to accomplish that leg of the build out. We expect this area to dramatically improve during the balance of this construction year (an alternate fiber vendor has been identified and additional fiber is on order and on schedule). To increase this area, we are to start the National Radio Astronomy Observatory to West Virginia University build in sectors or legs as the engineering is complete. | 30 | We started distribution and deployment of the 1064 routers for the community anchors. Effective within the last 30 days, installation and programming started in earnest. Each community anchor representative assures the grant implementation team that by calendar year end, we should be near milestones for equipment deployment. | 5 | Microwave radios will be benchmarked, programmed, and tested during August. Immediately after that effort (likely mid September) we will be at or near base line in this area. | 2011-08-09 13:39 | 2011-08-09 13:39 | 7135 | 7135 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2011 | Q3 | Q3 - 2011 | 3963 | 3820 | TRUE | 39 | This is based on cost projections of actual purchase orders cut and actual towers constructed. Because fiber deployment lags, the number remains inherently low. We are diligently working with our NTIA program officer to submit and have approved a satisfactory mitigation plan to the fiber installation lag. Includes matching. | 0 | N/A | N/A | 90 | The remaining environmental assessment to be completed lies within the confines of the programmatic agreement. As the remaining Community Anchor sites are engineered, any environmental variance must be complete. We will meet the 100% of this goal when the last anchor is engineered. | 85 | This number is rapidly moving to the 100%; however, due to some issues with microwave network efforts, we lost some time. The network full design will be complete by the end of next quarter. | 90 | As the Community Anchor Institution sites are engineered, there could be additional efforts necessary. As all sites will be engineered during the next quarter, the next report will likely show this as 95% to 100%. | 90 | As the Community Anchor Institution sites are engineered, there could be additional efforts necessary. As all sites will be engineered during the next quarter, the next report will likely show this as 95% to 100%. Please note that all tower sites are complete. | 90 | As the Community Anchor Institution sites are engineered, there could be additional efforts necessary. As all sites will be engineered during the next quarter, the next report will likely show this as 95% to 100%. Please note that all tower sites are complete. | 90 | Most equipment has been ordered, but not yet received. Equipment procurement will be at 95% to 100% next quarter. | 45 | This percentage shows a change due to reassessing the overall project build and subsequent mitigation plan. It includes the tower portion, the West Virginia University to National Radio Observatory, and fiber portions and is better calculated on actual installation coupled with actual expenditures. This is indicative by the overall change as noted. | 55 | All routers have been delivered to the owning community anchor; however, only 200 are installed. Five towers are complete, but the radios are being installed and will not be fully installed for about six months. We will complete this portion of the project. | 40 | Community anchor sites are being tested as installed and the tower suitability is being tested; however, until equipment is installed and functional, it cannot be fully tested. Because the fiber installation is lacking so in the testing percentage. As the fiber build out jump starts and comes to fruition, so will the testing. | 2011-11-10 14:20 | 2011-11-10 14:20 | 7135 | 7135 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2011 | Q4 | Q4 - 2011 | 5193 | 4861 | TRUE | 47 | As with previous quarters, this amount includes application of in-kind and cash matches. It is based on actual towers constructed. However, five of the ninety-five existing towers need replaced due to structural load bearing capabilities. These five replacements effectively caused a lower than anticipated percentage of completion. | 0 | N/A | N/A | 94 | At 94% the Environmental Assessment process continues to progress. As noted in 2a, the five replacement towers have an inherent amount of environmental effort, without which, the environmental percentage would be higher. We will meet the 100% baseline when these replacement towers are engineered into the environmental process and when the last Community Anchor is engineered. The tower replacement environmental process may go into the 3d quarter of 2012 and the Community Anchor engineering should be complete 2nd quarter of 2012. | 95 | The remaining Community Anchor Institutes are being engineered and should be complete within the next several weeks. Immediately after this process is fully complete, we expect the network design to be at 100%. | 95 | As the remaining Community Anchor Institutes are engineered, any further rights of way requirements will be identified. As noted in 2c, this process is rapidly coming to fruition. Rights of way should be at approximately 100% during the next quarter. | 95 | As the remaining Community Anchor Institutes are engineered, any further construction permits will be identified. As noted in 2c, this process is rapidly coming to fruition. This area should be at approximately 100% during the next quarter. | 92 | Site preparation is commensurate with the number of towers complete and the number of Community Anchors to be built. As the engineering came to fruition, the sites were identified and the preparation was complete. The five (5) replacement towers will have minimal associated preparation and we should be at 98% next quarter. | 95 | Most equipment has been ordered, but not yet received. Equipment procurement should be at approximately 98% next quarter. | 50 | This percentage remains sluggish, but is rapidly moving to a mark commensurate with the base line. The State of WV, specifically Frontier Communications, developed a full mitigation plan that was subsequently approved by NTIA. Frontier is ahead of mitigation plan schedule. As this trend continues we are poised to meet the 100% goal by February 2013 as specified in the NOFA. | 60 | The remaining microwave radios will be received during January â€“ March 2012 and deployed to the specified tower sites. The points of contact for their respective Community Anchors are currently engaged in router deployment. This percentage should increase to approximately 80% during the next quarter. | 45 | Community Anchor sites are being tested as installed and the tower suitability is being tested. Until the full amount of equipment is installed and functional, it will not/ cannot be fully tested. As the fiber installation increases tempo, the percentage will dramatically increase. | 2012-02-22 15:14 | 2012-02-22 15:14 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2012 | Q1 | Q1 - 2012 | 6319 | 5762 | TRUE | 54 | This quarterâ€™s financial report includes application of in-kind and cash matches. As we receive approval for the five replacement towers, we will order materials (steel) and begin construction. As this comes to fruition, and the balance of the microwave radios are received, the percent complete will increase by 10+%/ As we continue advancement of the overall Frontier mitigation plan this number will increase another 5+%. | 0 | N/A | N/A | 97 | The environmental assessment process continues to make progress. The five replacement towers have cleared state and federal agency reviews and await the EHP pre-screening FONSI approval process at NTIA prior to ordering steel and equipment. We will meet the 100% baseline when the CAI is engineered and approved by the state agencies per the original EA. The CAI engineering may go into the 3rd quarter of 2012. | 98 | The remaining community anchor institutions are being engineered and should be complete within the next several weeks. Immediately after this process is complete we will be at 100% of the current approved anchors. | 98 | As we complete the compliance process we will move this area to 100%. | 95 | Storm water construction inspections for 7 of the 12 towers (58%) has been completed. The remaining 5 tower inspections (0%) will be conducted when the towers are stacked. Then the WVDEP permit can be closed. The 5 replacement towers (0%) will not involve new ground disturbance and do not require a storm water construction permit. Inspections will be conducted at these 5 replacement towers as construction progresses. Construction inspections for the Community Anchors (0%) will begin in the 2nd quarter 2012 and will continue until end of January 2013. Inspections to close out the WVDEP permits for applicable counties(CIA - 0%) will progress as Frontier completes the construction activities in each county. The last inspections are anticipated to be in January 2013. | 98 | Per the existing approved sites, we are at 98% completion. The remaining 2% reflects any preparation necessary for the replacement sites and the recently approved WVNET initiative. | 95 | Most equipment has been ordered, but not received. The remaining 5% reflects any preparation necessary for the WVNET and WVU/NRAO initiative. | 60 | Frontier continues to move ahead of the mitigation plan. We are poised to meet the February 2013 completion projection. | 75 | Router deployment to CAI locations is on-going and on-track. | 60 | As CAI fiber terminations complete, testing is verified. | 2012-05-29 12:15 | 2012-05-29 12:15 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2012 | Q2 | Q2 - 2012 | 6997 | 6126 | TRUE | 56 | This area remains short of baseline; however, we have the following potential commitments in the job flow currently (but not limited to): $26M Frontier Communications, $3.5M WVNet, $6.3M NRAO, $9M for microwave radios. We anticipate some residual funding from the grant which will be forecasted and a revised budget submitted by mid August. The baseline shortfall was generated by a sluggish start-up of Fiber Build Out, (compensated by Frontier mitigation plan), slowness of Environmental Planning Processes (compensated by construction and make up). | 0 | N/A | N/A | 97 | At 97%, the Environmental Assessment (EA) process continues to make progress. The five replacement towers await the EHP pre-screening FONSI approval process at NTIA prior to ordering steel and equipment. We will meet the 100% baseline when the last Community Anchor is engineered and approved by the state agencies per the original EA. The Community Anchor engineering may go into the 3rd quarter of 2012. EA work will begin once CAI replacement sites are engineered. Also, facility build-out (FBO) sites started entering the EA process in the 2nd quarter. | 98 | This area remains at 98% complete. It will not reach100% until we are closer to the end of the overall project. The remaining 2% leaves room for any unknown issues that might surface. | 98 | This area remains at 98% complete. It will not reach 100% until we are closer to the end of the overall project. The remaining 2% leaves room for any unknown issues that might surface. There remain a few problems with agreements with a few utility companies for use of their utility poles. | 96 | Storm water construction inspections for 7 of the 12 towers (58%) has been completed. The remaining five (5) tower inspections (0%) will be conducted when the towers are stacked. Then the WVDEP permit can be closed. Construction inspections on buried segments for the Community Anchors (22 inspections - 6%) began in the 2nd quarter 2012 and will continue until February 2013. Inspections to close out the WVDEP permits (notice of termination - NOT) for applicable counties (4/30 counties - 13%) will progress as Frontier and FBO construction activities are completed in each county. The last inspections are anticipated to be in February 2013. | 98 | The 2% remains for any unforeseen site preparation work that may occur as we complete the tower portion of the grant. | 95 | Microwave Radios and CAI Routers have been ordered and shipped to WV. The WVNet equipment has been ordered. The remaining 5% reflects the upcoming purchases. | 65 | Frontier continues to move forward with their mitigation plan; however, the major wind storm affecting West Virginia caused them to lose approximately one month production. | 75 | This reflects a variance of 20% from the baseline. This difference will be made up during the upcoming quarter. However, as NTIA receives and approves the WV request for modification to the overall Community Anchor list, this % will be slow to change. WV will be at 100% by the end of the grant. | 60 | As CAI locations are completed, this % will increase. As we added the WVNet equipment and network during the last quarter, there was little change in the overall %. | 2012-08-10 10:00 | 2012-08-10 10:00 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2012 | Q3 | Q3 - 2012 | 7973 | 6693 | TRUE | 64 | The 64% is includes the Match portion of the grant. This area remains short of baseline; however, we have the following potential commitments in the job flow currently (but not limited to): $20M Frontier Communications, $3.5M WVNet, $6.3M NRAO, and $9M for microwave radios. We anticipate some residual funding from the grant which will be forecasted and a revised budget submitted by mid November. The baseline shortfall was generated by a sluggish start-up of Fiber Build Out, (compensated by Frontier mitigation plan), slowness of Environmental Planning Processes (compensated by construction and make up). | 0 | N/A | N/A | 98 | The Environmental Assessment (EA) process continues to make progress. The five replacement towers received FONSI approval from NTIA with steel and equipment ordered. We will meet the 100% baseline when the last Community Anchor is engineered and approved by the state agencies per the original EA. The Community Anchor engineering may go into the 4th quarter of 2012. EA work began on the 2nd CAI replacement sites including engineering and EA process. Facility build-out (FBO) sites continues to progress through the EA process in the 3rd quarter. | 98 | This remains at 98% complete. There are two additional CAIs which require network engineering and design. Once completed, this should finalize the fiber design work for the project. | 98 | This remains at 98% complete. There are only some minor issues for use of utility poles still under discussion. This should be completed before the end of the project. | 97 | The state-wide power outage in early July 2012 caused the inspection process to be behind. Storm water construction inspections for towers as follows: 3 complete; 6 inspected with vegetation needs; 3 under construction; 5 replacement towers not started. The towers will be re-inspected once the vegetation is at 75-80%. Then the WVDEP permit can be closed. Construction inspections on buried segments for the Community Anchors (additional 12 inspections - 3%) continued in the 3rd quarter 2012 and will continue until February 2013. Eight counties (Jefferson, Pendleton, Hancock, Doddridge, Braxton, Calhoun, Wirt, and Mason) are BTOP fiber and EA-complete (8/54 - 15%). Inspections to close out the WVDEP permits (notice of termination - NOT) for applicable counties (1/30 counties closed, or 3%, with 6 counties in the close-out process, or 20%) will progress as Frontier and FBO construction activities are completed in each county. The last inspections will be in 2013. | 98 | This section will remain at 98% until completion of the five replacement towers. | 95 | This remains at 95%. The NRAO/WVU network equipment is currently out to bid and should be finalized in the last quarter. | 85 | As noted in 2f, 5 replacement towers have been approved. This percentage should increase by approximately 5% during the next quarter; however, it will not be at 100% until the replacement towers are functional. | 80 | With the approval of the Replacement/Additional CAI list, all equipment deployment should be completed by end of the project. | 70 | As CAI's locations complete, the % will continue to increase. This will be 100% by the end of the project. | 2012-11-20 11:58 | 2012-11-20 11:58 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2012 | Q4 | Q4 - 2012 | 8979 | 7758 | TRUE | 70 | This 70% includes the Match portion of the Grant. This area remains short of baseline; however we have the following partial commitments in the job flow: multiple FTR invoices, equipment purchases, & payroll for DHHR and Slait consulting. The baseline shortfall was generated by a sluggish start-up of Fiber Build out (compensated by Frontier Mitigation Plan), slowness of Environmental Planning Processes (compensated by construction and make up), and Super Storm Sandy. | 0 | N/A | N/A | 99 | The Environmental Assessment (EA) process continues to make progress. We will meet the 100% baseline when the last Community Anchor is engineered and approved by the state agencies per the EA. | 99 | Super Storm Sandy caused some overall project hindrances effectively delaying the final design. | 99 | As the five replacement towers are developed and constructed, and the last CAIs are complete, this effort will move to 100%. Most likely this will occur 2nd quarter of 2013. | 98 | The state-wide power outage in July continues to have impacts on the inspection process. The last inspections will be during 2nd quarter 2013. | 98 | NRAO/WVU build continues to progress and the CAI build is rapidly coming to closure; however, Super Storm Sandy inhibited efforts while causing some significant damages. By the end of the first quarter 2013, this percentage should move to about 95%. | 95 | The equipment order for NRAO/WVU build will be complete during January/February 2013 which will move the equipment percentage to approximately 98%. | 90 | The last original tower will be constructed during first quarter 2013 and the five replacement towers will begin the construction/completion phase. Coupled with the completion of the NRAO link and Community Anchor builds, this percentage will move to 95 â€“ 98 percent during the next quarter. | 85 | Inhibitor one includes the purchase of the NRAO equipment which has been ordered and will be deployed shortly after receipt. Inhibitor two includes deployment of WV Net equipment which has been received and will be installed during first quarter 2013. The balance of the percentage deficit hinges on completion of the router deployments. By the end of next quarter this percentage should move to approximately 95%. | 85 | As WVNet, NRAO, CAIs, and wireless come to completion this percentage will quickly move to approximately 90 â€“ 95 percent. We expect this next quarter. | 2013-02-26 14:50 | 2013-02-26 14:50 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2013 | Q1 | Q1 - 2013 | 9933 | 8510 | TRUE | 72 | We have drawn down a total of $82,438,432.65 for the grant execution. Match portion is $33,500,000.00. This brings our Grant expenditure total to $115,938,432.65. Although this indicator is based on expenditures, only approximately 7 Community Anchor Institutes remain for fiber build-out, the National Radio Astronomy Observatory to WVU link is nearly complete, and the wireless portion is rapidly coming to conclusion. Router deployment is rapidly coming to a close. Invoicing is inherently slower than actual build. | 0 | N/A | N/A | 99 | The Environmental Assessment (EA) process continues to make significant process. We will meet the 100% baseline as we complete the close out of tower and fiber sites. | 99 | There are three (3) CAI locations and two (2) sections of the NRAO/WVU fiber build (Super Storm Sandy repair) awaiting EA process. Then, network design will be at 100 percent. | 99 | On track to complete 2nd quarter of 2013. | 98 | On track to complete 2nd quarter of 2013. | 98 | Super Storm Sandy inhibited efforts while causing some significant damages. Significant is the last portion of fiber build for NRAO/WVU. We are on track to complete 2nd quarter of 2013. | 95 | We experienced purchasing delays in acquiring the NRAO/WVU equipment. | 92 | Five CAI segments, one new tower, and five replacement towers still require efforts to complete the network build. | 90 | The balance of the percentage deficit hinges on completion of the router deployments. By the end of next quarter this percentage should move to approximately 99%. | 90 | By 2nd quarter of 2013, this percentage should reflect 98%. | 2013-05-28 14:15 | 2013-05-28 14:15 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2013 | Q2 | Q2 - 2013 | 10801 | 9073 | TRUE | 75 | The invoice flow tempo (during the last several weeks) has improved. We work with the Governorâ€™s Executive Office Financial Staff on a daily basis and will continue to see increases on both the number of invoices processed and paid. $87,462,098.42 OF $126,323,296. Including match portion of $33,500,000 for a total of $120,962,098.42 OF $159,823,296. | 0 | N/A | N/A | 99 | Environmental Progress remains at 99%. We will hit the 100% mark as the grant closes, especially the completion of the tower and Community Anchor Institute Sites. | 100 | Network Design for all portions of the grant is 100% complete. | 99 | Rights of Way efforts of the grant are 99% complete. There remains one tower access road at Workman that may require a right of way. | 99 | Construction Permits of the grant are 100% complete. There remains one tower (Workman) that may require construction permits to reroute an access road. | 99 | There are three (3) CAI's awaiting Facility Build-Out (FBO) completion on premise. Once completed, Frontier will terminate last three fiber installs. Scheduled for completion in July 2013. | 95 | NRAO/WVU equipment purchase is still pending award. Should NTIA approve a GigaPop project there will be additional equipment to order and install. | 99 | Awaiting completion on one of the original towers. CAI portion is completed. Wireless is pending construction of the five replacement towers. | 95 | There are forty (40) routers pending deployment. This will be completed by Sept. 2013. Wireless equipment deployment will complete as the replacement towers are fully constructed. | 99 | There are three (3) CAI's to finalize for fiber installation. This will be completed in July 2013. Final testing for the wireless portion will be completed as the wireless closes construction. | 2013-08-29 09:08 | 2013-08-29 09:08 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2013 | Q3 | Q3 - 2013 | 11343 | 9472 | TRUE | 78 | As of 30 September 2013 we have drawn down a total of $90,515,463.56 for the grant execution. At the end of September 2013, Frontier submitted 100% of their fiber invoices which will push the totals significantly by next quarter. The invoices were submitted and are now in the payment process. Remaining to pay Frontier is Approximately $25,000,000. As of 30 September 2013 by grant definition, 632 community anchor institutes are complete with new construction (fiber & router). 21 of the 632 were accounted for in the 3rd quarter. 460 are complete with improved service. 10 of the 460 were accounted for in the 3rd quarter. A total of 1092 community anchors considered complete. 88 routers are left to be distributed. This will bring our total to 1180 sites. The current total numbers for Facility Build Outs (FBO) are 324. Of the 324 there are 324 complete with zero FBO remaining. Total BTOP fiber mileage to date is 675.2 miles which completes BTOP Fiber Miles. On the wire | 0 | N/A | N/A | 99 | Progress is still at 99 percent with site inspections for fiber (CAIs) and wireless (towers) ongoing. Proper documentation will be submitted to WVDEP for permit closeout during 4Q 2013. | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 95 | Should NTIA approve a GigaPop project there will be additional equipment to order and install. | 100 | Completed | 95 | Should NTIA approve a GigaPop project there will be additional equipment to order and install. | 99 | Fiber portion 100%; remaining is final wireless testing. | 2013-11-22 09:21 | 2013-11-22 09:21 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2013 | Q4 | Q4 - 2013 | 12365 | 10547 | TRUE | 100 | The construction associated with the WV BTOP grant is 100% complete. We have drawn down a total of $124,374,998.75 for the grant execution. Including the Match portion this brings our total to $157,874,998.75 We completed 675.2 fiber miles to 644 physical locations of which 85.2 miles were completed in the West Virginia University (WVU) to National Radio Astronomy Observatory (NRAO). Noteworthy is the $1M partnership funds that WVU pledged to this continuing effort. All of the 324 New Facility Build Out (FBO) are complete. All WV K12 schools have fiber available. Some examples of dramatic improvements resultant from this construction include: Southside K-8 (new speed/cost â€“ 100 Mbps@$1505 mo: $15/Mbps); Woodrow Wilson (new speed/cost â€“ 500 Mbps @$2500 mo:$5/Mbps); New River Health 500 Mpbs@$200 mo: $20 Mbps) and NRAO 10 Gbps@ $5000 mo: $0.50 Mbps). Each of these examples plus many more reflect greater service at significant unit reduction in cost. Fiber and or New routers | 0 | N/A | N/A | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 2014-07-30 13:23 | 2014-07-30 13:23 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570032 | 2010 | Q2 | Q2 - 2010 | 56 | 1324 | FALSE | 10 |  | 0 |  |  | 100 |  | 100 |  | 0 |  | 30 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | 2010 | Q3 | Q3 - 2010 | 361 | 1447 | TRUE | 7 | Resolution of the environmental issues took longer than expected; the problem relates to resolution of some Section 106 issues. The corrective action is to resolve the differences between the NTIA and the State historic preservation office. Once construction can begin we expect to catch up. We have selected several contractors and are awaiting completion of the environmental assessment to contract and begin construction. | 0 | NONE | No deviation from expected progress | 85 | In the course of doing the environmental assessment, some properties with potential cultural significance were identified. The common method for dealing with these issues, referred to as section 106 questions, is to enter into an agreement between the applicant, the federal agency, and the state historic preservation office. This has been delayed because of differences in expectations about the form of the agreement between NTIA and SHPO. This will be resolved by getting an agreement between SHPO and NTIA. | 85 | The need for an archeological review of some excavations (related to the delayed environmental assessment) delayed completion of the network design. This has been resolved and the network design will be completed this quarter. | 0 | Progress has been delayed by the review of the proposed methodology for securing the federal interest and thus the ownership of the required right of way permissions. This deviation will be corrected by resolution of the ownership question with NTIA, or in the alternative, by acquisition of the necessary permissions to initiate construction in the rights of way. | 10 | The number of actual construction permits required will be determined by the resolution of the ownership of the fibers. The baseline projectin was made based on earlier discussions with NTIA which were understood to indicate acceptance of the proposal to vest ownership of the installed fiber in the loca jurisdictions where the fiber will be installed. Whenit was learned that this question remained open, the estimates of progress were revised downward. The project will get back on track by resolving the issue of ownership with NTIA, or in the alternative, by seeking otherwise unnecessary construction permits. | 0 | No deviation from expected progress | 0 | A portion of the design of the system was recalculated, changing the number and type of certain equipment necessary. This design has been chosen and equipment procurement can proceed. | 0 | The delay in completing the environmental assessment and the delay in resolving the ownership question have delayed the initiation of the network build. LCOG has proceeded with as many preliminary steps as possible, so that, when the environmental assessment is completed, we will be able to catch up quickly. | 0 | The baseline projections were too optimistic. The need for a more detailed design cause delays in the selection of equipment and thus in the deployment of the equipment. LCOG will be able to catch up on this portion of the project as it moves forward with other aspects of the project. | 0 | No deviation from expected progress | 2010-11-19 16:37 | 2010-11-19 16:37 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2010 | Q4 | Q4 - 2010 | 1095 | 2137 | TRUE | 8 | Because of the need for tribal compliance, resolution of the historical properties section of the environmental assessment took much longer than expected. That issue has been resolved. We are working to get back on schedule and hope to start construction very soon. |  |  | NA | 90 | In the course of doing the enviornmental assessment, some properties with the potential of cultual significance were identified. It took significantly longer than expected to get tribal concurrance on the propsed method of resolving the cultual questions. That tribal concurrence has finally been achieved. The environmental assessment is nearly completed. The final submissions were made in January. | 90 | The design work is completed for most of the construction. Bid documents are being prepared so that construction can start soon after the environmental assessment is completed. Final design work will be accomplished with the successful bidders. | 10 | Progress has been delayed by the need to finish the environmental work. Initial discussions have begun and it is anticipated that once cleared for construction, progress can be made quickly on this aspect of the project. | 10 | Applications for the permits have been started. This portion of the project will proceed more quickly when the enviornmental assessment is completed. | 0 | This work cannot begin until the environmental assessment is completed. | 5 | Some of the equipment specifications have been determined. The regulations governing equipment acquisition have been clarified so that procurement can move forward. | 0 | The delay in resolving the ownership issue has caused delays in this aspect of the project. Now that issue is resolved, LCOG has begun the final acquisition steps, so that in the next quarter LCOG will be able to secure nearly all of the network elements. | 0 | The baseline projections were too optimistic. Deployment will follow construction, which has been delayed until the environmental assessment is completed. | 0 | This is not out of schedule | 2011-02-11 16:46 | 2011-02-11 16:46 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2011 | Q1 | Q1 - 2011 | 1951 | 2721 | TRUE | 4 | The Environmental Assessment took much longer than anticipated in the original baseline plan. We expect that we will be able to work back to the planned progress over the next year. | 0 |  | NA | 100 | This aspect of the project has been completed. | 90 | The design is completed except for the final refinements that will be done during construction to respond to changed circumstances in the field. | 20 | The application process has been initiated. All necessary rights of way have been obtained in two cities. | 15 | Applications have been submitted in several cities. With the Environmental Assessment submitted, this portion of the project can begin to move quickly. | 0 | This portionof theproject has been waiting for the completionof theEnvironmental Assessment. With the selection of some of the construction contractors, this work can commence. | 5 | Some of the equipment specifications have been determined. The procurement regulations have been clarified so that acquisition can move forward. | 10 | The terms for the IRUs for the match have been settled. Execution of the IRUs is expected this quarter. This will allow the completion of more than half of the Network Build. | 0 | Deployment will follow construction. With construction set to begin in Q2 of 2011, equipment deployment may start in Q3 or Q4. | 0 | This is not out of schedule. | 2011-05-11 20:18 | 2011-05-11 20:18 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2011 | Q2 | Q2 - 2011 | 3241 | 3383 | TRUE | 22 | The Environmental Assessment took much longer than anticipated in the original baseline plan. We expect that we will be able to work back to the planned progress over the next year. | 0 |  | NA | 100 | Completed | 90 | The design is completed except for the final refinements that will be done during construction to respond to changed circumstances in the field. | 30 | This is proceeding on track according to the revised schedule after the environmental assessment was completed. | 20 | Applications have been submitted in several cities. With the Environmental Assessment submitted, this portion of the project can begin to move quickly. | 5 | This portion of the project has been waiting for the completion of the Environmental Assessment. With the selection of some of the construction contractors, this work can commence. | 5 | Eqipment procurment will begin this quarter and is expected to proceed rapidly. | 40 | The IRUs have been approved, and the most significant one has been completed. We expect to catch up to the baseline projections sometime in the second quarter 2012. | 0 | This is proceeding on track according to the revised schedule after the environmental assessment was completed. | 10 | This is proceeding on track according to the revised schedule after the environmental assessment was completed. | 2011-08-19 16:12 | 2011-08-19 16:12 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2011 | Q3 | Q3 - 2011 | 4257 | 3979 | TRUE | 24 | This is beginning to get back on track after the loss of schedule due to the environmental review. | 0 |  | NA | 100 | Completed | 92 | This is beginning to get back on track after the loss of schedule due to the environmental review. We will be hiring design/build contractors to catch up. Expect to regain baseline 2nd quarter 2012. | 60 | This is beginning to get back on track after the loss of schedule due to the environmental review. | 60 | This is beginning to get back on track after the loss of schedule due to the environmental review. | 15 | This is beginning to get back on track after the loss of schedule due to the environmental review. We will be hiring design/build contractors to catch up. Expect to regain baseline 2nd quarter 2012. | 10 | This is beginning to get back on track after the loss of schedule due to the environmental review. We have begun to work with our providers to purchase equipment early to avoid last minute delays. We expect to regain the baseline second quarter 2012. | 50 | One IRU, representing approximately fifty percent of the total route miles has been secured. A second IRU representing another ten percent is being signed as the quarter ends. Expect to be back to baseline by year end 2011. | 0 | Deployment must wait at least until construction has begun. We hope to get deployment to be coincidental with construction, so that there will be no delays in the initiation of service. We expect to be back to the baseline by end of second quarter 2012. | 15 | This is beginning to get back on track after the loss of schedule due to the environmental review. This should be back to the baseline progress in the second quarter of 2012. | 2011-11-23 13:44 | 2011-11-23 13:56 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2011 | Q4 | Q4 - 2011 | 5101 | 4771 | TRUE | 35 | This is getting back to the originally projected schedule, after a loss of time due to the extended environmental review. We expect to be back to the original projections sometime in third quarter 2012 | 0 |  | NA | 100 | An amended environmental review will be required due to route changes. | 95 | The only remaining issue has to do with pole attachements and the demands of the utilities for make ready. | 75 | This continues to move forward ahead of construction. We expect to be back to the baseline projections second quarter 2012. | 75 | All permits needed have been identified and applied for. We expect to be back to the baseline projections second quarter 2012. | 55 | This is getting back to the originally projected schedule, after a loss of time due to the extended environmental review. We expect to be back to the baseline projections second quarter 2012. | 30 | This is getting back to the originally projected schedule, after a loss of time due to the extended environmental review. We expect to be back to the baseline projections second quarter 2012. | 75 | All IRUs have been secured. Construction is moving forward quickly. We expect to be back to the baseline projections third quarter 2012. | 10 | Deployment will follow construction. Some deployments have been carried out as construction is finished at individual sites. We expect to be back to the baseline projections third quarter 2012. | 20 | This is getting back to the originally projected schedule, after a loss of time due to the extended environmental review. We expect to be back to the baseline projections third quarter 2012. | 2012-02-17 14:47 | 2012-02-17 14:47 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2012 | Q1 | Q1 - 2012 | 5955 | 5577 | TRUE | 58 | This is getting back to the originally projected schedule, after a loss of time due to the extended environmental review. We expect to be back to the original projections sometime in third quarter 2012. | 0 |  | NA | 100 | We have submitted an amended environmental review to takeinto account several route changes. | 95 | the only remaining issues have to do with pole attachment agreements and the make ready work that may be required. We expect completion 2nd quarter 2012. | 80 | We have obtained nearly all the franchises required. We expect completion 2nd quarter 2012. | 75 | All permits needed have been identified and applied for. We expect to be back to the baseline projections second quarter 2012. | 60 | This is getting back to the originally projected schedule, after a loss of time due to the extended environmental review. We expect to be back to the baseline projections second quarter 2012. | 55 | This is getting back to the originally projected schedule, after a loss of time due to the extended environmental review. We expect to be back to the baseline projections second quarter 2012. | 80 | All IRUs have been secured. Construction is moving forward quickly. We expect to be back to the baseline projections third quarter 2012. | 20 | Deployment will follow construction. Some deployments have been carried out as construction is finished at individual sites. We expect to be back to the baseline projections third quarter 2012. | 35 | This is getting back to the originally projected schedule, after a loss of time due to the extended environmental review. We expect to be back to the baseline projections third quarter 2012. | 2012-05-08 11:05 | 2012-05-08 11:05 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2012 | Q2 | Q2 - 2012 | 7275 | 6265 | TRUE | 68 | This is getting back to the originally projected schedule, after a loss of time due to the extended environmental review. We expect to be back to the original projections sometime in third quarter 2012. | 0 |  | NA | 80 | The first environmental review has been completed. A second environmental review was necessitated by the route changes requested. This is progressing but is not complete yet. | 100 | This is completed, including the route changes. | 85 | Additional permits and franchises have been obtained, there are only a few outstanding. | 80 | Additional permits have been obtained. Completin is expected this quarter. | 80 | This is nearing completion. All site prep work should be completed early in the third quarter 2012. | 60 | We are trying to keep expenditures in line. To be sure that we do not overspend, we are delaying some equipment purchases to deal with some cost changes in the network construction. | 85 | Construction continues. Environmental issues - especailly the review of route changes has delayed us again. We expect to pick up the pace and get back to the original schedule in the third quarter 2012. | 30 | We have begun deployment in places where construction is finished. This will pick up in the third quarter. | 45 | This continues to pick up. We expect to be on schedule in the third quarter of 2012. | 2012-08-29 15:09 | 2012-08-29 15:09 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2012 | Q3 | Q3 - 2012 | 7933 | 6671 | TRUE | 75 | We are now nearly back to the original schedule after delays caused by extensive environmental review. | 0 |  | NA | 100 | This is on schedule. | 100 | This is on schedule. | 95 | Permissions to work has been obtained for the entire route. There is one remaining franchise to obtain. | 100 | This is on schedule. | 90 | This is nearing completion. | 70 | Now that we have a better idea of the rest of the budget, we will begin to do more equipment procurement. | 90 | This is getting back on schedule. | 40 | As constructin is completed, we are deploying more equipment. This should be back on schedule in the fourth quarter. | 50 | This continues to catch up. As network elements come on line, the testing is done immediately thereafter. | 2012-11-16 16:46 | 2012-11-16 16:46 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2012 | Q4 | Q4 - 2012 | 8709 | 7515 | TRUE | 81 | We are now nearly back to the original schedule. | 0 |  | NA | 100 | Some additional environmental review will be necessary for one new site, but it is minimal. | 100 | On schedule | 95 | One of the new sites has some additional right-of-way to acquire, so even though we made progress this should not be considered complete. | 100 | Some additional work may be required with some new sites added, but it is very small.. | 90 | This would have been complete except for the new sites added. | 75 | This has been delayed while we were completing construction. We expect to get back on schedule within the next two or three months | 90 | The addition of some new sites keeps this at the same level even though progress has been made. | 50 | This has been delayed by the need to complete construction before beginning final equipment acquisition and deployment. We expect to be back on schedule this quarter. | 50 | This continues to catch up. As network elements come on line, the testing is done immediately thereafter. | 2013-02-11 16:54 | 2013-02-11 16:54 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2013 | Q1 | Q1 - 2013 | 10031 | 8566 | TRUE | 86 | The final equipment purchases have been held back to make certain that the budget comes in within plans. | 0 |  | NA | 100 | According to the most recent conditional approval of the environmental assessment there is one site remaining needing action. That action is underway. | 100 | Completed | 99 | One right of way on a newly approved segment is being negotiated. | 100 | Completed | 100 | Completed | 80 | Equipment purchases will be completed this quarter. | 95 | Only the newly approved elements are not completed. | 70 | Equipment deployment will be completed this quarter. | 85 | This will be completed this quarter. | 2013-05-31 15:45 | 2013-05-31 15:45 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2013 | Q2 | Q2 - 2013 | 10823 | 9084 | TRUE | 94 | The final equipment purchases have been held back to make certain that the budget comes in within the original plan. | 0 |  | NA | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 85 | Equipment purchases will be completed next quarter | 95 | Only the newly approved elements are not complete. They will be completed in July. | 70 | Equipment deployment will be completed in July. Delays in equipment delivery limited progress last quarter. | 90 | This will be completed in July. | 2013-08-30 14:20 | 2013-08-30 14:20 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2013 | Q3 | Q3 - 2013 | 12027 | 10191 | TRUE | 100 | Completed | 0 | NA | NA | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2014-04-08 15:49 | 2014-04-08 15:49 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570033 | 2010 | Q2 | Q2 - 2010 | 57 | 1332 | FALSE | 7 |  |  |  |  | 100 |  | 50 |  | 30 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2010 | Q3 | Q3 - 2010 | 409 | 1471 | TRUE | 7 | No variance from baseline. | 0 | Administration and Project Management (18%) Federal Grant Expenditures (3%) | No variance from baseline. Variance of 4% because of the transmittal and approval of a reprogram-rebudget request in the SAC budget, network design verification and delay in start construction activities since EA-FONSI have not been completed because of SHPO delay. | 85 | Variance of 15% due to needed update of the network design (Ex. spectrum, site locations and commercial tower availability). Also as a critical factor for variance is the time that the State Historic Preservation Office (SHPO) has taken to issue comments. | 50 | No variance from baseline. | 30 | No variance from baseline. | 0 | Variance of 20% due to needed update of the network design (Ex. spectrum, site locations and commercial tower availability). Also as a critical factor for variance is the time that the State Historic Preservation Office (SHPO) has taken to issue comments. | 0 | Variance of 5% due to needed update of the network design (Ex. spectrum, site locations and commercial tower availability). Also as a critical factor for variance is the time that the State Historic Preservation Office (SHPO) has taken to issue comments. | 0 | No variance from baseline. | 0 | No variance from baseline. | 0 | No variance from baseline. | 0 | No variance from baseline. | 2010-11-24 07:07 | 2010-11-24 07:07 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2010 | Q4 | Q4 - 2010 | 1309 | 2336 | TRUE | 4 | Variance of 7% process for completion of EA "Environmental Assessment" held up. During the quarter received Environmental Assessment, FONSI approval (Finding of No Significant Impact ) | 0 | Administration and Project Management (17%) Federal Grant Expenditures (4.1%) | Variance of 10% due to delays in EA-FONSI completion Variance of 22.9% due to delay in completing EA "Environmental Assessment". | 100 | No variance from baseline. | 100 | No variance from baseline. | 25 | Variance of 25% Due to network redesign | 5 | Variance of 45% due to delay in completing EA "Environmental Assessment". | 0 | Variance of 20% due to delay in completing EA "Environmental Assessment". | 0 | Variance of 5% due to delay in completing EA "Environmental Assessment". | 0 | Variance of 5% due to delay in completing EA "Environmental Assessment". | 0 | Variance of 5% due to delay in completing EA "Environmental Assessment". | 0 | No variance from baseline. | 2011-02-22 15:58 | 2011-02-22 15:58 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2011 | Q1 | Q1 - 2011 | 1985 | 2738 | TRUE | 4 | Time to complete network design update and EA " Environmental Assessment". Currently RFP "Request for Proposals", process in full cycle with three RFP's being worked on in the quarter. | 27 | Administrative Project Management 27% | NOTE: For the Q1 report we revised the milestone percentages to reflect the actual expenditures in the line items/categories. Our prior reports had been based upon activities not cash expenditures. We are very involved in processing Request for Proposals which have required a lot of preparation, we are now executing the RFP's along a strategy of quadrant priorities which will ensure we meet the expenditures guidelines. | 88 | Received FONSI approval (Finding of No Significant Impact) received on Nov 23, 2010. The contract for the EA Environmental Assessment was made with a small portion of the funds allocated to ongoing support during the twelve months following the delivery of the EA report. In this way we have eliminated the need for additional contracts for the ongoing support in this critical area. | 100 | No variance. Network redesign update completed | 0 | Due to delay in completing network redesign update and EA process. Signed contracts for land lease for new build towers sites. Received draft leasing contract or letter of intent for all existing tower sites. | 0 | Delay in completing network redesign update and EA process. Published Request for Proposal evaluated proposals, selected entity, established contract and initiated work. | 0 | Delay in completing network redesign update and Environmental Assessment "EA" process. Published Request for Proposal for Site Preparation of existing towers in state newspaper. Held meeting with over 50 interested companies. We initially underestimated the time it would take to construct new towers and the time to process the RFPâ€™s for construction permits. Our project planning activities and RFPâ€™s activities currently has the first towers expenditures completed in Q1 2012. | 1 | Delay in completing network redesign update and EA process. Completed Draft of Request for Proposal for acquisition of Telecom equipment ( Microwave and Wimax). Initiated FCC licencing agreements for all Point to Point links. | 0 | Delay in completing network redesign update and EA process. | 0 | Delay in completing network redesign update and EA process. | 0 | No variance from baseline. | 2011-05-12 16:48 | 2011-05-12 16:48 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2011 | Q2 | Q2 - 2011 | 3393 | 3460 | TRUE | 8 | Time to complete network design update and EA " Environmental Assessment". Currently RFP "Request for Proposals", process in full cycle with three RFP's being evaluated and awarded . | 41 | Administrative Project Management 41% | We have completed 3 of 4 major RFP's, Request for Proposals which require a lot of preparation, we are now executing the RFP's along a strategy of quadrant priorities which will ensure we meet the expenditures guidelines. | 91 | Received FONSI approval (Finding of No Significant Impact) received on Nov 23, 2010. The contract for the EA Environmental Assessment was made with a small portion of the funds allocated to ongoing support during the twelve months following the delivery of the EA report. In this way we have eliminated the need for additional contracts for the ongoing support in this critical area. | 100 | No variance from baseline. Network redesign update completed. | 5 | Due to delay in completing network redesign update and EA process. Signed contracts for land lease for new build towers sites. Completing contracts for all existing tower sites. | 15 | Delay in completing network redesign update and EA process. Published Request for Proposal evaluated proposals, selected entity, established contract. Soil studies, terrain elevation and preliminary foundation design completed for 5 towers. We initially underestimated the time it would take to construct new towers and the time to process the RFPâ€™s for construction permits. We initially underestimated the time it would take to construct new towers and the time to process the RFPâ€™s for construction permits. | 0 | Delay in completing network redesign update and Environmental Assessment "EA" process. Received proposals from 10 companies for Site Preparation RFP (2). Proposals were evaluated, best proposal was selected and awarded. Our project planning activities have the first first sites preparation of existing towers completed in Sept. and first new towers expenditures completed in Q1 2012. | 2 | Delay in completing network redesign update and EA process. Published RFP 3 acquisition of Telecommunications Equipment ( Microwave and Wimax). Received proposals from 6 companies, best proposal was selected and awarded. Secured FCC licencing agreements for all Point to Point links. | 2 | Delay in completing network redesign update and EA process. | 2 | Delay in completing network redesign update and EA process. | 2 | No variance from baseline. | 2011-08-31 09:40 | 2011-08-31 09:40 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2011 | Q3 | Q3 - 2011 | 4057 | 3872 | TRUE | 13 | Initial delay due to Time to complete network design update and EA " Environmental Assessment". Currently RFP "Request for Proposals", process in full cycle with the fourth RFP , NOC Equipment , in process . | 46 | Administrative Project Management 46% | We have completed 3 of 4 major RFP's, Request for Proposals which required a lot of time for preparation and execution. A strategy of quadrant priorities was implemented which will ensure we meet the expenditures guidelines. | 93 | Received FONSI approval (Finding of No Significant Impact) received on Nov 23, 2010. | 100 | No variance from baseline. Network redesign update completed. | 23 | Initial delay due to completing network redesign update and EA process. Signed contracts for land lease for new build towers sites were performed. Completed lease contracts for 10 additional existing tower sites. | 32 | Delay in completing network redesign update and EA process. Developed agreement to be able to meet FCC substantial use requirements for the 2.5 MHz licensed frequencies to be used by the network. Submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency and authorization granted for the construction of four new telecommunications towers to be used by the network in underserved areas. We initially underestimated the time it would take to construct new towers and the time to process the RFPâ€™s for construction permits. | 0 | Delay in completing network redesign update and Environmental Assessment "EA" process. Completed contract negotiation and signature for Request for Proposal #2 (Site Preparation & Construction). The vendor for RFP #2, â€œSite Preparationâ€ initiated construction work on six sites, Hurricanes and major storms affected work flow, no invoices were completed in the quarter. | 2 | Delay in completing network redesign update and EA process. Completed contract negotiation and signature for Request for Proposal #3 (Telecommunications Equipment). The vendor initiated equipment purchase and transfer to island. Hurricanes and major storms affected work flow and deliveries, few invoices were processed. We are developing system to provide inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of being received, staged and implemented. Published Request for Proposal #4; ''Acquisition and Implementation of the Central Office Equipment for INTECO'S Broadband Network", in state newspaper. | 2 | Delay in completing network redesign update and EA process. The vendor for RFP #3 #3 (Telecommunications Equipment) initiated equipment purchase and transfer to island. Hurricanes and major storms affected work flow, few invoices were processed. | 2 | Delay in completing network redesign update and EA process. The vendor for RFP #3 #3 (Telecommunications Equipment) initiated equipment purchase and transfer to island. Hurricanes and major storms affected work flow, few invoices were processed. | 2 | Delay in completing network design update and EA process. | 2011-11-16 10:05 | 2011-11-16 10:05 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2011 | Q4 | Q4 - 2011 | 5061 | 4734 | TRUE | 35 | Initial delay due to Time to complete network design update and Environmental Assessment. Currently various Request for Proposals, process in full cycle with the latest Request for Proposal #5; Tower Construction, in process. | 56 | Administrative Project Management | We have completed 4 of 5 major Request for Proposals. Request for Proposals which required a lot of time for preparation and execution. A strategy of quadrant priorities was implemented which will ensure we meet the expenditures guidelines. | 93 | Received FONSI approval (Finding of No Significant Impact) received on 23, 2010. | 100 | Network redesign update completed. | 30 | Initial delay due to completing network redesign update and Environmental Assessment process. Completed lease contracts for total 13 existing tower sites. Completed land lease contracts for 6 sites. | 56 | Delay in completing network redesign update and Environmental Assessment process. Submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency for three additional sites, we already have authorization granted for the construction of four new telecommunications towers to be used by the network in underserved areas. We initially underestimated the time it would take to construct new towers and the time to process the Request for Proposals for construction permits. | 12 | Delay in completing network redesign update and Environmental Assessment process. Completed Site Preparation & Construction on 10 existing tower sites. Request for Proposal #5 completed, published for three tower construction projects. | 33 | Delay in completing network redesign update and Environmental Assessment process. The vendor for Request for Proposal #3; Telecommunications Equipment, initiated equipment purchase and transfer to island. The staging of the microwave radios for integration and acceptance testing was delayed until early next quarter. We developed system to provide inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of being received, staged and implemented. Completed evaluation and awarded, Request for Proposal #4; Acquisition and Implementation of the NOC Equipment for INTECO'S Broadband Network. | 33 | Delay in completing network redesign update and Environmental Assessment process. The vendor for Request for Proposal #3; Telecommunications Equipment, initiated equipment purchase and transfer to island. The staging of the microwave radios for integration and acceptance testing was delayed until early next quarter. Completed evaluation and awarded, Request for Proposal #4; Acquisition and Implementation of the NOC Equipment for INTECO's Broadband Network. | 33 | Delay in completing network redesign update and Environmental Assessment process. The vendor for Request for Proposal #3, Telecommunications Equipment, initiated equipment purchase and transfer to island. The staging of the microwave radios for integration and acceptance testing was delayed until early next quarter. | 33 | Delay in completing network design update and Environmental Assessment process. The vendor for Request for Proposal #3 Telecommunications Equipment, initiated equipment purchase and transfer to island. The staging of the microwave radios for integration and acceptance testing was delayed until early next quarter. | 2012-02-16 08:29 | 2012-02-16 08:29 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2012 | Q1 | Q1 - 2012 | 6047 | 5623 | TRUE | 72 | Initial delay due to Time to complete network design update and Environmental Assessment. Tower Construction, in process. | 72 | Administrative Project Management | We met the expenditures guidelines as per SAC with a 72% expenditures of the project to date. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 77 | Complete lease contracts for total 16 existing tower sites. Complete land lease contracts for six sites. | 60 | Submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency for three additional sites, we already have authorization granted for the construction of four new telecommunications towers to be used by the network in underserved areas. | 28 | Completed Site Preparation & Construction on 14 existing tower sites. Contractors selected for Request for Proposal #5 (three new tower construction) initiated work in a fast track mode and significant work was completed on foundation preparation. | 80 | The vendor for Request for Proposal #3; Telecommunications Equipment, has completed the purchase of equipment. We developed a system to provide inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of being received, staged and implemented. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was substantially completed. | 79 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 was substantially completed. | 79 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 was substantially completed. | 79 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 was substantially completed and is now ready for systems and integration testing. | 2012-05-14 07:11 | 2012-05-14 07:11 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2012 | Q2 | Q2 - 2012 | 7185 | 6220 | TRUE | 81 | Initial delay due to Time to complete network design update and Environmental Assessment. Tower Construction, in process. All towers to be completed by Q4 2012. | 76 | Administrative Project Management | We have met the expenditures guidelines as per SAC with a 81% expenditures of the project to date. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 83 | Completed lease or land lease contracts for total 21 tower sites. | 76 | Submission of permits, including if necessary soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency. We have pending three sites to receive permits for roof-top installation. All permits to be completed by Q4 2012. | 58 | Completed site preparation , construction, telecommunication enclosures installation and telecommunication equipment installation in fifteen tower sites. We have work pending on nine sites, of these contractors are completing construction work on three new towers. | 86 | The vendor for Request for Proposal #3; Telecommunications Equipment, has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. | 86 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network, Request for Proposal #4 was completed. All network build to be completed by Q4 2012. | 86 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed installing equipment on initial two quadrants. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network, Request for Proposal #4 was installed on NOC site. | 86 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed installing equipment on initial two quadrants. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 was completed and vendor is fully involved in systems and integration testing in NOC site. | 2012-08-21 12:22 | 2012-08-21 12:22 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2012 | Q3 | Q3 - 2012 | 7843 | 6626 | TRUE | 86 | Variance from baseline 12%. Initial delay due to Time to complete network design update and Environmental Assessment. Tower Construction, in process. All towers to be completed by Q4 2012. | 86 | Administrative Project Management | Variance of 4%. We have met the expenditures guidelines as per SAC with a 86% expenditures of the project to date. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 88 | Variance from baseline 12%. Delay in negotiations and written contract leased and/or ownership agreements. Completed lease or land lease contracts for total 23 tower sites. | 91 | Variance of 9%. Delay in governmental procedures to obtain permits. Submission of permits, including if necessary soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency. We have pending three sites to receive permits for roof-top installation. All permits to be completed by Q4 2012. | 67 | Variance of 33%. Delay in getting invoices from suppliers. Completed site preparation , construction, telecommunication enclosures installation and telecommunication equipment installation in ninteen tower sites. We have work pending on five sites, of these contractors are completing construction work on remaining new tower and four roof-tops. | 87 | Variance of 13%. The vendor for Request for Proposal #3; Telecommunications Equipment, has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. | 87 | Variance of 13%. The vendor for Telecommunications Equipment, completed completed the purchase of all equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network, Request for Proposal #4 was completed. All network build to be completed by Q4 2012. | 87 | Variance of 3% from baseline. The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and is completing equipment installation in last two quadrants. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network, Request for Proposal #4 was installed on NOC site. | 87 | Variance of 3% from baseline. The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and is completing equipment installation in last two quadrants. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network, Request for Proposal #4 was completed and vendor is fully involved in systems and integration testing in NOC site. | 2012-11-13 13:18 | 2012-11-13 13:18 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2012 | Q4 | Q4 - 2012 | 9137 | 7936 | TRUE | 96 | All sites implementation to be completed by Q1-2013. | 94 | Administrative Project Management | Variance of 6%. We have met the expenditures guidelines as per SAC with a 96% expenditures of the project to date. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 97 | Variance from baseline 3%. Delay in negotiations and written contract leased and/or ownership agreements. Completed lease or land lease contracts for all 24 tower sites. | 97 | Variance of 3%. Delay in governmental procedures to obtain permits. Submission of permits, including if necessary soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency. All permits to be completed by Q1 2013. | 92 | Variance of 8%. Delay in getting invoices from suppliers. Completed site preparation , construction, telecommunication enclosures installation and telecommunication equipment installation in twenty two tower sites. We have work being completed on two sites. | 96 | Variance of 4%. The vendor for Request for Proposal #3; Telecommunications Equipment, has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. | 96 | Variance of 4%. The vendor for Telecommunications Equipment, completed the purchase of all equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network, Request for Proposal #4 was completed. All network build to be completed by Q1 2013. | 96 | Variance of 4% from baseline. The vendor for Telecommunications Equipment, is completing equipment installation in last two sites. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network, Request for Proposal #4 was completed in NOC site. All equipment deployment to be completed in Q1-2013. | 96 | Variance of 4% from baseline. The vendor for Telecommunications Equipment is completing equipment installation in last two sites. Acquisition, installation, testing and verification of the NOC Equipment for INTECO's Broadband Network will be completed in Q1 2013. | 2013-03-14 12:33 | 2013-03-14 12:33 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2013 | Q1 | Q1 - 2013 | 9899 | 8491 | TRUE | 97 | All sites implementation to be completed by Q2-2013. | 99 | Administrative Project Management | We have met the expenditures guidelines. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 98 | Delay in negotiations and written contract leased and/or ownership agreements. Completed lease or land lease contracts for all 24 tower sites. | 97 | Delay in local governmental procedures to obtain permits. Submission of permits, including if necessary soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency. All permits to be completed by Q2-2013. | 98 | Delay in getting invoices from suppliers. Completed site preparation , construction, telecommunication enclosures installation and telecommunication equipment installation in twenty four tower sites. | 97 | Delay in getting invoices from suppliers. The vendor telecommunications equipment, has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. | 97 | Delay in getting invoices from suppliers. All telecommunications equipment purchase was completed. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. All network build to be completed by Q2-2013. | 97 | The vendor for Telecommunications Equipment, completed equipment installation in last two sites. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed in NOC site. | 97 | The vendor for Telecommunications Equipment is completing network testing in Q2-2013. | 2013-05-24 11:41 | 2013-05-24 11:41 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2013 | Q2 | Q2 - 2013 | 10693 | 9008 | TRUE | 100 | All sites and network implementation completed | 100 | Administrative Project Management | We have met the expenditures guidelines. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 100 | Delay in negotiations and written contract leased and/or ownership agreements. Completed lease or land lease contracts for all 24 tower sites. | 100 | Delay in local governmental procedures to obtain permits. Submission of permits, including if necessary soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency. One remaining permit submitted to be received in Aug. | 100 | Completed site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in twenty four tower sites. | 100 | All equipment purchases completed. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. | 100 | All telecommunications equipment purchase was completed. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. All network build completed. | 100 | Completed equipment all telecommunications equipment, installation. All NOC Equipment for INTECO's Broadband Network was completed in NOC site. | 100 | All network testing for telecommunications equipment is completed. | 2013-08-22 09:41 | 2013-08-22 09:41 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2013 | Q3 | Q3 - 2013 | 11633 | 9755 | TRUE | 100 | All sites and network implementation completed. | 100 | Administrative Project Management | We have met the expenditures guidelines. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 100 | Completed lease or land lease contracts for all 23 tower sites. | 100 | Submission of permits, including if necessary soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency were completed. | 100 | Completed site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in twenty four tower sites. | 100 | All equipment purchases completed. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. | 100 | All telecommunications equipment purchase was completed. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. All network build completed. | 100 | Completed depolyment and instalation of all telecommunications equipment. All NOC Equipment for INTECO's Broadband Network was installed and completed in NOC. | 100 | All network testing for telecommunications equipment is completed. | 2014-01-21 14:38 | 2014-01-21 14:38 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570034 | 2010 | Q2 | Q2 - 2010 | 58 | 1288 | FALSE | 1 |  | 0 |  |  | 100 |  | 34 |  | 0 |  | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2010 | Q3 | Q3 - 2010 | 359 | 1446 | TRUE | 1 | Environmental Assessment milestone complete. Spending will accelerate in the Fourth Quarter in order to meet the 2010 forecasted budget milestones. | 0 |  | N/A | 100 | FONSI issued on 09/30/2010.Environmental Assessment was deemed a sole-source procurement and was not approved for funding under the grant. | 21 | Network design progressing according to budget plan. | 0 | N/A | 0 | Due to FONSI being issued on 09/30/2010, milestone was delayed. | 0 | Due to FONSI being issued on 09/30/2010, milestone was delayed. | 0 | Due to FONSI being issued on 09/30/2010, milestone was delayed. | 0 | Due to FONSI being issued on 09/30/2010, milestone was delayed. | 0 | Planned for Fourth Quarter 2010. | 0 | Planned for Fourth Quarter 2010. | 2010-11-19 16:00 | 2010-11-19 16:00 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2010 | Q4 | Q4 - 2010 | 1207 | 2241 | TRUE | 37 | Marginally behind baseline plan of 43% complete, due to late start as a result of delay in obtaining approval of Environmental Assessment. Anticipate milestone to be on scheduled by the end of first quarter 2011. | 0 |  | N/A | 100 | FONSI issued on 09/30/2010. Professional Services fees incurred related to the Environmental Assessment were deemed a sole-source procurement and were not approved for funding under the grant. | 48 | On schedule | 0 | N/A | 11 | On schedule | 94 | On schedule | 44 | On schedule | 38 | Behind schedule as a result of late start associated with delay in Environmental Assessment approval. Anticipate milestone to be on scheduled by the end of first quarter 2011. | 30 | On schedule | 0 | Behind schedule as a result of late start associated with delay in Environmental Assessment approval. Anticipate milestone to be on scheduled by the end of first quarter 2011. | 2011-02-17 17:02 | 2011-02-17 17:02 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2011 | Q1 | Q1 - 2011 | 2089 | 2790 | TRUE | 65 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay; however, DeltaCom's project is currently projected to complete in the fourth quarter of 2011, well in advance of the BTOP deadline of January 31, 2013. | 68 |  | In-kind assets comprised of dark fiber and land were dedicated to project on March 14, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 48 | Network design was completed in the first quarter of 2011; however, vendor invoices are not scheduled to be paid until second quarter of 2011. This milestone will be in line with the baseline plan in second quarter 2011. | 0 | N/A | 16 | To date, costs associated with this milestone have under run projected budget expenditures. | 100 | On schedule | 64 | Expenditures for equipment are slightly behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan in third quarter 2011. | 74 | DeltaCom anticipates a marginal under run variance against the baseline plan for this milestone. DeltaCom will complete work associated with this milestone category in third quarter 2011. | 42 | The baseline plan over run associated with this milestone is due to invoice payment timing. No significant variance to the overall baseline plan is anticipated. | 0 | DeltaCom currently has an under run variance against the baseline plan for this milestone. Funds were budgeted for test equipment that have not been required to date. Funds will be required prior to completion of the project. | 2011-05-17 14:44 | 2011-05-17 14:44 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2011 | Q2 | Q2 - 2011 | 2963 | 3239 | TRUE | 76 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay; however, DeltaCom's project is currently projected to complete in the fourth quarter of 2011, well in advance of the BTOP deadline of January 31, 2013. | 100 |  | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 62 | Network design was completed in the first quarter of 2011. Additional invoices are being processed and scheduled to be paid. This milestone currently has an under run variance against the baseline plan. | 0 | N/A | 16 | To date, costs associated with this milestone have under run projected budget expenditures. | 100 | Completed | 66 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan in fourth quarter 2011. | 86 | DeltaCom anticipates a marginal under run variance against the baseline plan for this milestone. DeltaCom will complete work associated with this milestone category in third and fourth quarter 2011. | 43 | The baseline plan over run associated with this milestone is due to invoice payment timing. No significant variance to the overall baseline plan is anticipated. | 0 | DeltaCom currently has an under run variance against the baseline plan for this milestone. Funds were budgeted for test equipment that have not been required to date. Funds will be required prior to completion of the project. | 2011-08-08 16:37 | 2011-08-08 16:37 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2011 | Q3 | Q3 - 2011 | 3967 | 3822 | TRUE | 82 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay; however, DeltaCom's project is currently projected to complete in the first quarter of 2012, well in advance of the BTOP deadline of January 31, 2013. | 100 |  | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 67 | Network design was completed in the first quarter of 2011. Additional invoices are being processed and scheduled to be paid. This milestone currently has an under run variance against the baseline plan. | 0 | N/A | 16 | To date, costs associated with this milestone have under run projected budget expenditures. | 100 | Complete | 74 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan in first quarter 2012. | 95 | DeltaCom anticipates a marginal under run variance against the baseline plan for this milestone. DeltaCom will complete work associated with this milestone category in first quarter 2012. | 43 | Milestone is forecast to be 80% complete in the fourth quarter of 2011 and to be 100% complete in first quarter 2012. | 0 | DeltaCom currently has an under run variance against the baseline plan for this milestone. Funds were budgeted for test equipment that have not been required to date. Funds will be required prior to completion of the project. | 2011-11-10 15:52 | 2011-11-10 15:52 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2011 | Q4 | Q4 - 2011 | 5071 | 4744 | TRUE | 88 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay; however, DeltaCom's project is currently projected to complete in the third quarter of 2012, well in advance of the BTOP deadline of January 31, 2013. | 100 | In-Kind Assetts | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 67 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. Additional cost will be incurred for final as-built drawings. | 0 | N/A | 27 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be incurred for the Cookeville lateral build in first quarter 2012. | 100 | Complete | 74 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan in second quarter 2012. | 100 | This milestone is not complete, however expenditures in this milestone are at 111% of the baseline category. Overall, the project remains under budget as noted in the SF-424C Budget below. Due to extended negotiations with make-ready and collocation vendors, DeltaCom expects to complete work associated with this milestone category in second quarter 2012. | 82 | DeltaCom expects to complete this milestone in the second quarter of 2012. | 62 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2012-02-16 15:14 | 2012-02-16 15:14 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2012 | Q1 | Q1 - 2012 | 6003 | 5601 | TRUE | 89 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay. Additional delays are due to extended negotiations with make-ready and collocation vendors. However, DeltaCom's project is currently projected to complete in the third quarter of 2012, well in advance of the BTOP deadline of January 31, 2013. | 100 | Dark Fiber and Land Assets | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. Additional cost will be incurred for final as-built drawings. | 0 | N/A | 27 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be incurred for the Cookeville lateral build in second quarter 2012. | 100 | Complete | 75 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan by the end of the project. | 100 | This milestone is not complete, however expenditures in this milestone are at 113% of the baseline category. Overall, the project remains under budget as noted in the SF-424C Budget below. Due to extended negotiations with make-ready and collocation vendors, DeltaCom expects to complete work associated with this milestone category in second quarter 2012. | 82 | DeltaCom expects to complete this milestone in the second quarter of 2012. | 67 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2012-05-10 11:34 | 2012-05-10 11:34 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2012 | Q2 | Q2 - 2012 | 7025 | 6140 | TRUE | 90 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay. Additional delays are due to extended negotiations with make-ready and collocation vendors. However, DeltaCom's project is currently projected to complete in the third quarter of 2012, with all expenditures being invoiced by the BTOP deadline of January 31, 2013. | 100 | Dark Fiber and Land Assets | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. Additional cost will be incurred for final as-built drawings. | 0 | N/A | 85 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be incurred and invoiced by the BTOP deadline of January 31, 2013. | 100 | Complete | 75 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan by the end of the project. | 100 | This milestone is not complete, however expenditures in this milestone are at 114% of the baseline category. Overall, the project remains under budget as noted in the SF-424C Budget below. Due to extended negotiations with make-ready and collocation vendors, DeltaCom expects to complete work associated with this milestone category in third quarter 2012. | 84 | DeltaCom expects to complete this milestone in the third quarter of 2012. | 67 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2012-08-10 18:01 | 2012-08-10 18:01 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2012 | Q3 | Q3 - 2012 | 8055 | 6734 | TRUE | 90 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay. Additional delays are due to extended negotiations with make-ready and collocation vendors. However, DeltaCom's project was completed in the third quarter of 2012, and all expenditures will be invoiced by the BTOP deadline of January 31, 2013. | 100 | Dark Fiber and Land Assets | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. | 0 | N/A | 93 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be invoiced by the BTOP deadline of January 31, 2013. | 100 | Complete | 75 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be invoiced by the BTOP deadline of January 31, 2013. | 100 | This milestone is complete and currently expenditures in this milestone are at 114% of the baseline category. Overall, the project remains under budget as noted in the SF-424C Budget below. Any additional expenditures will be invoiced by the BTOP deadline of January 31, 2013. | 89 | This milestone currently has an under run variance against the baseline plan. Equipment deployment was completed in the third quarter of 2012. | 67 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2012-11-26 17:05 | 2012-11-26 17:05 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2012 | Q4 | Q4 - 2012 | 8871 | 7658 | TRUE | 93 | Project expenditures are below the baseline plan due to an under run in the overall project budget. DeltaCom's project was completed in the third quarter of 2012, and all expenditures will be invoiced by the BTOP deadlines. | 100 | Dark Fiber and Land Assets | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. | 0 | N/A | 93 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be invoiced by the BTOP deadlines. | 100 | Complete | 79 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be invoiced by the BTOP deadlines. | 100 | This milestone is complete and currently expenditures in this milestone are at 114% of the baseline category. Overall, the project remains under budget as noted in the SF-424C Budget below. Any additional expenditures will be invoiced by the BTOP deadlines. | 89 | This milestone currently has an under run variance against the baseline plan. Equipment deployment was completed in the third quarter of 2012. | 67 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2013-02-21 11:47 | 2013-02-21 11:47 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2013 | Q1 | Q1 - 2013 | 9891 | 8486 | TRUE | 91 | Complete Project expenditures are below the baseline plan due to an under run in the overall project budget. DeltaCom's project was completed in the third quarter of 2012, and all expenditures were invoiced by 05/01/2013. The decrease in this milestone category is the result of a return of funds to ASAP for expenditures not covered by the grant. | 100 | Dark Fiber and Land Assets Close Out Activities | Complete In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. Fees associated with close out activities were expended and reimbursed by 05/01/2013. | 100 | Complete DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | Complete This milestone has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. | 0 | N/A | 93 | Complete This milestone has an under run variance against the baseline plan. | 100 | Complete | 79 | Complete This milestone has an under run variance against the baseline plan. | 100 | Complete Expenditures in this milestone are at 107% of the baseline category. Overall, the project remained under budget as noted in the SF-424C Budget below. The decrease in this milestone category is the result of a return of funds to ASAP for expenditures not covered by the grant. | 89 | Complete This milestone has an under run variance against the baseline plan. Equipment deployment was completed in the third quarter of 2012. | 67 | Complete This milestone has an under run variance against the baseline plan. | 2013-05-23 16:38 | 2013-05-23 16:38 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570035 | 2010 | Q3 | Q3 - 2010 | 415 | 1474 | TRUE | 1 | On 7/27/2010 NTIA notified Hardy that it would accept a co-first priority, pari-passu security interest subject to successful negotiations of terms and conditions between NTIA and Hardy's existing first priority secured lenders. Hardy is awaiting written confirmation from NTIA. | 0 | NA | Same as above | 80 | Same as above, funded by Hardy to date | 0 | Same as above | 0 | Same as above | 0 | Same as above | 0 | Same as above | 0 | Same as above | 0 | Same as above | 0 | Same as above | 0 | Same as above | 2010-11-24 12:09 | 2010-11-24 12:09 | 5525 | 5525 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2010 | Q4 | Q4 - 2010 | 1263 | 2290 | TRUE | 22 | Intercreditor Agreement and Historic Preservation Review pending. | 0 | N/A | N/A | 85 | Historic Preservation Review pending. | 72 | In process | 40 | In process | 62 | Historic Preservation Review pending. Highway Dept. permitting in progress. No other state or federal permits required. | 12 | Historic Preservation Review pending. | 8 | Equipment procurement in process, pending Intercreditor Agreement. | 12 | Intercreditor Agreement and Historic Preservation Review pending. | 8 | Equipment procurement in process, pending Intercreditor Agreement. | 0 | Network deployment not yet completed. | 2011-02-21 17:36 | 2011-02-21 17:36 | 5525 | 5525 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2011 | Q1 | Q1 - 2011 | 2237 | 2864 | TRUE | 25 | -44% Variance. Delays in Intercreditor Agreement, Environmental Assessment review, and completion of Historic and Cultural Preservation Review prevented draw down of funds. Finding of No Significant Impact not yet released at 3/31/2011, precluding procurement of materials and commencement of deployment. | 0 | Inspection | -100% Variance. Finding of No Significant Impact not released by NTIA as of 3/31/2011, preventing network construction. | 100 | +341% Variance. Cost of environmental assessment and archaeological services ran significantly over budget due to the high number of prehistoric and historic sites in Hardy County, WV | 47 | -28% Variance. Resources reallocated to completion of environmental/archaeological assessments. Segments of the network were rerouted, and redesigned from buried cable to aerial placement, to avoid identified historic and cultural sites. | 12 | -88% Variance. The baseline forecast included costs of land, structures and appraisals in the Right of Way budget category. Delays in Environmental Assessment review and completion of Historical and Cultural Preservation Review delayed purchases of land for building placement sites and required easements. Phase 1 archaeological survey and shovel testing required to discover artifacts in 9.3 mile buried section and land for building placement. Land purchases for building sites deferred. | 63 | -38% Variance. Delays in Environmental Assessment review and completion of Historical and Cultural Preservation review delayed permitting and other approvals. Sections of line were rerouted and redesigned as aerial placement to avoid historic and cultural sites along the route. | 0 | -100% Variance. Land clearing and site preparation not allowable until completion of Phase 1 archaeological survey and shovel testing as required to discover artifacts. Notification of requirement by NTIA and WV Office of State Historic Preservation not received until 3/25/2011. | 14 | -86% Variance. Delays in approval of Intercreditor Agreement and Environmental Assessment prevented procurement of electronics and equipment. | 20 | -46% Variance. Delays in approval of Intercreditor Agreement and Environmental Assessment prevented procurement of materials and commencement of construction. Hardy contributed existing network infrastructure and electronics deployed to Community Anchor Institutions, but no new deployment allowed until Finding of No Significant Impact released by NTIA. Finding not released as of 3/31/2011. | 0 | Baseline forecast included equipment installation & testing in Equipment Procurement budget. | 0 | Same as above | 2011-05-20 23:40 | 2011-05-20 23:40 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2011 | Q2 | Q2 - 2011 | 3243 | 3384 | TRUE | 30 | (58.3)% Variance. Delays in Intercreditor Agreement, Environmental Assessment review, and completion of Historic and Cultural Preservation Review prevented draw down of funds until April, 2011. | 0 | Inspection | -100% Variance. Same as Network Build. | 100 | 462.9% Variance. Cost of environmental assessment and archaeological services ran significantly over budget due to the high number of prehistoric and historic sites in Hardy County, WV and the requirement for a Phase 1 archaeological survey and shovel testing. | 75 | (7.9)% Variance. Resources reallocated to completion of environmental/archaeological assessments. Segments of the network were rerouted and redesigned from buried cable to aerial placement, to avoid identified historic and cultural sites. | 12 | (88.1)% Variance. The baseline forecast included costs of land, structures, and appraisals in this category. Rights of Way acquisition costs have been included in the Construction Permits and Other Approvals Category. Delays in Environmental Assessment review and completion of Historical and Cultural Preservation Review delayed purchases of land for building placement sites and required easements. Phase 1 archaeological survey and shovel testing required to discover artifacts in 9.3 mile buried section and land for building placement. Land has been purchased for one building site, but site prep and building placement may not proceed until the Phase survey is completed and approvals obtained. | 100 | 52.9% Variance. Sections of line were rerouted and redesigned as aerial placement to avoid historic and cultural sites along the route. Rights of Way acquisition costs have been included in this category. | 0 | (100)% Variance. Site preparation may not proceed until completion of Phase 1 archaeological survey and approval by WV Historic Preservice Office and National Telecommunications & Information Administration | 12 | (88.4%) Variance. This category included Equipment Deployment in the Baseline. Deployment expenditures have been included for consistency. Equipment has been specified and prices negotiated. Delivery dates are established but deferred until two facilities sites are connected over fiber. | 18 | (81.8%) Variance. Delays in approval of Intercreditor Agreement and Environmental Assessment prevented procurement of materials and commencement of construction prior to tsecond quarter of 2011. Hardy contributed existing network infrastructure and electronics deployed to Community Anchor Institutions, representing 18% completion. Major materials have been ordered, and construction drawings and requests for proposals documentation completed for all four phases of construction. | 0 | N/A. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | N/A. Same as above. | 2011-08-19 16:23 | 2011-08-19 16:23 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2011 | Q3 | Q3 - 2011 | 4237 | 3967 | TRUE | 34 | (59.4%) Variance. Delays in Intercreditor Agreement, Environmental Assessment review, and completion of Historic and Cultural Preservation Review prevented draw down of funds until April, 2011. | 0 | Inspection | (100.0%) Variance. Same as Network Build. | 100 | 629.2% Variance. Cost of environmental assessment and archaeological services ran significantly over budget due to the high number of prehistoric and historic sites in Hardy County, WV and the requirement for a Phase 1 archaeological survey and shovel testing. | 90 | (1.4%) Variance. Resources reallocated to completion of environmental/archaeological assessments. Segments of the network were rerouted and redesigned from buried cable to aerial placement, to avoid identified historic and cultural sites. | 12 | (88.1%) Variance. The baseline forecast included costs of land, structures, and appraisals in this category. Rights of Way acquisition costs have been included in the Construction Permits and Other Approvals Category. Delays in Environmental Assessment review and completion of Historical and Cultural Preservation Review delayed purchases of land for building placement sites and required easements. Phase 1 archaeological survey and shovel testing required to discover artifacts in 9.3 mile buried section and land for building placement. Land has been purchased for one building site, but site prep and building placement may not proceed until the Phase survey is completed and approvals obtained. | 100 | 86.4% Variance. Sections of line were rerouted and redesigned as aerial placement to avoid historic and cultural sites along the route. Rights of Way acquisition costs have been included in this category. | 0 | (100.0%) Variance. Site preparation may not proceed until completion of Phase 1 archaeological survey and approval by WV Historic Preservice Office and National Telecommunications & Information Administration | 15 | (84.7%) Variance. This category included Equipment Deployment in the Baseline. Deployment expenditures have been included for consistency. Delivery dates were deferred until facilities sites could be connected over fiber. Equipment has been deployed in three central office facilities. | 18 | (81.7%) Variance. Delays in approval of Intercreditor Agreement and Environmental Assessment prevented procurement of materials and commencement of construction prior to second quarter of 2011. Hardy contributed existing network infrastructure and electronics deployed to Community Anchor Institutions, representing 18% completion. Major materials have been ordered, and construction drawings and requests for proposals documentation completed for all four phases of construction. Contracts have been awarded, and construction commenced 9-26-2011. Construction invoices were not received by end of Q3 2011. | 0 | N/A. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | N/A. Same as above. | 2011-11-22 16:57 | 2011-11-22 16:57 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2011 | Q4 | Q4 - 2011 | 5271 | 4940 | TRUE | 68 | (32%) Variance. Delays in Intercreditor Agreement and completion of Historic and Cultural Preservation Review prevented draw down of funds until April, 2011. | 52 | Inspection | (48)% Variance. Inspection included in Network Build but broken out for clarity. Delays in approval of Intercreditor Agreement and Environmental Assessment prevented procurement of materials and commencement of construction prior to third quarter of 2011. Construction commenced 9-26-2011 with 76.6 miles deployed or approximately 70% of backbone ring. | 100 | 779% Variance. Cost of environmental assessment and archaeological services ran significantly over budget due to the high number of prehistoric and historic sites in Hardy County, WV and the requirement for a Phase 1 archaeological survey and shovel testing. | 100 | 45% Variance. Resources reallocated to completion of environmental/archaeological assessments. Segments of network rerouted and redesigned from buried cable to aerial placement to avoid identified historic and cultural sites. Route modifications due to R/W acquisition issues. | 12 | (88)% Variance. The baseline forecast included costs of land, structures, and appraisals in this category. Rights of Way acquisition costs have been included in the Construction Permits and Other Approvals Category. Delays in Environmental Assessment review and completion of Historical and Cultural Preservation Review delayed purchases of land for building placement sites and required easements. Phase 1 archaeological survey and shovel testing required to discover artifacts in 9.3 mile buried section and land for building placement. | 100 | (118)% Variance. Sections of line were rerouted and redesigned as aerial placement to avoid historic and cultural sites along the route. Rights of Way acquisition costs have been included in this category. | 0 | (100)% Variance. Site prep to be covered by Recipient. | 24 | (76)% Variance. This category included Equipment Deployment in the Baseline. Deployment expenditures have been included for consistency. Delivery dates were deferred until facilities sites could be connected over fiber. Equipment has been deployed in 20 central offices and remote sites. | 59 | (41)% Variance. Delays in approval of Intercreditor Agreement and Environmental Assessment prevented procurement of materials and commencement of construction prior to third quarter of 2011. Construction commenced 9-26-2011 with 76.6 miles deployed approximately 70% of the network backbone ring. | 0 | (100)% Variance. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | (100)% Variance. Same as above. | 2012-02-27 01:51 | 2012-02-27 01:51 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2012 | Q1 | Q1 - 2012 | 6241 | 5723 | TRUE | 91 | (9%) Variance. Historic preservation studies and surveys significantly delayed buried construction and ground-disturbing activities | 100 |  | 88% Variance. Utilization of multiple contractors and crews to overcome environmental and historic preservation delays to construction commencement. Delays prevented construction prior to third quarter of 2011. | 100 | 911% Variance. Historic preservation studies and surveys significantly delayed buried construction and materially increased project costs. | 100 | 40% Variance. Network reroutes or changes in deployment methods to avoid potential effects on historic sites; Network redesigned to leverage Hardy AnchorRing Middle Mile backbone network to provide fiber facilities for the Hardy OneNet Last Mile Fiber-to-the-Home ("FTTH") network funded by the Rural Utilities Service ("RUS") of the U.S. Dept. of Agriculture under the Broadband Initiatives Program ("BIP"). | 12 | (88)% Variance. The baseline included costs of land, structures, and appraisals in this category. Private rights of way acquisition costs were included in the Construction Permits and Other Approvals Category. The number of facilities required to transmit services decreased due to the use of long-range optics and availability of fiber-to-the-home in the BIP-funded Hardy OneNet network. | 100 | 146% Variance. Sections of line were rerouted and/or redesigned as aerial placement to avoid potential effects to historic and cultural sites along the route. Private rights of way acquisition costs are included in this category. | 0 | (100%) Variance. Site preparation costs covered by Recipient | 27 | (73%) Variance. Baseline category included Equipment Deployment. Deployment expenditures have been included for consistency. Equipment deployed in 20 central offices and remote sites. Vendor negotiations produced significant savings on electronics. Use of long-range optics and availability of fiber-to-the-home in the BIP funded Hardy OneNet network reduced the requirement for electronics at all sites. | 92 | (8)% Variance. Delays in approval of Intercreditor Agreement and Environmental and Historic Preservation Assessments and Surveys prevented procurement of materials and commencement of construction prior to third quarter of 2011. | 0 | (100)% Variance. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | (100)% Variance. Same as above. | 2012-05-21 22:14 | 2012-05-21 22:14 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2012 | Q2 | Q2 - 2012 | 7087 | 6171 | TRUE | 98 | (2%) Variance. | 100 |  | 119% Variance. Utilization of multiple contractors and crews to overcome environmental and historic preservation delays to construction commencement. Delays prevented construction prior to third quarter of 2011. | 100 | 775% Variance. Historic preservation studies and surveys significantly delayed buried construction and materially increased project costs. | 100 | 61% Variance. Network reroutes or changes in deployment methods to avoid potential effects on historic sites; Network redesigned to leverage Hardy AnchorRing Middle Mile backbone network to provide fiber facilities for the Hardy OneNet Last Mile Fiber-to-the-Home ("FTTH") network funded by the Rural Utilities Service ("RUS") of the U.S. Dept. of Agriculture under the Broadband Initiatives Program ("BIP"). Delays in review and approval of required route additions and modifications by NTIA historic preservation staff. | 12 | (88)% Variance. No change from prior quarter. The baseline included costs of land, structures, and appraisals in this category. Private rights of way acquisition costs were included in the Construction Permits and Other Approvals Category. The number of facilities required to transmit services decreased due to the use of long-range optics and availability of fiber-to-the-home in the BIP-funded Hardy OneNet network. | 100 | 146% Variance. No change from prior quarter. Sections of line were rerouted and/or redesigned as aerial placement to avoid potential effects to historic and cultural sites along the route. Private rights of way acquisition costs are included in this category. | 0 | (100%) Variance. Site preparation costs covered by Recipient | 34 | (66%) Variance. Baseline category included Equipment Deployment. Deployment expenditures have been included for consistency. Equipment deployed in 20 central offices and remote sites. Vendor negotiations produced significant savings on electronics. Use of long-range optics and availability of fiber-to-the-home in the BIP funded Hardy OneNet network reduced the requirement for electronics at all sites. | 98 | (2)% Variance. Delays in approval of Intercreditor Agreement and Environmental and Historic Preservation Assessments and Surveys prevented procurement of materials and commencement of construction prior to third quarter of 2011. Delays in review and approvals of requested route additions and modifications of Community Anchor Institute routes delayed completion of 24 connections. | 0 | (100)% Variance. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | Baseline value = 0. Network testing costs included in professional services. | 2012-08-15 15:46 | 2012-08-15 15:46 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2012 | Q3 | Q3 - 2012 | 7875 | 6642 | TRUE | 100 | (0.2)% Variance. | 100 | Inspection | 232% Variance. Utilization of multiple contractors and crews to overcome environmental and historic preservation delays to construction commencement. Delays prevented construction prior to third quarter 2011. | 100 | 875% Variance. Historic preservation studies and surveys significantly delayed buried construction and materially increased project costs. | 100 | 78% Variance. Network reroutes or changes in deployment method to avoid potential effects on historic sites. Network redesign to leverage deployment of the Hardy AnchorRing Middle Mile backbone network to provide fiber facilities for the Hardy OneNet Last Mile Fiber-to-the-Home network funded by the Rural Utilities Service of the U. S. Department of Agriculture under the Broadband Initiatives Program. Delays by NTIA historic preservation staff in review and approval of required route additions and modifications. | 12 | (88)% Variance. No change from prior quarter. The baseline included costs of land, structures and appraisals in this category. Private rights of way acquisition costs were included in the Construction Permits and Other Approvals category. The number of facilities required to transmit services decreased due to the use of long-range optics and availability of fiber-to-the-home in the Hardy OneNet network funded under the Broadband Initiatives Program. | 100 | 157% Variance. No change from prior quarter. Sections of the network were rerouted and/or redesigned as aerial placement to avoid potential effects to historic and cultural sites along the route. Private rights of way acquisition costs are included n this category. | 0 | (100)% Variance. Site preparation costs were covered by Recipient. | 34 | (66)% Variance. The baseline included Equipment Deployment costs in this budget category. Deployment expenditures have been included for consistency. Significant savings were produced through negotiations with vendors, as well as due to the use of long-range optics and availability of fiber-to-the-home in the Hardy OneNet network funded by the Broadband Initiatives Program, which reduced the requirement for electronics at all facilities. | 100 | 1% Variance. | 0 | (100)% Variance. The baseline included Equipment Deployment costs in the Equipment Procurement budget category. | 0 | (100)% Variance. Baseline = 0. Network Testing costs were included in the Professional Services budget category. | 2012-11-14 14:47 | 2012-11-14 14:47 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2012 | Q4 | Q4 - 2012 | 8791 | 7590 | TRUE | 100 | 17% Variance. See sections below. | 100 | Inspection | 289% Variance. This category includes Network Testing, Inspection and Construction Supervision. Utilization of multiple contractors increased inspection and supervision costs. | 100 | 1105% Variance. Historic preservation studies, shovel testing, and surveys of planned buried routes and route modifications in the field significantly delayed buried construction and materially increased project costs. | 100 | 65% Variance. Network reroutes or changes in deployment method to avoid permitting, ROW, and potential effects on historic sites, and to ensure compliance with standards. Network redesign to leverage deployment of the Hardy AnchorRing Middle Mile backbone network to provide fiber facilities for the Hardy OneNet Last Mile Fiber-to-the-Home network funded by the Rural Utilities Service of the U. S. Department of Agriculture under the Broadband Initiatives Program. | 100 | (88)% Variance. Baseline included costs of land, structures and appraisals in this category. Private rights of way acquisition costs were included in the Construction Permits and Other Approvals category. The number of facilities required to transmit services decreased due to the use of long-range optics and availability of fiber-to-the-home in the Hardy OneNet network funded under the Broadband Initiatives Program. | 100 | 157% Variance. No change from prior quarter. Sections of the network were rerouted and/or redesigned as aerial placement to avoid potential effects to historic and cultural sites along the route, or permitting/ ROW issues. Private rights of way acquisition costs are included n this category. | 100 | 151% Variance. Site preparation costs include grading and concrete equipment pad at Hardy's Southfork Central Office for HVAC equipment. Funds for these expenditures were drawn from the federal award. | 100 | (49)% Variance. Baseline included Equipment Deployment costs in this budget category. Significant savings were produced through negotiations with vendors, as well as due to the use of long-range optics and availability of fiber-to-the-home in the Hardy OneNet network funded by the Broadband Initiatives Program, which reduced the requirement for electronics at all facilities. | 100 | 14% Variance. Increased costs of rock trenching, rock sawing, boring, and duct placement, and design changespreviously discussed. | 100 | (100)% Variance. The baseline included Equipment Deployment costs in the Equipment Procurement budget category. | 100 | 0% Variance. Baseline = 0. Network Testing costs were included in the category "Other - Inspection", | 2013-02-14 21:31 | 2013-02-14 21:31 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570036 | 2010 | Q2 | Q2 - 2010 | 59 | 1302 | FALSE | 35 |  | 0 |  |  | 100 |  | 50 |  | 0 |  | 25 |  | 0 |  | 25 |  | 15 |  | 15 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2010 | Q3 | Q3 - 2010 | 397 | 1465 | TRUE | 50 | On track | 0 |  | N/A | 100 | Complete | 50 | Managing multiple projects; for efficiency reasons, modified project prioritization. Will be on track in 4Q10 and 1Q11. | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 50 | On track | 0 | During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. | 0 | Pending 2g | 0 | Pending 2g | 0 | On track | 2010-11-23 17:18 | 2010-11-23 17:18 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2010 | Q4 | Q4 - 2010 | 1155 | 2196 | TRUE | 45 | Completed all network and engineering designs simultaneously. Construction procurement process still in progress. Variance due to delay in construction procurement activities. | 0 |  | N/A | 100 | Complete | 75 | Completed wavelength system designs for all sites. Variance due to delay in design for SONET system. | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 20 | Construction procurement process still in progress. | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 2011-02-15 17:44 | 2011-02-15 17:44 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2011 | Q1 | Q1 - 2011 | 2309 | 2900 | TRUE | 28 | Completed all network and engineering designs simultaneously. Construction procurement process is complete. Variance due to delay in construction procurement activities. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Completed all dense wavelength divisional multiplexing and synchronous optical networking system designs. | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 5 | Construction contractor has been selected. Per April 19th NTIA guidance the percent complete is strictly based on the budget. | 34 | Most dense wavelength divisional multiplexing and synchronous optical networking systems have been purchased. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 2011-05-25 16:37 | 2011-05-25 16:37 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2011 | Q2 | Q2 - 2011 | 3377 | 3452 | TRUE | 31 | We have made good progress with the construction phase of the project. Inside plant work is completed, so equipment deployment will pick up next quarter. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 5 | Construction of the inside plant work is complete and the outside plant will begin early in the 3rd quarter. Delays are due to longer construction procurement process than expected. The percent complete is based on invoiced expenses in 2Q. | 36 | Most DWDM and ADM equipment has been purchased. | 10 | Our network build will be the deployment of transport equipment (2i) at each of our interconnection sites. Delays are due to longer construction procurement process than expected. | 10 | The DWDM deployment has begun and the ADM deployment will follow its completion. | 0 | Pending the completion of construction and equipment deployment at each site (items 2f and 2i). Delays are due to longer construction procurement process than expected. | 2011-08-30 13:36 | 2011-08-30 13:36 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2011 | Q3 | Q3 - 2011 | 4333 | 4023 | TRUE | 36 | We have made good progress with our construction and equipment deployments. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 5 | Most of the construction has been completed at each of the sites. Percent complete is strictly based on the budget. | 42 | The majority of the equipment has been purchased. Percent complete is strictly based on the budget. | 95 | We are finalizing the network build now that the equipment has been deployed. | 100 | All equipment has been deployed. | 80 | All DWDM systems have been tested. The ADM systems have completed testing in 2 or 4 sites. | 2011-11-30 14:38 | 2011-11-30 14:38 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2011 | Q4 | Q4 - 2011 | 5297 | 4968 | TRUE | 43 | All construction and equipment deployments are complete. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 57 | The construction has been completed. Finalizing invoices with the construction contractor. Percent complete is strictly based on the budget. | 42 | All equipment has been purchased. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:43 | 2012-02-27 15:43 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2012 | Q1 | Q1 - 2012 | 6053 | 5626 | TRUE | 43 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 61 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 42 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete. | 2012-05-14 11:59 | 2012-05-14 11:59 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2012 | Q2 | Q2 - 2012 | 6513 | 5871 | TRUE | 43 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 61 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 42 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete. | 2012-07-27 12:06 | 2012-07-27 12:06 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2012 | Q3 | Q3 - 2012 | 7691 | 6530 | TRUE | 43 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete. | 100 | Complete. | 0 | N/A - All construction will be on our own property. | 100 | Complete. | 61 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 42 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. | 100 | Complete. | 100 | Complete. | 2012-10-30 22:57 | 2012-10-30 22:57 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2012 | Q4 | Q4 - 2012 | 8527 | 7254 | TRUE | 43 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete. | 100 | Complete. | 0 | N/A - All construction will be on our own property. | 100 | Complete. | 61 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 42 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. | 100 | Complete. | 100 | Complete. | 2013-01-30 16:20 | 2013-01-30 16:20 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2013 | Q1 | Q1 - 2013 | 11979 | 10138 | TRUE | 100 | Final expenses will be for closeout costs. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 100 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 2014-03-21 16:00 | 2014-03-21 16:00 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570037 | 2010 | Q2 | Q2 - 2010 | 60 | 1300 | FALSE | 30 |  | 0 |  |  | 100 |  | 45 |  | 50 |  | 50 |  | 10 |  | 20 |  | 5 |  | 5 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Columbia, County of | TRUE
NT10BIX5570037 | 2010 | Q3 | Q3 - 2010 | 145 | 1339 | TRUE | 25 | Waiting on Environmental Assessment Approval | 0 |  | N/A | 95 | Waiting on MOA between FCC, GA-SHPO, and Columbia County to resolve tower adverse effect | 45 | N/A | 50 | N/A | 50 | N/A | 10 | N/A | 20 | Recording of in-kind equipment for project | 0 | Waiting on Environmental Assessment Approval | 0 | Waiting on Environmental Assessment Approval | 0 | N/A | 2010-10-12 10:07 | 2010-10-12 10:07 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2010 | Q4 | Q4 - 2010 | 499 | 1524 | TRUE | 30 | Environmental Assessment and permit process taking longer than anticipated | 0 |  | N/A | 100 | Received our Mitigated Finding of No Significant Impact (FONSI) on December 7, 2010 | 65 | N/A | 60 | Working with City of Harlem and Grovetown on rights of way issues. | 60 | Erosion, Sedimentation and Pollution Control Plan has to be completed for each fiber construction phase to obtain permits. | 60 | Site plans are prepared for each construction phase. | 20 | Recording of in-kind equipment for project | 1 | Started construction on December 13, 2010 | 0 | N/A | 0 | N/A | 2011-01-21 07:42 | 2011-01-21 07:42 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2011 | Q1 | Q1 - 2011 | 2067 | 2779 | TRUE | 19 | Environmental Assessment and permit process taking longer than anticipated | 0 |  | N/A | 100 | Completed | 65 | Environmental Assessment and permit process taking longer than anticipated | 75 | Working with City of Harlem and Grovetown on rights of way issues. | 75 | Phase IV/V permits to be completed, still waiting on Railroad Permits from CSX. | 60 | Environmental Assessment and permit process taking longer than anticipated | 20 | Ordered Intelligence Traffic System equipment, the rest of equipment is dependant upon network design | 15 | Only conduit has been installed Environmental Assessment and permit process taking longer than anticipated | 0 | Intelligence Traffic System equipment on order. Once our network design has been completed, we will issue RFP to procure network equipment to deploy. Our focus is on network build and once our construction has been completed, we will deploy equipment. | 0 | Only conduit has been installed. Network testing is dependant upon equipment deployment. | 2011-05-17 06:22 | 2011-05-17 06:22 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2011 | Q2 | Q2 - 2011 | 2917 | 3216 | TRUE | 34 | Environmental, permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 85 | Permit and Environmental process taking longer than anticipated | 90 | Working with cities on ROW issues | 90 | Working with CSX on Railroad permits. | 75 | CSX Permits and ROW delays inside cities | 5 | Received traffic switches and should start deploying equipment in third quarter 2011. Currently working on Electronics RFP to be issued third quarter 2011. | 18 | Railroad permits and ROW issues inside cities taking longer than anticipated. Delay in fiber shipments has impacted schedule. | 0 | Issuing electronics RFP to be issued third quarter 2011. Our current focus is to build out fiber infrastructure before deploying equipment. | 0 | Network testing is dependant upon equipment deployment. | 2011-08-02 07:19 | 2011-08-02 07:19 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2011 | Q3 | Q3 - 2011 | 3929 | 3803 | TRUE | 52 | Environmental, permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 90 | Permits, ROW and Environmental process has impacted network design. | 90 | Actively acquiring easements inside cities and anticipate completion by January 31, 2012. | 95 | Working with GA DOT on one (1) interstate permit, and required permits for Phase VI of construction. | 90 | ROW delays inside cities. | 5 | Currently the County is seeking network electronics proposals to provide various broadband middle mile services. Once the proposals are submitted, County staff will evaluate the submitted proposals. County staff should recommend a firm for approval by February 2012. | 55 | 141 miles of conduit, 73 miles of fiber and 4 tower facilities have been constructed | 0 | Currently the County is seeking network electronics proposals to provide various broadband middle mile services. Once the proposals are submitted, County staff will evaluate the submitted proposals. County staff should recommend a firm for approval by February 2012. | 0 | Currently the County is seeking network electronics proposals to provide various broadband middle mile services. Once the proposals are submitted, County staff will evaluate the submitted proposals. County staff should recommend a firm for approval by February 2012. | 2011-11-09 06:40 | 2011-11-09 06:40 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2011 | Q4 | Q4 - 2011 | 5341 | 5013 | TRUE | 68 | Environmental, permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 98 | Fiber splicing schematics should be completed by January 31, 2012 and minor changes may take place after electronics have been selected. | 98 | Actively working with the cities and home owners to acquire permanent easements. We currently have 9 outstanding easements to obtain. | 99 | Waiting on one interstate DOT permit. | 99 | We have all DOT permits except one final interstate permit. We are currently installing broadband infrastructure where we have permits and approvals. These delays should not impact overall project. | 10 | Purchased some electronics to connect traffic CAIs. County staff currently reviewing submitted electronic proposals. | 72 | 159.5 miles of conduit, 124 miles of fiber and 4 towers have been completed. | 2 | Dependant upon electronics selected and purchased. | 0 | Dependant upon construction, electronics selected and purchased. | 2012-02-28 13:00 | 2012-02-28 13:00 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2012 | Q1 | Q1 - 2012 | 5923 | 5561 | TRUE | 79 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 99 | Fiber splicing plan completed and minor changes may take place after electronics have been selected. | 99 | Easements obtained, reviewing final survey to file in Clerk of Court. | 100 | Completed | 100 | Completed | 10 | Purchased some electronics to connect traffic CAIs. County staff reviewing submitted electronic proposals. | 86 | 182.75 miles of conduit, 150.5 miles of fiber and all towers have been completed. | 2 | Dependant upon electronics selected and purchased. | 2 | Dependant upon electronics selected and purchased. | 2012-05-04 07:46 | 2012-05-04 07:46 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2012 | Q2 | Q2 - 2012 | 7125 | 6190 | TRUE | 85 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 99 | Fiber Splicing plan completed and minor changes may take place after electronics are being installed. | 100 | Completed | 100 | Completed | 100 | Finalized Building entrances for each CAI | 10 | Purchased some electronics to connect traffic CAIs, County has issued a PO to purchase Carrier Ethernet and Firewall equipment to Cyan and Torrey Point. | 95 | 196 miles of fiber and conduit installed and all towers have been installed. Started building terminations on July 1, 2012 | 2 | Dependant upon electronic equipment. | 2 | Dependant upon electronic equipment. | 2012-08-17 16:40 | 2012-08-17 16:40 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2012 | Q3 | Q3 - 2012 | 7845 | 6627 | TRUE | 90 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 95 | Purchased all equipment except the wireless access points. | 99 | 205 Miles of conduit, 230 miles of fiber and 5 towers have been constructed. | 50 | Wireless Access points to be purchased and installed. Network Interface devices (NIDS) to be installed at remaining CAIs. | 100 | Completed | 2012-11-13 13:53 | 2012-11-13 13:53 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2012 | Q4 | Q4 - 2012 | 9129 | 7910 | TRUE | 98 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 98 | Ordered Wireless Access Points waiting on delivery of equipment. | 100 | Completed | 98 | Ordered Wireless Access Points waiting on delivery of equipment. | 100 | Completed | 2013-03-06 15:32 | 2013-03-06 15:32 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2013 | Q1 | Q1 - 2013 | 9177 | 8010 | TRUE | 100 | Completed | 0 |  | N/A | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2013-04-15 08:08 | 2013-04-15 08:08 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570038 | 2010 | Q2 | Q2 - 2010 | 61 | 1306 | FALSE | 30 |  | 0 |  |  | 100 |  | 45 |  | 0 |  | 75 |  | 20 |  | 15 |  | 10 |  | 10 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2010 | Q3 | Q3 - 2010 | 395 | 1464 | TRUE | 35 | Completed all network and engineering designs simultaneously | 0 |  | N/A | 100 | Complete | 100 | Completed all network designs for all sites simultaneously | 0 | N/A - All construction will be on our own property | 100 | Completed all engineering designs for all sites simultaneously | 20 | On track | 0 | During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. | 0 | Pending 2g | 0 | Pending 2g | 0 | On track | 2010-11-23 17:12 | 2010-11-23 17:12 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2010 | Q4 | Q4 - 2010 | 1101 | 2143 | TRUE | 40 | Completed all network and engineering designs simultaneously. Construction procurement process still in progress. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 20 | Construction procurement process still in progress. | 30 | DWDM and ADM equipment has been purchased for Zolfo Springs project site. | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 2011-02-11 17:24 | 2011-02-11 17:24 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2011 | Q1 | Q1 - 2011 | 1821 | 2654 | TRUE | 21 | Completed all network and engineering designs simultaneously. Construction procurement process is complete. Variance due to delay in construction procurement activities. Per April 19th guidance from NTIA, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Completed all dense wavelength divisional multiplexing and synchronous optical networking system designs. | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 4 | Construction contractor has been selected. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 25 | Most dense wavelength divisional multiplexing and synchronous optical networking systems have been purchased. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 2011-05-02 09:40 | 2011-05-02 09:40 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2011 | Q2 | Q2 - 2011 | 3379 | 3453 | TRUE | 26 | Construction is complete. The percentage complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 8 | All construction work is complete. The percentage complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 30 | Most dense division wavelength multiplexing and ADM equipment has been purchased. The support and management equipment for our MOSS network will continue into next quarter. | 30 | Our network build will be the deployment of transport equipment (2i) at each of our interconnection sites. | 30 | Deployment of dense division wavelength multiplexing equipment is in progress and the ADM equipment will follow in the 3rd quarter. | 10 | Bruce and Clarksville wavelength testing is complete. | 2011-08-30 13:37 | 2011-08-30 13:37 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2011 | Q3 | Q3 - 2011 | 4335 | 4024 | TRUE | 36 | All deployments for our DWDM, ADM and IP management systems are complete. Testing for each of the systems is also complete. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 35 | Construction and equipment deployments have been completed. | 37 | We've been invoiced for the majority of our equipment purchases. | 100 | Complete | 100 | Complete | 100 | Complete | 2011-11-30 14:40 | 2011-11-30 14:40 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2011 | Q4 | Q4 - 2011 | 5299 | 4970 | TRUE | 39 | All construction and equipment deployments are complete. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 52 | The construction has been completed. Finalizing invoices with the construction contractor. Percent complete is strictly based on the budget. | 37 | All equipment has been purchased. Percent complete is strictly based on the budget. We will under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:46 | 2012-02-27 15:46 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2012 | Q1 | Q1 - 2012 | 6055 | 5627 | TRUE | 39 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 53 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 37 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete | 2012-05-14 12:00 | 2012-05-14 12:00 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2012 | Q2 | Q2 - 2012 | 6515 | 5872 | TRUE | 39 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 53 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 37 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete. | 2012-07-27 12:11 | 2012-07-27 12:11 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2012 | Q3 | Q3 - 2012 | 7693 | 6531 | TRUE | 39 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 54 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 37 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 22:59 | 2012-10-30 22:59 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2012 | Q4 | Q4 - 2012 | 8531 | 7257 | TRUE | 39 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 54 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 37 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 16:23 | 2013-01-30 16:23 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2013 | Q1 | Q1 - 2013 | 12029 | 10194 | TRUE | 100 | Final expenses will be for closeout costs. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 100 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 2014-04-14 12:10 | 2014-04-14 12:10 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570039 | 2010 | Q2 | Q2 - 2010 | 62 | 1281 | FALSE | 9 |  | 70 |  |  | 100 |  | 100 |  | 45 |  | 30 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2010 | Q3 | Q3 - 2010 | 329 | 1431 | TRUE | 7 | N/A | 65 | Contracts, Auditing, Admin | Requirement to issue new RFPs has delayed | 99 | Final EA Submitted, awaiting FONSI | 70 | Requirement to issue new RFPs has delayed | 20 | Requirement to issue new RFPs has delayed | 15 | Requirement to issue new RFPs has delayed | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-16 21:38 | 2010-11-16 21:38 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2010 | Q4 | Q4 - 2010 | 1183 | 2217 | TRUE | 10 | See 3 following for explanation of variance. | 75 |  | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 100 | See 3 following for explanation of variance. | 75 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 25 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 20 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 0 | See 3 following for explanation of variance. | 0 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 0 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 0 | See 3 following for explanation of variance. | 0 | See 3 following for explanation of variance. | 2011-02-16 14:54 | 2011-02-16 14:54 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2011 | Q1 | Q1 - 2011 | 2165 | 2828 | TRUE | 8 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. | 90 | contracts, etc | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. | 100 | OpenCape has a continual process of review to ensure compliance with its EA FONSI. This process involves OpenCape, its field survey and engineering contractor, and its environmental engineering contractor. Potential deviations from the original EA are identified and will be consolidated into a future submission for amendment of the EA. OpenCape has also engaged the Army Corps of Engineers for the crossing of the Cape Cod Canal and will fulfill the specific EA requirement of their process as stated in the EA and FONSI. | 75 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. The preliminary design of the microwave, fiber optic, transport, and municipal RAN are near complete. Specific design is well underway. | 35 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. Preliminary work to secure rights of way is well underway. | 35 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. Preliminary work related to selecting a construction manager for the renovation of the collocation center, the submission of special permit applications, obtaining licenses to towers, and securing an FCC 700Mhz waiver are well underway. | 0 | N/A | 5 | OpenCapeâ€™s contractor has engaged vendors of fiber optics, optronics, and other equipment to determine qualified bidders and issue bid documents. Major equipment purchases are anticipated in Y2Q2 and Y2Q3 of fiber and optronics. | 0 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. | 0 | Equipment deployment is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, and construction completion. It is anticipated equipment deployment will follow at expected pace. | 0 | Network testing shall keep pace with the construction of segments of the network. | 2011-05-19 11:30 | 2011-05-19 11:30 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2011 | Q2 | Q2 - 2011 | 2933 | 3224 | TRUE | 15 | Due primarily to a requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. | 100 |  | Completed. | 100 | OpenCape has a continual process of review to ensure compliance with its EA FONSI. This process involves OpenCape, its field survey and engineering contractor, and its environmental engineering contractor. Potential deviations from the original EA are identified and will be consolidated into a future submission for amendment of the EA. OpenCape has also engaged the Army Corps of Engineers for the crossing of the Cape Cod Canal and will fulfill the specific EA requirement of their process as stated in the EA and FONSI. | 80 | Due primarily to a requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. The design of the microwave, fiber optic, transport, and municipal RAN are near complete. As engineering site visits are conducted and detailed analysis performed there are issues that arise to delay completion of the Network Design. For example, OpenCape has intended to use an existing fire tower on Martha's Vineyard for a microwave link from Cape Cod to the Island. Preliminary analysis indicates this tower is currently overloaded. A detailed engineering evaluation is scheduled to determine if the tower can be altered to accommodate OpenCape equipment while simultaneously alternative towers are being evaluated. | 50 | Due primarily to a requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. OpenCape is fully engaged in the process of submitting special permits, developing the contractual basis of leases to towers to support the microwave component, and applying for access to Verizon Central Offices. The Army Corps of Engineers permitting of critical crossings at the Cape Cod Canal and the Taunton River process is underway, but is slow and represents a critical element of delay in this category. Obtaining access to towers for the placement of microwave equipment is also a time consuming process because the tower owners must go through a process required by Chapter 30B of the Massachusetts General Laws; however, this process is moving forward at an acceptable pace. | 45 | Due primarily to a requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. OpenCape has contracted with Stateside Construction to renovate the former Barnstable County Public Safety Building to become the OpenCape Regional Collocation Center. An RFP was issued to select a contractor to build the Collocation Data Center in the ground floor of the renovated building. The submission of special permit applications, obtaining licenses to towers, and application for securing an FCC 700Mhz waiver are well underway and progressing at an acceptable pace. | 0 | N/A | 15 | OpenCapeâ€™s contractor has engaged vendors of fiber optics, optronics, and other equipment to determine qualified bidders and issue bid documents. The first order of 35 miles of fiber has been placed with an anticipated delivery in September, 2011. The delivery date was 8 weeks after order placement. This is consistent with the timeline of anticipated completed make ready and sub-contractor selection for installation of the fiber beginning in October 2011. | 0 | Due primarily to a requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. | 0 | Equipment deployment is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, and construction completion. It is anticipated equipment deployment will follow at an acceptable pace. | 0 | Network testing shall keep pace with the construction of segments of the network. | 2011-08-05 14:21 | 2011-08-05 14:21 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2011 | Q3 | Q3 - 2011 | 3931 | 3804 | TRUE | 18 | OpenCape lags its Baseline Projection and federal expenditure pace for several reasons: 1) OpenCape pursued its grant with a construction contractor as a partner, but had to initiate a new RFP process months into its grant; 2) the process of obtaining a Finding of No Significant Impact was far longer than anticipated; 3) the process of negotiating the many legal contracts associated with the project has taken longer than anticipated; 4) Commonwealth of Massachusetts procurement laws have caused delays in obtaining underlying rights or leases from county and municipal entities; 5) the process of negotiating Master Agreements with utility pole and conduit owners was far longer than anticipated; 6) the capacity of utility companies to perform make ready assessment and make ready work is limited and insufficient using conventional processes; 7) pole survey and make ready work was negatively impacted in the third quarter of 2011 by a Verizon strike from August 7-20 and Hurricane Irene | 100 |  | Completed | 100 | OpenCape has a continual process of review to ensure compliance with its EA FONSI. Though the EA Assessment and FONSI are complete,an amendment was necessary to record changes from the original submission. | 85 | Early delays caused by the transition to a new contractor have been overcome and the design of the microwave, fiber optic, transport, and municipal RAN are near complete. | 60 | Early delays caused by the transition to a new contractor have been overcome and OpenCape has submitted necessary applications to obtain access to two crossings of the Cape Cod Canal. Obtaining access to towers for the placement of microwave equipment is underway but the process is slow as the owners of the towers are public entities that must comply with Commonwealth of Massachusetts procurement laws. | 55 | Early delays caused by the transition to a new contractor have been overcome and OpenCape is fully engaged in the process of submitting applications for and receiving permits locally, with state agencies, railroad owners, and others. Permit applications have been submitted for the renovation of the former Barnstable County Public Safety building with the necessary entities. | 0 | N/A | 30 | OpenCape is on a path for procurement consistent with on time completion of the project. The first fiber delivery of nine reels arrived in September, 2011 and deliveries of 35 miles each month are anticipated. Ciena was selected as the provider of routing and switching equipment and orders will be placed early in the fourth quarter. The completion of the microwave path assessment and start of frequency studies will result in the potential order of radio equipment in the fourth quarter. | 5 | Network Build is greatly dependent on make ready completion. It is therefore delayed. However, sub-contractors for fiber construction have been selected and materials are in hand to begin construction. Make ready has begun in the National Grid territory of the project. Underground work is primed to begin, but awaits a positive Environmental Assessment Amendment review. Microwave construction is dependent on obtaining lease rights from municipal authorities under a complex and slow procurement process required by Commonwealth of Massachusetts Chapter 30B. | 0 | Equipment deployment is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, and construction completion. It is anticipated equipment deployment will follow at an acceptable pace as the vendor has been selected for switching and routing and configuration of DWDM can be achieved in parallel with construction of the fiber. | 2 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber. | 2011-11-09 10:16 | 2011-11-09 10:16 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2011 | Q4 | Q4 - 2011 | 5211 | 4881 | TRUE | 25 | OpenCape lags its Baseline Projection and federal expenditure pace for several reasons: 1) OpenCape pursued its grant with a construction contractor as a partner, but had to initiate a new RFP process six months into its grant; 2) the process of obtaining a Finding of No Significant Impact was far longer than anticipated; 3) the process of negotiating the many legal contracts associated with the project has taken longer than anticipated; 4) Commonwealth of Massachusetts procurement laws have caused delays in obtaining underlying rights or leases from county and municipal entities; 5) the process of negotiating Master Agreements with utility pole and conduit owners was far longer than anticipated; 6) the capacity of utility companies to perform make ready assessment and make ready work is limited and insufficient using conventional processes; 7) pole survey and make ready work was negatively impacted by a Verizon strike and Hurricane Irene in August, and an unusual October Noreaster | 80 |  | Additional contract work was required that has necessitated continued work through the fourth quarter. OpenCape Board has authorized up to $325,000 additional to be expended in this milestone from Construction. | 100 | OpenCape received its original FONSI, but submitted an Environmental Assessment Amendment to reflect route and other changes. Approval of the EA Amendment was received in the fourth quarter of 2011. | 88 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps are near complete. | 60 | All pole and conduit applications submitted. Pole make ready well underway and licenses beginning to flow. Conduit applications all in at least rod and rope phase, with many in innerduct placement phase. OpenCape is negotiating agreements for the crossing of the Cape Cod Canal at two locations and the crossing of the Taunton River. Early delays have been overcome and agreements are expected in Q1 2012. Obtaining access to towers as leases under Massachusetts General Law Chapter 30B requirements proved too difficult to achieve in time to meet engineering and construction time-lines. A license is currently being sought for each tower with a parallel long term lease process. | 60 | Early delays caused by the transition to a new contractor have been overcome and OpenCape is fully engaged in the process of submitting applications for and receiving permits locally, with state agencies, railroad owners, and others. | 0 | N/A | 75 | OpenCape is on a path for procurement consistent with on time completion of the project. Nearly half of the fiber reels are in hand for the backbone and all is expected to be delivered by June. Switching and routing equipment has been delivered. Microwave equipment has been ordered and is in shipment for delivery in early January. Elevator for the building has been ordered. DWDM equipment has been delivered and is undergoing assembly and configuration. | 15 | Network Build is greatly dependent on make ready completion. It is therefore delayed. However, sub-contractors for fiber construction have been selected and materials are in hand to begin construction. Fiber splicing and lateral sub-contractor selection process is underway. Make ready is complete and licenses in hand to build at least 40 miles of fiber in the first quarter, consistent with current planning. Approximately 3200 feet of conduit has been placed in the fourth quarter representing approximately 25% of the new underground work required. | 0 | Equipment deployment is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, and construction completion. It is anticipated equipment deployment will follow at an acceptable pace in parallel with fiber construction. | 5 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber. | 2012-02-23 14:34 | 2012-02-23 14:34 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2012 | Q1 | Q1 - 2012 | 5529 | 5359 | TRUE | 47 | OpenCape lags its Baseline Projection and federal expenditure pace for several reasons: 1) OpenCape pursued its grant with a construction contractor as a partner, but had to initiate a new RFP process six months into its grant; 2) the process of obtaining a Finding of No Significant Impact was far more lengthy than anticipated; 3) the process of negotiating the many legal contracts associated with the project has taken longer than anticipated; 4) Commonwealth of Massachusetts procurement laws have caused delays in obtaining underlying rights or leases from county and municipal entities; 5) the process of negotiating Master Agreements with utility pole and conduit owners took far longer than anticipated; 6) the capacity of utility companies to perform make ready assessment and make ready work is limited and insufficient using conventional processes; 7) pole survey and make ready work was negatively impacted by a Verizon strike and Hurricane Irene in August, and an unusual October 20 | 92 |  | Additional contract work was required that has necessitated continued work through the fourth quarter. OpenCape Board has authorized up to $525,000 additional to be expended in this milestone from Construction. | 100 | OpenCape received its original FONSI, but submitted an Environmental Assessment Amendment to reflect route and other changes. Approval of the EA Amendment was received in the fourth quarter of 2011. | 95 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps are near complete. | 75 | All pole and conduit applications submitted, all assessments done, and all invoices for make ready paid. Pole make ready well underway and licenses flowing. Conduit applications all in at least rod and rope phase, with many in innerduct placement phase or license issued. OpenCape is negotiating agreements for the crossing of the Cape Cod Canal at two locations and the crossing of the Taunton River. Early delays have been overcome and agreements are expected in Q2 2012. Obtaining access to towers as leases under Massachusetts General Law Chapter 30B requirements proved too difficult to achieve in time to meet engineering and construction time-lines. A license is currently being sought for each tower with a parallel long term lease process. | 85 | Early delays caused by the transition to a new contractor have been overcome and OpenCape is fully engaged in the process of submitting applications for and receiving permits locally, with state agencies, railroad owners, and others. | 0 | N/A | 77 | OpenCape is on a path for procurement consistent with on time completion of the project. Over 75% of the fiber reels are in hand and all is expected to be delivered by June. Most switching, routing, and microwave equipment has been delivered. DWDM equipment assembly and configuration is complete. Elevator for the building has been ordered. | 31 | Sub-contractors for fiber construction have begun construction with 46 miles complete in Q1 2012. Approximately 3200 feet of conduit has been placed, representing approximately 25% of the new underground work required. | 25 | Equipment deployment is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, and construction completion. It is anticipated equipment deployment will follow at an acceptable pace in parallel with fiber construction. | 10 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber. | 2012-04-26 10:27 | 2012-04-26 10:27 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2012 | Q2 | Q2 - 2012 | 6903 | 6078 | TRUE | 59 | OpenCape lags its Baseline Projection and federal expenditure pace for several reasons: 1) OpenCape pursued its grant with a construction contractor as a partner, but had to initiate a new RFP process six months into its grant; 2) the process of obtaining a Finding of No Significant Impact was far more lengthy than anticipated; 3) the process of negotiating the many legal contracts associated with the project has taken longer than anticipated; 4) Commonwealth of Massachusetts procurement laws have caused delays in obtaining underlying rights or leases from county and municipal entities; 5) the process of negotiating Master Agreements with utility pole and conduit owners took far longer than anticipated; 6) the capacity of utility companies to perform make ready assessment and make ready work is limited and insufficient using conventional processes; 7) pole survey and make ready work was negatively impacted by a Verizon strike and Hurricane Irene in August, and an unusual October 20 | 95 |  | Additional contract work was required that has necessitated continued work through the fourth quarter. OpenCape Board has authorized up to $525,000 additional to be expended in this milestone from Construction. | 100 | OpenCape received its original FONSI, but submitted an Environmental Assessment Amendment to reflect route and other changes. Approval of the EA Amendment was received in the fourth quarter of 2011. | 98 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps are near complete. | 90 | All pole and conduit applications submitted, all assessments done, and all invoices for make ready paid. Pole make ready well underway and licenses flowing. Conduit lease applications all received less one. OpenCape received easement for both bridge crossings of the Cape Cod Canal from the Army Corps of Engineers. Negotiating contract for crossing of the Taunton River. Licenses for all Cape Cod towers in hand or near issued. License for primary tower on Martha's Vineyard in hand. Secondary towers under negotiation. Penikese Island link is a challenge and negotiation of an additional link from Fairhaven to Cuttyhunk Island is underway. | 95 | All building and fiber network permits are in hand less one minor road work permit. Permits for installation of antennas on towers are in preparation. | 0 | N/A | 90 | OpenCape is on a path for procurement consistent with on time completion of the project. Over 96% of the fiber reels are in hand. All switching and routing equipment has been delivered. DWDM equipment assembly and configuration is complete. 75% of microwave radio equipment is in hand. Elevator for the building has been delivered and installed. Generator for the building has been ordered. Chillers, PDU, and UPS for Collocation Data Center remain to be ordered in Q3. | 45 | 94 miles of fiber has been installed and an additional 40 miles has been released for construction. Over 50% of underground construction is complete. The Cape Cod Canal Railroad Bridge construction is complete. | 30 | Equipment deployment is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, and construction completion. It is anticipated equipment deployment will follow at an acceptable pace in parallel with fiber construction. DWDM equipment is assembled and configured. Construction in at least 9 of the 11 regeneration sites is expected to be complete in July, 2012 with installation of DWDM shortly thereafter in those sites to await fiber connection. | 20 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber and during splicing. | 2012-08-07 15:40 | 2012-08-07 15:40 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2012 | Q3 | Q3 - 2012 | 8165 | 6793 | TRUE | 66 | OpenCape lags its Baseline Projection and federal expenditure pace for several reasons: 1) OpenCape pursued its grant with a construction contractor as a partner, but had to initiate a new RFP process six months into its grant; 2) the process of obtaining a Finding of No Significant Impact was far more lengthy than anticipated; 3) the process of negotiating the many legal contracts associated with the project has taken longer than anticipated; 4) Commonwealth of Massachusetts procurement laws have caused delays in obtaining underlying rights or leases from county and municipal entities; 5) the process of negotiating Master Agreements with utility pole and conduit owners took far longer than anticipated; 6) the capacity of utility companies to perform make ready assessment and make ready work is limited and insufficient using conventional processes; 7) pole survey and make ready work was negatively impacted by a Verizon strike and Hurricane Irene in August, and an unusual October 20 | 95 |  | Additional contract work was required that has necessitated continued work through the fourth quarter. | 100 | OpenCape received its original FONSI, but submitted an Environmental Assessment Amendment to reflect route and other changes. Approval of the EA Amendment was received in the fourth quarter of 2011. | 98 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps are near complete. | 95 | All pole and conduit applications submitted, all assessments done, and all invoices for make ready paid. Pole make ready well underway and licenses flowing. All off-Cape path has been released for construction. Conduit lease applications all received less one. OpenCape received easement for both bridge crossings of the Cape Cod Canal from the Army Corps of Engineers. Negotiating contract for crossing of the Taunton River. Licenses for all Cape Cod towers in hand or near issued. License for primary tower on Martha's Vineyard in hand. Secondary towers under negotiation. | 95 | All building and fiber network permits are in hand. Permits for installation of antennas on towers are in preparation. | 0 | N/A | 92 | OpenCape is on a path for procurement consistent with on time completion of the project. One hundred percent of the fiber reels are in hand. All switching and routing equipment has been delivered. DWDM equipment assembly and configuration is complete. 75% of microwave radio equipment is in hand. Elevator for the building has been delivered and installed. Generator for the building has been ordered and is enroute for delivery. Chillers, PDU, and UPS for Collocation Data Center ordered. | 60 | 180 miles of fiber has been installed and an additional 55 miles has been released for construction. Over 90% of underground construction is complete. Fifteen anchor laterals are complete and interior work finished. Two microwave tower laterals complete. The Cape Cod Canal Railroad Bridge construction is complete. | 35 | Equipment deployment is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, and construction completion. It is anticipated equipment deployment will follow at an acceptable pace in parallel with fiber construction. DWDM equipment is assembled and configured. Construction in 11 regeneration sites has begun. Installation of DWDM will begin after construction is complete. | 25 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber and during splicing. | 2012-11-30 08:57 | 2012-11-30 08:57 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2012 | Q4 | Q4 - 2012 | 9013 | 7789 | TRUE | 77 | OpenCape lags its Baseline Projection and federal expenditure pace for several reasons: 1) OpenCape pursued its grant with a construction contractor as a partner, but had to initiate a new RFP process six months into its grant; 2) the process of obtaining a Finding of No Significant Impact was far more lengthy than anticipated; 3) the process of negotiating the many legal contracts associated with the project has taken longer than anticipated; 4) Commonwealth of Massachusetts procurement laws have caused delays in obtaining underlying rights or leases from county and municipal entities; 5) the process of negotiating Master Agreements with utility pole and conduit owners took far longer than anticipated; 6) the capacity of utility companies to perform make ready assessment and make ready work is limited and insufficient using conventional processes; 7) pole survey and make ready work was negatively impacted by a Verizon strike and Hurricane Irene in August, and an unusual October 2011 N | 95 |  | Additional contract work was required that has necessitated continued work through the fourth quarter. | 100 | OpenCape received its original FONSI, but submitted an Environmental Assessment Amendment to reflect route and other changes. Approval of the EA Amendment was received in the fourth quarter of 2011. | 98 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps are near complete. Final patch panel assignments are in progress. | 95 | All pole and conduit applications submitted, all assessments done, and all invoices for make ready paid. Pole make ready well underway and licenses flowing. All off-Cape path has been released for construction. Conduit lease applications are complete. OpenCape received easement for both bridge crossings of the Cape Cod Canal from the Army Corps of Engineers. Negotiating contract for crossing of the Taunton River. Licenses for all Cape Cod towers in hand or near issued. License for primary and secondary tower on Martha's Vineyard in hand. | 95 | All building and fiber network permits are in hand. Permits for installation of antennas on towers are in preparation and have been submitted for 6 locations. Initial review of requirements for all sites has been completed in preparation for final submissions. | 0 | N/A | 92 | One hundred percent of the fiber reels are in hand. All switching and routing equipment has been delivered. DWDM equipment assembly and configuration is complete. 75% of microwave radio equipment is in hand. Ordering of frequency specific components lags until final FCC licenses are approved. Generator for the regional data center has been installed on it's pad. Electical switchboard equipment remains to be received to complete hookup. Chillers, PDU, and UPS for the regional data center have been received and are in the process of being installed. All equipment cabinets have been installed. | 73 | 222 route miles of fiber have been installed and an additional 62 route miles have been released for construction. Underground construction on all backbone segments is complete. Twenty anchor laterals are complete and interior work finished. Cable pull through existing conduit for the second Cape Cod Canal crossing was completed. | 45 | Construction of 2 regeneration sites including DWDM and carrier Ethernet equipment is complete. Construction and installation of equipment in 8 additional sites is underway. | 30 | Approximately 10% of the network is lit with production electronic equipment for final configuration, tuning, and testing. Other network testing will keep pace with the construction of segments of the network. Initial testing of all fiber was completed at delivery of the fiber. Additional fiber testing will occur when segments of the network are constructed and spliced end to end along each segment. | 2013-02-27 14:14 | 2013-02-27 14:14 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2013 | Q1 | Q1 - 2013 | 10053 | 8583 | TRUE | 83 | OpenCape lags its Baseline Projection and federal expenditure pace for several reasons: 1) OpenCape pursued its grant with a construction contractor as a partner, but had to initiate a new RFP process six months into its grant; 2) the process of obtaining a Finding of No Significant Impact was far more lengthy than anticipated; 3) the process of negotiating the many legal contracts associated with the project has taken longer than anticipated; 4) Commonwealth of Massachusetts procurement laws have caused delays in obtaining underlying rights or leases from county and municipal entities; 5) the process of negotiating Master Agreements with utility pole and conduit owners took far longer than anticipated; 6) the capacity of utility companies to perform make ready assessment and make ready work is limited and insufficient using conventional processes; 7) pole survey and make ready work was negatively impacted by a Verizon strike and Hurricane Irene in August, and an unusual October 2011 N | 95 |  | Additional contract work was required that has necessitated continued work through the first quarter. | 100 | Completed | 98 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps and patch panel assignments are complete. Final as-builts are in preparation. | 96 | All rights of way are complete. Additional late billing of make-ready for the rights of way are still being received. | 95 | All building and fiber network permits are in hand. Permits for installation of antennas for the microwave network are in progress. Building permit for 1 site has been received. When sufficient site permits are in hand to support crew mobilization, construction will begin. | 0 | N/A | 93 | All fiber, switching, routing, and DWDM equipment has been delivered. Installation is proceeding with Verizon as the barrier to completion. Ordering of frequency specific components of the microwave system lags until final FCC licenses are approved. All equipment associated with the collocation data center has been received with final hookup, turn up, and test is dependent upon NStar power upgrade. | 81 | 300 of 311 route miles of new fiber have been installed. 78 new route miles were added this quarter. All but 0.6 of the remaining route miles were under construction or released for construction. | 50 | Deployment of equipment was underway in all 11 regeneration facilities. DWDM equipment was installed in all sites, with 5 sites powered up in readiness for testing, tuning, and calibration of equipment. Deployment of microwave equipment has not yet begun. | 35 | Post-construction testing began during this quarter. Initial OTDR testing was used to begin validation of the fiber installation, performance of the fiber, and match of the installation to design signal loss budgets. | 2013-06-05 07:44 | 2013-06-05 07:44 | 7679 | 7679 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2013 | Q2 | Q2 - 2013 | 10359 | 8805 | TRUE | 90 | OpenCape lags its Baseline Projection and federal expenditure pace for several reasons: 1) OpenCape pursued its grant with a construction contractor as a partner, but had to initiate a new RFP process six months into its grant; 2) the process of obtaining a Finding of No Significant Impact was far more lengthy than anticipated; 3) the process of negotiating the many legal contracts associated with the project has taken longer than anticipated; 4) Commonwealth of Massachusetts procurement laws have caused delays in obtaining underlying rights or leases from county and municipal entities; 5) the process of negotiating Master Agreements with utility pole and conduit owners took far longer than anticipated; 6) the capacity of utility companies to perform make ready assessment and make ready work is limited and insufficient using conventional processes; 7) pole survey and make ready work was negatively impacted by a Verizon strike and Hurricane Irene in August, and an unusual October 2011 N | 97 | Misc contract work | Additional contract work was required that has necessitated continued work through the first quarter. | 100 | Completed. | 100 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps and patch panel assignments are complete. | 98 | All rights of way are complete. Additional late billing of make-ready for the rights of way are still being received. Approval of the additional laterals this quarter triggered the need for additional pole license agreements. Engineering work began that will lead to additional pole license applications as needed. | 98 | All building and fiber network permits are in hand. Permits for installation of antennas for the microwave network are in progress. Building permit for 1 site has been received. When sufficient site permits are in hand to support crew mobilization, construction will begin. | 0 | N/A | 94 | All fiber, switching, routing, and DWDM equipment has been delivered. Installation is proceeding with Verizon as the barrier to completion. Ordering of frequency specific components of the microwave system lags until final FCC licenses are approved. All equipment associated with the collocation data center has been received with final hookup, turn up, and test is dependent upon NStar power upgrade. | 90 | 300 of 311 route miles of new fiber have been installed. 78 new route miles were added this quarter. All but 0.6 of the remaining route miles were under construction or released for construction. | 90 | Deployment of equipment was underway in all 11 regeneration facilities. DWDM equipment was installed in all sites, with 5 sites powered up in readiness for testing, tuning, and calibration of equipment. Deployment of microwave equipment has not yet begun. | 60 | Post-construction testing began during this quarter. Initial OTDR testing was used to begin validation of the fiber installation, performance of the fiber, and match of the installation to design signal loss budgets. | 2013-07-30 15:23 | 2013-07-30 15:23 | 7679 | 7679 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2013 | Q3 | Q3 - 2013 | 11339 | 9470 | TRUE | 95 | Microwave component of the project is delaying completion, but also allowing more time for make ready work on the additional laterals. Local permitting processes are holding up the microwave portion of the project. | 99 | Misc contract work | Remaining microwave site leases are delaying completion of miscellaneous contract work. | 100 | Complete | 100 | Complete | 99 | Rights of way for the microwave (leases) and pole licenses on the additional make ready are remaining. | 99 | Special permits and building permits for microwave sites are holding up completion of the project. | 0 | N/A | 99 | Some minor components related to microwave mounts remain to be ordered, depending on approval of construction drawings. Materials are readily available. | 94 | Microwave component approvals are delaying completion of the network build, though allowing more time for make ready work on additional laterals. | 95 | Microwave component approvals are delaying completion of the network build, though allowing more time for make ready work on additional laterals. | 97 | All fiber testing is complete except the additional laterals. Microwave network testing remains. | 2013-11-21 19:58 | 2013-11-21 19:58 | 7679 | 7679 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2013 | Q4 | Q4 - 2013 | 12277 | 10448 | TRUE | 100 | Complete | 100 | Misc contract work | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-06-19 15:43 | 2014-06-19 15:43 | 7679 | 7679 | OpenCape Corporation | TRUE
NT10BIX5570040 | 2010 | Q2 | Q2 - 2010 | 63 | 1307 | FALSE | 30 |  | 0 |  |  | 100 |  | 80 |  | 0 |  | 90 |  | 75 |  | 20 |  | 15 |  | 15 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2010 | Q3 | Q3 - 2010 | 399 | 1466 | TRUE | 30 | On track | 0 |  | N/A | 100 | Complete | 80 | On track | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 75 | On track | 0 | During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. | 0 | Pending 2g | 0 | Pending 2g | 0 | On track | 2010-11-23 17:25 | 2010-11-23 17:25 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2010 | Q4 | Q4 - 2010 | 1157 | 2197 | TRUE | 35 | Completed all network and engineering designs simultaneously. Construction procurement process still in progress. Variance due to delay in construction procurement activities; award anticipated in February 2011. | 0 |  | N/A | 100 | Complete | 95 | Completed wavelength system designs for all sites. Variance due to delay in design for SONET system. | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 75 | Construction procurement process still in progress; award anticipated in February 2011. | 10 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 2011-02-15 17:55 | 2011-02-15 17:55 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2011 | Q1 | Q1 - 2011 | 2363 | 2927 | TRUE | 21 | Completed all network and engineering designs simultaneously. Construction procurement process is complete. Variance due to delay in construction procurement activities. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Completed all dense wavelength divisional multiplexing and synchronous optical networking system designs. | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 4 | Construction contractor has been selected. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 25 | Most dense wavelength divisional multiplexing and synchronous optical networking systems have been purchased. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 3 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 2011-05-27 08:08 | 2011-05-27 08:08 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2011 | Q2 | Q2 - 2011 | 3363 | 3445 | TRUE | 30 | Construction has moved along very quickly. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 4 | Construction is either complete or under way at each site. The percentage complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 35 | Most equipment has been purchased. The percentage complete is based on invoiced expenses in 2Q. | 10 | Our network build will be the deployment of transport equipment (2i) at each of our interconnection sites. Delays are due to longer construction procurement process than expected. | 10 | Equipment has been deployed at Soperton. The equipment deployment will follow the completion of the inside plant work. Delays are due to longer construction procurement process than expected. | 5 | The dense division multiplexing equipment has been tested in Soperton. The remaining testing will take place as the rest of the equipment is deployed. Delays are due to longer construction procurement process than expected. | 2011-08-29 23:57 | 2011-08-29 23:57 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2011 | Q3 | Q3 - 2011 | 4303 | 4002 | TRUE | 33 | Construction and equipment deployments have been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 7 | Construction is complete. The percentage complete is strictly based on the budget. | 38 | We've been invoiced for the majority of our equipment purchases. | 100 | Complete | 100 | Complete | 100 | Complete | 2011-11-29 10:36 | 2011-11-29 10:36 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2011 | Q4 | Q4 - 2011 | 5301 | 4972 | TRUE | 37 | All construction and equipment deployments are complete. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 36 | The construction has been completed. Finalizing invoices with the construction contractor. Percent complete is strictly based on the budget. | 38 | All equipment has been purchased. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:50 | 2012-02-27 15:50 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2012 | Q1 | Q1 - 2012 | 6057 | 5628 | TRUE | 37 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 38 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete | 2012-05-14 12:01 | 2012-05-14 12:01 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2012 | Q2 | Q2 - 2012 | 7149 | 6202 | TRUE | 37 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 38 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete | 2012-08-20 10:00 | 2012-08-20 10:00 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2012 | Q3 | Q3 - 2012 | 7695 | 6532 | TRUE | 37 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 38 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete | 2012-10-30 23:00 | 2012-10-30 23:00 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2012 | Q4 | Q4 - 2012 | 8539 | 7269 | TRUE | 37 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 38 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete | 2013-01-30 16:40 | 2013-01-30 16:40 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2013 | Q1 | Q1 - 2013 | 12033 | 10196 | TRUE | 100 | Final expenses will be for closeout costs. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 100 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 2014-04-14 12:15 | 2014-04-14 12:15 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2010 | Q2 | Q2 - 2010 | 64 | 1308 | FALSE | 35 |  | 0 |  |  | 100 |  | 60 |  | 0 |  | 90 |  | 25 |  | 30 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2010 | Q3 | Q3 - 2010 | 401 | 1467 | TRUE | 30 | On track | 0 |  | N/A | 100 | Complete | 15 | Managing multiple projects; for efficiency reasons, modified project prioritization. Will be on track in 4Q10 and 1Q11. | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 15 | See 2c | 0 | During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. | 0 | Pending 2g | 0 | Pending 2g | 0 | On track | 2010-11-23 17:33 | 2010-11-23 17:33 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2010 | Q4 | Q4 - 2010 | 907 | 1948 | TRUE | 30 | Completed all network and engineering designs simultaneously. Construction RFP still in progress | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 20 | Construction RFP still in progress. | 0 | Pending 2f | 0 | Pending 2f | 0 | Pending 2f | 0 | Pending 2f | 2011-01-29 17:13 | 2011-01-29 17:13 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2011 | Q1 | Q1 - 2011 | 2365 | 2928 | TRUE | 12 | Completed all network and engineering designs simultaneously. Construction procurement process is complete. Variance due to delay in construction procurement activities. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Completed all dense wavelength divisional multiplexing and synchronous optical networking system designs. | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 4 | Construction contractor has been selected. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 13 | Most dense wavelength divisional multiplexing and synchronous optical networking systems have been purchased. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 2011-05-27 08:10 | 2011-05-27 08:10 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2011 | Q2 | Q2 - 2011 | 3365 | 3446 | TRUE | 34 | Construction is complete or under way at each site. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 6 | Construction is under way or complete at 6 sites. The percent complete is based on invoiced expenses in 2Q. | 39 | All dense wavelength division multiplexing and ADM equipment has been purchased. The percent complete is based on invoiced expenses in 2Q. Began purchasing equipment for the support and management of our MOSS Network. | 5 | Our network build will be the deployment of transport equipment (2i) at each of our interconnection sites. | 5 | Equipment deployment is dependent on the inside plant work. This will pick up in the 3rd quarter with the completion of the inside plant work. | 0 | Dependent on the equipment deployment. This will pick up in the 3rd quarter with the completion of the inside plant work. | 2011-08-30 00:11 | 2011-08-30 00:11 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2011 | Q3 | Q3 - 2011 | 4301 | 4001 | TRUE | 37 | Equipment deployments and construction has been completed. Testing will be completed next quarter. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 14 | Construction is complete. The percentage complete is strictly based on the budget. | 41 | We've been invoiced for the majority of our equipment purchases. | 80 | We are finalizing the network build now that the equipment has been deployed. | 100 | Complete | 85 | All DWDM systems have been tested. The ADM systems have completed testing in 8 or 17 sites. | 2011-11-29 10:33 | 2011-11-29 10:33 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2011 | Q4 | Q4 - 2011 | 5303 | 4974 | TRUE | 46 | All construction and equipment deployments are complete. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 65 | The construction has been completed. Finalizing invoices with the construction contractor. Percent complete is strictly based on the budget. | 44 | All equipment has been purchased. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:52 | 2012-02-27 15:52 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2012 | Q1 | Q1 - 2012 | 6059 | 5629 | TRUE | 47 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 71 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 44 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete | 2012-05-14 12:02 | 2012-05-14 12:02 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2012 | Q2 | Q2 - 2012 | 7151 | 6203 | TRUE | 47 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 71 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 44 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete | 2012-08-20 10:08 | 2012-08-20 10:08 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2012 | Q3 | Q3 - 2012 | 7697 | 6533 | TRUE | 47 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 72 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 44 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 23:00 | 2012-10-30 23:00 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2012 | Q4 | Q4 - 2012 | 8543 | 7276 | TRUE | 47 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 72 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 44 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 16:51 | 2013-01-30 16:51 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2013 | Q1 | Q1 - 2013 | 12031 | 10195 | TRUE | 100 | Final expenses will be for closeout costs. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 100 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 2014-04-14 12:13 | 2014-04-14 12:13 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2010 | Q2 | Q2 - 2010 | 65 | 1309 | FALSE | 50 |  | 0 |  |  | 75 |  | 75 |  | 0 |  | 75 |  | 25 |  | 50 |  | 10 |  | 10 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2010 | Q3 | Q3 - 2010 | 403 | 1468 | TRUE | 40 | Satisfied Section 106 SAC towards end of 3Q | 0 |  | N/A | 100 | Complete | 25 | Satisfied Section 106 SAC towards end of 3Q | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 0 | Section 106 SAC satisfied towards end of 3Q | 0 | During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. | 0 | Pending 2g | 0 | Pending 2g | 0 | On track | 2010-11-23 17:43 | 2010-11-23 17:43 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2010 | Q4 | Q4 - 2010 | 1159 | 2198 | TRUE | 45 | Completed all network and engineering designs simultaneously. Construction procurement process still in progress. | 0 |  | Pending the construction procurement process (item 2f). | 100 | Complete | 75 | Completed wavelength system designs for all sites. | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 20 | Construction procurement process still in progress. | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 2011-02-15 18:02 | 2011-02-15 18:02 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2011 | Q1 | Q1 - 2011 | 2367 | 2929 | TRUE | 13 | Completed all network and engineering designs simultaneously. Construction procurement process is complete. Variance due to delay in construction procurement activities. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Completed all dense wavelength divisional multiplexing and synchronous optical networking system designs. | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 4 | Construction contractor has been selected. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 15 | Most dense wavelength divisional multiplexing systems have been purchased. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 15 | Build to support Palo Cedro site was completed. The rest is pending the construction procurement process (item 2f). | 25 | DWDM equipment was deployed in 5 sites. The rest is pending the construction procurement process (item 2f). | 15 | Testing of DWDM equipment was completed at 5 sites. The rest is pending the construction procurement process (item 2f). | 2011-05-27 08:13 | 2011-05-27 08:13 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2011 | Q2 | Q2 - 2011 | 3369 | 3448 | TRUE | 19 | Construction is complete or under way at each site. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 15 | Most construction is complete. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 20 | All equipment has been purchased. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 10 | Our network build will be the deployment of transport equipment (2i) at each of our interconnection sites. | 10 | Most inside plant work is now finished, so we expect the equipment deployment to pick up in the 3rd quarter. | 5 | Dependent on the equipment deployment. This will pick up in the 3rd quarter with the completion of the inside plant work. | 2011-08-30 00:19 | 2011-08-30 00:19 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2011 | Q3 | Q3 - 2011 | 4339 | 4026 | TRUE | 29 | Construction has been completed at each site. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 36 | Construction is complete. The percentage complete is strictly based on the budget. | 28 | Most equipment purchases are complete. The percentage complete is strictly based on the budget. | 75 | Finalizing fiber assignments at four of the eleven sites. Should be completed early next quarter. | 85 | Completion of the the equipment deployments will follow the fiber assignments discussed in 2h. | 70 | DWDM testing has been completed at seven of the eleven sites. The remaining sites will follow the equipment deployments. | 2011-11-30 14:41 | 2011-11-30 14:41 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2011 | Q4 | Q4 - 2011 | 5307 | 4977 | TRUE | 32 | All construction and equipment deployments are complete. Finalizing equipment testing at 3 sites. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 56 | The construction has been completed. Finalizing invoices with the construction contractor. Percent complete is strictly based on the budget | 28 | All equipment has been purchased. Percent complete is strictly based on the budget. | 95 | Network build is complete at 8 of the 11 sites. All sites will completed in the 1st quarter of 2012. | 95 | Equipment deployment is complete at 8 of the 11 sites. All sites will completed in the 1st quarter of 2012. | 95 | Network testing is complete at 8 of the 11 sites. All sites will completed in the 1st quarter of 2012. | 2012-02-27 15:55 | 2012-02-27 15:55 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2012 | Q1 | Q1 - 2012 | 6061 | 5630 | TRUE | 32 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 59 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 28 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete | 2012-05-14 12:03 | 2012-05-14 12:03 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2012 | Q2 | Q2 - 2012 | 6521 | 5875 | TRUE | 32 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 59 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 28 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete | 2012-07-27 12:20 | 2012-07-27 12:20 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2012 | Q3 | Q3 - 2012 | 7699 | 6534 | TRUE | 32 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 60 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 28 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 23:01 | 2012-10-30 23:01 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2012 | Q4 | Q4 - 2012 | 8545 | 7278 | TRUE | 32 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 60 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 28 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 16:54 | 2013-01-30 16:54 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2013 | Q1 | Q1 - 2013 | 12035 | 10197 | TRUE | 100 | Final expenses will be for closeout costs. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 100 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 2014-04-14 12:17 | 2014-04-14 12:17 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2010 | Q2 | Q2 - 2010 | 66 | 1310 | FALSE | 25 |  | 0 |  |  | 100 |  | 50 |  | 0 |  | 75 |  | 0 |  | 25 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2010 | Q3 | Q3 - 2010 | 405 | 1469 | TRUE | 40 | Ahead | 0 |  | N/A | 100 | Complete | 50 | On track | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 25 | On track | 0 | During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. | 0 | Pending 2g | 0 | Pending 2g | 0 | On track | 2010-11-23 17:50 | 2010-11-23 17:50 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2010 | Q4 | Q4 - 2010 | 1161 | 2199 | TRUE | 40 | Completed all network and engineering designs simultaneously. Construction procurement process still in progress. Variance due to delay in construction procurement activities. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 20 | Construction RFP still in progress. Variance due to delay in construction procurement activities. Award anticipated in February 2011. | 35 | Variance due to delay in construction procurement activities (item 2f). | 0 | Variance due to delay in construction procurement activities (item 2f). | 0 | Variance due to delay in construction procurement activities (item 2f). | 0 | Variance due to delay in construction procurement activities (item 2f). | 2011-02-15 18:09 | 2011-02-15 18:09 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2011 | Q1 | Q1 - 2011 | 2369 | 2930 | TRUE | 19 | Completed all network and engineering designs simultaneously. Construction procurement process is complete. Variance due to delay in construction procurement activities. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Completed all dense wavelength divisional multiplexing and synchronous optical networking system designs. | 0 | N/A - All construction will be on our own property. | 100 | Completed all engineering designs for all sites simultaneously. | 4 | Construction contractor has been selected. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 24 | Most dense wavelength divisional multiplexing and synchronous optical networking systems have been purchased. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 0 | Pending the construction procurement process (item 2f). | 2011-05-27 08:17 | 2011-05-27 08:17 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2011 | Q2 | Q2 - 2011 | 3371 | 3449 | TRUE | 30 | All inside and outside plant construction was completed. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 21 | Inside and outside plant work is complete, which will allow for the fiber splicing in the 3rd quarter. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 34 | All equipment has been purchased. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 10 | Our network build will be the deployment of transport equipment (2i) at each of our interconnection sites. | 10 | All equipment has been purchased and construction is complete, so the deployment will pick up in the 3rd quarter. | 10 | Pending the completion of the equipment deployment at each site (2i). | 2011-08-30 00:36 | 2011-08-30 00:36 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2011 | Q3 | Q3 - 2011 | 4341 | 4027 | TRUE | 40 | Completed all construction, equipment deployments and testing at each of the interconnection points. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 46 | Construction is complete. The percentage complete is strictly based on the budget. | 41 | Equipment procurement complete. The percentage complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2011-11-30 14:43 | 2011-11-30 14:43 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2011 | Q4 | Q4 - 2011 | 5309 | 4979 | TRUE | 44 | All construction and equipment deployments are complete. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 66 | The construction has been completed. Finalizing invoices with the construction contractor. Percent complete is strictly based on the budget. | 42 | All equipment has been purchased. Percent complete is strictly based on the budget. We will come in under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:57 | 2012-02-27 15:57 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2012 | Q1 | Q1 - 2012 | 6063 | 5631 | TRUE | 44 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 67 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 42 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete | 2012-05-14 12:05 | 2012-05-14 12:05 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2012 | Q2 | Q2 - 2012 | 6523 | 5876 | TRUE | 44 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 67 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 42 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete | 2012-07-27 12:22 | 2012-07-27 12:22 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2012 | Q3 | Q3 - 2012 | 7701 | 6535 | TRUE | 44 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 67 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 42 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete | 2012-10-30 23:02 | 2012-10-30 23:02 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2012 | Q4 | Q4 - 2012 | 8549 | 7285 | TRUE | 44 | Payments to construction contractor are complete. All physical work has been completed. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 67 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 42 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 17:01 | 2013-01-30 17:01 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2013 | Q1 | Q1 - 2013 | 11973 | 10135 | TRUE | 100 | Final expenses will be for closeout costs. Percent complete for the overall project is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Percent complete is strictly based on the budget. All physical work is complete and we will be under budget for this line item. | 100 | All equipment has been purchased and we will be under budget for this line item. Percent complete is strictly based on the budget. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 100 | Complete. All physical work is complete. | 2014-03-20 16:23 | 2014-03-20 16:23 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570044 | 2010 | Q2 | Q2 - 2010 | 67 | 1292 | FALSE | 5 |  | 0 |  |  | 100 |  | 20 |  | 0 |  | 0 |  | 0 |  | 10 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | University of Illinois | TRUE
NT10BIX5570044 | 2010 | Q3 | Q3 - 2010 | 447 | 1490 | TRUE | 0 | We had projected 5% completion through this quarter, so this is behind when measured by expenditures. No grant expenditures had cleared the University's accounting system by 9/30/10 which makes this a zero. If measured by accomplishments this would be closer to 2-3%. | 0 |  | N/A | 0 | We had projected 100% completion during this quarter. We did complete the Environmental Assessment, it was accepted, and we received a Finding Of No Significant Impact. The payment to the engineering firm that worked on the EA had not cleared the University's accounting system by 9/30/10, so this artificially looks to be behind. We are on schedule for the EA. | 0 | We had projected 20% of this to be completed by this quarter. While we are well into our network design, no charges for time had cleared the University's accounting system by 9/30/10, so this looks to be behind, while based on effort and accomplishment it is probably right at 20% as projected. | 0 | N/A | 0 | Our engineering firm will be securing these permits and approvals, but we did not finalize the selection of that firm until the 4th quarter. We expect to be back on schedule in this area by the end of the 1st Quarter in Year 2. Our baseline plan estimate was too aggressive in this category. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-29 19:19 | 2010-11-29 19:19 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2010 | Q4 | Q4 - 2010 | 1325 | 2349 | TRUE | 1 | See narrative below. | 0 |  | N/A | 100 | Completed on Schedule | 25 | Baseline was 100%. At the time this figure was included in the revised project baseline, we thought that we would complete our Environmental Assessment and hire our engineering firm in a shorter period of time than it actually took. We were overly optimistic in predicting that the engineering would be complete by the end of the 4th quarter. We did hire our engineering firm - Shive-Hattery - in this quarter quarter and they had been on the job for a month at the end of this quarter. Despite the record snowfall in December, they made a lot of progress towards completing this milestone. As things stand now, they are scheduled to deliver the construction bid documents in early April. | 25 | Baseline was 100%. At the time this figure was included in the revised project baseline, we thought that we would complete our Environmental Assessment and hire our engineering firm in a shorter period of time than it actually took. We were overly optimistic in predicting that the rights-of-way would be acquired by the end of the 4th quarter. Since they have been working on our project, our engineering firm - Shive-Hattery - has identified the needed private easements for rights-of-way. In order to continue to make progress on the construction, an "easement free" design will initially be bid, with the paths that require private easements bid as alternates. That will allow the lengthy process of securing the private easements to continue in parallel with the construction bidding. We know that we will have to do some of our construction in 2012, and the areas that will require private easements for rights-of-way will be scheduled for that second year of construction. That should allow a | 25 | Baseline was 100%. At the time this figure was included in the revised project baseline, we thought that we would complete our Environmental Assessment and hire our engineering firm in a shorter period of time than it actually took. We were overly optimistic in predicting that the construction permits and other approvals would be complete by the end of the 4th quarter. All permits have been applied for and Shive-Hattery will secure all needed permits prior to the release of the construction bid documents in April of 2011. | 0 | As planned | 10 | As planned. The fiber-to-the-premise (FTTP) electronics Request for Proposals (RFP)was released in December. | 0 | As planned | 0 | As planned | 0 | As planned | 2011-02-23 11:04 | 2011-02-23 11:04 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2011 | Q1 | Q1 - 2011 | 2257 | 2874 | TRUE | 2 | When we completed the 12/31/2010 PPR report, we believed that we would have completed our engineering as well as purchased our first suite of FTTP equipment for testing purposes. Had our engineering firm finished their design work by 3/31/11 and had we purchased some FTTP equipment by then, we would have obligated a lot more money and been much closer to our forecast percentages for the Overall Project and Network Design. | 0 |  | N/A | 100 | This is consistent with our baseline plan. | 50 | Baseline was 100%. The complexity of the UC2B project has resulted in the network designs taking longer than we had previously anticipated. That complexity is exemplified by the fact that we will have three separate construction bid packages and there are multiple points where the multiple construction areas must connect to each other. For two of the areas, we have existing infrastructure to incorporate into the final design, and it turns out that Urbana did not have documentation of its facilities at the level of detail needed for our engineering firm. We had originally hoped to be out to bid by the end of March, but we did not make that self-imposed deadline. To avoid unnecessary waste, we are trying to eliminate as many errors as possible from the drawings before the bidding and those errors turn into costly change orders. We are currently paying a price in time, but hopefully saving money in the long run. Our engineering firm - Shive-Hattery - is on track to deliver the comple | 50 | Baseline was 100%. We have identified all of the private easements that will be required for rights-of-way and have designed our construction bid documents to take the private easements into account. It will most likely be the 4th quarter of this year before all the private easement issues have been resolved. To allow for the time required for assessments and to secure private easements, the construction in those areas will be scheduled for 2012. Therefore the lack of having the private easements for rights of way will not impact the start of our construction in 2011. Once we determined that we could not complete the private easements and still build fiber infrastructure in this calendar year, we went with the â€œeasement-freeâ€ design alternatives and stopped working on the private easements. We have been totally focused on getting the construction bids out on the street. When that has happened, we will be able to circle back and work on the private easements. | 50 | Baseline was 100%. We will catch up in the coming quarter. All permit applications have been filed. All IDOT permits were received 4/29/11. Some railroad permits are still outstanding but we expect to receive them in the next quaeter as well. | 0 | This is consistent with our baseline plan. | 10 | We believe that completing our RFP process for the FTTP electronics was 10% of our overall equipment procurement process. As of 3/31/11 we had not finalized contracts with our FTTP electronics vendor, so we have not actually purchased any equipment. By virtue of completing the FTTP RFP, we believe we are 10% done with the overall equipment procurement process, even though we have not actually purchased any equipment yet. | 1 | This is slightly ahead of our baseline plan. | 0 | Baseline was 10%. We will catch up in the coming quarter now that our FTTP electronics RFP process is complete. | 0 | This is consistent with our baseline plan. | 2011-05-23 17:22 | 2011-05-23 17:22 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2011 | Q2 | Q2 - 2011 | 3255 | 3390 | TRUE | 6 | Our baseline projected 45%, which was based on getting a lot of construction completed this summer. Due to the delays in completing our detailed fiber design and in hiring our construction contractors, construction will not begin until the 3rd quarter of 2011. We expect to complete our overall project in January of 2013. | 0 |  | N/A | 100 | Complete | 100 | Complete | 80 | Baseline projected 100%. All of our IDOT ROW permits are complete. We still lack several private easements. Those will be negotiated in the 3rd quarter as soon as our construction contracts are finalized. | 80 | Baseline Projected at 100%. All but two of our railroad crossing permits are complete. The railroad has been short-staffed due to the flooding along the Mississippi River. We expect to secure all construction permits and approvals in September of 2011. | 0 | Baseline projected at 100%. Due to the delays in completing our detailed fiber design and in hiring our constriction contractors, construction will not begin until the 3rd quarter. We expect to spend all of these site construction dollars by the end of the 4th quarter of 2011. | 10 | Baseline projected at 60%. While the RFP winner for the UC2B FTTP electronics was approved both by the University of Illinois Board of Trustees as well as the State of Illinois procurement office, the vendor has a major hardware/software release scheduled for August 21st, so we will wait until then to begin purchasing this equipment. We will buy much of this equipment up-front to bring up the core network in the 4th quarter of 2011. However, the equipment that resides at a customer location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase the customer equipment too far ahead of time, we use up too much of the warranty before it is ever deployed. We expect to purchase the last of this customer-specific equipment in the 4th quarter of 2012. | 1 | Baseline projection was 30%. Construction has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. The final Network Build will be completed in January of 2013. | 0 | Baseline projection was 60%. Equipment Deployment has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We will be installing customers through January of 2013, so the final date for equipment deployment will be January 31, 21013. | 0 | Baseline projection was 25%. Network Testing has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We projected Network testing to be complete by the 2nd quarter of 2012. It seems likely that the actual date will be late in the 3rd quarter or early in the 4th quarter of 2012 instead. | 2011-08-22 11:40 | 2011-08-22 11:40 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2011 | Q3 | Q3 - 2011 | 4277 | 3989 | TRUE | 7 | Our baseline projected 75%, which was based on getting a lot of construction completed this summer. Due to the delays in completing our detailed fiber design and in hiring our construction contractors, construction did not begin until the end of the 3rd quarter of 2011. Both contractors will not have fiber until January of 2012, but both are installing conduit, manholes and handholes. Now that we have construction workers in the field, we expect to complete our overall project in January of 2013. | 0 |  | N/A | 100 | Complete | 100 | Complete | 90 | Baseline projected 100%. All of our IDOT ROW permits are complete. We still lack two private easements. Those will be negotiated in the 4th quarter. Our engineering firm has been concentrating on getting the main construction started, and has not had time to finalize these two remaining easements. | 90 | Baseline Projected at 100%. All but two of our railroad crossing permits are complete. The railroad has been short-staffed due to the flooding along the Mississippi River. We expect to secure all construction permits and approvals in the 4th Quarter of 2011. | 0 | Baseline projected at 100%. Due to the delays in completing our detailed fiber design and in hiring our constriction contractors, construction did not begin until the 3rd quarter. We expect to spend all of these site preparation dollars by the end of the 4th quarter of 2011. | 10 | Baseline projected at 70%. While the RFP winner for the UC2B FTTP electronics was approved both by the University of Illinois Board of Trustees as well as the State of Illinois procurement office, the vendor had a major hardware/software release scheduled for August 21st, so we waited until then to begin purchasing this equipment. Unfortunately that data slipped by 6 weeks, but the upgrade has been released now. We will buy much of our equipment to bring up the core network in the 4th quarter of 2011. However, the equipment that resides at a customer location will be purchased on an as-needed basis. There is typically a one or two year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase the customer equipment too far ahead of time, we use up too much of the warranty before it is ever deployed. We expect to purchase the last of the customer premise equipment in the 4th quarter of 2012. | 2 | Baseline projection was 69%. Construction was delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. The final Network Build will be completed in January of 2013. While this is not a metric that NTIA is tracking, we did install our first 3 miles of conduit in September. | 0 | Baseline projection was 70%. Equipment Deployment has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We will be installing customers through January of 2013, so the final date for equipment deployment will be January 31, 21013. | 0 | Baseline projection was 60%. Network Testing has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We projected Network testing to be complete by the 2nd quarter of 2012. It seems likely that the actual date will be late in the 3rd quarter or early in the 4th quarter of 2012 instead. | 2011-11-27 22:32 | 2011-11-27 22:32 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2011 | Q4 | Q4 - 2011 | 5081 | 4753 | TRUE | 15 | Our baseline projected 78%, which was based on getting a lot of construction completed this past summer. Due to the delays in completing our detailed fiber design and in hiring our construction contractors, construction did not begin until the end of the 3rd quarter of 2011. Both contractors will not have fiber until February of 2012, but both are currently installing conduit, manholes and handholes. Now that we have construction workers in the field, we expect to complete our overall project in January of 2013.The percentage shown reflects the actual dollars spent to date. | 0 |  | N/A | 100 | Complete | 100 | Complete | 90 | Baseline projected 100%. We are in the final stages of securing several previously identified private easements. Since construction has started, we have discovered several additional locations where the cities thought they had an existing right-of-way, but the nearby property owners believe otherwise. Those issues are in the process of being resolved. We do not project this to impact the timely completion of our project. | 100 | Complete | 100 | Complete | 0 | Baseline projected at 80%. This was erroneously reported as 10% in the Q3 PPR. It should have been zero then as well as no equipment funds had been spent yet. We have now ordered 25% of our total equipment and determined what we will purchase for the network core. Billing for those purchases should show up in the next quarter. The equipment that resides at a customer location will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase the customer equipment too far ahead of time, we use up too much of the warranty before it is ever deployed. We expect to purchase the last of the customer premise equipment in the 4th quarter of 2012. | 5 | Baseline projection was 90%. Construction was delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We will also not receive our fiber until the first quarter of 2012. The final Network Build will be completed in January of 2013. While this is not a metric that NTIA is tracking, we have installed 50 miles of conduit through December, which represents 30% of the total conduit for the project. | 0 | Baseline projection was 80%. Equipment Deployment has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We will be installing customers through January of 2013, so the final date for equipment deployment will be January 31, 21013. | 0 | Baseline projection was 70%. Network Testing has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We projected network testing to be complete by the 2nd quarter of 2012. It seems likely that the actual date will be late in the 3rd quarter or early in the 4th quarter of 2012 instead. | 2012-02-16 23:14 | 2012-02-16 23:14 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2012 | Q1 | Q1 - 2012 | 5931 | 5565 | TRUE | 25 | Our baseline projected 85%, which was based on getting a lot of construction completed this past summer. Due to the delays in completing our detailed fiber design and in hiring our construction contractors, construction did not begin until the end of the 3rd quarter of 2011. Both contractors now have fiber and are currently installing conduit, manholes and handholes. Now that we have construction workers in the field, we expect to complete our overall project in January of 2013.The percentage shown reflects the actual dollars spent to date. |  |  | N/A | 100 | Complete | 100 | Complete | 95 | Baseline projected 100%. We are in the final stages of securing several previously identified private easements. Since construction has started, we have discovered several additional locations where the cities thought they had an existing right-of-way, but the nearby property owners believe otherwise. Those issues are in the process of being resolved. We do not project this to impact the timely completion of our project. | 100 | Complete | 100 | Complete | 3 | Baseline projected at 90%. We have now received 25% of our equipment, but those invoices did not clear by the end of the quarter. The equipment that resides at a customer location will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase the customer equipment too far ahead of time, we use up too much of the warranty before it is ever deployed. We expect to purchase the last of the customer premise equipment in the 4th quarter of 2012. | 20 | Baseline projection was 92%. Construction was delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. The final Network Build will be completed in January of 2013. While this is not a metric that NTIA is tracking, we have installed 118 miles of conduit through March, which represents 74% of the total conduit for the project. | 0 | Baseline projection was 90%. Equipment Deployment has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We will be installing customers through January of 2013, so the final date for equipment deployment will be January 31, 21013. | 0 | Baseline projection was 80%. Network Testing has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We originally projected network testing to be complete by the 2nd quarter of 2012. It seems likely that the actual date will be late in the 3rd quarter or early in the 4th quarter of 2012 instead. | 2012-05-06 14:50 | 2012-05-06 14:50 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2012 | Q2 | Q2 - 2012 | 6901 | 6077 | TRUE | 46 | Our baseline projected 95%, which was based on getting a lot of construction completed in the summer of 2011, which did not happen. Due to the delays in completing our detailed fiber design and in hiring our construction contractors, construction did not begin until the end of the 3rd quarter of 2011. Both contractors now close to completing their conduit, manholes and handholes and are pulling and splicing fiber. Now that we have construction workers in the field, we expect to complete our overall project in January of 2013.The percentage shown reflects the actual dollars spent to date. | 0 |  | N/A | 100 | Complete | 100 | Complete | 95 | Baseline projected 100%. We are in the final stages of securing several previously identified private easements. Since construction has started, we have discovered several additional locations where the cities thought they had an existing right-of-way, but the nearby property owners believe otherwise. Those issues are in the process of being resolved. There are also some lingering easement issues with the owners of two mobile home parks. We do not project these issues will impact the timely completion of our construction. | 100 | Complete | 100 | Complete | 50 | Baseline projected at 100%. We have now received 50% of our equipment, but not all of those invoices cleared by the end of the quarter. The equipment that resides at a customer location will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase the customer equipment too far ahead of time, we use up too much of the warranty before it is ever deployed. We expect to purchase the last of the customer premise equipment in the 1st quarter of 2013. | 75 | Baseline projection was 96%. Construction was delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. The final Network Build will be completed in January of 2013. While this is not a metric that NTIA is tracking, we have installed 146 miles of conduit through June, which represents 92% of the total conduit for the project. | 50 | Baseline projection was 100%. Equipment Deployment has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. Our 14 core active Ethernet chassis have all been deployed as have most of our core network electronics. None of our Customer Premise Equipment (CPE) has been deployed however. We will be installing customers through January of 2013, so the final date for equipment deployment will be January 31, 2013. | 0 | Baseline projection was 100%. Network Testing has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We originally projected network testing to be complete by this quarter. It now seems likely that the actual date will be late in the 3rd quarter or early in the 4th quarter of 2012 instead. | 2012-08-07 15:29 | 2012-08-07 15:29 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2012 | Q3 | Q3 - 2012 | 8059 | 6736 | TRUE | 53 | Our baseline projected 100%, which was based on getting a lot of construction completed in the summer of 2011, which did not happen. Due to the delays in completing our detailed fiber design and in hiring our construction contractors, construction did not begin until the end of the 3rd quarter of 2011. Our Phase One contractors are very close to completing the middle-mile fiber, Community Anchor Institution laterals and the fiber to the curb in the Fiber-to-the-Premise (FTTP) areas. Our Phase Two contractor which is connecting our FTTP locations to the fiber in the public rights-of-way is not making as much progress as we would like. That portion of our project is in jeopardy of not being complete by our deadline. The percentage shown reflects the actual total dollars spent to date, not our federal dollar percentage, which is 48.75%. As our State matching grant expires in October, we have been spending our local match dollars faster than our NTIA grant dollars. | 0 |  | N/A | 100 | Complete | 100 | Complete | 97 | Baseline projected 100%. We are in the final stages of securing several previously identified private easements. Since construction has started, we have discovered several additional locations where the cities thought they had an existing right-of-way, but the nearby property owners believed otherwise. There is now only one of those issues left to resolve, and supposedly the signed easement form is in the mail. There are also some lingering easement issues with the owners of two mobile home parks in our Fiber-to-the-Premise (FTTP) service area. One of those owners has now indicated a willingness to sign the easement, the second has not yet done so, despite our best efforts to instill a sense of urgency with that owner. | 100 | Complete | 100 | Complete | 80 | Baseline projected at 100%. We have now received 80% of our equipment, but have not yet ordered the final half of the customer premise equipment. We had projected a total of 2,700 customers, and we currently have just under 1,200 enrolled, so we will wait to order the additional equipment until our sales require us to do so. The equipment that resides at a customer location will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase the customer equipment too far ahead of time, we use up too much of the warranty before it is ever deployed. We expect to purchase the last of the customer premise equipment in the 1st quarter of 2013. | 80 | Baseline projection was 100%. Construction was delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. The final Middle-Mile Network Build will be completed next quarter. While this is not a metric that NTIA is tracking, we have installed 163.4 miles of conduit through September, which represents 97% of the total Middle-Mile conduit for the project. 157.1 miles (94% percent) of our Middle-Mile fiber and fiber-to-the-curb has been pulled. What remains are the drop cables from the curb into the homes, businesses and Anchor Institutions. | 60 | Baseline projection was 100%. Equipment Deployment has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. Our 14 core Active Ethernet chassis have all been deployed as has all of our core network electronics. At the end of the 3rd quarter, only 20 of our Customer Premise Equipment (CPE) had been deployed. The Phase Two construction crews are now averaging some 8-10 installations a day, so the number of Customer CPE climbs weekly. As of October 30th there were 120 live customers on the UC2B network. We will continue installing customers through January of 2013, so the final date for equipment deployment will be January 31, 2013. | 20 | Baseline projection was 100%. Network Testing has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We originally projected network testing to be complete by last quarter. It now seems likely that the actual date will be in the 4th quarter of 2012 instead. Testing has been done on some of the middle-mile ring cables and some of the fiber-to-the-curb cables, and will continue in the 4th quarter until complete. | 2012-11-26 18:07 | 2012-11-26 18:07 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2012 | Q4 | Q4 - 2012 | 8735 | 7534 | TRUE | 64 | Our baseline projected 100%, which was based on getting a lot of construction completed in the summer of 2011, which did not happen. Due to the delays in completing our detailed fiber design and in hiring our construction contractors, construction did not begin until the end of the 3rd quarter of 2011. Our Phase One contractors are very close to completing the middle-mile fiber, Community Anchor Institution laterals and the fiber to the curb in the Fiber-to-the-Premise (FTTP) areas. Our Phase Two contractor which is connecting our FTTP locations to the fiber in the public rights-of-way has completed more that 700 sites, but still has several hundred yet to do. That portion of our project was in jeopardy of not being complete by our deadline, so we sought and received a no-cost time extension through September 30, 2013. The percentage shown reflects the actual total dollars spent to date, not our federal dollar percentage, which is 62%. Our State matching grant expired in October, so we | 0 |  | N/A | 100 | Complete | 100 | Complete | 99 | Baseline projected 100%. At the end of December we were in the final stages of securing the last needed private easement. That has now been secured. Since construction started, we discovered several additional locations where the cities thought they had an existing right-of-way, but the nearby property owners believed otherwise. Those easements are now signed. There was the one lingering easement issue with the owner of a mobile home park in our Fiber-to-the-Premise (FTTP) service area. That was the last easement we needed and it was secured in January. | 100 | Complete | 100 | Complete | 80 | Baseline projected at 100%. We have now received 80% of our equipment, but have only ordered the final half of the customer premise equipment. We had projected a total of 2,700 customers, and we currently have just under 1,100 enrolled, so we will wait to order any additional equipment until our sales require us to do so. From here out, the equipment that resides at a customer location will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase the customer equipment too far ahead of time, we use up too much of the warranty before it is ever deployed. We now expect to purchase the last of the customer premise equipment in the 3rd quarter of 2013. | 84 | Baseline projection was 100%. Construction was delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. The final bit of the original Middle-Mile Network Build will be completed next quarter. It is at 99% today. What remains to be completed are some of the the drop cables from the curb into the homes, businesses and Anchor Institutions. With the addition in January of 61 additional Community Anchor Institutions, there will some 8 miles of additional middle-mile construction to connect them. | 65 | Baseline projection was 100%. Equipment Deployment has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. Our 14 core Active Ethernet chassis have all been deployed as has all of our core network electronics. At the end of the 4th quarter, only 776 of our Customer Premise Equipment (CPE) had been deployed. The final date for equipment deployment will be September 30, 2013. | 30 | Baseline projection was 100%. Network Testing has been delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We originally projected network testing to be complete by the 2nd quarter of 2012. It now seems likely that the actual date will be in the 1st quarter of 2013 instead. Testing has been done on some of the middle-mile ring cables and some of the fiber-to-the-curb cables, and will continue in the 1st quarter of 2013 until complete. | 2013-02-12 23:56 | 2013-02-12 23:56 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2013 | Q1 | Q1 - 2013 | 9807 | 8439 | TRUE | 67 | We are beyond the performance period of our baseline plan, which had our project complete by now. The metrics supplied with the extension request did not include an overall project completion percentage. The percentage supplied is based solely on total funds expended. As is detailed elsewhere in this report, there is a tie lag between when work is done and when NTIA pays for it. Because of that time lag, our actual one-the-ground completion percentage is close to 13% higher than is reflected in the financial numbers alone. | 0 |  | N/A | 100 | Complete | 99 | We were complete, but we added 61 additional Anchor Institutions via an Award Action Request that was approved in January, and the design work for them is now being finalized. | 99 | The original work is complete, but we may have a few rights-of-way agreements to obtain in conjunction with the 61 additional Anchor Institutions we added via an Award Action Request in January. | 99 | The original work is complete, but we may have a few Illinois Department of Transportation (IDOT) permits to obtain in conjunction with the 61 additional Anchor Institutions we added via an Award Action Request in January. | 99 | The original work is complete, but we may have a little site preparation work to complete in conjunction with the 61 additional Anchor Institutions we added via an Award Action request in January. | 90 | Based on our revised customer numbers that were approved in our no-cost Extension request, we are very close to having all the equipment we will need | 90 | We have about 9.2 route miles of additional fiber to construct to reach the the 61 additional Anchor Institutions we added via an Award Action request in January. We also have about 15.2 miles of drops cables to install to our remaining customers that have subscribed but have not yet been connected. | 82 | The core network equipment is all deployed. We have electronics in 905 customer sites with ~519 sites left to install, However not all of the remaining sites will get dedicated UC2B electronics. Some will get electronics through a service provider that has leased fiber or the site is part of a multi-site organization that is getting one big UC2B connection and then sharing that internally over dark fiber and their own electronics. | 80 | Much of this quarter was spent testing, troubleshooting and correcting any problems with the 7 backbone fiber rings or with the lateral fiber cables connecting Anchor Institutions. In some cases when we solved an issue for one customer, it also cleared up an issue with additional customers. Our most common mistake was reversing the 12-strand ribbon cables when they were spliced together so rather than than strand #1 being spliced to strand #1 and strand #12 being spliced to strand #12, one of the cables was "upside-down" so #1 was connected to #12, #12 was connected to #1 and all the strands in between were similarly mismatched. Our contractors have now submitted their as-built documentation and it is being checked for completeness and accuracy. We are very close to formally accepting the backbone rings and Anchor laterals. | 2013-05-19 18:15 | 2013-05-19 18:15 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2013 | Q2 | Q2 - 2013 | 10721 | 9024 | TRUE | 81 | We are beyond the performance period of our original baseline plan, which had our project complete by now. The metrics included with the extension request did not include an overall project completion percentage. The percentage supplied here is based solely on total funds expended. We have actually only spent 79% of our Federal funds. While we did not spend much money in the second quarter, we did make significant payments for work done previously. However, the draw to cover those payments was not completed within the quarter. A draw covering the the $3.86 million was made in early July. | 0 |  | N/A | 100 | Complete | 99 | The network design was complete, but we added 61 additional Community Anchor Institutions via an Award Action Request that was approved in January, and the design work for them is now being finalized. | 100 | Complete | 100 | Complete | 99 | The original work is complete, but we may have a little site preparation work to complete in conjunction with the 61 additional Community Anchor Institutions we added via an Award Action Request in January. | 95 | Based on our revised customer numbers that were approved in our no-cost Extension request, we are very close to having all the equipment we will need. We may need to purchase a few more small customer routers for deployments in the third quarter. | 90 | We have about 9.2 route miles of additional fiber to construct to reach the the 61 additional Anchor Institutions we added via an Award Action Request in January. We also have about 11 miles of drops cables to install to our remaining customers that have subscribed but have not yet been connected. | 83 | The core network equipment is all deployed. We have electronics in 913 customer sites with approximately 360 sites left to install, However not all of the existing or remaining sites will get dedicated UC2B electronics. Some will get electronics through a service provider that has leased UC2B dark fiber or the site is part of a multi-site organization that is getting one big UC2B connection and then sharing that internally over their own leased UC2B dark fiber and their own electronics | 90 | Much of this quarter was spent finishing testing, troubleshooting and correcting any problems with the 7 backbone fiber rings or with the lateral fiber cables connecting the Community Anchor Institutions. In some cases when we solved an issue for one customer, it also cleared up issues with additional customers. Our backbone ring fiber contractors have now submitted their as-built documentation and it is being checked for completeness and accuracy. We are very close to formally accepting the backbone rings and Community Anchor Institution lateral connections. | 2013-08-23 18:02 | 2013-08-23 18:02 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2013 | Q3 | Q3 - 2013 | 12077 | 10240 | TRUE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-04-25 15:18 | 2014-04-25 15:18 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570045 | 2010 | Q2 | Q2 - 2010 | 68 | 1327 | FALSE | 11.1 |  | 0 |  |  | 100 |  | 100 |  | 25 |  | 15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2010 | Q3 | Q3 - 2010 | 463 | 1498 | TRUE | 11 | Did not obtain FONSI as expected in 3Q2010 so no construction activities have commenced. Completed fiber construction bid and selected contractor for first 3 of 6 service areas | 0 |  | N/A | 95 | UW has completed section 7 and 106 consultations and draft 2 of EA (after 1 round of NTIA comments). UW is awaiting NTIA comments from the EA submission and FONSI determination. | 92 | EA required us to finalize routes much faster than originally planned (or known when we submitted modified baseline) in order to submit plans to SHPO, THPOs and EA consultant. | 25 | N/A | 0 | Expected to obtain FONSI in 3Q2010 but did not such that we do not have permission to acquire permits yet | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-12-01 11:50 | 2010-12-01 11:50 | 5201 | 5201 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2010 | Q4 | Q4 - 2010 | 1261 | 2289 | TRUE | 11 | Obtained FONSI on 12/23/10 so no construction activities have commenced. | 0 |  | N/A | 100 | EA was approved during 4Q2010. | 92 | N/A | 25 | N/A | 0 | We have not acquired permits during the fourth quarter as we received FONSI at the end of 4Q2010 | 0 | The FONSI was approved on December 23, 2010. FONSI required for ground-breaking activities. | 0 | The equipment procurement is behind schedule from the infrastructure milestone category baseline report because the receipt of the Finding of No Significant Impact (FONSI) report was approved on December 23, 2010. Equipment procurement can only occur after receipt of the approved FONSI. | 0 | The FONSI was approved on December 23, 2010. FONSI required for ground-breaking activities. | 0 | The FONSI was approved on December 23, 2010. FONSI required for ground-breaking activities. | 0 | The FONSI was approved on December 23, 2010. FONSI required for ground-breaking activities. | 2011-02-21 17:12 | 2011-02-21 17:12 | 5201 | 5201 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2011 | Q1 | Q1 - 2011 | 2023 | 2757 | TRUE | 0 | Percent Complete is .4%, however, this form does not accept fraction percentages. FONSI timing and weather caused our delay from our baseline projection. We expect to move in line with baseline schedule in 4Q2011. | 0 |  | N/A | 95 | FONSI was received in 4Q2010. We were not aware that an EA was required. We have used funds from SF-424C's architectural and engineering fees to cover the cost of the EA. We expect to expend approximately $1,500 to cover the cost of an on-site archeologist as required during the Monona Drive Service area. | 100 | Our baseline assumed network engineering design could be completed in phases. However, the EA required us to complete all engineering before proceeding with construction. | 25 | No variance from baseline. | 0 | FONSI timing and weather. Permits are only good for six months and permitting authorities strongly prefer permits be pulled close to commencement of construction. | 0 | FONSI timing and engineering resources were used to complete network design. See answer to question 3 below. | 0 | FONSI timing. Also, we were conducting CAI needs assessments before procuring hardware which we did not include in our baseline. See answer to question 3 below. | 0 | FONSI timing. Also, we were conducting CAI needs assessments before procuring hardware which we did not include in our baseline. See answer to question 3 below. | 0 | FONSI timing. Also, we were conducting CAI needs assessments before procuring hardware which we did not include in our baseline. See answer to question 3 below. | 0 | FONSI timing and weather. See answer to question 3 below. | 2011-05-13 16:08 | 2011-05-13 16:08 | 5201 | 5201 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2011 | Q2 | Q2 - 2011 | 2967 | 3241 | TRUE | 5 | The Finding of No Significant Impact (FONSI) timing and weather caused our delay from our baseline projection. The FONSI was received in December 2010 which prevented construction activities to commence in November 2010 as originally planned. We expect to move in line with baseline schedule in 4Q2011. | 0 |  | N/A | 95 | FONSI was received in 4Q2010. We were not aware that an EA was required. We have used funds from SF-424C's architectural and engineering fees to cover the cost of the EA. We expect to expend approximately $1,500 to cover the cost of an on-site archeologist as required during the Monona Drive Service area. | 100 | Our baseline assumed network engineering design could be completed in phases. However, the EA required us to complete all engineering before proceeding with construction. | 25 | Right of way negotiation with City of Middleton is not complete as expected in baseline. Right of way negotiations for Monona Drive service area are delayed until winter 2011/2012 due to road construction changes. | 15 | FONSI timing and weather. Permits are only good for six months and permitting authorities strongly prefer permits be pulled close to commencement of construction. | 0 | Received quote from contractor. Discovered we need to file Davis-Bacon Wage conformance (SF-1444) in order to begin site preparation at 525 Science Dr. | 0 | FONSI timing. Also, we were conducting CAI needs assessments before procuring hardware which we did not include in our baseline. | 0 | .4 % expenditure for network build occurred in 2Q2011. Form does not allow fractions. | 0 | FONSI timing. Also, we were conducting CAI needs assessments before procuring hardware which we did not include in our baseline. | 0 | FONSI timing. Also, we were conducting CAI needs assessments before procuring hardware which we did not include in our baseline. | 2011-08-09 11:44 | 2011-08-09 11:44 | 5201 | 5201 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2011 | Q3 | Q3 - 2011 | 4017 | 3849 | TRUE | 45 | The Finding of No Significant Impact (FONSI) timing and weather caused our delay from our baseline projection. The FONSI was received in December 2010 which prevented construction activities to commence in November 2010 as originally planned. We expect to move in line with baseline schedule in 4Q2012. | 0 |  | N/A | 95 | FONSI was received in 4Q2010. We were not aware that an EA was required. We have used funds from SF-424C's architectural and engineering fees to cover the cost of the EA. We expect to expend approximately $1,500 to cover the cost of an on-site archeologist as required during the Monona Drive Service area in 3Q2012. | 95 | EA required us to complete all engineering ahead of time such that we had 100% completed - including optical engineering. However, after network design mtgs, we must redesign the optical transport as ALL entities want redundancy. This began in 3Q2011 and will complete by end of 4Q2011. | 75 | Have right-of-ways for all but Monona Drive service area (remaining 25% difference from our baseline with completion (100%) by 1Q2012. | 54 | We are just past 1Q2010 baseline plan but will not catch up with our baseline of 100% completed until 2Q2012 due to road construction changes in University Ave, Monona Dr, Mineral Point and East Washington service areas (can not obtain permits in construction areas until work is nearly complete) | 0 | Received quote from contractor. Filed Davis-Bacon Wage conformance (SF-1444) in late 3Q2011 for site preparation at 525 Science Dr. Expect to meet baseline by end of 1Q2012. | 0 | We are redesigning optical transport system due to unexpected CAI demands for redundancy. Will begin procuring hardware in late 4Q2011 after optical network (re)design is complete which we did not include in our baseline as we believed this was already completed. Will be on track with baseline in 1Q2012. | 48 | We are behind due to delayed EA. Will catch up at 4Q2012. | 0 | We expected to immediately deploy "North ring" but delayed due to network assessment meetings with CAIs and resulting surprise in demand. Redesigning optical system now with anticipated 1Q2012 deployment to catch up to baseline. Will not catch up to final 100% baseline until 4Q2012 as Monona Drive service area was delayed by 1yr due to road construction (orig. deployment was 1Q2012). | 10 | Tested completed laterals in 3Q2011 though due to EA and splicing completion delays, we will not catch up to 2Q2011 baseline until 1Q2012 and will not complete this until 4Q2012 due to construction delays. | 2011-11-14 11:56 | 2011-11-14 11:56 | 5201 | 5201 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2011 | Q4 | Q4 - 2011 | 5391 | 5071 | TRUE | 55 | The Finding of No Significant Impact (FONSI) timing and weather caused our delay from our baseline projection. The FONSI was received in December 2010 which prevented construction activities to commence in November 2010 as originally planned. We expect to move in line with baseline schedule in 4Q2012. | 0 |  | N/A | 95 | FONSI was received in 4Q2010. We were not aware that an EA was required. We have used funds from SF-424C's architectural and engineering fees to cover the cost of the EA. We expect to expend approximately $1,500 to cover the cost of an on-site archeologist as required during the Monona Drive Service area in 3Q2012. | 95 | EA required us to complete all engineering ahead of time such that we had 100% completed - including optical engineering. However, after network design mtgs with CAIs, we determined MUFN must redesign the optical transport as ALL entities want redundancy. This began in 3Q2011 and will complete by end of 1Q2012. | 75 | Have right-of-ways for all but Monona Drive service area (remaining 25% difference from our baseline with completion (100%) by 1Q2012. | 79 | We are just past 1Q2010 baseline plan but will not catch up with our baseline of 100% completed until 2Q2012 due to road construction changes in University Ave, Monona Dr, Mineral Point and East Washington service areas (can not obtain permits in construction areas until work is nearly complete) | 0 | Received quote from contractor. Filed Davis-Bacon Wage conformance (SF-1444) in late 3Q2011 for site preparation at 525 Science Dr and received comformance on 12/20/12. Expect to meet baseline by end of 2Q2012. | 0 | We are redesigning optical transport system due to unexpected CAI demands for redundancy. Will begin procuring hardware in early 1Q2012 after optical network (re)design is complete which we did not include in our baseline as we believed this was already completed. Will be on track with baseline in 2Q2012. | 62 | We are behind due to delayed EA. Will catch up at 4Q2012. | 0 | We expected to immediately deploy "North ring" but delayed due to network assessment meetings with CAIs and resulting surprise in demand. Redesigning optical system now with anticipated 2Q2012 deployment to catch up to baseline. Will not catch up to final 100% baseline until 4Q2012 as Monona Drive service area was delayed by 1yr due to road construction (orig. deployment was 1Q2012). | 46 | Tested completed laterals in 4Q2011 though due to EA and splicing completion delays, we will not catch up to baseline until 4Q2012 due to road construction delays delaying fiber installation in Monona Dr service area and 3 in E. Washington Ave and University Ave Service Areas. | 2012-02-29 12:24 | 2012-02-29 12:24 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2012 | Q1 | Q1 - 2012 | 5983 | 5591 | TRUE | 63 | The Finding of No Significant Impact (FONSI) timing and weather caused our delay from our baseline projection. The FONSI was received in December 2010 which prevented construction activities to commence in November 2010 as originally planned. We expect to move in line with baseline schedule in 4Q2012. | 0 |  | N/A | 95 | The Finding of No Significant Impact (FONSI) timing (received 12/24/2010) & 2010 winter weather caused delays from our baseline projection. We expect to expend approximately $1,500 to cover the cost of an on-site archeologist as required during the Monona Drive Service area in 3Q2012. We expect to move in line with baseline schedule in 3Q2012. | 95 | EA required us to complete all engineering ahead of time such that we had 100% completed - including optical engineering. However, after network design mtgs with CAIs, we determined MUFN must redesign the optical transport as ALL entities want redundancy. This began in 3Q2011 and will complete by end of 2Q2012. | 75 | Acquiring remaining right-of-way in City of Monona and with Madison Gas and Electric (poles) as part of MUFN Phase 3. Expect to meet baseline in 2Q2012 - would have met this in 1Q2012 as reported last quarter though our construction bid took longer than anticipated. | 84 | We are just past 1Q2010 baseline plan but will not catch up with our baseline of 100% completed until 3Q2012 due to road construction changes in University Ave, Monona Dr, Mineral Point and East Washington service areas (cannot obtain permits in construction areas until work is nearly complete) | 0 | Received Davis-Bacon Wage conformance for site preparation at 525 Science Dr on 12/20/12. Contractor is requoting bid with conformance wages. Expect to meet baseline by end of 3Q2012. | 0 | We are redesigning optical transport system due to unexpected CAI demands for redundancy. Will begin procuring hardware in 2Q2012 after optical network (re)design is complete which we did not include in our baseline as we believed this was already completed. Will be on track with baseline in 3Q2012. | 77 | We met our planned 3Q2011 baseline but are behind our 1Q2012 due to delayed EA and unanticipated road construction plan changes. Will catch up to at 4Q2012. | 0 | We expected to immediately deploy "North ring" but delayed due to network assessment meetings with CAIs and resulting surprise in demand. Redesigning optical system now with anticipated 3Q2012 deployment to catch up to baseline. Will not catch up to final 100% baseline until 4Q2012 as Monona Drive service area was delayed by 1yr due to road construction (orig. deployment was 1Q2012). | 80 | Tested completed laterals in 1Q2011 though due to EA and splicing completion delays, we will not catch up to baseline until 4Q2012 due to road construction delays delaying fiber installation in Monona Dr service area and 3 in E. Washington Ave and University Ave Service Areas. | 2012-05-09 12:52 | 2012-05-09 12:52 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2012 | Q2 | Q2 - 2012 | 6993 | 6124 | TRUE | 64 | The Finding of No Significant Impact (FONSI) timing and weather caused our delay from our baseline projection. The FONSI was received in December 2010 which prevented construction activities to commence in November 2010 as originally planned. We expect to move in line with baseline schedule in 4Q2012. | 0 |  | N/A | 95 | The Finding of No Significant Impact (FONSI) timing (received 12/24/2010) & 2010 winter weather caused delays from our baseline projection. We expect to expend approximately $1,500 to cover the cost of an on-site archeologist as required during the Monona Drive Service area in 3Q2012. We expect to move in line with baseline schedule in 3Q2012. | 100 | EA required us to complete all engineering ahead of time such that we had 100% completed - including optical engineering. However, after network design mtgs with CAIs, we determined MUFN must redesign the optical transport as ALL entities want redundancy. Design is now complete. | 92 | Submitting route change on a portion of Monona Drive PFSA due to planned multi-year road construction - can't finalize license to attach to MG&E poles until final route approval is received. | 90 | We are past 1Q2010 baseline plan but will not catch up with our baseline of 100% completed until 3Q2012 due to road construction changes in University Ave, Monona Dr, Mineral Point and East Washington service areas (cannot obtain permits in construction areas until road work is nearly complete in 3Q2012) | 0 | Received Davis-Bacon Wage conformance for site preparation at 525 Science Dr on 12/20/12. Contractor requoted bid with conformance wages. Expect to meet baseline by end of 3Q2012. | 15 | We redesigned the optical transport system due to unexpected CAI demands for redundancy. We are developing bid specifications now and plan to release and award an RFP in 3Q2012. Will be on track with baseline in 3Q2012. | 77 | We met our planned 3Q2011 baseline but are behind our 1Q2012 due to delayed EA and unanticipated road construction plan changes. Will catch up to at 4Q2012. | 0 | We expected to immediately deploy "North ring" but delayed due to network assessment meetings with CAIs and resulting surprise in demand. Redesigning optical system now with anticipated 4Q2012 deployment to catch up to baseline. Will not catch up to final 100% baseline until 4Q2012 as Monona Drive service area was delayed by 1yr due to road construction (orig. deployment was 1Q2012). | 82 | Tested completed laterals in 2Q2011 though due to EA and splicing completion delays, we will not catch up to baseline until 4Q2012 due to road construction delays delaying fiber installation in Monona Dr service area (aerial route change) and 3 in E. Washington Ave and University Ave Service Areas. | 2012-08-09 18:32 | 2012-08-09 18:32 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2012 | Q3 | Q3 - 2012 | 7831 | 6619 | TRUE | 67 | The Finding of No Significant Impact (FONSI) timing and weather caused our delay from our baseline projection. The FONSI was received in December 2010 which prevented construction activities to commence in November 2010 as originally planned. We expect to move in line with baseline schedule in 4Q2012 based on rebudget request as we have been running well under our initially proposed construction budget | 0 |  | N/A | 95 | The Finding of No Significant Impact (FONSI) timing (received 12/24/2010) & 2010 winter weather caused delays from our baseline projection. Did not perform lateral construction work in 3Q2012 in Monona Dr service area requiring on-site archaeologist as expected but will do so in 4Q2012. We will be in line with baseline in 4Q2012. | 100 | N/A | 92 | Finalizing license agreement with MG&E (electrical utility pole provider) once Monona Dr route change is approved. This will be done in 4Q2012 assuming route change approval is received. | 94 | Need to obtain permits in Monona Dr and Mineral Point Rd route change areas (pending NTIA approval). Expect permit for last CAI on E. Washington Ave and last 2 in University Ave service area in early 4Q2012 as road work fell behind schedule by 2 weeks so MUFN could not obtain excavation permits by end of 3Q2012 as previously expected. Will meet baseline in 4Q2012. | 67 | Contractor fell behind planned 3Q2012 completion due to delays with inspections. Will meet baseline in early 4Q2012 | 75 | Released RFP for optical equipment and RFB for DC power system hardware and received responses. Will complete evaluations and award in early 4Q2012. | 86 | We met our planned 3Q2011 baseline but are behind our 1Q2012 due to delayed EA and unanticipated road construction plan changes and delays completing the MUFN Consortium agreement. Will catch up to baseline in 4Q2012. | 0 | We expected to immediately deploy "North ring" but delayed due to network assessment meetings with CAIs and resulting surprise in demand. Redesigning optical system now will be installed in 4Q2012 deployment to catch up to baseline. Will not catch up to final 100% baseline until 4Q2012 as Monona Drive service area was delayed by 1yr due to road construction (orig. deployment was 1Q2012). | 86 | Tested completed laterals and backbone segments in 3Q2011. We will not catch up to baseline until 4Q2012 due to route changes and road construction delays in Monona Dr service area. Road construction in E. Washington Ave and University Ave Service Areas is ending in late Oct which will allow us to complete 3 CAI laterals and backbone in those service areas. | 2012-11-13 08:15 | 2012-11-13 08:15 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2012 | Q4 | Q4 - 2012 | 8769 | 7564 | TRUE | 74 | Did not receive/remit payment for several significant invoices (e.g. optical equipment, site prep, fiber database consulting) in late 4Q2012 as expected due to snowstorm, other late shipments and late completion of work just before or between holidays. Expect to meet baseline in January. | 0 |  | N/A | 100 | All environmental assessment work is complete. | 100 | All network design activities are complete. | 100 | All right-of-way acquisition activities are complete. | 100 | All construction permits and other approval activities are complete. | 100 | All site preparation activities are complete. | 100 | All equipment procurement activities are complete. | 86 | MUFN Phase 4 route change approval in early Dec. resulted in 18.25 miles to build (late start). MUFN is behind our baseline due to a snowstorm delaying December construction and delays finalizing the MUFN Consortium Agreement. Will be close to or meet baseline (100%) in late January pending weather to complete phase 4. | 67 | Two of two passive optical systems deployed; 7 of 12 active optical system nodes deployed. Received hardware 1 week later than planned (12/27/12) due to snowstorm 12/20-12/21 and Xmas Holiday (University closed 12/22-12/25). Will meet baseline by 1/16/13. | 86 | We will not catch up to baseline until January 2013 due to late start on phase 4 route change; resulting in more backbone testing. | 2013-02-14 09:10 | 2013-02-14 09:10 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2013 | Q1 | Q1 - 2013 | 9711 | 8389 | TRUE | 95 | Adverse winter weather conditions slowed and then halted construction (ice in conduits). Expect full completion by 6/7/13 | 0 |  | N/A | 100 | All environmental assessment work is complete. | 100 | All network design activities are complete. | 100 | All right-of-way acquisition activities are complete. | 100 | All construction permits and other approval activities are complete. | 100 | All site preparation activities are complete. | 100 | All equipment procurement activities are complete. | 93 | MUFN Phase 4 route change approval in early Dec. resulted in 18.25 miles to build (late start). Adverse winter weather conditions slowed and then halted construction on 1/30/13 due to ice in conduits. Anticipate completion by 6/7/13. | 100 | All equipment installation activities are complete. | 93 | Anticipate completion by 6/7/13 after fiber installation is complete. | 2013-05-14 09:02 | 2013-05-14 09:02 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2013 | Q2 | Q2 - 2013 | 10843 | 9097 | TRUE | 100 | All construction is complete | 0 |  | N/A | 100 | All environmental assessment work is complete. | 100 | All network design activities are complete. | 100 | All right-of-way activities are complete | 100 | All construction is complete | 100 | All site preparation activities are complete | 100 | All equipment has been procured | 100 | Network build is complete | 100 | All equipment has been installed | 100 | Network has been fully tested | 2013-09-12 15:23 | 2013-09-12 15:23 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570046 | 2010 | Q2 | Q2 - 2010 | 69 | 1293 | FALSE | 3 |  |  |  |  | 10 |  | 8 |  | 10 |  | 0 |  | 0 |  | 2 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | 2010 | Q3 | Q3 - 2010 | 437 | 1485 | TRUE | 1 | The engineering and combined environment assessment is now under the direction of the State Facility Planning and Control (FP&C). The Board of Regents/LONI is the user agency providing specifications, requirements and needs to FP&C. | 0 |  | N/A | 1 | The Joint Legislative Committee of Budget approved our construction, engineering design and environmental budget on 8/10/20. The State Facility Planning and Control has selected a firm for engineering and combined environmental assessment. | 3 | Consulting with Cisco Systems and other potential vendors. | 4 | Continue to work with DOTD on road and bridge permits and have started discussion with Railroads, US FWS, SHPO, THPO and US Army Corp of Engineers and soon the engineering firm will take over responsibility. | 0 | N/A | 0 | N/A | 1 | $219,140.93 was paid of our cash match to Cisco Systems for network equipment. It is our intention to follow state procurement statutes, guidelines and guidance and issue a public competitive RFP for equipment purchases above $250,000. For equipment purchases below $250,000 we will utilize existing state contracts and/or other short-term bid response vehicles. | 0 | N/A | 0 | It is our intention to follow state procurement statutes, guidelines and guidance and issue a public competitive RFP for equipment purchases above $250,000. For equipment purchases below $250,000 we will utilize existing state contracts and/or other short-term bid response vehicles. | 0 | N/A | 2010-11-29 14:08 | 2010-11-29 14:08 | 5537 | 5537 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | 2010 | Q4 | Q4 - 2010 | 1375 | 2388 | TRUE | 5 | We were delayed by the Executive Branch from being authorized to spend the awarded federal funding until August 18, 2010. | 0 | N/A | N/A | 40 | GEC has been working on the research and data collection for the Existing Environment section of the EA was started. Several sub-sections, including, geology and soils, air quality, water quality, biological resources, land use, and aesthetics were completed substantially (95%). GEC has worked on the subsections for cultural resources and infrastructure commenced (50%). Office coordination with the LA SHPO is ongoing. Coordination letters to the U.S. Fish and Wildlife and the U.S. Army Corps of Engineers (New Orleans and Vicksburg Districts) were delivered. GEC's environmental field crews inspected over 800 miles of the route to determine potential environmental issues and data was delivered to environmental personnel for processing. | 10 | GEC's communications field crews surveyed all project segments (both rural and urban areas) to determine which side of the existing roadway is the optimal route. This information was forwarded to the environmental field crews and design personnel for processing. | 15 | Required permits are being identified as part of the EA document preparation as well as field inspections. ROW issues, if any, are and will continue to be discovered during the preliminary and final inspections of the OSP route and interconnect point locations. | 0 | 0 variance | 0 | 0 variance | 1 | 0 variance | 0 | 0 variance | 0 | 0 variance | 0 | 0 variance | 2011-02-25 14:22 | 2011-02-25 14:22 | 5537 | 5537 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | 2011 | Q1 | Q1 - 2011 | 2313 | 2902 | TRUE | 6 | STATEMENT PROVIDED BY LONI. NTIA conducted their site visit on March 17-18, 2011. GEC has delivered two of its five contracted submittals including draft EA. | 0 | N/A | N/A | 98 | STATEMENT PROVIDED BY GEC. Work on the research and data collection for the Existing Environment, Environmental Consequences, and other sections of the EA was completed. Environmental field crews completed inspections of the route for the purpose of determining Draft EA was submitted on January 31, 2011. Coordination, for the EA effort, with the U.S. Fish and Wildlife Service (USFWS), the U.S. Army Corps of Engineers New Orleans District and the Louisiana Department of Natural Resources (LDNR) was completed. Coordination, for the EA effort, with the U.S. Army Corps of Engineers - Vicksburg District, the Louisiana State Historic Preservation Office (LASHPO), and the United States Forest Service (USFS) continued. Final draft EA is substantially complete, will be submitted once agency coordination is complete, and will include the information necessary to allow the preparation of a Finding Of No Significant Impact (FONSI). Remaining items to be included are (1) SOV response letter | 55 | STATEMENT PROVIDED BY GEC. Communications field crews began surveying each project segment (both rural and urban areas) for the purpose of finalizing the OSP route and identifying the placement of conduit (HDD, trench, structure), handholes, and interconnect points and for identifying required permits for construction. Field inspection / survey data was delivered to design personnel daily for review and for Field inspection / survey data was delivered to design personnel daily for review and for incorporation into route maps for construction. Draft route maps were delivered to design personnel and field crews for review and verification. Coordination for placement of interconnect points (new standalone building or within existing building) and development of installation details commenced. Specification preparation and development of design details commenced. STATEMENT PROVIDED BY LONI. We continue to refine our Optical and Ethernet network designs. | 35 | STATEMENT PROVIDED BY GEC. Required permits are being identified as part of the EA document preparation as well as field inspections. ROW issues, if any, are and will continue to be discovered during the final inspections of the OSP route and interconnect point locations. Permits identified include the United States Army Corps of Engineers - New Orleans and Vicksburg Districts, Louisiana State Historic Preservation Office (LASHPO), Louisiana Department of Natural Resources (LDNR), United States Forest Service (USFS), United States Fish and Wildlife Service (USFWS), Louisiana Department of Transportation and Development (LADOTD), railroads, pipelines, levee districts, and cities / municipalities. Assembly of forms and permit preparation commenced. | 0 | STATEMENT PROVIDED BY GEC. Construction anticipated to begin 3rd quarter of 2011. | 0 | STATEMENT PROVIDED BY GEC. Construction anticipated to begin 3rd quarter of 2011. | 1 | STATEMENT PROVIDED BY LONI. We have completed a site visit to one perspective equipment bidder. | 0 | 0 variance | 0 | 0 variance | 0 | 0 variance | 2011-05-25 17:02 | 2011-05-25 17:02 | 5537 | 5537 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | 2011 | Q2 | Q2 - 2011 | 3155 | 3338 | TRUE | 7 | STATEMENTS PROVIDED BY THE STATE: GEC has failed to delivered on their last three contracted submittals. | 0 | N/A | N/A | 100 | STATEMENTS PROVIDED BY GEC: Coordination, for the EA effort, with the U.S. Fish and Wildlife Service (USFWS), the U.S. Army Corps of Engineers - New Orleans and Vicksburg Districts, the Louisiana State Historic Preservation Office (LASHPO), the United States Forest Service (USFS), and the Louisiana Department of Natural Resources (LDNR) was completed. Coordination with these agencies for construction and permitting purposes continued. Final draft EA was submitted on April 27, 2011. Revised final draft EA was submitted on May 11, 2011. Finding of No Significant Impact (FONSI) was issued by NTIA on June 3, 2011. | 55 | STATEMENTS PROVIDED BY GEC: Communications field crews completed the survey of each rural project segment and continued the survey of each urban project segment for the purpose of finalizing the OSP route and identifying the placement of conduit (HDD, trench, structure), handholes, and interconnect points. Identification of permits for construction continued. Field inspection / survey data was delivered to design personnel for review and for incorporation into route maps for construction. Draft route maps were delivered to design personnel and field crews for review and verification. Incorporation of route maps into construction documents commenced. Twelve bid packages were identified and assembly of such packages started. Coordination for placement of interconnect points (new standalone building or within existing building) and development of installation details continued. Incorporation of these interconnect point details into the appropriate bid package commenced. Specification pr | 35 | STATEMENTS PROVIDED BY GEC: Required permits continued to be identified as part of the EA document preparation as well as field inspections. ROW issues, if any, are and will continue to be discovered during the final inspections of the OSP route and interconnect point locations. Permits identified include the United States Army Corps of Engineers - New Orleans and Vicksburg Districts Louisiana State Historic Preservation Office (LASHPO) Louisiana Department of Natural Resources (LDNR), United States Forest Service (USFS), United States Fish and Wildlife Service (USFWS), Louisiana Department of Transportation and Development (LADOTD), railroads, pipelines, levee districts, and cities / municipalities. Assembly of forms and permit documentation and coordination with permitting entities continued. STATEMENTS PROVIDED BY THE STATE: The team organized access and dialogue to the Department of Transportation and Development in an effort to get GEC to met their contracted submittal schedule | 0 | STATEMENTS PROVIDED BY GEC: Construction anticipated to begin 4th quarter 2011. STATEMENTS PROVIDED BY THE STATE: The team organized access and dialogue to the Department of Transportation and Development in an effort to get GEC to met their contracted submittal schedule. | 0 | STATEMENTS PROVIDED BY GEC: Construction anticipated to begin 4th quarter 2011. STATEMENTS PROVIDED BY THE STATE: The team organized access and dialogue to the Higher Education campuses and the Department of Transportation and Development in an effort to get GEC to met their contracted submittal schedule. | 1 | STATEMENTS PROVIDED BY THE STATE: LONI continues to refine their optical and Ethernet network designs based upon movements within the project and availability of current technology. LONI has procured a GIS system (including hardware and software) to manage the fiber and equipment assests of this project. | 0 | 0 variance | 0 | 0 variance | 0 | 0 variance | 2011-08-17 14:37 | 2011-08-17 14:37 | 5537 | 5537 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | 2011 | Q3 | Q3 - 2011 | 4141 | 3917 | TRUE | 7 | 0 variance | 0 | N/A | N/A | 100 | 0 variance | 55 | 0 variance | 35 | 0 variance | 0 | 0 variance | 0 | 0 variance | 1 | 0 variance | 0 | 0 variance | 0 | 0 variance | 0 | 0 variance | 2011-11-18 15:00 | 2011-11-18 15:00 | 5537 | 5537 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | 2011 | Q4 | Q4 - 2011 | 5191 | 4859 | TRUE | 7 | 0 variance | 0 | N/A | N/A | 100 | 0 variance | 55 | 0 variance | 35 | 0 variance | 0 | 0 variance | 0 | 0 variance | 1 | 0 variance | 0 | 0 variance | 0 | 0 variance | 0 | 0 variance | 2012-02-22 14:58 | 2012-02-22 14:58 | 5537 | 5537 | Louisiana Board of Regents | TRUE
NT10BIX5570047 | 2010 | Q2 | Q2 - 2010 | 70 | 1320 | FALSE | 5 |  |  |  |  | 100 |  | 35 |  | 25 |  | 5 |  | 5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2010 | Q3 | Q3 - 2010 | 365 | 1449 | TRUE | 1 | The Finding of No Significant Impact (FONSI), which was originally forecasted to be received in 2nd Quarter was received late in the 3rd Quarter. This delayed the projected construction start date, which is now scheduled to begin in the 4th quarter of the calendar year. In addition, the permitting process is showing early indications to take longer than expected on some select routes. | 0 |  | N/A | 100 | N/A | 35 | N/A | 10 | See 2a. above describing delay from initial projections. | 5 | N/A | 5 | N/A | 5 | N/A | 0 | See 2a. above describing delay from initial projections. | 0 | See 2a. above describing delay from initial projections. | 0 | See 2a. above describing delay from initial projections. | 2010-11-19 17:22 | 2010-11-19 17:22 | 5529 | 5529 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2010 | Q4 | Q4 - 2010 | 753 | 1787 | TRUE | 5 | The overall project is lagging the baseline as a result of the time consumed on the Environmental Assessment (EA) and subsequent receipt of the Finding of No Significant Impact (FONSI). During the fourth quarter of 2010, significant progress has been made towards permitting, yet final receipt of permits and State Environmental Protection Act clearance has protracted constructions start dates. | 0 | N/A | N/A | 100 | N/A | 50 | N/A | 25 | See 2a. above. | 30 | See 2a. above. | 20 | See 2a. above. | 15 | See 2a. above. | 0 | Based on the above comments, construction has not yet started. | 0 | See 2a. above. | 0 | In addition to comments provided in 2a., construction has not yet started, consequently not allowing for Network Testing to be initiated. | 2011-01-28 13:55 | 2011-01-28 13:55 | 5529 | 5529 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2011 | Q1 | Q1 - 2011 | 2263 | 2877 | TRUE | 6 | The overall project is lagging the Baseline as the project originally had intentions of starting construction in the third quarter of year one. Additional resources and timeline revisions have been made to insure completion on schedule. | 0 | N/A | N/A | 95 | The Biological Assessment (BA) for Sub Recipient Pacific Public Utility District is currently underway. Completion and finalization of this metric is anticipated by end of Quarter 2, 2011. | 70 | No variance. | 35 | Rights of Way acquisition continued this quarter with progression made on routes targeted for construction this year. Indications are we will be caught up with this metric by end of calendar year 2011. | 45 | Permitting continues on primary routes selected for construction during the early part of this year. Required permits for several routes including all EC routes and SE/SW-1 and 2's have been completed for Ecology, Department of Natural Resources, and Washington State Department of Transportation. Additionally, permit acquisition for construction scheduled later will commence in the second half of 2011 and this metric is expected to substantially complete by the end of the year. | 25 | Staking and site preparation continue as work toward making up some of the lag in the projected milestones initially set forth in the project continues. | 17 | Additional equipment was purchased and installed this quarter. Work continues toward booking our In Kind assets that fall within this category. Equipment procurement will more than likely not attain the Baseline projections until Quarter 1 of 2012. | 1 | Network build has commenced and shows progress against the milestone starting in this quarter. This metric will attain Baseline projections by end of 2011. | 15 | Some backbone segments have been upgraded to facilitate additional traffic, testing on failover protection in preparation for new route and redundancy configurations is underway. This metric will be met as additional equipment is procured and In Kind assets are attributed toward the project. Baseline projections will be met following completion of 2011 backbone route construction expected to catch up to the milestone by Quarter 1, 2012. | 0 | Testing of the network will commence once construction has advanced and fiber is operational. | 2011-05-24 09:07 | 2011-05-24 09:07 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2011 | Q2 | Q2 - 2011 | 3091 | 3303 | TRUE | 10 | The overall project is lagging the Baseline as the project had originally intended to start construction in the third quarter of the first year of the project. Additional resources and adjustments to the project time line have been made to insure a timely completion as outlined by the program. | 0 | N/A | N/A | 98 | The Environmental Assessment is substantially complete. | 85 | No variance. | 70 | Rights of Way acquisition continued on routes selected for construction in 2011 and this metric is expected to concur with the Baseline projections by then end of 2011. | 60 | Permitting for routes initially projected for construction in the second year of the project life cycle are in process. This metric is anticipated meeting projections by the end of 2011. | 45 | Site preparation is only slightly behind Baseline projections and is anticipated to meet projections over the next two quarters. | 30 | A majority of Equipment is comprised of In Kind Assets currently being reviewed for approval. Once approved and booked to the project, this metric will meet or exceed projections. | 2 | This category was originally projected to start much earlier than it actually did. Based on the Environmental approval process taking longer than anticipated, this metric will not meet Baseline projections until sometime during the final year of the project. | 25 | As was mentioned under 'Equipment Procurement' above, a large amount of Equipment is in the form of In Kind assets being contributed towards the Project. Once approved, this metric will be met or exceeded. | 5 | Network Testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter three of year three of the project. | 2011-08-15 16:57 | 2011-08-15 16:57 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2011 | Q3 | Q3 - 2011 | 4217 | 3957 | TRUE | 31 | With the 'booking' of our In Kind Match this metric improved from the last quarter actual. Though actual compared to baseline projection is lagging, progress towards meeting the Broadband Technologies opportunity Program guidelines is being made. Northwest Open Access Network anticipates a considerable amount of productivity towards narrowing the current gap between actual and baseline numbers over the next year and will reach the project timeline outlined by the BTOP Program. | 0 |  | N/A | 100 | No Variance. | 95 | No Variance. | 85 | Rights of Way acquisition continued as we approach the final phase of the three year time frame. Anticipation is to bring this metric in line with Baseline by the end of quarter one 2012. | 85 | No Variance. | 55 | Site preparation will continue into the final year of the project as construction slated for year three of the project will have Site Preparation completed early into next year. This metric will be projected to meet Baseline by quarter two of 2012. | 80 | No Variance. | 16 | Network Build metric will continue to lag as construction was originally forecasted to start much earlier in the project life cycle. All available resources will be utilized to bring this metric to baseline projections by the end of year three. The end of the quarter reflected over one hundred seventy miles of conduit and fiber placed bringing the percent completed to sixteen. Northwest Open Access is taking an aggressive approach to installing conduit so that when the February arrival of fiber is received, it can be expeditiously installed. | 35 | Equipment deployment will follow the Network Build metric and will attain the projections by quarter three of 2012. | 10 | Network Testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter three of the last year of the project timeline and follow the same metric as Network Build. | 2011-11-22 14:19 | 2011-11-22 14:19 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2011 | Q4 | Q4 - 2011 | 5387 | 5064 | TRUE | 48 | Although lagging this metric, progress continues with aggressive construction scheduling and a compressed 2012 schedule. Current projections indicate this metric will be attaining the 70% completion at the end of second quarter 2012. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 90 | Rights of Way acquisition is wrapping up with final work being completed in the upcoming quarter. | 90 | Northwest Open Access Network continues to work with each of the segments pending final changes and necessary rescopes within the project to acquire all permits as required. This process will continue until all routes are finalized and route modifications approved. | 75 | Site preparation has lagged baseline with delays in approval of the environmental assessment. Final Site preparation will be taking place in quarter two of 2012. | 85 | No Variance. | 30 | The Network Build metric will continue to lag as construction was scheduled to start much earlier in the project time line. All available resources will be utilized to bring this metric to baseline projections by the end of year three. The end of the quarter reflected 120 miles of fiber and 300 miles of conduit placed bringing the percent completed to thirty. Northwest Open Access Network is taking an aggressive approach to installing conduit so that when the February arrival of fiber is received, it can be expeditiously installed. This category was previously calculated using miles deployed. | 55 | Equipment deployment will follow the Network Build metric and will attain the projections by quarter three of 2012. | 20 | Network Testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter three of the last year of the project timeline and follow the same metric as Network Build. | 2012-02-29 11:00 | 2012-02-29 11:00 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2012 | Q1 | Q1 - 2012 | 6185 | 5695 | TRUE | 56 | This metric continues to lag as we enter the final year of the project. This gap will narrow as we reach the final quarters of 2012. Project completion will occur on time with final construction slated for December 2012. | 0 |  | N/A | 100 | No variance. | 100 | No variance. | 95 | This metric is nearing completion with minimal ROW acquisition remaining. Completion of this metric is slated for end of Q2 2012. | 95 | No variance. | 80 | Site preparation has lagged baseline with delays in approval of the environmental assessment. Final Site preparation will be taking place in quarter three of 2012. | 90 | Equipment procurement will lag into the final stages of the project with minimal purchasing yet to be completed. Final procurement will occur in the third quarter of 2012. | 57 | The Network Build will continue to lag as construction was scheduled to start much earlier in the project time line. All available resources will continue to be utilized to bring this metric to baseline projections by end of year three. At the end of Q1, 243 miles of fiber and 229 miles of conduit have been placed bringing the percent complete to 57. | 65 | Equipment is being deployed as fiber routes are completed. Delays in fiber shipment has forced equipment deployment to follow final fiber splicing projected in quarter four of 2012. | 25 | Network testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter three of 2012 of the project time line and follow the same metric as Network Build. | 2012-05-18 12:29 | 2012-05-18 12:29 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2012 | Q2 | Q2 - 2012 | 6827 | 6040 | TRUE | 66 | This metric continues to lag as we are midway through the final year of the project. This gap will narrow as we reach the final two quarters of 2012. Project completion will occur on time with final construction slated for December 2012. | 0 |  | N/A | 100 | No variance. | 100 | No Variance. | 97 | Minimal rights of way remain at the end of the quarter with additional acquisitions remaining and forecasted to be completed by the end of Q3 2012. | 97 | A minimal number of permits remain to be obtained at the end of this quarter. A few difficult permits will be left to obtain and project to complete this metric in Q3 2012. | 90 | Site preparation has lagged baseline with delays in approval of the environmental assessment. Final Site preparation will be taking place in quarter three of 2012. | 95 | Minimal Equipment Procurement remains as the majority of all equipment is ordered and in place. All equipment procurement will be completed by end of Q3 2012. | 71 | The Network Build will continue to lag as construction was scheduled to start much earlier in the project time line. All available resources will continue to be utilized to bring this metric to baseline projections by end of year three. At the end of Q2, 588.3 miles have been constructed of which 381 miles of conduit have been placed bringing the percent complete to 71. | 80 | Equipment is being deployed as fiber routes are completed. Delays in fiber shipment has forced equipment deployment to follow final fiber splicing projected in quarter four of 2012. | 40 | Network testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter four of 2012 of the project time line and follow the same metric as Network Build. | 2012-08-01 15:00 | 2012-08-01 15:00 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2012 | Q3 | Q3 - 2012 | 7935 | 6672 | TRUE | 78 | This metric continues to lag as we are three quarters of the way through the final year of the project. This gap will narrow as we reach the final quarter of 2012. Project completion will occur on time with final construction slated for December 2012. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 89 | The Network Build will continue to lag as construction was scheduled to start much earlier in the project time line. All available resources will continue to be utilized to bring this metric to baseline projections by end of year three. At the end of Q3, 704 miles have been constructed bringing the percent complete to 89. | 90 | Equipment is being deployed as fiber routes are completed. Delays in fiber shipment has forced equipment deployment to follow final fiber splicing projected in quarter four of 2012. | 60 | Network testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter four of 2012 of the project time line and follow the same metric as Network Build. | 2012-11-16 17:01 | 2012-11-16 17:01 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2012 | Q4 | Q4 - 2012 | 8793 | 7591 | TRUE | 87 | Final expenditures and invoices have yet to be received for the project. Estimates are anticipated that final closeout activities will take place in the second quarter of 2013. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 95 | Minimal completion of the Network Build remained at the end of the quarter. Some additional segments needed minimal closeout for final completion. | 100 | No Variance. | 85 | Final testing is being completed and anticipated with completion in January. | 2013-02-14 23:12 | 2013-02-14 23:12 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2013 | Q1 | Q1 - 2013 | 9907 | 8495 | TRUE | 95 | Final expenditures and invoices have yet to be received for the project. Estimates are anticipated that final closeout activities will take place in the second quarter of 2013. Primary construction activity has been completed, with only connections to CAI's remaining. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 99 | Minimal purchases of equipment for various connections to CAI's will remain going into July 2013. | 99 | Primary backbone construction was completed in January with only connections to Community Anchor Institutions remaining. | 98 | Some remaining equipment pertaining to the CAI connections will remain until July of 2013. | 95 | Final testing is being accomplished and anticipated to be complete following connections to Community Anchor Institutions. | 2013-05-24 17:06 | 2013-05-24 17:06 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2013 | Q2 | Q2 - 2013 | 10689 | 9006 | TRUE | 95 | Final expenditures and invoices have yet to be received for the project. Estimates are anticipated that final closeout activities will take place in the third quarter of 2013. Primary construction activity has been completed, with only connections to CAI's remaining. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2013-08-21 17:22 | 2013-08-21 17:22 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2013 | Q3 | Q3 - 2013 | 12183 | 10367 | TRUE | 100 | Project is complete. | 0 | N/A | N/A | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 2014-05-12 17:42 | 2014-05-12 17:42 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570049 | 2010 | Q2 | Q2 - 2010 | 71 | 1325 | FALSE | 7 |  |  |  |  | 100 |  | 12 |  | 15 |  | 5 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570049 | 2010 | Q3 | Q3 - 2010 | 147 | 1340 | TRUE | 8 | Lagging baseline by 2% due to slow project start but exceeded 7% estimate for this quarter provided in Qtr 2 PPR, future project indicators. | 0 |  | N/A | 95 | NTIA comments re EA provided late Sept, requests additional document work to meet revised guidelines and consultation with Corps of Engineers (initiated, waiting); still awaiting response from USFWS; NTIA advised hold on final document submittal until all changes made and all consultation responses received - estimated in late October. | 12 | Lagging baseline by 8% due to slow project start but met estimate for this quarter provided in Qtr 2 PPR, future project indicators | 15 | No change | 5 | No change | 0 | N/A | 0 | No change | 0 | No Change | 0 | No Change | 0 | No change | 2010-10-13 10:53 | 2010-10-13 10:53 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2010 | Q4 | Q4 - 2010 | 817 | 1852 | TRUE | 10 | Variance due to extended time to secure easement agreements with property owners and to complete the EA. | 0 |  | N/A | 95 | EA not final until tower applications submitted to FCC. NTIA will use PA to issue FONSI on project upon notice of FCC submittal. Estimate submittal in February. | 60 | On Track | 75 | On Track | 35 | Permits cannot be finalized until all ROW easement agreements are secured. Permit drawings under way, with submittal pending final design confirmation (aerial and underground). | 0 | N/A | 0 | On track | 0 | On Track | 0 | On Track | 0 | On Track | 2011-01-28 15:58 | 2011-01-28 15:58 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2011 | Q1 | Q1 - 2011 | 1907 | 2699 | TRUE | 25 | No change - overall completion reflects combined completion of all project tasks. Not reflected in federal fund expenditures due to delayed drawdown process. | 0 |  | NA | 100 | No change | 75 | Variance due to awating final design changes requested by VDOT and Central Virginia Electric Cooperative (make ready). The rebid of the Network Operator RFP delayed incorporation of operator requirements in final design. | 85 | Waiting on VDOT for ROW agreement in limited access area in Lovingston town limits. Pole attachment agreement with electric utility nearly complete. Agreements with land owners complete. | 75 | VDOT permits still in progress; requiring agreement for placement in limited access area within Lovingston town limits and small changes to design; agreement in process. Negotiations for make ready work by the electric authority in progress, additional pole loading calculations required to agree on pole replacement needs. Tower permitting in progress with FCC on two towers, have not selected third tower site, and local permitting will be pursued following FCC approval. | 0 | NA | 25 | No change; specifications prepared for bid next quarter, draft bill of materials developed | 0 | No change | 0 | No change | 0 | No change | 2011-05-06 14:58 | 2011-05-06 14:58 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2011 | Q2 | Q2 - 2011 | 3245 | 3385 | TRUE | 16 | Variance due to high make ready costs from utility for aerial attachments, potential to revise deployment at least in some areas to underground. Additional design and consultation with VDOT in progress. Waiting for fiber and conduit delivery, protracted delivery times due to inventory shortages. Won't start construction until halfway through Qtr 3. The budget milestones were developed at the beginning of the project and have not matched due to 1) longer time spent on environmental assessment, and 2) cash accounting (expenditures lag work completed). Materials ordered but no expenditures until received in Qtr 3. Expect expenditures to catch up to milestones to a greater extent in Qtr 3 as deployment starts. | 0 |  | N/A | 100 | No variance at this time | 75 | Variance: High make ready costs resulted reviewing effects of design changes to go underground and bypass areas of high make ready. Design not finalized until cost review is completed and VDOT input regarding underground in ROW. Design progress percent of completion is correct; regression due to reworking design from aerial to underground to bypass high make ready expense. Expect to catch up in 3rd Qtr. | 75 | Variance: Design changes will require VDOT approval, VDOT reviewing route for preliminary approval then permits to be requested. Technically VDOT has 45 days to approve. Rights of Way percent of completion is correct; regression due to reworking design from aerial to underground to bypass high make ready expenses. VDOT permitting affected by redesign process. Expect to catch up in 3rd Qtr. | 60 | Variance: Have not finalized VDOT permitting due to potential design changes. VMRC reviewing water crossings to determine extent of permitting required. Construction Permits and Other Approvals percent of completion is correct; regression due to reworking design from aerial to underground to bypass high make ready expenses. Delayed water permitting process. Expect to catch up in 3rd quarter. | 0 | N/A | 25 | Variance: Fiber ordered, conduit and vaults ready to be ordered in Qtr 3. Aerial attachment hardware not ordered yet, pending any design changes; if necessary ready to be ordered in Qtr 3. Payment not made until delivered. | 0 | Variance: Construction not started due to make ready issues, delay in fiber delivery. | 0 | No variance | 0 | No variance | 2011-08-19 18:19 | 2011-08-19 18:19 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2011 | Q3 | Q3 - 2011 | 4171 | 3934 | TRUE | 21 | Variance due to delayed construction start after redesign to all underground was required to eliminate high make ready expenses and environmental re-consultation was initiated. Materials have been received in this quarter that will not be paid until Qtr 4. Construction will start in Qtr 4 and an additional order for construction materials will have been received. Payments for work completed on this project will always lag grant expenditures by approximately one month due to required Board of Supervisor approval prior to issuing payment to contractors and vendors. | 0 |  | No variance | 100 | No variance to baseline, but reconsultation initiated for change from aerial to underground. Initial response from agencies is no adverse affect, but addendum to be submitted to NTIA for clearance in October. Does not substantially change FONSI received previous quarter. | 100 | No variance from baseline | 100 | No variance from baseline. Verbal approval from VDOT received, permits submitted and awaiting signatures at the end of September. | 95 | Variance, awaiting permitting from Marine Resource Commission for five water crossings and formal notification of no permit required from US Army Corps of Engineers. Verbal approvals received, expect permits to be issued in October. | 0 | N/A | 0 | Variance due to redesign, held off on ordering materials until all underground design was approved. $271,632 in materials were received in Qtr 3 (total 44% of budget including unliquidated obligations)but will not be paid until Qtr 4. An additional order for construction materials of approximately $33,000 will be ordered in Qtr 4. Operating and premise equipment will not be ordered until approximately Qtr 1 of 2012. | 0 | Variance, delay due to make ready issue causing redesign, materials delivery, final permitting and awaiting final environmental assessment amendment approval. Contractor ready to start when final approvals received. Materials needed to start construction on on hand. Construction anticipated to be in progress starting by early November. | 0 | Variance due to delayed network construction. Equipment deployment will not occur until approximately Qtr 2 of 2012. | 0 | No variance | 2011-11-21 09:56 | 2011-11-21 09:56 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2011 | Q4 | Q4 - 2011 | 4411 | 4071 | TRUE | 36 | Delayed construction start due to a redesign to avoid high make ready costs. Construction was originally projected to start in July but work didn't begin until November when utility locates were conducted by the construction crew. Construction was in progress but has not been billed, and materials received and on order that have not been billed. There were fewer than anticipated construction work days in December due to VDOT restrictions on construction surrounding holiday travel periods and extended rain delays. | 0 | N/A | N/A | 100 | No variance to baseline. Environmental assessment amendment approved for all underground construction of fiber. | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 45 | Delayed construction start, delayed receipt of materials. 45% of the equipment budget has been expended with $73,534 in unliquidated obligations for materials received and on order. | 13 | Delayed construction start by approximately 6 months. The fiber network construction was underway in December with a majority of the construction materials received. Tower construction not anticipated until summer or fall of 2012. | 0 | Delayed construction start by approximately 6 months. Network operating and end user equipment will not be deployed until the fiber construction is complete, anticipated to occur in Qtr 2 of 2012. | 0 | Delayed construction start by approximately 6 months. Less than 1 miles of construction completed and no circuits ready for testing. Expect testing to begin near end of Qtr 1 2012 as significant construction segments connecting to the Lovingston network operating center are completed. | 2012-01-24 13:55 | 2012-01-24 13:55 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2012 | Q1 | Q1 - 2012 | 6129 | 5667 | TRUE | 49 | Overall project completion variance is due to a network redesign to avoid high make ready costs that delayed the project start. Construction did not start in earnest until December and experienced numerous delays due to weather and department of transportation restrictions on work around holiday periods. Construction has since progressed at a steady pace. The overall project progress will continue to lag baseline expectations as measured by expenditures due to a hold back payment contract with the construction company. | 0 |  | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 60 | Variance due to a delayed construction start and outside plant materials orders placed on pace with construction to ensure efficient use of materials. The remainder of the outside plant materials have been ordered, most received but expenditures will not be made until next quarter. | 25 | Delayed construction start by approximately 6 months. The fiber network was well underway this quarter and completed approximately 45% of the conduit installation. Tower construction will occur in the third and fourth quarters of 2012. | 0 | Delayed construction start by approximately 6 months. Network operating and end user equipment will not be deployed until the fiber construction is complete. Deployment of equipment anticipated to start in quarter 2 of 2012. | 0 | Delayed construction start by approximately 6 months. Testing anticipated to begin in Quarter 2 of 2012. | 2012-05-16 11:43 | 2012-05-16 11:43 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2012 | Q2 | Q2 - 2012 | 7041 | 6148 | TRUE | 70 | Overall project completion variance is due to a network redesign to avoid high make ready costs that delayed the project start. Construction did not start in earnest until December and experienced numerous delays due to weather and department of transportation restrictions on work around holiday periods. Construction has since progressed at a steady pace. The overall project progress will continue to lag baseline expectations as measured by expenditures due to a hold back payment contract with the construction company. | 0 |  | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 71 | Variance due to a delayed construction start and outside plant materials orders placed on pace with construction to ensure efficient use of materials. Small orders for miscellaneous outside plant materials expected but the majority of construction materials expenditures have been completed. The order for network electronics has been placed but payments not expected until next quarter. | 65 | Delayed construction start by approximately 6 months. Construction of the fiber network continued steadily with approximately 74.2% of conduit and 35.5% of fiber installed by the quarter end. Tower construction will occur in the third and fourth quarters of 2012. | 0 | Delayed construction start by approximately 6 months. Network operating and end user equipment will not be deployed until the fiber construction is complete. Order for network electronics has been placed and deployment anticipated to start in the following quarter. | 0 | Delayed construction start by approximately 6 months. Testing anticipated to begin in the following quarter. | 2012-08-13 09:13 | 2012-08-13 09:13 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2012 | Q3 | Q3 - 2012 | 7787 | 6595 | TRUE | 87 | The overall project completion variance is due to a network redesign to avoid high make ready costs that delayed the project start. The fiber network construction is nearing completion as the last conduit tie-ins and fiber pulls are being made. Equipment deployment is in process in the network operating center and in the community anchor institutions, and testing has begun on both the fiber and the equipment. Two towers have been ordered, foundation designs approved and construction will occur in the following quarter. Work to secure the third tower site continues with one tentative site currently in negotiation with the property owner. | 0 | N/A | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 90 | Variance due to a delayed construction start and outside plant materials ordered on pace with construction to ensure efficient use of materials and funds. Small orders for final outside plant items placed to accommodate the final pieces of fiber network construction. The majority of network equipment has been ordered but expenditures will not be completed until the following quarter. | 80 | Variance due to a delayed construction start of approximately six months. The fiber network construction is nearing completion as the last conduit tie-ins and fiber pulls are being made. Construction closeout activities have begun that include grounds restoration, construction clean up and preparation for a materials audit. Two towers have been ordered that will be erected in the following quarter, and the third tower site has not been secured but is in negotiations at this time. | 65 | Variance due to a delayed construction start of approximately six months. Equipment is in process of installation in the network operating center in Lovingston, installation of customer premise units is underway and the cabinet has been set at the Colleen tower. Cabinets at the Avon and Afton towers will be set in the following quarter. Testing of fiber and equipment is ongoing as the equipment is being installed and will be complete in the following quarter. | 65 | Variance due to a delayed construction start of approximately six months. Testing of fiber and equipment is in process by both the fiber install crew and the network equipment vendor. The wholesale internet provider completed collocation in the network operating center and the circuit is operational. Testing will be complete in the following quarter. | 2012-11-07 16:02 | 2012-11-07 16:02 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2012 | Q4 | Q4 - 2012 | 8889 | 7678 | TRUE | 93 | Variance due to delayed construction start, difficulties in securing an optimum tower location in Massie's Mill, and significant weather events that impacted resources and ground conditions. The backbone fiber construction and community anchor facility connections are complete but rework in some areas as requested by the Virginia Department of Transportation is in progress. The Avon and Afton towers were constructed and fiber interconnections installed to the tower compounds including one at the Colleen tower. The last remaining tower is scheduled for construction in the first quarter of 2013 that will complete the network build. | 0 |  | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 99 | Variance due to delayed construction start and difficulties in securing an optimum tower location in Massie's Mill. The microwave backhaul equipment remains to be ordered and will occur in the first quarter of 2013. | 99 | Variance due to delayed construction start, difficulties in securing an optimum tower location in Massie's Mill, and significant weather events that impacted resources and ground conditions. The backbone fiber construction and community anchor facility connections are complete, and work to close out the Virginia Department of Transportation permit is in progress. The last remaining tower is scheduled for construction in the first quarter of 2013 that will complete the network build. | 99 | Variance due to delayed construction start and difficulties in securing an optimum tower location in Massie's Mill. The microwave backhaul system remains to be deployed. Quotes have been received, a vendor selected, and the contract in development. The equipment will be deployed in the first quarter of 2013. | 99 | Variance due to a delayed construction start, difficulties in securing an optimum tower location in Massie's Mill, and significant weather events that impacted resources and ground conditions. The backbone fiber construction and community anchor connections are complete, and splicing and testing was completed in this quarter. Final splice testing will be conducted in the first quarter of 2013 following close out of the Virginia Department of Transportation permit. | 2013-02-21 16:51 | 2013-02-21 16:51 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2013 | Q1 | Q1 - 2013 | 9713 | 8391 | TRUE | 99 | Variance due to a delayed construction start and significant weather events that impacted resources and ground conditions. Final completion of all activities to turn up the last tower and secure microwave frequency licensing is currently delayed due to a backlog at the National Radio Quiet Zone; the Quiet Zone is currently engaged in reviewing narrow banding applications unrelated to this project. The last remaining tower was erected in this quarter but the microwave equipment will be installed and tested in the following quarter. Completion of the FCC licensing is expected to occur in the following quarter as well. | 0 | 0 | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 100 | No variance | 99 | Variance due to a delayed construction start and significant weather events that impacted resources and ground conditions. Final completion of all activities to turn up the last tower and secure microwave frequency licensing is currently delayed due to a backlog at the National Radio Quiet Zone; the Quiet Zone is currently engaged in reviewing narrow banding applications unrelated to this project. The last remaining tower was erected in this quarter but the microwave equipment will be installed and tested in the following quarter. Completion of the FCC licensing is expected to occur in the following quarter as well. | 99 | Variance due to delayed construction start and significant weather events that impacted resources and ground conditions. The last remaining equipment to be deployed is for microwave backhaul between the Massie's Mill, Wintergreen and Avon towers. Equipment has been procured and will be installed in the following quarter. Testing and turn up of the equipment will occur upon receipt of licensing by FCC also expected in the following quarter. | 99 | Variance due to delayed construction start and significant weather events that impacted resources and ground conditions. Testing and turn up of the fiber network is complete. The last remaining equipment to be deployed is for microwave backhaul between the Massie's Mill, Wintergreen and Avon towers. Equipment has been procured and will be installed in the following quarter. Testing and turn up of the equipment will occur upon receipt of licensing by FCC also expected in the following quarter. | 2013-05-14 13:37 | 2013-05-14 13:37 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2013 | Q2 | Q2 - 2013 | 11985 | 10147 | TRUE | 100 | No variance, project complete. | 0 |  | N/A | 100 | No variance, project complete. | 100 | No variance, project complete. | 100 | No variance, project complete. | 100 | No variance, project complete. | 0 | N/A | 100 | No variance, project complete. | 100 | No variance, project complete. | 100 | No variance, project complete. | 100 | No variance, project complete. | 2014-03-25 11:12 | 2014-03-25 11:12 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570050 | 2010 | Q2 | Q2 - 2010 | 72 | 1284 | FALSE | 5 |  | 0 |  |  | 100 |  | 60 |  | 15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2010 | Q3 | Q3 - 2010 | 193 | 1363 | TRUE | 5 | Make ready planning is ahead of schedule. | 0 |  | N/A | 100 | Received FONSI first week of October | 60 | Make ready planning is ahead of schedule. | 15 | Make ready planning is ahead of schedule. | 0 | N/A | 0 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 2010-10-28 14:47 | 2010-10-28 14:47 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2010 | Q4 | Q4 - 2010 | 1055 | 2094 | TRUE | 11 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Due to make ready planning and fiber purchase ahead of schedule. | 0 |  | N/A | 100 | No Variance from Baseline Report | 90 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 25 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Make ready planning and submission ahead of schedule. | 0 | No Variance from Baseline Report | 10 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 25 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Ahead of schedule on equipment purchases. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 0 | No Variance from Baseline Report | 2011-02-10 16:03 | 2011-02-10 16:03 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2011 | Q1 | Q1 - 2011 | 2199 | 2845 | TRUE | 24 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 0 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 95 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 36 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010 and make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 0 | No Variance from Baseline Report | 30 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 5 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. The percentage decrease is due to updated guidance on calculating percent complete based off of expenditures. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 4 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Conneaut Telephone fiber purchase is 70% complete. Zito expects to be back on schedule by the end of the September 2011 quarter. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 2011-05-20 10:52 | 2011-05-20 10:52 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2011 | Q2 | Q2 - 2011 | 3131 | 3323 | TRUE | 30 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 0 | N/A | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 48 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010 and make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 0 | No Variance from Baseline Report | 50 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Negative variance also due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 5 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010 and make ready delays. Negative variance of funds expended due to fiber and hardware shipment delay. Zito expects initial orders in September quarter and expects to receive remaining shipments in December 2011 quarter and March 2012 quarter. Zito expects to be back on schedule by the end of the December 2011 quarter. | 4 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Fiber purchase & lease in northeast Ohio near completion. Zito expects to be back on schedule by the end of the December 2011 quarter. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 2011-08-16 17:03 | 2011-08-16 17:03 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2011 | Q3 | Q3 - 2011 | 4085 | 3886 | TRUE | 50 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 0 | N/A | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 77 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010 and make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 0 | No Variance from Baseline Report | 85 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Negative variance also due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 28 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010 and make ready delays. Negative variance of funds expended due to fiber and hardware shipment delay. Zito expects initial orders in September quarter and expects to receive remaining shipments in December 2011 quarter and March 2012 quarter. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 4 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Fiber purchase & IRU in northeast Ohio near completion. The percent complete remains the same as construction did not commence during the quarter. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 2011-11-16 16:12 | 2011-11-16 16:12 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2011 | Q4 | Q4 - 2011 | 5063 | 4735 | TRUE | 66 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has started albeit slowly during the quarter. In the next quarter as make ready delays lessen construction will increase as more crews are utilized. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 0 | n/a | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 93 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Make ready delays continue but are alleviating. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 0 | No Variance from Baseline Report | 85 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Negative variance also due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 53 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010 and make ready delays. Negative variance of funds expended due to fiber shipment delay. Zito expects expects to receive remaining shipments in March 2012 quarter. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 18 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Negative variance due to continued make ready delays. Construction has started albeit slowly during the quarter. In the next quarter Zito expects this metric to increase as make ready delays lessen allowing more construction crews to be used. Fiber purchase & IRU in northeast Ohio not yet activated. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 10 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. None of the fiber constructed is currently active. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 2012-02-16 09:08 | 2012-02-16 09:08 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2012 | Q1 | Q1 - 2012 | 6111 | 5658 | TRUE | 76 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress was hampered by inconsistent make ready completion. As Zito's construction crews get out of the urban areas construction pace will increase. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 0 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | Percentage is based off of rights of way expenditures from budget. | 0 | No Variance from Baseline Report | 90 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the inconsistent make ready completion hampering complete stretches of fiber from being completed. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 67 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Percentage based off of expenditures from the equipment budget line item. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 30 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress was hampered by inconsistent make ready completion. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 25 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress was hampered by inconsistent make ready completion. Majority of network electronics have not been installed as network build is not active due to incomplete make ready. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 3 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Only a small portion of the network is currently active. The negative variance is due to inconsistent make ready completion that hampers complete stretches of fiber from being constructed. | 2012-05-15 15:54 | 2012-05-15 15:54 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2012 | Q2 | Q2 - 2012 | 7071 | 6163 | TRUE | 88 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress was hampered by inconsistent make ready completion. As Zito's construction crews get out of the urban areas construction pace will increase. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | 0 | n/a | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 95 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the inconsistent make ready completion hampering complete stretches of fiber from being completed. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | 100 | Variance due to rebudget that reallocated funds to construction and rights of way. | 53 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress was hampered by inconsistent make ready completion. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | 35 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress was hampered by inconsistent make ready completion. Majority of network electronics have not been installed as network build is not active due to incomplete make ready and decreased construction production. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | 15 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Only a small portion of the network is currently active. The negative variance is due to inconsistent make ready completion that hampers complete stretches of fiber from being constructed. | 2012-08-15 10:04 | 2012-08-15 10:04 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2012 | Q3 | Q3 - 2012 | 7871 | 6640 | TRUE | 92 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress was hampered by inconsistent make ready completion. As Zito's construction crews get out of the urban areas construction pace will increase. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | 0 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 98 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the inconsistent make ready completion hampering complete stretches of fiber from being completed. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | 100 | No Variance from Baseline Report | 70 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress was hampered by inconsistent make ready completion. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | 55 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress was hampered by inconsistent make ready completion and dual build. Majority of network electronics have not been installed as network build is not active due to incomplete make ready and decreased construction production. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | 40 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Only a small portion of the network is currently active. The negative variance is due to inconsistent make ready completion that hampers complete stretches of fiber from being constructed. | 2012-11-14 14:05 | 2012-11-14 14:05 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2012 | Q4 | Q4 - 2012 | 8775 | 7569 | TRUE | 99 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 0 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 98 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Negative variance also due to the delayed construction completion. | 100 | No Variance from Baseline Report | 98 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito was able to complete most of the project build in the current quarter. | 70 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Negative variance also due to the delayed construction completion. | 60 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. The negative variance is due construction crews still completing the project build. Due to continuing construction portions of the network are not active delaying network testing. | 2013-02-14 12:05 | 2013-02-14 12:05 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2013 | Q1 | Q1 - 2013 | 9239 | 8059 | TRUE | 100 | No Variance from Baseline Report | 0 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 2013-04-24 12:28 | 2013-04-24 12:28 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2013 | Q2 | Q2 - 2013 | 10683 | 9003 | TRUE | 100 | No Variance from Baseline Report | 0 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 2013-08-21 15:19 | 2013-08-21 15:19 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2013 | Q3 | Q3 - 2013 | 11293 | 9444 | TRUE | 100 | No Variance from Baseline Report | 0 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 2013-11-19 14:25 | 2013-11-19 14:25 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570051 | 2010 | Q2 | Q2 - 2010 | 73 | 1312 | FALSE | 37 |  | 0 |  |  | 100 |  | 100 |  | 0 |  | 90 |  | 25 |  | 40 |  | 10 |  | 10 |  | 10 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2010 | Q3 | Q3 - 2010 | 345 | 1439 | TRUE | 14 | equipment procurement not started, With the anticipated release of funds, First Step will increase purchasing in the 3rd quarter to bring the project back on track with the baseline projections. | 0 |  | n/a | 99 | submitted waiting on Finding of No Significant Impact | 100 | submitted Environmental Assessmentdid not require any network adjustments | 0 | n/a | 90 | Federal Communications Commission/Federal Aviation Administration clearance for tower received, Conditional Use Permit in progress for Paradise Ridge tower. road access dispute has surfaced | 0 | funding has not been released to start this phase of the project | 10 | bids have been submitted/reviewed but purchasing has not occurred. awaiting Finding of No Significant Impact and security interest filing | 0 | not started due to Finding of No Significant Impact | 0 | not started due to Finding of No Significant Impact | 0 | not started due to Finding of No Significant Impact | 2010-11-18 10:47 | 2010-11-18 10:47 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2010 | Q4 | Q4 - 2010 | 1137 | 2176 | TRUE | 15 | equipment bids reviewed and scored. Ready for purchasing to begin when weather clears. Q1 purchasing will occur to bring project closer to projected time line. | 0 | n/a | n/a | 100 | Completed Finding of No Significant Impact issued 10/18/2010. | 100 | submitted network design has been approved | 0 | n/a | 90 | Conditional Use Permit still required for Paradise Ridge location. Land owner, road access dispute still ongoing. Building permit for Lewiston Rim site secured. | 0 | not started due to winter weather conditions | 10 | bid review completed. contracts for winning bids are being prepared. | 0 | not started due to winter weather conditions | 0 | not started due to winter weather conditions | 0 | not started due to winter weather conditions | 2011-02-14 16:09 | 2011-02-14 16:09 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2011 | Q1 | Q1 - 2011 | 1989 | 2740 | TRUE | 7 | environmental completed, procurement process for primary equipment vendors completed, purchasing of initial project communication huts completed | 0 | n/a | n/a | 100 | Completed Finding of No Significant Impact issued 10/18/2010 | 100 | submitted network design has been approved | 0 | n/a | 90 | Conditional Use Permit still required for Paradise Ridge location. Land owner, road access dispute still ongoing. | 0 | not started due to winter weather conditions, First Step will re-adjust scheduling to ensure that project goals are met in accordance with prior project planning and adjustments. First is continually adjusting scheduled construction activities based on weather and other factors, while keeping in mind the 67% completion requirement by the end of the project year. | 15 | communication huts purchased, being prepared for use by contractor. Procurement has been delayed due to weather and environmental analysis. | 0 | not started due to winter weather conditions, not started due to winter weather conditions, First Step will re-adjust scheduling to ensure that project goals are met in accordance with prior project planning and adjustments. First is continually adjusting scheduled construction activities based on weather and other factors, while keeping in mind the 67% completion requirement by the end of the project year. | 0 | not started due to winter weather conditions, not started due to winter weather conditions, First Step will re-adjust scheduling to ensure that project goals are met in accordance with prior project planning and adjustments. First is continually adjusting scheduled construction activities based on weather and other factors, while keeping in mind the 67% completion requirement by the end of the project year. | 0 | not started due to winter weather conditions, not started due to winter weather conditions, First Step will re-adjust scheduling to ensure that project goals are met in accordance with prior project planning and adjustments. First is continually adjusting scheduled construction activities based on weather and other factors, while keeping in mind the 67% completion requirement by the end of the project year. | 2011-05-12 17:59 | 2011-05-12 17:59 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2011 | Q2 | Q2 - 2011 | 3067 | 3291 | TRUE | 25 | First Step is behind in the overall project due to the late winter. With the start of construction and the additional trained staff, we anticipate being on track Q4. | 0 |  | n/a | 100 | Completed Finding of No Significant impact issued 10/18/2010 | 100 | submitted network design has been approved | 0 | n/a First Step will not be working within any established rights of way | 90 | Conditional use permit required for Paradise Ridge. Access road dispute between land owners is resolved | 20 | Lewiston Rim site prep is completed. SpudHill site is underway. Others have not yet started. | 25 | Phase 1 radios have been purchased. All tower and communication hut structures have been acquired. Additional staffing is being used to speed the deployment of equipment in the field. The speed of deployment directly effects the rate at which equipment is procured so as to have appropriate storage and inventory/cost management | 0 | No network build has been started at the close of Q2, 2011. The extended winter and regulatory compliance hampered the start of the construction phase of the project. First Step has added additional staff to bring the project back in line with the previous project estimates | 0 | equipment deployment has not yet started due to the weather conditions and regulatory delays. First Step has added additional staff to bring the project back in line with the previous project estimates | 0 | network testing starts and run concurrently with equipment deployment. Weather and regulatory delays have caused the project to fall behind estimates. First Step has added staff to bring the project back in line with milestone estimates | 2011-08-12 17:41 | 2011-08-12 17:41 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2011 | Q3 | Q3 - 2011 | 4067 | 3877 | TRUE | 40 | First year environmental and weather delays put the project behind. Additional staff is working to bring the project back in line with projections. | 0 | n/a | n/a | 100 | completed. Finding of no significant impact issued 10/18/2010 | 100 | submitted network design approved | 0 | n/a | 95 | First Step is working with the US Forest Service to secure the final location approval. All other permits have been received. | 70 | 7 of 10 tower sites have been prepared. The 3 sites in Elk City remain. Those are expected to be completed in Q4 | 41 | Phase 1 and Phase 2 radios have been ordered and received. Switching equipment has been received. Routing and management for Phase 1 and Phase 2 radios has been acquired. | 25 | The first 13 microwave paths have been completed. Additional staff is working to deploy additional paths to catch up with projected plan. | 25 | The first 13 microwave paths have been completed. Additional staff is working to deploy additional paths to catch up with projected plan. | 25 | Network testing is completed along with the deployment of the paths before turning the path up for the Community Anchor Institution or for using the path as a middle mile segment of the network. | 2011-11-16 13:36 | 2011-11-16 13:36 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2011 | Q4 | Q4 - 2011 | 5403 | 5084 | TRUE | 46 | First year environmental and weather delays put the project behind. Additional staff has been added to bring the project back in line and to ensure the project is completed by 2/28/2013. | 0 | n/a | n/a | 100 | completed, Finding of No Significant Impact issued 10/18/2010 | 100 | submitted network design approved | 0 | n/a | 95 | First Step continues to work with the US Forest Service to secure the final location approval. No significant project delay expected and all other permits have been received. | 100 | 10 of 10 tower sites have been prepared and foundations poured. | 49 | Phases 1 - 3 of the radio equipment has been ordered and received. All switching equipment has been procured. | 57 | 39 of 69 fixed microwave paths have been built representing 57% of the paths to build. Additional staff has been assigned to the project to bring it into compliance with both the 67% completion requirement by 2/28/2012 as well as 100% completion by 2/28/2013. | 57 | 39 of 69 fixed microwave paths have been built representing 57% of the paths to build. Additional staff has been assigned to the project to bring it into compliance with both the 67% completion requirement by 2/28/2012 as well as 100% completion by 2/28/2013. | 57 | Network testing is completed along with the deployment of the microwave paths. Once testing is completed the path is turned over to the Community Anchor Institution or put into service as part of the middle mile network. | 2012-02-29 13:58 | 2012-02-29 13:58 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2012 | Q1 | Q1 - 2012 | 5913 | 5556 | TRUE | 53 | Winter weather and the Environmental requirements put the project behind schedule from the very beginning. First Step has completed its project improvement plan and it has been accepted. The project process is right in line with the overall project improvement plan. First Step has completed 77% of the physical microwave paths as projected. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 95 | First Step continues to work with the US Forest Service to secure the final approval for the erection of the HighCamp (Mt. Ida) tower site. No significant project delay is expected as a result of this action. | 100 | 10 of 10 tower sites have been prepared and the foundations have been poured | 77 | 77% of the microwave paths and associated equipment have been procured and installed. All switching equipment has been procured. | 77 | The continued winter weather kept progress slowed. However the project remains on track with its approved project improvement plan and the project is expected to be 100% physically constructed by the end of Q3, 2012, ahead of schedule. | 77 | The continued winter weather kept progress slowed. However the project remains on track with its approved project improvement plan and the project is expected to be 100% physically constructed by the end of Q3, 2012, ahead of schedule. | 77 | The network testing occurs as the project is built and deployed. The continued winter weather kept progress slowed. However the project remains on track with its approved project improvement plan and the project is expected to be 100% physically constructed by the end of Q3, 2012, ahead of schedule. | 2012-05-02 16:42 | 2012-05-02 16:42 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2012 | Q2 | Q2 - 2012 | 7287 | 6271 | TRUE | 57 | Winter weather and the Environmental requirements put the project behind schedule from the very beginning. First Step has completed its project improvement plan and it has been accepted. The project process is right in line with the overall project improvement plan. First Step has completed 77% of the physical microwave paths as projected. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 95 | First Step continues to work with the US Forest Service to secure the final approval for the erection of the HighCamp (Mt. Ida) tower site. No significant project delay is expected as a result of this action. | 100 | 10 of 10 tower sites have been prepared and the foundations have been poured | 90 | 90% of the microwave paths have been procured. 77% of the paths have been physically installed. All switching equipment has been procured. 77% puts First Step right on with their 2 year construction projections. | 77 | The continued poor spring weather and remote locations kept progress slowed. However the project remains on track with its approved project improvement plan and the project is expected to be 100% physically constructed by the end of Q3, 2012, ahead of schedule. | 77 | The continued poor spring weather and remote locations kept progress slowed. However the project remains on track with its approved project improvement plan and the project is expected to be 100% physically constructed by the end of Q3, 2012, ahead of schedule. | 77 | The network testing occurs as the project is built and deployed. The continued winter weather kept progress slowed. However the project remains on track with its approved project improvement plan and the project is expected to be 100% physically constructed by the end of Q3, 2012, ahead of schedule. | 2012-08-29 23:39 | 2012-08-29 23:39 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2012 | Q3 | Q3 - 2012 | 8019 | 6716 | TRUE | 60 | Winter weather and the Environmental requirements put the project behind schedule from the very beginning. First Step has completed its project improvement plan and it has been accepted. First Step has completed 86% of the physical microwave paths. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | Final permits from the US Forest Service for the High Camp (Mt. Ida) tower site have been received. | 100 | 10 of 10 tower sites have been prepared and the foundations have been poured. | 90 | 90% of the microwave paths have been procured. 86% of the paths have been physically installed. All switching equipment has been procured. | 86 | Our project timeline shows that the project will have ~95% of the construction completed by Q1 of 2013. That projection was based on a shovel ready start date of Q1 2010 with a 2 year window to completion of construction. Due to the project start delays concerning the EA, First Step has only been under construction for 2 actual years, even though we are in the 11th quarter of the 12 quarter project. First Step will still complete the project on time and on budget. | 86 | Our project timeline shows that the project will have ~95% of the construction completed by Q1 of 2013. That projection was based on a shovel ready start date of Q1 2010 with a 2 year window to completion of construction. Due to the project start delays concerning the EA, First Step has only been under construction for 2 actual years, even though we are in the 11th quarter of the 12 quarter project. First Step will still complete the project on time and on budget. | 86 | The network testing occurs as the project is built and deployed and will remain consistent with the network build and equipment deployment. | 2012-11-21 14:27 | 2012-11-21 14:27 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2012 | Q4 | Q4 - 2012 | 8751 | 7548 | TRUE | 69 | Winter weather and the Environmental requirements put the project behind schedule from the very beginning. First Step has completed its project improvement plan and it has been accepted. First Step has completed 94% of the physical microwave paths. First Step has 4 paths and 1 tower left for complete project completion. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 95 | First Step requested and received approval to add an additional 2 towers to the project. One of those towers, McGary Butte has been completed. The 2nd tower, Gilbert Grade, has not yet been completed. First Step is awaiting the final report from the Nez Perce Tribal Historic Preservation Office for approval to begin construction. Approval is expected shortly and construction is poised to begin immediately. | 95 | All sites except the Gilbert Grade site have been completed. | 95 | 100% of the microwave paths have been procured. 94% of those paths have been physically installed. The remaining equipment procurement consisting mostly of backup battery power will occur in January 2013 | 94 | 94% of all paths are completed. Our project timeline shows that the project will have ~95% of the construction completed by Q1 of 2013. That projection was based on a shovel ready start date of Q1 2010 with a 2 year window to completion of construction. Due to the project start delays concerning the EA, First Step has only been under construction for 2 actual years, even though we are in the 11th quarter of the 12 quarter project. First Step will still complete the project on time and on budget. | 94 | 94% of all paths are completed. Our project timeline shows that the project will have ~95% of the construction completed by Q1 of 2013. That projection was based on a shovel ready start date of Q1 2010 with a 2 year window to completion of construction. Due to the project start delays concerning the EA, First Step has only been under construction for 2 actual years, even though we are in the 11th quarter of the 12 quarter project. First Step will still complete the project on time and on budget. | 94 | The network testing occurs as the project is built and deployed and will remain consistent with the network build and equipment deployment. | 2013-02-13 13:46 | 2013-02-13 13:46 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2013 | Q1 | Q1 - 2013 | 9225 | 8051 | TRUE | 74 | Winter weather and the Environmental requirements put the project behind schedule from the very beginning. First Step has completed its project improvement plan and it has been accepted. First Step has completed 100% of the physical microwave paths and all 12 of the approved towers. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | First Step received final approval for the construction of the Gilbert Grade tower site. This site has now been completed. | 100 | All tower sites are completed. | 100 | All equipment has been procured for the initial project as planned. First Step is awaiting final approval for the no-cost project extension. | 100 | All project paths and towers are completed. First Step is working with the EHP team for approval to add 7 additional path to the project to connection additional CAI's to the network. | 100 | All equipment for the initial project scope has been deployed. | 100 | All installed network paths have been tested and are currently online. | 2013-04-23 14:10 | 2013-04-23 14:10 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2013 | Q2 | Q2 - 2013 | 10585 | 8950 | TRUE | 78 | Winter weather and the Environmental requirements put the project behind schedule from the very beginning. First Step has completed its project improvement plan and it has been accepted. First Step has completed 100% of the physical microwave paths and all 12 of the approved towers. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | completed | 100 | All tower sites are completed | 100 | All equipment has been procured for the initial project as planned. First Step is awaiting final approval for the no-cost project extension. | 100 | All project paths and towers are completed. First Step is working with the EHP team for approval to add 7 additional path to the project to connection additional CAI's to the network. | 100 | All equipment for the initial project scope has been deployed. | 100 | All installed network paths have been tested and are currently online. | 2013-08-14 17:38 | 2013-08-14 17:38 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2013 | Q3 | Q3 - 2013 | 11319 | 9460 | TRUE | 81 | Winter weather and the Environmental requirements put the project behind schedule from the very beginning. First Step has completed its project improvement plan and it has been accepted. First Step has completed 100% of the physical microwave paths and all 12 of the approved towers. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | completed | 100 | All tower sites are completed. | 100 | All equipment has been procured for the initial project as planned. First Step was approved for a no-cost project extension on September 18, 2013. | 100 | All project paths and towers are completed. First Step is working with the EHP team for approval to add 7 additional path to the project to connection additional CAI's to the network. | 100 | All equipment for the initial project scope has been deployed. | 100 | All installed network paths have been tested and are currently online | 2013-11-21 10:29 | 2013-11-21 10:29 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2013 | Q4 | Q4 - 2013 | 11815 | 9994 | TRUE | 84 | Winter weather and the Environmental requirements put the project behind schedule from the very beginning. First Step has completed its project improvement plan and it has been accepted. First Step has completed 100% of the physical microwave paths and all 12 of the approved towers. First Step is working with the EHP Team for approval of final paths. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | completed | 100 | All tower sites are completed | 100 | All equipment has been procured for the initial project as planned. First Step was approved for a no-cost project extension on September 18, 2013. | 100 | All project paths and towers are completed. First Step is working with the EHP team for approval to add 6 additional paths to the project to connection additional CAI's to the network. | 100 | All equipment for the initial project scope has been deployed. | 100 | All installed network paths have been tested and are currently online | 2014-02-13 17:22 | 2014-02-13 17:22 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570053 | 2010 | Q2 | Q2 - 2010 | 74 | 1299 | FALSE | 3 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 1.77 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2010 | Q3 | Q3 - 2010 | 461 | 1497 | TRUE | 2 | IT&E has issued three Purchase Orders for three projects.Implementation is well underway. Projects are moving on schedule, but the expenditures are tracking behind the baseline schedule because IT&E does not draw down and pay until invoices are received from the contractors. | 4 | Travel/Training/Conversion Strategy | Travel to inter-islands for site survey and inspection. Expenditures and the costs were not closed by the September 30, 2010. Thus, these expenditures will be included in the 4th Quarter PPR.] | 0 | IT&E has received a Categorical Exclusion. | 5 | RFP for Network Wiring was rejected. RFP for Prepaid will be re-issued. Review of Statement of Work for the Interisland Microwave and Fiber Optic Project. Expenditures will be accrued upon receipt of invoices and recorded in the 4th Quarter PPR. | 0 | IT&E has received a Categorical Exclusion. No Work will be done in the Rights of Way. | 0 | 0.48% Complete - Purchase Order issued for FCC License. | 3 | Materials have a 6 to 8 weeks lead team. Network Wiring RFP was not awarded. | 0 | 0.02% Complete - Purchase Orders were issued this quarter for three projects. Equipment have a 6 to 8 weeks lead time. Equipment can't be ordered for other projects until network design is finalized. Expenditures will be accrued upon receipt of equipment and invoices. Some equipment has been delivered this quarter and we expect to accrue significant expenditures in the 4th quarter, which will appear in the 4th Quarter PPR. | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-30 18:53 | 2010-11-30 18:53 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2010 | Q4 | Q4 - 2010 | 1063 | 2099 | TRUE | 15 | IT&E has issued two additional purchase orders for the Interisland Microwave Project and the 29 Hops 3G Back Haul Project. Installation of one project has been completed during the quarter. Installation of another project is at 65%. Projects are moving on schedule, but the expenditures are tracking behind the baseline schedule because IT&E does not draw down and pay until invoices are received from vendors or contractors. | 7 | TRAVEL/TRAINING/CONVERSION STRATEGY | Travel has been mainly for inter-island site survey, project implementation and inspection. | 0 | IT&E has a Categorical Exclusion. | 9 | Re-design of NOCR Project had to be done. Re-issuance of Prepaid RFP added another delay. Purchase Order was just issued for the 29 Hops Project. Percentage complete is based on actual expenditures, however, project is progressing and we expect expenditures to catch up with actual project progress once invoices are received. | 0 | IT&E has received a Categorical Exclusion. No work will be done in the Rights of Way. | 4 | Purchase Orders had just been issued this quarter. Information being gathered to submit FCC license application. Percentage complete is based on actual expenditures, however, project is progressing and we expect expenditures to catch up with actual project progress once invoices are received. | 3 | Shipping delay of racks. | 21 | Expenditures will be accrued upon receipt of equipment and invoices. | 8 | Installation of Fiber Optic Cards completed this quarter. | 8 | Installation of Fiber Optic Cards completed this quarter. Equipment for 17 Hops were installed. | 9 | Fiber Optic Project has been tested and cut over. | 2011-02-10 18:27 | 2011-02-10 18:27 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2011 | Q1 | Q1 - 2011 | 1995 | 2743 | TRUE | 27 | Project is moving on schedule, but the expenditures are tracking behind the baseline schedule because IT&E does not draw down and pay until invoices are received from the vendors and contractors. Two projects have been completed. | 10 | Travel/Training/Conversion Strategy | Inter-island travel to the other islands for site survey, project implementation and inspection. | 0 | IT&E has a Categorical Exclusion | 14 | Prepaid Billing System RFP had to be re-issued. Best and Final Offers were conducted. | 0 | IT&E has received a Categorical Exclusion. No work will be done in the Rights of Way. | 6 | FCC license applications have been submitted but approvals have not been granted. | 5 | Shipment of racks were delayed. | 41 | Purchase Orders have been issued. However, expenditures will be accrued upon receipt of equipment and invoices. | 10 | 17 Hops Project installed. | 10 | Equipment deployment continues for the MPLS Project. | 12 | 17 Hops Project has been tested and cut over. | 2011-05-13 03:52 | 2011-05-13 03:52 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2011 | Q2 | Q2 - 2011 | 3221 | 3372 | TRUE | 54 | Prepaid Billing Contract just awarded. Equipment have just been received. The 54% completion is based upon actual expenditures. Although construction is further ahead, IT&E does not pay invoices until they are received, normally after the work has been accomplished. This creates a lag in reporting project completion. Construction for some projects are is ahead of schedule. The damaged dish on the Interisland Microwave Upgrade was not anticipated but it will not delay the entire project as there are other areas locations that the contractor is working on. The Prepaid RFP had to be re-issued which caused a delay as well. | 20 |  | Travel to other islands expected as more equipment installed. | 0 | IT&E has a Categorical Exclusion. | 75 | Prepaid Billing Contract just awarded. | 0 | IT&E has received a Categorical Exclusion. No work will be done in the Rights of Way. | 90 | Remaining FCC license applications submitted. | 55 | Equipment for other projects have been just received. | 83 | Prepaid Billing Contract just awarded this quarter. | 30 | NOC Relocation Project completed. | 30 | Equipment deployment started this quarter for the 29 Hops Project. | 30 | MPLS equipment installed and cut over. Some links for the 29 Hops have been cut over. | 2011-08-18 23:20 | 2011-08-18 23:20 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2011 | Q3 | Q3 - 2011 | 4113 | 3900 | TRUE | 68 | The 68% is based upon actual expenditures. Construction is further ahead with the Interisland Microwave Upgrade and the 29 Hops Project completed this reporting period. IT&E does not pay invoices until they are received, normally after the work has been accomplished. This creates a lag in reporting project completion. There are only two subprojects remaining under this Grant Award. | 50 |  | Training and Inter-island travel due to project implementation. | 0 | IT&E received a categorical exclusion. | 85 | Postpaid Billing Project will be awarded next quarter. | 0 | No work will be done in the Rights of Way. | 100 | All FCC licenses have been received that were applied for. | 70 | Racks and servers were installed for Prepaid Billing Project. | 94 | Postpaid Billing Project will be awarded next quarter. | 70 | Postpaid Billing Project will be awarded next quarter. | 90 | Postpaid Billing Project will be awarded next quarter. | 70 | 29 Hops and Interisland Microwave Projects were completed. | 2011-11-17 14:57 | 2011-11-17 14:57 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2011 | Q4 | Q4 - 2011 | 4719 | 4369 | TRUE | 77 | The 77% is based upon actual expenditures. Construction is further ahead with the Prepaid Billing Project in the testing phase. The Prepaid Billing Project and the Postpaid Billing Project, which has just been awarded this quarter are the only two subprojects remaining under this Grant Award. IT&E does not pay invoices until they are received, normally after the work has been accomplished. This creates a lag in reporting project completion. | 71 |  | Inter-island travel continues for project management. No off-island travel/training occurred this quarter. | 0 | IT&E received a categorical exclusion. | 85 | Postpaid Billing Project has not started. | 0 | No work will be done in the ROW. | 100 | FCC licenses applied for have been received. | 93 | J-Bolts replacement work has not been invoiced by contractor. | 94 | Postpaid Billing Project has not started. | 70 | Postpaid Billing Project has not started. | 90 | Postpaid Billing Project has not started. | 80 | Testing continues for the Prepaid Billing Project. | 2012-01-30 16:13 | 2012-01-30 16:13 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2012 | Q1 | Q1 - 2012 | 5907 | 5553 | TRUE | 85 | The 85% is based upon actual expenditures. Prepaid Billing Project is in the testing phase for other modules. The Postpaid Billing Project started this quarter. IT&E does not pay invoices until they are received, normally after the work has been accomplished. This creates a lag in reporting project completion. | 80 |  | User Training conducted under the Prepaid Billing Project. Inter-island travel continues for both Billing Projects. | 0 | IT&E received a categorical exclusion. | 98 | Postpaid Billing Project has started this quarter. | 0 | No work will be done in the ROW. | 100 | FCC licenses applied for have been received. | 100 | All site work has been completed. | 97 | Hardware for Postpaid Billing Project has been ordered. | 80 | Postpaid Billing Project has started. | 95 | Postpaid Billing hardware has just been ordered and project has just started. | 85 | Testing conducted for Prepaid Billing Project continues. | 2012-05-02 01:01 | 2012-05-02 01:01 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2012 | Q2 | Q2 - 2012 | 6843 | 6048 | TRUE | 93 | The 93% is based upon actual expenditures. The Postpaid Billing Project continues. IT&E does not pay invoices until they are received, normally after the work has been accomplished. This creates a lag in reporting project completion. | 85 |  | Training (on-site support) continues for the Prepaid Billing Project. Travel for Prepaid and Postpaid Billing Projects between the islands. | 0 | IT&E received a categorical exclusion. | 99 | Work on Postpaid Systems Requirement Specifications (SRS) took longer than expected and extended past the end of the 1st quarter. | 0 | No work will be done in the ROW. | 100 | FCC licenses applied for have been received. | 100 | All site work has been completed. | 100 | All equipment have been procured. | 90 | Hardware Configuration was completed. Software Development and Customization started for the Postpaid Billing Project. | 97 | Configuration for Hardware for Postpaid Billing Project started; deliver of hardware was delayed by Manufacturer. | 87 | Migration of existing prepaid customers completed this quarter. Working on minor issues. | 2012-08-02 21:59 | 2012-08-02 21:59 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2012 | Q3 | Q3 - 2012 | 7853 | 6631 | TRUE | 97 | The 97% is based upon actual expenditures. The Postpaid Billing Project continues. IT&E does not pay invoices until they are received, normally after the work has been accomplished. This creates a lag in reporting project completion. | 90 |  | Training (on-site support) has been extended this quarter for the Prepaid Billing Project. Travel for Postpaid Billing Projects between the islands. | 0 | IT&E received a categorical exclusion. | 100 | Systems Requirements Specifications completed. | 0 | No work will be done in the Rights of Way. | 100 | FCC licenses applied for have been received. | 100 | All Site Preparation work has been completed. | 100 | All Equipment has been procured. | 95 | Software Development and customization will continue based on the Systems Requirements Specifications (SRS). | 100 | Hardware for Postpaid Billing Project has been installed at Data Network Operations Center (NOC). | 90 | Postpaid Billing Project software development will continue. | 2012-11-13 23:02 | 2012-11-13 23:02 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2012 | Q4 | Q4 - 2012 | 8689 | 7504 | TRUE | 100 | Postpaid Billing is the remaining project under this grant. IT&E has added more than the required Match Share. | 99 |  | Travel for Postpaid Billing Projects between the islands. Training started for Postpaid Billing this quarter. | 0 | IT&E received a categorical exclusion. | 100 | Systems Requirements Specifications completed. | 0 | No work will be done in the Rights of Way. | 100 | FCC licenses applied for have been received. | 100 | All Site Preparation work has been completed. | 100 | All Equipment has been procured. | 99 | Software Development and customization will continue based on the Systems Requirements Specifications (SRS). Data migration will continue. | 100 | All Equipment has been deployed. | 99 | ATP Testing will commence. | 2013-02-11 01:55 | 2013-02-11 01:55 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2013 | Q1 | Q1 - 2013 | 11391 | 9504 | TRUE | 100 | Postpaid Billing Project completed. IT&E has added more than the required Match Share. | 100 |  | Travel and training completed. | 0 | IT&E received a categorical exclusion. | 100 | Network Design completed. | 0 | No work done in the rights of way. | 100 | All FCC licenses approved and received. | 100 | Site preparation completed. | 100 | All equipment has been procured. | 100 | Build has been completed. | 100 | All equipment deployed. | 100 | Testing completed | 2013-11-26 13:24 | 2013-11-26 13:24 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570054 | 2010 | Q2 | Q2 - 2010 | 75 | 1321 | FALSE | [23 empty] | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2010 | Q3 | Q3 - 2010 | 225 | 1379 | TRUE | 3 | See #3 below | 0 | N/A | N/A | 95 | Waiting for two government agencies to submit review letters. Both are due in November. | 0 | See #3 below | 0 | See #3 below | 0 | See # 3 below | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-10-29 12:49 | 2010-10-29 12:49 | 5552 | 5552 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2010 | Q4 | Q4 - 2010 | 1385 | 2397 | TRUE | 5 | No variance | 0 |  | N/A | 100 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-02-28 13:37 | 2011-02-28 13:37 | 5552 | 5552 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2011 | Q1 | Q1 - 2011 | 1459 | 2443 | TRUE | 15 | no variance | 0 | NA | NA | 100 | NA | 25 | no variance | 30 | no variance | 35 | no variance | 0 | NA | 15 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | 2011-04-22 14:35 | 2011-04-22 14:35 | 5552 | 5552 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2011 | Q2 | Q2 - 2011 | 3231 | 3377 | TRUE | 7 | The budget milestones were developed at the beginning of the project and have not matched due to 1) longer time spent on environmental assessment, and 2) cash accounting (expenditures lag work completed). The design work to date has not been invoiced by the contractor in accordance with the contract with the Authority; this was not anticipated when the budget milestone estimates were developed. In addition to design, work to complete permitting and right of way agreements is in progress but has also not been expended and is included in the milestone payment agreement with the contractor. Due to the significant lag in payment expenditures versus work being completed by the construction contractor, it is unlikely expenditures will catch up to budget milestones until the construction reaches the significant completion milestone near the end of this year. (Note: The percent complete number is rounded from 6.7%, actual amount drawn as of 6/30/11 to 7% to allow for entry into the PDF) | 0 |  | N/A | 100 | No Variance | 50 | No variance | 50 | VDOT permit applications submitted but not all approved which was anticipated in the forecast for Qtr 2, No agreement yet with electric utility due to negotiations over make ready costs which was not anticipated. Negotiations with the electric utility are in progress and expected to be completed in Qtr 3. Have completed negotiations with Towns to lease space for point of presence facilities. | 60 | Some of the permits are not affected by the current delay in design and right of way negotiations such as railroad permits. At this time we anticipate significant completion of permitting and approvals in Qtr 4. | 0 | N/A | 15 | The contractor has ordered materials that would not be affected by a change in deployment technique (i.e. aerial to underground). Until a final design is approved, which could potentially change deployment in some areas to underground in order to bypass areas of high make ready expense, the bill of materials cannot be developed. It would not be fiscally prudent to expend funds for materials that may not be needed. | 1 | Construction was originally expected to begin by the end of Qtr 2 with the placement of point of presence (POP) facilities in Luray, Stanley, Shenandoah and Rileyville. Only the facility in Luray was constructed (facility only no equipment) at the end of Qtr 2. | 0 | No Variance | 0 | No Variance | 2011-08-19 13:25 | 2011-08-19 13:25 | 7118 | 7118 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2011 | Q3 | Q3 - 2011 | 4235 | 3966 | TRUE | 9 | The original baseline projected the overall project to be at 75% of completion this quarter. The current project expenditure variance is due primarily to design engineering fees in the amount of $139,886.41 in an unliquidated obligation not yet paid to contracted design/construction firm because of pending redesign. Significant work has been completed on this project that is not reflected in expenditures due to the design/construction contract stipulating payment at significant construction completion points. The project is currently on hold pending modification to change design. High make ready estimate from incumbent electric cooperative forcing redesign to reduce fiber deployment and to move some areas of construction from aerial to underground. | 0 |  | No Variance | 100 | No Variance: anticipate EA amendment needed after NTIA approval of project modification. | 17 | The original baseline projected the network design activities to be at 100% of completion this quarter. As of the end of Qtr 2 2011 the design was at 50% of completion although no expenditures had been made in accordance with the Shentel contract for payments at significant construction completion points. A redesign is now necessary because of exorbitant make ready for aerial construction. This quarter's variance to the baseline projection is a result of delays in negotiating with the electric utility for a reduction in fees, arising from high make-ready and pole attachment costs requiring a new design to avoid these poles. Expenditures to date for network design include fees for design coordination and examination of various methods to reduce the high make ready fees. There is an unliquidated obligation in the amount of $139,886.41 for the cost of the previously completed network design in preparation for construction not reflected in the this quarter's completion percentage. | 50 | The original baseline projected the rights of way activities to be at 100% of completion this quarter. Due to an exorbitant make ready estimate from the electric cooperative for aerial deployment of infrastructure a redesign was initiated that delayed execution of a right of way agreement with the cooperative. Negotiations with the Towns to lease space for point of presence facilities is complete and the Luray facility has been constructed. Pre-permitting discussions for underground deployment in the proposed redesign have held with VA DOT and permitting will commence following design modification approval. | 60 | Pending redesign will require permitting with VDOT for underground in previously proposed aerial areas. No water permits needed and only 2 railroad crossing permits needed. Permitting activities will begin again following NTIA approval of project modification. | 0 | N/A | 0 | The original baseline projected the equipment procurement to be at 100% of completion this quarter. The contractor has ordered materials that would not be affected by a pending change in deployment from aerial to underground but the cost for the materials is included in the overall design/construction contract and will not be expended until significant completion of construction. No additional materials or equipment have been procured because of the need to change the design to bypass high make ready areas. The proposed redesign will reduce the quantity of additional materials required for construction. A project modification will be submitted in October 2011 for approval to change the design. | 0 | The original baseline projected the network build to be at 75% of completion this quarter. Construction was anticipated to begin on the network and associated facilities in Qtr2 2011. A point of presence/interconnection facility was constructed in Luray at the end of Qtr 2 2011 but is currently an unliquidated obligation in the amount of $30,745.91 representing 1% of the entire network build. The network build is on hold pending approval to change the design to bypass areas requiring extensive make ready. | 0 | The original baseline projected equipment deployment to be at 25% of completion this quarter. Purchase of equipment and construction materials is on hold pending NTIA approval of project modification to be submitted in October 2011. | 0 | No Variance | 2011-11-22 16:56 | 2011-11-22 16:56 | 7118 | 7118 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2011 | Q4 | Q4 - 2011 | 5393 | 5077 | TRUE | 8 | Variance due to project on hold pending NTIA approval of project modification. High make ready estimate from incumbent electric cooperative forcing redesign to reduce fiber deployment and to move some areas of construction from aerial to underground. Project drawdown variance due to design engineering not billed yet by contracted construction firm because of pending redesign approval. | 0 |  | No Variance. | 100 | No Variance: anticipate EA amendment needed after NTIA approval of project modification. | 50 | A redesign is necessary because of high make ready for proposed aerial construction. Redesign required to substitute microwave backhaul for fiber back haul between communities. Original design was complete as of last reporting period. This variance to our baseline is a result of design delays arising from high make-ready and pole attachment costs requiring a new design to avoid these poles. | 50 | Variance: Execution of agreement with incumbent electric cooperative pending project modification approval from NTIA. Have completed negotiations with Towns to lease space for point of presence facilities. Pre-permitting discussions held with VA DOT in anticipation of underground work proposed. | 60 | Variance: Pending redesign will require permitting with VDOT for underground in previously proposed aerial areas. No water permits needed and only 2 railroad crossing permits needed. Permitting activities will begin following NTIA approval of project modification. | 0 | N/A | 0 | Variance: Purchase of equipment and construction materials is on hold pending NTIA approval of project modification to be submitted in December 2011. | 1 | Variance: The network build is on hold pending NTIA approval of a project modification. Modification submitted estimates construction of the network to begin following environmental assessment amendment. Only the facility in Luray has been constructed (facility only no equipment). | 0 | Purchase of equipment and construction materials is on hold pending NTIA approval of project modification to be submitted in October 2011. | 0 | Variance: The network build is on hold pending NTIA approval of a project modification. Modification submitted estimates construction of the network to begin following environmental assessment amendment and network testing to follow construction of the network. | 2012-02-29 12:54 | 2012-02-29 12:54 | 7118 | 7118 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2012 | Q1 | Q1 - 2012 | 6267 | 5736 | TRUE | 18 | Variance due to project modification. High make ready estimate from incumbent electric cooperative forcing redesign to reduce fiber deployment and move to microwave connectivity and to move some areas of construction from aerial to underground. Project modification approval in January 2012 by NTIA and NOAA Grants Office and work restarted to implement the project. | 0 |  | No Variance | 90 | Variance: Project modification required re-consultation for National Environmental Protection Act (NEPA) and National Historic Preservation Act (NHPA) review and development of a supplemental environmental assessment (EA). Anticipate no adverse effect determinations from all agencies and supplemental EA submission in April 2012. | 20 | Variance, A redesign is necessary because of high make ready for proposed aerial construction. Redesign required to substitute microwave backhaul for fiber back haul between communities. Original design was complete as of last reporting period. Redesign initiated following project modification approval in January 2012 and completion of contract amendments with design/build firm. Final construction design to be complete by end of June 2012 or sooner. | 50 | Variance: Execution of agreement with incumbent electric cooperative underway based on project modification approval by NTIA and NOAA grants office in January 2012. Have completed negotiations with Towns to lease space for point of presence facilities. Pre-permitting discussions held with VA Department of Transportation (VDOT) in anticipation of underground work proposed. | 60 | Variance: Pending redesign will require permitting with VDOT for underground in previously proposed aerial areas. No water permits needed and only 2 railroad crossing permits needed. Permitting activities underway following NTIA and NOAA grants office approval of the project modification in January 2012. | 0 | N/A | 0 | Variance: Purchase of equipment and construction materials was on hold pending NTIA and NOAA grants office approval of project modification. Procurement will begin with completion of design (currently underway). | 1 | Variance: The network build was on hold pending approval of a project modification which was approved in January 2012 by NTIA and the NOAA Grants Office. The approved Project Modification estimates construction of the network to begin following environmental assessment amendment approval. Only the facility in Luray has been constructed (facility only no equipment). | 0 | Purchase of equipment and construction materials was on hold pending approval of project modification which was approved in January 2012 by NTIA and the NOAA Grants Office. Equipment will be deployed once the environmental assessment amendment and final design are complete. | 0 | Variance: The network build was on hold pending NTIA and NOAA grants office approval of a project modification, approved January 2012. The approved Project Modification estimates construction of the network to begin following environmental assessment amendment and network testing to follow construction of the network. | 2012-05-23 14:01 | 2012-05-23 14:01 | 7118 | 7118 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2012 | Q2 | Q2 - 2012 | 7143 | 6199 | TRUE | 19 | Variance due to project modification. High make ready estimate from incumbent electric cooperative forcing redesign to reduce fiber deployment and move to microwave connectivity and to move some areas of construction from aerial to underground. Project modification approval in January 2012 by NTIA and NOAA Grants Office and work restarted to implement the project. | 0 |  | N/A | 100 | Variance: Project modification required re-consultation for National Environmental Protection Act (NEPA) and National Historic Preservation Act (NHPA) review and development of a supplemental environmental assessment (EA). No adverse effect determinations from all agencies and supplemental EA submission approved by NTIA and the NOAA Grants Office in April 2012. | 95 | Variance: A redesign is necessary because of high make ready for proposed aerial construction. Redesign required to substitute microwave backhaul for fiber back haul between communities. Redesign initiated following project modification approval in January 2012 and completion of contract amendments with design/build firm. Final construction design was completed and submitted to the PCBA to review on June 22, 2012. The Final construction design included Segments 1-3 and 5 of the network. Final design for Segment 4 was underway during the reporting period. | 60 | Variance: Execution of agreement with incumbent electric cooperative underway based on project modification approval by NTIA and NOAA Grants Office in January 2012. Have completed negotiations with Towns to lease space for point of presence facilities. Permit applications submitted to VDOT for underground work in Luray, Stanley and Springfield. | 90 | Variance: Lease negotiations began with tower owners and draft contracts submitted. Permitting was completed with VMRC for two water crossings and the railroad companies for two crossings. | 0 | N/A | 10 | Variance: Purchase of equipment and construction materials was on hold pending final design completion and approval. Final procurement will begin with design approval by the PCBA in July 2012. | 1 | Variance: The network build was on hold pending final design completion and approval. Only the facility in Luray has been constructed (facility only, no equipment). Network build is scheduled to begin in August, 2012. | 0 | Purchase of equipment and construction materials was on hold pending final design completion and approval. Equipment will be deployed once the environmental assessment amendment and final design are complete. | 0 | Variance: The network build was on hold pending NTIA and NOAA Grants Office approval of a project modification, approved January 2012 and subsequent final design completion and approval. The approved Project Modification estimates construction of the network to begin following final design review and NTP starting in August 2012 and network testing to follow construction of the network. | 2012-08-20 08:57 | 2012-08-20 08:57 | 7393 | 7393 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2012 | Q3 | Q3 - 2012 | 8135 | 6776 | TRUE | 17 | Variance due to project modification. High make ready estimate from incumbent electric cooperative forcing redesign to reduce fiber deployment and move to microwave connectivity and to move some areas of construction from aerial to underground. Project modification approval in January 2012 by NTIA and NOAA Grants Office and work restarted to implement the project. | 0 |  | N/A | 100 | No Variance: Project modification required re-consultation for National Environmental Protection Act (NEPA) and National Historic Preservation Act (NHPA) review and development of a supplemental environmental assessment (EA). No adverse effect determinations from all agencies and supplemental EA submission approved by NTIA and the NOAA Grants Office in April 2012. | 100 | No Variance. | 95 | Variance: Execution of agreement with incumbent electric cooperative underway based on project modification approval by NTIA and NOAA Grants Office in January 2012. Have completed negotiations with Towns to lease space for point of presence facilities. Permit applications submitted to VDOT for underground work in Luray, Stanley and Springfield. | 90 | Variance: Lease negotiations signed with tower owners. Permitting was completed with VMRC for two water crossings and the railroad companies for two crossings. | 0 | N/A | 10 | Variance: Purchase of equipment and construction materials is currently underway following approval of design segments in July 2012. Final procurement of equipment and materials expected in Q4-2012. | 1 | Variance: The network build was on hold pending final design completion and approval. Only the facility in Luray has been constructed (facility only, no equipment). Network build began on September 27, 2012. | 5 | Purchase of equipment and construction materials is underway following approval of design in July 2012. Equipment deployment/network build began on September 27, 2012. | 0 | Variance: The network build was on hold pending NTIA and NOAA Grants Office approval of a project modification, approved January 2012 and subsequent final design completion and approval. Following approval of project modification and issuance of a notice to proceed in July 2012, equipment deployment began on September 27, 2012; network testing to follow construction of the network in Q4-2012. | 2012-11-29 11:33 | 2012-11-29 11:33 | 7393 | 7393 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2012 | Q4 | Q4 - 2012 | 9145 | 7962 | TRUE | 45 | Variance due to project modification. High make ready estimate from incumbent electric cooperative forcing redesign to reduce fiber deployment and move to microwave connectivity and to move some areas of construction from aerial to underground. Project modification approval in January 2012 by NTIA and NOAA Grants Office and work restarted to implement the project. | 0 | N/A | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 95 | The PCBA is awaiting final third party review of network testing results. | 2013-03-25 13:25 | 2013-03-25 13:25 | 7393 | 7393 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2013 | Q1 | Q1 - 2013 | 12153 | 10337 | TRUE | 83 | Variance due to project modification and left over funds. High make ready estimate from incumbent electric cooperative forcing redesign to reduce fiber deployment and move to microwave connectivity and to move some areas of construction from aerial to underground. Project modification approval in January 2012 by NTIA and NOAA Grants Office and work restarted to implement the project. Project was completed on February 28, 2013. | 0 | N/A | N/A | 59 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 45 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 10 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 23 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 100 | No Variance. | 47 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 100 | No Variance. Actuals from project inception through end of the current reporting period are 200% of the budget figures. Activity complete. | 100 | No Variance. Actuals from project inception through end of the current reporting period are 200% of the budget figures. Activity complete. | 45 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 2014-05-01 09:03 | 2014-05-01 09:03 | 7393 | 7393 | Page County Broadband Authority | TRUE
NT10BIX5570055 | 2010 | Q2 | Q2 - 2010 | 76 | 1336 | FALSE | 15 |  | 0 |  |  | 100 |  | 100 |  | 75 |  | 75 |  | 5 |  | 25 |  | 5 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2010 | Q3 | Q3 - 2010 | 265 | 1399 | TRUE | 15 | No Variance | 0 |  | - | 100 | No Variance (Final Draft of EA has been completed and submitted) | 100 | No Variance (Engineering Design has been completed) | 43 | Projecting completion by end of next quarter | 75 | No Variance | 5 | Projecting to begin construction in the next quarter | 25 | No Variance. Procurement process is proceeding on schedule | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2010-10-29 18:18 | 2010-10-29 18:18 | 5554 | 5554 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2010 | Q4 | Q4 - 2010 | 1175 | 2209 | TRUE | 15 | No Variance | 0 |  | No Variance | 100 | No Variance | 100 | No Variance | 50 | 100% of ROW has been completed for the Fiber Optic Backbone, Projecting completion of ROW for laterals and towers by end of next quarter | 100 | No Variance | 10 | No Variance | 50 | No Variance | 0 | The reason for variances from the baseline for the fiber miles deployed is as follows: Delay is due to receipt of fiber orders and compliance with Rural Utility Service (RUS) regulations. The NTUA initiated its procurement process consistent with the terms of the Grant Award, e.g., did not place orders for certain material until after the Environmental Assessment had been completed. Since that time, NTUA staff has been working diligently to complete material and equipment orders to meet the overall project schedule. Further, NTUA has additionally faced the task of having the material installed on RUS-backed infrastructure be approved by RUS. Unfortunately, such approval can only occur after the vendor has been selected and installation specifics are known. In addition to the protracted procurement process, NTUA has also been improving upon its existing materials management plan, working with NTUA Safety department to implement a plan for flaggers, road crossing, etc... The N | 0 | No Variance | 0 | No Variance | 2011-02-16 11:09 | 2011-02-16 11:09 | 5554 | 5554 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2011 | Q1 | Q1 - 2011 | 2189 | 2840 | TRUE | 8 | Reasons for the variance include the following: 1. Delays in make ready. To expedite the make ready work, NTUA will add crews from within NTUA or from contractors. 2. Additional RUS requirements for OPGW construction. To expedite the RUS approval, NTUA has worked with the RUS to complete the first span and created a model for subsequent spans. 3. Delays in obtaining state road crossing permits. To avoid work stoppage and further delays, the NTUA has instructed the contractor to continue with the build out and dead-end the fibers in areas where they have not obtained the permits. 4. Delays in obtaining all materials for fiber optic build out. To expedite the process, NTUA has instructed the vendors to deliver all hardware and cable in a lump sum rather than a phased approach. | 0 |  | No Variance | 90 | The Environmental Assessment was 100% completed and approved however, due to changes in design of the tower locations and fiber optic segments, additional addendums to the EA will have to be submitted for approval. | 95 | The Network Design was fully completed however changes to the original route require further modifications to the original design. | 50 | Right of Way was acquired for the Navajo Nation Trust Lands however extensive right of way is required for the existing Indian Allotments. A total of 15 Allotments exist. To expedite the easement process, NTUA has hired a consultant to approach the land owners directly for consent. Furthermore, if consent can not be acquired in a reasonable and timely manner, NTUA is creating a contingency plan to address the problem including the potential for route changes. If route changes are required, NTUA will follow the requisite steps required by the NTIA. | 50 | Reasons for the variance include obtaining the state road crossing permits. On the New Mexico side, eight permits are remaining. NTUA has submitted all permit applications and are awaiting approval. NTUA anticipates receiving NM permits by June 18, 2011. On the Arizona side, to expedite the process, NTUA has hired T&D Surveyors to finish the profiles. Approval by the Arizona Department of Transportation is projected to occur within 4 weeks after their receipt of the profiles and application. | 25 | No Variance | 75 | No Variance | 8 | Reasons for the variance include the following: 1. Delays in make ready. To expedite the make ready work, NTUA will add crews from within NTUA or from contractors. 2. Additional RUS requirements for OPGW construction. To expedite the RUS approval, NTUA has worked with the RUS to complete the first span and created a model for subsequent spans. 3. Delays in obtaining state road crossing permits. To avoid work stoppage and further delays, the NTUA has instructed the contractor to continue with the build out and dead-end the fibers in areas where they have not obtained the permits. 4. Delays in obtaining all materials for fiber optic build out. To expedite the process, NTUA has instructed the vendors to deliver all hardware and cable in a lump sum rather than a phased approach. | 0 | Variance is due to the following 1. The LTE RFP process. NTUA is scheduled to present to their board of directors the selected LTE vendor at the board meeting in May 2011. 2. Delay in tower build out required to deploy LTE and microwave equipment. NTUA intends to increase staffing for the construction of the tower build out. 3. Delay in electronics deployment required to light the fibers and back-haul the signal to tower locations. NTUA intends to increase staffing for the deployment of the electronics. | 0 | The variance in network testing is due to a delay in overall construction. Although the installed network has not been tested, the fiber optic cables required for the network have been tested prior to delivery and the NTUA tested the loose tube cable after delivery. The OPGW will be tested prior to and after installation by the contractor. A final test will be conducted by the electronics vendor after installation of electronics. | 2011-05-19 16:41 | 2011-05-19 16:41 | 5554 | 5554 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2011 | Q2 | Q2 - 2011 | 2971 | 3243 | TRUE | 14 | Reasons for the variance include: 1. Delays in the overall project are due to subsequent delays in Make Ready production. Make Ready delays were caused due to failure of pole strength calculations on certain segments of NTUA power lines which required additional replacement of poles and reduction of pole spans. Areas in which pole replacement was not feasible, re-design was necessary in order to maintain integrity of the system and adhere to all applicable NESC and RUS codes and regulations. 2. Traversing over Indian Allotments have caused delays in fiber optic build out. NTUA has taken multiple steps to resolve issue including the following: 1. Hiring consultant to obtain Allottee consent 2. Approaching Bureau of Indian Affairs for assistance 3. Engineering an alternate route design | 0 |  | - | 90 | Reasons for variance in the EA are due to changes in the location of towers that are outside the original EA. To start construction on the sites the following steps are required. 1. Further environment and cultural studies and final assessment 2. Acquire approvals from Fish & Wildlife 3. Submit changes to the NTIA for approval Formal environmental and cultural studies are currently under way and NTUA anticipates submitting an action award request for NTIA approval once NTUA obtain final results of the studies and approval from U.S. Fish and wildlife. | 95 | Variance in Network Design is due to the following: 1. Additional network design is required as a contingency plan if Indian allotment negotiations fail. 2. Augmentation of original design to account for change in fiber optic cable placement on electric poles in certain segments to increase production of fiber optic plant construction as well as increase safety for electrical linemen. | 55 | Variance in ROW is a consequence of previous delays in obtaining ROW as well as changes in the Navajo Nation and BIA process for ROW approval. We note that it appears that the issues related to these delays have been resolved. | 55 | Variance in construction permit approvals is due to delays in the submittal process. NTUA has submitted all permit applications required for New Mexico. Furthermore, NTUA hired T&D Contractors to expedite the development of profiles required for permit application in Arizona. NTUA will submit permit applications to the Arizona Department of Transportation in piecemeal fashion as they receive profiles for individual areas from T&D contractors. | 50 | No Variance | 75 | Variance is due to delays in network build | 14 | Reasons for the variance include the following: 1. Discrepancies in OPGW construction approval process from RUS. NTUA has revised and submitted the RUS OPGW Approval Package in accordance with RUS requests. 2. Delay in OPGW construction due to conflict with electrical power loading issues resulting in inability to de-energize the Navajo Agricultural Products Industry (NAPI) farms area of construction. To remedy the issue, NTUA is re-designing the placement of the fiber optic cable to allow for energized work. 3. Delays in Tower RFP process. Tower RFP process has been initiated to remedy this schedule delay. | 0 | Variance is due to the following 1. Delay in finalizing IRU agreements. NTUA is in the final stage of signing the IRU Agreement. 2. Delays in physical network build out. NTUA is developing remedies to increase production of build out. | 0 | Variance in network testing is due overall build out. NTUA can not commence network testing until electronics are delivered. NTUA anticipates delivery of first phase of electronics in September 2011. | 2011-08-09 13:10 | 2011-08-09 13:10 | 5554 | 5554 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2011 | Q3 | Q3 - 2011 | 4353 | 4033 | TRUE | 27 | Reasons for variance from the baseline are as follows: 1. Delays in the overall project are due to subsequent delays in Make Ready production. To alleviate the delay, NTUA has hired additional contractors to assist. 2. Delays in obtaining Rural Utilities Service (RUS) approvals for transmission line work. NTUA in conjunction with their consultants are working directly with RUS to expedite the approval process. 3. Delays in acquiring Indian Allotments approvals and Rights of Way. NTUA has taken a proactive approach to resolving the Indian Allotment issue including the various alternatives such as route change, gigabit laser, and utilizing existing microwave system as a temporary measure until approval is obtained. 4. Weather Delays |  |  | - | 85 | Reasons for the variance in the environmental assessment (EA) are due to changes in the location of towers and additional fiber optic laterals requiring EA. | 90 | Variance in network design is due to the following: 1. Changes in fiber optic lateral locations 2. Additional fiber optic engineering to account for potential alternative route to by-pass Indian Allotment 3. Change in optical ground wire (OPGW) fiber optic design from overbuild to underbuild for safety reasons | 60 | Variance in obtaining Rights of Way (ROW) is due to changes in Navajo Nation ROW process. To alleviate the problem, NTUA ROW agents / Government liaisons are working directly with the Navajo Nation, Bureau of Indian Affairs (BIA), and the Arizona Department of Transportation to expedite the approval process. | 60 | Variance in obtaining construction permits is due to delays in the submittal process. NTUA has submitted all permit applications required for New Mexico. Profiles required for Arizona permits are currently being developed. To expedite the process, NTUA hired T&D Contractors to assist in the development of profiles. T&D is currently working on the crucial, time-sensitive profiles and will submit to NTUA on a piecemeal basis for submission to the Arizona department of transportation. | 75 | No Variance | 80 | Variance is due to delays in construction. All middle mile equipment has been ordered and NTUA has requested delivery of equipment be staged in accordance with the construction schedule. | 22 | Variances in network build are due to the following reasons. 1. Delays in approvals of Indian Allotments. NTUA is actively reviewing permanent and temporary solutions as alternatives to by pass the Indian Allotments until approvals are obtained. 2. Delays in obtaining Rural Utilities Service (RUS) approvals. NTUA's consultants are working directly with the RUS to expedite the approval process. 3. Delays in Make Ready. NTUA has hired contractors to assist with Make Ready. 4. Weather Delays. | 25 | Variance is due to the following: 1. Subsequent delays in construction have caused delays in electronics equipment deployment. NTUA has taken steps to expedite construction. The greatest impediment to construction is make ready and NTUA has hired outside contractors to assist with make ready. 2. Delays in the Microwave Request for Bids (RFP) process has caused further delays in the deployment of Long Term Evolution 4G (LTE) last mile equipment. Revised Microwave RFP is due on October 21, 2011 3. Due to changes in technology, NTUA has decided to wait to order dongles and laptops until July 2012. | 20 | Variance in network testing is due to delays in construction. DBTech has commenced with optical time-domain reflectometer (OTDR) testing on the fiber optic segments that are constructed. | 2011-11-30 16:02 | 2011-11-30 16:02 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2011 | Q4 | Q4 - 2011 | 5285 | 4955 | TRUE | 37 | Reasons for variance from the baseline are as follows: 1. Delays in the overall project are due to delays in Make Ready production. To alleviate the delay, NTUA has hired additional contractors to assist. NTUA anticipates all make ready work completed in the following quarter. 2. Delays in fiber optic construction caused by delays in Make Ready. To increase production, NTUA requested the fiber optic construction contractor to increase crew sizes and increase the work schedule to 7 days per week. NTUA anticipates the additional crews will increase production to meet the obligations of the grant. 3. Delays in acquiring Indian Allotments approvals and Rights of Way. NTUA has taken a proactive approach to resolving the Indian Allotment issue including reviewing various alternatives such as route change, gigabit laser, and utilizing existing microwave system as a temporary measure until approval is obtained. Any alternatives NTUA deploys will be outside the scope of the BTOP grant. |  |  | - | 85 | Reasons for the variance in the environmental assessment (EA) are due to requests for changes in the 2 shelter locations. NTUA shall submit an AAR to address the changes to the NTIA during the following quarter. | 95 | Variance in network design is due to the following: Additional fiber optic engineering to account for relocating two telecommunications shelters that are critical to the NTUA electronics design. NTUA shall submit an AAR to address the changes to the NTIA during the following quarter. | 80 | Variance in obtaining Rights of Way (ROW) stems from previous delays in submittal process as well as changes in Navajo Nation ROW process. NTUA ROW agents / Government liaisons are working directly with the Navajo Nation, Bureau of Indian Affairs (BIA), and the Arizona Department of Transportation to expedite the approval process. | 75 | Variance in obtaining construction permits is due to delays in the submittal process. NTUA has received blanket approval from the State of Arizona Department of Transportation to commence with fiber optic construction on the fiber backbone. NTUA is currently working on the plans and profiles for the obtaining permits for the laterals to the community anchor institutions. NTUA will submit the permit applications for the laterals on a piecemeal basis as the profiles are completed. | 85 | Variance in preparation of all sites is due to changes in the two telecommunications shelter locations. NTUA shall submit an AAR to address the changes to the NTIA during the following quarter. | 85 | Variance is due to delays in construction. All middle mile equipment has been ordered and NTUA has requested delivery of equipment be staged in accordance with the construction schedule. With respect to last mile equipment, NTUA has procured all 4G LTE equipment from ZTE. NTUA is in negotiations to obtain the Netbooks, modems and SIM cards by October 2012. NTUA anticipates procuring the last mile test equipment during the following quarter. | 45 | Variances in network build are due to the following reasons. 1. Delays in approvals of Indian Allotments. NTUA is actively reviewing permanent and temporary solutions as alternatives to by pass the Indian Allotments until approvals are obtained. 2. Delays in Make Ready. NTUA has hired contractors to assist with Make Ready and anticipates all Make Ready work completed during the following quarter. 3. Weather Delays. | 50 | Variance is due to the following: 1. Delays in construction have caused further delays in electronics equipment deployment. NTUA has taken steps to expedite construction. The greatest impediment to construction was make ready however NTUA hired additional help to alleviate the make ready issues. 2. Due to changes in technology, NTUA has decided to wait to order dongles and laptops until July 2012. | 35 | Variance in network testing is due to delays in construction. DBTech has commenced with optical time-domain reflectometer (OTDR) testing on the fiber optic segments that are constructed | 2012-02-27 13:21 | 2012-02-27 13:21 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2012 | Q1 | Q1 - 2012 | 6313 | 5759 | TRUE | 63 | Reasons for variance from the baseline are as follows: Delays in the overall project are due to previous delays in the make ready process, Indian Allotment issues, and ROW. NTUA took proactive steps to alleviate the issues including increasing crew sizes for the fiber optic construction, hiring additional contractors to assist with Make Ready, and hiring a consultant to address the allotment issues. |  |  | - | 90 | Variance in the Environmental Assessment is due to changes in six tower locations. NTUA is in the process of finalizing the documentation to submit to the NTIA for approval including cultural resources compliance forms, biological compliance forms, landuserâ€™s approvals, legal survey, etc... | 100 | No Variance | 85 | Variance in obtaining Rights of Way (ROW) stems from previous delays in submittal process as well as changes in Navajo Nation ROW process. NTUA ROW agents / Government liaisons are working directly with the Navajo Nation, Bureau of Indian Affairs (BIA), and the Arizona Department of Transportation to expedite the approval process. All submittals have been submitted to the various agencies and NTUA is currently waiting for approval | 80 | Variance in obtaining permits is due previous delays. To speed up the process, NTUA is augmenting the ROW team with additional resources from the NTUA Engineering Dept. The Engineering Department is assisting with acquiring the permits for the laterals to the community anchor institutions as well as bringing power to the sites. | 90 | Variance in site preparation is due to changes in tower locations. NTUA is in the process of finalizing the documentation to submit to the NTIA for approval. Once the award action request is submitted and approved, NTUA shall commence with the final site preparation for the six remaining tower sites that require changes. | 90 | Variance is due to delay last mile contract negotiations. All middle mile equipment has procured and staged in accordance with the construction schedule. With respect to last mile equipment, NTUA has procured all 4G LTE equipment and the Netbooks. NTUA is in negotiations to obtain the dongles and SIM cards by October 2012. | 75 | Variance is due to a delay in constructing the six towers that require additional approvals due to site changes as well as delays in obtaining the easement rights to transverse the Indian Allotments. To alleviate the delays, NTUA has hired a consultant to address the allotments. With respect to the six towers changes, NTUA will submit an award action request during the following quarter. | 65 | Variance is due to previous delays in the construction of the fiber optic plant, the tower build out, and delays in finalizing the microwave procurement. NTUA has taken steps to address the delays in construction including hiring additional contractors to assist the NTUA and the microwave procurement contract is complete. NTUA anticipates obtaining all microwave equipment during the first month of the next quarter. | 45 | Variance in network testing is due to delays in construction. DBTech has commenced with optical time-domain reflectometer (OTDR) testing on the fiber optic segments that are constructed | 2012-05-29 10:27 | 2012-05-29 10:27 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2012 | Q2 | Q2 - 2012 | 6863 | 6058 | TRUE | 78 | Variance is due to the Indian Allotment Issues and the change in six tower site locations. NTUA has developed a contingency plan for the allotment issues. Regarding the site locations changes for towers, NTUA has submitted an award action request for three of the six towers. NTUA anticipates submitting an AAR for the remaining three towers that requires an environmental assessment (EA) during the next quarter. |  |  | - | 92 | Variance in the environmental assessment is due to changes in three of the remaining six towers that require construction. NTUA is in the process of completing the EA and anticipates submitting the finalized EA with the tower award action request. The EA will be completed prior to the end of the next quarter. | 100 | No Variance | 90 | Variance is obtaining Rights of Ways (ROW) stems from previous delays. NTUA has received all ROWs for the fiber optic backbone however NTUA continues to work with the various agencies including the Navajo Nation, Bureau of Indian Affairs, and the department of transportation to acquire the easement rights for the laterals to the community anchor institutions and tower locations. NTUA anticipates completion of all ROW issues prior to the end of the next quarter. | 85 | Variance for construction permits is a result of obtaining easements to cross Indian Allotments (IA). In order to energize the system, NTUA is utilizing a temporary solar powered microwave solution to by-pass one of the critical IA. The remaining Indian Allotments for which NTUA requires permission to transverse exist on the last phase of the fiber optic build out. NTUA's government liaison is working with the allottees to resolve the issue. NTUA has also taken the proactive step in developing a contingency plan if negotiations with the allottees fails. | 92 | Variance in site preparation is due to changes in the remaining six tower site locations. Three of the six tower sites have been submitted to NTIA for approval. The remaining three are in the final process of environmental assessment (EA). Once the EA is complete, NTUA will submit the sites for NTIA approval. Once approval is received, NTUA shall commence with the site projects. | 100 | No Variance | 85 | Variance in the network build out is due to the following reasons: 1. Six remaining tower sites require NTIA approval of which 3 require completion of an EA prior to construction. NTUA anticipates completion of environmental assessment for the three tower sites prior to the end of the next quarter. 2. Delays in obtaining easement rights to cross over Indian Allotments caused a deceleration of the fiber optic construction. NTUA has developed a contingency plan to by-pass the Indian Allotments if negotiations fail. | 85 | Variance in deploying equipment is related to the following: 1. Initial delay in microwave (MW) contract. NTUA did finalize the MW contract and is in the process of installing the MW. 2. Delays in finalizing the contract for Last Mile devices. NTUAW has finalized the contract and has received sample devices for testing purposes. The remaining Last Mile devices are currently being manufactured. | 50 | Variance in testing is the result of previous delays in fiber optic and tower construction. NTUA anticipates all testing to be completed prior to the end of the fourth quarter. | 2012-08-06 13:36 | 2012-08-06 13:36 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2012 | Q3 | Q3 - 2012 | 8119 | 6767 | TRUE | 84 | Variance is due to previous changes in site locations and delays in procurement and design. NTUA has taken steps to assure completion of all construction prior to the end of the next quarter. |  |  |  | 100 | No Variance | 100 | No Variance | 95 | Variance is due to delays in the approval process for the following sites: 1. Fort Defiance Chapter House (CAI) 2. Red Lake Tower (lateral to tower) 3.Hole in the Rock Tower (lateral to tower) The Rights of Way packages have been sent to the Navajo Nation. NTUA is anticipating receiving the notice to proceed with construction prior to the end of October. | 100 | No Variance. | 95 | Variance is due to the six remaining towers that NTUA is obligated to build. NTUA is waiting for NTIA approval for the sites prior to commencing with any site prep. NTUA anticipates approval for 3 of the 6 sites during the month of October followed by approval for the remaining in November. | 100 | No Variance | 88 | Variance in the network build is due to the following: 1. Approval for the change in locations for the remaining six towers. 2. Delays in the microwave installation for the towers not built. NTUA shall commence with construction on the aforementioned sites promptly after approval is obtained. | 90 | Variance is deploying equipment is due to the following: 1. Previous delays in finalizing the microwave contract. All microwave equipment will be installed and tested prior to the end of the next quarter. 2. Delays in finalizing the distribution plan for the Last Mile netbooks. NTUA has obtained all the netbooks and anticipates distributing all netbooks prior to the end of the next quarter. | 75 | Variance in testing is the result of previous delays in the middle mile build out. NTUA shall complete with all testing prior to the end of the next quarter. | 2012-11-28 15:51 | 2012-11-28 15:51 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2012 | Q4 | Q4 - 2012 | 8907 | 7691 | TRUE | 89 | NTUA has experienced various circumstances that have caused delays. The most noteworthy of these circumstances are listed below: 1. Weather â€“ Throughout the course of the completing the project, NTUA ran into scheduling delays due to severe weather conditions. The remote nature of the fiber and tower installation within the extremely rural Navajo Nation often dictated caution govern before moving forward in the severe weather conditions. These conditions include: 1) severe wind storms that delayed hanging fiber and installing towers and related equipment; 2) freezing temperatures and snow conditions that makes rural roads impassable for trucks and vehicles necessary to complete the installation of fiber and towers. Additionally, Hurricane Sandy prompted numerous contractor employees to depart the project to either address personal impacts or to seek employment in that urban area. 2. Need for Tower Relocations â€“ As a result of ownership issues related to numerous relatives |  |  |  | 100 | No Variance | 100 | No Variance | 97 | Variance is due to delays in receiving approval to build the power line to Hole in the Rock Tower and the Red Lake Tower. NTUA anticipates recieving approval during the next quarter to build the power lines. | 100 | No Variance | 96 | Variance is due to adverse weather conditions that are preventing NTUA from completing the foundation for Hole in the Rock. Also, NTUA encountered hard rock at the Piney Hill tower which caused delays in the drilling process. | 93 | Variance is due to delays in obtaining switching electronics for the microwave sites and procuring a new tower piece required to complete the Little Water tower installation. NTUA has ordered the remaining piece for Little Water and anticipates delivery in early February 2013. | 92 | Variance in the network build is due to the following: 1. Approval for the change in locations for the remaining six towers. 2. Delays in the microwave installation for the towers not built. NTUA has received approval to build the remaining tower sites and construction is underway. | 92 | Variance is due to delays in receiving the remaining tower section for the Little Water tower site which was damaged. | 80 | Variance is due to delays in tower construction leading to delays in microwave installation and LTE installation. | 2013-02-22 14:34 | 2013-02-22 14:34 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2013 | Q1 | Q1 - 2013 | 9939 | 8513 | TRUE | 97 | NTUA has experienced various circumstances that have caused delays throughout the project. The most significant factor causing delays this quarter is weather. NTUA has faced severe weather conditions throughout the quarter including high winds, adverse snow conditions, and extreme temperatures. The conditions have made rural roads impassable for trucks and heavy machinery required to complete the towers. Furthermore, additional time was required for the rural roads to stabilize once the snow melted due to excessive mud. |  |  |  | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 98 | Variance is due to adverse weather conditions as well as foundation issues at the Piney Hill tower site. The construction company has resolved the foundation issue at Piney Hill and NTUA anticipates completion of all tower sites during the next quarter. | 96 | Variance is due to obtaining additional switching electronics at the microwave hub locations. The additional electronics are slated for delivery and installation during the next quarter. | 95 | Variance is due to the delays in tower construction which have caused delays in microwave installation and LTE 4G installation. | 95 | Variance is due to manufacture delays in shipping the microwave hub electronics. | 95 | Variance in network testing is due to delays in overall network build. | 2013-05-28 15:28 | 2013-05-28 15:28 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2013 | Q2 | Q2 - 2013 | 10511 | 8908 | TRUE | 98 | NTUA has experienced various circumstances that have caused delays throughout the project. The most significant factor causing delays this quarter is weather. NTUA has faced severe weather conditions throughout the quarter including high winds and dust storms. The high winds have made microwave and LTE installations on towers hazardous and additional time consuming safety precautions have been put in place to mitigate any chance of accidents. NTUA is on schedule to complete the project including all construction and associated testing and commissioning prior to the end of the next quarter. |  |  |  | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 98 | Variance is due to previous delays in obtaining additional switching gear for the microwave protection rings and integration of the various electronics components including fiber optics, microwave, and 4G LTE equipment. NTUA has received the additional equipment required and is in the process of installation. | 98 | Variance in network testing is due to delays in overall network build. NTUA anticipates completion of all testing within the next quarter. | 2013-08-07 14:03 | 2013-08-07 14:03 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2013 | Q3 | Q3 - 2013 | 11369 | 9490 | TRUE | 99 | NTUA has experienced various circumstances that have caused delays throughout the project. The most significant factor causing delays this quarter is related to network issues on the last mile side. The contractor related to the network issues has sent a team of specialist to resolve the problem and NTUA is on schedule to complete the project including all construction and associated testing and commissioning prior to the end of the next quarter. |  |  |  | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 99 | Variance is due to obtaining some additional equipment to install LTE antennas at the two remaining LTE sites. NTUA is on schedule to finish the remaining install and testing prior to the end of the next quarter. | 99 | Variance in network testing is due to delays in overall network build. | 2013-11-25 10:46 | 2013-11-25 10:46 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2013 | Q4 | Q4 - 2013 | 12651 | 10935 | TRUE | 100 | No Variance | 100 |  | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2015-01-29 11:43 | 2015-01-29 11:43 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570056 | 2010 | Q3 | Q3 - 2010 | 455 | 1494 | TRUE | 0 | N/A | 0 |  | N/A | 100 | N/A Received categorical exclusion. | 0 | In the process of submitting a request for tower/route change. | 0 | In the process of submitting a request for tower/route change. | 0 | In the process of submitting a request for tower/route change. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-30 15:38 | 2010-11-30 15:38 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | 2010 | Q4 | Q4 - 2010 | 1097 | 2138 | TRUE | 35 | Awaiting approval for tower/route change and winter weather delays. | 30 |  | Outreach to local libraries and responses to Idaho library RFP. | 100 | N/A | 100 | N/A | 35 | Awaiting approval for tower/route change and winter weather delays. | 0 | Awaiting approval for tower/route change and winter weather delays. (Decided to wait and submit all tower sites at one time for permits and approvals.) | 0 | Awaiting approval for tower/route change and winter weather delays. | 0 | N/A | 0 | Awaiting approval for tower/route change and winter weather delays. | 0 | Awaiting approval for tower/route change and winter weather delays. | 0 | N/A | 2011-02-11 17:07 | 2011-02-11 17:07 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | 2011 | Q1 | Q1 - 2011 | 1875 | 2683 | TRUE | 1 | Previous quarter mis-calculated | 35 |  | Outreach to local libraries and responses to Idaho library RFP | 100 | N/A | 100 | N/A | 35 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 2011-05-02 22:58 | 2011-05-02 22:58 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | 2011 | Q2 | Q2 - 2011 | 3101 | 3308 | TRUE | 1 | Asset sale in process | 35 |  | Outreach to local libraries and responses to Idaho library RFP | 100 | N/A | 100 | No Variance from Baseline | 35 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-08-15 21:55 | 2011-08-15 21:55 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | 2011 | Q3 | Q3 - 2011 | 3565 | 3557 | TRUE | 1 | Asset sale in process | 35 |  | Outreach to local libraries and responses to Idaho library RFP | 100 | N/A | 100 | N/A | 35 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 2011-10-28 00:54 | 2011-10-28 00:54 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | 2011 | Q4 | Q4 - 2011 | 5329 | 5002 | TRUE | 1 | Project on hold pending review of progress. | 35 |  | Outreach to local libraries and responses to Idaho library RFP | 100 | N/A | 100 | N/A | 35 | Project on hold pending review of progress. | 0 | Project on hold pending review of progress. | 0 | Project on hold pending review of progress. | 0 | N/A | 0 | Project on hold pending review of progress. | 0 | Project on hold pending review of progress. | 0 | N/A | 2012-02-28 08:50 | 2012-02-28 08:50 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | 2012 | Q1 | Q1 - 2012 | 5711 | 5453 | TRUE | 1 | Project Terminated | 35 |  | Outreach to local libraries and responses to Idaho Library RFP | 100 | N/A | 100 | N/A | 35 | Project Terminated | 0 | Project Terminated | 0 | Project Terminated | 0 | N/A | 0 | Project Terminated | 0 | Project Terminated | 0 | Project Terminated | 2012-04-29 21:49 | 2012-04-29 21:49 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2010 | Q3 | Q3 - 2010 | 457 | 1495 | TRUE | 0 | N/A | 0 |  | N/A | 100 | N/A Received categorical exclusion. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-30 15:56 | 2010-11-30 15:56 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2010 | Q4 | Q4 - 2010 | 1113 | 2152 | TRUE | 30 | Network design is 70% complete. | 30 | Library outreach | Local libraries have been contacted, RFPs completed. | 100 | N/A | 70 | Tower site selection, backhaul design, and coverage plans have been completed. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 20 | Components needed have been identified by site. | 20 | Construction vendors have been interviewed. | 0 | N/A | 2011-02-11 18:03 | 2011-02-11 18:03 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2011 | Q1 | Q1 - 2011 | 1877 | 2684 | TRUE | 1 | Previous quarter mis-calculated | 30 |  | Local Libraries have been contacted, RFPs completed | 100 | N/A | 70 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 2011-05-02 23:01 | 2011-05-02 23:01 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2011 | Q2 | Q2 - 2011 | 3269 | 3397 | TRUE | 2 | Asset sale in process | 35 |  | Outreach to local libraries and responses to Idaho library RFP | 100 | N/A | 100 | No Variance from Baseline | 35 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-08-23 00:10 | 2011-08-23 00:10 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2011 | Q3 | Q3 - 2011 | 4319 | 4010 | TRUE | 1 | Asset sale in process | 35 |  | Outreach to local libraries and responses to Idaho library RFP | 100 | N/A | 100 | N/A | 35 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 2011-11-29 15:20 | 2011-11-29 15:20 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2011 | Q4 | Q4 - 2011 | 5331 | 5004 | TRUE | 1 | Project on hold pending progress review. | 35 |  | Outreach to local libraries and responses to Idaho library RFP | 100 | N/A | 100 | N/A | 35 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | N/A | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | N/A | 2012-02-28 08:58 | 2012-02-28 08:58 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2012 | Q1 | Q1 - 2012 | 5713 | 5454 | TRUE | 1 | Project Terminated | 35 |  | Outreach to local libraries and responses to Idaho Library RFP | 100 | N/A | 100 | N/A | 35 | Project Terminated | 0 | Project Terminated | 0 | Project Terminated | 0 | N/A | 0 | Project Terminated | 0 | Project Terminated | 0 | Project Terminated | 2012-04-29 21:51 | 2012-04-29 21:51 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570058 | 2010 | Q3 | Q3 - 2010 | 373 | 1453 | TRUE | 9 | Projection was estimate of project time line. Engineering and especially drafting of construction documents have created delays in overal project. | 0 | None | N/A | 0 | N/A | 100 | No Variance from baseline | 100 | No Variance from baseline | 100 | No Variance from baseline | 0 | N/A | 0 | No Variance from baseline | 0 | No Variance from baseline | 0 | No Variance from baseline | 0 | No Variance from baseline | 2010-11-22 12:33 | 2010-11-22 12:33 | 5557 | 5557 | City of Williamstown | TRUE
NT10BIX5570058 | 2010 | Q4 | Q4 - 2010 | 1283 | 2309 | TRUE | 20 | Projection was estimate of project time line. Previous engineering, contract draft delays, and winter weather have created delays in overall project. Project is expected to proceed quickly, meeting projections as spring weather arrives. | 0 |  | No Variance from Baseline | 0 | N/A | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 0 | N/A | 60 | Projection was estimate of project time line. Previous engineering and contract draft delays effected delays in bidding, resulting in variance in this item from baseline. This item should agree with baseline in next quarter report. | 18 | Projection was estimate of project time line. Previous engineering and contract draft delays effected delays in bidding, resulting in variance in this item from baseline. This item will be closer to agreeing with baseline in next quarter report. | 15 | We are slightly ahead of baseline projections for this item. | 0 | No Variance from Baseline | 2011-02-22 11:30 | 2011-02-22 11:30 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2011 | Q1 | Q1 - 2011 | 1963 | 2727 | TRUE | 55 | Contractor has not yet invoiced us for work done. |  |  |  | 0 | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 0 | N/A | 71 | Some of the electronics are back-ordered and we have not been invoiced for everything yet. | 80 | Ahead of baseline due to contractors abilities and few obstacles. | 50 | No variance from baseline | 0 | No variance from baseline | 2011-05-12 11:48 | 2011-05-12 11:54 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2011 | Q2 | Q2 - 2011 | 3345 | 3436 | TRUE | 76 | Have not received all invoices | 0 |  | No variation from baseline. | 0 | n/a | 100 | no variation from baseline | 100 | no variation from baseline | 100 | no variation from baseline | 0 | n/a | 75 | Waiting on final invoices and a couple pieces of equipment | 99 | Still awaiting invoices | 75 | Contractor has only invoiced once since beginning of project | 0 | began testing; Contractor has not invoiced for testing | 2011-08-29 11:47 | 2011-08-29 11:47 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2011 | Q3 | Q3 - 2011 | 3989 | 3833 | TRUE | 76 | Have not received/processed all invoices by end of reporting period. | 100 |  | Ahead of baseline, all equipment for customer registration/installs are purchased and paid for. We are still installing customers. | 0 | N/A | 100 | No variation from baseline | 100 | No variation from baseline | 100 | No variation from baseline | 0 | N/A | 99 | Have not received/processed all invoices by end of reporting period. | 100 | No variation from baseline | 100 | No variation from baseline | 100 | No variation from baseline | 2011-11-11 12:05 | 2011-11-11 12:05 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2011 | Q4 | Q4 - 2011 | 5411 | 5096 | TRUE | 88 | We have not made the final draw downs for the equipment. | 100 |  | Slightly ahead of baseline for customer registration and installation, installed 66 by the end of quarter. | 0 | N/A | 100 | No variation from baseline. | 100 | No variation from baseline. | 100 | No variation from baseline. | 0 | N/A | 99 | Have not made final draw down for equipment. | 100 | No variation from baseline. | 100 | No variation from baseline. | 100 | No variation from baseline. | 2012-02-29 15:35 | 2012-02-29 15:35 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2012 | Q1 | Q1 - 2012 | 6103 | 5654 | TRUE | 88 | We have not made final draw down for equipment. | 83 |  | Had 86 customers of the 103 in baseline at the end of reporting period, We believe the economy has something to do with the lower number. Also in the last quarters progress report we incorrectly reported 100 % based on being ahead of baseline as far as number of subscribers installed. which we are now only at 83% of expenditures and number of subscribers. | 0 | N/A | 100 | No variation from baseline. | 100 | No variation from baseline. | 100 | No variation from baseline. | 0 | N/A | 99 | Have not made final draw down for equipment. | 100 | No variation from baseline. | 100 | No variation from baseline. | 100 | No variation from baseline. | 2012-05-15 15:09 | 2012-05-15 15:09 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2012 | Q2 | Q2 - 2012 | 6987 | 6121 | TRUE | 88 | We have not made final draw down for equipment. | 83 |  | We still are at 86 subscribers and at 83 percent of expenditures. Plus we feel it has to do with a poor economy and this being a very rural community. | 0 | N/A | 100 | No variation from baseline. | 100 | No variation from baseline. | 100 | No variation from baseline. | 0 | N/A | 99 | Have not made final draw down for equipment. | 100 | No variation from baseline. | 100 | No variation from baseline. | 100 | No variation from baseline. | 2012-08-09 17:28 | 2012-08-09 17:28 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2012 | Q3 | Q3 - 2012 | 7783 | 6593 | TRUE | 100 | Project Complete, All draw downs have been made. | 100 |  | Project Complete, All draw downs have been made. | 0 | N/A | 100 | No Variation from baseline. | 100 | No Variation from baseline. | 100 | No Variation from baseline. | 0 | N/A | 100 | No Variation from baseline. | 100 | No Variation from baseline. | 100 | No Variation from baseline. | 100 | No Variation from baseline. | 2012-11-07 13:26 | 2012-11-07 13:26 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570059 | 2010 | Q3 | Q3 - 2010 | 423 | 1478 | TRUE | 1 | Pend Oreille dedicated considerable resources to the completion of the Environmental Assessment (EA) earlier in the quarter. However, delay in the construction process caused by the EA preparation and subsequent waiting for the FONSI has created a situation where several milestones have not been met, since project implementation can not be initiated without EA approval. | 1 | Sales Tax | The basis for this percent mirrors 2a. and therefore the same narrative in 2a. applies. | 90 | N/A | 15 | See narrative in 2a. above. | 0 | See narrative in 2a. above. | 0 | See narrative in 2a. above. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-24 15:09 | 2010-11-24 15:09 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2010 | Q4 | Q4 - 2010 | 981 | 2025 | TRUE | 2 | Our project milestone for this category is approximately on schedule based on expenditures and milestone categories below. | 0 | N/A | No variance. | 99 | Although Finding of No Significant Impact was anticipated by quarter end, it was received the first week of the following quarter. | 80 | No variance. | 40 | No variance. | 70 | No variance. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 2011-02-04 15:49 | 2011-02-04 15:49 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2011 | Q1 | Q1 - 2011 | 2159 | 2825 | TRUE | 9 | Baseline12-Total expenditures toward the project currently lag anticipated projections, but we are confident in our substantially complete by end of year. | 0 | sales tax | 12-Sales tax will be incorporated into the reporting and categorized as materials and construction expenses are incurred. | 98 | 100-Environmental process is complete. | 20 | 80-Expenditures are falling significantly short of projected expenses in this category. | 78 | 60-Substantially complete. | 19 | 95- Permitting lags Baseline projections slightly and will be made up over the course of this calendar year. | 15 | 20-Site preparation does lag planned expenditures due to seasonably cooler and wetter winter and thus a more difficult time to be in the field prepping. | 7 | 40-Equipment originally forecasted via the Baseline should not have been budgeted this early in the project timeline. Requests and processes are in place for bidding and ordering over the second and third quarters of 2011. | 7 | 5-Expenditures towards the Network Build have slightly exceeded the plan. No concerns or issues as the effect is minimal. | 0 | 0-No variance. | 0 | 0-No variance. | 2011-05-19 09:44 | 2011-05-19 09:44 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2011 | Q2 | Q2 - 2011 | 2931 | 3223 | TRUE | 12 | Baseline 35-Early Baseline projections had indicated an earlier start to construction of the project. Based on a longer time frame for Environmental and Network Design, the project is lagging an aggressive Baseline projection for overall project completion. It is anticipated that variances will continue for the remaining year 2011, with the potential to catch up early in 2012. | 0 |  | 35-Sales tax will be incorporated into the reporting and categorized as materials and construction expenses are incurred. | 98 | 100- Environmental process is complete. | 40 | 80-Final stages of the network design are in progress. Expenditures in this category will fall significantly below those projected. | 80 | 80-No Variance. | 40 | 95-Permitting is progressing although lagging an early projection for this Baseline milestone. Anticipation that this milestone will catch up by end of year 2011. | 40 | 40-No variance. | 7 | 80-Equipment purchases originally called out for in our Baseline projections will not need to be purchased this soon in the project timeline. | 7 | 35-An aggressive Baseline projection in this category over the previous quarter has caused us to fall behind. We continue to believe that the project is on track for completion as outlined in our Baseline projections. | 7 | 10-This milestone lags and will follow Equipment Procurement as far as milestones are concerned. Transport and Switching equipment will be the first ordered for delivery yet by the end of 2011. | 0 | 0-No variance. | 2011-08-05 12:39 | 2011-08-05 12:39 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2011 | Q3 | Q3 - 2011 | 4061 | 3874 | TRUE | 20 | Baseline 49-LQ actual 12-Original Baseline projections had indicated an earlier start to construction of the project. Based on a longer time frame for Environmental and Network Design, the project is lagging an aggressive Baseline projection for overall project completion. It is anticipated that variances will continue until early 2012 when the projection is met. | 0 |  | 49-Sales tax will be allocated here at a point down the line. | 100 | 100-98- No Variance. | 50 | 80-40-Network design is substantially complete and will not expend the full amount of the budget for this metric. | 85 | 80-80-Exceeding Baseline projections. | 70 | 95-40-Permitting continues to lag earlier projections. This metric will be met in the second half of 2012. Permitting will continue into the final year of the project which was not originally planned. | 60 | 60-40-No Variance. | 7 | 80-7-Equipment will be purchased going into next year (2012) for installation in the same year. This was originally projected to be purchased early on in the project. Planning is currently taking place for completion during the final project year. | 20 | 49-7-Aerial and Make Ready work continue at a strong pace with material supplies not affecting this project so far. Additional crews have been added and will continue to be monitored for successful completion. | 7 | 25-7-Equipment originally forecasted to be put in service will not be required until 2012. This metric will be attained during the final year of the project. | 0 | 15-0-Network testing will occur once equipment is connected to the network and services are turned up. Attaining this metric will occur sometime during the final phase of the project. | 2011-11-16 11:51 | 2011-11-16 11:51 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2011 | Q4 | Q4 - 2011 | 4641 | 4286 | TRUE | 29 | Baseline-62-LQ Actual 20-Original Baseline projections indicated an earlier start to construction of the project. Based on a longer time froma e for Environmental and Network Design, the project is lagging an aggressive Baseline projection for overall project completion. It is anticipated that variances will continue until early 2012 when the projection is met. | 1 | Sales Tax | 62-0 Sales tax has started to be implemented and tracked separately. | 100 | 100-100-No Variance. | 55 | 80-50-Network Design is substantially complete and will not expend the full amount of the budget. | 90 | 80-85-Exceeding Baseline. | 80 | 95-70-Permitting continues to lag earlier projections. This metric will be met in the second half of 2012. Permitting will continue into the final year of the project which was not originally forecasted. | 70 | 60-60-Exceeding Baseline. | 10 | 80-7- Equipment will be purchased going into next year (2012) for installation in the same year. This was originally projected to be purchased early on in the project. Planning is currently taking place for completion during the final project year. | 30 | 62-20 Aerial and Make Ready work continue at a strong pace with material supplies not affecting this project so far. Additional crews have been added and will continue to be monitored for successful completion. | 10 | 40-7 Equipment originally forecasted to be put in service will not be required until 2012. This metric will be attained during the final year of the project. | 0 | 25-0-Network testing will commence once equipment has been installed and connected to the network. | 2012-01-30 11:54 | 2012-01-30 11:54 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2012 | Q1 | Q1 - 2012 | 6113 | 5659 | TRUE | 35 | LQ Actual 29- Baseline 69- As measured by dollars spent, the most expensive part of the project by design is to be completed in the last three quarters of 2012. | 1 |  | 1-69 Sales tax has been broken out and will continue to be tracked separately. | 100 | 100-100 No Variance. | 70 | 55-90 Network design is substantially complete as we enter the final phase, underground construction, for the project. | 95 | 90-90 Exceeding Baseline. | 90 | 80-95 Permitting continues to lag however is close to being completed for the project. | 85 | 70-60 Exceeding Baseline. | 10 | 10-90 Equipment specifications and requirements are currently being reviewed and purchase is anticipated in quarter two and three of this year. | 45 | 30-69 Progress continues at a strong pace with aerial portions of the build. Underground will begin in quarter two of this year. Completion is scheduled for the end of 2012. | 10 | 10-50 Equipment originally planned for the project will not be required until mid to late 2012. As a result, this metric will continue to lag until early 2013. | 0 | 0-30 Network testing will commence once equipment is installed and connected to the network. | 2012-05-15 17:16 | 2012-05-15 17:16 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2012 | Q2 | Q2 - 2012 | 6833 | 6043 | TRUE | 49 | LQ35-BL87 Expenditures have started increasing as we are now in the underground phase of construction, and the most expensive. Expectations are to meet the desired Baseline in the first quarter of 2013. | 1 |  | 1-87 Sales tax has been broken out and will continue to be tracked separately. | 100 | No Variance. | 90 | 70-90 Meeting Baseline. | 98 | 95-90 Exceeding Baseline. | 95 | 90-95 Meeting Baseline. | 90 | 85-80 Exceeding Baseline. | 40 | 10-90 Equipment procurement is currently in process with specifications determined, vendors selected, and orders placed. It is anticipated that we will meet this metric in Q1 2013. | 70 | 45-87 Although currently lagging as compared to Baseline projections, the network build is progressing according to our revised schedule and anticipated to reach the Baseline metric in the first quarter of 2013. Additional crews are added as deemed necessary to insure an on time completion. | 15 | 10-60 Equipment will be placed during the last half of 2012 and during the final quarter of the project. This metric will be attained in the first quarter of 2013. | 0 | 0-40 Testing will commence once equipment has been installed and connected to the network. This metric should attain Baseline projections in the fourth quarter of 2012. | 2012-08-02 10:30 | 2012-08-02 10:30 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2012 | Q3 | Q3 - 2012 | 8057 | 6735 | TRUE | 65 | LQ-49 BL-94 Expenditures have started increasing as we are well into the underground phase of construction, and the most expensive. Expectations are to meet the desired Baseline in the first quarter of 2013. | 1 |  | 1-94 | 100 | 100-100 No Variance. | 100 | 90-90 Exceeding Baseline. | 100 | 98-90 Exceeding Baseline. | 98 | 95-95 Exceeding Baseline. | 95 | 90-90 Exceeding Baseline. | 40 | 40-90 Equipment procurement is currently in process as purchases are pending with shipments arriving now and also planned for next quarter. This metric will be met in Q1 2013. | 78 | 70-94 With a revised number of miles to be built at 585, this metric will be attained in Q1 2013. | 35 | 15-70 Meeting Baseline. | 30 | 0-60 Exceeding Baseline. | 2012-11-26 17:52 | 2012-11-26 17:52 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2012 | Q4 | Q4 - 2012 | 8773 | 7567 | TRUE | 90 | LQ-65 BL-97 Expenditures through 2012 are not meeting Baseline projections as the Network Build is not as far as originally anticipated during the planning phase. Final project completion is anticipated during Q2 2013. | 1 | Sales Tax | 1-97 Sales tax has not been broken out as originally planned, but has been included in the above metrics where tax has been assessed. | 100 | 100-100 No Variance. | 100 | 100-100 No Variance. | 100 | 100-90 No Variance. | 99 | 98-100 Although this metric is very near completion we are still awaiting some final permits for the underground phase. | 98 | 95-100 Minimal Site Preparation remains for the final miles to be constructed. This consists of primarily drops and some underground middle mile sections. | 91 | 40-95 Much of the equipment has been procured at this time. Smaller amounts of expenditures may take place during the final quarter of the project. | 85 | 78-97 The network build has been slowed by weather but will commence again at full production as soon as conditions allow. This metric will near completion in Q2 2013. | 65 | 35-80 Equipment deployment will occur in sequence with the final network construction phase as most of it has now been received. | 40 | 30-80 Final testing will occur as equipment is installed and fiber lit. This metric will be met in the final quarter of the project timeline. | 2013-02-14 10:33 | 2013-02-14 10:33 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2013 | Q1 | Q1 - 2013 | 9841 | 8457 | TRUE | 95 | LQ-90 BL 100 With the project extension approved until September of 2013, Pend Oreille will be able to complete the necessary | 1 |  | LQ-1 BL-100 Sales tax has not been broken out as originally planned, but has been included in the above metrics where tax has been assessed. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 98 | LQ-98 BL-100 With the delay in construction and the No Cost Extension granted, some additional work will be necessary for preparation of sites prior to construction. | 95 | LQ-91 BL-100 Much of the equipment has been procured at this time. Smaller amounts of expenditures may take place during the final quarter of the project. | 95 | LQ-85 BL-100 The network build has been slowed by weather but will commence again at full production as soon as conditions allow. This metric will near completion in Q2 2013, with minimal activity remaining in Q3. | 90 | LQ-65 BL-100 Equipment deployment will occur in sequence with the final network construction phase as the majority has now been received. Final equipment deployment will take place in the third quarter of 2013. | 45 | LQ-40 BL-100 Final testing will occur as equipment is installed and fiber lit. This metric will be met in the final quarter of the project timeline. With the approved No Cost Extension this will be occurring in the third quarter of 2013. | 2013-05-21 10:02 | 2013-05-21 10:02 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2013 | Q2 | Q2 - 2013 | 10763 | 9047 | TRUE | 99 | Although all Federal Funds have been expended for the project and the overall budget will be exceeded, Pend Oreille Public Utility District will cover the overrun with all the necessary funding to complete the project. | 0 | N/A | With the approval of the revised budget this quarter, this metric was removed. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 99 | LQ-98 BL-100 Minimal Site Preparation remains as only lateral drops are being completed and fiber is being blown in to existing ducts. | 98 | LQ-95 BL-100 The majority of equipment has been purchased and ready for final installation. Minimal remaining purchases are being made at this timeframe in the project. | 95 | LQ-90 BL-100 Only remaining lateral drops and underground fiber is remaining to be blown into existing duct work. | 95 | LQ-90 BL-100 With minimal construction remaining, any additional equipment is scheduled to be installed in conjunction with the Network Build. | 65 | LQ-45 BL-100 All Network Testing will be completed as the project closes out and all construction is completed. The project extension has allowed any testing to be completed in the third quarter of 2013. | 2013-08-27 14:21 | 2013-08-27 14:21 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2013 | Q3 | Q3 - 2013 | 12079 | 10241 | TRUE | 100 | Project is Completed. | 100 | N/A | This metric was removed as a result of the revised budget. | 100 | Project is Completed. | 100 | Project is Completed. | 100 | Project is Completed. | 100 | Project is Completed. | 100 | Project is Completed. | 100 | Project is Completed. | 100 | Project is Completed. | 100 | Project is Completed. | 100 | Project is Completed. | 2014-04-25 16:49 | 2014-04-25 16:49 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570060 | 2010 | Q3 | Q3 - 2010 | 323 | 1428 | TRUE | 5 | - | 0 |  | N/A | 100 | Completed and submitted | 100 | - | 0 | N/A | 100 | - | 0 | - | 0 | - | 0 | - | 0 | - | 0 | - | 2010-11-16 10:29 | 2010-11-16 10:29 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2010 | Q4 | Q4 - 2010 | 1215 | 2247 | TRUE | 10 | - | 0 |  | N/A | 100 | Completed and submitted | 100 | - | 0 | N/A | 100 | - | 0 | Project was significantly delayed while waiting for FONSI approval | 0 | Project was significantly delayed while waiting for FONSI approval | 0 | - | 0 | - | 0 | Project was significantly delayed while waiting for FONSI approval | 2011-02-18 11:18 | 2011-02-18 11:18 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2011 | Q1 | Q1 - 2011 | 2011 | 2751 | TRUE | 13 | - | 0 |  | N/A | 100 | Completed and submitted | 100 | - | 0 | N/A | 100 | - | 23 | - | 3 | The RFP and contracting process has taken longer than anticipated but currently 30% is under contract. Actual procurement will lag behind baseline projected procurement for 2 quarters. Pine Telephone Company was able to lock in project pricing but will have the equipment shipped as need for many of the high dollar components. This will reduce the up front payments but still insure best pricing. Pine has completed the RFP & Contracting process items with long lead times and necessary to get started. | 0 | The FONSI, RFP and contracting process has taken longer than anticipated. Equipment will be arriving in Q2 of 2011 and will immediately be installed at sites. Pine Telephone plans to be back on baseline schedule by Q3 of 2011 and move ahead of schedule in Q4 of 2011. The FONSI process significantly delayed the project as compared to the front of the baseline projections but this also means there will be no delays in the middle of the project because of site acquisition, historical or environmental issues which will actually make the total project complete earlier than projected. | 0 | The FONSI, RFP and contracting process has taken longer than anticipated. Equipment will be arriving in Q2 of 2011 and will immediately be installed at sites. Pine plans to be back on baseline schedule by Q3 of 2011 and move ahead of schedule in Q4 of 2011. The FONSI process significantly delayed the project as compared to the front of the baseline projections but this also means there will be no delays in the middle of the project because of site acquisition, historical or environmental issues which will actually make the total project complete earlier than projected. | 0 | The FONSI, RFP and contracting process has taken longer than anticipated. Equipment will be arriving in Q2 of 2011 and will immediately be installed at sites. Pine plans to be back on baseline schedule by Q3 of 2011 and move ahead of schedule in Q4 of 2011. The FONSI process significantly delayed the project as compared to the front of the baseline projections but this also means there will be no delays in the middle of the project because of site acquisition, historical or environmental issues which will actually make the total project complete earlier than projected. | 2011-05-13 13:35 | 2011-05-13 13:35 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2011 | Q2 | Q2 - 2011 | 3053 | 3284 | TRUE | 19 | Indicator is based on overall expenditures. | 0 |  | N/A | 100 | Completed and submitted | 100 | - | 0 | N/A | 100 | - | 60 | - | 20 | The RFP and contracting process has taken longer than anticipated but over 80% of the equipment is under contract and being delivered. Actual procurement will lag behind baseline projected procurement for two quarters. Pine Telephone Company was able to lock in project pricing but will have the equipment shipped as need for many of the high dollar components. This will reduce the up front payments but still insure best pricing. Pine has completed the RFP & Contracting process items with long lead times and necessary to get started. | 10 | The FONSI, RFP and contracting process has taken longer than anticipated, but over 80% of the equipment is under contract and being delivered. Pine Telephone plans to move ahead of schedule in Q4 of 2011. The FONSI process significantly delayed the project as compared to the front of the baseline projections but this also means there will be no delays in the middle of the project because of site acquisition, historical or environmental issues which will foster earlier completion of the project than projected. | 0 | The FONSI, RFP and contracting process has taken longer than anticipated, but over 80% of the equipment is under contract and being delivered. Pine Telephone plans to move ahead of schedule in Q4 of 2011. The FONSI process significantly delayed the project as compared to the front of the baseline projections but this also means there will be no delays in the middle of the project because of site acquisition, historical or environmental issues which will foster earlier completion of the project than projected. | 0 | The FONSI, RFP and contracting process has taken longer than anticipated, but over 80% of the equipment is under contract and being delivered. Pine Telephone plans to move ahead of schedule in Q4 of 2011. The FONSI process significantly delayed the project as compared to the front of the baseline projections but this also means there will be no delays in the middle of the project because of site acquisition, historical or environmental issues which will foster earlier completion of the project than projected. | 2011-08-12 15:33 | 2011-08-12 15:33 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2011 | Q3 | Q3 - 2011 | 3953 | 3815 | TRUE | 23 | The number is slightly lower than projected because the broadband access equipment will not be billed until after 10 sites are fully in-service. | 0 |  | N/A | 100 | Completed and submitted | 100 | - | 0 | N/A | 100 | - | 70 | - | 45 | The Request For Proposal (RFP) and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 2012. | 29 | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 2012. | 20 | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 2012. | 15 | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 2012. | 2011-11-10 11:18 | 2011-11-10 11:18 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2011 | Q4 | Q4 - 2011 | 4967 | 4642 | TRUE | 34 | Overall project total is lower than other milestones because broadband access equipment will not be billed until after 10 sites are fully in-service. In other words, overall completion is below predictions because Pine Telephone Company will not pay for the equipment until at least 10 sites are fully complete. | 0 |  | N/A | 100 | Completed and submitted | 100 | - | 0 | N/A | 100 | - | 90 | Continuing progress | 70 | The RFP and contracting process has taken longer than anticipated but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 2012. | 62 | The RFP and contracting process has taken longer than anticipated but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 2012. | 48 | The RFP and contracting process has taken longer than anticipated but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 2012. | 45 | The RFP and contracting process has taken longer than anticipated but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 2012. | 2012-02-13 12:20 | 2012-02-13 12:20 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2012 | Q1 | Q1 - 2012 | 5997 | 5598 | TRUE | 69 | Continuing progress | 0 |  | N/A | 100 | Completed and submitted | 100 | - | 0 | N/A | 100 | - | 95 | Continuing progress | 80 | We have 95% of the equipment contracted, but the equipment cost is currently running under budget. | 95 | Continuing progress | 90 | Continuing progress | 78 | Pine currently has 25 sites live to customers. | 2012-05-09 17:28 | 2012-05-09 17:28 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2012 | Q2 | Q2 - 2012 | 7063 | 6159 | TRUE | 72 | Although monies were expended during the quarter, Pine Telephone Company (PTC) did not complete a draw down during the quarter. | 0 |  | N/A | 100 | Completed and submitted | 100 | - | 0 | N/A | 100 | - | 100 | - | 80 | PTC has 95% of the equipment contracted, but the equipment cost is currently running under budget. | 95 | Continuing progress | 95 | Continuing progress | 90 | Pine currently has 29 sites live to customers | 2012-08-14 16:23 | 2012-08-14 16:23 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2012 | Q3 | Q3 - 2012 | 7837 | 6623 | TRUE | 73 | Monies were expended and drawn down during this quarter. | 0 | 0 | N/A | 100 | Completed and submitted | 100 | - | 0 | N/A | 100 | - | 100 | - | 80 | PTC has 95% of the equipment contracted, but the equipment cost is currently running under budget. | 95 | Continuing progress | 95 | Continuing progress | 90 | Pine currently has 32 sites live to customers | 2012-11-13 09:48 | 2012-11-13 09:48 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2012 | Q4 | Q4 - 2012 | 8439 | 7144 | TRUE | 75 | Monies were expended in this quarter and will be drawn down next quarter. | 0 |  | N/A | 100 | Completed and submitted | 100 | - | 0 | N/A | 100 | - | 100 | - | 80 | PTC has 95% of the equipment contracted, but the equipment cost is currently running under budget. | 95 | Continuing progress | 95 | Continuing progress | 90 | Pine currently has 32 sites live to customers | 2013-01-30 11:57 | 2013-01-30 11:57 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2013 | Q1 | Q1 - 2013 | 9755 | 8412 | TRUE | 86 | Monies were expended in this quarter and will be drawn down next quarter. | 0 |  | N/A | 100 | Completed and submitted | 100 | - | 0 | N/A | 100 | - | 100 | - | 90 | PTC has 95% of the equipment contracted, but the equipment cost is currently running under budget. | 98 | Continuing Progress | 95 | Continuing Progress | 90 | Pine currently has 32 sites live to customers | 2013-05-16 09:33 | 2013-05-16 09:33 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2013 | Q2 | Q2 - 2013 | 12047 | 10206 | TRUE | 100 | Completed | 0 |  | N/A | 100 | Completed and submitted | 100 | - | 0 | N/A | 100 | - | 100 | - | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2014-04-18 13:22 | 2014-04-18 13:22 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570062 | 2010 | Q3 | Q3 - 2010 | 459 | 1496 | TRUE | 0 | N/A | 0 |  | 0 | 100 | N/A Received categorical exclusion. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-11-30 15:58 | 2010-11-30 15:58 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | 2010 | Q4 | Q4 - 2010 | 1107 | 2147 | TRUE | 30 | Network design is 70% complete. | 30 | Library outreach | Local libraries have been contacted, RFPs completed. | 100 | N/A | 70 | Tower site selection, backhaul design, and coverage plans have been completed. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 20 | Components needed have been identified by site. | 20 | Construction vendors have been interviewed. | 0 | N/A | 2011-02-11 17:44 | 2011-02-11 17:44 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | 2011 | Q1 | Q1 - 2011 | 2393 | 2942 | TRUE | 1 | Previous quarter mis-calculated | 30 |  | Local Libraries have been contacted, RFPs completed | 100 | N/A | 70 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 2011-05-30 22:26 | 2011-05-30 22:26 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | 2011 | Q2 | Q2 - 2011 | 3103 | 3309 | TRUE | 1 | Asset sale in process | 35 |  | Outreach to local libraries and responses to Idaho library RFP | 100 | N/A | 100 | No Variance from Baseline | 35 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-08-15 21:57 | 2011-08-15 21:57 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | 2011 | Q3 | Q3 - 2011 | 4321 | 4011 | TRUE | 1 | Asset sale in process | 35 |  | Outreach to local libraries and responses to Idaho library RFP | 100 | N/A | 100 | N/A | 35 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-11-29 15:23 | 2011-11-29 15:23 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | 2011 | Q4 | Q4 - 2011 | 5333 | 5007 | TRUE | 1 | Project on hold pending progress review. | 35 |  | Outreach to local libraries and responses to Idaho library RFP | 100 | N/A | 100 | N/A | 35 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | N/A | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 2012-02-28 09:01 | 2012-02-28 09:01 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | 2012 | Q1 | Q1 - 2012 | 5715 | 5455 | TRUE | 1 | Project Terminated | 0 |  | Outreach to local libraries and responses to Idaho Library RFP | 100 | N/A | 100 | N/A | 35 | Project Terminated | 0 | Project Terminated | 0 | Project Terminated | 0 | N/A | 0 | Project Terminated | 0 | Project Terminated | 0 | Project Terminated | 2012-04-29 21:52 | 2012-04-29 21:52 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570065 | 2010 | Q3 | Q3 - 2010 | 159 | 1346 | TRUE | 2 | No variance | 0 |  | N/A | 15 | No variance | 100 | No variance | 0 | N/A | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2010-10-27 09:05 | 2010-10-27 09:05 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2010 | Q4 | Q4 - 2010 | 1319 | 2344 | TRUE | 0 | No variance. | 0 | N/A | N/A | 0 | No variance. | 0 | No variance. | 0 | N/A | 0 | No variance. | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-02-23 07:27 | 2011-02-23 07:27 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2011 | Q1 | Q1 - 2011 | 1541 | 2488 | TRUE | 0 | The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of each quarter. While there has been progress made on the overall project the percent complete is zero because the first draw down was made against the grant on the last day of the quarter. However, payments to the vendors were not made until the beginning of April, which fell in a different quarter. | 0 |  | N/A | 0 | No variance | 0 | The network has been designed, however, a detailed propagation map will be created by Airspan, the WiMax equipment vendor. This will be utilized for planning purposes as well as by sales representatives who will be assisting customers during the sign-up process. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of each quarter. While there has been progress made in the Network Design category, the percent complete is zero because no dollars have been spent in this category. The detailed propagation maps that will be completed by Airspan will not be completed until a contract is signed. The contract between Airspan and Buggs Island Telephone Cooperative has been negotiated, and it is awaiting ratification by the Buggs Island Telephone Cooperative Board of Directors. Once this contract has been ratified the detailed propagation maps will be created by Airspan. | 0 | N/A | 0 | No variance | 0 | The 35 existing tower locations have been identified and tower negotiations have begun. Buggs Island Telephone Cooperative has contacted the owners of each of the towers and has received standard contracts from many of them for review. This is the first step in site preparation, however, the projections for percent completion on the Baseline Report and here for the Site Preparation category, are based on total dollars spent at the end of each quarter. While there has been progress made in this category the percent complete is zero because no dollars have been spent in this category. | 0 | The WiMax equipment vendor, Airspan, has been selected for this project. The contract between Airspan and Buggs Island Telephone Cooperative has been negotiated and is awaiting ratification by the Buggs Island Telephone Board of Directors. Once this contract has been ratified and order will be placed with Airspan for the WiMax equipment for this project. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of each quarter. While there has been progress made in the Equipment Procurement category, the percent complete is zero because the first draw down was made against the grant on the last day of the quarter. However, payments to the vendors were not made until the beginning of April, which fell in a different quarter. | 0 | No variance | 0 | The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of each quarter. While there has been progress made in the Equipment Deployment category, the percent complete is zero because no dollars have been spent in this category. The contract between Airspan, the WiMax vendor procured for this project, and Buggs Island Telephone Cooperative has been negotiated, and it is awaiting ratification by the Buggs Island Telephone Cooperative Board of Directors. Once this contract has been ratified the an order for equipment will be placed with Airspan for the WiMax equipment for this project. | 0 | The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of each quarter. While there has been progress made in the Network Testing category, the percent complete is zero because the first draw down was made against the grant on the last day of the quarter. However, payments to the vendors were not made until the beginning of April, which fell in a different quarter. The engineering firm procured by Buggs Island Telephone Cooperative is working to write detailed testing procedures throughout equipment deployment to ensure the equipment performs as desired. | 2011-04-27 16:44 | 2011-04-27 16:44 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2011 | Q2 | Q2 - 2011 | 3357 | 3442 | TRUE | 5 | The projections for percent completion on the Baseline Report for each of the categories listed below are based on total dollars spent at the end of each quarter. For the Overall Project percent Completion a weighted average of the total percentages for each of the categories below is computed. While there has been progress made on the overall project the percent complete is less than what was originally projected because there are timing differences between when work has been performed in the categories below and the submission of invoices for payment. | 0 |  | N/A | 100 | No variance | 0 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map that will be ready next quarter. This will be utilized for planning purposes as well as by sales representatives who will be assisting customers during the sign-up process. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of each quarter. While there has been progress made in the Network Design category, the percent complete is zero because no dollars have been spent in this category. | 0 | N/A | 0 | No variance | 0 | The 35 existing tower locations have been identified and tower negotiations have begun. Buggs Island Telephone Cooperative has contacted the owners of each of the towers and has received standard contracts from many of them for review. This is the first step in site preparation, however, the projections for percent completion on the Baseline Report and here for the Site Preparation category, are based on total dollars spent at the end of each quarter. While there has been progress made in this category the percent complete is zero because no dollars have been spent in this category. | 63 | Buggs Island Telephone has sent out the last of the Requests for Proposals to vendors for miscellaneous supplies for this project. The selection of vendors for these supplies will be done next quarter, at which time Equipment Deployment will be 100% complete. | 0 | The network has been designed and 35 existing tower locations have been identified for equipment deployment. However, Buggs Island Telephone Cooperative signed the contract with Airspan, the WiMax equipment vendor procured for this project, this quarter. Buggs Island Telephone Cooperative had anticipated signing the contract last quarter, and therefore had reflected that in the percentage completion anticipated for this quarter. Now that the contract has been signed Buggs Island Telephone Cooperative is awaiting shipment of equipment from Airspan and has contractors ready for equipment deployment when the equpment arrives. It is anticipated that this category will be back on schedule by the end of next quarter. | 1 | Buggs Island Telephone Cooperative signed the contract with Airspan, the WiMax equipment vendor procured for this project, this quarter. Buggs Island Telephone Cooperative had anticipated signing the contract last quarter, and therefore had reflected that in the percentage completion anticipated for this quarter. Now that the contract has been signed Buggs Island Telephone Cooperative is awaiting shipment of equipment from Airspan and has contractors ready for equipment deployment when the equipment arrives. It is anticipated that this category will be back on schedule by the end of next quarter. | 3 | The engineering firm procured by Buggs Island Telephone Cooperative is continuing to write detailed testing procedures throughout equipment deployment to ensure the equipment performs as desired. Buggs Island Telephone Cooperative signed the contract with Airspan, the WiMax equipment vendor procured for this project, this quarter. Buggs Island Telephone Cooperative had anticipated signing the contract last quarter, and therefore had reflected that in the percentage completion anticipated for this quarter. Now that the contract has been signed Buggs Island Telephone Cooperative is awaiting shipment of equipment from Airspan and has contractors ready for equipment deployment when the equipment arrives. It is anticipated that this category will be back on schedule by the end of next quarter. | 2011-08-29 16:26 | 2011-08-29 16:26 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2011 | Q3 | Q3 - 2011 | 4089 | 3888 | TRUE | 28 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance | 22 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map which was anticipated to be complete by the end of this quarter. However, this has not been complete due to the fact that some of the towers are structurally inadequate to hold the WiMax equipment. BIT has submitted a request for approval of the sites identified as alternates, but has not yet received approval through the Environmental Assessment process. As soon as approval for the alternate sites is granted work will continue on the propagation maps. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of the quarter. | 0 | N/A | 0 | At the end of the quarter, tower leases have been secured for approximately one third of the total towers. The permitting process has not yet begun due to the fact that the leases needed to be obtained before we could proceed with permits. Now that the lease process is well underway, the permitting process will begin and be back on track by next quarter. | 48 | At the end of the quarter, tower leases have been secured for approximately one third of the total towers. The site preparation process has begun but it is not where we anticipated because the leases needed to be obtained before we could move forward with site preparation. Now that the lease process is well underway, site preparation will begin to move forward as the build out of the network begins in October, 2011. | 100 | No variance | 28 | At the end of the quarter, tower leases have been secured for approximately one third of the total towers. Network build preparation has been underway and will speed up now that the tower leases are being executed. The build out will begin in October, 2011. | 1 | At the end of the quarter, tower leases have been secured for approximately one third of the total towers. Equipment deployment could not begin until the tower leases had been executed. The build out will begin in October, 2011. | 6 | At the end of the quarter, tower leases have been secured for approximately one third of the total towers. Network testing cannot be completed until equipment has been deployed. The build out will begin in October, 2011. | 2011-11-16 16:15 | 2011-11-18 13:37 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2011 | Q4 | Q4 - 2011 | 5179 | 4843 | TRUE | 54 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance. | 45 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This map has not been complete due to the fact that some of the towers are structurally inadequate to hold the WiMax equipment. BIT submitted a request for approval of the sites identified as alternates, but did not receive approval through the Environmental Assessment process until December 27, 2011. Now that the alternative sites are approved work will continue on the propagation maps. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of the quarter. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 56 | The build-out of the network began in October, 2011. As of 12/1/11 ten (10) of the 35 sites had WiMax equipment installed on the tower. BIT is currently scheduled to have 24 of the 35 towers completed by the end of March, 2012. | 30 | The build-out of the network began in October, 2011. As of 12/1/11 ten (10) of the 35 sites had WiMax equipment installed on the tower. BIT is currently scheduled to have 24 of the 35 towers completed by the end of March, 2012. | 6 | The build-out of the network began in October, 2011. As of 12/1/11 ten (10) of the 35 sites had WiMax equipment installed on the tower, but none of them had been completed. BIT is currently scheduled to have 24 of the 35 towers completed by the end of March, 2012. Network testing will begin once each tower is commissioned. | 2012-02-21 17:34 | 2012-02-21 17:34 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2012 | Q1 | Q1 - 2012 | 5961 | 5580 | TRUE | 73 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance. | 45 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This map has been completed for the portion of the network that has been deployed. These maps will not be complete until the remaining sites are installed at the end of 2012 and will be billed together at that time. Until it is invoiced and paid there will be a variance for this category. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of the quarter. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 75 | Equipment has been installed on 24 of the 35 tower locations. Construction will begin on the remaining 10 sites in quarter three (3) of 2012. | 53 | Equipment has been installed on 24 of the 35 tower locations. Construction will begin on the remaining 10 sites in quarter three (3) of 2012. | 6 | Equipment has been installed on 24 of the 35 tower locations. Network testing has begun on these 24 sites and we anticipate completion of this testing in June of 2012. Construction will begin on the remaining 10 sites in quarter three (3) of 2012 with testing to begin after installation. | 2012-05-08 12:46 | 2012-05-08 12:46 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2012 | Q2 | Q2 - 2012 | 7117 | 6186 | TRUE | 79 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance. | 45 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This map has been completed for the portion of the network that has been deployed. These maps will not be complete until the remaining sites are installed at the end of 2012 and will be billed together at that time. Until it is invoiced and paid there will be a variance for this category. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of the quarter. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 78 | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter three, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter four, 2012 equipment will be installed on the remaining 11 sites. | 76 | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter three, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter four, 2012 equipment will be installed on the remaining 11 sites. | 6 | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter three, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter four, 2012 equipment will be installed on the remaining 11 sites. | 2012-08-17 16:13 | 2012-08-17 16:13 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2012 | Q3 | Q3 - 2012 | 7341 | 6304 | TRUE | 80 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance. | 45 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This map has been completed for the portion of the network that has been deployed. These maps will not be complete until the remaining sites are installed at the end of 2012 and will be billed together at that time. Until it is invoiced and paid there will be a variance for this category. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of the quarter. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 78 | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter four 2012, at which time the 24 site system will be ready for a commercial launch and in quarter one, 2013 equipment will be installed on the remaining 11 sites. | 79 | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter four 2012, at which time the 24 site system will be ready for a commercial launch and in quarter one, 2013 equipment will be installed on the remaining 11 sites. | 6 | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter four 2012, at which time the 24 site system will be ready for a commercial launch and in quarter one, 2013 equipment will be installed on the remaining 11 sites. | 2012-10-23 08:55 | 2012-10-23 08:55 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2012 | Q4 | Q4 - 2012 | 9091 | 7864 | TRUE | 80 | The percent completion reflects the required build-out of 66 & 2/3rds percent plus the installation of the core network. | 0 |  | N/A | 100 | No Variance | 50 | The 700 network is ongoing change due to interference issues. The 3.65 network is virtually completed. | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 78 | Airspan did complete optimization on the network but problems exist with reliability and speeds, so the system is yet to be deemed commercially ready to market. | 79 | 24 of the 35 sites have been deployed, but not yet accepted. | 8 | The 3.65 network is 95% tested and only lacks lab testing. The 700 network is being reconfigured. | 2013-02-28 15:45 | 2013-02-28 15:45 | 5565 | 5565 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2013 | Q1 | Q1 - 2013 | 10069 | 8593 | TRUE | 81 | WiMAX equipment was installed on 24 tower sites and tested. Extreme interference issues with neighboring companies using LTE technology resulted in BIT, in coordination with the grant funding agencies, to abandon the WiMAX system and convert to a compatible LTE system. Due to limited grant funds remaining and if approved by NTIA, the LTE build-out will cover a 5-county service area versus the original plans to cover a 15-county service area. Construction is projected to begin in Q3 of 2013. The project completion date was extended as a result of WiMAX interference and the need for additional time to deploy LTE. Costs to date reflect actual expenses incurred in constructing the WiMAX and 3.65 networks. The 3.65 network, consisting of six towers, is fully operational with testing and commercial launch to be implemented in Q2 of 2013. | 36 |  | The costs included in this category include 1) Admin and Legal, 2) Engineering -Project Management, 3) Project Inspection, 4) Monthly Tower Lease Payments, and 5) Monthly Backhaul Fees. The remaining costs in this category will be expended as the project proceeds over the next 6 to 8 months and these activities are implemented. | 100 | The Environmental Assessment is complete. | 77 | The 700 network is being re-designed due to interference issues. The 3.65 network is complete. The remaining funds will be used to design the LTE build-out in the 5-county service area if approved by NTIA. | 0 | Not Applicable | 100 | All construction permits have been acquired for the project. | 57 | Costs to date reflect structural improvements to tower sites to accommodate the WiMAX equipment that has been installed. | 85 | Costs to date are reflective of the procurement activity which was implemented to purchase WiMAX and 3.65 equipment. The 3.65 network is complete. Due to extreme interference issues, the WiMAX system will be abandoned and a new LTE system will be deployed on towers that cover a 5-county area if approved by NTIA. Funds remaining in this category will be utilized to cover expenses associated with the procurement of LTE equipment. | 0 | Not Applicable | 84 | WiMAX equipment was purchased and installed on 24 of the 35 original tower sites identified to cover a 15-county service area. Due to extreme interference issues associated with the WiMAX equipment and neighboring LTE neighbors, Buggs Island made the decision to abandon the WiMAX system and convert to a LTE system if approved by NTIA. The remaining funds available in this category will be used to purchase and install LTE equipment on tower sites that will cover a 5-county area. The project was reduced in scope due to the limited grant dollars available to fund the conversion. | 14 | Network testing was implemented on the WiMAX and 3.65 network. As noted previously, the WiMAX system will be abandoned and replaced with a LTE system if approved by NTIA. The 3.65 testing resulted in a successfully installed system that can be commercially launched. Additional costs are expected in this category to cover costs associated with the WiMAX and 3.65 testing and upcoming LTE testing once deployed. | 2013-06-21 14:50 | 2013-06-21 14:50 | 7685 | 7685 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2013 | Q2 | Q2 - 2013 | 10783 | 9061 | TRUE | 83 | WiMAX equipment was installed on 24 tower sites and tested. Extreme interference issues with neighboring companies using LTE technology resulted in BIT, pending grant funding agency (NTIA) approval, developing plans to abandon the WiMAX system and converting to a compatible LTE system. Due to limited grant funds remaining, the LTE build-out will cover a 5-county service area versus the original plans to cover a 15-county service area. Construction is projected to begin in Q3-2013. The project completion date was extended as a result of WiMAX interference and the need for additional time to deploy LTE. Costs to date reflect actual expenses incurred in constructing the WiMAX and 3.65 networks. | 72 |  | The costs included in this category include: 1) Admin and Legal, 2) Engineering -Project Management, 3) Project Inspection, 4) Monthly Tower Lease Payments, and 5) Monthly Backhaul Fees. The percentage significantly increased due to past due invoices (held as a result of the grant suspension) to Engineering Associates and current invoices to Southside PDC for Admin, MBC for monthly backhaul fees, and several tower companies for monthly tower lease fees being submitted for grant reimbursement during the Q2 report period. The remaining costs in this category will be expended as the project proceeds and these activities are implemented. | 100 | The Environmental Assessment is complete | 77 | The 700 network is being re-designed due to interference issues. The 3.65 network is complete. The remaining funds will be used to design the LTE build-out in the 5-county service area if approved by NTIA. | 0 | Not Applicable | 100 | All construction permits have been acquired for the project. | 100 | Costs to date reflect structural improvements to tower sites to accommodate the WiMAX equipment that had been installed. The percentage significantly increased due to past due invoices (held as a result of the grant suspension) from MBC for the installation of backhaul, Wagstaff for tower modifications and Crown Castle for site work received during the Q2 reporting period. | 85 | Costs to date are reflective of the procurement activity which was implemented to purchase WiMAX and 3.65 equipment. The 3.65 network is complete. Due to extreme interference issues, the WiMAX system will be abandoned and a new LTE system will be deployed on towers that cover a 5-county area if approved by NTIA. Funds remaining in this category will be utilized to cover expenses associated with the procurement of LTE equipment. | 0 | Not Applicable | 83 | WiMAX equipment was purchased and installed on 24 of the 35 original tower sites identified to cover a 15-county service area. Due to extreme interference issues associated with the WiMAX equipment and neighboring LTE neighbors, Buggs Island made the decision to abandon the WiMAX system and convert to a LTE system if approved by NTIA. The remaining funds available in this category will be used to purchase and install LTE equipment on tower sites that will cover a 5-county area. The project was reduced in scope due to the limited grant dollars available to fund the conversion. | 70 | Network testing was implemented on the WiMAX and 3.65 network. As noted previously, the WiMAX system will be abandoned and replaced with a LTE system, contingent upon NTIA approval. The 3.65 testing resulted in a successfully installed system that was commercially launched. Additional costs are expected in this category to cover expenses associated with the proposed LTE testing once deployed. | 2013-08-28 10:00 | 2013-08-28 10:00 | 7685 | 7685 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2013 | Q3 | Q3 - 2013 | 11335 | 9468 | TRUE | 84 | As stated above, the deployment of LTE is projected to begin in Q4-2013. The project completion date was extended to 9/30/14 to provide the time needed to dismantle WiMAX equipment on 24 tower sites and to deploy the new LTE equipment on10 tower sites. Costs to date reflect actual expenses incurred in constructing the WiMAX 700 MHZ and 3.65 GHz networks and the new LTE network. | 47 | Admin/Legal/Tower Backhaul/Tower Lease/Engineering Management | The budget items included in this category are: 1) Admin and Legal, 2) Engineering-Project Management, 3) Project Inspection, 4) Monthly Tower Lease Payments and Settlements, and 5) Monthly Backhaul Fees. | 100 | BIT submitted data to the environmental review team to determine whether an environmental review is required for BITâ€™s Revised Plan. | 81 | The 700 MHz network is being re-designed due to issues encountered with the initial build-out. The remaining funds will be used to design the LTE build-out in the 5-county service area. | 0 | Not Applicable | 99 | Additional permits will need to obtained for the installation of LTE equipment. | 100 | No additional costs are expected in this category. | 90 | Funds remaining in this category will be utilized to cover expenses associated with the procurement of an LTE system on 10 towers that cover a 5-county serving area. | 0 | Not Applicable | 88 | The remaining funds available in this category will be used to purchase and install LTE equipment on 10 tower sites that cover a 5-county service area. | 70 | Additional costs are expected in this category to cover expenses associated with the LTE testing once deployed. | 2013-11-21 16:49 | 2013-11-21 16:49 | 7685 | 7685 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2013 | Q4 | Q4 - 2013 | 11793 | 9963 | TRUE | 86 | BIT originally projected having SIM cards and CPE ordered and the make ready at 6 sites completed by Q4 2013. Extended contract negotiations with the LTE vendors delayed the execution which caused a delay on the projected order dates. Now that the project is underway, the above mentioned uncompleted tasks are projected to be completed in Q1 2014. Costs to date reflect actual expenses incurred in constructing the WiMAX 700 MHZ and 3.65 GHz networks, the new LTE network, decommissioning the 14 tower sites, order of the network equipment and transport circuits, and establishing the final network design. | 50 |  | The budget items included in this category are: 1) Admin and Legal, 2) Engineering-Project Management, 3) Project Inspection, 4) Monthly Tower Lease Payments and Settlements, and 5) Monthly Backhaul Fees. | 100 | No Variance. | 84 | The remaining funds will be used to design the LTE build-out in the 5-county service area. | 0 | Not Applicable | 99 | No Variance. | 100 | No Variance | 90 | The actual LTE radio access network equipment procurement was 100% complete by the end of Q4 2013. BIT had projected to have the CPE equipment procurement finalized and ordered in Q4 2013, but BIT did not meet this deadline due to delays in the execution of the vendor contracts, however, plans to complete the CPE procurement and the order will be placed in Q1 2014. | 0 | Not Applicable | 89 | The remaining funds available in this category will be used to purchase and install LTE equipment on 10 tower sites that cover the 5-county service area. | 70 | Additional costs are expected in this category to cover expenses associated with the LTE testing once deployed. | 2014-02-05 13:35 | 2014-02-05 13:35 | 7685 | 7685 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570066 | 2010 | Q4 | Q4 - 2010 | 1127 | 2167 | TRUE | 1 | Progressing as planned | 100 | Grant Preparation | N/A | 99 | Draft submitted on Dec 14, 2010. Addressing items listed from review. Updates due Jan 24, 2011. | 8 | N/A | 0 | N/A | 60 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-14 09:54 | 2011-02-14 09:59 | 5930 | 5930 | BVU Authority | TRUE
NT10BIX5570066 | 2011 | Q1 | Q1 - 2011 | 2167 | 2829 | TRUE | 23 | This percent complete is based on weighted amounts for each category, as shown in BVU's baseline report. As all BVU in-kind was charged to the grant during Q1-2011 to prevent further depreciation of assets, some categories appear further ahead than originally planned. As most recent guidance directed to use expenditures/category amount as the way to calculate percent complete, categories with in-kind appear further ahead of schedule than they physically are. | 100 | Grant Preparation | N/A | 93 | NOTED CHANGE- This category has decreased since last quarter; however, BVU assumed 100% complete meant all activities were completed in the category, not all funds expended. The EA was completed under budget, and as a result, only 93% of its budgeted funds have been used. | 15 | Actual work performed is at 27% invoiced, but work paid is 15%. | 65 | Dollars charged to this category are strictly in-kind at this point, and account for 65% of rights-of-way budgeted dollars. PoP engineering and build has been pushed to a later date by engineering, so PoP construction will not begin until sometime in the next two quarters. | 15 | Stream and RR Crossings continue to be pursued by the engineering firm. Stream crossing permits have proven to be extensive, and RR crossing permits have been delayed by the agencies through which they are obtained. NOTED CHANGE- This category has decreased in percentage complete since last quarter. BVU had been tracking by activities complete; however, this does not match with expended dollars. To account for the difference in the two, BVU has decided to allocate 5% of total engineering dollars spent to permitting, since actual work performed by the engineering firm cannot be tracked by hours specifically to permitting. | 21 | NOTED CHANGE- This category has appeared to rise extensively since the previous quarter. BVU has decided, for tracking purposes, to allocate 0.5% of total construction dollars expended to site preparation, thus making it linkable to actual construction dollars spent. | 46 | Dollars charged to this category are strictly in-kind at this point, and account for 46% of equipment procurement budgeted dollars. PoP engineering and build has been pushed to a later date by engineering, so this procurement will not begin until sometime in the next two quarters. While no electronics have been procured, Category 10- Electronics' budgeted dollars are divided between equipment procurement and equipment deployment, as the cost of deploying the electronics is included in the cost of procuring them. Thus, by charging in-kind to an over arching Electronics budget, money is shown as charged to equipment procurement. | 21 | This category is composed of everything in Category 9- Construction of the OMB Budget, which is all construction of network and all materials related to fiber build (conduit, fiber, etc). Of the overall 21% of categorical dollars expended, about 1% represents construction deployment, paid for by NTIA funds and BVU match funds, about 20% represents in-kind dollars, and no dollars had yet been expended for materials as of 3/31/2011. | 46 | Dollars charged to this category are strictly in-kind at this point, and account for 46% of equipment deployment budgeted dollars. PoP engineering and build has been pushed to a later date by engineering, so this PoP electronic deployment will not begin until sometime in the next two quarters. While no electronics have been deployed (or even procured), Category 10- Electronics' budgeted dollars are divided between equipment procurement and equipment deployment, as the cost of deploying the electronics is included in the cost of procuring them. Thus, by charging in-kind to an over arching Electronics budget, money is shown as charged to equipment deployment. | 0 | Fiber is not to the point of testing yet. | 2011-05-19 11:35 | 2011-05-19 11:35 | 5930 | 5930 | BVU Authority | TRUE
NT10BIX5570066 | 2011 | Q2 | Q2 - 2011 | 3401 | 3464 | TRUE | 34 | The project continues to be ahead of schedule when tracking by dollars expended because BVU charged all in-kind dollars to the grant last quarter. This percentage is extremely close to our predicted percentage complete from last quarters projections (33%). | 98 | Grant Preparation | This category was 100% complete, but during preparation for our audit, we discovered an invoice for grant preparation ($1,144) which was incurred after the grant application was turned in. We credited this back to NTIA by removing the same amount from the next drawdown. | 100 | This category, which includes environmental assessment work, as well as mapping and Davis Bacon compliance, is slightly over-budget at 103%. However, as the EA funds and grant preparation funds are within the same OMB budget category, the removal of an invoice from our grant preparation category made some room for some extra expenditures in this category. | 31 | This category is behind baseline calculations, but is very close to last quarter's projection (probably a more accurate estimate) of 30%. | 65 | This category has not changed from the previous quarter, as predicted. | 31 | Allocation of 5% of Engineering dollars to Construction Permits. Close to last quarter's projection of 30%. | 33 | Allocation of 0.5% of Construction dollars to Site Preparation. Close to last quarter's projection of 32%. | 46 | BVU still has not begun equipment procurement, as the PoPs for the equipment are part of a currently-proposed Project Modification. Once approval is received for this modification, we will begin to incur expenses in this category. Dollars charged to this category so far are in-kind dollars. | 33 | Network build is ahead of schedule budget-wise mainly because all in-kind was expensed to the project last quarter. The project is ahead on baseline projections, but is very close to last quarter's projection of 32%. | 46 | BVU still has not begun equipment deployment, as the PoPs for the equipment are part of a currently-proposed Project Modification. Once approval is received for this modification, we will begin to incur expenses in this category, probably in Q4-2011. Dollars charged to this category so far are in-kind dollars. | 0 | Network testing has not begun to have dollars charged to it, as no electronics are on the network yet. | 2011-08-31 17:38 | 2011-08-31 17:38 | 5930 | 5930 | BVU Authority | TRUE
NT10BIX5570066 | 2011 | Q3 | Q3 - 2011 | 4331 | 4021 | TRUE | 55 | The project has experienced some slow downs due to drilling complications, and thus the weeks we were ahead last quarter has been consumed and putting us slightly behind original schedule. Percent complete also impacted by the additional in-kind contributions added to the budget per OIG request. Since project complete percentage is based on overall dollars, the percentage will increase somewhat on just the in-kind adjustment versus actual expenses. That is why the current percentage complete reflects a large jump over last quarter's report's projection of 45%, even though we had a slow down in construction. | 100 | Grant Preparation | Completed. | 100 | All known assessments are complete. | 45 | This category is slightly below projected percentage based on last quarter's report, but still significantly ahead of construction so no delays due to design expected. | 70 | No actual dollars were expended to this category during this period, but as noted in last quarter's report, the percentage was expected to increase slightly due to budget changes discussed previously. | 45 | Allocation of 5% of Engineering dollars to Construction Permits. DOne in conjunction with Network Design, so slightly below projection is consistent with Network Design percentage. | 56 | Allocation of 0.5% of Construction dollars to Site Preparation. Large percentage jump due to additional in-kind dollars to construction discussed previously. | 59 | BVU still has not begun equipment procurement, as the PoPs for the equipment are part of a currently-proposed Project Modification. Once approval is received for this modification, we will begin to incur expenses in this category. Dollars charged to this category so far are in-kind dollars. No actual dollars were expended to this category during this period, but as noted in last quarter's report, the percentage was expected to increase slightly due to budget changes discussed previously. | 56 | Network build is ahead of schedule budget-wise mainly because all in-kind was expensed to the project last quarter. Large percentage jump due to additional in-kind dollars to construction discussed previously. | 59 | BVU still has not begun equipment deployment, as the PoPs for the equipment are part of a currently-proposed Project Modification. Once approval is received for this modification, we will begin to incur expenses in this category, probably in Q4-2011. Dollars charged to this category so far are in-kind dollars. Large percentage jump due to additional in-kind dollars to equipment discussed previously. | 0 | Network testing has not begun to have dollars charged to it, as no electronics are on the network yet. | 2011-11-30 12:05 | 2011-11-30 12:05 | 5930 | 5930 | BVU Authority | TRUE
NT10BIX5570066 | 2011 | Q4 | Q4 - 2011 | 5035 | 4708 | TRUE | 38 | *****Please note that many of the percentages are lower than last report due to the change in in-kind valuation and reporting (see #1 above for more info). Based on expensed versus project dollars. Baseline projected 148.5 miles built out by end of Q1 2012 and we are currently at 120 at the end of Q4 2011. Good progress was made last quarter and expectation is that this rate of build out will continue. | 100 | Grant Prep | Completed. | 100 | All assessments are complete. | 61 | Emphasis was put on getting design and engineering complete during this quarter, so significant progress was made | 61 | Agreement with Virginia Department of Transportation gives BVU Rights-of-Way for all routes. Percent complete based on new method to account for in-kind use described in overview above | 61 | Allocation of 5% of Engineering dollars to Construction Permits. Done in conjunction with Network Design, so projection is consistent with Network Design percentage. | 39 | Allocation of 0.5% of Construction dollars to Site Preparation, so projection is consistent with Network Build percentage. | 15 | BVU still has not begun equipment procurement. Dollars charged to this category so far are in-kind dollars based on new methodology. Expect first wave of new equipment dollars to be expended in next quarter. | 39 | Network build percentage affected by change in-kind dollars methodology. Actual federal dollars expended is in line with percentage build out of miles. | 0 | No electronics have been installed as yet. Expect first route to be lit this quarter. | 0 | Network testing has not begun to have dollars charged to it, as no electronics are on the network yet. | 2012-02-15 15:07 | 2012-02-15 15:07 | 5930 | 5930 | BVU Authority | TRUE
NT10BIX5570066 | 2012 | Q1 | Q1 - 2012 | 5939 | 5569 | TRUE | 48 | Based on expensed versus project dollars. Baseline projected 148.5 miles built out by end of Q1 2012 and we are currently at 209 at the end of Q1 2012. Good progress was made last quarter and expectation is that this rate of build out will continue. | 100 | Grant Prep | Completed. | 100 | All assessments are complete. | 76 | Based on expensed versus project dollars. Emphasis was put on getting design and engineering complete during this quarter, so significant progress was made | 61 | Percent complete based on mileage. Agreement with Virginia Department of Transportation gives BVU Rights-of-Way for all routes. | 76 | Based on expensed versus project dollars. Allocation of 5% of Engineering dollars to Construction Permits. Done in conjunction with Network Design, so percentage is consistent with Network Design percentage. | 49 | Based on expensed versus project dollars. Allocation of 0.5% of Construction dollars to Site Preparation, so projection is consistent with Network Build percentage. | 36 | Based on expensed versus project dollars. Allocation done in conjunction with Equipment Deployment, so percentage is consistent with Equipment Deployment percentage. | 49 | Based on expensed versus project dollars. Actual federal dollars expended is in line with percentage build out of miles. | 36 | Based on expensed versus project dollars. Allocation done in conjunction with Equipment Procurement, so percentage is consistent with Equipment Procurement percentage. | 3 | Based on expensed versus project dollars. | 2012-05-07 11:15 | 2012-05-07 11:15 | 5930 | 5930 | BVU Authority | TRUE
NT10BIX5570066 | 2012 | Q2 | Q2 - 2012 | 6957 | 6106 | TRUE | 68 | Based on expensed versus project dollars. Baseline projected 249 miles built out by end of Q2 2012 and we are currently at 258.6 at the end of Q2 2012. Progress slowed over last quarter due to easement and permit issues. Once these issues are addressed, additional crews can be engaged to increase build out rate. | 100 | Grant prep | Complete. | 100 | All current route environmental assessments complete. | 100 | All current route network design complete. | 73 | Percent complete based on mileage. Agreement with Virginia Department of Transportation gives BVU Rights-of-Way for all routes. | 95 | Based on expensed vs project dollars. 5% of engineering dollars allocated to category. Has been done in conjunction with Network Design on assumption was that permits and easements would be received as design built. This is no longer true due to easement issues. | 69 | Based on expensed versus project dollars. Allocation of 0.5% of Construction dollars to Site Preparation, so projection is consistent with Network Build percentage. | 51 | Based on expensed versus project dollars. Allocation done in conjunction with Equipment Deployment, so percentage is consistent with Equipment Deployment percentage. | 69 | Based on expensed versus project dollars. Actual federal dollars expended is (69%) in line (slightly below) with percentage build out of miles (73%). | 51 | Based on expensed versus project dollars. Allocation done in conjunction with Equipment Procurement, so percentage is consistent with Equipment Procurement percentage. | 13 | Based on expensed versus project dollars. | 2012-08-09 10:41 | 2012-08-09 10:42 | 7556 | 7556 | BVU Authority | TRUE
NT10BIX5570066 | 2012 | Q3 | Q3 - 2012 | 8029 | 6721 | TRUE | 78 | Based on expensed/in-kind versus project dollars. Current expenditures are at 78%, which is exactly in line with miles built out. Baseline projected 297 miles (82%) built out by end of Q3 2012 and we are currently at 284.5 miles (78%) at the end of Q3 2012. Progress slowed over last quarter due to easement and permit issues. Once these issues are addressed, additional crews can be engaged to increase build out rate. | 100 | Grant Preparation | Complete. | 100 | All current route environmental assessments complete. | 100 | All current route network design complete. | 78 | Percent complete based on mileage. Agreement with Virginia Department of Transportation gives BVU Rights-of-Way for all routes. | 95 | We have changed tracking method of this category from expensed versus projected dollars to actual tracking of known outstanding easement and permits versus total needed easements and permits. Original assumption was that easements and permits would be received during engineering phase did not hold, thus the need to change tracking method. | 81 | Based on expensed/in-kind versus project dollars. Allocation of 0.5% of Construction dollars to Site Preparation, so projection is consistent with Network Build percentage. | 70 | Based on expensed/in-kind versus project dollars. Allocation done in conjunction with Equipment Deployment, so percentage is consistent with Equipment Deployment percentage. | 81 | Based on expensed/in-kind versus project dollars. Percent of actual federal dollars expended (77.7%) is in line with percentage build out of miles (78.4%). Additional percent due to in-kind contributions. | 70 | Based on expensed versus project dollars. Allocation done in conjunction with Equipment Procurement, so percentage is consistent with Equipment Procurement percentage. | 21 | Based on expensed versus project dollars. | 2012-11-26 11:34 | 2012-11-26 11:34 | 7556 | 7556 | BVU Authority | TRUE
NT10BIX5570066 | 2012 | Q4 | Q4 - 2012 | 8699 | 7509 | TRUE | 84 | Based on expensed/in-kind versus project dollars. Current expenditures are at 84%, which is in line with miles built out. Baseline projected 336 miles (88.43%) built out by end of Q2 Year 3 and we are currently at 324.7 miles (85.6%) at the end of Q2 Year 3. Progress slowed over last quarter due to easement and permit issues. Large majority of these issues have been addressed, and additional crews now can be engaged to increase build out rate. Routes completed and lit: 12; Routes in progress: 16 (28.7 miles remaining); Routes remaining to be worked: 2 (24 miles) | 100 | Grant preparation | Complete | 100 | All current route environmental assessments complete. | 100 | All current route network design complete unless issues found during built out which may cause a very minor adjustment. | 82 | Note: Change in calculation method per request from Federal Program Officer. Was based on mileage, now will be based on construction dollars expensed versus total budget construction dollars. Rights of Way follow construction, so percentage is consistent with Network Build percentage. | 92 | We have changed tracking method of this category from [expensed versus projected dollars] to [actual tracking of known outstanding easement and permits versus total needed easements and permits]. Original assumption was that easements and permits would be received during engineering phase did not hold, thus the need to change tracking method. We have encountered some slow down on obtaining property easements on some of the routes. All negotiations have been completed and any property easement not obtained have been send to the appropriate counties for quick-take condemnation. Do not see any impact to completion at this time. | 82 | Based on expensed/in-kind versus project dollars for construction. Site prep is allocated of 0.5% of construction dollars, so projection is consistent with Network Build percentage. | 61 | Based on expensed/in-kind versus project dollars for equipment. Allocation done in conjunction with [Equipment Deployment], so percentage is consistent with [Equipment Deployment] percentage. Please note that previously all equipment in-kind dollars were included, but after discussions with FPO we have adjusted to include only a percentage of in-kind equipment dollars based on percent of miles built out. Due to method change, the percentage will be less than last quarter report. | 82 | Based on expensed/in-kind versus project dollars. Percent of actual federal dollars expended (84.6%) is in line with percentage build out of miles (85.6%). Additional percent due to in-kind contributions. | 61 | Based on expensed/in-kind versus project dollars for equipment. Allocation done in conjunction with [Equipment Procurement], so percentage is consistent with [Equipment Procurement] percentage. Please note that previously all equipment in-kind dollars were included, but after discussions with FPO we have adjusted to include only a percentage of in-kind equipment dollars based on percent of miles built out. Due to method change, the percentage will be less than last quarter report. | 31 | Based on expensed versus project dollars. | 2013-02-11 12:05 | 2013-02-11 12:05 | 7556 | 7556 | BVU Authority | TRUE
NT10BIX5570066 | 2013 | Q1 | Q1 - 2013 | 9829 | 8451 | TRUE | 89 | Based on expensed/in-kind versus project dollars. Current expenditures are at 89%, which is in line with percentage of miles built out. Baseline projected 357 miles (94%) built out by end of Q3 Year 3 and we are currently at 338 miles (89.5%) at the end of Q3 Year 3. Progress slowed over last quarter due to easement and make-ready issues. Large majority of these issues have been addressed, and additional crews now can be engaged to increase build out rate. Routes completed and lit: 14; Routes in progress: 16 (30.4 miles remaining) | 100 | Grant preparation | Completed. | 100 | All route environmental assessments complete. | 100 | All route network design complete unless build out issues found which may cause minor adjustments. | 89 | Note: Change in calculation method done per request from Federal Program Officer (B Brown). Was based on mileage, now will be based on construction dollars expensed versus total budget construction dollars. Rights of Way follow construction, so percentage is consistent with Network Build percentage. | 99 | We have changed tracking method of this category from [expensed versus projected dollars] to [actual tracking of known outstanding easement and permits versus total needed easements and permits]. Original assumption was that easements and permits would be received during engineering phase did not hold, thus the need to change tracking method. We had encountered some slow down on obtaining property easements and make-reaady turnaround on some of the routes. Do not see any impact to completion at this time. Easements needed (437); Easements received (436) | 89 | Based on expensed/in-kind versus project dollars for construction. Site prep is allocated of 0.5% of construction dollars, so projection is consistent with Network Build percentage. | 65 | Based on expensed/in-kind versus project dollars for equipment. Allocation done in conjunction with [Equipment Deployment], so percentage is consistent with [Equipment Deployment] percentage. Please note that previously all equipment in-kind dollars were included, but after discussions with FPO we have adjusted to include only a percentage of in-kind equipment dollars based on percent of miles built out. | 89 | Based on expensed/in-kind versus project dollars for equipment. Allocation done in conjunction with [Equipment Procurement], so percentage is consistent with [Equipment Procurement] percentage. | 65 | Based on expensed/in-kind versus project dollars for equipment. Allocation done in conjunction with [Equipment Procurement], so percentage is consistent with [Equipment Procurement] percentage. | 40 | Based on expensed versus project dollars. | 2013-05-20 14:32 | 2013-05-20 14:32 | 7556 | 7556 | BVU Authority | TRUE
NT10BIX5570066 | 2013 | Q2 | Q2 - 2013 | 10649 | 8985 | TRUE | 94 | [PLEASE NOTE: Some of the categories below were reported on based on percentage of work completed, however, FPO has requested that we now strictly report on percentage of dollars used, which may make a category report lower than last quarter] Percentage based on [expensed + in-kind dollars] versus overall project dollars. Current expenditures are at 94.4%. Current miles built out are 365.2 of the projected 369.12 (98.95%). Routes completed and lit: 19; Routes completed and waiting fiber splice: 7; Routes in progress: 4 | 100 | Grant preparation | All activities and costs for grant preparation are completed. | 100 | All activities and costs associated with environmental assessments are complete. | 99 | All activities and costs associated with network design are complete, except for a few hours for final engineering of last 1.2 miles due to switching from buried to aerial | 100 | All activities and costs for rights-of-way and easements are complete | 100 | All activities and costs for the needed 437 easements are complete | 91 | Based on [expensed + in-kind dollars] versus project dollars for construction. [Site preparation] is allocated of 0.5% of construction dollars, so projection is consistent with [Network Build] percentage. Installation of distribution cabinets and NAP's will also entail site preparation. | 70 | Based on [expensed + in-kind dollars] versus project dollars for equipment. Allocation done in conjunction with [Equipment Deployment], so percentage is consistent with [Equipment Deployment] percentage. | 91 | Based on [expensed + in-kind dollars] versus project dollars for construction. | 70 | Based on [expensed + in-kind dollars] versus project dollars for equipment. Allocation done in conjunction with [Equipment Procurement], so percentage is consistent with [Equipment Procurement] percentage. | 50 | Based on [expensed + in-kind dollars] versus project dollars for [Network Testing]. Testing will also be needed on new cabiinets and NAP's. | 2013-08-20 10:16 | 2013-08-20 10:16 | 7556 | 7556 | BVU Authority | TRUE
NT10BIX5570066 | 2013 | Q3 | Q3 - 2013 | 12287 | 10459 | TRUE | 100 | Percentage based on [expensed + in-kind dollars] versus overall project dollars. Final [expensed + in-kind dollars] are at 100% of project budget. | 100 | Grant preparation | All activities and costs associated with this item are complete. | 100 | All activities and costs associated with this item are complete. | 100 | All activities and costs associated with this item are complete. | 100 | All activities and costs associated with this item are complete. | 100 | All activities and costs associated with this item are complete. | 100 | All activities and costs associated with this item are complete. | 100 | All activities and costs associated with this item are complete. | 100 | All activities and costs associated with this item are complete. | 100 | All activities and costs associated with this item are complete. | 100 | All activities and costs associated with this item are complete. | 2014-06-24 10:52 | 2014-06-24 10:52 | 5759 | 5759 | BVU Authority | TRUE
NT10BIX5570067 | 2010 | Q4 | Q4 - 2010 | 1253 | 2284 | TRUE | 10 | Percent complete is based on amount budgeted vs spent, and includes both federal funds and matching funds. Total project spend is ahead of baseline (4%) due to large equipment purchases paid for in the period ending 12/31/2010. | 0 |  | N/A | 81 | On plan, as % of estimated effort to complete. | 90 | The pct complete here is expressed as a % of effort (vs budget). Network design is largely complete (although some level of design activity will be continuous, however, the bulk of effort was "up front"). | 0 | There were no new rights of way that were needed to be acquired. The project baseline was established as the physical walkouts were being conducted for the EA. It was assumed for planning purposes some new rights of way might be needed, and that these would be acquired during the walkout and EA process. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline. We do anticipate we may need one or two. As these are encountered, and budget from the "Land, Structures, Rights of Way" is expended, it will be reported here. | 1 | By period end permitting with utility companies was just ramping up; baseline reflects an incorrect plan percentage of 50% based on EA approval dependency. Permissions to enter new hub sites planned will also be reported here, and by 12/31/2010 no new colocation agreements had been signed. Less than 1% of the total project budget had been expended by 12/31/2010 for permitting with the utility infrastructure owners. | 0 | Not commenced due to dependency on EA approval | 6 | The percent complete is based on % of total program budget. First shipments of networking gear were received in December on plan; baseline of 45% anticipated more equipment arriving in the quarter than we were able to achieve for federally funded purchases. Matching equipment (both cash and in kind) occurred by 12/31/2011 as well. | 0 | Percent complete is expressed as a % of the federal program budget. No construction has been started as of 12-31-10. | 0 | Percent complete is expressed as a % of the federal program budget. No construction or equipment deployment has begun as of 12-31-10. | 0 | Not commenced | 2011-02-20 22:33 | 2011-02-20 22:33 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2011 | Q1 | Q1 - 2011 | 1941 | 2716 | TRUE | 14 | Percent complete is based on amount budgeted vs spent, and includes both federal funds and matching funds. As this reflects the % of total funds available vs actually spent, we are at 14% complete. This is behind our baseline; the baseline assumed large equipment and material expenditures would need to occur in the first 6 months. Favorable shipping and payment terms have allowed us to defer some of the larger "up front" expenditures we anticipated. | 0 |  | Other funds were not budgeted, but were expended in the quarter. These other expenses include web conference services (webex), government data publications, bank fees, and misc expenses | 100 | COMPLETE | 100 | Network design is complete as a percent of budget. Initial budgeted amount has been consumed; there may be additional design work as routes are optimized, or need to change if an environmental protection measure detects a problem on a route, etc... | 0 | There were no new rights of way that were needed to be acquired. The project baseline was established as the physical walkouts were being conducted for the EA. It was assumed for planning purposes some new rights of way might be needed, and that these would be acquired during the walkout and EA process. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline. We do anticipate we may need one or two. As these are encountered, and budget from the "Land, Structures, Rights of Way" is expended, it will be reported here. | 4 | By period end permitting with utility companies was still ramping up; baseline reflects an incorrect plan percentage of 65% based on EA approval dependency. Permissions to enter new hub sites planned will also be reported here, and by 03/31/2011 no new collocation agreements had been signed. 3.9% complete is expressed as amount spent of the total project budget for construction permits and approvals, which had been expended by 3/31/2011 for permitting with the utility infrastructure owners. We are behind plan due to the arrival of the FONSI late in the quarter. | 20 | Matching funds were expended to move into a new data center facility | 51 | The percent complete is based on % of total program budget, both fed and match portions. All initial shipments of networking gear were received by 3/31 on plan; baseline of 60% anticipated more equipment arriving in the quarter than we were able to achieve for federally funded purchases. | 0 | Percent complete is expressed as a % of the federal program budget. No construction has been started as of 03-31-2011, as the FONSI was received late in the quarter. | 0 | Percent complete is expressed as a % of the federal program budget. No construction or equipment deployment has begun as of 03-31-2011, as the FONSI was received late in the quarter. | 0 | Not commenced, dependent on 2h and 2i | 2011-05-11 13:15 | 2011-05-11 13:15 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2011 | Q2 | Q2 - 2011 | 3185 | 3353 | TRUE | 25 | Percent complete is based on amount budgeted vs spent, and includes both federal funds and matching funds. As this reflects the % of total funds available vs actually spent, we are at 25% complete. This is behind our baseline; the baseline assumed large equipment and material expenditures would need to occur in the first 6 to 9 months. Favorable shipping and payment terms have allowed us to defer some of the larger "up front" expenditures we anticipated. In addition, the baseline assumed we would be able to make payments for "make ready" work much faster than our actual experience to-date. | 0 |  | Other funds were not budgeted, but were expended in the quarter. These other expenses include web conference services (webex), government data publications, bank fees, and misc expenses | 100 | Complete. | 100 | Network design is complete as a percent of budget. Initial budgeted amount has been consumed; there may be additional design work as routes are optimized, or need to change if an environmental protection measure detects a problem on a route, etc... | 0 | There were no new rights of way that were needed to be acquired. The project baseline was established as the physical walkouts were being conducted for the EA. It was assumed for planning purposes some new rights of way might be needed, and that these would be acquired during the walkout and EA process. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline. We do anticipate we may need one or two. As these are encountered, and budget from the "Land, Structures, Rights of Way" is expended, it will be reported here. | 15 | By period end permitting with utility companies was underway; baseline reflects an incorrect plan percentage of 65% based on EA approval dependency. Permissions to enter new hub sites planned will also be reported here, and by 06/30/2011 no new collocation agreements had been signed. 15.6% complete is expressed as amount spent of the total project budget for construction permits and approvals, which had been expended by 6/30/2011 for permitting with the utility infrastructure owners. We are behind plan due to lead times required by many incumbents in our area of operation. | 20 | Matching funds were expended to move into a new data center facility. We are slightly behind plan in expenses required, mainly due to internal cost optimizations and controls. | 89 | The percent complete is based on % of total program budget, both fed and match portions. All initial shipments of networking gear were received by 6/30 on plan; baseline of 65% anticipated less equipment & materials arriving in the quarter than we were able to achieve for federally funded purchases. We are ahead of plan. | 2 | Percent complete is expressed as a % of the federal program budget. Baseline is at 5%, we are slightly behind due to "make ready" taking longer than anticipated | 9 | Percent complete is expressed as a % of the federal program budget. Baseline is at 5%, we are slightly ahead of plan due to progress made in installation of electronics in existing and new hub sites. | 6 | Percent complete expressed as a % of budget. We are ahead of plan with some initial testing activities, primarily at hub sites. | 2011-08-18 08:43 | 2011-08-18 08:43 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2011 | Q3 | Q3 - 2011 | 4129 | 3911 | TRUE | 35 | Percent complete is based on amount budgeted vs spent, and includes both federal funds and matching funds. As this reflects the % of total funds available vs actually spent, we are at 35% complete. Our baseline is at 48% so we are behind; the baseline assumed large equipment and material expenditures would need to occur in the first 6 to 9 months. Favorable shipping and payment terms have allowed us to defer some of the larger "up front" expenditures we anticipated. In addition, the baseline assumed we would be able to make payments for "make ready" work much faster than our actual experience to-date | 100 | miscellaneous items | we have incurred project-inception-to-date miscellaneous administrative costs which have been recovered from the project (0.16% of total federal spending) | 100 | Completed in Q1-2011. Assessment work continues in conjunction with enforcement of our Special Award Conditions related to our Environmental Protection Measures (EPMs) | 100 | Completed in Q1-2011 | 0 | There were no new rights of way that were needed to be acquired. The project baseline was established as the physical walkouts were being conducted for the EA. It was assumed for planning purposes some new rights of way might be needed, and that these would be acquired during the walkout and EA process. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline. We do anticipate we may need one or two. As these are encountered, and budget from the "Land, Structures, Rights of Way" is expended, it will be reported here. | 47 | By period end permitting with utility companies, and other entities was filed on approximately half of the network, with plans to have 70% filed by Q4-2011. We have established personal contact with all permitting entities, including railroads and dept of transportation officials as well as utility and telecom companies, and our permit applications are getting turned around much faster. We are behind our baseline as of 9/30/2011 however, which was at 90%. | 20 | The percent complete is based upon total program budget, both federal and match portions. Baseline is at 50%. | 90 | The percent complete is based on % of total program budget, both fed and match portions. All initial shipments of networking gear and fiber were received by 9/30 on plan; baseline of 70% anticipated less equipment & materials arriving in the quarter than we were able to achieve for federally funded purchases. | 3 | Percent complete is expressed as a % of the federal program budget. Baseline is at 15%, we are behind due to "make ready" taking longer than anticipated | 58 | Baseline is at 10%. Equipment Deployment is at 58.57% complete, based on hub sites upgraded and in progress (not including testing). | 9 | Baseline is at 0%. We are slightly ahead of schedule having completed one of our smaller ring segments (approx 35 miles), and testing of equipment installed in the Equipment Deployment. | 2011-11-18 12:09 | 2011-11-18 12:09 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2011 | Q4 | Q4 - 2011 | 5287 | 4956 | TRUE | 42 | Percent complete is based on total program amount budgeted vs spent, and includes both federal funds and matching funds. As this reflects the % of total funds available vs actually spent, we are at 35% complete. Our baseline is at 56% so we are behind a bit. We are at 57% of federal funds expended, and will be at 2/3 by June 30, 2012 per our milestone. | 100 | Legal | Percent complete is expressed as a percent of budget expended. We have had minor cost overruns, primarily in legal fees to review subrecipient and vendor contracts for compliance, and in obtaining a CLEC license so we could apply for access to certain utility pole owners' poles. | 100 | Our Environmental Assessment was completed in Q1-2011. Assessment work continues in conjunction with enforcement of our Special Award Conditions related to our Environmental Protection Measures (EPMs) | 100 | Completed in Q1 2011. Network design activities occur as needed for route optimization and EPM enforcement. | 0 | There were no new rights of way that were needed to be acquired. The project baseline was established as the physical walkouts were being conducted for the EA. It was assumed for planning purposes some new rights of way might be needed, and that these would be acquired during the walkout and EA process. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline. We do anticipate we may need one or two. As these are encountered, and budget from the "Land, Structures, Rights of Way" is expended, it will be reported here. | 58 | Significant progress was made during Q4 2011, and we are getting back on track toward our 2/3 completion milestone. By period end permitting with utility companies, and other entities was filed on approximately 3/4 of the network. Our largest pole owner in our Project Area is Ohio Edison. We currently have agreement from them to deliver on 3/31 and again on 6/1 sufficient poles that we will be able to complete our 2/3 milestone by 6/30/2012. This is of course subject to winter weather. We are behind our baseline as of 12/31/2011 however, which was at 95%. Percent complete is stated as a percent of total budget vs actual. This 58% reflects the amount of total project budget spent. | 24 | We remain on plan. Baseline is at 60%, however, we have not had need to expend any further funds on site preparation as of 12-31-2011. | 100 | Percent complete is percent of budget expended. As of 12-31-11 all but one shipment had been received. We have all fiber and electronics to complete the core network build out and major laterals outlined in our application. | 6 | Percent complete is expressed as percent of budget. As a percent of miles, we are approximately 7% complete. We are behind our baseline of 25% due to slow start up due to make ready work delays. we expect to be at 67% by 6/30/2011 still given current commitments from utility pole owners - once paths are cleared we have sufficient crews and materials in inventory to complete the work. | 13 | We are on plan, given the delays due to make ready. Equipment is staged and waiting on the fiber. Baseline is at 25% so we are a bit behind. | 7 | We are on plan, given the delays due to make ready. Equipment is staged and waiting on the fiber. Baseline is at 15% so we are a bit behind. | 2012-02-27 13:29 | 2012-02-27 13:29 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2012 | Q1 | Q1 - 2012 | 6117 | 5661 | TRUE | 47 | Percent complete is based on total program amount budgeted vs spent, and includes both federal funds and matching funds. Our baseline is at 65% so we are behind a bit. We anticipate being at 2/3 by June 30, 2012 per our milestone. | 100 | legal & admin | Percent complete is expressed as a percent of budget expended. We have had minor cost overruns, primarily in legal fees to review subrecipient and vendor contracts for compliance, and in obtaining a CLEC license so we could apply for access to certain utility pole owners' poles. | 100 | Our Environmental Assessment was completed in Q1-2011. Assessment work continues in conjunction with enforcement of our Special Award Conditions related to our Environmental Protection Measures (EPMs) | 100 | Completed in Q1 2011. Network design activities occur as needed for route optimization and EPM enforcement. | 0 | There were no new rights of way that were needed to be acquired. The project baseline was established as the physical walkouts were being conducted for the EA. It was assumed for planning purposes some new rights of way might be needed, and that these would be acquired during the walkout and EA process. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline. We do anticipate we may need one or two. As these are encountered, and budget from the "Land, Structures, Rights of Way" is expended, it will be reported here. | 88 | As of 3/31 we were at 89% of construction permits/approvals, as a percentage of budget, against a baseline of 92%. We are on target to complete the permits/make ready/other approvals needed in order to meet our June 30 milestone | 24 | We remain on plan. Baseline is at 65%, however, we have not had need to expend any further funds on site preparation as of 03-31-2012. As more fiber is "lit" in Q2, we anticipate needing to make some investments in our hub sites | 100 | All equipment has been acquired for the project, as budgeted for in the program budget. Baseline is at 80%, so we are ahead of baseline | 14 | Percent complete is based on budget expended. Baseline is at 40%, however, we are not that far behind in terms of fiber miles deployed. With the spring weather in March & April we have made significant headway, and anticipate being 2/3 complete of fiber deployed by 6/30/2012. | 23 | Percent complete is based on budget expended. Baseline is at 40% of budget expended, but we have been able to run under budget to this point. We anticipate an increase in budget spending as more of our backbone gets complete and we "turn up" hub sites. | 8 | Percent complete is based on budget expended. Baseline is at 30% of budget being expended by 3/31/2012, but we have been able to run under budget to this point. We anticipate an increase in budget spending as more of our backbone gets complete and we "turn up" hub sites. | 2012-05-15 21:01 | 2012-05-15 21:01 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2012 | Q2 | Q2 - 2012 | 7101 | 6178 | TRUE | 53 | Percent complete is based on total program amount budgeted vs spent, and includes both federal funds and matching funds. Our baseline is at 73% so we are behind due to matching funds just beginning to materialize, and "make ready" still to be invoiced. | 100 | legal and admin | Percent complete is expressed as a percent of budget expended. We have had minor cost overruns, primarily in legal fees to review subrecipient and vendor contracts for compliance, and in obtaining a CLEC license so we could apply for access to certain utility pole owners' poles. | 100 | Our Environmental Assessment was completed in Q1-2011. Assessment work continues in conjunction with enforcement of our Special Award Conditions related to our Environmental Protection Measures (EPMs) | 100 | Completed in Q1 2011. Network design activities occur as needed for route optimization and EPM enforcement. | 0 | There were no new rights of way that were needed to be acquired. The project baseline was established as the physical walkouts were being conducted for the EA. It was assumed for planning purposes some new rights of way might be needed, and that these would be acquired during the walkout and EA process. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline. We do anticipate we may need one or two. As these are encountered, and budget from the "Land, Structures, Rights of Way" is expended, it will be reported here. | 90 | As of 6/30, and as a result of our concerted efforts to reach substantial completion, we were able to accelerate much of the "make ready" we needed. The percent complete is based on REMAINING WORK (vs. budget, as the original budget underestimated total program spending required for make ready) | 24 | We remain on plan. Baseline is at 80%, however, we have not had need to expend any further funds on site preparation as of 06-30-2012. As more fiber has been "lit" in Q2, we anticipate needing to make some investments in our hub sites possibly in Q3 2012. | 100 | All equipment has been acquired for the project, as budgeted for in the program budget. Equipment purchases continue as needed to bring CAI locations onto the network ("on net") (e.g., to ensure compatibility with customer LAN/WAN). Also, purchases of small switches for customer premise equipment (CPE) may be warranted as more CAI's are signed up. | 16 | Network build, equipment deployment and testing work all continues as planned. Baseline here is at 55% of total budget being expended to reach our 2/3 milestone in miles complete, however we are experiencing greater productivity than planned (which has kept the overall program within budget). Productivity includes an overall lower per foot cost due to a number of contributing factors including: aerial / underground mix has been more aerial (cheaper to deploy, more expensive to operate); per crew daily/weekly footages ahead of estimate due to clear paths and able to make longer runs non-stop. | 29 | Network build, equipment deployment and testing work all continues as planned. Baseline here is at 55% of total budget being expended to reach our 2/3 milestone in miles complete, however we are experiencing greater productivity than planned (which has kept the overall program within budget). | 8 | Network build, equipment deployment and testing work all continues as planned. Baseline here is at 40% of total budget being expended to reach our 2/3 milestone in miles complete, however we are experiencing greater productivity than planned (which has kept the overall program within budget). | 2012-08-15 20:04 | 2012-08-15 20:04 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2012 | Q3 | Q3 - 2012 | 8075 | 6744 | TRUE | 60 | Percent complete is based on total program amount budgeted vs spent, and includes both federal funds and matching funds. Our baseline is at 83% so we are behind due to matching funds from program income now coming in, and "make ready" still to be invoiced. | 100 |  | Percent complete is expressed as a percent of budget expended. We have had minor cost overruns, primarily in legal fees to review sub-recipient and vendor contracts for compliance, and in obtaining a CLEC license so we could apply for access to certain utility pole owners' poles. | 100 | Our Environmental Assessment was completed in Q1-2011. Assessment work continues in conjunction with enforcement of our Special Award Conditions related to our Environmental Protection Measures (EPMs) | 100 | Completed in Q1 2011. Network design activities occur as needed for route optimization and EPM enforcement. | 0 | There were no new rights of way that were needed to be acquired. The project baseline was established as the physical walkouts were being conducted for the EA. It was assumed for planning purposes some new rights of way might be needed, and that these would be acquired during the walkout and EA process. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline. We do anticipate we may need one or two. As these are encountered, and budget from the "Land, Structures, Rights of Way" is expended, it will be reported here. | 90 | As of 9/30, and as a result of our concerted efforts to reach substantial completion, we were able to accelerate much of the "make ready" we needed. The percent complete is based on REMAINING WORK (vs. budget, as the original budget underestimated total program spending required for make ready). In addition, we continue to add CAI locations well ahead of plan, which for each site will require some permitting. | 40 | We remain on plan. Baseline is at 90%, however, we have not had need to expend any further funds on site preparation as of 09-30-2012. | 100 | All equipment has been acquired for the project, as budgeted for in the program budget. Equipment purchases continue as needed to bring CAI locations onto the network ("on net") where customer premise equipment (CPE) is required to connect the CAI. We are ahead of plan and budget due to all the pending CAI deals. | 22 | Network build, equipment deployment and testing work all continues as planned. Baseline plan for network build is at 70% of budget, however we have yet to purchase new leased fiber which would bring us more in line with planned budget expenditures. Through Q2 202 we had experienced greater productivity than plan (which has kept the overall program within budget as well). There is a disconnect with the original program budget and baseline, and the current reporting. The original plan included in network build out costs the cost of outside plant (OSP) equipment and materials. Through the PPR reporting the OSP equipment has been properly reported as equipment. We are in the process of completing a Corrective Action Plan, and will be submitting a budget modification and new baseline for the program, most likely in Q4 2012. | 30 | Network build, equipment deployment and testing work all continues as planned. Baseline here is at 75% of total budget being expended to reach our 2/3 milestone in miles complete, however we are experiencing greater productivity than planned (which has kept the overall program within budget). | 10 | Network build, equipment deployment and testing work all continues as planned. Baseline here is at 50% of total budget being expended to reach our 2/3 milestone in miles complete, however we are experiencing greater productivity than planned (which has kept the overall program within budget). | 2012-11-27 15:25 | 2012-11-27 15:25 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2012 | Q4 | Q4 - 2012 | 9065 | 7839 | TRUE | 72 | Percent complete is based on REVISED total program amount budgeted vs spent, and includes both federal funds and matching funds. Our baseline is at 95% so we are behind due to matching funds from program income now coming in, and "make ready" still to be invoiced. We have also slowed down our "burn rate" to allow for more time to generate match. | 100 |  | Percent complete is based on revised budget vs. actual expenses. Very little additional expenses are expected in this category | 100 | Our Environmental Assessment was completed in Q1-2011. Assessment work continues in conjunction with enforcement of our Special Award Conditions related to our Environmental Protection Measures (EPMs) | 77 | Completed in Q1 2011. Network design activities occur as needed for route optimization and EPM enforcement. | 0 | There were no new rights of way that were needed to be acquired. The project baseline was established as the physical walkouts were being conducted for the EA. It was assumed for planning purposes some new rights of way might be needed, and that these would be acquired during the walkout and EA process. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline. We do anticipate we may need one or two. As these are encountered, and budget from the "Land, Structures, Rights of Way" is expended, it will be reported here. | 56 | Percent complete is based on revised budget amount vs actual expenses. Incumbent utility pole owners are still slow to invoice us for make ready. | 31 | Percent complete expressed as a % of budget. We remain on plan. Baseline is at 95%, however, we have not had need to expend any further funds on site preparation as of 12-31-2012. | 94 | Percent complete is based on REVISED BUDGET amount vs. actual expenses. Our baseline is at 95%. We are on plan. | 52 | Percent complete is based on REVISED BUDGET vs. actual expenses. Network build, equipment deployment and testing work all continues as planned. Baseline plan for network build is at 85% of budget, however we have yet to purchase new leased fiber which would bring us more in line with planned budget expenditures. Through 2012 we had experienced greater productivity than plan (which has kept the overall program within budget as well). We will be able to finish within the grant period. | 100 | Percent complete is based on revised budget vs actual expenses. We are at 100% of budget, vs our baseline of 85%. All equipment has been racked and staged. As hub sites are completed in Q1 2013, testing will accelerate; we will finish on time. | 48 | Percent completed is based on revised budget vs actual expenses. Our baseline is at 70%, we are behind this due to slowing down some portions of the program. We will be able to complete all testing before the end of the grant period. | 2013-02-28 12:12 | 2013-02-28 12:12 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2013 | Q1 | Q1 - 2013 | 10035 | 8568 | TRUE | 79 | Percent complete is based on REVISED total program amount budgeted vs spent, and includes both federal funds and matching funds. Our baseline is at 99% so we are behind due to matching funds from program income now coming in, and "make ready" still to be invoiced. | 100 | miscellaneous | Current percent complete is based on revised budget vs. actual expenditures. | 100 | Percent complete is based on REVISED budget. Our Environmental Assessment was completed in Q1-2011. Assessment work continues in conjunction with enforcement of our Special Award Conditions related to our Environmental Protection Measures (EPMs) | 79 | Percent complete is based on REVISED budget. Network design initially completed in Q1 2011. Network design activities occur as needed for route optimization and EPM enforcement. | 0 | There were no new rights of way that were needed to be acquired. The project baseline was established as the physical walkouts were being conducted for the EA. It was assumed for planning purposes some new rights of way might be needed, and that these would be acquired during the walkout and EA process. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline. We do anticipate we may need one or two. As these are encountered, and budget from the 424C category of "Land, Structures, Rights of Way" is expended, it will be reported here. For "make ready" and other permitting, budget for that is reported in 2e, Construction Permits & Other Approvals, which reflects all of the spending from the 424C budget category of Land, Structures, Rights of Way. | 74 | Percent complete is based on revised budget amount vs actual expenses, both federal funds & match funds expended (as budgeted in the 424C category of Land, Structures & Rights of Way). Incumbent utility pole owners are still slow to invoice us for make ready. | 33 | Percent complete expressed as a % of revised budget. We remain on plan. Baseline is at 100%, however, we have not had need to expend any further funds on site preparation as of 03-31-2013. | 98 | Percent complete is based on REVISED BUDGET amount vs. actual expenses. Our baseline is at 100%. | 58 | Percent complete is based on REVISED BUDGET vs. actual expenses. Network build, equipment deployment and testing work all continues as planned. Baseline plan for network build is at 100% of budget, however we have yet to purchase new leased fiber which would bring us more in line with planned budget expenditures. Through 2012 we had experienced greater productivity than plan (which has kept the overall program within budget as well). | 94 | Percent complete is based on REVISED budget for the program. Baseline is at 100%, so we are behind baseline due to wrap up of major ring segments ("middle mile" backbone). We anticipate finishing equipment deployment by 6/30/2013 | 30 | Percent complete is based on REVISED budget for the program. Baseline is at 90%. Our current percent complete is based on expended portion of budgeted amounts (both fed and match dollars). We will complete ring-wide deployments & testing by 6/30/2013. | 2013-05-31 16:13 | 2013-05-31 16:13 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2013 | Q2 | Q2 - 2013 | 10813 | 9079 | TRUE | 84 | Percent complete is based on the total actual expenditures as related to the revised budget for both federal and matching funds. Our baseline is at 100% so we are behind due to matching funds from program income now coming in, and "make ready" still to be invoiced. Our grant has received a "no cost extension" in order to complete these items. | 100 | miscellaneous & admin | Current percent complete is based on revised budget vs. actual expenditures. Total expenditures in this category amounts to less than 1% of total project. | 100 | Percent complete is based on revised budget approved in Q1 2013. Our Environmental Assessment was completed in Q1-2011. Assessment work continues in conjunction with enforcement of our Special Award Conditions related to our Environmental Protection Measures (EPMs) | 80 | Percent complete is based on revised budget. Network design initially completed in Q1 2011. Network design activities occur as needed for route optimization and EPM enforcement. | 0 | There were no new rights of way that were needed to be acquired. The project baseline was established as the physical walkouts were being conducted for the EA. It was assumed for planning purposes some new rights of way might be needed, and that these would be acquired during the walkout and EA process. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline. We do anticipate we may need one or two. As these are encountered, and budget from the 424C category of "Land, Structures, Rights of Way" is expended, it will be reported here. For "make ready" and other permitting, budget for that is reported in 2e, Construction Permits & Other Approvals, which reflects all of the spending from the 424C budget category of Land, Structures, Rights of Way. | 77 | Percent complete is based on revised budget amount vs actual expenses, both federal funds & match funds expended (as budgeted in the 424C category of Land, Structures & Rights of Way). Incumbent utility pole owners are still slow to invoice us for make ready. Baseline is at 100%, so we are behind, and have extended the project until 9/30 to resolve this. | 33 | Percent complete expressed as a % of revised budget. We remain on plan. Baseline is at 100%, however, we have not had need to expend any further funds on site preparation as of 03-31-2013. | 100 | Percent complete is based on the total actual expenditures as related to the revised budget for both federal and matching funds. Our baseline is at 100% so we are on plan. | 68 | Percent complete is based on revised budget vs. actual expenses. Network build, equipment deployment and testing work all continues as planned. Baseline plan for network build is at 100% of budget, however we have yet to purchase new leased fiber which would bring us more in line with planned budget expenditures. | 100 | Baseline is at 100%, so we are on plan. Equipment deployment is largely complete, with perhaps minor modifications needed based on network testing results. | 42 | Baseline is at 90%. Our current percent complete is based on expended portion of budgeted amounts (both fed and match dollars). We are behind in our testing, but will be completed during the extension period. In addition, testing productivity has been high as we have not found many issues requiring resolution, due to solid installation practices we followed. | 2013-08-29 17:10 | 2013-08-29 17:10 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2013 | Q3 | Q3 - 2013 | 12521 | 10699 | TRUE | 100 | Project Award Period is complete; Project is in Project Closeout period, where all final invoices and reporting will be addressed. | 100 | admin | Project Award Period is complete. | 100 | Project Award Period is complete | 100 | Project Award Period is complete | 0 | There were no new rights of way that were needed to be acquired. The project baseline was established as the physical walkouts were being conducted for the EA. | 100 | Project Award Period is complete. Construction has halted; some invoices may arrive post-9/30 for work done in September. | 100 | Project Award Period is complete | 100 | Project Award Period is complete | 100 | Project Award Period is complete. Construction has halted; some invoices will arrive post-9/30 for work done in September. | 100 | Project Award Period is complete. Construction has halted; some invoices may arrive post-9/30 for work done in September. | 100 | Project Award Period is complete. Construction has halted; some invoices may arrive post-9/30 for work done in testing. | 2014-10-07 10:41 | 2014-10-07 10:41 | 7897 | 7897 | ONECOMMUNITY | TRUE
NT10BIX5570068 | 2010 | Q3 | Q3 - 2010 | 259 | 1396 | TRUE | 0 | In the Phase 1 Environmental Assessment phase of the project | 0 | N/A | N/A | 0 | Just started the Phase 1 EA. Communicating with the Federal Preservation Officer to ensure Phase 1 EA compliance. Archaeologist is doing desktop analysis. Biologist working on site this week. | 70 | Lot selection completed in Brownsville. Lots selected in Weslaco and Edinburg, but not closed. Also assessing the middle mile route design. | 0 | Depends on completion of Phase 1 EA | 0 | Depends on completion of Phase 1 EA | 0 | Depends on completion of Phase 1 EA | 0 | Too early in the process | 0 | Too early in the process | 0 | Too early in the process | 0 | Too early in the process | 2010-10-29 16:52 | 2010-10-29 16:52 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2010 | Q4 | Q4 - 2010 | 501 | 1525 | TRUE | 1 | Still in early stages | 0 | N/A | N/A | 100 | Submitted draft EA Dec 22, 2010 | 0 | Awaiting EA Approval | 0 | Awaiting EA Approval | 0 | Awaiting EA Approval | 0 | Awaiting EA Approval | 0 | Awaiting EA Approval | 0 | Awaiting EA Approval | 0 | Awaiting EA Approval | 0 | Awaiting EA Approval | 2011-01-21 09:02 | 2011-01-21 09:02 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2011 | Q1 | Q1 - 2011 | 1509 | 2468 | TRUE | 2 | See below | 95 | Land & Buildings | Awaiting closure on three properties under contract in Brownsville, Weslaco and Edinburg | 100 | Submitted Final EA for approval on March 21, 2011 | 1 | Implemented Duct searches in AT&T service areas, Engineering at anchor institutions | 0 | Awaiting EA approval | 0 | Awaiting EA approval | 0 | Awaiting EA approval | 0 | Awaiting EA approval | 0 | Awaiting EA approval | 0 | Awaiting EA approval | 0 | Awaiting EA approval | 2011-04-27 09:58 | 2011-04-27 09:58 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2011 | Q2 | Q2 - 2011 | 2925 | 3220 | TRUE | 3 | See below | 26 | land | Closed on 3 properties under contract in Brownsville, Weslaco, and Edinburg. Initiated building design RFP with Megamorphosis | 100 | Received our FONSI on 4/8/11 | 25 | Implemented engineering at five CAI locations. Completed staking in Rio Grande City. Completed the engineering design and 50% staking on middle mile route segment from Harlingen to Brownsville. | 0 | Nothing to Report | 9 | Completed duct searches in Harlingen, Brownsville, McAllen and Edinburg. | 0 | Beginning site preparation, nearing completion in Weslaco | 0 | Fiber is scheduled for delivery every month starting in July. Purchase is being delayed until construction is scheduled. | 0 | Awaiting engineering completition | 0 | Awaiting building construction completition | 0 | Testing will commence as route segments are completed | 2011-08-04 16:57 | 2011-08-04 16:57 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2011 | Q3 | Q3 - 2011 | 4337 | 4025 | TRUE | 4 | See Below | 23 | Land & Bldg | Land is 100% complete. Closed on 3 properties under contract in Brownsville, Weslaco, & Edinburg. Costs came in under budget by about $260,000. Initiated building design RFP with Megamorphosis. | 100 | Received our FONSI on 4/8/11 | 8 | Implemented engineering at five CAI locations. Completed permitting and staking in Rio Grande City for STC & UTPA. Completed the engineering and staking on middle mile route segment from Harlingen to Brownsville. Awaiting permits. | 0 | No Budget for this item | 0 | Construction permits received for Rio Grande City. No budget dollars for this item. | 0 | Will start when building construction starts. | 0 | Fiber is scheduled for delivery every month starting in July. Purchase is being delayed until construction is scheduled. | 0 | Awaiting Engineering Completion | 0 | Awaiting Building construction completion | 0 | Testing will commence as route segments are completed | 2011-11-30 14:40 | 2011-11-30 14:40 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2011 | Q4 | Q4 - 2011 | 5013 | 4685 | TRUE | 17 | See Below | 28 | Land | Land: Purchased land in Brownsville, Weslaco, & Edinburg. Building design completed. Construction under way as soon as city permits are received. | 100 | Received our FONSI on April 8,2011 | 47 | Completed the following: Rio Grande City, Middle Mile: Harlingen-Brownsville, Brownsville-Weslaco-Hidalgo, Duct verification: Harlingen, Brownsville, McAllen, Edinburg | 0 | Nothing to Report | 0 | We have received engineering and construction permits but there are no separate budget dollars for this line item so actual dollars are not separately reported. Permits Received: Rio Grande City, Harlingen-Brownsville, Brownsville-Weslaco-Hidalgo; | 12 | Site Prep: Surveys completed for Brownsville, Weslaco, Edinburg | 92 | Purchased CO (routers) and Transport (DWDM & DC Plant) equipment. | 0 | Rio Grande City (STC & UT Pan Am) campus and middle mile around RGC under construction. No invoices received, yet. | 0 | Awaiting building construction completion | 0 | Testing will commence as route segments are completed | 2012-02-14 18:09 | 2012-02-14 18:09 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2012 | Q1 | Q1 - 2012 | 6219 | 5712 | TRUE | 53 | As described in the Performance Improvement Plan (PIP) update | 49 | Land & Building | Construction under way in Brownsville, Weslaco, & Edinburg | 100 | Received Program Office approval for supplemental EA | 47 | Completed: Rio Grande City, Brownsville to Weslaco to Hidalgo Duct verification: Harlingen, Brownsville, McAllen, Edinburg | 0 | Nothing to Report | 0 | We have received engineering and construction permits but there are no separate budget dollars for this line item so actual dollars are not separately reported. | 100 | Surveys completed for Brownsville, Weslaco, Edinburg | 98 | Purchased CO (routers) and Transport (DWDM & DC Plant) equipment. | 50 | Rio Grande City middle mile complete and campus (STC & UT Pan Am) connectivity under construction. In-kind contribution accepted. | 0 | Awaiting building construction completion | 0 | Testing will commence as route segments are completed | 2012-05-21 09:13 | 2012-05-21 09:13 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2012 | Q2 | Q2 - 2012 | 7049 | 6152 | TRUE | 79 | As described in the Performance Improvement Plan (PIP) | 85 | Land & Building | Buildings are complete | 100 | N/A | 67 | Completed Hidalgo - McAllen (West) and Hidalgo - McAllen (East) route engineering | 0 | N/A | 0 | N/A | 100 | N/A | 98 | Purchased equipment has been received | 79 | Completed Harlingen - Brownsville and Brownsville - Weslaco routes. Weslaco - Hidalgo route has achieved 97% completion. | 0 | N/A | 0 | N/A | 2012-08-13 17:28 | 2012-08-13 17:28 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2012 | Q3 | Q3 - 2012 | 8125 | 6770 | TRUE | 83 | As described in the Performance Improvement Plan (PIP) | 92 | Land & Building | N/A | 100 | N/A | 72 | Five campuses engineered | 0 | N/A | 0 | N/A | 100 | N/A | 98 | Equipment installation at POPs | 82 | No new miles deployed this quarter, IBWC issues | 0 | N/A | 0 | N/A | 2012-11-28 17:47 | 2012-11-28 17:47 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2012 | Q4 | Q4 - 2012 | 9085 | 7858 | TRUE | 84 | As described in the Performance Improvement Plan (PIP) | 92 | Land & Building | N/A | 100 | N/A | 80 | Engineering P-CAI campuses | 0 | N/A | 0 | N/A | 100 | N/A | 98 | Equipment installation at POPs | 83 | No new miles deployed this quarter, IBWC issues | 0 | N/A | 0 | N/A | 2013-02-28 14:43 | 2013-02-28 14:43 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2013 | Q1 | Q1 - 2013 | 9791 | 8431 | TRUE | 92 | N/A | 100 | Land & Building | Land and Building completed under budget | 100 | N/A | 85 | Only Edinburg and Brownsville campus sites need to be finished | 100 | N/A | 100 | N/A | 100 | N/A | 98 | N/A | 93 | N/A | 0 | All equipment installation will be done in the last quarter of project | 0 | All network testing will be done in the last quarter of project | 2013-05-17 12:01 | 2013-05-17 12:01 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2013 | Q2 | Q2 - 2013 | 11281 | 9435 | TRUE | 100 | N/A | 100 | Land & Building | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 2013-11-19 08:02 | 2013-11-19 08:02 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570069 | 2010 | Q4 | Q4 - 2010 | 985 | 2031 | TRUE | 3 | No variance from revised Baseline Plan | 0 | NA | NA | 99 | Draft EA submitted November 28th. All requested revisions to EA Draft have been addressed. EA resubmitted on 11/29/2010. | 80 | Final high level Network Design has been substantially completed. Pending any EA related mitigation requirements discovered during actual construction high level Network Design should remain unchanged throughout the remainder of the project | 0 | No variance from revised Baseline Plan (note 2c) | 0 | No variance from revised Baseline Plan (note 2c) | 0 | No variance from revised Baseline Plan (note 2c) | 0 | Equipment Procurement was scheduled to begin at the end of the current reporting period but did not occur. This was because the RFPâ€™s were not released. RFPâ€™s are 95% complete awaiting: a) Final user address verification for New IRU RFP It is anticipated that all RFPâ€™s will be posted for vendor reply by the end of the upcoming reporting period. | 0 | No variance from revised Baseline Plan (note 2c) | 0 | No variance from revised Baseline Plan | 0 | No variance from revised Baseline Plan | 2011-02-07 11:25 | 2011-02-07 11:25 | 5888 | 5888 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2011 | Q1 | Q1 - 2011 | 1947 | 2719 | TRUE | 1 | Variance from the baseline due to the delay in approval of the FONSI and the need to have approval from the Iowa Legislature to exceed our contractual spending cap for this project. With Approval of the FONSI in February and approval from the Legislature early in the 2nd quarter, equipment contracts are being finalized and equipment ordered early in the current quarter. | 0 |  | NA | 100 | EA FONSI received February 21, 2011 | 100 | No variance from baseline. | 0 | No Variance from baseline, This is lower than the projected percent for this quarter due to removal of the Decatur County build. See question 3 for further explanation. | 0 | No Variance from baseline. This is lower than the projected percent for this quarter due to removal of the Decatur County build. See question 3 for further explanation. | 0 | No Variance from baseline | 0 | Equipment RFP materially scored with testing underway in first part of second quarter. In the projections for this quarter it was expected that the FONSI approval would be forth coming in the first part of the quarter as would approval from the Iowa Legislature to exceed the codified contract limit for the term of this project. The FONSI was not received until February 21, and the Legislative approval did on occur until after the end of the current quarter. No contracts could be awarded or equipment ordered until both events had occurred. | 0 | No Variance from baseline | 0 | The FONSI was not received until February 21, and the Legislative approval for exceeding the codified contractual cap did on occur until after the end of the current quarter. No contracts could be awarded or equipment ordered until both events had occurred. These events resulted in the anticipated 5% deployment not occurring. This report shows 0%. This shortfall is expected to be made up for in the next quarter. | 0 | No Variance from baseline | 2011-05-11 17:19 | 2011-05-11 17:19 | 5888 | 5888 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2011 | Q2 | Q2 - 2011 | 3247 | 3386 | TRUE | 2 | Baseline shows 14. Variance from the baseline due to the delay in approval of the FONSI and the need to have approval from the Iowa Legislature to exceed our contractual spending cap for this project. With Approval of the FONSI in February and approval from the Legislature early in the 2nd quarter, equipment contracts are being finalized and equipment ordered early in the current quarter. | 0 |  | NA | 100 | EA FONSI received February 21, 2011, funds budgeted for EA were included in 424C Site preparation and 100% of budget expended. | 0 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Though the end of this quarter, no grant matching or Federal grant dollars were expended for Network Design. | 0 | Baseline represents expected completion of Rights of Way acquisition. No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Construction Permits etc., percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | NA; The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 1 | Baseline shows 100%. In the projections for this quarter it was expected that the FONSI approval would be forth coming in the first part of the quarter as would approval from the Iowa Legislature to exceed the codified contract limit for the term of this project. The FONSI was not received until February 21, and the Legislative approval did not occur until near the end of the current quarter. No contracts could be awarded or equipment ordered until both events had occurred. | 0 | Baseline report shows 15. Variance is due to sub-recpients still in the planning and network design phase. IRU contracts still being negotiated or services not yet turned up by end of the quarter. | 0 | No federal or ICN matching funds yet expended on equipment deployment. | 0 | No specific budget line for network testing. No federal or ICN matching funds yet expended on equipment deployment. | 2011-08-20 09:14 | 2011-08-20 09:14 | 5888 | 5888 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2011 | Q3 | Q3 - 2011 | 4209 | 3953 | TRUE | 8 | Baseline shows 28%. Variance from baseline due to carry over from issues identified in previous quarter, delays in deployment of new field technical resources and due to baseline milestones being calculated on actual work done vs. expenditures. | 0 |  | NA | 100 | EA FONSI received February 21, 2011, funds budgeted for EA were included in 424C Site preparation and 100% of budget expended. | 8 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Construction Permits etc., percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | NA The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 8 | Baseline shows 100%. Actual procurement was delayed due to late start. Variance from baseline also due to baseline milestones being calculated on actual work done versus expenditures. | 0 | Baseline report shows 13. Variance is due to sub-recpients still in the planning and network design phase. IRU contracts still being negotiated or services not yet turned up by end of the quarter. | 8 | Baseline shows 15. Variance due to delayed start and because baseline milestones being calculated on actual work done versus expenditures. | 0 | No specific budget line for network testing. No federal or ICN matching funds yet expended on equipment deployment. | 2011-11-22 10:00 | 2011-11-22 10:00 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2011 | Q4 | Q4 - 2011 | 5419 | 5106 | TRUE | 33 | Baseline shows 45%. Variance from baseline due to carry over from issues identified in previous quarter, delays in deployment of new field technical resources and due to baseline milestones being calculated on actual work done vs. expenditures. Project is ahead of what was projected for 11Q4 in the last quarterâ€™s (11Q3) PPR. | 0 |  | NA | 100 | EA FONSI received February 21, 2011, funds budgeted for EA were included in 424C Site preparation and 100% of budget expended. | 33 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Though the end of this quarter, no grant matching or Federal grant dollars were expended for Network Design. Project is ahead of what was projected for 11Q4 in the last quarterâ€™s (11Q3) PPR. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Construction Permits etc., percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | NA The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 33 | Baseline shows 100%. Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Project is ahead of what was projected for 11Q4 in the last quarterâ€™s (11Q3) PPR. | 4 | Baseline report shows 25%. Variance is due to sub-recpients still in the planning and network design phase. IRU contracts still being negotiated or services not yet turned up by end of the quarter. | 25 | No variance from baseline. | 0 | No specific budget line for network testing. No federal or ICN matching funds yet expended on equipment deployment. | 2012-02-29 17:53 | 2012-02-29 17:53 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2012 | Q1 | Q1 - 2012 | 5935 | 5567 | TRUE | 46 | Baseline shows 64%. Variance due to IRU deployment and payment taking longer than anticipated. IRUs cannot be paid under Iowa law until delivered, tested and accepted. | 0 |  | No specific budget line for network testing. | 100 | EA FONSI received February 21, 2011, funds budgeted for EA were included in 424C Site preparation and 100% of budget expended. | 44 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Construction Permits etc., percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 84 | Baseline shows 100%. Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 19 | Baseline report shows 38%. Variance is due to sub-recpients still in the planning and network design phase. IRU contracts still being negotiated or services not yet turned up by end of the quarter. | 36 | No variance from baseline. | 0 | No specific budget line for network testing. | 2012-05-07 09:13 | 2012-05-07 09:13 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2012 | Q2 | Q2 - 2012 | 6853 | 6053 | TRUE | 62 | Baseline shows 79%. Variance due to IRU deployment and payment taking longer than anticipated. IRUs cannot be paid under Iowa law until delivered, tested and accepted. | 0 |  | N/A | 100 | EA FONSI received February 21, 2011, funds budgeted for EA were included in 424C Site preparation and 100% of budget expended. | 62 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Any expenses that would be considered Network Design are included in the Site Work cost classification. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Construction Permits etc., percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | NA The Iowa Communications Network does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 85 | Baseline shows 100%. Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 40 | Baseline report shows 38%. Variance is due to sub-recpients still in the planning and network design phase. IRU contracts still being negotiated or services not yet turned up by end of the quarter. | 47 | No variance from baseline | 36 | No variance from baseline | 2012-08-03 16:20 | 2012-08-03 16:20 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2012 | Q3 | Q3 - 2012 | 7955 | 6683 | TRUE | 67 | Baseline shows 89%. Variance due to IRU deployment and payment taking longer than anticipated. IRUs cannot be paid under Iowa law until delivered, tested and accepted. | 0 |  | N/A | 100 | EA FONSI received February 21, 2011, funds budgeted for EA were included in 424C Site preparation and 100% of budget expended. | 67 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for this line time are classified in the Site Work category in the budget. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Construction Permits etc., percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | N/A. The Iowa Communications Network does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 95 | Baseline shows 100%. Variance due to equipment purchase plans evolving as described in submitted AARs. | 63 | No variance from baseline. | 60 | No variance from baseline. | 40 | No variance from baseline. | 2012-11-19 12:55 | 2012-11-19 12:55 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2012 | Q4 | Q4 - 2012 | 9125 | 7907 | TRUE | 72 | Baseline shows 95%. Variance due to IRU deployment and payment taking longer than anticipated. IRUs cannot be paid under Iowa law until delivered, tested and accepted. | 0 |  | N/A | 100 | EA FONSI received February 21, 2011, funds budgeted for EA were included in 424C Site preparation and 100% of budget expended. | 72 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Network Design expenses are included in the Site Work category in the budget. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Construction Permits etc., percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | N/A. The Iowa Communications Network does not have activities that meet the definition of Site Preparation per the Baseline instructions. BBaseline shows 100%. Variance due to equipment purchase plans evolving as described in submitted AARs. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 76 | Baseline shows 100%. Variance due to equipment purchase plans evolving as described in submitted AAR's and the remaining IRU's to be completed. The percentage recorded in previous PPR's only considered physical equipment and did not taken into account the 15-year IRU's. | 75 | No variance from baseline. | 72 | No variance from baseline. | 60 | No variance from baseline. | 2013-03-06 08:43 | 2013-03-06 08:43 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2013 | Q1 | Q1 - 2013 | 9775 | 8422 | TRUE | 81 | Baseline shows 97%. Variance due to IRU deployment and payment taking longer than anticipated. IRUs cannot be paid under Iowa law until delivered, tested and accepted. | 0 |  | N/A | 100 | EA FONSI received February 21, 2011, funds budgeted for EA were included in 424C Site preparation and 100% of budget expended. | 93 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Completion percentage is reported as equal to the percentage of sites remaining to be engineered and designed which on average should be equal to the dollars spent. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | Baseline represents expected completion of rights of way acquisition. No separate budget for Construction Permits etc., percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | N/A. The Iowa Communications Network does not have activities that meet the definition of Site Preparation per the Baseline instructions. BBaseline shows 100%. Variance due to equipment purchase plans evolving as described in submitted AARs. reakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 98 | Baseline shows 100%. Variance due to equipment purchase plans evolving as described in submitted AARs. | 80 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Budget items included in this category are expenditures on completed IRU's and reported sub-recipient construction. | 86 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. This percentage equals the dollars spent on equipment actually deployed as of the end of the 1st quarter of 2013. | 86 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. This percentage equals the dollars spent on equipment actually deployed as of the end of the 1st quarter of 2013. | 2013-05-16 15:25 | 2013-05-16 15:25 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2013 | Q2 | Q2 - 2013 | 11839 | 10015 | TRUE | 100 | The ICN dropped 283 total CAI's from ICN's original planned list of 3,101. A total of 2,818 CAI's were served through the project activities resulting in 95% spent. | 100 | N/A | N/A | 100 | EA FONSI received February 21, 2011, funds budgeted for EA were included in 424C Site preparation and 100% of budget expended. | 100 | The ICN dropped 283 total CAI's from ICN's original planned list of 3,101. A total of 2,818 CAI's were served through the project activities resulting in 95% spent. | 100 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 100 | No separate budget for Construction Permits etc., percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 100 | N/A. The Iowa Communications Network does not have activities that meet the definition of Site Preparation per the Baseline instructions. The breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 100 | The ICN dropped 283 total CAI's from ICN's original planned list of 3,101. This resulted in total spending on equipment being $988,727 less than budgeted. | 100 | No variance from baseline. | 100 | The ICN dropped 283 total CAI's from ICN's original planned list of 3,101. This resulted in total spending on equipment being $988,727 less than budgeted. | 100 | The ICN dropped 283 total CAI's from ICN's original planned list of 3,101. | 2014-02-19 12:52 | 2014-02-19 12:52 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570070 | 2010 | Q4 | Q4 - 2010 | 1009 | 2056 | TRUE | 3 | Overall Project is on target compared against our baseline. | 58 |  | Other is 6% behind baseline projections. Federal Compliance Manager position ramped up during this period more slowly than expected and costs charged to the project were lower than expected. | 100 | While our final has not been submitted, expenditures are 11% ahead of the baseline projections. MassBroadband 123 handed in draft EA and conducted consultations ahead of schedule. We have also had additional SHPO work and route modifications to avoid environmental impacts. | 20 | Network Design is on target compared against our baseline. | 8 | Rights of Way is 4% behind baseline projections. MassBroadband 123 hired a Field Data Collection firm to survey poles. While surveying work has begun, it has been a bit slower than expected due to inclement weather. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-08 18:01 | 2011-02-08 18:01 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2011 | Q1 | Q1 - 2011 | 2273 | 2882 | TRUE | 11 | 1% behind Overall Project projection for the quarter, mainly due to delays in field data collection that were caused by the unusually severe weather and have slightly delayed pole license application and the associated fees | 91 |  | 23% ahead of projection, largely due to outside consultants and legal counsel involvement with agreement negotiation and procurement process. | 100 | Completed as planned. Construction has not yet begun, so monitoring has not yet begun. Compliance requirements with environmental mitigation was included in the Design Build RFP and the Owner's Project Manager will oversee this work. | 34 | 4% ahead of projection, largely due to the majority of the Owner's Project Manager consulting costs going towards Network Design | 10 | 17% behind projection, largely due to the aforementioned delay in field data collection and the pole license application process. With weather improved, contractor is expected to be back on track for next quarter | 0 | 1% behind projection. Both environmental and non-environmental permitting are gearing up in preparation of Design Builder on-boarding, Make Ready work has been delayed due to previously mentioned delay in Field Data Collected. Expected to improve for next quarter | 0 | On par with last quarter's PPR projections and baseline. | 0 | On par with last quarter's PPR projections and baseline. | 12 | 2% behind projection. Expenditures are representative of the I-91 portion of the build. Consulting costs from this category were allocated to the Network Design category for this portion of the project. As a result, Network Build is 2% behind, while Network Design is 4% ahead. This is expected to even out as construction approaches and commences. | 0 | On par with last quarter's PPR projections and baseline. | 0 | On par with last quarter's PPR projections and baseline. | 2011-05-24 10:50 | 2011-05-24 10:50 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2011 | Q2 | Q2 - 2011 | 3119 | 3317 | TRUE | 14 | Tracking very closely with budget projections, 2% variance under baseline for cumulative reasons set forth below in this section. | 94 |  | Ahead on percentage by 20%, however; there were no significant expenditures from this category this quarter which aligns with PPR projections and baseline. Costs included in the Other category are as follows: â€¢ Federal Compliance Staff related costs â€¢ BTOP Non-Construction Staffing and Other costs (i.e. NTIA Conference travel, non-construction BTOP related staff time) â€¢ Application and Post Application Submission Costs as allowed under the NOFA and included in our approved budget including staffing and professional services â€¢ Staff, Consulting and Legal Costs associated with the Network Operator Procurement | 100 | Complete. Construction has not begun, so monitoring has not yet begun. Compliance requirements with environmental mitigation was included in the Design-Build RFP and the owners project manager will oversee this work. | 65 | Ahead on percentage spent by 29%, due to front-loaded costs in areas of Owner, Owner's Project Manager and Design Build procurement which has recently completed. Anticipated that variance will close next quarter | 27 | Behind on percentage by 16%. This remains consistent with last quarter. Field data collection is close to complete and make ready applications will continue to gain momentum | 2 | Behind on percentage by 4%. Environmental and non-environmental permits applications withheld until final design achieved in collaboration with Design Builder. Make ready work will continue to ramp up and gains will be made on the variance. | 0 | On par with last quarter's PPR projections and baseline | 0 | On par with last quarter's PPR projections and baseline | 12 | Behind on percentage by 5%. Expenditure is representative of the I-91 portion of the build. | 0 | On par with last quarter's PPR projections and baseline | 0 | On par with last quarter's PPR projections and baseline | 2011-08-16 14:16 | 2011-08-16 14:16 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2011 | Q3 | Q3 - 2011 | 3973 | 3825 | TRUE | 22 | Tracking very closely to budget projections, 4% variance under baseline due to cumulative reasons set forth below in this section. | 96 |  | Ahead on percentage by 19%, however; there were no significant expenditures from this category this quarter which aligns with PPR projections and baseline. Costs included in the Other category are as follows: â€¢ Federal Compliance Staff related costs â€¢ BTOP Non-Construction Staffing and Other costs (i.e. NTIA Conference travel, non-construction BTOP related staff time) â€¢ Application and Post Application Submission Costs as allowed under the NOFA and included in our approved budget including staffing and professional services â€¢ Staff, Consulting and Legal Costs associated with the Network Operator Procurement | 100 | Complete. Compliance requirements with environmental mitigation was included in the Design-Build RFP and the owner's project manager will oversee this work. | 95 | Ahead on percentage by 55%, due to front-loaded costs in areas of Owner, Owner's Project Manager, Design Builder and other consultants as network design progressed. Costs are now projected to be higher than were projected in original NTIA budget | 95 | Ahead on percentage by 36%. Make ready application submissions have picked up and pole survey work has increased over the past quarter to advance this category ahead of schedule. | 13 | Behind on percentage by 8%. Utility companies are still ramping up on delivering costs and estimates for make ready, so expenditures continue to lag slightly behind. Expected to get closer to baseline in the next quarter | 0 | Behind on percentage by 25%. The expenditures were budgeted for this past quarter; however, the schedule has been pushed out to next quarter. | 0 | On par with last quarter's PPR projections | 15 | Behind on percentage by 12%. Slower than expected Design Build ramp-up and make ready construction work by utilities have led to less expenditures to date than initially planned. Additionally, some costs included in the baseline report under this category are being captured under Network Design. | 0 | On par with last quarter's PPR projections and baseline. | 0 | On par with last quarter's PPR projections and baseline. | 2011-11-10 16:49 | 2011-11-10 16:49 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2011 | Q4 | Q4 - 2011 | 5159 | 4824 | TRUE | 35 | Tracking closely to budget projections; 3% variance under baseline due to cumulative reasons set forth below | 97 |  | Expected to be ahead on percentage by 17%, however; no significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs included in approved budget â€¢ Staff, Consulting and Legal Costs with procurements | 100 | Complete and at baseline projection. Compliance requirements with environmental mitigation included in Design-Build RFP and the owner's project manager will oversee work | 100 | Ahead on percentage by 52%, due to front-loaded focus of Owner, Owner's Project Manager, Design Builder and other consultants as network design progressed. Costs are now projected to be high than the original NTIA budget | 100 | Ahead on percentage by 25%. Make ready application submissions have picked up and pole survey work has nearly completed | 36 | Tracking closely to projections; 1% under baseline. Consistent with expectations | 0 | Behind on percentage by 50% due to activities now being projected to occur in Year2 Quarter4. Costs will be less than baseline projection. | 26 | Ahead on percentage by 13%. Orders of equipment and materials were procured and paid for earlier than scheduled due to industry-wide lengthened lead times on delivery. | 20 | Behind on percentage by 20%. Design-Build ramp-up and slower-than-expected make ready construction work by utilities has led to less expenditures to date than planned. Additionally, some costs included in the baseline report under this category are being captured under Network Design | 0 | Behind on percentage by 13% due to equipment deployment costs starting later than planned | 0 | On par with baseline | 2012-02-21 09:54 | 2012-02-21 09:54 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2012 | Q1 | Q1 - 2012 | 6035 | 5617 | TRUE | 48 | Tracking closely to budget projections; 4% under baseline to to cumulative reasons set forth below | 100 |  | Ahead on budgeted expenditures by 17% due to costs including: -Federal Compliance Staff -BTOP Non-Construction Staffing -Application and Post Application Submission Costs included in approved budget -Staff, Consulting and legal costs with agreements | 100 | Complete and at baseline projection. Compliance requirements with environmental mitigation included in Design-Build RFP and the Owner's Project Manager will oversee work | 100 | Ahead on budgeted expenditures by 43%, due to front-loaded focus of Owner's Project Manager, Design Builder and other consultants as network design progressed. Costs are now projected to be higher than the original NTIA budget | 100 | Ahead on budgeted expenditures by 9%. Pole survey work has completed and make ready applications are nearly complete. | 68 | Ahead on budgeted expenditures by 15% due to high make ready costs during quarter. Cost are projected to be higher than original NTIA budget. | 0 | Behind on budgeted expenditures by 75% due to activities now being projected to occur in Year 2 Quarter 4. Costs will be less than baseline projection. | 42 | Ahead on budgeted expenditures by 4%. Equipment and materials were procured and paid for earlier than schedule due to industry-wide lengthened lead times on delivery. | 22 | Behind on budgeted expenditures by 30%. Design Build ramp-up and slower-than-expected. Make ready construction work by utilities has led to less expenditures to date than planned. Additionally, some costs included in the baseline report under this category are being captured under Network Design. | 21 | Behind on budgeted expenditures by 17% due to equipment deployment starting later than planned | 0 | On par with baseline | 2012-05-11 10:14 | 2012-05-11 10:14 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2012 | Q2 | Q2 - 2012 | 7079 | 6167 | TRUE | 68 | Throughout this report, we are calculating Percent Complete with reference to the approved NTIA budget. Costs are now projected to be higher than that approved budget, and MTC has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the approved NTIA budget. Tracking closely to budget projections; 1% ahead of baseline due to cumulative reasons set forth below | 100 |  | Ahead on budgeted expenditures by 12% due to costs including: -Federal Compliance Staff -BTOP Non-Construction Staffing -Application and Post Application Submission Costs included in approved budget -Staff, Consulting and legal costs with agreements | 100 | Complete and at baseline projection. Compliance requirements with environmental mitigation included in Design-Build RFP and the Owner's Project Manager will oversee work | 100 | Ahead on budgeted expenditures by 33%, due to front-loaded focus of Owner's Project Manager, Design Builder and other consultants as network design progressed. | 100 | Ahead on budgeted expenditures by 2%. Pole survey work has completed and make ready applications are nearly complete. | 100 | Ahead on budgeted expenditures by 32% due to high make ready costs during quarter. | 16 | Behind on budgeted expenditures by 84% due to costs being allocated in other categories. Costs will be less than baseline projection. | 70 | Tracking closely with budgeted expenditures; 3% behind expenditures | 31 | Behind on budgeted expenditures by 34%. Design Build ramp-up and slower-than-expected Make ready construction work by utilities has led to less expenditures to date than planned. Additionally, some costs included in the baseline report under this category are being captured under Network Design. | 100 | Ahead on budgeted expenditures by 25% due to higher costs and increased inside plant installation activities. | 0 | On par with baseline budget | 2012-08-15 14:20 | 2012-08-15 14:20 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2012 | Q3 | Q3 - 2012 | 7961 | 6687 | TRUE | 79 | Throughout this report, we are calculating Percentage Complete with reference to the approved NTIA budget. Costs are now projected to be higher than that approved budget, and MTC has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the approved NTIA budget. Tracking closely to budget projections; 6% behind baseline due to cumulative reasons set forth below. In comparison to the new project budget, 64% of the budget has been spent. | 100 |  | Ahead on budgeted expenditures by 8% due to costs including: -Federal Compliance Staff -BTOP Non-Construction Staffing -Application and Post Application Submission Costs included in approved budget -Staff, Consulting and legal costs with agreements | 100 | Complete and at baseline projection. Compliance requirements with environmental mitigation included in Design-Build RFP and the Owner's Project Manager will oversee work | 100 | Ahead on budgeted expenditures by 24%, due to front-loaded focus of Owner's Project Manager, Design Builder and other consultants as network design progressed | 100 | On par with baseline budget as pole survey work and make ready application costs are winding down | 100 | Ahead on budgeted expenditures by 21% due to high make ready costs offset by additional matching funds from the Commonwealth of Massachusetts | 31 | Behind on budgeted expenditures by 69% due to costs being allocated in other categories. Costs will be less than baseline projection | 98 | On par with baseline budget | 42 | Behind on budgeted expenditures by 44%. Design Build ramp-up and slower-than-expected make ready construction work by utilities has led to less expenditures to date than planned. Some work was also delayed while MTC sought NTIA approval of route and installation type changes. Additionally, some costs included in the baseline report under this category are being captured under Network Design | 100 | On par with baseline budget | 0 | Behind by 22% due to the aforementioned construction delays that have subsequently delayed the onset of testing. | 2012-11-19 16:55 | 2012-11-19 16:55 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2012 | Q4 | Q4 - 2012 | 9007 | 7781 | TRUE | 88 | Throughout this report, we are calculating Percentage Complete with reference to the approved NTIA budget. Costs are now projected to be higher than that approved budget, and MTC has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the approved NTIA budget. Tracking closely to budget projections; 3% behind baseline due to cumulative reasons set forth below. In comparison to the new project budget, 69% of the budget has been spent. | 100 |  | Ahead on budgeted expenditures by 5% due to costs including: -Federal Compliance Staff -BTOP Non-Construction Staffing -Application and Post Application Submission Costs included in approved budget -Staff, Consulting, and legal costs | 100 | Complete and at baseline projection. Compliance requirements with environmental mitigation included in Design-Build RFP and the Owner's Project Manager will oversee work | 100 | Ahead on budgeted expenditures by 15%, due to front-loaded focus of Owner's Project Manager, Design Builder and other consultants as network design progressed | 100 | On par with baseline budget as pole survey work and make ready application costs are essentially complete | 100 | Ahead on budgeted expenditures by 10% due to high make ready costs offset by additional matching funds from the Commonwealth of Massachusetts | 42 | Behind on budgeted expenditures by 58% due to costs being allocated in other categories. Costs will be less than baseline projection | 100 | Ahead on budgeted expenditures by 1%, tracking closely to baseline projections | 54 | Behind on budgeted expenditures by 37%. Design Build ramp-up and slower-than-expected make ready construction work by utilities has led to less expenditures to date than planned. Some work was also delayed while MTC sought NTIA approval of route and installation type changes. Additionally, some costs included in the baseline report under this category are being captured under Network Design | 100 | On par with baseline budget | 2 | Behind by 42% due to the aforementioned construction delays that have subsequent delayed the anticipated testing schedule | 2013-02-27 11:23 | 2013-02-27 11:23 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2013 | Q1 | Q1 - 2013 | 9889 | 8485 | TRUE | 100 | Throughout this report, we are calculating Percentage Complete with reference to the approved NTIA budget. Costs are now projected to be higher than that approved budget, and MTC has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the approved NTIA budget. In comparison to the new project budget, 80% of the budget has been spent. | 100 |  | Ahead on budgeted expenditures by 2% due to costs including: -Federal Compliance Staff -BTOP Non-Construction Staffing -Application and Post Application Submission Costs included in approved budget -Staff, Consulting, and legal costs Costs will be offset by additional matching funds from the Commonwealth of Massachusetts | 100 | Complete and at baseline projection. Compliance requirements with environmental mitigation included in Design-Build RFP and the Owner's Project Manager will oversee work | 100 | Ahead on budgeted expenditures by 5%, due to front-loaded focus of Owner's Project Manager, Design Builder and other consultants as network design progressed and due to aforementioned higher costs | 100 | On par with baseline budget as pole survey work and make ready application costs are essentially complete | 100 | On par with baseline percentage; high costs offset by additional matching funds from the Commonwealth of Massachusetts | 58 | Behind on budgeted expenditures by 42% due to costs being allocated in other categories. Costs will be less than baseline projection | 100 | On par with baseline percentage; high costs offset by additional matching funds from the Commonwealth of Massachusetts | 72 | Behind on budgeted expenditures by 24%. Design Build work has caught up with delays to close gap of expenditures, while some work continues to be delayed while MTC awaits NTIA approval of route and installation type changes. Additionally, some costs included in the baseline report under this category are being captured under Network Design | 100 | On par with baseline percentage; high costs offset by additional matching funds from the Commonwealth of Massachusetts | 18 | Behind by 49% due to the aforementioned construction delays that have subsequently delayed the anticipated testing schedule | 2013-05-23 16:07 | 2013-05-23 16:07 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2013 | Q2 | Q2 - 2013 | 10779 | 9059 | TRUE | 100 | In this section, we are calculating Percentage Complete with reference to the approved NTIA budget. Actual Costs are now 114% of the approved budget. MassTech has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the approved NTIA budget. In comparison to the new project budget, 90% of the budget has been expended | 100 |  | Costs included in this category are: -Federal Compliance Staff -BTOP Non-Construction Staffing -Application and Post Application Submission Costs included in approved budget -Staff, Consulting, and legal costs Costs will be offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 125% of the baseline budget. | 100 | Compliance requirements with environmental mitigation included in Design-Build RFP and the Owner's Project Manager will oversee work. Complete and actual costs is 159% of baseline budget. | 100 | Some costs included in Network Build are now categorized under Network Design. High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs is 258% of baseline budget. | 100 | Pole survey work and make ready application costs are essentially complete. Actual costs are 133% of baseline budget. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 137% of the baseline budget | 90 | Behind on budgeted expenditures by 10% due to costs being allocated in other categories. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 130% of the baseline budget | 85 | Behind on budgeted expenditures by 15%; some costs included in the baseline report under this category are being captured under Network Design | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 334% of the baseline budget | 100 | Testing for CAIs, POIs, and fiber segments in full gear across the network. High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 129% of the baseline budget | 2013-08-28 09:06 | 2013-08-28 09:06 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2013 | Q3 | Q3 - 2013 | 11411 | 9524 | TRUE | 100 | In this section, we are calculating Percentage Complete with reference to the approved NTIA budget. Actual Costs are now 119% of the approved budget. MassTech has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the approved NTIA budget. In comparison to the new project budget, 95% of the budget has been expended. | 100 |  | Costs included in this category are: -Federal Compliance Staff -BTOP Non-Construction Staffing -Application and Post Application Submission Costs included in approved budget -Staff, Consulting, and legal costs Costs will be offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 129% of the baseline budget. | 100 | Compliance requirements with environmental mitigation included in Design-Build RFP and the Owner's Project Manager will oversee work. Complete and actual costs are 159% of baseline budget. | 100 | Some costs included in Network Build are now categorized under Network Design. High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 258% of baseline budget. | 100 | Pole survey work and make ready application costs are complete. Actual costs are 132% of baseline budget. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 139% of the baseline budget. | 100 | Although some of these costs have been allocated to other categories, actual costs are higher than budgeted. Actual costs are 101% of the baseline budget. Site preparation is essentially complete. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 135% of the baseline budget. | 91 | Behind on budgeted expenditures by 9%; some costs included in the baseline report under this category are being captured under Network Design. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 334% of the baseline budget. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 149% of the baseline budget. | 2013-11-26 17:25 | 2013-11-26 17:25 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2013 | Q4 | Q4 - 2013 | 12043 | 10203 | TRUE | 100 | In this section, we are calculating Percentage Complete with reference to the approved NTIA budget. Actual Costs are now 122% of the approved budget. MassTech has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the approved NTIA budget. In comparison to the new project budget, 97% of the budget has been expended. | 100 |  | Costs included in this category are: -Federal Compliance Staff -BTOP Non-Construction Staffing -Application and Post Application Submission Costs included in approved budget -Staff, Consulting, and legal costs Costs will be offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 132% of the baseline budget. | 100 | Compliance requirements with environmental mitigation included in Design-Build RFP and the Owner's Project Manager will oversee work. Complete and actual costs are 159% of baseline budget. | 100 | Some costs included in Network Build are now categorized under Network Design. High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 259% of baseline budget. | 100 | Pole survey work and make ready application costs are complete. Actual costs are 132% of baseline budget. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 140% of the baseline budget. | 100 | Although some of these costs have been allocated to other categories, actual costs are higher than budgeted. Actual costs are 103% of the baseline budget. Site preparation is essentially complete. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 139% of the baseline budget. | 95 | Behind on budgeted expenditures by 5%; some costs included in the baseline report under this category are being captured under Network Design. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 334% of the baseline budget. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 161% of the baseline budget. | 2014-04-16 14:15 | 2014-04-16 14:15 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570071 | 2010 | Q4 | Q4 - 2010 | 479 | 1506 | TRUE | 4 | There are currently no variances. | 0 |  | N/A | 70 | This was delayed based on a delay in getting the award posted in GOL so that Zayo could accept our award. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-01-11 19:35 | 2011-01-11 19:35 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570071 | 2011 | Q1 | Q1 - 2011 | 2361 | 2926 | TRUE | 2 | Zayo is ahead of our baseline by 2%. We are ahead of our baseline but behind of last quarters projections because we did not receive our FONSI yet. | 0 |  | N/A | 95 | N/A | 10 | We are ahead of our baseline but behind of last quarters projections because we did not receive our FONSI yet. | 0 | N/A | 0 | N/A | 0 | We are ahead of our baseline but behind of last quarters projections because we did not receive our FONSI yet. | 0 | We are ahead of our baseline but behind of last quarters projections because we did not receive our FONSI yet. | 0 | We are ahead of our baseline but behind of last quarters projections because we did not receive our FONSI yet. | 0 | We are ahead of our baseline but behind of last quarters projections because we did not receive our FONSI yet. | 0 | We are ahead of our baseline but behind of last quarters projections because we did not receive our FONSI yet. | 2011-05-26 18:45 | 2011-05-26 18:45 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570071 | 2011 | Q2 | Q2 - 2011 | 3183 | 3352 | TRUE | 3 | This is 1.7% behind our baseline. This is because of delays in permitting which has delayed materials purchasing. | 0 |  | N/A | 100 | This is 100% ahead of our baseline. | 40 | This is 40% ahead of our baseline. Zayo's engineering contractor has been working hard and fast. | 3 | This is 3% ahead of our baseline. | 3 | This is 3% ahead of our baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-08-17 22:57 | 2011-08-17 22:57 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570071 | 2011 | Q3 | Q3 - 2011 | 4127 | 3910 | TRUE | 17 | This is 4.1% ahead of our baseline. This is based on our ability to get our engineers in the field quicker than expected after receiving our environmental assessment finding of no significant impact. | 0 |  | N/A | 100 | This is 5% ahead of our baseline. This is based on a quicker response from the agencies than expected. We expected that we may have had issues getting approval from some agencies that would have taken longer. | 60 | This is 40% ahead of schedule based on receipt of or environmental assessment finding of no significant impact. | 0 | This is on target. This corrects an error on our last report. | 1 | This is 1% ahead of our baseline. This also corrects an error on our last report. | 9 | This is on target. | 72 | This is 63% ahead of schedule based on early request for proposal process and award selection and award. | 5 | This is 4% behind schedule. This is because of issues with pole providers as discussed below in 3. Zayo is looking at a work around to void excessive pole change out cost. | 0 | This is 9% behind our baseline. This is because of network build issues sited above in 2h. | 0 | This is 5% behind our baseline. This is because of the network build issues sited above in 2h. | 2011-11-18 11:43 | 2011-11-18 11:43 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570072 | 2010 | Q4 | Q4 - 2010 | 1049 | 2089 | TRUE | 1 | No Variance | 100 | Pre-Award Acceptance | Other items included in the Baseline report included Project Management and Administration Reporting at 10% complete, Contractual Solution Sales at 0% and Operation Support Systems at 0%. | 80 | A ten percent negative variance is reported based on the number of outstanding consultations required with agencies prior to finalization of the Environmental Assessment Report at the end of 2010. Additional time and resources will be required in January for follow-up with agencies in order to complete consultations in a timely manner. | 9 | A seven percent positive variance is reported due to involvement of Com Net Route Design and Permitting Firm in the Environmental Assessment. This involvement allowed the Route Design Firm to pull ahead certain field work items associated with the project by conducting route drive-outs as part of the Environmental Assessment. | 1 | A one percent negative variance is reported as much of the Right-of-Way work will require review of the FONSI prior to finalizing | 1 | A one percent negative variance is reported as much of the Right-of-Way work will require review of the FONSI prior to finalizing | 0 | No Variance | 2 | A one-percent positive variance is reported. Com Net transferred four CISCO 76XX series Ethernet Switch/Routers (3-7606s and one 7609) to the GigEPAC project as part of its in-kind commitment. The four Ethernet Switch/Routers transferred were for the sites Watch Tower, Worthington, Columbus and Lima as so denoted in the GigEPAC application project budget detail. The book value was greater than that reported in the application based on the actual line card population being more extensive than that used for the application budget. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-02-10 14:39 | 2011-02-10 14:39 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2011 | Q1 | Q1 - 2011 | 2289 | 2890 | TRUE | 2 | Negative Variance of 8% due to Com Net not yet receiving its initial FONSI and Com Net activities being limited to administrative, project planning, bid management, contract management, environmental assessment, appraisals and limited equipment/materials purchasing. In order to effectively manage cash flow Com Net is attempting to manage the supply of materials on a just-in-time basis to avoid excessive storage requirements and aging of inventory. | 100 | Pre-Award Acceptance & Applications | Other items included in the Baseline report included Project Management and Administration Reporting at 22% complete, Contractual Solution Sales at 0% and Operation Support Systems at 1%. | 100 | Work was completed as of the end of March with Final EA just dependent on inclusion of consultation and findings as attachments to the document based on guidelines. EA Consultant Expense versus budget ran $25,000 over due to extended time period associated with agency consultations and report preparation. The cost overrun on the EA Consultant was offset through favorable performance to budget on Route Design Environmental Assessment support on route drive-outs and desk reviews as well as on EA Assessment Consultant procurement in Request for Proposal (RFP) development and Bid Management. The net effect was that performance of actual EA expenses were $5,077.67 over or 104% of the 6-Month Budget . | 10 | No Variance against baseline and 7% unfavorable to prior quarter projections. Com Net's Q4 Performance Progress Report (PPR) percent complete projections were based on Final Environmental Assessment (EA) Report being issued in January and a construction start date of March 2011. Com Net managed progress in order to have for construction designs ready and permits/Right-of-Ways (RoW)acquired ahead of receipt of the Finding of No Significant Impact (FONSI) on the environmental assessment to allow us to immediately commence with construction on receipt of FONSI and lifting of the Special Award Conditions (SAC) in order to avoid further slippage against our baseline and begin closing the gap against the baseline/time line. This effort to get ahead on permits and Right-of-Way was balanced against the fact that engineering still had to review the design against the final EA to ensure all environmentally sensitive areas, endangered species, cultural resources and listed avoidance commitm | 11 | Positive Variance of 2%. Most Road Right of Way applications are non-fee based. Progress in this area is primarily judged against receipt of approval on all applications for occupancy in Road Right of Way including crossing of non-navigable and navigable waterways. At the end of March for the Network Design completed according to 2c only the applications with the Core of Engineer for the Right of Way across navigable/non-navigable waterways were outstanding. Com Net need to watch limitation on approvals based on construction commencing and being completed within a defined time frame from date of issue. If application/approval process gets to far in front of construction process before receipt of FONSI it could result in duplication of effort, time and expenses. | 3 | Negative Variance of 6%. Many permits and occupancy agreements require work to be completed within 30-120 days of issuance depending on the Authority Having Jurisdiction. Given this fact and that Com Net has not yet received its initial FONSI and had no definitive time line by which it would be issued, permits/RoW applications are being managed on a Just-in-Time basis dependent on time frame by which work has to be completed to avoid duplication of permitting expenses. Com Net is also selecting and releasing routes at this time that involve a minimal number of RR crossings, pole attachments and lease of third party conduit. Com Net is implementing avoidance as it relates to private easements especially associated with RR crossings. | 0 | Negative Variance of 11%. Com Net has not received its initial FONSI due to delays in completion of consultations with authorities having jurisdiction therefore no progress has been made in this area | 2 | Negative Variance of 18%. For cash flow purposes Com Net is managing equipment supply on a Just in Time Basis. Com Net is also not authorizing sub-recipients to complete any transfers until finalization of the FONSI and upgrade of agreement from binding Memorandum of Understanding (MoU) to Sub-Recipient Contract. No additional equipment received in March, only POs initiated for Outside Plant Construction Materials and for Upgrade Cards for equipment in Worthington, OH made part of the project in 2010. Com Net's FONSI was still outstanding at the time of issue. Equipment and Materials are not considered procured until received into warehouse and accepted. | 0 | Negative Variance of 1%. Com Net has not received its initial FONSI due to delays in completion of consultations with authorities having jurisdiction therefore no progress has been made in this area | 0 | Negative Variance of 10%. Com Net has not received its initial FONSI due to delays in completion of consultations with authorities having jurisdiction therefore no progress has been made in this area | 0 | Negative Variance of 1%. Com Net has not received its initial FONSI due to delays in completion of consultations with authorities having jurisdiction therefore no progress has been made in this area | 2011-05-24 23:23 | 2011-05-24 23:23 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2011 | Q2 | Q2 - 2011 | 3253 | 3389 | TRUE | 8 | Negative Variance of 17% to baseline and 3% to 2011Q2 forecast. At the close of June 30, 2011, Com Net had unpaid invoices that, when taken into account, put the overall completion at 13%. The variance is driven by two primary factors, which were receipt of FONSI after May 1, 2011 and then weather delays upon receipt of FONSI. Com Net feels confident that it is back on schedule with the forecast for the upcoming quarter based on invoices in hand but not yet paid for work completed making them unliquidated obligations for June month end reporting. The primary invoices received, but not paid, were in the area of permits and other approvals, Network Construction, Network Inspection and Equipment Procurement. | 100 | Pre-Award Acceptance & Application | Other items included in the Baseline report are Project Management and Administration at 38% complete for a positive variance of 9% to baseline and 11% to Q3 projection, which is simply due to Com Net focusing on administrative and project management systems during the time frame it could not undertake ground disturbing activities. Contractual Solution Sales at 5% completion which is a negative variance of 1% to baseline and a positive variance of 2% versus 2011Q2 projections. Operation Support Systems at 11% completion for a negative variance versus baseline of 22% and a negative variance versus 2011Q2 projections of 9%. This is a result of actual transfer value of Com Net billing system being less than originally projected and delays in deploying the CYAN CYMS monitoring system, which was a management decision based on the delays in equipment deployment. | 100 | Completed in 2011Q2 from a budget and work perspective and confirmed through receipt of FONSI in May 2011. In the event a design modification requires services of Com Net's environmental assessment consultant, such costs shall be recorded and tracked with Network Design. | 25 | Positive Variance of 3% to Baseline and negative 3% to 2011Q2 projections. This was driven, again, due to the delays encountered in the receipt of FONSI and weather causing construction activities not to commence until June 8 , 2011. This was a balancing act to avoid permits being received too far in advance of planned construction especially in areas where Com Net is required to make a deposit and is given 90 days from the permit approval date until construction must be completed to avoid forfeiture of deposit. | 19 | Negative 2% Variance versus baseline and Negative 4% Variance versus 2011Q2 Projections. Com Net is redirecting resources from permit application process to follow-up with Authorities Having Jurisdiction (AHJs) to pursue issuing of permits. Prior to receiving a FONSI, Com Net was allowing AHJ to issue permits without follow-up and specifying a desired due date. With the FONSI in hand, Com Net is now utilizing a follow-up program to reduce the cycle time from application to receipt of permit primarily with cities/village and county authorities, as well as in some areas with the State of Ohio and Army Core of Engineers. | 6 | Negative Variance of 28% to baseline and no variance to 2011Q2 projections. Com Net has encountered a few Authorities Having Jurisdiction that are requiring a deposit and ninety-day completion time frames, which is limiting Com Net's ability to work significantly ahead on obtaining permits in certain counties/communities as originally planned. This will be accounted for by adjusting our plan to increase efforts on post applicable permit follow-up status to reduce cycle times. In addition, as originally projected, Com Net will see increased expenses as construction commences along the I-75 corridor due to the increased number of railroad crossings, pole attachments and the need to address other obstructions. This increased expense will close the variance as Com Net's original baseline percent complete was heavily weighted based the number of route miles for which permits have been secured rather than the method used for this performance progress reporting, which is based on the | 0 | Negative Variance of 42% versus baseline and no variance against 2011Q2 projections. Com Net is intentionally directing resources away from this area based on a critical path method of project management to focus on long lead time cable placement construction activities. Com Net is, also, using this time frame to evaluate options to utilize existing facilities that could be equipped to be carrier class Points-of Presence (PoPs) or that are in the process of being constructed by others at tower sites. Com Net will increase activity in the area as construction of fiber routes moves to segments that involve such planned sites and Com Net prepares to initiate equipment deployment in September. | 20 | Negative variance of 6% versus baseline and a negative variance of 5% versus 2011Q2 forecast. The procurement of equipment is being delayed by approximately ninety days as Com Net conducts a power audit at existing Points-of-Presence (PoPs) and delays deployment at new sites to coincide with cable placement operations. Com Net has limited controlled environment storage space for incoming electronics so inventory is committed to, but held at, the manufacturers facilities. Com Net will release equipment for shipment in September as the existing nine units in inventory are deployed for installation. | 2 | Negative 10% variance versus baseline and a negative 3% variance versus 2011Q2 projections. The original 2011Q2 projection was based on receipt of FONSI the beginning of May and commencement of construction by mid May. Due to delays in receipt of FONSI and weather delays, construction didn't commence until June 8th; therefore, invoices for construction were still outstanding as of June end of month. The unknown date for receiving the FONSI and the weather resulted in a delay in the crew ramp-up on the job site. The month of June was used as a ramp-up month. Com Net is updating its moderate projections for cable placement progress in the upcoming quarter to be at 5.0 miles per week from July through August 7th, 6.5 to 7.5 miles per week from August 8th through September 18th and 8.5 to 9.5 miles per week from September 19th forward. The original projections were based on a progress rate of 6.5 to 7.5 miles per week. Com Net projects to close the gap at a rate of 2.0 miles p | 0 | Negative variance of 48% versus baseline and negative variance of 13% versus 2011Q2 projections. Com Net had an oversight in the 2011Q2 projection in that it did not re-adjust the time line to account for the lead time associated with purchasing power upgrades at legacy collocation sites that will be housing equipment. Com Net was deferring this operating expense increase until it had a definitive time line for the lifting of the Special Award Conditions since equipment could not be deployed to the field until all conditions were met. Com Net, also, delayed equipment deployment at existing facilities for purpose of conducting meetings with legacy customers as the upgrade at several sites will be a hot cut that will compromise the protected ring status during cut-in and affect customers served locally from certain PoP sites. Com Net is, also, conducting a power audit at all sites prior to deployment at the recommendation of a key customer. Com Net expects to initiate deployment a | 0 | Negative variance of 24% versus baseline and negative variance of 10% versus 2011Q2 projections. This item will track in line with 2i with the exception of passive facility testing and inspection, which isn't significant in comparison to equipment deployment testing. | 2011-08-22 11:09 | 2011-08-22 11:09 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2011 | Q3 | Q3 - 2011 | 4251 | 3976 | TRUE | 14 | Negative Variance of 2% versus 2011Q2 projection and 23% to Baseline. At the end of Q3 2011, Com Net had outstanding obligations that, when taken into account, put the percent completion at 23% or a 10% advancement over the prior quarter. The primary invoices received but not paid were in the area of route design, route inspection, route construction and outside plant materials. Route construction billing continues to lag as segment finalization continues to lag due to outstanding aerial make readies. Com Net plans to implement partial acceptance of route segments in the upcoming quarter to facilitate the activation of service to community anchor institutions. | 100 | Pre-Award Acceptance and Application | Other items included in the Baseline report are Project Management and Administration at 47% complete for a positive variance versus Q2 2011 projections of 6% and 9% versus Baseline as we continue to adjust plans to manage the project based on items within our control. Contractual Solution Sales at 8% for a negative variance versus Q2 2011 projections of 7% and a negative variance versus Baseline of 4%. The variance was driven by contractual sales to Broadband Service Providers lagging behind in parallel with route construction with a partial offset as significant progress was made with relation to Community Anchor Institutions under a term contract. Operation Support System were at 11% completion for a negative variance versus Q2 2011 projections and 56% versus Baseline. The variance was driven by a favorable purchase price on hardware for Cyan CyMS element management system, as well as continued deferral in the purchase of the NISC plant and trouble module, as well as a decisio | 100 | Com Net is projecting additional expenses in the area of Environmental Assessment as Com Net engages Mannik & Smith for additional consultation with ODNR and OHPO with respect to route modifications and in the implementation of protocols and procedures set forth in the projects special award conditions for Compliance with Environmental Protocols and Measures as construction is modified from underground to aerial to avoid underground obstructions and other unforeseen circumstances. Com Net has also initiated activity to engage Mannik and Smith for historic and cultural resource protection in association with hut site acquisition and site preparation, as well as an ODNR approved herpetologist to conduct a habitat survey for the Eastern Plains Garter Snake in the area around Killdeer Nature Preserve as this route segment is expected to proceed to construction prior to year end 2011. | 35 | 0% Variance versus 2011 Q2 projections, a +1% Variance versus Baseline. Com Net had outstanding obligations that, when taken into account, put the percent completion at 37%. This is consistent with Com Net's objective to ensure significant progress is being made in route design to allow permit application work to proceed in an effort to keep long lead time items like make readies and fiber cable supply from negatively affecting the ability to progress on outside plant route construction. | 23 | A negative 10% variance versus budget and a negative 23% versus baseline. Com Net has refocused resources on permit follow-up. In doing so Com Net has encountered the need to meet with several counties to secure authorization to proceed with direct plow (also referred to as slit-trench construction techniques). At the end of the quarter significant progress was made with authorities for granting use of right-of-ways, however the permits still had not been released. | 13 | A negative variance of 8% versus Q2 2011 projections and a negative variance of 28% versus baseline. Com Net continues to balance the timing of construction permits and other approvals against securing right of way and outside plant materials versus deposit and ninety day completion time frames being required by some authorities. Com Net has elected to proceed with underground construction where significant contiguous permitted lengths (greater than 10 miles) can be achieved. Com Net will then return to the route segments and finalize construction upon finalization of aerial make readies. | 0 | A negative variance of 7% versus Q2 2011 projections and a 42% negative variance versus baseline. Com Net continues to hold on actual site preparation until such time that the Area of Potential Effect and other environmental protocol and procedures have been completed to ensure historic and cultural resources are protected. The site preparation delay is not impacting to the overall project at this point as route construction has not progressed to the point requiring full completion of site preparation work. | 27 | A negative variance versus Q2 2011 projected of 2% and a negative variance versus baseline of 12%. Com Net had outstanding obligations in the area of equipment procurement that, when taken into account, put the percent completion at 31%. Com Net experienced delays in the cut-over of the initial sites installed due to customer notification requirements. Com Net is projecting that in 2011 Q4 the initial sites will be cut over with equipment purchases and site installation accelerated for the upcoming quarter. | 7 | A negative variance versus Q2 2011 projected of 10% and a negative variance versus baseline of 16%. At the end of the quarter, Com Net had outstanding obligations that, when taken into account, put the percent completion at 10%. The liquidated obligations are being impacted due to the inability to complete the full route segments based on aerial spans that are on hold pending completion of make readies in order to proceed with pole attachments. Com Net plans to begin accepting portions of route segments such that they can be placed into service to serve Community Anchor Institutions. This will result in some of the unliquidated obligations being liquidated. Com Net is projecting the gap between liquidated and unliquidated obligations in this area to widen as more route segments involving aerial construction are to be encountered for the upcoming quarter. Com Net expects release of aerial segments for construction to lag behind direct-buried segments by approximately six mon | 0 | A negative variance versus Q2 2011 projections of 6% and a negative variance versus baseline of 68%. Com Net encountered delays in activation of the sites planned for the quarter as these sites were on a link of legacy facilities made part of the project that were already in service where the equipment was being upgraded. The delay was due to customer notification periods, as well as additional training and testing to ensure the implementation was successful. Com Net plans to accelerate deployment in the upcoming quarter, however several sites will only be partial implementation as full implementation can not be achieved due to the completion of new routes lagging behind schedule. | 9 | A positive variance versus Q2 2011 projections of 2% and a negative variance versus baseline of 28%. Network Testing to date has been limited to route inspection of cable placement to specifications and optical time domain reflectometer (OTDR) testing of fiber optic cable placed and spliced. Testing of facilities with active electronics/optronics installed will occur in the upcoming quarter. Network Testing will continue to lag behind as route construction lags behind. | 2011-11-23 12:47 | 2011-11-23 12:47 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2011 | Q4 | Q4 - 2011 | 5237 | 4899 | TRUE | 19 | No Variance versus 3rd Quarter 2011 Performance Progress Report Projections, but a 30% Variance versus baseline primarily driven by a later than expected construction start date. | 100 | Pre-Award Acceptance and Application | Project Management and Administrative Reporting of 58% versus 3rd Quarter 2011 Performance Progress Report Projections of 60% and a baseline of 44%. The variance versus projection is positive as legal expenses for finalization of agreement was less than projected. The closure of the progress in this area on a financial basis versus baseline should continue to close based on work pulled ahead for boiler plate contract development. Contractual Sales Solutions continue to perform favorably to budget expectations, as well as Community Anchor Institution Sales. The finalization of contractual agreements with Broadband Service Partners and Wholesalers continues to lag behind expectations, however these providers have a tendency to not put a high priority on such agreements until the facilities are deployed. Operation Support System was at 12% for no variance versus 3rd Quarter 2011 projections and a 2% variance versus baseline. Operation Support System was at 12% versus 3rd Quar | 100 | Follow-up Environmental Assessment activities for route modification requests and implementation of Environmental Assessment Measures and Protocols pursuant to the EA FONSI. | 45 | Positive variance versus 3rd Quarter 2011 Performance Progress Report Projections and a 4% positive variance versus baseline. Com Net is attempting to work further ahead on permit application and construction packages in preparation for an aggressive Spring thru Fall 2012 Construction Period. | 30 | Negative Variance versus 3rd Quarter 2011 Performance Progress Report Projections and a 24% Negative Variance versus Baseline due to the fact that, as of the end of the quarter, Com Net had not yet reached agreement with Hardin, Shelby and Miami counties to authorize the use of the direct plow method of construction. Although significant progress was made, right-of-way permits for these counties were still outstanding at the end of the year. | 23 | Positive Variance of 7% versus 3rd Quarter 2011 Performance Progress Report Projections and a negative variance of 23% versus Baseline. Com Net continues to see better than expected turn-around time on permits and other approvals for railroad crossings. Com Net has also implemented EA protocol and measures to move to aerial construction on existing pole lines, which has increased the expected run rate for pole attachment application and make ready fees. | 6 | Negative Variance of 7% versus 3rd Quarter 2011 Performance Progress Report Projections and a negative variance of 59% versus baseline. Com Net was able to progress work associated with improvements associated with its Findlay Point-of-Presence at a collocation site and with site acquisition and surveying work associated with its Wood County Point-of-Presence. Progress on the Huntsville Point-of-Presence was delayed as we were unable to complete the acquisition of an easement for the site prior to year-end. Com Net has several modification pending submissions that will further reduce the number of new construction Point-of-Presence sites by occupying existing leased space. | 32 | Negative Variance of 2% versus 3rd Quarter 2011 Performance Progress Report and a negative 19% variance versus baseline. Variance from third quarter 2011 is associated with auxiliary equipment that will be purchased and deployed in early 2012 as needed on a site-by-site basis. | 12 | No Variance versus 3rd Quarter 2011 Performance Progress Report Projections and a negative variance of 20% versus baseline. This category is the primary driver in the Overall Project Progress. Construction of routes progressed in the 4th quarter as projected primarily due to rain and flooding conditions rather than snow and ice conditions. | 1 | Negative Variance of 7% versus 3rd Quarter 2011 Performance Progress Report Projections and a negative variance of 81% versus baseline. The negative variance versus 3rd Quarter 2011 Performance Progress Report was strictly due to continued invoicing delays by CYAN for installation of professional services. The actual number of sites deployed exceeded Com Net's original 3rd quarter projections with four of the deployed sites cut-over into service on the network. This indicator will continue to lag until invoicing is brought current. | 41 | Positive Variance of 16% versus 3rd Quarter 2011 Performance Progress Report Projections and a negative variance of 7% versus baseline. Network Testing has increased in volume as Com Net requests testing and release of portions of routes to establish service to Community Anchor Institutions prior to completion of the full segment. Com Net will need to monitor expenses in this area as crews are redeployed to test facilities upon full segment completion for Point-of-Presence to Point-of-Presence Community Pair turn-ups. | 2012-02-23 18:23 | 2012-02-23 18:23 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2012 | Q1 | Q1 - 2012 | 6233 | 5719 | TRUE | 28 | Negative variance versus baseline of 28% and negative variance versus 2011 Q4 PPR of 1%. The negative variance was driven primarily due to excess crew moves negatively impacting projected construction progress and utilization of design resources to focus on route modifications and associated supporting documentation. | 100 | Pre-Award Acceptance and Application | Project Management and Administrative Reporting of 67% versus 4th Quarter 2011 Performance Progress Report Projections of 64% and a baseline of 53%. The variance versus projection is a result of increased management efforts in securing right-of-way permits. Contractual Sales Solutions continue to perform favorably to budget expectations, as well as Community Anchor Institution Sales. The finalization of contractual agreements with Broadband Service Partners and Wholesalers showed significant progress during the quarter as these prospects were able to see visible construction progress in their areas of interest,. Operation Support System was at 18% for a positive variance versus 4th Quarter 2011 projections and a 82% negative variance versus baseline as Com Net reviewed Service Level Agreement and upgraded its in-house VLAN monitoring system. Com Net continues to defer NISC iVUE plant and trouble module implementation, as well as a decision to defer mapping until the end of the | 100 | All future activity by environmental consultant shall be considered part of construction and/or as a construction permit and other approval. | 57 | Positive variance versus Baseline of 2% and negative variance of 10%versus 2011Q4 PPR projections. The negative variance was a result of design resources being refocused on route modification efforts and a higher than expected level of support with right-of-way and permitting efforts. | 39 | Negative variance versus baseline of 25% and a negative variance versus 2011Q4 PPR projection of 3%. Significant progress was made on securing right-of-way authorization in Hardin County and Shelby County as projected. Permits were still outstanding with Miami County at the end of the 1st quarter of 2012. | 32 | Negative variance versus baseline of 32% and a negative variance versus 2011Q4 PPR projection of 7%. This was primarily driven by higher than expected level of support required in securing rights-of-way in Hardin, Shelby and Miami counties, as well as the redirection of design resources to support route modification efforts. | 8 | Negative variance versus baseline of 65% and negative variance versus 2011 Q4 PPR projections of 3%. This variance versus baseline is a result of a later than expected start date on ground disturbing construction activities for the network build-out. The negative variance versus 2011 Q4 PPR projections was a result of pending route modifications and procurement of back-up generator installation services. Con Net is projecting that its actual site preparation cost will come in at 60% of budget based on the transition of multiple sites from new construction to leased space pursuant to route modifications submitted and approved. Com Net projects completing 3 new construction sites by the end of the 3rd quarter of 2012 and finalizing the preparation work for occupied space at another 3 sites by the end of the 3rd quarter 2012 with the balance of the leased sites full prepared by the 4th quarter of 2012 with the remaining new construction site in Greenfield, Oh to be completed in t | 39 | Negative variance versus baseline of 24% but a positive variance of 3% versus 2011 Q4 PPR projections. The positive variance was a result of positive efforts in securing contractual arrangements with Broadband service providers for connectivity to the Com Net GigEPAC backhaul network. | 21 | Negative variance versus baseline of 17% and a negative variance versus 2011 Q4 PPR projections of 3%. The negative variance versus 2011 Q4 projections were primarily due to invoice timing on construction activities completed. Favorable weather presented the opportunity to further advance the network build, but outstanding route modifications forced excess moves of crews that negatively impacted efforts to progress the build based on a favorable winter construction season. | 18 | Negative variance versus baseline of 65% but a positive variance versus 2011 Q4 PPR projections of 3%, which can be directly correlated to the positive variance on equipment procurement. | 67 | Positive variance versus baseline of 1% and a negative variance versus 2011 Q4 PPR projections of 13%. In the 2011 Q4 PPR projections, Com Net was projecting a cost overrun for network testing/inspection. The negative variance versus projections is a result of Com Net cost control efforts on network testing/inspection. Com Net is still projecting a cost overrun on network testing and inspections, however not to the same degree as a result of cost control efforts. The overrun is still projected based on the network build-out status being significantly below baseline while network testing/inspection expenses are already in line with baseline expectations. | 2012-05-21 15:50 | 2012-05-21 15:50 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2012 | Q2 | Q2 - 2012 | 6923 | 6089 | TRUE | 37 | Negative variance versus baseline of 31% and negative variance versus 2012 Q1 PPR of 3%. Construction or Network Build-out is the controlling factor in performance versus budget. The lack of contiguously permitted route mileage using the slit trench method of construction negatively impacted the ability to add a fourth plow train. In order to obtain permits in a timely fashion, we are also experiencing a higher call-out rate for boring operations in comparison to slit trench. This is being addressed through the procurement process to bring on additional boring crews and equipment through sub-contracting. The inability to secure significant contiguous route mileage is resulting in the movement of crews, which in turn results in multiple segments remaining as Work-in-Progress with a higher than expected level of unliquidated obligations. | 100 | Pre-Award Acceptance and Application | Project Management and Administrative Reporting liquidated expenses of 73% versus a baseline of 63% and projections of 76%. This was primarily driven by a reduction in the involvement of professional services in negotiating agreement with authorities having jurisdiction over right-of-ways. Contractual Sales Solutions performed favorable to baseline with Broadband wholesalers and last mile providers while service activation to Community Anchor Institution flat lined during the quarter. Contractual sales were at 52% compared to a baseline of 63% and projection of 55%. The operation support systems continues to perform significantly below budget at 20% versus a baseline of 100% and prior quarter projections of 23%. This continues to be based on Com Net's election not to request federal funding of plant and trouble module upgrades to its legacy customer care and billing system. As well as our continued decision to defer the internalization of a mapping system until the end of th | 100 | All future activity by environmental consultant shall be considered part of construction and/or as a construction permit and other approval. | 62 | Negative variance versus baseline of 18% and negative variance versus 2012 Q1 PPR of 17%. The route design firm encountered permitting issues with 4 townships, 2 counties and 4 municipalities that required a concerted effort by all involved to allow enough mileage to be released for construction to keep crews active. This issue was alleviated at the end of the quarter. A change order was agreed to extending the design period on several segments based on this redirection of resources. Network design activities will be adjusted to close the gap, however securing permits with authorities at two counties continue to pose a risk to the planned routes. | 54 | Negative variance versus baseline of 24% and positive variance versus 2012 Q1 PPR of 9%. At the end of the quarter Com Net secured permits for right-of-ways on two outstanding townships along with accelerated approval on planned route construction in Hancock, Putnam and Henry Counties. At the end of the quarter, right-of-ways with two townships, three municipalities and two counties continued to pose concerns. The concerns were in respect to underground construction method being permitted and the associated impact on timeline and budget. The alternative would be to identify, EA, design and construct a different route(s) following a US Highway or Interstate. A decision was pending at the end of the quarter. | 52 | Negative variance versus baseline of 32% and positive variance versus 2012 Q1 PPR of 14%. At the end of the quarter, Com Net received notice of completion on several outstanding make readies associated with aerial construction. Com Net, also, experienced higher than originally projected permitting expenses in Monroe County, Michigan, which drove liquidated expenses to a higher level than forecasted. | 11 | Negative variance versus baseline of 77% and negative variance versus 2012 Q1 PPR of 3%. Although this line item remains significantly behind budget, it is a relatively low percentage of the overall project and the actual project hours required for completion are minimal. Activity on site preparation did not commence in line with expectations due to a delay in securing a building permit with a single authority as they evaluated the sustained wind rating of the planned structures. The final permit was secured at the end of the quarter and work will be scheduled for the completion of 3 new sites and the augmentation of a fourth existing site during the upcoming quarter. | 55 | Negative variance versus baseline of 16% and negative variance versus 2012 Q1 PPR of 4%. The completion of contiguous route segments continued to be delayed due to the lack of permits for full completions of the released construction segment. As a result, Com Net held on the purchase of additional equipment until the third quarter of 2012. In addition to Com Net's managed and operated network facilities, OARnet procured a significant portion of the electronics equipment that it will manage and operate as part of the project. | 29 | Negative variance versus baseline of 26% and negative variance versus 2012 Q1 PPR of 1%. Although the percentage does not look significant, Com Net's inability to secure a significant amount of contiguous mileage for construction resulted in us not being able to deploy a fourth plow train, thereby resulting in us giving up some of the gains made during the 1st quarter of 2012 and negatively impacting dependent milestones. This can be seen in the significant increase in unliquidated obligations due to incomplete route segments, which is projected to continue into the upcoming quarter. From a liquidated expense perspective, progress will increase at an accelerated rate as construction moves into more congested areas to the south with Miami, Montgomery and Clarke counties; and to the north in the Toledo metro areas where costs were budgeted at a higher rate per mile. Rural construction costs per mile are, also, budgeted to increase as we move into areas on the northern and souther | 18 | Negative variance versus baseline of 70% and negative variance versus 2012 Q1 PPR of 13%. The negative variance on equipment deployment was driven by the fact that contiguous fiber segments were not available to allow us to cut over connectivity between city pairs. Due to the lack of fiber facilities between nodes, equipment deployment activities were delayed until the third quarter of 2012 for efficiency purposes by allowing the equipment to be deployed and city pairs cut over into service through a single visit by the manufacturer. | 88 | Positive variance versus baseline of 50% and negative variance versus 2012 Q1 PPR of 5%. Network testing expenses continue to run at a higher rate than originally projected due to the need to accept partial passive route segments in order to progress the project toward completion. Although the run rate is higher than budgeted, it was below projections primarily due to delays in testing associated with the cut over of city pairs and the completion of services to Community Anchor Institutions that occurred during the quarter. | 2012-08-08 12:21 | 2012-08-08 12:21 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2012 | Q3 | Q3 - 2012 | 7963 | 6688 | TRUE | 46 | Positive Variance of 1% versus prior quarter projection with a negative 30% variance versus baseline. Work-in-Progress continued to show a significant backlog with $4.5 Million in unliquidated obligations at the end of the quarter. The 46% Project Completion Rate represents a 9% gain from prior quarter. | 100 |  | Project Management and Administrative Reporting liquidated expenses of 80% for a negative variance versus projections of 3% and a positive variance versus baseline of 8%. The negative variance versus projections is actually favorable as it indicates that project management expenses ran 3% less than projected at the end of 2nd quarter and represents a gap closure against baseline projections. Contract Sales continued to be negatively impacted by the network build being behind schedule versus baseline and prior quarter projections. The negative variance versus the prior quarter was impacted by delays in permitting in certain areas of the segments under construction, which prevented us from completing contiguous segments required for serving certain Community Anchor Institutions. Com Net was, however able to make some progress with respect to contract sales during the quarter posting a 7% gain from the prior quarter. Operation Support progress based on liquidated expenses showed | 100 | All future activity by environmental consultant shall be considered part of construction and/or as a construction permit or other approval. | 74 | Positive Variance of 8% versus prior quarter with a negative 17% variance versus baseline. Major design activities will be drawing to a close in the first part of the 4th quarter of 2012. The majority of the activity by the route, design and permitting firm will be in the tracking of permitting and addressing design concerns with the authority(s) having jurisdiction. | 58 | Negative Variance of 9% versus projections and a negative variance of 20% versus baseline. Rights-of-Way lagged behind schedule as Com Net continued to address concerns with the City of Springfield and the Ohio Department of Transportation in an effort to secure contiguous permitted sections for construction. | 55 | Negative Variance of 1% versus prior quarter projections and a negative variance of 33% versus baseline. The negative variance versus baseline was primarily driven by higher than expected permitting costs with the City of Springfield and Clarke County versus our short range outlook. The negative variance versus baseline is partially due to timing issues in securing permits, as well as a marginally favorable performance in actual permitting costs versus budget. | 41 | Site Preparation showed an increase of 30% from prior quarter with a positive variance versus prior quarter projections of 13% with a negative variance versus baseline of 47%. The positive variance versus prior quarter projections was driven by a faster turn around time than projected by site preparation contractors from completion of work to billing. At the end of the quarter, Com Net was waiting on final inspection of its Huntsville, OH Point-of-Presence prior to installation of the electrical hookup. Findlay and Wood County were strictly pending electrical hook-up by the local utility. The allocation of space at Com Net's wholly owned subsidiary, Independents Fiber Network, site in Lima, OH was pending electrical specification from sub-recipient OARnet before being applied to the project. | 62 | A 1% postive variance versus prior quarter projections and a negative 21% variance versus budget. The large variance versus budget is primarily driven by Com Net's decision to equip all Cyan chassis with switched layer 2 packet Metro Ethernet capabilities and reduce the number of sites equipped with MPLS network equipment. This is being implemented as a favorable network architecture over a multi-node MPLS network for the coverage area. This design change will be reflected in an upcoming route modification to be submitted by Com Net. | 39 | Favorable variance of 2% versus prior quarter projections and a negative 24% variance versus baseline. The favorable variance versus prior quarter was driven through the completion of multiple sub-contractor awards made by KG Myers to increase the number of directional drilling crews active on the project. Com Net monitored the procurement process utilized by KG Myers to ensure compliance with program requirements. KG Myers completed the procurement process and issued award to three sub-contractors with sub-contractor crews deployed to the field in early September. | 33 | Positive variance of 5% versus budget and a negative 59% variance versus baseline. The positive variance was insignificant and represents an on target performance. The negative variance versus baseline is driven by the fact that equipment is not considered to be fully deployed until the city-pair nodes are cut into service, therefore a significant portion remains as work-in-progress as Com Net waits for fiber routes to be constructed. In addition, sub-recipient OARnet continues to focus on its 100 Gbps network deployment in Northeast Ohio, as Com Net awaits splice work by MERIT and Level3 before releasing fiber facilities to OARnet for its management and operation. In addition, ZAYO's deployment of equipment continues to be delayed until the major segments of Toledo-to-Lima and Lima-to-Dayton are completed, which are not projected for completion until late 2012/early 2013. | 100 | As disclosed in the prior quarter projections, Com Net is experiencing an overrun in network testing/inspection costs as we release partial segments in order to allow for the activation of service to Community Anchor Institutions prior to full segment completion. The budget overrun for network testing will be offset through savings in the areas of equipment procurement and network build. | 2012-11-19 17:59 | 2012-11-19 17:59 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2012 | Q4 | Q4 - 2012 | 8827 | 7612 | TRUE | 58 | Negative variance of 3 percent versus prior quarter projections and a negative variance of 21 percent against baseline. The current project expenditures are expected to be 8.77 percent under budget. When compared against projected expenditures through the end of the award period, the percent of completion is 63 percent or a positive 2 percent variance versus prior quarter projections. | 100 | Application and Award Acceptance Period, Project Management and Project Administrative Reporting, Contract Sales and Operation Support Systems | Application and award acceptance period budget continues to be closed at one-hundred percent complete. Project Management and Administrative Reporting ran three percent under projections, which was positive as administrative reporting continues to become more efficient, allowing us to close on early overruns in reporting time and expense. Contractual sales continue to lag behind with community anchor institutions primarily in the area of higher educational institutions due to timing and lack of firm commitments. Operational support systems will continue to lag behind as CNI continues to have Sigma Technologies maintain mapping records as its Route Design and Permitting Firm with final transfer to occur during the last quarter, as well as, its decision not to utilize federal funds on the NISC plant and trouble module upgrade. | 100 | All future activity by environmental consultant shall be considered part of construction, and/or as a construction permit or other approval. | 83 | Negative variance of 3 percent versus prior quarter projections and a negative variance of eight percent versus baseline. Requests by authority having jurisdiction of route design changes, outstanding route modifications with NTIA and bedrock conditions preventing underground construction are extending network design activities. | 69 | Negative variance of 3 percent versus prior quarter projections and a negative variance of twenty-three percent versus baseline. Finalization of rights-of-way is dependent on satisfaction of route changes that are currently pending route modification review by NTIA. | 61 | Negative variance of 3 percent versus prior quarter projections and a negative variance of thirty-three percent versus baseline. Finalization of construction permits and other approvals is dependent on satisfaction of route changes that are currently pending route modification review by NTIA. | 71 | Positive variance of 15 percent versus prior quarter projections and a negative variance versus baseline of twenty-nine percent. Significant progress was made in finalizing site preparation by completing hut facilities in Wood County (Bowling Green), Findlay and Huntsville (Indian Lake Region-Russells Point). | 68 | Negative variance of 2 percent versus prior quarter projections and a negative variance of thirty-two percent versus baseline. At the end of the quarter, CNI had procured all Cyan DWDM chassis. The outstanding equipment still to be purchased includes CNI's MPLS Network Equipment, as well as, OARnet's equipment for lighting the fiber facilities for which it will be responsible for managing as part of the project and ZAYO's electronics and collocation hardware required for the fiber facilities for which it will be responsible for managing as part of the project. | 52 | Negative variance of 4 percent versus prior quarter projections and a negative variance of thirty-five percent versus baseline. This is the category with the largest dollar value. Zayo made significant progress on its Toledo route construction for the quarter completing all but a half mile that requires conduit repair. It was projected a portion of the expenses associated with this construction would have been liquidated in the 4th quarter of 2012, but they continue to be held until the ~0.5 mile of conduit can be repaired and ~1.5 mile of cable placed between access points. There were, also, several CNI managed routes that were fully constructed by year-end, however invoicing was not received for processing by year-end. | 33 | Negative variance of 14 percent versus prior quarter projections and a negative sixty-seven percent variance versus baseline. Cutover of the Cyan DWDM chassis was delayed for a pending minor software release. It was put on-hold when it was determined that activation prior to the release would result in a service interruption once the release was implemented. | 100 | Zero variance versus prior quarter projections and baseline, however network testing is running over budget due to the partial acceptance and activation process being followed to satisfy project timeline requirements. Inspection activities will continue for the balance of the project; therefore, additional overruns will occur. However, in the scope of the entire project, the network testing budget category dollar amount is insignificant and, therefore, will not adversely impact the overall project budget. | 2013-02-15 22:38 | 2013-02-15 22:38 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2013 | Q1 | Q1 - 2013 | 9917 | 8500 | TRUE | 66 | A negative variance versus prior quarter projection of 8% and negative variance versus baseline of 29%. The completion of the project may no longer be viable based on the amount of work that still has to be completed once disposition of the outstanding route modification is received. CNI is therefore basing its projections on final disposition of the outstanding route modification on or before May 10, 2013. | 100 | Applications and Award Acceptance Period, Project Management and Project Administrative Reporting, Contract Sales and Operation Support Systems | A negative variance versus prior quarter projection of 0% and negative variance versus baseline of 0%. No variance in the Application and Award Acceptance Period milestone as it continues to be complete at 100%. Project Management and Administrative Reporting milestone expenditures continue to run ahead of projections due to administrative costs incurred prior to ground disturbing activities commencing. Contractual Sales milestones continue to lag behind in direct relationship to construction progress as community anchor institutions continue to withhold firm order commitments. Progress on the Operational Support System milestone was closed to within seven percent of baseline during the quarter with CNI executing on the purchase of the plant records module for its NISC iVUE customer care system. The liquidated expenditures for this milestone are expected to hold at this level unless software or programming expenditures are required to convert CAD drawings into KML files for as-b | 100 | A negative variance versus prior quarter projection of 0% and negative variance versus baseline of 0%. | 85 | A negative variance versus prior quarter projection of 14% and negative variance versus baseline of 12%. Network design activities are drawing to a close, with the majority of activities associated with change orders due to field conditions or changes required by authorities having jurisdiction on outstanding permits and rights-of-way. The most significant activities remaining for completion of the Network Design milestone are dependent on approval of the route modification. | 78 | A negative variance versus prior quarter projection of 0% and negative variance versus baseline of 20%. The Rights-of-Way milestone is primarily associated with securing the conduit pathway in the city of Dayton, permits with the city of Columbus, city of West Alexandria, city of Springfield and Clark County. | 63 | A negative variance versus prior quarter projection of 10% and negative variance versus baseline of 37%. The liquidated expenditures for achieving this milestone are expected to come in under budget. There are, however, outstanding expenditures with railroad companies, pole owners, private property owners and municipalities that will be liquidated between now and completion of the project. | 95 | A positive variance versus prior quarter projection of 19% and negative variance versus baseline of 5%. There are two major activities that still need to be addressed to realize completion of this milestone. The construction of a point-of-presence on a property in Greenville, Ohio that a favorable Area of Potential Effects study was completed on; and the finalization of Agreement and payment for leased sites. It is projected that a slight overrun will be experienced with respect to the liquidated expenditures associated with this mileston. | 73 | A positive variance versus prior quarter projection of 1% and negative variance versus baseline of 27%. CNI continued to hold on the procurement of MPLS network equipment until after the Cyan equipped city-pairs were cut into service. Furthermore, minimal progress has been observed with respect to sub-recipients procurement and deployment of equipment on facilities they will be managing and operating. | 62 | A negative variance versus prior quarter projection of 9% and negative variance versus baseline of 28%. The network build milestone continues to influence the overall project progress. CNI did not execute its IRU for facilities in the Columbus metropolitan area as the route modification request remained outstanding for the entire quarter. CNI construction crews' progress was not impacted by the outstanding route modification during the quarter, but this is expected to change by mid-May of the 2nd quarter if disposition of the route modification is not received. At this time CNI is projecting the liquidated expenditures for realizing completion of this milestone will come in under budget, however CNI remains cautious in its planning as several risks still exist for cost overruns. | 33 | A negative variance versus prior quarter projection of 40% and negative variance versus baseline of 67%. The progress on completing this milestone continues to run behind schedule as CNI only recognizes the deployment of Cyan chassis upon successful turn-up of the city-pairs. Furthermore, CNI continues to hold on procurement and deployment of the MPLS Network equipment until after turn-up of the related Cyan city-pairs. Finally there has been little to no progress on the procurement and deployment of the balance of equipment by sub-recipients in associations with facilities they will be operating and managing as part of the project. | 100 | The difference from projection is 0% and there is a positive variance versus baseline of 5%. The liquidated expenditures in association with this milestone ran 55% over budget. The reason for the overrun is related to the up front delay in the project before ground disturbing activities could commence. As a result of this CNI modified its plans to test and accept partial segments rather than full segments, which drove costs up. CNI also deviated from its original plan to internalize the network testing and inspection function. This plan was abandoned due to the expertise and training requirements not being conducive to the reduced time frame for construction after receipt of the project FONSI. | 2013-05-28 09:59 | 2013-05-28 09:59 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2013 | Q2 | Q2 - 2013 | 10749 | 9040 | TRUE | 76 | A negative variance versus prior quarter projection of 9%, negative variance versus baseline of 24%. The primary reason for the variance was due to delays by ZAYO and OARnet in requesting draw down in association with equipment procurement and slower than projected construction progress due to the fact that as of the end of the quarter CNI had not yet successfully secured a decision on its outstanding route modification request. | 100 | Applications and Award Acceptance Period, Project Management and Project Administrative Reporting, Contract Sales and Operation Support Systems | No variance in the Application and Award Acceptance Period milestone as it continues to be complete at 100%. Project Management and Administrative Reporting milestone expenditures continue to run ahead of projections due to administrative costs incurred prior to ground disturbing activities commencing. Contractual Sales milestones continue to lag behind in direct relationship to construction progress as community anchor institutions continue to withhold firm order commitments. In the 1st quarter of 2013 progress on the Operational Support System milestone was closed to within seven percent of baseline during the quarter with CNI executing on the purchase of the plant records module for its NISC iVUE customer care system. The liquidated expenditures for this milestone held at this level as no software or programming expenditures were required to convert CAD drawings into KML files for as-built mapping records. | 100 | A negative variance versus prior quarter projection of 0% and no variance versus baseline. Actual expenditures are 4%over budget for this category. | 88 | A negative variance versus prior quarter projection of 0% and negative variance versus baseline of 12%. This variance was driven by the fact the category is expected to come in under budget, as well as due to the fact that a disposition on CNI's outstanding route modification had not been received as of the end of the quarter limiting our ability to finalize network design on several routes. | 78 | A negative variance versus prior quarter projection of 12% and negative variance versus baseline of 22%. This variance is driven by two primary factors. First, CNI is projecting expenditures in this category to come in under budget based on favorable performance. Second, CNI was unable to finalize right of way applications in several areas due to the fact that its requested route modification remained unresolved as of the end of the quarter. | 75 | A positive variance versus prior quarter projection of 2% and negative variance versus baseline of 25%. The negative variance versus baseline is driven by two factors. First, CNI is projecting expenditures in this category to come in under budget based on favorable performance. Second, CNI was unable to finalize construction permits and pursue other approvals in several areas due to the fact that its requested route modification remained unresolved as of the end of the quarter. | 100 | No variance reported based on progress measured against expenditures. CNI is experiencing an overrun versus budget in this category, which it projects to continue to grow during the extension period as outstanding invoices are received with respect to finalization of the Greenville Hut. | 75 | A negative variance versus prior quarter projection of 19% and negative variance versus baseline of 25%. This was primarily driven by the fact that sub-recipients ZAYO and OARnet did not progress the procurement of their equipment pursuant to the project plan. | 75 | A negative variance versus prior quarter projection of 6% and negative variance versus baseline of 25%. This milestone negatively impacted all other milestones in this section as CNI was unable to secure approval of its 2012 route modification request by the required date set in the 2012Q1 PPR projections. | 33 | A negative variance versus prior quarter projection of 12% and negative variance versus baseline of 67%. This was primarily driven by the fact that sub-recipients ZAYO and OARnet did not progress the deployment of their equipment pursuant to the project. | 100 | No variance versus baseline and projections reported based on expenditures exceeding budget for this category. CNI continues to see an overrun in expenditures for network testing as it continues to accept partial route segments in order to connect and activate services to Community Anchor Institutions to advance the objectives of the BTOP program. This overrun is projected to continue to grow during the extension period in association with testing and acceptance of fiber routes as well as turn-up of additional city pairs. | 2013-08-27 06:55 | 2013-08-27 06:55 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2013 | Q3 | Q3 - 2013 | 12061 | 10222 | TRUE | 100 | At the end of the third quarter, CNI had not expended six percent (6%) of its overall project budget. CNI's inability to complete 8.6 miles in the Dayton metropolitan area accounted for approximately 3%,and the remaining 3% is attributed to favorable overall expenditure performance versus budget. | 100 |  | No variance in the Application and Award Acceptance Period milestone as it continues to be complete at 100%. Project Management and Administrative Reporting milestone finished over budget due to administrative costs incurred prior to ground disturbing activities commencing and a decision not allocate executive management to other categories. Contractual Sales milestones were fully complete at 100% by the end of the award. Operational Support System milestone was fully complete at 100% by the end of the award. | 100 | Actual expenditures are 4% over budget for this category. | 100 | Actual expenditures finished 11% under budget. The outstanding expenditures were driven by the fact that this budget category is expected to come in under budget, as well as, due to the fact that CNI was unable to complete approximately 8.6 miles in the Dayton metropolitan area as described in greater detail under Network Build prior to the end of the award. | 100 | Actual expenditures finished under budget. This is due to favorable performance versus budget and the fact CNI was unable to finalize right-of-way applications in association with approximately 8.6 miles on two routes in the Dayton metropolitan area as described in greater detail under Network Build prior to the end of the award. | 100 | Actual expenditures finished sixteen percent (16%) under budget. Actual expenditures for this category came in under budget based on favorable performance. In addition, CNI was unable to finalize construction permits and pursue other approvals in association with approximately 8.6 miles on two routes in the Dayton metropolitan area as described in greater detail under Network Build prior to the end of the award. | 100 | CNI experienced an overrun versus budget in this category. This is due to the recording of professional charges for work conducted in completing Site Preparation, Equipment Deployment and Network Testing in order to turn-up all City Pairs by September 30, 2013. All work was completed by the end of the award. | 100 | Actual expenditures for this category finished on budget for this category. | 100 | Actual expenditures for this category finished 9% under budget. CNI was unable to complete the construction of approximately 3.6 miles from Liscum Avenue to W 2nd Street in Dayton, Ohio. This was driven by the fact that CNI's route modification was not approved until late July 2013, along with the fact that AT&T did not complete their conduit make-ready work of removing lead sheathed cable in the Dayton area in order to allow CNI to proceed with cable placement. CNI is attempting to complete this construction prior to the end of the 1st quarter of 2014. CNI was, also, unable to complete the construction of a 5 mile fiber route from the intersection of Harshman Road and Beatrice Drive to CNI's partner's eastern route to Wright State University due to the delay in receiving approval of its route modification and permitting lead times with Wright Patterson Air Force Base. CNI continues to work with Wright Patterson Air Force Base to identify a route that can be constructed that avoids all | 100 | Expenditures for this category finished 34% under budget. This was driven by the categorization of professional expenses between Equipment Deployment, Network Testing and Site Preparation. Equipment Deployment expenses are significantly under projections while Network Testing and Site Preparation currently show an overrun. | 100 | CNI experienced an overrun in expenditures for network testing as it accepted partial route segments in order to connect and activate services to Community Anchor Institutions to advance the objectives of the BTOP program. CNI projects expenditures for the Equipment Deployment category to be under budget. Equipment Deployment, Site Preparation and Network Testing were performed in unison with one another using network professional services. | 2014-04-23 11:03 | 2014-04-23 11:03 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570073 | 2010 | Q4 | Q4 - 2010 | 1059 | 2096 | TRUE | 1 | N/A | 0 | N/A | N/A | 95 |  | 100 | N/A | 38 | 21 total required; 8 out of 17 permit entities complete; 0 out 3 Franchise/agreements complete. All are in progress. | 38 | 21 total required; 8 out of 17 permit entities complete; 0 out 3 Franchise/agreements complete. All are in progress. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-10 16:38 | 2011-02-10 16:38 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2011 | Q1 | Q1 - 2011 | 2311 | 2901 | TRUE | 10 | Behind due to delay in obtaining FONSI. | 0 |  | No other progress milestones at this time. | 90 | We are preparing to submit the final EA. We do have mitigation items that will remain high priority to accomplish post FONSI. | 5 | Network design of the GePON technology is complete. | 60 | 23 total required. This increased from last report. 16 out of 20 permits submitted. Received 6 to date. 0 out of 3 franchise/ROW agreements complete. Received agreement that we did not have to have 20 years ROW in the franchise agreements. We do need to account for the 20 years for our audit. Negotiations are in progress. | 60 | 23 total required. This increased from last report. 16 out of 20 permits submitted. Received 6 to date. 0 out of 3 franchise/ROW agreements complete. Negotiations are in progress. We require permits from the following federal agencies in order to start construction. Not all routes require all these entities: -Bureau of Land Management -US Forest Service -Bureau of Reclamation -National Grasslands We have been drawing funds for both permits and ROW under the Land, ROW budget category. | 0 | We have five routes to accomplish. Dependent on FONSI, permitting and CAI contracts, the priority of the routes may change. | 70 | We are in process of receiving all our materials for the builds. The equipment specific to the technology (OTN, GePON and MOE) is in progress of contract negotiation for shipment timeframes. | 0 | We anticipate starting soon. | 0 | Once routes are built, we can start this milestone. | 0 | Once routes are built, we can start this milestone. | 2011-05-25 16:50 | 2011-05-25 16:50 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2011 | Q2 | Q2 - 2011 | 3197 | 3359 | TRUE | 2 | The EA process took longer than anticipated from our baseline project plan. | 0 | NA | No other progress milestones at this time. | 100 | We received FONSI on July 19, 2011. | 100 | Network design of the fiber infrastructure and GePON technology is complete. | 95 | We have all necessary ROW for the main infrastructure legs and laterals for Community Anchor Institutions. We still need to obtain one ROW for one GePON build. | 95 | We have received all of our permits except for the federal agencies of BLM, USFS and Bureau of Rec and one utility (in progress). We anticipate to receive these very soon. We are working with an utility company as a large percentage of our pole attachment permits were rejected. | 0 | We have not started construction, therefore no site preparation has been started. | 0 | We have received all materials except for the specific technologies of OTN and GePON. | 0 | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | 0 | NA - we are providing middle mile only. | 0 | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | 2011-08-18 12:57 | 2011-08-18 12:57 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2011 | Q3 | Q3 - 2011 | 4273 | 3987 | TRUE | 27 | Based on dollars expended to date. | 0 | NA | NA | 100 | Complete | 100 | Complete | 98 | We need to obtain one right of way access for a private industrial park. We anticipate by end of Jan 2012. | 100 | We have obtained all our construction and other permits. | 0 | We have not begun construction. We will be 30% complete in Q1 2012. | 80 | We have all our equipment and fiber. We are putting out RFPs for rebid for OTN and GePON technologies. We will award the two remaining equipment technology in Q4 and purchase in Q12012. | 0 | Construction has not begun yet. We will be 30% complete in Q1 2012. | 0 | Construction has not begun yet. We will be 30% complete in Q1 2012. | 0 | Construction has not begun yet. We will be 30% complete in Q1 2012. | 2011-11-25 14:44 | 2011-11-25 14:44 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2011 | Q4 | Q4 - 2011 | 5031 | 4702 | TRUE | 29 | Based on dollars expended to date | 0 | NA | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 10 | Started construction on three of five main routes. Have not started on GePON installations. We anticipate starting the GePON builds by 3/19/2012. | 80 | We have all our equipment and fiber. We have put out bids for GePON and OTN that were due 1/20/2012. | 4 | 8% main routes (conduit only - fiber not pulled yet); 0% CAI laterals; 0% GePON builds. We anticipate starting the GePON builds by 3/19/2012. We have been focused on main routes first. | 0 | Main fiber route construction in progress; equipment is required for the GePON. | 0 | Main fiber route construction in progress; equipment is required for the GePON. | 2012-02-15 12:53 | 2012-02-15 12:53 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2012 | Q1 | Q1 - 2012 | 5971 | 5585 | TRUE | 33 | Based on dollars expended to date | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 38 | Started construction on five of five main routes. Have not started construction on GePON routes. We anticipate starting on the GePON builds in May 2012. | 80 | We have construction materials and fiber. We submitted RFPs for GePON equipment that we will send out. OTN RFPs to go out in May 2012. | 30 | 41% (main routes); 0% CAIs; 0% GePON builds. We anticipate starting on the GePON builds in May 2012. | 0 | Main fiber construction in progress; equipment required for CAI and GePON. We are targeting end of Q3 completion of main routes/GePON builds. | 0 | Main fiber construction in progress, equipment required for CAI and GePON. We are targeting end of Q3 to complete all main routes/GePON builds. | 2012-05-08 15:52 | 2012-05-08 15:52 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2012 | Q2 | Q2 - 2012 | 7037 | 6146 | TRUE | 49 | Based on dollars drawn to date; we are behind in reimbursements. Next quarter we will catch up to actual progress on the project. | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 59 | 79% main routes; 10% Passive Optical Networks (PONs) builds. All Passive Optical Networks (PONs) builds will be complete in Q3 except for one. | 90 | Optical Transport Network (OTN) technology selection in progress. Will be complete in Q3. | 59 | 79% main routes; 10% Passive Optical Networks (PONs) builds. All Passive Optical Networks (PONs) builds will be complete in Q3 except for one. | 0 | Equipment required for CAI and PON builds will be deployed in Q3. | 0 | Will be testing all main routes in Q3. | 2012-08-11 18:42 | 2012-08-11 18:42 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2012 | Q3 | Q3 - 2012 | 8065 | 6739 | TRUE | 77 | 77% complete budget wise. 98% complete project wise. Four out of five main routes complete with the last route almost complete. Three out of the four GePON construction started and almost complete. Last route and all GePON locations to be complete in Q4. | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 90 | Four out of five main routes complete with the last route almost complete. Three out of the four GePON construction started and almost complete. Last route and all GePON locations to be complete in Q4. | 90 | Four out of five main routes complete with the last route almost complete. Three out of the four GePON construction started and almost complete. Last route and all GePON locations to be complete in Q4. | 90 | Four out of five main routes complete with the last route almost complete. Three out of the four GePON construction started and almost complete. Last route and all GePON locations to be complete in Q4. | 2012-11-27 11:04 | 2012-11-27 11:04 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2012 | Q4 | Q4 - 2012 | 8707 | 7513 | TRUE | 86 | 86% complete budget wise and 99% complete project wise. | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 99 | Complete except for remaining Community Anchor institutions | 100 | Complete | 2013-02-11 16:44 | 2013-02-11 16:44 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2013 | Q1 | Q1 - 2013 | 10009 | 8549 | TRUE | 97 | 97% complete budget wise and 99.9% project wise | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-05-30 14:38 | 2013-05-30 14:38 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2013 | Q2 | Q2 - 2013 | 11367 | 9489 | TRUE | 100 | NA | 100 |  | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 2013-11-24 19:06 | 2013-11-24 19:06 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570074 | 2010 | Q4 | Q4 - 2010 | 991 | 2034 | TRUE | 1 | Unforeseen variables arose during the quarter that delayed the submittal of the Environmental Assessment (EA). While we were able to submit before the due date, we did not submit as early as planned, therefore the Finding Of No Significant Impact (FONSI) was not received as anticipated on the baseline. Since the Finding of No Significant Impact was not received, no funds have been spent other than the allowed funds as described in the Environmental Assessment Special Award Condition (SAC). | 0 |  | No Variance | 95 | Unforeseen variables arose during the quarter that delayed the submittal of the Environmental Assessment. While we were able to submit before the due date, we did not submit as early as planned, therefore the Finding Of No Significant Impact (FONSI) was not received as anticipated on the baseline. | 75 | Unforeseen variables arose during the quarter due to additional needs surrounding the Environmental Assessment . Resources that would have been used to design the network had to be pulled and used for Environmental Assessment needs. | 15 | After discussions with several of the entities involved in rights of way, Contact Network Inc. now sees that Rights of Way need to be submitted on a county/service area basis. Therefore our percent complete as reported in the baseline will not be accurate based on how the rights of way are currently being processed. | 0 | Unforeseen variables arose during the quarter that delayed the submittal of the Environmental Assessment. While we were able to submit before the due date, we did not submit as early as planned, therefore the Finding Of No Significant Impact was not received as anticipated on the baseline. Since the Finding Of No Significant Impact was not received, no funds have been spent other than the approved funds as described in the Environmental Assessment SAC. | 0 | No Variance | 5 | We are in the process of negotiating additional equipment to purchase. Not all vendor meetings or equipment evaluation has taken place, therefore we have not purchased all equipment anticipated when baseline was completed. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-02-07 13:01 | 2011-02-07 13:01 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2011 | Q1 | Q1 - 2011 | 2101 | 2796 | TRUE | 2 | During this quarter it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 0 |  | No Variance from Baseline | 99 | The Environmental Assessment is complete and the Finding of No Significant Impact was received during this quarter, however we expect to receive one more invoice from the Environmental Consulting Firm for services rendered to close out the project after March 31, 2011. | 75 | During this quarter it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs are held with various utilities and permits are negotiated with various entities the network design may need to be updated/changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 15 | During this quarter it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 3 | During this quarter it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict timelines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 6 | During this quarter it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 5 | During this quarter it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Also, delays caused by the Environmental Assessment in prior quarter hindered our progress developing and publishing the Equipment RFP. The equipment RFP was not posted as anticipated during this quarter, therefore the procurement is behind versus the baseline projections. | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 2011-05-17 17:44 | 2011-05-17 17:44 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2011 | Q2 | Q2 - 2011 | 2879 | 3197 | TRUE | 6 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | N/A | 100 | No Variance from Baseline | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 15 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 7 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 8 | During this quarter a total of fifteen Community Anchor Institutions were connected to our network. The site preparation was complete for these fifteen entities. Our projections for this quarter were to connect a total of twenty-two Community Anchor Institutions. The construction and site preparation for remaining seven institutions were not complete as of June 30, 2011 causing a variance in our projections. | 14 | Equipment is being purchased on an as needed basis. We expect significant purchases to be made during the next quarter. | 4 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 7 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 7 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 2011-08-01 14:58 | 2011-08-01 14:58 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2011 | Q3 | Q3 - 2011 | 4121 | 3904 | TRUE | 10 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category varies from our initial baseline report. |  |  |  | 100 | No Variance from Baseline. | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 11 | A total of twenty one Community Anchor Institutions are now connected to our network. The site preparation has been completed for these entities. Our projections for this quarter were to have a total of thirty-three Community Anchor Institutions thus causing a variance in our projections. | 15 | Equipment is being purchased on an as needed basis. We expect significant purchases to made during the next quarter. | 9 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 11 | A total of twenty one Community Anchor Institutions are now connected to our network. The site preparation has been completed for these entities. Our projections for this quarter were to have a total of thirty-three Community Anchor Institutions thus causing a variance in our projections. | 11 | A total of twenty one Community Anchor Institutions are now connected to our network. The site preparation has been completed for these entities. Our projections for this quarter were to have a total of thirty-three Community Anchor Institutions thus causing a variance in our projections. | 2011-11-17 17:27 | 2011-11-17 17:27 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2011 | Q4 | Q4 - 2011 | 5343 | 5017 | TRUE | 24 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No Variance | 100 | No Variance from Baseline. | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 18 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 18 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 18 | A total of thirty threeCommunity Anchor Institutions are now connected to our network. The site preparation has been completed for these entities. Our projections for this quarter were to have a total of sixty two Community Anchor Institutions thus causing a variance in our projections. | 23 | Equipment is being purchased on an as needed basis. | 24 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 18 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 18 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 2012-02-28 13:35 | 2012-02-28 13:35 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2012 | Q1 | Q1 - 2012 | 5941 | 5570 | TRUE | 36 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance | 100 | No Variance from Baseline. | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 28 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 28 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 30 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 27 | Equipment is being purchased on an as needed basis. | 36 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 30 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 30 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 2012-05-07 15:04 | 2012-05-07 15:04 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2012 | Q2 | Q2 - 2012 | 7131 | 6193 | TRUE | 60 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category varies from our initial baseline report. | 0 | N/A | No Variance | 100 | No Variance from Baseline. | 85 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 85% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 65 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 65 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 43 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 31 | Equipment is being purchased on an as needed basis. | 60 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 43 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 43 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 2012-08-17 17:16 | 2012-08-17 17:16 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2012 | Q3 | Q3 - 2012 | 8013 | 6713 | TRUE | 80 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category is a little ahead of our initial baseline report. | 0 |  | No Variance | 100 | No Variance from Baseline. | 90 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 90% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 81 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 81 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 45 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 52 | Equipment is being purchased on an as needed basis. | 82 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category varies from our initial baseline report. | 45 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 45 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 2012-11-21 11:07 | 2012-11-21 11:07 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2012 | Q4 | Q4 - 2012 | 8847 | 7630 | TRUE | 92 | This is ahead of our anticipated percent complete reported in our baseline. | 0 |  | No variance | 100 | No variance from baseline | 92 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 92% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 89 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 89 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 52 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 56 | Equipment is being purchased on an as needed basis based on the number of Community Anchor Institutions contracted etc. | 92 | This is ahead of our anticipated percent complete reported in our baseline. | 52 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 52 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 2013-02-19 16:12 | 2013-02-19 16:12 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2013 | Q1 | Q1 - 2013 | 9839 | 8456 | TRUE | 93 | This is slightly less - two percent - due to timing issues with construction invoicing. | 0 |  | No variance from baseline | 100 | No variance from baseline | 95 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 95% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 95 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 95 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 52 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 56 | Equipment is being purchased on an as needed basis based on the number of Community Anchor Institutions contracted etc. | 95 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 55 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 55 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 2013-05-20 16:53 | 2013-05-20 16:53 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2013 | Q2 | Q2 - 2013 | 10761 | 9046 | TRUE | 100 | No variance from baseline | 0 |  | No variance from baseline | 100 | No variance from baseline | 98 | Slight variance from baseline due to the finalization of laterals to connect Community Anchor Institutions. | 98 | Slight variance from baseline due to the finalization of laterals to connect Community Anchor Institutions. | 98 | Slight variance from baseline due to the delay in receiving railroad permits. | 72 | Slight variance from baseline due to the finalization of laterals to connect Community Anchor Institutions. | 100 | No variance from baseline | 98 | Slight variance from baseline due to the finalization of laterals to connect Community Anchor Institutions. | 98 | Slight variance from baseline due to the finalization of laterals to connect Community Anchor Institutions. | 98 | Slight variance from baseline due to the finalization of laterals to connect Community Anchor Institutions. | 2013-08-27 13:37 | 2013-08-27 13:37 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2013 | Q3 | Q3 - 2013 | 11485 | 9603 | TRUE | 100 | No variance from baseline | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2013-12-16 13:35 | 2013-12-16 13:35 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570075 | 2010 | Q4 | Q4 - 2010 | 1355 | 2371 | TRUE | 10 | The project anticipated roughly $1M in installation expenses that would have the been the result of executing the IRU contract with Level 3. Since the contract signing was delayed until the next quarter, the project spending is roughly $1M or 1% below projections. | 0 |  | NA | 0 | NA | 100 | NA | 0 | NA | 0 | NA | 0 | NA | 10 | Rather than purchasing new routers for the peering service portion of the network, existing router platforms within the core of the network are receiving an upgrade and the former core routers are being moved to the peering service. This resulted in a slight change in the timing of expenses for this quarter. | 5 | The original baseline estimate for network build anticipated the IRU contract being completed during this reported quarter. The IRU contract was completed in the quarter following the one for this report, and therefore we anticipate catching up significantly to this milestone. | 0 | NA | 0 | NA | 2011-02-24 08:32 | 2011-02-24 08:32 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2011 | Q1 | Q1 - 2011 | 1973 | 2732 | TRUE | 23 | The overall project, in terms of expenditures, is lagging slightly for this particular quarter due to the length of time required to finalize major contracts, as well as the need to realign our rate of purchases so that we do not incur operations costs for facilities longer than required before they have been put in production. We are, however, making progress in improving this metric and expect to have expenditures on plan by the end of the year. | 0 |  | NA | 0 | NA | 100 | NA | 0 | NA | 0 | NA | 0 | NA | 24 | Finalizing contracts has been an issue for equipment purchase | 5 | We're slightly ahead on this metric, due to activities related to upgrading the peering portion of the network facilities. | 10 | NA | 0 | NA | 2011-05-12 14:24 | 2011-05-12 14:24 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2011 | Q2 | Q2 - 2011 | 3297 | 3411 | TRUE | 30 | The overall project is lagging slightly for this particular quarter due to the length of time required to finalize contracts, as well as the need to realign our rate of purchases so that we do not incur operations costs for facilities longer than required before they have been put in production. We are making progress in improving this metric and expect to have expenditures on target by the end of the year. | 0 |  | NA | 0 | NA | 100 | NA | 0 | NA | 0 | NA | 0 | NA | 30 | Finalizing contracts has been a challenge for equipment purchase. We continue to lag slightly in equipment procurement due to extra time that has been necessary to complete contract negotiations and ensure proper installation arrangements. Although we have experienced delays in contract completion for both IRUs and equipment, the terms for these agreements have been finalized, ad we are accelerating completion of purchasing, receiving, and paying for IRUs and equipmente. We are projecting to be ahead of the baseline projection (45% vs 39.3%) by the end of Q3. | 28 | We continue to be ahead on this metric due to activities related to upgrading the peering portion of network facilities. Our baseline projections assumed a certain pace that has experienced some delays because of the difference between the dates when we committed to purchases versus the actual purchase orders and receipt. We anticipate being fully caught up by the end of the year. The Q2 2011 completion percentage reflects this. | 31 | NA | 0 | NA | 2011-08-24 16:37 | 2011-08-24 16:37 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2011 | Q3 | Q3 - 2011 | 4179 | 3938 | TRUE | 44 | The overall project, in terms of expenditures, is lagging slightly for this particular quarter due to the length of time required to finalize major contracts, as well as the need to realign our rate of purchases so that we do not incur operations costs for facilities longer than required before they have been put in production. Equipment procurement for the overall project construction is likely to end a year ahead of schedule, so we expect to surpass the baseline expectations in the 3rd or 4th quarter of Year 2. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 46 | Internet2 continues to improve on its schedule and execute equipment purchases as quickly as the deployment will allow. We expect this metric to level off relative to the baseline for the next two quarters, then surpass the baseline again in the 3rd and 4th quarters of year 2. | 70 | We have purchased all the fiber IRUs for Phase 1 and Phase 2. By Year 2, Quarter 3, we expect to purchase the remaining Phase fiber 3 to allow the project to complete ahead of schedule. | 31 | While equipment procurement is trending ahead of the baseline, the deployment of the equipment is lagging due to the length of time to ship the equipment from Internet2's optical vendor. Much of the equipment is fabricated in real-time in response to the purchase order. Internet2 anticipates the deployment percentage will increase in Year 1, Quarter 2 and will ultimately end up ahead of the baseline in Year2, Quarter 3. | 0 | NA | 2011-11-21 14:28 | 2011-11-21 14:28 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2011 | Q4 | Q4 - 2011 | 5357 | 5026 | TRUE | 55 | The overall project, in terms of expenditures, has exceeded the projection that was put in place last quarter, though it is lagging behind the baseline expectations. This is largely due to the timing of equipment procurement and work acceptance. Internet2 still expects the overall project to be substantially complete ahead of schedule. Internet2 is expecting to place orders for its third phase of optical networking equipment in the 3rd Quarter of Year 2. Deployment of that equipment is expected to be largely complete by Year 2, Quarter 4, nearly a year ahead of the project schedule projections. We expect to be at 87% at Year 2, Quarter 4. We expect to be at 100% before Year 2, Quarter 4. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 57 | Internet2 continues to improve on its schedule and execute equipment purchases as quickly as the deployment will allow. We expect this metric to level off relative to the baseline for the next two quarters, then surpass the baseline again in the 3rd and 4th quarters of year 2. | 81 | We have purchased all the fiber IRUs for Phase 1 and Phase 2 and the majority of fiber for Phase 3. By Year 2, Quarter 3, we expect to purchase the remaining Phase fiber 3 to allow the project to complete ahead of schedule. | 57 | While equipment procurement is trending ahead of the baseline, the deployment of the equipment is lagging due to the length of time to ship the equipment from Internet2's optical vendor. Internet2 expects to advance the schedule significantly in Year 2, Quarter 3 through the purchase of the majority of Phase 3 optical equipment. This equipment should be largely deployed by Year2, Quarter 4- roughly a year ahead of schedule | 0 | NA | 2012-02-28 14:46 | 2012-02-28 14:46 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2012 | Q1 | Q1 - 2012 | 6093 | 5649 | TRUE | 67 | Internet2 has exceeded the projection made last quarter, however the overall project, in terms of expenditures, is lagging behind the baseline. Internet2 still expects the overall project to be substantially complete ahead of schedule. We expect to be at 87% at Year 2, Quarter 4; and 91% at Year 3, Quarter 1. We expect to be at 100% before Year 3, Quarter 4. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 71 | Internet2 surpassed the baseline for this metric. | 89 | Internet2 has completed procurements and installation is ongoing. Once installation, test, turn up, and billing are complete, this metric will catch up with the baseline. | 71 | Internet2 met the baseline for this metric. | 0 | NA | 2012-05-15 13:29 | 2012-05-15 13:29 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2012 | Q2 | Q2 - 2012 | 7051 | 6153 | TRUE | 75 | Internet2 has advanced the overall deployment schedule by roughly a year and completed a substantial amount of the Phase 3 Ciena optical build by the end of June. However the overall project, in terms of expenditures, is lagging behind the baseline. The Internet2 project is substantially complete. The entire project will complete ahead of schedule. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 80 | Internet2 met the baseline for this metric. | 95 | Internet2 has completed procurements and installation is ongoing. Once installation, test, turn up, and billing are complete, this metric will catch up with the baseline. | 80 | Internet2 surpassed the baseline for this metric. | 0 | NA | 2012-08-14 08:15 | 2012-08-14 08:15 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2012 | Q3 | Q3 - 2012 | 8143 | 6782 | TRUE | 91 | Internet2 met the baseline for this metric. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 97 | Internet2 met the baseline for this metric. | 99 | Internet2 met the baseline for this metric. | 97 | Internet2 met the baseline for this metric. | 0 | NA | 2012-11-29 14:39 | 2012-11-29 14:39 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2012 | Q4 | Q4 - 2012 | 8977 | 7756 | TRUE | 92 | Internet2 met the baseline for this metric. | 0 | true | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 98 | The Internet2 project is substantially complete. Expenditures are slightly lagging behind the baseline. | 100 | Internet2 met the baseline for this metric. | 98 | The Internet2 project is substantially complete. Expenditures are slightly lagging behind the baseline. | 0 | NA | 2013-02-26 14:21 | 2013-02-26 14:21 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2013 | Q1 | Q1 - 2013 | 9855 | 8465 | TRUE | 95 | Internet2 met the baseline for this metric. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 94 | All equipment has been procured. Expenditures are slightly lagging behind the baseline. | 100 | Internet2 met the baseline for this metric. | 94 | All equipment has been deployed. Expenditures are slightly lagging behind the baseline. | 0 | NA | 2013-05-21 17:57 | 2013-05-21 17:57 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2013 | Q2 | Q2 - 2013 | 12039 | 10201 | TRUE | 100 | Internet2 met the baseline. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 100 | Internet2 met the baseline. | 100 | Internet2 met the baseline for this metric. | 100 | Internet2 met the baseline. | 0 | NA | 2014-04-15 15:39 | 2014-04-15 15:39 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570076 | 2010 | Q4 | Q4 - 2010 | 1299 | 2329 | TRUE | 1 | Baseline report estimated 2% to be completed, behind schedule due to the project overlap. | 0 |  | N/A | 25 | Draft Environmental Assessment filed with NTIA early in December 2010, due date was 1/2/2011. Baseline report estimated 75% to be completed. Project behind baseline plan due to ongoing issue with project overlap. | 1 | The baseline report estimated 10% completion. Behind baseline plan due to ongoing issue with project overlap; in Q4 continued discussion of project overlap with NTIA and other BTOP awardee; RFP issued for Professional Services Contract; initial pole attachment applications filed; continued network design to select optimal routes for CAI interconnection and contacted CAI's to discuss service options and confirm commitments to purchase services. | 0 | N/A - Project uses public rights of way | 1 | CPCN obtained to provide telecommunications services in VT; filed initial pole attachment applications. Baseline report estimated 10% completion. Behind baseline due to overlap issue. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-22 14:53 | 2011-02-22 14:53 | 6614 | 6614 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2011 | Q1 | Q1 - 2011 | 2413 | 2952 | TRUE | 1 | As detailed below, much of the work scheduled for this quarter has been held up due to the delay in the release of the Finding of No Significant Impact (FONSI). However, we have made progress on pole surveying and mapping which is ongoing. At the time last quarterâ€™s projections were made, we anticipated that the FONSI would be issued in February, 2011 or soon after, however delays from the consultation and subsequent programmatic agreement with the Vermont SHPO have pushed the FONSI schedule out. It is anticipated that the FONSI and EA SAC requirements will be completed in May, 2011. Once the FONSI is issued, we estimate that at the end of the first quarter of 2012 we will reach the original target spend for the other milestones as the make ready begins on poles, network design is finalized, and the project moves into the construction phase. This level of activity will enable the project to meet the 67% time line after 8 quarters which was part of the original target spend rate. | 0 |  | N/A | 27 | Negotiating programmatic agreement with National Telecommunications and Information Administration (NTIA) and VT SHPO | 1 | The project design on which an engineering firm would work could have been impacted by changes to the project implemented to mitigate environmental impacts. As a result, Sovernet decided to dedicate the time of key staff to completing work on the EA and delay completing the engineering firm RFP process. SFC has selected an engineering firm who is very familiar with our project and has extensive experience with fiber build projects. After consulting with them, we feel confident that we can proceed quickly with network design and reach our original target spend rates by the end of the first quarter of 2012. | 0 | Project uses public rights of way | 15 | Sovernet Fiber Corp (SFC) is prepared to move forward with approving pole attachment applications as soon as the FONSI is issued, and pole attachment agreements can be signed. Over 150 miles of poles representing over 20% of the poles in the project have been applied for and are awaiting issuance of the FONSI. We will continue to aggressively pursue additional pole applications once the FONSI is released. | 0 | SFC is prepared to move forward with make ready work, as soon as the FONSI is issued. The make ready process will allow permitting work and final design to be completed on the rest of the project and to proceed to the construction phase. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-05-31 17:24 | 2011-05-31 17:24 | 5890 | 5890 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2011 | Q2 | Q2 - 2011 | 3125 | 3320 | TRUE | 3 | Work scheduled for this quarter was delayed by the timing of the release of the Finding of No Significant Impact. Nevertheless, we have made substantial progress in surveying and mapping and surveyed 47% of the estimated poles along our network route. With the release of the Finding of No Significant Impact and the engagement of professional engineering services we expect to make continued progress in surveying, make ready, network design and construction and estimate that we will reach the original target spend of 50% for our milestones by the end of the first quarter of 2012. Much of the spending on this project will be for construction and purchase of fiber optic cable. Work on network design will set the stage for further increases in spending in coming quarters, as the project moves into the construction phase. | 0 |  | N/A | 46 | EA work required for Finding of no Significant Impact is completed. Anticipate further work for route modifications as network routes are surveyed pursuant to the programmatic agreement. We believe our budget of $100,000 for EA work will be spent over the life of the project. Possible additional expenditures include archeological consulting work and ER review of any project revisions. | 7 | Sovernet deferred engaging the design services of an engineering firm until this quarter since the design on which the firm could work could have been impacted by changes implemented to mitigate environmental impacts. With the release of the Finding of No Significant Impact this quarter, Sovernet Fiber Corp. selected an engineering firm that is very familiar with our project and has extensive experience with fiber build projects. We feel confident we will reach our original target spend rates by the end of the first quarter of 2012. | 0 | N/A | 36 | Work was delayed pending the release of the Finding of no Significant Impact. With the Finding of no Significant Impact, we have made substantial progress this quarter and nearly reached our baseline goal of 40% complete by June 2011. | 7 | Site preparation is construction work which had to be delayed pending the release of the Finding of No Significant Impact. We made strong progress with this aspect of the project in the past quarter once the Finding of No Significant Impact was issued in April 2011. | 0 | N/A | 0 | Network build was delayed pending the release of the Finding of No Significant Impact. As anticipated in our March 2011 Progress Performance Report, we did not spend in this area during the quarter ended June 2011. | 2 | Initiated colocation conduit verification requests for four sites; applied for colocation at three sites. | 0 | N/A | 2011-08-16 14:56 | 2011-08-16 14:56 | 6334 | 6334 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2011 | Q3 | Q3 - 2011 | 4147 | 3922 | TRUE | 6 | Actual spending trails the baseline plan primarily due to uncertainty prior to NTIA lifting Special Award Condition 10 regarding the ultimate scope of the project due to potential modifications required to resolve overlap with other BTOP projects, as well as limitations on work that could be initiated prior to the lifting of the Special Award Condition 10 and issuance of the FONSI. | 30 |  | Expenses are roughly in-line with those budgeted for. | 46 | 50% completion (as measured by expenditures relative to project budget) was projected through Sept. 30 in the June PPR. The Environmental Assessment ("EA") work required to obtain a Finding of No Significant Impact ("FONSI") is complete. However, archeological surveys will continue on a site-specific basis as poles requiring relocation and conduit locations are identified, and EA work may be required in support of a potential Award Action Request for approval of route modifications. | 19 | As measured by expenditures, completion increased by 12% over the quarter. Cumulative spending on Network Design through Sept 30 was short of the 25% projection in the June PPR primarily due to deferred start of design tasks while overlapping BTOP awards were resolved. Engineering firms retained for detailed route surveys, network design, overall project engineering support and management continue to assist SFC with all elements of the project. | 0 | N/A | 65 | Activity included in this expense category are principally make-ready survey fees. Expenditures to date exceed the 57% baseline goal that was projected for Sept. 30 in the June PPR. SFC has applied for pole attachment licenses for approximately 53% of utility poles involved in the project. | 15 | This category is comprised of pole make-ready work by pole owners and third party attachees. Cumulative expenditures in this category increased from 7% to 15% of budget during the quarter, as make-ready work was authorized on poles previously surveyed. Although spending is behind projection in this budget category, progress is running ahead of expenditures. Cumulative spending equal to 28% of budget was projected in the June PPR thru Sept. 30, while make-ready charges have been paid for approximately 42% of poles. | 1 | Cumulative spending to date is in line with the 1% completion projected through Sept. 30 on the June PPR. Purchases to date have been for test equipment. Progress made in the quarter that will lead to substantial expenditures on equipment included SFC's execution of a Statement of Work with its engineering firm to develop equipment specifications, as well as issuance of an RFQ for Packet Optical Equipment, receipt and review of vendor proposals, and follow-up technical sessions with potential vendors. | 0 | Consistent with the projection in the June PPR, minimal expenses were incurred through Sept. 30 in this category, which includes outside plant construction and fiber cable. Activities during the quarter that will enable spending in the Network Build category in subsequent quarters include issuance of an RFQ for construction of 90+ route miles, review of the bids from outside plant contractors, issuance of a RFQ for fiber cable, and selection of two vendors to provide bulk fiber optic cable. SFC and a construction firm entered a contract for construction of the first 90 route miles shortly after the close of the quarter. Make-ready expenditures, which are in the Network Design category have totalled approximately $1.2M to date. | 3 | 15% was projected through Sept. 30 on the June PPR Report. Submission of collocation applications to incumbent local exchange companies provides the foundation for expenditures in subsequent quarters on collocation installs and augments. Preparation of collocation space by SFC, which comprises the majority of the planned spending in this category, was deferred while the owner of the collo space prepares the space. | 0 | N/A | 2011-11-18 16:14 | 2011-11-18 16:14 | 6334 | 6334 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2011 | Q4 | Q4 - 2011 | 5195 | 4865 | TRUE | 13 | Overall spending through end of the quarter trails the original baseline target of 35% primarily due to initial delay in resolving Special Award Condition 10 and issuance of the FONSI. However, the rate of spending increased markedly during the quarter as SFC purchased fiber-optic cable and started outside plant construction. Overall spending slightly exceeds the 13% goal set for the quarter in the previous PPR. Make-ready surveys and make-ready work continued, with 70% of utility poles surveyed and make-ready work authorized by SFC for 59% of poles by end of the quarter. A contract for construction of 90 miles of plant was awarded during the quarter, and construction started in mid-December. A contractor was selected during the quarter for an additional 62 miles of outside plant construction, and a bid package was prepared for another 58 miles. Permitting (primarily railroad crossing agreements, highway work permits and right-of-way notifications) continued. Service commitmen | 49 | Admin & Legal | Expenses are roughly in-line with budget. | 49 | Environmental Assessment activities for the project are complete, except to the extent necessary for review and approval of route revisions, and for archeological site assessments required under the Programmatic Agreement. Archaeological staff have been contracted and the process was implemented for review of proposed construction activities in non-exempt areas. | 34 | As measured by expenditures, network design increased by 15% during the quarter as engineering firms continued to assist SFC with network design, route surveys and overall project management. Cumulative spending on Network Design through end of quarter exceeded the 30% projected in the previous PPR. | 0 | Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor added 4 staff members during the quarter to continue to identify parcels for which rights-of-way must be obtained, and where necessary contact property owners to obtain easements or other consents. | 75 | Expenses in this category are principally make-ready survey application fees. During the quarter, surveys were requested for 3,500 poles. Through the quarter, surveys have been requested for approximately 70% of utility poles involved in the project. In addition, numerous applications were submitted during the quarter for railroads crossings, interstate highway crossings, and municipal and state roadways. | 24 | Expenses in this category are principally for make-ready work by pole owners and third party attachees. Cumulative expenditures in this category increased from 15% to 24% of budget during the quarter, exceeding the forecast by 2%. SFC has authorized make-ready work for approximately 59% of utility poles involved in the project. Delayed make-ready billing by third parties and lower-than-budgeted unit costs for make ready are the primary reason for the variance between spending variance and activity completion indicators. | 2 | Expenditures on equipment procurement trail the baseline projection of 40% for end of the quarter, as SFC has not yet started to purchase the principal electronic equipment -- packet optical and routers -- needed for the project. Vendor proposals for packet optical equipment were obtained and, as of the end of quarter, under technical review. An RFQ for IP Routers has been drafted and is near release as of end of quarter. Although execution of the electronics contracts trails the original milestone, additional time taken to finalize equipment specifications and select a vendor will not delay completion of the project. | 9 | Outside plant construction expenditures are behind the original baseline projection (of 50% complete by end of this quarter) due to initial project delays associated with Special Award Condition 10 were resolved and the FONSI obtained. The gap between actual and original projected expenditures will narrow as outside plant construction jobs are released to contractors. A contract for construction of 90 miles of plant was awarded during the quarter, and construction started in mid-December. 22 miles of strand were attached to poles by close of the quarter. A contractor was selected during the quarter for an additional 62 miles of outside plant construction, and bid package prepared for another 58 miles. By the end of the quarter, SFC had received 1.2 million feet of fiber-optic cable in preparation for construction in 2012. | 5 | SFC applied during the quarter for collocation permits for 2 additional collocation sites owned by third parties, bringing the total to date to 13. Preparation of the spaces -- primarily power system augments and rack installation -- by location owners are in varying stages of completion. | 5 | Although no budgeted expenses fall within this reporting category, a baseline projection for Network Testing was made to reflect anticipated fiber testing and network verification. Fiber delivered by vendors has been tested before deployed to the field. Network testing will follow completion of network segments. | 2012-02-22 17:34 | 2012-02-22 17:34 | 6334 | 6334 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2012 | Q1 | Q1 - 2012 | 6001 | 5600 | TRUE | 20 | Most of the variance between actual spending to date and the baseline spending is due to delays in electronic equipment purchases and outside plant construction. OSP construction in turn, has been constrained by the limited number and locations of make-ready licenses issues. Overall, however, SFC has made signficant progress on parallel fronts to assure that the network can be constructed within the schedule required by NTIA. SFC has a substantial stock of fiber optic cable. All pole and route design survey work has been released to contractors. Make-ready has been requested on 68% of poles. Licenses have been obtained on 38% of poles. Service commitments have been obtained for 183 community anchor locations. | 57 | Admin & Legal Expenses | Expenses are roughly in line with the 58% projected for the quarter in the previous PPR. | 49 | No expenses were incurred during the quarter for environmental assessment work. Environmental Assessment activities for the project are complete, except to the extent necessary for review and approval of route revisions, and archeological site assessments required under the Programmatic Agreement. Archeological staff have been contracted and the process was implemented for review of proposed construction activities in non-exempt areas. | 49 | As measured by expenditures, network design increased from 34% to 49% during the quarter as engineering firms continued to assist SFC with network design, route surveys and overall project management. Cumulative spending on Network Design through the quarter is consistent with the 49% that was projected in the previous PPR. | 0 | Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor continued during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 96 | Expenses in this category are principally make-ready survey application fees. During the quarter, surveys were requested for approximately 1,500 poles. Through the quarter, surveys have been requested for approximately 77% of the utility poles involved in the project. In addition, numerous permits were received during the quarter for railroad crossings, interstate highway crossings, municipal and state roadways. Additional permits applications were submitted during the quarter for the same. | 32 | Expenses in this category are principally for make-ready work by pole owners and third party attachees. Cumulative expenditures in this category increased from 24% to 32% of budget during the quarter, on target with the 32% projected in the previous PPR. Make-ready work has been authorized on roughly 68% of the poles encompassed by the project. Pole attachment licenses were issued during the quarter for 9,100 poles -- approximately 39% of the poles encompassed by the project. Delayed make-ready billing by third parties and lower-than-budgeted unit costs for make-ready are the primary reasons for the variance between indicators of spending and activity completion. | 2 | Expenditures on equipment procurement trail the baseline projection of 50% and previous PPR projection of 16% budget spent by end of the quarter, as SFC has not yet started to purchase the principal electronic equipment -- packet optical and routers -- needed for the project. During the quarter, SFC issued an RFQ and RFP for routers, obtained proposals from vendors, and exchanged technical specifications with vendors. As of end of quarter, SFC was negotiating contract terms with a packet optical equipment vendor, and awaiting revised pricing from router vendors. Although equipment procurement trails the original milestone in terms of overall spending, the additional time taken to select vendors will not delay completion of the project. | 16 | Outside plant construction expenditures, which were projected in the original baseline plan to be 55% of budget the end of this quarter have been constrained by several factors. Those initially included project delays associated with Special Award Condition 10 and issuance of a FONSI following the environmental assessment. Subsequently, the overall volume of make-ready completion has been less than projected due to diversion of utility crews, as well as pole inventory, to restore plant damaged by severe weather in Vermont and nearby states. Last, outside plant construction has been constrained by locations of make-ready work completed by pole owners; much of the make-ready completed to date has not been geographically contiguous, limiting the ability to deploy construction crews to hang strand and cable. By end of quarter, roughly 37 miles of strand and 19 miles of cable had been installed. In spite of these challenges, progress during the quarter on make-ready and outside plant c | 6 | SFC's spending in this budget category is in line with the 6% projected in the previous PPR, although it trails the 40% baseline projection. The primary activity in this category is preparation of conditioned collocation space to house network equipment. During the quarter, SFC applied for collocation permits for 6 additional locations owned by third parties, bringing the total to date to 16. Preparation of the spaces by location owners were in varying stages of completion as of the end of quarter, with 10 locations having been released to SFC. | 10 | Although no budgeted expenses fall within this reporting category, a baseline project for Network Testing has been made to reflect anticipated fiber testing and network verification. Fiber delivered to vendors has been tested before delivered to construction contractors. Network testing will follow completion of network segments. | 2012-05-10 10:30 | 2012-05-10 10:30 | 6334 | 6334 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2012 | Q2 | Q2 - 2012 | 7241 | 6248 | TRUE | 28 | Most of the variance between actual spending to date and the baseline spending is due to delays in electronic equipment purchases and outside plant construction. OSP construction in turn, has been constrained by the limited number and locations of make-ready licenses issues. Overall, however, SFC has made significant progress on parallel fronts to assure that the network can be constructed within the schedule required by NTIA. SFC has a substantial stock of fiber optic cable. All pole and route design survey work has been released to contractors. Design is complete for 94% of network routes. Make-ready has been requested on 93% of poles. Licenses have been obtained on 52% of poles. Cable has been placed on 118 route miles. Service commitments have been obtained for 186 community anchor locations. | 78 | Admin & Misc. Expenses | Cumulative expenses at end of quarter slightly exceeded the 75% projected in the previous PPR. | 49 | No expenses were incurred during the quarter for environmental assessment work. Environmental Assessment activities for the project are complete, except to the extent necessary for review and approval of route revisions, and archeological site assessments required under the Programmatic Agreement. Archeological staff have been contracted and the process was implemented for review of proposed construction activities in non-exempt areas. | 65 | As measured by expenditures, network design increased from 49% to 65% during the quarter as engineering firms continued to assist SFC with network design, route surveys and overall project management. Cumulative spending on Network Design through the quarter exceeded the 60% that was projected in the previous PPR. | 0 | Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor continued during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Expenses in this category are principally make-ready survey application fees. During the quarter, surveys were requested for approximately 3,600 poles. Through the quarter, surveys have been requested for approximately 94% of the utility poles involved in the project. In addition, numerous permits were received during the quarter for railroad crossings, interstate highway crossings, municipal and state roadways. Additional permits applications were submitted during the quarter for the same. | 40 | Expenses in this category are principally for make-ready work by pole owners and third party attachees. Cumulative expenditures in this category increased from 32% to 40% of budget during the quarter, as compared to 46% projected in the previous PPR. Make-ready work has been authorized on roughly 78% of the poles encompassed by the project. Pole attachment licenses were issued during the quarter for 3,150 poles -- approximately 13% of the poles encompassed by the project. Delayed make-ready billing by third parties and lower-than-budgeted unit costs for make-ready are the primary reasons for the variance between indicators of spending and activity completion. | 2 | Expenditures on equipment procurement trail the baseline projection of 55% and previous PPR projection of 28% for end of the quarter, as SFC has not yet paid for the principal electronic equipment -- packet optical and routers -- needed for the project. However, during the quarter, SFC completed contract negotiations with a packet optical equipment vendor and placed an initial purchase order for $2.4 million - roughly a third of the project budget for equipment. SFC continued to negotiate with router vendors. Although equipment procurement trails the original milestone in terms of overall spending, the additional time taken to select vendors will not delay completion of the project. | 24 | Outside plant construction expenditures, which were projected in the original baseline plan to be 70% of budget at the end of this quarter have been constrained by several factors. Those initially included project delays associated with Special Award Condition 10 and issuance of a FONSI following the environmental assessment. Subsequently, the overall volume of make-ready completion was less than projected due to diversion of utility crews, as well as pole inventory, to restore plant damaged by severe weather in Vermont and nearby states. Currently, outside plant construction is constrained by locations of make-ready work completed by pole owners; portions of the make-ready completed to date has not been geographically contiguous, limiting the ability to deploy construction crews to hang strand and cable in an economic manner and without excessive cable splices. Nonetheless, 101 miles of strand and cable were installed during the quarter, bringing the cumulative total at end of qua | 12 | SFC's spending in this budget category trails the 39% projected in the previous PPR as well as the original, baseline projection of 50%. The primary activity in this category is preparation of conditioned collocation space to house network equipment. During the quarter, SFC applied for the last of collocation permits needed, four additional collocations facilities were released to SFC, bringing the total released to 14. | 10 | Although no budgeted expenses fall within this reporting category, a baseline project for Network Testing has been made to reflect anticipated fiber testing and network verification. Fiber delivered to vendors has been tested before being released to construction contractors. Network testing will follow completion of network segments. | 2012-08-24 16:01 | 2012-08-24 16:01 | 6334 | 6334 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2012 | Q3 | Q3 - 2012 | 8145 | 6783 | TRUE | 41 | Most of the variance between actual spending to date and the baseline spending has been due to delays in electronic equipment purchases and outside plant construction. However, initial purchase orders and receipts of packet optical network equipment as well as the release of all construction packages and an increased rate of construction resulted in a significant pick-up in spending during the quarter. Overall spending during the quarter totaled $5.9 million, and $19.2 million cumulatively. Roughly 173 miles of strand and fiber-optic cable were placed during the quarter, bringing the cumulative strand and fiber in place to 316 and 291 miles, respectively. In addition, DWDM gear was received, installed and tested at major network nodes. A contract was awarded and orders placed for IP router equipment, laying the foundation for substantial expenditures and installations during subsequent quarters. Design and fit-up of collocation facilities continued, with all but one facility comp | 86 | Admin & Legal Expenses | Cumulative expenses in this category increased during the quarter from 78% to 86% of budget, reflecting on-going administrative and legal expenses. | 49 | No expenses were incurred during the quarter for environmental assessment work. Environmental Assessment activities for the project are complete, except to the extent necessary for review and approval of route revisions, and as necessary for archeological site assessments required under the Programmatic Agreement. Archeological staff have been contracted and a process implemented for review of proposed construction in non-exempt areas. | 79 | As measured by expenditures, network design increased from 65% to 79% during the quarter as engineering firms continued to assist SFC with network design, route surveys and overall project management. Cumulative spending on Network Design through the quarter exceeded the 78% that was projected in the preceding PPR. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor continued during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Expenses in this category are principally make-ready survey application fees. Expenditures are exceeding the amount originally estimated. Over 700 poles were surveyed during the quarter. Through the quarter, surveys have been requested for approximately 22,500 utility poles involved in the project; any remaining surveys are likely to be associated with minor route or design changes. In addition, numerous permits were obtained during the quarter for railroad crossings, interstate highway crossings, and for work along municipal and state roadways. Additional permit applications were also submitted during the quarter for the same. | 54 | Expenses in this category are principally for make-ready work by pole owners and third party attachees. Cumulative expenditures in this category increased from 40% to 54% of budget during the quarter, as compared to 53% projected in the previous PPR. Make-ready work has been authorized on roughly 89% of the poles encompassed by the project. Pole attachment licenses were issued during the quarter for 2,800 poles -- approximately 12% of the poles encompassed by the project, bringing total obtained to 14,850 or roughly 63% of those needed. Lower-than-budgeted unit costs for make-ready are the primary reasons for the variance between indicators of spendng and activity completion. | 32 | DWDM and IP router electronic equipment purchased comprise most of this budget category. Cumulative expenditures through end of the quarter increased from 2% to 32% of budget during the quarter, slightly below the 36% spending estimated in the previous PPR. Phase 1, consisting of ten nodes was installed, tested and lit during this quarter. A contract was entered and purchase orders submitted for IP routers during the quarter. With contracts in place for all major equipment, and purchase orders placed for much of the stock required for project completion, procurement of equipment is not expected to delay project completion. | 31 | The original baseline plan estimated 85% of the network route would be complete by the end of 3Q2012. The variance between actual route miles placed and the initial forecast is principally due to delays associated with Special Award Condition 10 (resolution of overlap with other BTOP projects) and a prolonged issuance of a FONSI following completion of the environmental assessment. In the previous PPR, construction of 200 route miles was forecast for the third quarter. While outside plant construction has been constrained by the quantity and locations of make-ready work completed by pole owners, and to a lesser extent by the need to secure permits, contractors nonetheless placed approximately 173 route miles of fiber and strand, during the quarter, bringing the totals as of September 30th to 291 and 316 miles, respectively. Roughly two-thirds of the make-ready licenses necessary for project completion have been obtained, and all remaining bid packages were released to constructio | 40 | The primary activity in this category is preparation of conditioned collocation space to house network equipment. As of the end of quarter, all but one collocation space has been fully prepared. Spending is likely to be under budget in this category. | 25 | Although no budgeted expenses fall within this reporting category, a baseline projection for Network Testing has been made to reflect anticipated fiber testing and network verification. Fiber delivered to vendors has been tested before being released to construction contractors. Network testing will follow completion of network segments. | 2012-11-29 14:39 | 2012-11-29 14:39 | 5928 | 5928 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2012 | Q4 | Q4 - 2012 | 8781 | 7580 | TRUE | 55 | Overall spending during the quarter totaled $6.85 million, as compared to $7.8 million projected in the previous PPR. A total of $26.0 million has been spent to date. Most of the variance between actual spending to date and the baseline spending projection has been due to delays in outside plant construction in previous quarters. Roughly 377 miles of fiber cable and an additional 24 miles of strand were in place as of end of quarter. Packet optical electronic equipment has been placed at seven network nodes. | 95 |  | Cumulative expenses in this category increased during the quarter from 86% to 95% of budget, reflecting on-going administrative and legal expenses. | 49 | No expenses were incurred during the quarter for environmental assessment work. Environmental Assessment activities for the project are complete, except to the extent necessary for review and approval of route revisions, and as necessary for archeological site assessments required under the Programmatic Agreement. Archeological staff have been contracted and a process implemented for review of proposed construction in non-exempt areas. | 91 | SFC has design surveyed and applied for attachments to 97% of the estimated number of poles encompassed by the project. As measured by expenditures, network design increased from 79% to 91% during the quarter as engineering firms continued to assist SFC with network design, route surveys and overall project management. Site design drawings were completed for approximately 120 CAI's. Cumulative spending on Network Design through the quarter exceeded the 79% that was projected in the preceding PPR. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor continued during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Expenses in this category are principally make-ready survey application fees. Expenditures are exceeding the amount originally estimated. As remaining design work winds down, approximately 450 poles were surveyed during the quarter. Through the quarter, surveys have been requested for approximately 22,900 utility poles involved in the project; any remaining surveys are likely to be associated with minor route or design changes. In addition, numerous permits were obtained during the quarter for railroad crossings, interstate highway crossings, and for work along municipal and state roadways. Additional permit applications were also submitted during the quarter for the same. | 61 | Expenses in this category are principally for make-ready work by pole owners and third party attachees. Cumulative expenditures in this category increased from 54% to 61% of budget during the quarter, as compared to 62% projected in the previous PPR. Make-ready work has been authorized on roughly 94% of the poles encompassed by the project. Pole attachment licenses were issued during the quarter for 3,400 poles -- approximately 14% of the poles encompassed by the project, bringing total obtained to 18,250 or roughly 78% of those needed. Lower-than-budgeted unit costs for make-ready are the primary reasons for the variance between indicators of spending and activity completion. | 74 | In addition to packet optical equipment previously installed, SFC ordered additional equipment for two network nodes that will be installed during 1Q2013. Customer premise equipment was received by SFC. IP routers were delivered to a staging area during the quarter for configuration and testing. | 42 | During the quarter, contractors placed approximately 61 route miles of cable and 110 miles of messenger strand, bringing the totals as of December 31 to 377 miles of fiber and 401 miles of strand. Progress fell short of the 190 mile goal set for the quarter. Outside plant construction was constrained by the quantity and locations of make-ready work completed by pole owners, and to a lesser extent by need to secure permits. Dispatch of Vermont utility crews to Hurricane Sandy restoration along the Eastern seaboard decreased the pace of make-ready completion by pole owners and release of route segments to SFC to begin construction. | 41 | The primary activity in this category is preparation of conditioned collocation space to house network equipment. As of the end of quarter, all collocation space has been fully prepared. Spending is likely to be under budget in this category. | 30 | Although no budgeted expenses fall within this reporting category, a baseline projection for Network Testing has been made to reflect anticipated fiber testing and network verification. Fiber delivered to vendors has been tested before being released to construction contractors. Network testing will follow completion of network segments. | 2013-02-14 15:52 | 2013-02-14 15:52 | 5928 | 5928 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2013 | Q1 | Q1 - 2013 | 9943 | 8515 | TRUE | 65 | Overall spending during the quartered totaled $4.9 million, as compared to $11.4 million projected in the previous PPR. A total of $31.1 million has been spent to date. Most of the variance between actual spending to date and the baseline spending projection has been due to delays in outside construction in previous quarters. At the end of this reporting quarter 461 miles of fiber cable and an additional 71 miles of strand were in place. | 100 | 100% | Cumulative expenses in this category increased during the quarter from 95% to 100% of budget, reflecting on-going administrative and legal expenses. | 49 | No expenses were incurred during the quarter for environmental assessment work. Environmental Assessment activities for the project are complete, except to the extent necessary for review and approval of route revisions, and as necessary for archeological site assessments required under the Programmatic Agreement. Archeological staff have been contracted and a process implemented for review of proposed construction in non-exempt areas. | 97 | SFC has design surveyed and applied for attachments to 99% of the estimated number of poles encompassed by the project. As measured by expenditures, network design increased from 91% to 97% during the quarter as engineering firms continued to assist SFC with network design, route surveys and overall project management. The project has 133 (41%) of the sites in Stage 1&2 (Field Work), 46 sites (14%) Stage 3 (Site Drawings Complete), 121 sites (38%) in Stage 4 (Construction), and 21 sites (7%) in Stage 5 (OSP Complete) . | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor continued during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Expenses in this category are principally make-ready survey application fees. Expenditures are exceeding the amount originally estimated. As remaining design work winds down, an additional 250 poles were surveyed during the quarter. Through the quarter, surveys have been requested for 23,150 utility poles involved in the project; any remaining surveys are likely to be associated with minor design changes. Based on AAR changes, permits were submitted and obtained during the quarter for railroad crossings, interstate highway crossings, and for work along municipal and state roadways. | 70 | Expenses in this category are principally for make-ready work by pole owners and third party attachees. Cumulative expenditures in this category increased from 61% to 70% of budget during the quarter, as compared to 73% projected in the previous PPR. Make-ready work has been authorized on roughly 98% of the poles encompassed by the project. Pole attachment licenses were issued during the quarter for 2,250 poles (10% of all poles), total obtained to date is 20,500 (87%) out of 23,160. The variance between indicators of spending and activity completion reflects both lower-than-budgeted unit costs for make-ready and slower-than-projected completion of make-ready by pole owners and other attachees, in part due to the several storm events in previous quarters. | 93 | Packet optical equipment was installed and turned up during the quarter. IP router equipment configuration was tested and confirmed in a lab environment. SFC ordered and received $1.5M of equipment during the quarter. Cumulative spending on equipment is 7% lower than the previous projection, primarily due to deferral of installations until outside plant is ready. Deferred installation will allow for maximum useful life of back-up battery power supplies, which have a finite life. | 50 | Outside plant construction fell short of the 230 mile goal set for the quarter. Contractors placed approximately 84 route miles of cable and 131 miles of messenger strand, bringing the totals to 461 miles of fiber and 532 miles of strand. Winter weather conditions limited available work days during the quarter. Outside plant construction was constrained by make-ready work not being completed by pole owners, AAR approval delay for route modifications, and the securing of permits. Overall completion levels reflect the cumulative effects of Vermont utility crews being diverted to storm restoration work as a result of Hurricane Sandy, Tropical Storm Irene and a June 2012 severe wind event in southwestern New England. Utility owners deferred make-ready for the project while crews restored service, repaired damage and rebuilt destroyed utility plant. Construction work on 21 CAI drops is complete, with 121 of the 382 CAI locations being released to construction contractors. The rate at | 63 | The primary activity in this category is preparation of conditioned collocation space to house network equipment. As of the end of quarter, all collocation space has been fully prepared. Spending is likely to be under budget in this category. | 40 | Although no budgeted expenses fall within this reporting category, a baseline projection for Network Testing has been made to reflect anticipated fiber testing and network verification. Fiber delivered to vendors is tested before being released to construction contractors. Network testing will follow completion of network segments. | 2013-05-28 16:27 | 2013-05-28 16:27 | 5928 | 5928 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2013 | Q2 | Q2 - 2013 | 10425 | 8855 | TRUE | 73 | By the end of this reporting quarter, 627 miles of fiber had been placed.Overall spending during the quarter totaled $3.1 million, as compared to $9.2 million projected in the previous PPR, with a total of $34.2 million spent to date. The primary factors for this difference were: delivery of a dark fiber IRU into 3Q2013, postponement of electronics orders in line with core transport route completion and related equipment installation charges. | 100 | NA | Administration of the project is ongoing. | 49 | Spending through the end of the quarter was in line with the 49% projected in the previous PPR. Additional expenses may be incurred as necessary if required for archeological site assessments. | 98 | Engineering firms will continue to assist SFC with network design and overall project management. Route surveys for the entire project are substantially complete. Most design work during the quarter will focus on service location entrance facilities. AAR#5: Network design is 100% complete | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will continue during the quarter to obtain easements or other consents where required. | 100 | VFC: Expenses in this category were principally application fees for make-ready surveys, all of which have been undertaken other than for potential, minor design changes. In addition, various permits were submitted and obtained during the quarter for railroad crossings, interstate highway crossings, and for work along municipal and state roadways. Expenditures exceeded the amount originally estimated. AAR#5: All applications have been submitted and 60% of the aerial pole licenses have been received. Awaiting receipt of 2 RR permits. | 71 | Expenses in this category are principally for make-ready work by pole owners and third party attachees. Cumulative expenditures in this category increased from 70% to 71% of budget during the quarter, as compared to 77% projected in the previous PPR. Make-ready work has been authorized for substantially all poles encompassed by the project. Licenses have been obtained for 21,810 (94%) of the 23,170 pole attachments applied for. AAR#5: All utility (power/telco) make ready is complete. Awaiting receipt of pole licenses. | 99 | The majority of IP router equipment has been installed. Portions of Phase 2 packet optical DWDM equipment were installed and turned up during the quarter. Phase 3 DWDM equipment was ordered. AAR#5: All materials have been ordered and due mid July | 60 | VFC: This quarter 221 route miles of fiber were placed, total of 627 on June 30. 96 route miles have been released for construction, 63 route miles pending receipt of permits and licenses. Construction of entrances to 187 CAIâ€™s has been completed, 64 locations became "ready to serve" this quarter with a total of 71 sites ready to serve in the project. AAR#5: Network build planned to commence on 8/5 to be complete 9/9 | 77 | The primary activity in this category is preparation of conditioned collocation space. All collocation space has been fully prepared. | 50 | Although no budgeted expenses fall within this reporting category, a baseline projection for Network Testing has been made to reflect anticipated fiber testing and network verification. Network testing will follow completion of network segments. The near-term emphasis is on testing strands that enable service to CAI's. | 2013-07-30 21:15 | 2013-07-30 21:15 | 5928 | 5928 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2013 | Q3 | Q3 - 2013 | 11421 | 9532 | TRUE | 84 | By the end of this reporting quarter, 763 miles of fiber had been placed. Overall spending during the quarter totaled $5.8 million, as compared to $12 million projected in the previous PPR, with a total of $39.7 million spent to date. The project experienced a delay finalizing a dark fiber IRU, and a postponement of electronics orders for core route completion, which in turn resulted in lower-than-forecast OSP construction completion. | 100 | Administration | Administration of the project is in-going. | 49 | Spending through the end of the quarter was in line with the 49% projected in the previous PPR. | 100 | Engineering firms continued to assist with network design and overall project management. Design work during the quarter focused on CAI and POI entrance facilities. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor continued during the quarter to obtain easements or other consents where required. | 100 | Nearly all remaining permits, including for railroad crossings, river crossings, interstate highway crossings, municipal and state roadway work permits, and land-use permits have been obtained. | 72 | At the beginning of the quarter 93% of pole licenses had been received, all poles involved with the project had make-ready requests, and by the end of the quarter, had obtained licenses for 95%. | 100 | Packet optical equipment was ordered and received. | 73 | Outside plant construction continued, as additional pole licenses, easements and other permits were obtained. During the quarter, 136 route miles of fiber were placed, bringing the total as of September 30 to 763 miles. An additional 18 route miles of in-place fiber were obtained from another carrier. Approximately 46 route miles remained to be placed. Construction of laterals and entrances to CAIâ€™s continues with work being released for construction. 236 locations are either in service ready or in service status, the remainder are in process of splicing, testing and provisioning. | 81 | The primary activity in this category is preparation of conditioned collocation space. All collocation space has been fully prepared. | 67 | Although no budgeted expenses fall within this reporting category, a baseline projection for Network Testing has been made to reflect anticipated fiber testing and network verification. Network testing will follow completion of network segments. The near-term emphasis is on testing strands that enable service to CAI's. | 2013-11-27 12:20 | 2013-11-27 12:20 | 5928 | 5928 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2013 | Q4 | Q4 - 2013 | 12637 | 10905 | TRUE | 93 | Overall spending during the quarter totaled $4.7 million, as compared to $4.6 million projected in the previous PPR, with a total of $44.7 million spent to date. | 100 | Administrative | Administration of the project is on-going. | 49 | Spending through the end of the quarter was in line with the 49% projected in the previous PPR. | 100 | Route surveys for the entire project are essentially complete with the exception of some small segments to reach the final POIs. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. | 100 | Nearly all remaining permits, including railroad crossings, river crossings, interstate highway crossings, municipal and state roadway work permits, and land-use permits have been obtained. | 73 | Substantially all pole attachment licenses required the project have been obtained. | 100 | Installation, configuration and launch of routers and DWDM nodes continued during the quarter. Network equipment was ordered and received. | 81 | Excluding laterals and drops to the 10 remaining CAI's and 20 remaining PoI's, Approximately 6 route miles of cable remained to be placed. Construction of laterals and entrances to CAIâ€™s continued during the quarter, with work being released for construction as site surveys and design for each location are completed. Construction of 97 CAI entrances were completed. All but 10 of the 316 CAIs were ready to serve by end of quarter. | 81 | The primary activity in this category is preparation of conditioned collocation space. All collocation space has been fully prepared. | 0 | This budget category has been included in line 2h above. Network testing continues through this period | 2015-01-21 14:19 | 2015-01-21 14:19 | 5928 | 5928 | Vermont Telecommunications Authority | TRUE
NT10BIX5570077 | 2010 | Q4 | Q4 - 2010 | 785 | 1823 | TRUE | 3 | No variance | 0 |  | N/A | 98 | Slightly ahead of the projected 95% | 60 | Slightly ahead of the projected 50% | 0 | N/A | 60 | Slightly behind the projected 80% due to easement issues encountered | 0 | N/A | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-01-28 15:20 | 2011-01-28 15:20 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2011 | Q1 | Q1 - 2011 | 2387 | 2939 | TRUE | 5 | Slightly ahead of projection due to earlier construction start than anticipated. | 0 |  | N/A | 100 | No variance | 100 | No variance | 0 | N/A | 100 | No variance | 0 | N/A | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-05-27 15:19 | 2011-05-27 15:19 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2011 | Q2 | Q2 - 2011 | 3211 | 3367 | TRUE | 10 | Variance is due to weather related construction delays in May and June | 0 |  | Match expenditures proportion to federal funds is skewed due to the up-front in-kind expenditures, including the environmental assessment consultant and design and permitting work | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 0 | No variance | 30 | Variance is a result of the accelerated schedule of the awarded construction vendor/contractor | 0 | No Variance | 0 | No variance | 2011-08-18 17:44 | 2011-08-18 17:44 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2011 | Q3 | Q3 - 2011 | 4039 | 3860 | TRUE | 65 | Accelerated construction by the Outside Plant Contractor | 0 |  | N/A | 100 | No variance | 100 | No variance | 0 | No Variance | 100 | No Variance | 0 | No Variance | 15 | Ahead of baseline because equipment has been ordered | 62 | Ahead of baseline: calculated on dollars spent | 0 | No variance | 0 | No variance | 2011-11-14 17:04 | 2011-11-14 17:04 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2011 | Q4 | Q4 - 2011 | 5427 | 5114 | TRUE | 79 | Variance due to accelerated construction contractor schedule | 0 |  | No Variance | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 75 | Variance due to accelerated construction contractor schedule | 67 | Variance due to accelerated construction contractor schedule | 40 | Variance due to accelerated construction contractor schedule | 40 | Variance due to accelerated construction contractor schedule | 2012-03-01 09:46 | 2012-03-01 09:46 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2012 | Q1 | Q1 - 2012 | 6019 | 5609 | TRUE | 79 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | N/A | 100 | No Variance | 0 | N/A | 100 | Variance due to accelerated construction progress | 80 | Variance due to accelerated construction progress | 80 | Variance due to accelerated construction progress | 80 | Variance due to accelerated construction progress | 2012-05-10 15:08 | 2012-05-10 15:08 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2012 | Q2 | Q2 - 2012 | 6991 | 6123 | TRUE | 83 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 100 | Variance due to accelerated construction | 90 | Variance due to accelerated construction | 90 | Variance due to accelerated construction | 90 | Variance due to accelerated construction | 2012-08-09 18:31 | 2012-08-09 18:31 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2012 | Q3 | Q3 - 2012 | 8031 | 6722 | TRUE | 92 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 100 | Variance due to accelerated construction progress | 100 | Variance due to accelerated construction progress | 98 | Variance due to accelerated construction progress | 90 | Variance due to accelerated construction progress | 2012-11-26 12:10 | 2012-11-26 12:10 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2012 | Q4 | Q4 - 2012 | 9017 | 7791 | TRUE | 100 | Variance due to accelerated construction. | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | Variance due to accelerated construction. | 2013-02-27 14:15 | 2013-02-27 14:15 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2010 | Q4 | Q4 - 2010 | 1321 | 2347 | TRUE | 3 | No variance | 0 |  | N/A | 98 | Slightly ahead of schedule. | 60 | 10% ahead of Baseline projected performance at 50% due to increased resource availability | 0 | N/A | 60 | 20% behind Baseline projected performance of 80% due to slower than anticipated performance of USFS and GTNPS | 0 | N/A | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-02-23 10:24 | 2011-02-23 10:24 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2011 | Q1 | Q1 - 2011 | 1759 | 2623 | TRUE | 5 | NO VARIANCE | 0 |  | N/A | 100 | NO VARIANCE | 100 | NO VARIANCE | 0 | N/A | 100 | NO VARIANCE | 0 | N/A | 0 | NO VARIANCE | 0 | NO VARIANCE | 0 | NO VARIANCE | 0 | NO VARIANCE | 2011-04-29 18:14 | 2011-04-29 18:14 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2011 | Q2 | Q2 - 2011 | 3213 | 3368 | TRUE | 22 | SLIGHTLY AHEAD OF PROJECTED FIGURE | 0 |  | N/A | 100 | NO VARIANCE | 100 | NO VARIANCE | 100 | NOW COMPLETE | 100 | NO VARIANCE | 0 | N/A | 0 | NO VARIANCE | 18 | SLIGHTLY BEHIND THE 20% PROJECTED DUE TO WEATHER DELAYS | 0 | BEHIND SCHEDULE DUE TO WEATHER DELAYS | 0 | NO VARIANCE | 2011-08-18 18:10 | 2011-08-18 18:10 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2011 | Q3 | Q3 - 2011 | 4183 | 3940 | TRUE | 38 | Invoices returned to contractor for itemization | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 0 | N/A | 0 | Equipment orders will be next quarter due to cash flow | 35 | Ahead of baseline: calculated on dollars spent | 0 | No Variance | 0 | No Variance | 2011-11-21 15:22 | 2011-11-21 15:22 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2011 | Q4 | Q4 - 2011 | 5349 | 5022 | TRUE | 53 | Variance is due to construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 0 | Variance is due to change in equipment procurement timeline to accommodate recipient budget cycle | 35 | Variance is due to construction progress | 0 | Equipment Deployment altered to accommodate recipient budget cycle | 0 | Network Testing altered to accommodate recipient budget cycle | 2012-02-28 14:08 | 2012-02-28 14:08 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2012 | Q1 | Q1 - 2012 | 6021 | 5610 | TRUE | 53 | Variance is due to construction halt during winter weather and recipient budget cycle | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 10 | Variance is due to change in equipment procurement timeline to accommodate recipient budget cycle | 37 | Variance is due to construction progress | 0 | Variance is result of equipment procurement timeframe and, therefore, no equipment being installed | 0 | Variance is result of equipment procurement timeframe and, therefore, no equipment being installed | 2012-05-10 15:10 | 2012-05-10 15:10 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2012 | Q2 | Q2 - 2012 | 6937 | 6096 | TRUE | 60 | Variance due to slight slow start to construction start and recipient budget cycle | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 50 | Variance due to anticipated summer construction progress and plan to complete project by year-end | 37 | Variance due to construction progress and change in equipment procurement timeline to accommodate recipient budget cycle | 15 | Variance due to change in equipment procurement timeline to accommodate recipient budget cycle | 10 | Variance due to change in equipment procurement timeline to accommodate recipient budget cycle | 2012-08-08 17:04 | 2012-08-08 17:04 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2012 | Q3 | Q3 - 2012 | 8033 | 6723 | TRUE | 70 | Variance due to slight slow construction start for 2012 season and recipient budget cycle | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 90 | No Variance | 37 | Variance due to construction progress and change in equipment procurement timeline to accommodate recipient budget cycle | 25 | Variance due to construction progress and change in equipment procurement timeline to accommodate recipient budget cycle | 10 | Variance due to construction progress and change in equipment procurement timeline to accommodate recipient budget cycle | 2012-11-26 12:14 | 2012-11-26 12:14 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2012 | Q4 | Q4 - 2012 | 9131 | 7914 | TRUE | 96 | Variance due to construction progress and change in equipment procurement timeline to accommodate recipient budget cycle. | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 88 | Variance due to construction progress and change in equipment procurement timeline to accommodate recipient budget cycle. | 96 | Variance due to construction progress. | 99 | Variance due to construction progress. | 99 | Variance due to construction progress. | 2013-03-06 18:29 | 2013-03-06 18:29 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2013 | Q1 | Q1 - 2013 | 11431 | 9547 | TRUE | 100 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-12-03 11:30 | 2013-12-03 11:30 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570079 | 2010 | Q4 | Q4 - 2010 | 999 | 2044 | TRUE | 2 | Consistent with Baseline | 0 | CAI Connection | Consistent with Baseline | 98 | Need to submit final NEPA, Matrix Comments completed, need final FONSI - Baseline had at 80% | 16 | Consistent with Baseline | 11 | Consistent with Baseline | 5 | Consistent with Baseline | 0 | Consistent with Baseline | 0 | Consistent with Baseline | 0 | Consistent with Baseline | 0 | Consistent with Baseline | 0 | Consistent with Baseline | 2011-02-07 19:01 | 2011-02-07 19:01 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2011 | Q1 | Q1 - 2011 | 2063 | 2777 | TRUE | 3 | Under projected 10% baseline - delays from make-ready, route changes and related design changes, and FONSI not recieved until January 2011. With construction beginning, project will proceed quickly. | 0 | CAI Connection | Consistent with Baseline | 0 | Under projected 100% baseline - percentage completed based on grant funding - EA currently funded outside of the grant so 0% grant funding completion. Actual project completion is 80% as the initial FONSI has been received. Current work is monitoring and EA amendments. Future activities may impact this funding. | 26 | Under projected 39% Baseline - delays from make-ready, anchor site changes and related design changes, and FONSI not received until January 2011. | 0 | Under projected 43% Baseline - budget for this was minimal to cover contractor processing of applications which is currently under design budget. Actual project progress is approximately 40% complete. This will change with Award Action Request to adjust budget to recognize ROW as in-kind. This will adjust when approved. | 0 | Under projected 40% Baseline - budget for this was minimal to cover contractor processing of applications which is currently under design budget. Actual project progress is approximately 20% complete. This will change with Award Action Request to adjust budget to recognize ROW as in-kind and will cause break out of permitting from design budget. | 0 | Under projected 15% Baseline - delays from CAI add / drops, route changes and pending EA review, and CAI inside wiring pathways. | 1 | Under projected 16% Baseline - delays from make-ready, anchor site changes and related design changes, and FONSI not received until January 2011. Award Action Request for Budget Reprogram Amendment under review. Will progress quickly next quarter as procurement and construction begin. | 0 | Slightly under projected 3% Baseline - delays from make-ready, anchor site changes and related design changes, and FONSI not received until January 2011. Will progress quickly next quarter as procurement and construction begin. | 0 | Consistent with Baseline | 0 | Consistent with Baseline | 2011-05-16 18:36 | 2011-05-16 18:36 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2011 | Q2 | Q2 - 2011 | 3105 | 3310 | TRUE | 16 | Under projected 27% baseline - due to delays from make-ready, fiber deliveries, permitting, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. | 0 | CAI Connection | Under projected 18% baseline - due to delays from make-ready, fiber deliveries, permitting, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. Several sites actually wired but need FODU completed to connect along with signed Service Level Agreement - in progress. | 90 | Was at projected 100% baseline with completion of FONSI. However, with required route changes under design, will require a Award Action Request for route changes with included EA Amendment - under Development. | 44 | Under projected 57% baseline - due to delays from make-ready, fiber deliveries, permitting, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. | 40 | Under projected 56% Baseline - 3 of 7 cities completed, others in progress. | 44 | Under projected 60 % Baseline but rapidly progressing. Municipal permits - 11 of 25 received, Railroad Permits - 2 of 9 received. | 25 | The inside wiring path to code and ready in approximately 40 of the projected 160 CAI sites. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment not part of grant. | 10 | 18.6 Middle Miles constructed of projected ~180 total network miles | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment not part of grant. | 0 | Need to get 1st FODU (Fiber Optic Distribution Unit) model constructed to test fiber, final design under review. | 2011-08-16 00:46 | 2011-08-16 00:46 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2011 | Q3 | Q3 - 2011 | 4163 | 3930 | TRUE | 30 | Under projected 43% baseline - due to delays from Portland General Electric make-ready, RoW permitting/franchising, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. | 0 | Anchor Site Connection | Under projected 48% baseline - due to delays from Portland General Electric make-ready, RoW permitting/franchising, route changes and related design changes. Current escalated construction should realign with baseline over next several quarters. Several sites actually wired but need Fiber Optic Distribution Unit completed to connect along with signed Service Level Agreement - in progress. | 95 | Was at projected 100% baseline with completion of FONSI. However, with required route changes under design (Highway 26 and Canby re-route), will require an Award Action Request for route changes with included Environmental Assessment Amendment â€“ under Development. | 83 | Over projected 76% baseline â€“ Network Design is expected to be completed over the next few quarters once Highway 26 and Canby re-route are determined along with finalized Anchor sites. | 56 | Under projected 68% baseline - 5 of 9 cities completed, others in progress. We expect to reach the next quarter projected baseline of 77% with an additional 2 cities (for a total of 7) by this next quarter Q4. | 88 | Over projected 80 % baseline. Municipal permits -25 of 25 received, Railroad Permits - 5 of 9 received. | 73 | The inside wiring path to code and ready in approximately 90 of the projected 123 anchor site sites. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment not part of grant. | 24 | 44 Middle Miles constructed of projected ~180 total network miles Total middle mile construction is less due to RoW issues and pole make-ready in Milwaukie and Oregon City. Crews ready to rapidly make up the construction lag once issues resolved. Will be close to baseline in the next quarter. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment not part of grant. | 0 | Need to get 1st Fiber Optic Distribution Unit (FODU) model constructed to test fiber, final design under review. | 2011-11-20 17:37 | 2011-11-20 17:37 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2011 | Q4 | Q4 - 2011 | 5059 | 4730 | TRUE | 42 | Under projected 56% baseline due to delays from Right of Way permitting/franchising, route changes in a US National Forest, and related design changes. Based on an AAR covering these refinements and their associated schedule changes, and booking at least $1.8 million of additional match, the overall project progress should realign with baseline by Q2 2012. | 0 | CAI Connection | Under projected 68% baseline due to delays with city RoW permitting/franchising issues, route changes and related design changes, delays in utility pole make-ready, and anchor sites returning signed service level agreements, . Because of the late start, coupled with these delays, we do not expect the number of CAIs served to realign with projections until Q2 2013. | 98 | The Environmental Assessment (EA) was at projected 100% baseline with completion of FONSI; however, the EA for the roughly 2 mile re-route in the US National Forest on Highway 26 is currently in process. | 86 | On target with projected 86% baseline â€“ Network Design is expected to be completed over the next few quarters once Oregon City and Canby re-routes are determined along with finalized anchor sites. | 67 | Under projected 77% baseline. We have Right-of-Way (RoW) authority from 6 of 9 cities. We have encountered RoW permitting challenges with Oregon City. Negotiations continue; however, we are working on an alternate route around Oregon City if efforts are not successful in addressing this issue in a manner that doesnâ€™t threaten sustainability. This re-route would require NTIA review and approval via an Award Action Request (AAR). We expect RoW to realign with projected baseline by the end of Q2 2012. | 90 | On target with the projected 90% baseline. Municipal permits: 46 of 48 received; Railroad Permits: 5 of 6 received; PGE Permits: 2771 of 3077 received. | 80 | Over projected 70% baseline - site prep has been completed for 98 of the projected 123 construction anchor sites. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 36 | Under projected 43% baseline. We have built 65 route miles. Due too route changes, we now project a total of 167 miles of fiber to be installed by the end of June 2013. This adjustment will be reflected in an AAR we plan to submit in February 2012. Based on this AAR adjustment, we expect to realign with the baseline during Q2 2012. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 23 | Under projected 36% baseline â€“Due to RoW permitting/franchising issues, we were unable to place fiber as scheduled, hence testing was delayed. With the late start, coupled with the delays in Oregon City and in the US National Forest , we do not expect network testing to realign with projections until Q2 2013. | 2012-02-15 20:37 | 2012-02-15 20:37 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2012 | Q1 | Q1 - 2012 | 5903 | 5551 | TRUE | 68 | Under projected 71% baseline-The overall project progress should realign with baseline by end of Q3 2012. | 25 |  | Under projected 82% baseline â€“ An Award Action Request was submitted in Q1 2012 asking to change lateral routes to anchor sites that would be more cost effective. Once the Award Action Request is approved, our contractor can start connecting the anchor sites we had included in the Award Action Request. We do not expect the number of CAIs served to realign with projections until Q2 2013. | 98 | The Environmental Assessment (EA) was at projected 100% baseline with completion of FONSI; however, the EA for the roughly 2 mile re-route in the US National Forest on Highway 26 is currently in process. | 86 | Under projected 87% baseline â€“ Network Design is expected to be completed over the next few quarters. Network design is expected to realign with projected baseline by end of Q3 2012. | 78 | Under projected 82% baseline. We have Right-of-Way (RoW) authority from 7 of 9 cities. We expect RoW to realign with projected baseline by the end of Q3 2012. | 87 | Under projected 90% baseline. Municipal permits: 62 of 63 received; Railroad Permits: 5 of 6 received; PGE Permits: 2837 of 3257 received. We expect to realign with projected baseline by the end of Q2 2012. | 93 | Over projected 80% baseline - site prep has been completed for 114 of the projected 123 construction anchor sites. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 62 | Over projected 61% baseline. We have built 38 route miles in Q1 2012 bringing the project total to 103 route miles built out of 167 projected. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 43 | Under projected 52% baseline â€“Due to RoW permitting/franchising issues, we were unable to place fiber as scheduled, hence testing was delayed. We expect network testing to realign with projections in Q3 2012. | 2012-05-01 20:49 | 2012-05-01 20:49 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2012 | Q2 | Q2 - 2012 | 6829 | 6041 | TRUE | 79 | Under projected 82% baseline-The overall project progress should realign with baseline by the end of Q3 2012. | 46 | CAI Connection | Under projected 96% baseline â€“ Our Award Action Request that was submitted in March 2012 is approved and our contractor is connecting anchor sites utilizing the approved routes. We do not expect the number of CAIs served to realign with projections until Q2 2013. | 100 | Complete - Continued environmental monitoring by contractor pursuant to procedures established in the Field Manual. | 95 | Over projected 89% baseline â€“ Network Design is expected to be complete by the end of Q3 2012. | 78 | Under projected 87% baseline. We have Right-of-Way (RoW) authority from 7 of 9 cities. We expect RoW to realign with projected baseline by the end of Q3 2012. | 88 | Under projected 90% baseline. Municipal permits: 77 of 78 received; Railroad Permits: 10 of 10 received; PGE Permits: 3250 of 3720 received. We expect to realign with projected baseline by the end of Q3 2012. | 100 | Over projected 95% baseline - site prep has been completed for 123 of the projected 123 construction anchor sites. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 81 | Over projected 74% baseline. We have built 32 route miles in Q2 2012 bringing the project total to 135 route miles built out of 167 projected. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 64 | Under projected 68% baseline â€“Due to RoW permitting/franchising issues, we were unable to place fiber as scheduled, hence testing was delayed. We expect network testing to realign with projections in Q3 2012. | 2012-08-01 17:10 | 2012-08-01 17:10 | 5569 | 5569 | Clackamas, County of | TRUE
NT10BIX5570079 | 2012 | Q3 | Q3 - 2012 | 7893 | 6651 | TRUE | 87 | Under projected 93% baseline-The overall project progress should realign with baseline of 99% by the end of Q4 2012. | 73 |  | Under projected 100% baseline â€“ Our AAR that was submitted in March 2012 is approved and our contractor is connecting anchor sites utilizing the approved routes. We do not expect the number of CAIs served to realign with projections until Q2 2013. | 100 | 100% baseline - Continued environmental monitoring by contractor pursuant to procedures established in the Field Manual. | 98 | Over projected 95% baseline â€“ Network Design is complete with the exception of the 4 miles on Mt Hood for the Portland General Electric Reliability Project. | 78 | Under projected 94% baseline. We have Right-of-Way (RoW) authority from 7 of 9 cities. We expect RoW to realign with projected baseline by the end of Q4 2012. | 96 | Over projected 95% baseline. Municipal permits: 80 of 82 received; Railroad Permits: 10 of 10 received; Portland General Electric Permits: 3389 of 3540 received. | 100 | Met projected 100% baseline. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 94 | Over projected 87% baseline. We have built 22 route miles in Q3 2012 bringing the project total to 157 route miles built out of 169 projected. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 68 | Under projected 84% baseline â€“Due to RoW permitting/franchising issues, we were unable to place fiber as scheduled, hence testing was delayed. Network testing will not be complete until the close of the project, Q2 2013. | 2012-11-15 10:31 | 2012-11-15 10:31 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2012 | Q4 | Q4 - 2012 | 8893 | 7682 | TRUE | 93 | Under projected 99% baseline-The overall project progress will realign with baseline by the end of Q2, 2013. | 75 | Anchor Site Connection | Under projected 100% baseline â€“We do not expect the number of CAIs served to realign with projections until Q2 2013 | 98 | Though we reported 100% in the last PPR, 4 miles of new poles are being relocated by the local electric utility. Once the poles are placed, the environmental assessment will be completed and a route AAR submitted. | 98 | Under projected 100% baseline â€“ Network Design is complete with the exception of the 4 miles on Mt Hood for the Portland General Electric Reliability Project. Once we have the design drawings from PGE, we can then complete the design for our network. | 78 | Under projected 100% baseline. We have Right-of-Way (RoW) authority from 7 of 9 cities. | 99 | Under baseline by 1%. Municipal permits: 82 of 82 received; Railroad Permits: 10 of 10 received; Portland General Electric Permits: 3495 of 3540 received. | 100 | Met projected 100% baseline. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 93 | Under projected 100% baseline. We have 12 route miles remaining to complete the project. Completion is not expected until Q2, 2013. Previously, the county was inadvertently recording sheath miles here. We have made the adjustment to reflect route miles built compared to route miles in the Baseline. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 58 | Under projected 100% baseline. This is less than reported last quarter because we had to add a hub on the existing route to make the design work. This increased the number in the denominator of this calculation, which reduced the percent complete. Network testing will not be complete until the close of the project, Q2 2013. | 2013-02-21 20:17 | 2013-02-21 20:17 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2013 | Q1 | Q1 - 2013 | 9853 | 8464 | TRUE | 96 | Under projected 99% baseline-The overall project progress will realign with baseline by the end of Q2, 2013. Note that the Q4 2012 PPR report had this figure at 97% complete. This was inaccurate because we had calculated additional in-kind match that should not have been figured in to the overall project calculation. We have made the adjustment for Q1, 2013. | 84 |  | Under projected 100% baseline â€“We do not expect the number of CAIs served to realign with projections until Q2 2013. | 98 | Under baseline by 2%, this is 3 miles of new poles being relocated by local electric utility before we can attach to them. | 98 | Under projected 100% baseline â€“ Network Design is complete with the exception of the 3 miles on Mt Hood for the Portland General Electric Reliability Project. Once we have the design drawings from PGE, we can then complete the design for our network. | 89 | Under projected 100% baseline. We have Right-of-Way (RoW) authority from 8 of 9 cities. | 99 | Under baseline by 1%. Municipal permits: 82 of 82 received; Railroad Permits: 10 of 11 received; Portland General Electric Permits: 3495 of 3540 received. | 100 | Met projected 100% baseline. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 98 | Under projected 100% baseline. We have 3 route miles remaining to complete the project. Completion is not expected until Q2, 2013. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 98 | Under projected 100% baseline. Due to RoW permitting/franchising issues, we were unable to place fiber as scheduled, hence testing was delayed. Network testing will not be complete until the close of the project, Q2 2013. | 2013-05-21 17:44 | 2013-05-21 17:44 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2013 | Q2 | Q2 - 2013 | 10681 | 9002 | TRUE | 97 | Under projected 100% baseline. Completion is expected by the end of Q3, 2013. | 88 |  | Under projected 100% baseline. We do not expect the number of CAI's served to realign with projections until the end of Q3, 2013. | 100 | Complete. | 100 | Complete. | 89 | Under projected 100% baseline. We have Right-of-Way (RoW) authority from 8 of 9 cities. | 99 | Under baseline by 1%. Municipal permits: 82 of 82 received; Railroad Permits: 10 of 12 received; Portland General Electric Permits: 3540 of 3540 received. | 100 | Complete. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 97 | Under projected 100% baseline. We have 5 route miles out of 180 remaining to complete the project. Completion is expected by the end of Q3, 2013. The percent complete is slightly lower than last quarter report due to an approved route change and the increased total route mileage. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 91 | Under projected 100% baseline. Completion is expected by the end of Q3, 2013. We inadvertently reported as 98% complete last quarter when it should have been 88%. | 2013-08-21 15:17 | 2013-08-21 15:17 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2013 | Q3 | Q3 - 2013 | 11945 | 10111 | TRUE | 100 | Project Complete. | 100 |  | Project Complete. | 100 | Project Complete. | 100 | Project Complete. | 100 | Project Complete. | 100 | Project Complete. | 100 | Project Complete. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 100 | Project Complete. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 100 | Project Complete. | 2014-03-13 10:03 | 2014-03-13 10:03 | 5569 | 5569 | Clackamas, County of | TRUE
NT10BIX5570080 | 2010 | Q4 | Q4 - 2010 | 1249 | 2280 | TRUE | 0 | No Variance from Baseline | 0 |  | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 2011-02-20 21:39 | 2011-02-20 21:39 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2011 | Q1 | Q1 - 2011 | 2241 | 2866 | TRUE | 4 | Due to the delay in receipt of a FONSI, OnWav's has not been able to begin and expend funds related to components of the deployment which have the FONSI as a prerequisite. OnWav is preparing plans for expenditure to ensure that the project can be accelerated once the FONSI is complete, but it is expected to take multiple quarters to catch up. | 0 |  | No Variance from Baseline | 100 | OnWav has completed all Tribal and FWS submissions and received clearance. Additionally, all SHPO documentation has been completed, however the SHPO has only issued Clearance on 9 of the 10 proposed installation sites (2 of 3 proposed new towers). OnWav is continuing to consult with the SHPO in order to alleviate all remaining concerns. Once the SHPO clears the final proposed Tower, OnWav's environmental firm will accelerate work to have a finalized EA ready quickly and request the FONSI be expedited to help get OnWav back on track. | 0 | OnWav has begun initial analysis of the Final Network design. Finalization will be dependent on vendor selection. In order to get back on track, OnWav is including RF design as a required component of an RFP to be released early in Q2 2011. | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 2011-05-23 10:11 | 2011-05-23 10:11 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2011 | Q2 | Q2 - 2011 | 3235 | 3380 | TRUE | 5 | Due to the delay in receipt of a FONSI, OnWav has not been able to begin expending funds related to components of the deployment which have the FONSI as a prerequisite. OnWav is preparing plans for expenditure to ensure that the project can be accelerated once the FONSI is complete, but it is expected to take multiple quarters to catch up. | 0 | BSS-OSS | OnWav's plans for BSS and OSS systems have been temporarily put on hold pending the 3rd party match support. OnWav is working on a plan which will not only bring progress on this category back to schedule, but complete it early. In the meantime, progress will be slow until the new plan can be implemented. OnWav hopes to have this resolved by the end of 2011 if not sooner. | 100 | No Variance from Baseline | 0 | OnWav has begun initial analysis of the Final Network design. However, finalization was not completed because it is dependent on both vendor selection as well as plans and benefits of working with the 3rd party who will be providing matching support. In order to get back on track OnWav will be issuing a new RFP for equipment which will also include Network design finalization. Due to FONSI delays, it is expected that it will take multiple quarters to catch up. | 0 | No Variance from Baseline | 0 | Due to the delay in receipt of a FONSI, OnWav has not been able to begin expending funds related to components of the deployment which have the FONSI as a prerequisite. OnWav is revising it's plans to take advantage of new relationships with a 3rd party who will be providing matching support, however it is expected to take multiple quarters to catch up/ | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 2011-08-19 14:10 | 2011-08-19 14:10 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2011 | Q3 | Q3 - 2011 | 4291 | 3996 | TRUE | 6 | Due to the delay in receipt of a FONSI, and approvals necessary to reorganize OnWav's new budget and new matching contribution plans, as well as delays as a result of the impending change in ownership, OnWav had to postpone further deployment. OnWav is preparing to issue multiple RFPs at the beginning of the next quarter. Additionally, by the end of the year, OnWav will finalize an initial IRU, formally securing an initial match contribution and providing a major step forward in this project, but it is expected to take multiple quarters to catch up. | 0 | BSS-OSS | OnWav's plans for BSS and OSS systems have been temporarily put on hold pending the 3rd party match support and pending change in ownership. OnWav hopes to have this resolved by the end of 2011 if not sooner. OnWav's new match partner and pending owner, which will be finalized in Q4 2011, will be providing these services and thus OnWav will be able to catch up very quickly in this category by utilizing their system. | 100 | No Variance from Baseline | 0 | OnWav has begun initial analysis of the Final Network design. However, finalization was not completed because it is dependent on both vendor selection as well as plans and benefits of working with the 3rd party who will be providing matching support. In order to get back on track OnWav made modifications to the technology used in its network to take advantage of match opportunities from a new partner. OnWav will issue an RFP for RF Engineering at the beginning of the next quarter to assist in finalizing the network design. OnWav believes that it will be caught up at the end of the year, or early in the first quarter of 2012. | 0 | No Variance from Baseline | 0 | Due to the delay in receipt of a FONSI, OnWav was not been able to begin expending funds related to components of the deployment which have the FONSI as a prerequisite. Further progress was delayed due to the impending change in ownership of OnWav. OnWav has revised its plans to take advantage of new relationship with the future owner who will provide matching support in the form of dark fiber. Much of this fiber is already existing, as such there will be minimal change in necessary permits and other approvals, however it is expected to take multiple quarters to catch up to OnWav's Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 0 | No Variance from Baseline | 2011-11-28 16:41 | 2011-11-28 16:41 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2011 | Q4 | Q4 - 2011 | 5125 | 4792 | TRUE | 40 | OnWav made substantial progress this quarter. The signing of an IRU for a large portion of the Fiber network provided all of the 20% match contribution for this project. Additionally, the acquisition of the land for the three new towers ensures that construction is able to begin as soon as the tower designs are complete. OnWav anticipates that it will be back on schedule in early 3rd Quarter 2012 | 0 | BSS-OSS | OnWav's plans for BSS and OSS systems are pending finalization based on the Equipment Contract award. However, once this is complete, OnWav expects it will not only bring progress on this category back to schedule, but complete it early. | 100 | No Variance from Baseline, OnWav will be conducting additional new environmental analysis regarding the new fiber acquisition in early 2012 | 0 | OnWav has finalized the Fiber route portion of the network design and is planning on placing an order for networking equipment in early 2012. This was completed entirely with internal resources, and so was done at no cost to the grant. However, finalization of the last mile portion of the network was not completed because it is dependent on equipment vendor selection which is still under review. OnWav believes that it will be caught up in the first quarter of 2012. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav is still working to finalize the lease agreements for the collocation sites, but does not anticipate capital costs with such efforts. | 0 | OnWav has been delayed in this category as a result of the pending Equipment Request for Proposal and Tower Construction Request for Proposal which are still in the review phase. However, both RFPs should be awarded in Q1 2012 and the process of acquiring permits can begin. | 0 | OnWav has purchased the land associated with the construction of the three new towers, but due to the delay in awarding the Tower Construction RFP, OnWav has not begun new tower construction. However, OnWav expects to begin work on this category in early 2012. | 0 | OnWav is still reviewing candidates for Equipment vendor and anticipates making an award in early 2012. | 99 | OnWav completed acquisition of over 190 miles of an expected approximately 210 miles of IRUs planned for in the network. | 0 | OnWav has been delayed in this category as a result of the pending Equipment Request for Proposal which is still in the review phase. However, the RFP should be awarded in Q1 2012 and the order placed for equipment placed. Some portions of the equipment will be delivered in Q1 2012, but the majority of the equipment may not be available for deployment until Q2 2012. | 0 | No Deviation from the Baseline | 2012-02-17 18:04 | 2012-02-17 18:04 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2012 | Q1 | Q1 - 2012 | 5967 | 5583 | TRUE | 42 | OnWav was somewhat delayed this quarter attempting to finalize contracts with major vendors. However, OnWav still anticipates that it will be back on schedule in early 3rd Quarter 2012 | 0 | BSS-OSS |  | 100 | OnWav's Environmental assessment is complete, however OnWav is conducting additional environmental work to create an EA amendment covering the additional work related to the planned fiber network. Because of the combination of OnWav's original Environmental Assessment efforts came in under-budget and the limited scope of the changes, OnWav will be able to complete these adjustments without going over-budget for Environmental services. | 0 | OnWav has finalized the Fiber route portion of the network design and is planning on placing an order for networking equipment in early 2012. This was completed entirely with internal resources, and so was done at no cost to the grant. However, finalization of the last mile portion of the network was not completed because it is dependent on equipment vendor selection which is still under contract negotiation. OnWav believes that it will be caught up in the second quarter of 2012. OnWav has hired an RF Engineering firm which will be able to complete work finalizing OnWav's network design based on chosen equipment vendor's offering. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav is still working to finalize the lease agreements for the collocation sites, but has received approval from the owners and does not expect any issues or additional expenses. | 0 | OnWav has been delayed in this category as a result of the pending Equipment Request for Proposal and Tower Construction Request for Proposal which are in the final phase of award and contract signature. However, both RFPs will be fully executed in Q2 2012 and the process of acquiring permits will begin. | 0 | OnWav has purchased the land associated with the construction of the three new towers, but due to the delay in awarding the Tower Construction RFP, OnWav has not begun new tower construction. However, OnWav expects to begin work on this category in Q2 2012. | 0 | OnWav is in the process of finalizing the Equipment vendor decision and anticipates making an award and signing a contract, placing an order and receiving an initial batch of equipment in Q2 2012. | 99 | OnWav has acquired over 190 miles of an expected approximately 210 miles of IRUs planned for in the network. The remaining miles are expected to be completed and acquired in Q2 2012 contingent upon timing of the Environmental Amendment | 0 | OnWav has been delayed in this category as a result of the pending Equipment Request for Proposal which is still in the review phase. However, the contract will be signed in Q2 2012 and the order placed for equipment placed. The initial equipment arrival and the initial site should be deployed in late Q2 2012. The majority of the equipment may not be available for deployment until Q2 2012, and not fully deployed until Q3 2012. | 0 | No Deviation from the Baseline | 2012-05-08 14:25 | 2012-05-08 14:25 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2012 | Q2 | Q2 - 2012 | 7069 | 6162 | TRUE | 56 | OnWav's progress in Q2 2012 revolved predominantly around completion of contracts and beginning of work related to Equipment and Tower construction contracts. This included the delivery of nearly all networking basestation and customer equipment as well as the initial engineering work to prepare for Tower construction. OnWav is slightly behind schedule on deployment but anticipates getting the initial two water tank sites installed in early Q3 2012. | 50 | BSS-OSS | OnWav has deployed the equipment which will run it's new OSS system over the wireless last mile network. However the final piece of the new BSS system has been delayed pending a software update to be released by the manufacturer in the next few months. | 100 | OnWav's Environmental assessment is complete, however OnWav is conducting additional environmental work to cover environmental considerations related to the planned fiber network. OnWav has already acquired SHPO and FWS concurrences, and is in the process of completing tribal consultations. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has reached agreement with the owners of the water towers for the the lease agreements for the collocation sites, but has received approval from the owners and does not expect any issues or additional expenses. | 33 | OnWav has received a formal letter confirming no zoning is required for the construction of the three new towers. Building and electrical permits will be pulled shortly before construction. The cost for all remaining permitting is wrapped into the total cost of tower construction under OnWav's Tower Construction Contract. | 0 | OnWav has completed surveys and will soon have the geological analysis which will determine the appropriate site preparation work to be completed for each of the three new towers. This work will be completed in the next quarter shortly before the foundation is poured and the new towers are constructed. | 25 | OnWav signed an Equipment contract, made an initial order and received the majority of the equipment already. OnWav anticipates receiving invoice and paying a large portion of the remainder of this amount in the next quarter. | 99 | OnWav has acquired over 190 miles of an expected approximately 210 miles of IRUs planned for in the network. The remaining miles are expected to be completed and acquired in Q2 2012 contingent upon timing of the Environmental Amendment | 0 | OnWav has been delayed in this category as a result of finalizing the Equipment Contract as well as delays resulting from the initial contractor's difficulty in meeting the BTOP requirements, in particular Davis Bacon. OnWav expects to make substantial progress in this category in the next quarter. | 0 | N/A | 2012-08-15 09:05 | 2012-08-15 09:05 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2012 | Q3 | Q3 - 2012 | 7937 | 6673 | TRUE | 65 | OnWav made significant progress on this project during the last quarter. OnWav's equipment entirely arrived, and almost entirely invoiced. The first two collocation sites have been completed and the initial batch of CAIs have been connected. | 90 | BSS-OSS | OnWav has deployed nearly all of it's new BSS/OSS system integrated with Twin Lake's system. One piece of electronics remains to be configured during Q4 2012 for the new system. | 100 | OnWav's Environmental assessment is complete, additionally, OnWav expects to complete the additional environmental work for the additional work related to the planned fiber network. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has reached agreement with the owners of the water towers for the the lease agreements for the collocation sites, but has received approval from the owners and does not expect any issues or additional expenses. | 33 | OnWav has received a formal letter confirming no zoning is required for the construction of the three new towers. Building and electrical permits will be pulled shortly before construction. The cost for all remaining permitting is wrapped into the total cost of tower construction under OnWav's Tower Construction Contract. | 0 | OnWav has completed all surveys and geological analysis. Site preparation is planned for Q4 2012 shortly before foundation pouring and tower construction. | 98 | Nearly all equipment has been procured. Only the site generators remain to be ordered during Q4 2012, all other equipment has been acquired. | 99 | OnWav has acquired over 190 miles of an expected approximately 210 miles of IRUs planned for in the network. The remaining miles are expected to be completed and acquired in Q4 2012. | 33 | OnWav has deployed 2 of the 6 sites. 3 more sites are expected to be completed in Q4 2012. | 0 | N/A | 2012-11-16 17:21 | 2012-11-16 17:21 | 7560 | 7560 | ONWAV INC. | TRUE
NT10BIX5570080 | 2012 | Q4 | Q4 - 2012 | 8819 | 7608 | TRUE | 67 | OnWav made significant progress on this project during the last quarter, which is not entirely represented by the money spent. OnWav's three new towers are under construction. Foundations are complete and ground work is nearly complete. The CAIs in the first two markets are nearly entirely turned up. Due to the delay between work complete and invoice date, payment for this work will not show up until Q1 2013. | 100 | BSS/OSS | OnWav has deployed all of it's new BSS/OSS system integrated with Twin Lake's system. One piece of electronics is in the final stages of testing and acceptance. | 100 | OnWav's Environmental assessment is complete, additionally, OnWav expects to complete the additional environmental work for the additional work related to the planned fiber network. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has reached agreement with the owners of the water towers for the the lease agreements for the collocation sites, but has received approval from the owners and does not expect any issues or additional expenses. | 100 | OnWav has completed all permits for the construction of the three new towers. Construction has commenced. | 100 | OnWav has completed all surveys and geological analysis. Site Clearing and grading is complete. Initial construction has begun at the fully prepared sites. | 98 | All equipment has been procured, However, final payment on the site generators remain to be paid in Q1 2013, all other equipment has been fully paid for. | 99 | OnWav has acquired over 190 miles of an expected approximately 210 miles of IRUs planned for in the network. The remaining miles are expected to be completed and acquired in Q1 2013. | 33 | OnWav has deployed 2 of the 6 sites. 3 more sites are expected to be completed in Q1 2013. | 0 | N/A | 2013-02-15 16:30 | 2013-02-15 16:30 | 7560 | 7560 | ONWAV INC. | TRUE
NT10BIX5570080 | 2013 | Q1 | Q1 - 2013 | 9635 | 8350 | TRUE | 71 | OnWav made significant progress on this project during the last quarter, which is not entirely represented by the money spent. OnWav's three new towers are completely constructed. RF Equipment is installed, and CAIs are connected to all three new sites. Due to the delay between work complete and invoice date, payment for this work will not show up until Q2 2013. | 100 | OSS/BSS | OnWav has deployed all of it's new BSS/OSS system integrated with Twin Lake's system. OnWav is completing the final Acceptance and testing Procedure. | 100 | OnWav's Environmental assessment is complete, additionally, OnWav expects to complete the additional environmental work for the additional work related to the planned fiber network. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has signed leases with the owners of the water towers for the the lease agreements for the collocation sites. OnWav has reached agreement with the owner of the final collocation site and expects to sign a lease in early Q2 2013 | 100 | OnWav has completed all permits for the construction of the three new towers. Construction has completed. | 100 | OnWav has completed all surveys and geological analysis. Site Clearing and grading is complete. Construction is complete at the three new sites. | 100 | OnWav has received and made payment on the Generators. All equipment is either deployed or awaiting construction in OnWav's warehouse. | 99 | OnWav has constructed the new portion of the fiber network, and is finalizing the legal documents; the fiber is lit and active. | 83 | OnWav has activated 5 of the 6 sites with CAIs active on the network. The final one to be completed in Q2 2013. | 0 | N/A | 2013-05-08 17:58 | 2013-05-08 17:58 | 7560 | 7560 | ONWAV INC. | TRUE
NT10BIX5570080 | 2013 | Q2 | Q2 - 2013 | 10757 | 9044 | TRUE | 85 | OnWav made significant progress on this project during the last quarter. OnWav completed turn-up of CAIs at the three new sites completed in the first quarter. OnWav completed a significant portion of acceptance testing of the 5 completed sites, and is preparing for installation at the 6th and final site. | 100 | OSS/BSS | OnWav has deployed all of it's new BSS/OSS system integrated with Twin Lake's system. | 100 | OnWav's Environmental assessment is complete, additionally, OnWav has completed all additional environmental work and compliance with OnWav's additional environmental requirements. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has signed leases with the owners of the water towers and the owner of the cell tower that will serve as the final site. | 100 | OnWav has completed all permits for the construction of the three new towers. Construction has completed. | 100 | OnWav has completed all surveys and geological analysis. Site Clearing and grading is complete. Construction is complete at the three new sites. | 100 | OnWav has received and made payment on the Generators. All equipment is either deployed or awaiting construction in OnWav's warehouse. | 99 | OnWav has constructed the new portion of the fiber network, and has finalized the legal documents; the fiber is lit and active. Final invoicing is not expected until the closeout period. | 83 | OnWav has activated 5 of the 6 sites with CAIs active on the network. The final one to be completed in July 2013. | 0 | N/A | 2013-08-27 11:02 | 2013-08-27 11:02 | 7560 | 7560 | ONWAV INC. | TRUE
NT10BIX5570080 | 2013 | Q3 | Q3 - 2013 | 11871 | 10044 | TRUE | 100 | OnWav made significant progress on this project during the last quarter. OnWav completed turn-up of final CAIs OnWav completed construction and testing of the last of the 6 sites. OnWav's remaining funds have been paid out on contracts and services related to closeout. | 100 | OSS/BSS | OnWav has deployed all of it's new BSS/OSS system integrated with Twin Lake's system. | 100 | OnWav's Environmental assessment is complete, additionally, OnWav has completed all additional environmental work and compliance with OnWav's additional environmental requirements. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has signed leases with the owners of the water towers and the owner of the cell tower that serves as the final site. | 100 | OnWav has completed all permits for the construction of the three new towers. Construction has completed. | 100 | OnWav has completed all surveys and geological analysis. Site Clearing and grading is complete. Construction is complete at the three new sites. | 100 | OnWav has received and made payment on the Generators. All equipment is deployed. | 100 | OnWav has constructed the new portion of the fiber network, and has finalized the legal documents; the fiber is lit and active. Final invoicing is not expected until the closeout period. | 100 | OnWav has activated 6 of the 6 sites with CAIs active on the network. | 0 | N/A | 2014-02-24 12:08 | 2014-02-24 12:08 | 7560 | 7560 | ONWAV INC. | TRUE
NT10BIX5570081 | 2010 | Q4 | Q4 - 2010 | 1091 | 2132 | TRUE | 0 | Baseline estimated 1% total project spend. Actual project spend through quarter is .28%. The reason for this is that expected project management and compliance procedures for the project are pending naming of competitively-selected project manager, so that federal funding may be used. This selection will be made in the next quarter (ending March 2011). DC-CAN still expects to reach the cumulative project spending goals committed in the DC-CAN Baseline Plan by next quarter (ending March 2011). DC-CAN will track to the baseline for the remainder of the project. | 2 | Project Management, Compliance procedures, Match accounting | DC-CAN still expects to reach the cumulative project spending goals committed in the DC-CAN Baseline Plan by next quarter (ending March 2011). DC-CAN will track to the baseline for the remainder of the project. | 100 | Completed this quarter, as per Baseline. | 30 | Consistent with Baseline. Continued route planning for fiber loops in Wards 8 and 8. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Consistent with Baseline. | 0 | Consistent with Baseline. | 0 | Consistent with Baseline. | 0 | Consistent with Baseline. | 2011-02-11 16:22 | 2011-02-11 16:22 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2011 | Q1 | Q1 - 2011 | 2169 | 2830 | TRUE | 1 | DC-Net has expended 1% vs. baseline target of 6% for this quarter. Items to fulfill baseline target are in procurement pipeline. Please refer to response to Question 3, for further clarification. | 1 | Finance, Compliance, Project Management | Project management has begun, and spending has started. DC-Net has expended 1% vs. baseline target of 19% for this quarter. Items to fulfill baseline target are in procurement pipeline. Please refer to response to Question 3, for further clarification. | 100 | Completed in prior quarter, as per Baseline. | 35 | On target per Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | DC-Net has received handholes, switches and innerduct. DC-Net has expended 0% vs. baseline target of 9% for this quarter. Items to fulfill baseline target are in procurement pipeline. Please refer to response to Question 3, for further clarification. | 0 | DC-Net has installed 5.5 linear miles of fiber cable and upgraded 9 anchor sites. DC-Net has expended 0% vs. baseline target of 2% for this quarter. Items to fulfill baseline target are in procurement pipeline. Please refer to response to Question 3, for further clarification. | 0 | At nine of the upgraded sites, new equipment has been installed. DC-Net has expended 0% vs. baseline target of 2% for this quarter. Items to fulfill baseline target are in procurement pipeline. Please refer to response to Question 3, for further clarification. | 0 | Testing is complete for the 9 upgraded anchor sites. DC-Net has expended 0% vs. baseline target of 2% for this quarter. Please refer to response to Question 3, for further clarification. | 2011-05-19 11:46 | 2011-05-19 11:46 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2011 | Q2 | Q2 - 2011 | 3037 | 3276 | TRUE | 5 | OCTO's DC-Net has expended 5% of project funds vs. Baseline target of 28% of funds planned to be expended by this quarter. Items to fulfill baseline target are in procurement and sales pipelines. Please refer to the response to Question 3, for further elaboration. | 19 | Finance, Compliance, Project Management | DC-Net has expended 19% vs. Baseline target of 28% of funds planned to be expended by this quarter. Items to fulfill baseline target are in procurement and delivery pipelines. Please refer to the response to Question 3, for further elaboration. | 100 | Completed in earlier quarter, as per Baseline. | 40 | On target, per Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 8 | DC-Net has received electronic equipment, hand-holes, etc. DC-Net has expended 8% vs. Baseline target of 48% of funds planned to be expended by this quarter. Items to fulfill baseline target are in procurement and sales pipelines. Please refer to the response to Question 3, for further elaboration. | 2 | DC-Net has installed fourteen (14) linear miles of fiber cable; and installed eight (8) new Community Anchors (3 health centers; 4 charter schools; 1 other). DC-Net has expended 2% vs. Baseline target of 7% of funds planned to be expended by this quarter. Items to fulfill baseline target are in procurement and delivery pipelines. Please refer to the response to Question 3, for further elaboration. | 2 | DC-Net has upgraded nine (9) existing Community Anchors (all Public Safety), to enable improved service and higher bandwidth. DC-Net has expended 2% vs. Baseline target of 14% of funds planned to be expended by this quarter. Items to fulfill baseline target are in procurement and delivery pipelines. Please refer to the response to Question 3, for further elaboration. | 2 | DC-Net has tested the fiber, and confirmed the new and upgraded Anchors are performing as expected. DC-Net has expended 2% vs. Baseline target of 7% of funds planned to be expended by this quarter. Items to fulfill baseline target are in procurement and delivery pipelines. Please refer to the response to Question 3, for further elaboration. | 2011-08-12 11:16 | 2011-08-12 11:16 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2011 | Q3 | Q3 - 2011 | 4075 | 3881 | TRUE | 10 | OCTO's DC-Net has expended 10% of DC-CAN project funds vs. Baseline target of 37% of funds planned to be expended by this quarter. As a result of the tsunami in Japan, there was a shortage of available fiber cable, which has impeded OCTO's ability to obtain, and thereby install, fiber, as planned. In addition, proposed Community Anchors have taken more time than we originally scheduled to evaluate the proposed long-term agreements for services; also, some target anchors are locked into commitments with their current service providers. As a government entity vigorously seeking the best value for all dollars expended, any major purchase requires close review and competitive bidding processes performed by our Office of Contracts and Procurements (OCP). Although this DC-CAN program is critically important to the District, OCTO's DC-Net currently has approximately five+ ($5.2) million worth of grant-funded equipment and fiber installation orders are currently working their way through | 35 | Project Management, Financial | DC-Net has spent 35% vs. DC-CAN Baseline target of 37% planned to be expended by this quarter. | 100 | Completed earlier, as per Baseline. | 50 | Completed as per Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 15 | DC-Net has received electronic equipment, hand-holes, etc. DC-Net has spent 15% vs. DC-CAN Baseline target of 48% planned to be expended by this quarter, measured against Equipment project budget. Additional equipment has been received, and invoices are pending payment. Once paid, overall progress would be measured at approximately 42%. | 4 | DC-Net has installed nine (9) new linear miles of DC-CAN fiber cable, bringing the total installed mileage to twenty-three (23) miles. DC-CAN began providing services to nine (9) additional new Community Anchor Institutions (CAI's), bring the total served to seventeen (17) new CAI's served. DC-CAN had no new CAI upgrades this quarter; the total remains at nine (9) upgraded CAI's. DC-Net has spent 4% vs. DC-CAN Baseline target of 26% planned to be expended by this quarter, measured as proportion of fiber installed against planned fiber miles. We experienced significant delays with fiber procurement due to unavailability of raw materials caused by the earthquake in Japan; we have received a large order of fiber enabling us to proceed with installation. We also incurred delays due to inclement weather conditions, as District had a near-record rain this summer. | 9 | DC-CAN began providing services to nine (9) additional new Community Anchor Institutions (CAI's), bring the total served to seventeen (17) new CAI's served. DC-Net has upgraded nine (9) existing Community Anchor Institutions (all Public Safety), providing improved service and higher bandwidth. DC-Net has spent 9% vs. DC-CAN Baseline target of 27% planned to be expended by this quarter, measured as proportion of new and upgraded anchors against project commitments (223 new plus 68 upgraded anchors). As a result of the tsunami in Japan, there was a shortage of available fiber cable, which has impeded OCTO's ability to obtain, and thereby install, fiber, as planned. In addition, proposed Community Anchors have taken more time than we originally scheduled to evaluate the proposed long-term agreements for services; also, some target anchors are locked into commitments with their current service providers. Each of these factors impacted DC-Net's ability to deploy equipment to anchors. | 4 | DC-Net has tested the installed fiber, and confirmed the new and upgraded Community Anchors are performing as expected. DC-Net has spent 4% vs. DC-CAN Baseline target of 26% planned to be expended by this quarter, measured as proportion of fiber installed against planned fiber miles. We experienced significant delays with fiber procurement due to unavailability of raw materials caused by the earthquake in Japan; we have received a large order of fiber enabling us to proceed with installation. We also incurred delays due to inclement weather conditions, as District had a near-record rain this summer. | 2011-11-16 15:52 | 2011-11-16 15:52 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2011 | Q4 | Q4 - 2011 | 5359 | 5028 | TRUE | 31 | OCTO's DC-Net has expended 31% of DC-CAN project funds vs. forecast target of 37% of funds planned to be expended by this quarter, and 66% baseline target. DC-CAN is making every effort to quickly catch up. The initial delay was due to shortage of fiber availability. Internal reviews at Community Anchors took longer than anticipated, resulting in delays in securing signed agreements. Now sign-ups are proceeding quickly; we are making good progress in identifying and turning up new community anchors (CAIs) and completing upgrades. Fiber installation is accelerating. In summary, DC-CAN will meet the 67% completion target by June 2012; and DC-CAN will be fully complete by June 2013. In addition to equipment already received and construction completed, invoices are pending payment. Once paid, overall project progress would be measured at approximately 34%. | 41 | Finance, Compliance, Reporting, Administration | DC-Net has spent 41% vs. DC-CAN Baseline target of 46% planned to be expended by this quarter. This is just slightly behind, but within our expected budget planning variance, as it is five (5) percent. | 100 | Completed earlier, as per Baseline. | 60 | On target with Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 49 | OCTO's DC-Net has spent 49% of DC-CAN project funds vs. forecast target of 58% of funds planned to be expended by this quarter, and 90% baseline target. DC-CAN will be caught up with the Baseline commitment by quarter ending September 2012. DC-Net is managing the DC-CAN equipment purchases consistent with the Community Anchor turnup, to support more just-in-time delivery of equipment. | 10 | DC-Net has installed twenty-two (22) new linear miles of DC-CAN fiber cable, bringing the total installed mileage to forty-five (45) miles. DC-CAN will be caught up with baseline network build targets by quarter ending December 2012. DC-CAN began providing services to fourteen (14) additional new Community Anchor Institutions (CAI's), bring the total served to thirty-one (31) new CAI's served. DC-CAN had twenty-four (24) new CAI upgrades this quarter, bringing the total to thirty-three (33) upgraded CAI's. DC-CAN installed one (1) additional point of interconnection (mega-points-of-presence, or mega-POP), bringing the total to three (3) mega-POPs. OCTO's DC-Net has expended 10% of DC-CAN project funds vs. baseline target of 44% of funds planned to be expended by this quarter.. Due to the delays in fiber availability, network build has been held back behind what was expected during baseline planning. However, DC-CAN's re-forecast of expected network build remains on track, and t | 27 | DC-CAN began providing services to fourteen (14) additional new Community Anchor Institutions (CAI's), bring the total served to thirty-one (31) new CAI's served. DC-CAN had twenty-four (24) new CAI upgrades this quarter, bringing the total to thirty-three (33) upgraded CAI's. DC-CAN installed one (1) additional point of interconnection (mega-points-of-presence, or mega-POP), bringing the total to three (3) mega-POPs. DC-Net has spent 27% vs. DC-CAN Baseline target of 41% planned to be expended by this quarter, measured as proportion of new and upgraded anchors against project commitments (223 new plus 68 upgraded anchors). DC-Net is catching up on equipment deployment, as community anchor agreements are finalized. As the rate of CAI sign-ups continues to improve, equipment deployment will improve quickly. | 10 | DC-Net has tested the installed fiber, and confirmed the new and upgraded Community Anchors are performing as expected. DC-Net has spent 10% vs. DC-CAN Baseline target of 44% planned to be expended by this quarter, measured as proportion of fiber installed against planned fiber miles. Network testing is proportional to the network build. DC-CAN is testing the network as it is installed; we will stay consistent with the network build ratios. | 2012-02-28 15:02 | 2012-02-28 15:02 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2012 | Q1 | Q1 - 2012 | 6165 | 5685 | TRUE | 41 | OCTO's DC-Net has expended 41% of DC-CAN project funds vs. forecast target of 37% of funds planned to be expended by this quarter, and 70% baseline target. DC-CAN is making every effort to quickly catch up. Sign-ups of Community Anchor Institutions (CAIs) are proceeding quickly; we are making good progress in turning up new CAIs and completing upgrades. Fiber installation is accelerating. In summary, DC-CAN will be fully complete by June 2013. See "Project Indicators (Next Quarter)" for assessment against "Significantly Complete" targets for June 2012. In addition to equipment already received and construction completed, invoices are pending payment. Once paid, overall project progress would be measured at approximately 43%. | 50 | Finance, Project Management, Reporting, Compliance. | DC-Net has spent 50% vs. DC-CAN Baseline target of 55% planned to be expended by this quarter. This is just slightly behind, but within our expected budget planning variance of five (5) percent. | 100 | Completed earlier, as per Baseline. | 70 | On target with Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 53 | OCTO's DC-Net has spent 53% of DC-CAN project funds vs. forecast target of 62% of funds planned to be expended by this quarter, and 90% baseline target. Additional equipment procurement is in process. DC-CAN will be caught up with the Baseline commitment by quarter ending September 2012. | 41 | DC-CAN has expended approximately 41% of DC-CAN project funds for network build vs. baseline target of 51% of funds planned to be expended by this quarter. DC-CAN installed an additional twenty-two (22) new linear miles of DC-CAN fiber cable this quarter, bringing the total installed mileage to sixty-seven (67) miles. 41% of network build funds have been expended to construct 39% of the total committed 173 miles to be built. DC-CAN is providing services to eighteen (18) additional new Community Anchor Institutions (CAIs), bringing the total served to forty-nine (49) new CAIs served. DC-CAN had nineteen (19) additional CAI upgrades this quarter, bringing the total to fifty-two (52) upgraded CAIs. DC-CAN is consistent with baseline target plan for three (3) points of inter-connection installed. | 35 | DC-CAN is providing services to eighteen (18) additional new Community Anchor Institutions (CAIs), to bring the total served to forty-nine (49) CAIs served, of a planned 223. DC-CAN upgraded an additional nineteen (19) CAIs this quarter, to bring the total to fifty-two (52) upgraded CAIs, of a planned 68. No wireless access points have been installed to date at new or upgraded CAIs. DC-CAN installed no additional points of inter-connection; the total remains at three (3) of a planned ten (10). 35% represents the proportional cumulative spend on equipment deployed to active CAIs and POIs. This is measured against a planned 44%, and a Baseline target of 51% planned to be expended by this quarter. Equipment is deployed as anchors and points of inter-connect are turned up. | 35 | DC-CAN has tested the installed fiber, and confirmed the new and upgraded Community Anchors are performing as expected. DC-CAN has spent 35% vs. DC-CAN Baseline target of 51% planned to be expended by this quarter, measured as proportion of fiber installed against planned fiber miles. Network testing is proportional to the network build. DC-CAN is testing the network as it is installed; we will stay consistent with the network build ratios. | 2012-05-17 18:24 | 2012-05-17 18:24 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2012 | Q2 | Q2 - 2012 | 7201 | 6228 | TRUE | 55 | OCTO's DC-Net has expended 55% of DC-CAN project funds vs. forecast target of 67% of funds planned to be expended by this quarter, and 81% baseline target. DC-CAN is making every effort to quickly catch up. Sign-ups of Community Anchor Institutions (CAIs) are proceeding quickly; we are making good progress in turning up new CAIs and completing upgrades. Fiber installation is accelerating. In summary, DC-CAN will be fully complete by June 2013. | 56 | Finance, Project Management, Reporting, Compliance. | DC-Net has spent 56% vs. DC-CAN Baseline target of 64% planned to be expended by this quarter. This is just slightly behind, and just outside our expected budget planning variance of five (5) percent. | 100 | Completed earlier, as per Baseline. | 80 | On target with Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 64 | OCTO's DC-Net has spent 64% of DC-CAN project funds vs. forecast target of 67% of funds planned to be expended by this quarter, and 100% baseline target. Additional equipment procurement is in process. | 52 | DC-CAN has expended approximately 52% of DC-CAN project funds for network build vs. baseline target of 64% of funds planned to be expended by this quarter. DC-CAN installed an additional twenty-three (23) new linear miles of fiber cable this quarter, bringing the total installed mileage to ninety (90) miles. 52% of network build funds have been expended to construct 52% of the total committed 173 miles to be built. DC-CAN is now delivering services to one hundred fifty-one (151) anchors, which is behind the baseline target of one hundred ninety-seven (197) anchors. However, at the end of the quarter, we received approval on two route modifications, permitting us to rapidly install several dozen new anchors next quarter. | 52 | DC-CAN is providing services to an additional forty-six (46) new Community Anchor Institutions (CAIs), to bring the total served to ninety (90) CAIs served, of a planned 223. DC-CAN upgraded an additional five (5) CAIs this quarter, to bring the total to sixty-one (61) upgraded CAIs, of a planned 68. The first nineteen (19) wireless access points (WAPs) were installed this quarter at new and upgraded anchor sites, of a planned 291. DC-CAN installed two (2) additional points of inter-connection (POIs), bringing the total to five (5) of an approved, increased goal of fourteen (14) POIs. 52% represents the proportional cumulative spend on actual equipment deployed to active CAIs and POIs, measured against the planned 52%, and a Baseline target of 65% planned to be expended by this quarter. Equipment is deployed as anchors and points of inter-connect are turned up. | 52 | DC-CAN has tested the installed fiber, and confirmed the new and upgraded Community Anchors are performing as expected. DC-CAN has spent 52% vs. DC-CAN Baseline target of 64% planned to be expended by this quarter, measured as proportion of fiber installed against planned fiber miles. Network testing is proportional to the network build. DC-CAN is testing the network as it is installed; we will stay consistent with the network build ratios. | 2012-08-21 17:22 | 2012-08-21 17:22 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2012 | Q3 | Q3 - 2012 | 8115 | 6765 | TRUE | 62 | OCTO's DC-Net has expended 62% of DC-CAN project funds vs. forecast target of 67% of funds planned to be expended by this quarter, and 86% baseline target. Sign-ups of Community Anchor Institutions (CAIs) are proceeding quickly; we aremaking good progress in turning up new CAIs and completing upgrades. Fiber installation is ahead of our re-forecast. In summary, DC-CAN will be fully complete by June 2013. | 63 | Finance, Project Management, Reporting, Compliance | DC-Net has spent 63% vs. DC-CAN Baseline target of 64% planned to be expended by this quarter. This is just slightly behind, and just outside our expected budget planning variance of five (5) percent. | 100 | Completed earlier, as per Baseline. | 90 | On target with Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 69 | OCTO's DC-Net has spent 69% of DC-CAN project funds vs. forecast target of 78% of funds planned to be expended by this quarter, and 100% baseline target. Equipment purchases were slightly deferred so that acquisition was more consistent with CAI implementation schedule. | 61 | DC-CAN has expended approximately 61% of DC-CAN project funds for network build vs. baseline target of 73% of funds planned to be expended by this quarter. DC-CAN installed an additional sixteen (16) new linear miles of fiber cable this quarter, bringing the total installed mileage to one hundred six (106) miles. 61% of network build funds have been expended to construct 61% of the total committed 173 miles to be built. DC-CAN is now delivering services to one hundred eighty-four (184) anchors, which is behind the baseline target of two hundred thirteen (213) anchors. | 63 | DC-CAN is providing services to an additional thirty (30) new Community Anchor Institutions (CAIs), to bring the total served to one hundred twenty (120) CAIs served, of a planned 223. DC-CAN upgraded an additional three (3) CAIs this quarter, to bring the total to sixty-four (64) upgraded CAIs, of a planned 68. DC-CAN installed an additional twenty-six (26) wireless access points (WAPs), to bring the total to forty-five (45) of a planned 291 at new and upgraded anchor sites. DC-CAN installed two (2) additional points of inter-connection (POIs), bringing the total to seven (7) of an approved goal of fourteen (14) POIs. 63% represents the proportional cumulative spend on actual equipment deployed to active CAIs and POIs, measured against the Baseline target of 74% planned to be expended by this quarter. | 61 | DC-CAN has tested the installed fiber, and confirmed the new and upgraded Community Anchors are performing as expected. DC-CAN has spent 61% vs. DC-CAN Baseline target of 73% planned to be expended by this quarter, measured as proportion of fiber installed against planned fiber miles. Network testing is proportional to the network build. DC-CAN is testing the network as it is installed; we will stay consistent with the network build ratios. | 2012-11-28 15:16 | 2012-11-28 15:16 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2012 | Q4 | Q4 - 2012 | 8941 | 7724 | TRUE | 75 | OCTO's DC-Net has expended 75% of DC-CAN project funds vs. forecast target of 73% of funds planned to be expended by this quarter, and 93% baseline target. We are making good progress in turning up new CAIs and have finished our upgrades. Fiber installation is ahead of our re-forecast. In summary, DC-CAN will be fully complete by June 2013. | 76 | Finance, Project Management, Reporting, Compliance | DC-Net has spent 76% vs. DC-CAN Baseline target of 82% planned to be expended by this quarter. This is just slightly behind, and just outside our expected budget planning variance of five (5) percent. | 100 | Completed. | 95 | Baseline had indicated project would be 100% complete with Network Design at this point. Due to selection of final community anchor institutions (CAIs), final route design will not be complete until next quarter. | 0 | N/A | 0 | N/A | 0 | N/A | 86 | OCTO's DC-Net has spent 86% of DC-CAN project funds vs. forecast target of 85% of funds planned to be expended by this quarter, and 100% baseline target. Equipment purchases were slightly deferred so that acquisition was more consistent with CAI implementation schedule. | 75 | DC-CAN has expended approximately 75% of DC-CAN project funds for network build vs. baseline target of 86% of funds planned to be expended by this quarter. DC-CAN installed an additional twenty-four (24) new linear miles of fiber cable this quarter, bringing the total installed mileage to one hundred thirty (130) miles. 75% of network build funds have been expended to construct 75% of the total committed planned 173 miles. DC-CAN is now delivering services to two hundred thirteen (213) anchors, slightly behind the baseline target of two hundred forty-nine (249) anchors. | 73 | DC-CAN is providing services to an additional twenty-five (25) new Community Anchor Institutions (CAIs), to bring the total served to one hundred forty-five (145) CAIs served, of a planned 223. DC-CAN upgraded the final four (4) CAIs this quarter, completing the allotment of sixty-eight (68) upgrades. DC-CAN installed an additional twenty-two (22) wireless access points (WAPs), bringing the total to sixty-seven (67) of a planned two hundred twenty-three (223) at new anchor sites. Installation of WAPs at upgrade sites is pending NTIA approval. DC-CAN installed two (2) additional points of inter-connection (POIs), bringing the total to nine (9) of an approved goal of fourteen (14) POIs. 73% represents the proportional cumulative spend on actual equipment deployed to active CAIs and POIs, measured against the Baseline target of 87% planned to be expended by this quarter. | 75 | DC-CAN has tested the installed fiber, and confirmed the new and upgraded Community Anchors are performing as expected. DC-CAN has spent 75% vs. DC-CAN Baseline target of 86% planned to be expended by this quarter, measured as proportion of fiber installed against planned fiber miles. Network testing is proportional to the network build. DC-CAN is testing the network as it is installed; we will stay consistent with the network build ratios. | 2013-02-25 16:17 | 2013-02-25 16:17 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2013 | Q1 | Q1 - 2013 | 9823 | 8448 | TRUE | 80 | OCTO's DC-Net has expended 80% of DC-CAN project funds vs. forecast target of 86% of funds planned to be expended by this quarter and 94% baseline target. We are making good progress in turning up new CAIs and have finished our upgrades. Fiber installation is ahead of our re-forecast. | 83 | Finance, Project Management, Reporting, Compliance | DC-Net has spent 83% vs. DC-CAN Baseline target of 91% planned to be expended by this quarter. This is just slightly behind, and just outside our expected budget planning variance of five (5) percent. | 100 | Completed. | 97 | Baseline had indicated project would be 100% complete with Network Design at this point. Due to selection of final community anchor institutions (CAIs), final route design will not be complete until next quarter. | 0 | N/A | 0 | N/A | 0 | N/A | 92 | OCTO's DC-Net has spent 92% of DC-CAN project funds vs. forecast target of 99% of funds planned to be expended by this quarter, and 100% baseline target. Equipment purchases were slightly deferred so that acquisition was more consistent with CAI implementation schedule. | 80 | DC-CAN has expended approximately 80% of DC-CAN project funds for network build vs. baseline target of 88% of funds planned to be expended by this quarter. DC-CAN installed an additional ten (10) new linear miles of fiber cable this quarter, bringing the total installed mileage to one hundred forty (140) miles. 80% of network build funds have been expended to construct 80% of the total committed planned 173 miles. DC-CAN is now delivering services to two hundred thirty (230) anchors, slightly behind the baseline target of two hundred forty-nine (249) anchors. | 79 | DC-CAN is providing services to an additional seventeen (17) new Community Anchor Institutions (CAIs), to bring the total served to one hundred sixty-two (162) CAIs served, of a planned 223. DC-CAN has completed all sixty-eight (68) upgraded CAIs. DC-CAN installed an additional twenty-three (23) wireless access points (WAPs), bringing the total to ninety (90) of a planned two hundred ninety-one (291) new and upgraded anchor sites. DC-CAN installed one (1) additional points of inter-connection (POIs) bringing the total to ten (10) of an approved goal of fourteen (14) POIs. 79% represents the proportional cumulative spend on actual equipment deployed to active CAIs and POIs, measured against the Baseline target of 87% planned to be expended by this quarter. | 80 | DC-CAN has tested the installed fiber, and confirmed the new and upgraded Community Anchors are performing as expected. DC-CAN has spent 80% vs. DC-CAN Baseline target of 88% planned to be expended by this quarter, measured as proportion of fiber installed against planned fiber miles. Network testing is proportional to the network build. DC-CAN is testing the network as it is installed; we will stay consistent with the network build ratios. | 2013-05-20 12:41 | 2013-05-20 12:41 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2013 | Q2 | Q2 - 2013 | 10687 | 9005 | TRUE | 86 | OCTO's DC-Net has expended 86% of DC-CAN project funds vs. forecast target of 86% of funds planned to be expended by this quarter and 100% baseline target. We are making good progress in turning up new CAIs and have finished all upgrades. Fiber installation has exceeded the program goal | 91 | Finance, Project Management, Reporting, Compliance | DC-Net has spent 91% vs. DC-CAN Baseline target of 100% planned to be expended by this quarter. Due to the approved extension, these tasks will be executed over a slightly longer period. | 100 | Completed. | 98 | Baseline had indicated project would be 100% complete with Network Design at this point. Due to selection of final community anchor institutions (CAIs), final route design will not be complete until next quarter. | 0 | N/A | 0 | N/A | 0 | N/A | 92 | OCTO's DC-Net has spent 92% of DC-CAN project funds vs. forecast target of 99% of funds planned to be expended by this quarter, and 100% baseline target. Equipment purchases were slightly deferred so that acquisition was more consistent with CAI implementation schedule. | 92 | DC-CAN has expended approximately 92% of DC-CAN project funds for network build vs. baseline target of 100% of funds planned to be expended by this quarter. DC-CAN installed an additional forty-six (46) new linear miles of fiber cable this quarter, bringing the total installed mileage to one hundred eighty-six (186), exceeding the program goal of one hundred seventy-four (174). DC-CAN is now delivering services to two hundred sixty (260) anchors, slightly behind the baseline target of two hundred ninety-one (291) anchors. | 89 | DC-CAN is providing services to an additional thirty (30) new Community Anchor Institutions (CAIs), to bring the total served to one hundred ninety-two (192) CAIs served, of a planned 223. DC-CAN has completed all sixty-eight (68) upgraded CAIs. DC-CAN installed an additional thirty (30) wireless access points (WAPs), bringing the total to one hundred twenty (120) of a planned two hundred twenty-three (223) at new anchor sites. DC-CAN installed one (1) additional points of inter-connection (POIs) bringing the total to eleven (11) of an approved goal of fourteen (14) POIs. 89% represents the proportional cumulative spend on actual equipment deployed to active CAIs and POIs, measured against the Baseline target of 100% planned to be expended by this quarter. | 92 | DC-CAN has tested the installed fiber, and confirmed the new and upgraded Community Anchors are performing as expected. DC-CAN has spent 92% vs. DC-CAN Baseline target of 100% planned to be expended by this quarter, measured as proportion of fiber installed against planned fiber miles. Network testing is proportional to the network build. DC-CAN is testing the network as it is installed; we will stay consistent with the network build ratios. | 2013-08-21 15:47 | 2013-08-21 15:47 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2013 | Q3 | Q3 - 2013 | 11499 | 9623 | TRUE | 100 | Per Baseline. Several project metrics exceeded baseline plan, especially fiber miles installed (211 actual vs 174 baseline). Overall project is complete as of the end of the closeout period, at 100%, with all payments having been made. | 100 | Finance, Project Management, Reporting, Compliance | Completed. | 100 | Completed. | 100 | Completed. | 0 | N/A | 0 | N/A | 0 | N/A | 100 | Completed. DC-CAN completed the installation of the final thirty-one (31) new Community Anchor Institutions (CAIs), bringing the total to the committed two hundred twenty-three (223). DC-CAN completed installation of the final one hundred three (103) rooftop wireless access points (WAPs), bringing the total to the committed two hundred twenty-three (223). DC-CAN completed installation of the final three (3) points of inter-connection to the committed fourteen (14). | 100 | Completed. | 100 | Completed. DC-CAN completed the installation of the final thirty-one (31) new Community Anchor Institutions (CAIs), bringing the total to the committed two hundred twenty-three (223). DC-CAN completed installation of the final one hundred three (103) rooftop wireless access points (WAPs), bringing the total to the committed two hundred twenty-three (223). DC-CAN completed installation of the final three (3) points of inter-connection to the committed fourteen (14). | 100 | Completed. | 2013-12-18 12:26 | 2013-12-18 12:26 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570082 | 2010 | Q3 | Q3 - 2010 | 181 | 1357 | TRUE | 3 | Initial project startup activity has begun this quarter | 5 | Project Management | Nearly full team hired and in place to lead project effort | 20 | Project received a Categorical Exclusion; state reviews underway | 26 | Design decisions relative to RFP release | 0 | In Progress | 0 | In Progress | 0 | In Progress | 0 | In Progress | 0 | In Progress | 0 | In Progress | 0 | Done when project construction is completed | 2010-10-28 10:50 | 2010-10-28 10:50 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2010 | Q4 | Q4 - 2010 | 1245 | 2276 | TRUE | 1 | Progressing on target according to baseline. | 7 | Project Management | Variance - 6%; Added tasks for communications and reporting tracking into project plan which reduced overall completion in this area from baseline. | 100 | Categorical Exclusion completes this category. Addressed local historical review in Construction Permits and Other Approvals. | 35 | Variance - 7%; RFP Process is taking longer than planned. CLEC application paperwork needed to be filed and additional questions from vendors and USNH stakeholders delayed contract negotiations. | 1 | Variance + 1%; NHDOT ahead of schedule in portions of Right of Way work. | 12 | Variance + 8 %; State historical review approval moved from environmental to this category and thus more accomplished than originally planned. | 0 | None this quarter. | 2 | Variance - 2%; NHDOT moved equipment procurement from Q4 2010 to Q1 2011. | 0 | None this quarter. | 0 | None this quarter. | 0 | None this quarter. | 2011-02-20 14:39 | 2011-02-20 14:39 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2011 | Q1 | Q1 - 2011 | 2109 | 2800 | TRUE | 2 | As noted in Q4 2010 PPR report projection, we estimated this number was going to be lower due to delays in signing a new sub-recipient. | 12 | Project Management | -10% Variance - With a delayed middle mile sub-recipient selection, increased project management activity has been delayed; will increase in next quarter. | 100 | Complete | 46 | -16% Variance - The variance will drop as sub-recipient is signed and items that would have been finished in Q3 should be recovered in Q4. | 0 | -1% Variance on projected spend on baseline plan, but project work has been completed in this area that has not yet incurred project funds draw. | 0 | -19% Variance on projected spend on baseline plan due to delay in signing construction sub-recipient, but project work has been completed in this area that has not yet incurred project funds draw. | 0 | -63% Variance - Variance on projected spend on baseline plan due to delay in signing construction sub-recipient, but project work has been completed in this area that has not yet incurred project funds draw. | 0 | -8% Variance on projected spend on baseline plan, but project work has been completed in this area that has not yet incurred project funds draw. | 0 | -3% Variance on projected spend on baseline plan due to delay in signing construction sub-recipient, but project work has been completed in this area that has not yet incurred project funds draw. | 0 | -5% Variance on projected spend on baseline plan, but project work has been completed in this area that has not yet incurred project funds draw. | 0 | Consistent with Baseline Plan | 2011-05-17 18:11 | 2011-05-17 18:11 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2011 | Q2 | Q2 - 2011 | 3087 | 3301 | TRUE | 7 | (Baseline 24%; -17% Variance) - Previous PPR had estimated this amount at 9%, and this included work to be done by the NH Department of Transportation that will be performed later in the year. | 32 | Project Management | (Baseline 31%; +1% Variance) As the majority of vendors have been signed, project management activities are back on baseline plan. | 100 | Completed | 61 | (Baseline 80%; -19% Variance) Actual completion of construction RFPs has occurred later than in baseline plan. Network design behind baseline estimates due to delays in signing agreements with construction vendors. The last construction vendor will be hired as of Q5 (Q3 2011). Work in this area should be complete as forecasted in the baseline by the end of Q8 (Q2 2012). | 0 | (Baseline 18%; -18% Variance) Delays in hiring construction vendor have delayed work in submitting applications for pole licenses. Pole license applications were submitted on the route in Q4, and we expect a substantial amount of progress on Make Ready estimates on the route in Q5 (Q3 2011). | 0 | (Baseline 38%; -38% Variance) Delays in hiring construction vendor have delayed work in submitting applications for pole licenses. Pole license applications were submitted on the route in Q4, and we expect a substantial amount of progress on Make Ready estimates on the route in Q5 (Q3 2011). Licensing should be completed by Q3 2012. | 0 | (Baseline 100%; -100% Variance) NH DOT is the only area of the project with site preparation work, and this has been moved to a completion date of May 2012. State reviews on the open toll project in Hooksett, NH are a contributing factor to this delay. DOT project will only take six months to complete, and accounts for only 10% of the overall project budget, so despite the delay in starting this area, it will not affect our ability to complete the project on schedule. | 0 | (Baseline 27%; -27% Variance) Fiber optic cabling quotes have been solicited for the entire middle mile route, and purchases are expected to be completed by Q4 2011. This bulk purchase is necessary as a result of the fiber optic cabling market supply drought that several national and worldwide disasters has caused. | 0 | (Baseline 6%; -6% Variance) Strand and Fiber placement expected to begin in Q4 2011. Crews will be working through the winter months. This will enable the project to be closer to our original baseline. | 0 | (Baseline 27%; -27% Variance) Project work in this area is underway, but expenditures have not yet been incurred. The majority of equipment deployment at this stage of the project should have been within the NHDOT project area, but is delayed until Q9. | 0 | (Baseline 3%; -3% Variance) Project work in this area is underway, but expenditures have not yet been incurred. | 2011-08-15 16:29 | 2011-08-15 16:29 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2011 | Q3 | Q3 - 2011 | 4077 | 3882 | TRUE | 13 | (Baseline 42%; -29% Variance) - We met our previous PPR estimate of 13%. Expenses such as Make Ready and equipment purchases were delayed due to delays in signing vendor agreements. We have seen significant progress in Make Ready work and are continuing to work with utilities to accelerate survey and Make Ready work. | 31 | Project Management | (Baseline 40%; 9% Variance) Baseline was calculated against project activity. As the majority of vendors have been signed, project plan activities are back on schedule. Expenditures lag due to delays in signing vendors. Our project plan status indicates 40% of tasks completed. | 100 | Completed | 71 | (Baseline 92%; -21% Variance) Baseline was calculated against project activity. Network design is behind baseline estimates due to delays in signing agreements with construction vendors and delays by electric companies responding to requests for pole surveys. Hurricane Irene recovery in early September 2011 was a priority for utilities, and survey work for pole licenses was delayed. Despite these challenges, we have seen a significant increase in survey and Make Ready quotes over the last quarter. The NH FastRoads construction vendor negotiations have taken longer than planned, but should be finalized in October 2011. Project plan work in Network Design should be complete as forecasted in the baseline by the end of Q8 (Q2 2012). Our project plan status indicates 69% of tasks completed. | 0 | (Baseline 44%; -44% Variance) Baseline was calculated against project activity. Tracking of pole surveys and make ready responses will be moved in our project plan to Site Preparation to more accurately align with financial projections. There are currently no financial expenditures projected in this category. | 40 | (Baseline 53%; -13% Variance) Baseline was calculated against project activity. Delays in hiring construction vendor delayed work in submitting applications for pole licenses. Pole license applications were submitted on the route in Q2 2011, and we have received Make Ready estimates for over a quarter of the route. We continue to expect a substantial amount of progress on Make Ready estimates on the route in Q6 (Q4 2011). Licences have started to be granted for portions of the route. Licensing should be completed by Q3 2012. Our project plan status indicates 17% of tasks completed. | 21 | (Baseline 100%; -79% Variance) Baseline was calculated against project activity. NH DOT is the only area of the project with site preparation work in the project plan, and this has been moved to a completion date of December 2012. An open road tolling project on the same route as our BTOP project was approved between the application submittal and award of the BTOP grant. The engineering for open road tolling delayed the final engineering work for the BTOP grant. The DOT project will only take six months to complete, and accounts for only 10% of the overall project budget, so despite the delay in starting this area, it will not affect our ability to complete the project on schedule. Financial expenditures have been incurred related to Make Ready in this area. Our project plan status indicates 0% of tasks completed. | 4 | (Baseline 20%; -16% Variance) Baseline was calculated against project activity. The purchase order was issued for the fiber for the entire middle mile route. This bulk purchase is necessary as a result of the fiber supply drought caused by national and worldwide disasters. We have received 15% of the fiber optic cabling, which is less than had been anticipated for this quarter, but we are confident we will obtain the remaining fiber. We were recently informed that the fiber manufacturer is raising the contracted price in 2012. Our project plan status indicates 11% of tasks completed. | 6 | (Baseline 15%; -9% Variance) Baseline was calculated against project activity. Fifty miles of fiber have been deployed between Manchester and Keene, NH. Strand and Fiber placement will continue in Q4 2011 as crews will be working through the winter months. This will enable the project to be closer to our original baseline. Our project plan status indicates 2% of tasks completed. | 0 | (Baseline 27%; -27% Variance) Baseline was calculated against project activity. Project work in this area is underway, but expenditures have not yet been incurred due to delays in signing vendors. Our project plan status indicates 24% of tasks completed. | 0 | (Baseline 8%; -8% Variance) Baseline was calculated against project activity. Project work in this area is underway, but expenditures have not yet been incurred due to delays in signing vendors. Our project plan status indicates 0% of tasks completed. | 2011-11-16 15:54 | 2011-11-16 15:54 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2011 | Q4 | Q4 - 2011 | 5027 | 4699 | TRUE | 26 | In section 2 below, our original baselines were based on project plan rather than financial spend percentages. Last quarter we re-aligned Percent Complete with financial expenditures. Our current project plan financial spend status is behind baseline due to delays in signing the engineering and construction vendors for Network New Hampshire Now project. Our progress is generally in line with the previous report's PPR projections. (Baseline 50%; -24% Variance; Previous PPR estimate 26%; no Variance) The project met the 26% projection from the previous PPR. We continue to work with utilities to process payments for Make-Ready work in as soon as estimates are received and validated We have made progress to increase throughput on pole licensing requests with utility stakeholders, and have received more than 50% of Make Ready estimates. Construction is proceeding on mountaintops. Engineering continues on Last Mile. | 43 | Project Management | (Baseline 48%; -5% Variance; Previous PPR estimate 35%; Variance +8%) Project team attended BTOP conference in Cleveland in October. The project team hosted a regional conference for BTOP infrastructure awardees on October 13. Last Mile project has been scheduling outreach and marketing with CAIs. | 100 | Completed | 100 | (Baseline 95%; Variance +5%; Previous PPR estimate: 75% - Variance +25% ) Our project plan activities are at 76%. NH FastRoads has awarded their RFP contract for engineering and construction. Engineering is underway in FastRoads Phase 1 locations in Enfield, Orford, Lyme, Hanover, and Lebanon. NHOS has received it's CLEC license in Vermont. Pole applications have been completed for the middle mile route. The fiber map for the middle mile is under review. | 100 | There are currently no financial expenditures projected in this category. | 41 | (Baseline 58%; Variance -17%; Previous PPR estimate 48%; Variance -7%) Our project plan is currently at 18%. Licenses have been received on about 4% of the route. We anticipate all licenses will be received by in the last quarter of 2012. We continue to work with the NH Public Utilities commission to complete applications on State of NH river and railroad crossings. | 32 | (Baseline 100%; -68% Variance; Previous PPR estimate 52%; Variance -20%) Our project plan is currently at 69%. The 52% projections for last quarter was missed due to expenses that were attributed to other milestones this quarter. Make-Ready estimates for pole owners on the middle mile are currently over 50%. Third party Make-Ready estimates for the middle mile are being invoiced at higher than expected rates, and we are working with CLECs to get clarifications on increases in their Make-Ready work. Last mile has submitted pole applications for Phase 1 of their route. | 19 | (Baseline 25%; -6% Variance; Previous PPR estimate 19%; Variance 0%) Our project plan is currently at 11%. We have received 34% of the fiber optic cabling. The fiber manufacturer is raising the contracted price in 2012. The microwave project has procured the majority of their equipment. The last mile project is currently reviewing RFP responses for network equipment. | 16 | (Baseline 22%; -6% Variance; Previous PPR estimate 14%; Variance +2%) Our project plan status indicates 2% of tasks completed. Strand and Fiber placement will continue in Q1 2012 as crews will be working through the winter months. | 0 | (Baseline 42%; -42% Variance; Previous PPR estimate 14%; Variance -14%; ) Our project plan status indicates 24% of tasks completed. Invoice for Q4 was submitted to the project too late to process in the quarter. These expenditures will be moved to Q1 2012. | 0 | (Baseline 9%; -9% Variance; Previous PPR estimate 0%; Variance 0%) Project work in this area is underway, but expenditures have not yet been incurred due to delays in signing vendors. | 2012-02-15 11:55 | 2012-02-15 11:55 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2012 | Q1 | Q1 - 2012 | 6007 | 5603 | TRUE | 48 | In section 2 below, our original baselines were based on project plan rather than financial spend percentages. We have re-aligned Percent Complete with financial expenditures. Our current project plan financial spend status is behind baseline due to delays in signing the engineering and construction vendors for Network New Hampshire Now project. Our progress is generally in line with the previous report's PPR projections. (Baseline 59%; -11% Variance; Previous PPR estimate 45%; Variance) | 50 | Project Management | (Baseline 57%; -7% Variance; Previous PPR estimate 50%; no Variance) | 100 | Completed | 100 | (Percent complete is actually trending at 116% - "Percent Complete" field will only accept 100; Baseline 98%; 14% Variance; Previous PPR estimate 107%; 9% Variance) The project has spent additional effort engineering to address Make-Ready challenges on various parts of the middle-mile route. | 100 | No expenditures scheduled in this milestone. | 44 | (Baseline 71%; -27% Variance; Previous PPR estimate 46%; 1% Variance) The NH Public Utilities Commission is continuing to process river and railroad crossing permits. | 67 | (Baseline 100%; -33% Variance; Previous PPR estimate 61%; 6% Variance) Middle Mile Make-Ready expenses continue to come in higher than planned. FastRoads has commenced make ready on their portion of the route. | 39 | (Baseline 38%; 1% Variance; Previous PPR estimate 32%; 7% Variance) Continuing to acquire fiber optic cables and materials and microwave equipment. | 40 | (Baseline 30%; 10% Variance; Previous PPR estimate 40%; no Variance) | 5 | (Baseline 51%; -46% Variance; Previous PPR estimate 25%; -20% Variance) An invoice from one of the vendors missed the processing deadline for quarter end. If included, the previous quarterly PPR projection would have been met. | 0 | (Baseline 9%; -24% Variance; Previous PPR estimate 0%; no Variance) | 2012-05-10 12:16 | 2012-05-10 12:16 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2012 | Q2 | Q2 - 2012 | 7013 | 6134 | TRUE | 62 | Baseline forecast 74 (Variance -12) Q2 PPR forecast 70 (Variance -8). Network New Hampshire Now came very close to reaching its target of 67% expenditure by the end of this quarter but missed that target due to two timing issues: -Delays in match funding for the the New Hampshire FastRoads project delayed anticipated expenditures. NH FastRoads has expended 19% of their budget. NH FastRoads anticipates receipt of match funding in early Q3 2012 and will expedite expenses to substantially improve the timeline in this area. -NHDOT had projected to spend an additional $2 million, but the State of NH approval process pushed this into Q3 2012. | 56 | Project Management | Baseline forecast 66 (Variance -10) Q2 PPR forecast 60 (Variance -4) | 100 | Completed | 100 | Actual is 118% Baseline forecast 100 (Variance +18) Q2 PPR forecast 122 (Variance - 4). New Hampshire FastRoads network design spending was lower than forecast. Match is being secured and progress should be near completion in Q3 2012. | 100 | No expenditures scheduled in this milestone | 47 | Baseline forecast 87 (Variance -40) Q2 PPR forecast 56 (Variance -9) Three projects had forecast expenditures in this milestone, but only totaled $127K: NHOS ($99K); NH FastRoads ($15K); and Green Mountain Communications ($13K). No actual expenditures occurred in this quarter due to process timing issues, but will be expended in the coming quarter. | 100 | Actual 102% Baseline forecast 87 (Variance +13) Q2 PPR forecast 56 (Variance +46) Tower Match was posted against this category, but will be transferred to a different category after approval of a budget revision through the Award Action Request (AAR) process. | 59 | Baseline forecast 47 (Variance +12) Q2 PPR forecast 66 (Variance -7) NH FastRoads had projected to award their networking equipment during this quarter, but was unable to solidify the required match funding. Match funding is expected in Q3 2012, which will put this milestone back on track. | 45 | Baseline forecast 57 (Variance -12) Q2 PPR forecast 56 (Variance -11) NHDOT had projected to spend 15% more than what was actually spent. The shortfall was due to a longer than expected approval process with the State of NH. This shortfall will be made up in the next quarter. | 38 | Baseline forecast 59 (Variance -21) Q2 PPR forecast 34 (Variance +4) We are slightly ahead of forecast from our previous quarter PPR projections. The project baseline will be met upon completion of Microwave equipment deployment in Q2 2013. | 0 | Baseline forecast 14 (Variance -14) Q2 PPR forecast 0 (No Variance). Network testing is anticipated to begin in Q3 2012. | 2012-08-10 14:20 | 2012-08-10 14:20 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2012 | Q3 | Q3 - 2012 | 7841 | 6625 | TRUE | 72 | Baseline forecast 85 (Variance -14) Q3 PPR forecast 74 (Variance -2). | 63 | Project Management | Baseline forecast 75 (Variance -12); Q3 PPR forecast 64 (Variance -1) No significant variance from previous PPR projections. Project management actuals were lower than forecasted due to a reduction in project management resources. | 100 | Completed | 100 | Actual is 124%; Baseline forecast 100 (Variance +24); Q3 PPR forecast 130 (Variance - 6) Third party make ready expenses on the middle mile have been difficult to project. A docket has been opened with the New Hampshire Public Utilities Commission(NH PUC), Docket 12-107, regarding a review of third party make ready costs in New Hampshire. Additional information has been provided the NH PUC as requested in an order in September to allow them to perform their review. Third party make ready delays have also pushed out design and construction on some routes of the Middle Mile. New Hampshire Optical Systems continues to work with a variety of Competitive Local Exchange Carriers (CLECs) to strive for resolutions in concert with the NH PUC review. New Hampshire FastRoads had anticipated to be completed with splice diagrams and fiber allocation. These expenses have been reallocated into projections for Q4 2012 and Q1 2013. | 100 | No expenditures scheduled in this milestone. | 72 | Baseline forecast 100 (Variance -18); Q3 PPR forecast 59 (Variance +13) Due to delays in signing a construction vendor, the network is behind schedule in obtaining pole licenses on the middle mile. The project has received over 72% of pole licenses from both the telecommunications pole owner and the electric company pole owner. Construction of fiber is complete on 1/3 of the network and 40% of the network has been constructed with strand. Construction is commenced immediately on each segment that we have received clear path notification from pole owners and third party CLECs. All licensing requests have been submitted to pole owners for the last mile and are currently either being surveyed or in Make Ready anticipating licensure in Q1 2013. | 100 | Actual 125%; Baseline forecast 100 (Variance +25); Q3 PPR forecast 111% (Variance +14) Actual expenses for utility Make Ready have exceeded projections. NHOS and New Hampshire Fast Roads continue to monitor Make Ready expenses. NHOS continues to work with the NH PUC and pole owners to examine these expenses. As this is a fixed price contract the vendor will not charge more than was awarded in their agreement. We have lowered strand count in some areas of the route to mitigate this expense. | 65 | Baseline forecast 96 (Variance -31); Q3 PPR forecast 67 (Variance -2) New Hampshire FastRoads secured match funding in Q3 2012. Purchase orders have been placed on all equipment but we decided to have the equipment delivered in phased rather than have it all delivered and then sit in storage. . Switching equipment has been received and paid, but remaining equipment has not been delivered, thus a reduction in anticipated expenditures in this category. New Hampshire FastRoads has also made a strategic change to co-locate one of their core sites instead of constructing in leased space. The funds allocated in Q3 for this activity will be incurred in Q4 2012. | 53 | Baseline forecast 83 (Variance -30); Q3 PPR forecast 63 (Variance -10) New Hampshire Optical Systems (NHOS) projections were 400K lower than actuals due to areas anticipated to be available to build have been delayed due to third party Make Ready issues. New Hampshire FastRoads had projected 871K of activity in Network build that did not occur due to availability of match funding and licensing not being finalized on the poles in last mile network. The New Hampshire Department of Transportation had forecast 2 million in spend but actuals incurred were approximately 1 million due to the timing of the State of New Hampshire invoicing process. | 47 | Baseline forecast 71 (Variance -24); Q3 PPR forecast 40 (Variance +7) Microwave router deployments exceeded projections. Other areas on hold for deployment of Network Equipment due to third party Make Ready issues | 0 | Baseline forecast 23 (Variance -23); Q3 PPR forecast 0 (No Variance) | 2012-11-13 13:11 | 2012-11-13 13:11 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2012 | Q4 | Q4 - 2012 | 9005 | 7780 | TRUE | 80 | Overall project spending was consistent with last quarterâ€™s 80% projection. The project continues to observe higher than expected make-ready charges from Competitive Local Exchange Carriers (CLECs) and longer than anticipated make-ready timelines. These delays have also pushed out design and construction on some routes of the Middle Mile. A docket was opened last quarter with the New Hampshire Public Utilities Commission (NH PUC), Docket DT 12-107, regarding a review of third party make ready costs in New Hampshire. Additional information has been provided to the NH PUC this quarter as was requested in an order in September to allow the PUC to perform their review of the Docket. Consequently, third party make-ready expenses on the Middle and Last Mile have been difficult to project. New Hampshire Optical Systems (NHOS) and the University of New Hampshire (UNH) continue to work with one CLEC to strive for resolutions in concert with the NH PUC review regarding make-ready. | 68 | Project Management | Baseline forecast 82 (Variance -14); Q3 PPR forecast 70 (Variance -2) No significant variance from previous PPR projections. Project management actuals were lower than forecast due to a reduction in project management resources. | 100 | Complete | 100 | Actual is 136%; Baseline forecast 100 (Variance +36); Q3 PPR forecast 127 (Variance +9) NH FastRoads had anticipated to be completed with splice diagrams and fiber allocation. These expenses have been reallocated into projections for Q1 2013 and Q2 2013. They are also continuing to reach an agreement with the town of New London to locate equipment. | 100 | No expenditures scheduled in this milestone. | 100 | Actual is 113%; Baseline forecast 100 (Variance +13); Q3 PPR forecast 86 (Variance +27) NH FastRoads spent approximately 10% more than projected make-ready costs due to utility pole licensure taking longer than expected. This has delayed make-ready construction for CLECs. All licensing requests have been submitted to pole owners for the last mile and are now in make-ready. Licensure is anticipated in Q1 2013. NHOS surpassed their projection this quarter because of significant cost overruns in make-ready. | 100 | Actual is 138%; Baseline forecast 100 (Variance +38); Q3 PPR forecast 126 (Variance +12) NHOS and NH FastRoads make-ready expenses were higher than originally budgeted. | 69 | Baseline forecast 100 (Variance -31); Q3 PPR forecast 70 (Variance -1) Both NHOS and NH FastRoads expected to have segments lit that are currently still in construction or waiting for make-ready. Equipment was purposely delayed to coincide with the availability of the network. The original microwave project timeline assumed that the system would come on line on a link-by-link basis. The engineering process revealed that the nature of the public safety communications system required us to modify the original plan so that the new network would be constructed in parallel with the existing T1-based network and then a single transition would take place. The entire system must be operational before the datacasting portion can be completed, therefore, we delayed the procurement process for this component of the project by a few quarters. Datacasting will be completed before Q2 2013. | 62 | Baseline forecast 96 (Variance -34); Q3 PPR forecast 66 (Variance -4) Both NH FastRoads and NHOS expended less in this category than expected. NHOS needed to spend funds originally allocated this quarter for Network Build to complete work for make-ready with NH CLECs. | 48 | Baseline forecast 87 (Variance -39); Q3 PPR forecast 54 (Variance -6) Previous PPR projection was not achieved as 2 pieces of Microwave equipment to be deployed missed year-end invoicing and will be realized in Q1 2013. While the percentage was high, the dollar amount is less than $100K. | 0 | Baseline forecast 55 (Variance -55); Q3 PPR forecast 50 (Variance -50) NH FastRoads had forecast they would be testing in Q4 2012, but have been delayed as they await route construction and coinciding equipment procurement. These expenses have been reallocated into projections for Q2 2013. | 2013-02-27 11:14 | 2013-02-27 11:14 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2013 | Q1 | Q1 - 2013 | 10023 | 8561 | TRUE | 83 | Actual is 83%. Baseline forecast 97.5% (Variance -14.5) Q4 PPR forecast 87% (Variance -4%) The project continues to observe higher than expected make-ready charges from Competitive Local Exchange Carriers (CLECs) and longer than anticipated make-ready timelines. These delays have also pushed out design and construction on some routes of the Middle Mile and the Last Mile. We started to see progress on third party make-ready work from the last CLEC at the end of the quarter. Docket DT 12-107 is open with the New Hampshire Public Utilities Commission (NH PUC) regarding a review of third party make-ready costs and process in New Hampshire. Additional information has been provided to the NH PUC this quarter after a Staff Recommendation letter was issued on January 30, 2013. Third party make-ready expenses on the Middle and Last Mile remain difficult to project. New Hampshire Optical Systems (NHOS) and the University of New Hampshire (UNH) continue to work with one CLEC to strive fo | 75 | Project Management | Baseline forecast 91 (Variance -16); Q4 PPR forecast 84 (Variance -9) It was our expectation that the budget AAR would have been submitted and approved during this quarter. That AAR would have reallocated Administrative and Legal category budgeted funds to the Site Preparation category. This reallocation would have reduced the total Administrative and Legal budget resulting in an increase of the percent expended in this category. Since the AAR was not submitted, it resulted in a missed projection for this category. | 100 | Complete | 100 | Actual is 137%; Baseline forecast 100 (Variance +37); Q4 PPR forecast 138 (Variance -1) NH FastRoads network design work did not meet Q1 2013 forecast, and is scheduled for completion in Q3 2013. | 100 | No expenditures scheduled in this milestone | 100 | Actual is 113%; Baseline forecast 100 (Variance +13); Q4 PPR forecast 122 (Variance -9) Work forecast by NHOS was not billed as projected during Q1 2013 and will be received in Q2 2013. | 100 | Actual is 139%; Baseline forecast 100 (Variance +39); Q4 PPR forecast 139 (No Variance) | 71 | Baseline forecast 100 (Variance -29 ); Q4 PPR forecast 75 (Variance -4) NH FastRoads and NHOS Network Builds did not occur as projected as a result of multiple snowstorms along with utility and third party make-ready delays. USNH equipment purchases were delayed by route that had been forecasted to be complete in Q1 2013. These expenses will be incurred in the coming quarter. Microwave datacasting equipment will be acquired in Q2 2013 instead of as forecast for Q1 2013. | 66 | Baseline forecast 97 (Variance -31 ); Q4 PPR forecast 70 (Variance -4 ) NH FastRoads and NHOS Network Build expenditures did not occur as projected as a result of multiple snowstorms along with utility and third party make-ready delays. | 51 | Baseline forecast 98(Variance -47); Q4 PPR forecast 66 (Variance -15) Equipment Deployment expenditures for middle mile and last mile networks did not complete as projected due to construction delays and third party make-ready work delays. | 0 | Baseline forecast 85 (Variance -50 ); Q4 PPR forecast 50 (Variance -50 ) Network testing expenditures for middle mile and last mile networks did not complete as projected due to construction delays and third party make-ready work delays. | 2013-05-31 11:44 | 2013-05-31 11:44 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2013 | Q2 | Q2 - 2013 | 10733 | 9030 | TRUE | 93 | Actual is 93%. Baseline forecast 100% (Variance -7) Due to third party Make-Ready delays, the project requested and received an extension to complete by December 31, 2013. NHOS has reached an agreement with a Competitive Local Exchange Carrier (CLEC) that removes remaining obstacles to construction in NH. NHOS is working with a Massachusetts CLEC to complete Make-Ready on the portion of the route that will connect with the Massachusetts Broadband Initiative (MBI) project, MassBroadband 123. | 87 | Project Management | Baseline forecast 100 (Variance -13) The new budget reduced the total Administrative and Legal budget resulting in an increase of the percent expended in this category. | 100 | Complete. | 100 | Actual is 103%; Baseline forecast 100 (Variance +3) Network design slightly exceeded budget. | 100 | No expenditures scheduled in this milestone. | 97 | Actual is 97%; Baseline forecast 100 (Variance -3) | 100 | Actual is 101%; Baseline forecast 100 (Variance +1) | 89 | Baseline forecast 100 (Variance -11 ) NH FastRoads and NHOS network builds did not occur as projected as a result of weather delays along with utility and third party Make-Ready delays. USNH delayed equipment purchases to coincide with completion of the Middle Mile route. These expenses will be incurred in the coming quarter. Microwave datacasting equipment was acquired in Q2 2013 instead of as forecast for Q1 2013. | 92 | Baseline forecast 100 (Variance -8 ) NH FastRoads and NHOS network build expenditures did not occur as projected as a result of multiple snowstorms and utility and third party Make-Ready delays. | 66 | Baseline forecast 100 (Variance -34) Equipment Deployment expenditures for Middle Mile and Last Mile networks did not complete as projected due to construction delays and third party Make-Ready work delays. | 35 | Baseline forecast 100 (Variance -65 ) Network testing expenditures for Middle Mile and Last Mile networks did not complete as projected due to construction delays and third party Make-Ready work delays. | 2013-08-26 11:54 | 2013-08-26 11:54 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2013 | Q3 | Q3 - 2013 | 11403 | 9514 | TRUE | 95 | Baseline 100 Projected last quarter to be 98. Due to shifting project priorities to complete the NH FastRoads network, portions of work on the Middle mile were delayed. Received an extension in Q2 2013 to complete remaining work by the end of Q4 2013. | 92 | Project Management | Baseline 100. Projection last quarter 96. Cash contribution was received but not posted by the end of Q3 2013. | 100 | Complete | 100 | Actual spend was104%. Baseline 100. Anticipate another 2% of expediture due to completion of turnup and design of the Fastroads network. Final expenses in this milestone were higher than anticipated but offset in in lower expenditures in other milestones. | 100 | No expenditures scheduled in this milestone. | 97 | Baseline 100. Work on microwave network will be completed in Q4 2013. | 100 | Actual spend was 101%. Baseline 100. This category is projected to be complete in Q4 2013. Anticipate another 1% of expenditure due to completion of turn-up and design of the FastRoads network. Final expenses in this milestone were higher than anticipated but offset in in lower expenditures in other milestones. | 93 | Baseline 100. Projection last quarter at 95. Anticipated final invoices on subawardees would have been received by end of the quarter. This invoices will be processed Q4 2013. | 94 | Baseline 100. Projection last quarter 97. Due to shifting project priorities to complete the NH FastRoads network, portions of work on the Middle Mile were delayed. | 68 | Baseline 100. Projection last quarter 98. Last microwave site did not complete as projected this quarter. Remaining work is on schedule to complete in Q4 2013. | 61 | Baseline 100. Projection last quarter 78. NH FastRoads testing completed, but awaiting invoicing. | 2013-11-26 15:17 | 2013-11-26 15:17 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2013 | Q4 | Q4 - 2013 | 12281 | 10452 | TRUE | 100 | Complete - Actual % was 100 | 100 | Project Management | Complete - Actual % was 105. | 100 | Complete - Actual % was 100. | 100 | Complete - Actual % was 101. | 100 | No expenditures scheduled in this milestone. | 100 | Complete - Actual % was 93. | 100 | Complete - Actual % was 103. | 100 | Complete - Actual % was 100. | 100 | Complete - Actual % was 96. | 100 | Complete - Actual % was 96. | 100 | Complete - Actual % was 137. | 2014-06-20 12:55 | 2014-06-20 12:55 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570084 | 2010 | Q4 | Q4 - 2010 | 1179 | 2213 | TRUE | 1 | Positive variance from revised Baseline Plan | 0 |  | No variance from revised Baseline Plan | 60 | Secured EA vendor and submitted draft EA for initial planned locations. All requested revisions/responses to EA draft are in-process. Outstanding issues remained with USFW and Iowa SHPO, follow up with Miami Tribe. Maps with narrative will be re-submitted with final EA, as requested. | 45 | High level Network Design has been substantially completed but finalization is pending EA and site acquisition activities. Pending any EA related mitigation requirements discovered during actual construction, high level Network Design should remain unchanged throughout the remainder of the project. Site Acquisition and RF Analysis will start next reporting period. | 0 | No variance from revised Baseline Plan (note 2c). | 0 | No variance from revised Baseline Plan | 0 | No variance from revised Baseline Plan | 0 | No variance from revised Baseline Plan | 0 | No variance from revised Baseline Plan | 0 | No variance from revised Baseline Plan | 0 | No variance from revised Baseline Plan | 2011-02-16 14:11 | 2011-02-16 14:11 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2011 | Q1 | Q1 - 2011 | 2085 | 2788 | TRUE | 1 | Due to the project modification we are not meeting our original baseline plan. If and when the project modification is approved we will be on track with our revised baseline report. | 0 |  | No variance from the Baseline Report | 30 | Followed up with Miami Tribe and there were no issues and also received a "no objection" letter from the USFW. Due to the project modification, we have not contacted the SHPO. If and when the project modification is approved, we will proceed with contacting the SHPO and negotiating a programmatic agreement. | 40 | Finalization is pending EA and site acquisition activities. If and when the project modification is approved we will be in track with our revised baseline report. | 0 | No variance from the Baseline Report | 0 | No variance from the Baseline Report | 0 | No variance from the Baseline Report | 0 | We have not procured any equipment due to not receiving a FONSI, therefore, we have variance from the Baseline Report. | 0 | No variance from the Baseline Report | 0 | No variance from the Baseline Report | 0 | No variance from the Baseline Report | 2011-05-17 12:49 | 2011-05-17 12:49 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2011 | Q2 | Q2 - 2011 | 3085 | 3300 | TRUE | 2 | Currently we are not on target with the originally approved baseline report. The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. | 0 |  | N/A | 35 | Currently we are not on target with the originally approved baseline report. The variance from the originally approved baseline report was caused by the need to complete a modification to the original project. EA activites were stopped so that IHS could identify site locations that would allow for sustainability after eliminating wireless infrastructure. | 45 | Finalization is pending EA and site acquisition activities. Currently we are not on target with the originally approved baseline report. The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. | 0 | Right of Way work is pending site acquisition activities. The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. | 0 | Construction Permits and Other approval work is pending EA and site acquisition activities. The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. | 0 | No variance from the Baseline Report | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability and not receiving a FONSI. | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. | 2011-08-15 14:13 | 2011-08-15 14:13 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2011 | Q3 | Q3 - 2011 | 3927 | 3802 | TRUE | 4 | IHS is currently on target with the baseline report. IHS identified the hut locations for the Main, North, West, and South Rings. OSP Design for the Main, North, West, and South Rings is started and in process. ISP Design for the North, West, South, East Long Haul, West Long Haul, and Central Rings is in process. The negotiations for the IRU are underway and pending finalization on receiving a FONSI. USFWS consultation, SHPO consultation, and Tribal consultations are underway. | 0 |  | No variance from the baseline report. | 45 | IHS EA/Section 106 for the 9 hut locations and corresponding fiber laterals are near completion. IHS received a "no objection" response from USFWS for the 9 hut locations and corresponding fiber lateral. the middle mile extension fiber routes are still under consultation with USFWS. | 70 | The ISP statewide network design is in process for North, West, East Long Haul, West Long Haul and the Central Ring. The OSP Design is in process for the Main, North, West, and South Ring. The OSP Engineering Vendor has been selected and working through the Master Service Agreement to finalize the OSP design. | 0 | No variance from the baseline report. | 0 | No variance from the baseline report. | 0 | No variance from the baseline report. | 0 | No variance from the baseline report. | 0 | No variance from the baseline report. | 0 | No variance from the baseline report. | 0 | No variance from the baseline report. | 2011-11-08 17:35 | 2011-11-08 17:35 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2011 | Q4 | Q4 - 2011 | 5099 | 4770 | TRUE | 56 | IHS is slightly under the 60% completion target anticipated for this quarter. Current activities completed include preliminary procurement of DWDM transport equipment, MRV Console, Huts, UPS Systems, and Generators in order to expedite our project prior to receiving the FONSI. The Programmatic Agreement was negotiated and went through administrative procedures allowing all appropriate parties to execute via electronic signature. The draft EA was submitted for review early in December and was returned for additional revisions needed prior to obtaining the FONSI. The draft EA revision is under way and projected to be submitted in early January 2012 for final review. The negotiations for the IRU are underway and pending finalization on receiving a FONSI. | 0 |  | No variance from the baseline report. | 49 | The Programmatic Agreement was negotiated and went through administrative procedures allowing all appropriate parties to execute via electronic signature. The draft EA was submitted for review early in December 2011 and was returned for additional revisions needed prior to obtaining the FONSI. The draft EA revision is under way and projected to be submitted in early January 2012 for final review. | 70 | OSP Engineering for the fiber laterals to the 9 hut locations are under way and ISP Engineering is almost complete as well, with the expectation to be completed in January 2012. | 0 | IHS anticipates that the Right of Way work will start Quarter 3, Year 2 (Jan-Mar 2012). | 0 | IHS anticipates the permitting for the 9 hut locations will be finalized after receiving the FONSI. | 0 | IHS anticipates the site preparation to begin Quarter 3, Year 2 (Jan-Mar). | 62 | IHS procured the equipment that was necessary to expedite the project once it receives a FONSI. Current activities completed include preliminary procurement of DWDM transport equipment, MRV Console, Huts, UPS Systems, and Generators. | 0 | The negotiations for the IRU are underway and pending finalization on receiving a FONSI. | 0 | No variance from the baseline report. | 0 | No variance from the baseline report. | 2012-02-17 14:47 | 2012-02-17 14:47 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2012 | Q1 | Q1 - 2012 | 5937 | 5568 | TRUE | 61 | IHS is Under the 83% completion target anticipated for this quarter. Current activities underway are the OSP and ISP engineering for the 9 hut locations, ROWs, and EA activities. The router procurement was completed and IHS/BBI committed its a portion of its cash match. | 0 |  | No variance from the baseline report. | 52 | IHS/BBI obtained its FONSI in February 2012. However, IHS/BBI encountered reroutes for the citites of Iowa City, Marshalltown, Davenport, and Waterloo due to either pole replacements of newly passed city ordinances. IHS/BBI anticipates to submit the reroute modification to NTIA during Q2 2012 for further direction. | 75 | OSP Engineering for the fiber laterals to the 9 hut locations are underway and ISP engineering is almost complete as well, with the expectation to be completed during Q4 2012 (Oct-Dec). IHS/BBI is slightly behind the 85% milestone due to the unknown location of Middle Mile Extensions. | 25 | Rights of Way activities are underway and IHS anticipates that the Right of Way work will be completed through Phase 2, hut installation, during Q2 2012 (Apr-Jun). | 45 | IHS/BBI anticipates the permitting for the 9 hut locations will be finalized during Q2 2012. | 0 | IHS anticipates the site preparation to begin Q2 2012. | 72 | IHS/BBI exceeds the baseline for procuring equipment. Ethernet Switches adn Installation Kits are anticipated to be procured during Q2 2012 (Apr-Jun). | 0 | The negotiations for the IRU are underway and will be finalized in Q2 2012 (Apr-Jun) | 0 | No variance from the baseline report. IHS/BBI anticipates Equipment Deployment to begin in Q2 2012 (Apr-Jun). | 0 | No variance from the baseline report. IHS/BBI anticipates Network Testing to begin in Q2 2012. | 2012-05-07 10:41 | 2012-05-07 10:41 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2012 | Q2 | Q2 - 2012 | 7005 | 6130 | TRUE | 69 | IHS is slightly behind target due to the route modifications requiring EA approval prior to construction, equipment cost savings, and middle mile extension fiber builds are pushed back due to signing customers. Another variance from baseline is due to the unanticipated time frame to obtain the permitting and land leases for the 9 hut locations. | 0 |  | N/A | 70 | IHS encountered fiber re-routes during Q1 2012 and has submitted the required documentation during Q2 2012 in anticipation of approval from NTIA and the Iowa SHPO. IHS anticipates approval from NTIA and SHPO concurrence to move forward with construction activities for the re-routes during Q3 2012. IHS anticipates more EA activities associated with the middle mile extension during Q3 2012. | 85 | Outside Plan and Inside Plant engineering has been completed for the 9 hut and lateral locations. IHS continues to work on obtaining last mile customers to migrate them onto the network. | 50 | Variance from baseline due to the unanticipated time frame to obtain permitting and land leases for the 9 hut locations. Rights of Way activities are almost completed for hut Installation and are underway for the Middle Mile Extensions. IHS anticipates ROW completion for the hut laterals in Q3 2012 and continued ROW for middle mile extensions through Q1 2013. | 70 | IHS has obtained all construction permits and most additional approvals for the 9 hut and lateral locations. IHS anticipates finalizing all additional approvals in Q3 2012 and continuing to obtain approvals for the middle mile extensions through Q1 2013. | 0 | Variance from baseline due to the unanticipated timeframe to obtain permitting and land leases for the 9 hut locations. IHS finalized agreements with two site prep vendors and they are projected to complete all site prep activities in Q3 2013. | 90 | IHS continues to move forward procuring equipment necessary to deploy to the proposed upgraded capacity. IHS selected an Ethernet Switch vendor and will procure ethernet switches as last mile customers are signed. | 40 | Variance from baseline due to the unanticipated time frame to obtain permitting and land leases for the 9 hut locations. IHS finalized the IRU with Long Lines to lease 99 miles of fiber to complete the western ring. IHS anticipates completing the 9 hut fiber laterals by end of Q3 2012 and starting the middle mile extension for three customers during Q3 2012 | 20 | IHS has deployed equipment to 8 site locations during Q1 2012. IHS anticipates deploying all equipment to bring up the main ring by Q4 2012 during Q3 2012 and into Q4 2012. | 0 | No variance from baseline. Network testing anticipated to start Q3 2012 | 2012-08-10 13:38 | 2012-08-10 13:38 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2012 | Q3 | Q3 - 2012 | 7989 | 6701 | TRUE | 73 | IHS is slightly behind target due to the route modifications requiring EA approval prior to construction for the 9 hut locations and middle mile extension fiber builds are pushed back due to route modification approvals. IHS anticipates that it will be at 80% of overall project completion by end of Q4 2012 to complete construction to 3 LMP customers and to activate the main ring. | 0 | N/A | N/A | 80 | IHS received approval from NTIA and SHPO concurrence to move forward with construction activities for the hut and lateral re-routes this quarter. IHS submitted another route modification for 3 middle mile customer reroutes during this qtr and anticipates approval start of Q4 2012. More EA activities associated with the middle mile extension during Q4 2012 are anticipated and the route modification package will be submitted to NTIA end of Q4 2012. | 95 | Outside Plan and Inside Plant engineering has been completed for the 9 hut and lateral locations. IHS continues to work on obtaining last mile customers to migrate them onto the network. IHS anticipates that all customers will be signed by end of Q4 2012 and plans to connect those customers will be finalized in Q1 2013. | 75 | Variance from baseline due to the unanticipated time frame to obtain permitting and land leases for the 9 hut locations and 3 last mile providers. Rights of Way activities are completed for the 9 hut sites and 3 last mile providers. IHS anticipates ROW completion for the middle mile extensions through Q1 2013. | 70 | IHS has obtained all construction permits and additional approvals for the 8 hut and lateral locations. IHS is finalizing the approvals for the Cedar Rapids lateral portion of the route and anticipates finalizing all additional approvals in Q4 2012. IHS will continue to obtain approvals for the middle mile extensions through Q1 2013. | 75 | Variance from baseline due to the unanticipated timeframe to obtain permitting and land leases for the 9 hut locations. IHS finalized agreements with two site prep vendors and they are projected to complete all site prep activities in Q3 2013. | 95 | IHS continues to move forward procuring equipment necessary to deploy to the proposed upgraded capacity. IHS anticipates to upgrade capacity on the western long haul route and will send in an AAR beginning of Q4 2012 for approval. Ethernet switches were procured during Q3 2012 for 3 last mile customer sites. | 80 | Variance from baseline due to the EA route changes to complete the 9 fiber lateral builds. IHS completed 8 hut fiber laterals by end of the quarter and will finish the 9th site by beginning of Q4 2012. IHS anticipates the middle mile extension for three customers to start following the Route Modification approval beginning Q4 2012. | 40 | IHS has deployed equipment to 14 site locations during Q3 2012. IHS anticipates deploying all equipment to bring up the main ring by Q4 2012. | 30 | Network testing started this qtr for the main ring with the anticipation of main ring activation by end of Q4 2012. | 2012-11-20 16:37 | 2012-11-20 16:37 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2012 | Q4 | Q4 - 2012 | 8835 | 7621 | TRUE | 85 | IHS has exceeded the overall project key indicators. IHS has had a successful last mile provider implementation for 3 construction builds, 9 hut lateral installations for the year, and main ring activation on the network. | 0 |  | N/A | 90 | IHS has exceeded the Environmental Assessment milestone and may only pursue one last route to close out the EA milestone by end of Q1 2013 | 97 | IHS is on target and is forecasted to remain on track to project completion by end of Q2 2013 | 80 | Variance from baseline due to the unanticipated time frame to obtain permitting. Rights of Way activities are completed for the 3 middle mile extension fiber routes being build through Q1and Q2 2013, however, are underway for the 4 newly proposed route changes with final ROW completion by end of Q1 2013 | 80 | Variance from baseline due to the unanticipated time frame to obtain permitting. IHS completed all construction permitting for the 3 route changes for middle mile extensions that were approved by NTIA in Q4 2013. IHS will continue to obtain approvals for middle mile extensions through Q1 2013 and complete all permitting the beginning of Q2 2013 | 80 | Variance from baseline due to the unanticipated time frame to obtain permitting. IHS will start the RFQ process to obtain competitive bids to start site prep for the 4 proposed route changes that will be submitted in the beginning of Q1 2013 but will not start any construction/site prep until NTIA approves of the newly proposed 4 route changes | 98 | IHS has exceeded the Equipment Procurement milestone. IHS completed equipment procurement for the network and only plans on procuring consummables as needed to complete the IHS network ring bring ups by end of Q1 2013 | 85 | Variance from baseline due to the unanticipated time frame to obtain permitting and will remain on schedule to complete all fiber builds for customers if the routes are approved by the beginning of Q2 2013 | 48 | Variance from baseline due to the unanticipated time frame to obtain permitting and EA approvals. IHS completed the main ring DWDM equipment deployment and activation in Q4 2012. All equipment deployment will be completed the beginning of Q2 2013 | 48 | Variance from baseline due to the unanticipated time frame to obtain permitting and EA approvals. IHS completed the main ring testing and activation for 21 sites. The remaining rings will be completed in Q1 and Q2 2013 | 2013-02-19 12:17 | 2013-02-19 12:17 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2013 | Q1 | Q1 - 2013 | 9901 | 8492 | TRUE | 89 | Variance from baseline due to major construction delays caused by a severe weather delays. | 0 | N/A | N/A | 100 | Complete: IHS/BBI exceeded this milestone and has completed all necessary/required environmental assessments. | 98 | Variance from baseline due to finalizing customer connections. | 100 | On Target | 90 | Variance from baseline due to the unanticipated time frame to obtain permitting. IHS completed all construction permitting for the 3 route changes for middle mile extensions that were approved by NTIA in Q4 2013. IHS will continue to obtain approvals for middle mile extensions through Q1 2013 and complete all permitting the beginning of Q2 2013 | 100 | Complete | 99 | Variance from baseline due to the unanticipated equipment procurement to bring on the final group of last mile connections. | 90 | Variance from baseline due to the unanticipated time frame to obtain permitting and weather delayed construction activities. IHS/BBI plans to start construction activities back up in Q2 2013, however, will not be completed by end of Q2. | 90 | On target. IHS/BBI deployed equipment on the north and western rings....and start on long haul routes Q2 2013. | 90 | On target | 2013-05-24 14:02 | 2013-05-24 14:02 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2013 | Q2 | Q2 - 2013 | 10697 | 9011 | TRUE | 89 | Variance from baseline due to major construction delays caused by a severe weather delays. |  |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 99 | Variance from baseline due to the unanticipated equipment procurement to bring on the final group of last mile connections. | 95 | Variance from baseline due to the unanticipated time frame to obtain permitting and weather delayed construction activities. IHS/BBI plans to start construction activities back up in Q2 2013, however, with completion by end of Q3 2013. | 95 | IHS/BBI is deploying equipment to connect customers....and start on long haul routes Q3 2013. | 95 | IHS/BBI plans to be complete all network testing by end of Q3 2013. | 2013-08-22 16:21 | 2013-08-22 16:21 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2013 | Q3 | Q3 - 2013 | 11835 | 10012 | TRUE | 100 | Complete | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-02-18 15:32 | 2014-02-18 15:32 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570085 | 2010 | Q4 | Q4 - 2010 | 1371 | 2385 | TRUE | 1 | No Variance | 5 | Vehicles | VTel purchased two broadband vehicles. | 70 | We have completed an environmental assessment draft. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2 | We have completed purchase of a Netapp Data Storage system. | 0 | No Variance | 2 | We have deployed a Netapp Data Storage system. | 2 | No Variance | 2011-02-25 08:50 | 2011-02-25 08:50 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2011 | Q1 | Q1 - 2011 | 2335 | 2913 | TRUE | 1 | The process of identifying overlap, removing it, and reprogram/rebudget of the project has put our project behind the original baseline; however due to the reduction in project scope, which removed approximately 50% of the new miles to be constructed we do not see a significant risk to the completion of the project within the allotted time line. In the next quarter we intend to create and submit an updated baseline that more accurately reflects the new project scope and funding level. The project scope change was not finalized until next quarter, which happened prior to submission of this quarterâ€™s report. | 100 | Vehicles | VTel purchased two broadband vehicles. | 70 | Please see narrative regarding overall project completion. The change to our project scope has required us to seek new consultations with the related agencies, including the Vermont State Historic Preservation Office, US Fish & Wildlife Services, and several others. Their responses are expected in the next quarter, along with completion of our FONSI. | 0 | Please see narrative regarding overall project completion. The change to our project scope required us to revisit the original network work design as it has deleted some portions of the network and has added others. Within the next quarter we expect of finalize the network design and begin to implementation of the network. | 0 | Please see narrative regarding overall project completion. Given the significant potential for routes to be changed, or removed, during the resolution we did not feel it was a responsible use of funds to pursue rights of way until we had a more clear understanding of the project scope, as we do now. | 0 | Please see narrative regarding overall project completion. Similar to the acquisition of rights of way, we did not feel it was responsible use of funds to pursue construction permits or other approvals until we had a clear understanding of the project scope. | 0 | Please see narrative regarding overall project completion. The change to the project has changed and reduced the scope of the site preparation. Within the next quarter we expect to have a finalized network design and a FONSI allowing us to begin site preparation. | 7 | Please see narrative regarding overall project completion. The change in the network design has cause a change in the configuration of the equipment needed. During the next quarter we expect to have completed the updated network design and issued RFP's to accelerate the procurement of the necessary equipment. | 0 | Please see narrative regarding overall project completion. The change in the project school has significantly reduced the amount of network build required. With updated environmental assessment and the expected issuance of the FONSI in the next quarter we can start the network build. | 2 | Please see narrative regarding overall project completion. The change in the network design has caused the update of the equipment procurement. During the next quarter we expect to have issued and begun the procurement of the equipment. The equipment procurement and the issuance of the FONSI in the next quarter will also allow us to continue the deployment of the equipment. | 2 | Please see narrative regarding overall project completion. With the change in the network design, equipment procurement and deployment, there is also a change in the scope of the network testing. | 2011-05-26 11:33 | 2011-05-26 11:33 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2011 | Q2 | Q2 - 2011 | 3249 | 3387 | TRUE | 3 | All of the projects SAC's have been satisfied and release of funds has been granted. We can now accelerate the project to meet future project milestones. | 50 | Vehicles | VTel purchased two broadband vehicles. | 100 | Enviromental Assement has been complete and a FONSI issued | 2 | The engineering firm has been selected and is mobilizing the resources to accelerate the process of network design to meet future milestones. | 2 | No Variance | 2 | No Variance | 0 | No Variance | 1 | During this quarter we have issued an RFP for our DWDM optical network. During the next quarter the selection of a vendor can be complete and equipment can be ordered. In our Q1 PPR we had | 0 | No Variance | 1 | The equipment deployment will be an element of the respective RFP's released during this quarter. Our prevoius PPR reported 7% completion. This percentage has been reduced as our budget has increased for equipment and we have submitted our updated baseline. | 1 | No Variance | 2011-08-22 09:07 | 2011-08-22 09:07 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2011 | Q3 | Q3 - 2011 | 4135 | 3914 | TRUE | 4 | Hurricane/Tropical Storm Irene impacted many areas of Vermont. Travel was difficult for some time, and other utility companies were scrambling to restore services for several weeks. This has caused a slight delay to engineering and permit requests. Baseline was 6%. | 0 |  | In working with the grants office it was determined that the vehicles were not an allowable expense. VTel is working with the grants office and NTIA staff to allocate the funding to other allowable, project-specific, costs. | 100 | Environmental Assessment has been completed, and the project received a Finding Of No Significant Impact in 2Q11. | 66 | 87.7 of 132 miles has been staked in the field by our engineering firm. | 2 | The requests for rights are being submitted during Q411 instead of Q311 due to delays associated with Hurricane/Tropical Storm Irene. Baseline was 10%. | 2 | The requests for rights are being submitted during Q411 instead of Q311 due to delays associated with Hurricane/Tropical Storm Irene. Baseline was 10% | 10 | No Variance. | 55 | No Variance. DWDM equipment is ordered and has begun to arrive. | 0 | No Variance. | 1 | DWDM equipment for upgraded miles has started to arrive and is scheduled to begin deployment during Q411. | 1 | No Variance. | 2011-11-18 14:12 | 2011-11-18 14:12 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2011 | Q4 | Q4 - 2011 | 5175 | 4840 | TRUE | 30 | Fiber construction is scheduled to begin in the 1st quarter of 2012. We have received and installed the majority of the electronic (DWDM) equipment and are in the process of cutting it over. The installation schedule of this equipment has experienced some delays, however those delays are not considered to have an impact on the overall project completion date. | 90 |  | Network testing equipment procurement occurred in this quarter. | 100 | Environmental Assessment has been completed, and the project received a Finding of No Significant Impact in 2Q11. | 89 | 117.34 of 132 miles has been staked in the field by our engineering firm. | 25 | Due to an unexpected absence of the person completing permit applications with our outside engineering company, the process was delayed slightly. Upon her return in the beginning of the 1st quarter 2012, the number of applications has increased to just under 50%. | 25 | See 2d. | 19 | No variance. | 75 | No variance. DWDM equipment has arrived although full payment for the equipment will not be processed until it is lit and tested. We expect to be on schedule with our baseline plan in the 1st quarter of 2012. | 0 | No variance. | 44 | Deployment of DWDM equipment started this quarter. Delays due to coordination with other utility companies, land owner's, and the vendor occurred but it is felt that the completion of the overall project will not be affected. We expect to be on schedule with our baseline plan in the 1st quarter of 2012. | 44 | See 2i. We expect to be on schedule with our baseline plan in the 1st quarter of 2012. | 2012-02-21 17:21 | 2012-02-21 17:21 | 5847 | 5847 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2012 | Q1 | Q1 - 2012 | 6237 | 5721 | TRUE | 43 | Fiber construction began in the 1st quarter of 2012. We are continuing to install the electronic equipment and are in the process of cutting it over. Although out electronics deployment is is happening in a more methodical way than we originally anticipated in our baseline we do not believe it will negatively affect the project completion. This approach is necessary as we want to minimize any possible transition affects of the upgraded system to existing customers. | 90 | N/A | No variance with baseline. | 100 | Environmental Assessment has been completed, and the project received a finding of No Significant Impact in 2Q11. We will be addressing any additional environmental assessments for route changes as they occur. | 100 | The majority of mileage has been staked and routes are finalized. Next quarter we anticipate filing our final routes, including any adds/moves/changes. | 60 | We have submitted a large number of applications at the beginning of the first quarter, and have been responding to make ready payment requests. Many of the make ready requests are scheduled to be complete during the next quarter. We continue to review make-ready status on a weekly basis to quickly address any areas of concern. | 60 | See 2d. | 21 | As mentioned in 2a, the electronics deployment has been done at a more measured pace than originally anticipated and we continue to work closely with the vendor to complete this deployment. | 75 | Our contract with the equipment manufacturer contains a retainer clause. Until the deployment is fully-complete and tested, final payments will not be made. | 5 | Network construction has begun and is progressing. We are slightly behind our baseline projections; however we feel confident that this will not negatively impact completion. | 55 | See 2f. We expect to reach baseline by the end of 2012. | 55 | See 2f. | 2012-05-21 16:28 | 2012-05-21 16:28 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2012 | Q2 | Q2 - 2012 | 7245 | 6250 | TRUE | 53 | Fiber construction continued in the second quarter and was initially delayed by lagging make ready, however in June this has improved. We continue to deploy our electronics. This methodical approach to deployment was not originally in our baseline, however, it is working well and is slated to be completed by the end of 2012. | 90 | Testing Equip. | Testing equipment has been purchased. | 100 | Environmental Assessment has been completed, and the project received a finding of No Significant Impact in 2Q11. We will be addressing any additional environmental assessments for route changes as they occur. | 100 | The majority of mileage has been staked and routes are finalized. We are considering a request for slight additions, removals, and changes in the third quarter 2012. | 60 | 97% of permits have been submitted, and make ready payments on the majority of those have been paid. We are monitoring the make ready deadlines, and are addressing concerns as they arise. | 60 | See 2d. | 59 | We continue to deploy our electronics. This methodical approach to deployment was not originally in our baseline, however, it is working well and is slated to be completed by the end of 2012. | 75 | Our contract with the equipment manufacturer contains a retainer clause. Until the deployment is fully complete and tested, final payments will not be made. | 25 | Network construction is progressing. We are behind our baseline projections; however we feel confident that this will not negatively impact completion. | 60 | See 2f. | 60 | See 2f. | 2012-08-24 16:25 | 2012-08-24 16:25 | 7374 | 7374 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2012 | Q3 | Q3 - 2012 | 8139 | 6780 | TRUE | 56 | Fiber construction continued in the third quarter. There has been a delay with make ready, requiring our outside engineer to conduct a detailed pole survey. There are many segments that have been partially made ready, but now that the on site survey has been completed, we will be able to make specific requests based on our construction plan. | 90 |  | Testing equipment has been purchased. | 100 | Environmental Assessment has been completed, and the project received a finding of No Significant Impact in 2Q11. We will be addressing any additional environmental assessments for route changes as they occur. | 100 | The mileage has been staked and routes are finalized. We have submitted a request to make some additions, removals, and changes in the original routes, which will require additional work here. | 60 | 100% of permits have been submitted, and make ready payments on the majority of those have been paid. We are monitoring the make ready deadlines, and are addressing concerns as they arise. | 60 | See 2d. | 65 | We continue to deploy our electronics. This methodical approach to deployment was not originally in our baseline, but progress is being made. | 75 | Our contract with the equipment manufacturer contains a retainer clause. Until the deployment is fully complete and tested, final payments will not be made. | 30 | Network construction is progressing. We are behind our baseline projections; however we feel confident that this will not negatively impact completion. | 65 | See 2f. | 65 | See 2f. | 2012-11-29 14:29 | 2012-11-29 14:29 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2012 | Q4 | Q4 - 2012 | 8733 | 7531 | TRUE | 59 | Fiber construction continued in the fourth quarter. Due to our difficulties and delays in make ready, we contracted with an individual to inspect segments that had not been licensed and to follow up with the local utility/pole owner to overcome delays. | 90 | Testing Equip. | Testing equipment has been purchased. | 100 | Environmental Assessment has been completed, and the project received a finding of No Significant Impact in 2Q11. We will be addressing any additional environmental assessments for route changes as they occur. | 100 | The mileage has been staked and routes are finalized. We have submitted a request to make some additions, removals, and changes in the original routes, which will require additional engineering. | 65 | 100% of permits have been submitted, and make ready payments on the majority have been paid. We are monitoring make ready deadlines, and are aggressively addressing any problems or road blocks. | 65 | See 2d. | 74 | We continue to deploy our electronics. This methodical approach to deployment was not originally in our baseline, but progress is being made. | 75 | Our contract with the equipment manufacturer contains a retainer clause. Until the deployment is fully completed and tested, final payments will not be made. | 34 | Network construction is progressing. We are behind our baseline projections; however we feel confident that this will not negatively impact completion. | 74 | See 2f. | 74 | See 2f. | 2013-02-12 16:34 | 2013-02-12 16:34 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2013 | Q1 | Q1 - 2013 | 10029 | 8565 | TRUE | 65 | Fiber construction continued in the fourth quarter. Due to our difficulties and delays in make ready, we contracted with an individual to inspect segments that had not been licensed and to follow up with the local utility/pole owner to overcome delays. | 95 | Testing Equip | Testing equipment has been purchased | 100 | Environmental Assessment has been completed, and the project received a finding of No Significant Impact in 2Q11. We will be addressing any additional environmental assessments for route changes as they occur. | 100 | The mileage has been staked and routes are finalized. We have submitted a request to make some additions, removals, and changes in the original routes, which will require additional engineering. | 75 | 100% of permits have been submitted, and make ready payments on the majority have been paid. We are monitoring make ready deadlines, and are aggressively addressing any problems or road blocks. | 75 | see 2d | 83 | We continue to deploy our electronics. This methodical approach to deployment was not originally in our baseline, but progress is being made. | 80 | Our contract with the equipment manufacturer contains a retainer clause. Until the deployment is fully completed and tested, final payments will not be made. | 34 | Network construction is progressing. We are behind our baseline projections, but are pushing all involved hard to reach completion. | 83 | see 2f | 83 | see 2f | 2013-05-31 15:43 | 2013-05-31 15:43 | 7374 | 7374 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2013 | Q2 | Q2 - 2013 | 10713 | 9020 | TRUE | 68 | Fiber construction continued in the 2nd quarter. Due prior difficulties and delays in make ready, we contracted with an outside contractor to handle all permitting for our AAR and to follow up with the local utility/pole owners to overcome delays. | 95 | Testing Equipment | Testing equipment has been purchased | 100 | Environmental Assessment has been completed, and the project received a finding of No Significant Impact in 2Q11. We will be addressing any additional environmental assessments for route changes as they occur. | 88 | The mileage has been staked and routes are finalized. Our submitted AAR has been approved and we have re-engineered the route changes. | 75 | 100% of permits have been submitted, and make ready payments on the majority have been paid. We are monitoring make ready deadlines, and are aggressively addressing any problems or road blocks. | 75 | see 2d | 84 | We continue to deploy our electronics. This methodical approach to deployment was not originally in our baseline, but progress is being made. | 80 | Our contract with the equipment manufacturer contains a retainer clause. Until the deployment is fully completed and tested, final payments will not be made. | 55 | Network construction is progressing. We are behind our baseline projections, but are pushing all involved hard to reach completion. | 68 | see 2f | 58 | see 2f | 2013-08-23 16:22 | 2013-08-23 16:22 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2013 | Q3 | Q3 - 2013 | 11351 | 9477 | TRUE | 74 | Fiber construction continued in the 3rd quarter. We continue to use an outside contractor to handle all permitting for our AAR and to follow up with the local utility/pole owners to overcome delays. | 95 | testing equipment | Testing equipment has been purchased | 100 | Environmental Assessment has been completed, and the project received a finding of No Significant Impact in 2Q11. We will be addressing any additional environmental assessments for route changes as they occur. | 90 | The mileage has been staked and routes are finalized. Our submitted AAR has been approved and we have re-engineered the route changes. | 80 | 100% of permits have been submitted, and make ready payments on the majority have been paid. We are monitoring make ready deadlines, and are aggressively addressing any problems or road blocks. | 80 | see 2d | 88 | We continue to deploy our electronics. This methodical approach to deployment was not originally in our baseline, but progress is being made. | 84 | Our contract with the equipment manufacturer contains a retainer clause. Until the deployment is fully completed and tested, final payments will not be made. | 65 | Network construction is progressing. We are behind our baseline projections, but are pushing all involved hard to reach completion. | 75 | see 2d | 65 | see 2d | 2013-11-22 15:35 | 2013-11-22 15:35 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2013 | Q4 | Q4 - 2013 | 12471 | 10651 | TRUE | 77 | Fiber construction continued in the 4th quarter as well as payments to Alcatel Lucent for equipment purchases. We continue to use an outside contractor to handle all permitting for our AAR GOL #2407329 and to follow up with the local utility/pole owners to overcome delays. Due to weather conditions we have not spent any substantial amounts on construction and expect to see the remainder of our baseline dollars spent in Q2 and Q3 of 2014. | 86 | admin & consulting | Application consulting, NTIA workshops, surveys | 93 | Environmental Assessment has been completed, and the project received a "Finding of No Significant Impact" in 2Q11. We will be addressing any additional environmental assessments for route changes should they occur; however, at this juncture non are expected. | 60 | The mileage has been staked and routes are finalized. Our submitted AAR has been approved and we have re-engineered the route changes. Finley Engineering, our engineering firm, has a retainage clause in their contract so this line item will not be fully expended until project closeout. | 86 | We hired a third party to oversee the execution of the rights of way necessary to complete our project. To date we have 6 more easements to get in the Arlburg segment of the project and we expect to have those by the end of Q2 of 2014. | 82 | The majority of our permits have been submitted, and make ready payments on the majority have been paid. We are monitoring make ready deadlines, and are aggressively addressing any problems or road blocks. We have brought on another firm to help us navigate through the utility company rules and regulations as they relate to permitting. At the end of Q1 2014 we will have all pole applications completed/submitted and by the end of Q2 2014 all make ready checks will be cut which will leave us the beginning of Q3 2014 to complete construction. | 73 | We continue to deploy our electronics. This methodical approach to deployment was not originally in our baseline, but progress is being made. | 81 | Our contract with the equipment manufacturer contains a retainer clause. Until the deployment is fully completed and tested, final payments will not be made. | 79 | Network construction is progressing. We are behind our baseline projections, but are pushing all involved hard to reach completion. | 81 | The costs associated with the deployment of our DWDM equipment is bundled with the procurement costs above. We have no break out from the vendor. | 85 | Equipment to test the network was purchased. If additional items are required we have enough money in the budget to cover costs as the remainder of the network is built. | 2014-08-29 15:57 | 2014-08-29 15:57 | 7797 | 7797 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570086 | 2010 | Q4 | Q4 - 2010 | 579 | 1597 | TRUE | 2 | No variance | 0 |  | N/A | 75 | No variance | 25 | No variance | 0 | Applications are being prepared, but had not been submitted by the end of the quarter. We anticipate being back on schedule by the end of next quarter. | 0 | Applications are being prepared, but had not been submitted by the end of the quarter. We anticipate being back on schedule by the end of next quarter. | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-01-27 09:56 | 2011-01-27 09:56 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2011 | Q1 | Q1 - 2011 | 2057 | 2774 | TRUE | 2 | Slightly delayed due to reasons listed below. | 0 |  | N/A | 90 | Slight delay due to additional detail requested by tribes. Expect to be on schedule by next quarter. | 60 | Delays are due to developing route change modifications and reviewing overlaps with other federally funded projects. | 60 | Delays are due to developing route change modifications and reviewing overlaps with other federally funded projects. | 50 | Delays are due to developing route change modifications and reviewing overlaps with other federally funded projects. | 0 | No variance | 0 | We were not able to order equipment since the EA is delayed and we do not yet have a FONSI. | 0 | No variance | 0 | No variance | 0 | No variance | 2011-05-16 17:16 | 2011-05-16 17:16 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2011 | Q2 | Q2 - 2011 | 2997 | 3256 | TRUE | 4 | We continue to be delayed due to reasons listed below. In addition, The receipt of our FONSI was one quarter later than anticipated. There were route modifications required as a result of findings in the EA process. Re-design and re-permit work of the modifications was required. We were able to begin building at the beginning of Q3, which is in line with our baseline project plan. | 0 |  | N/A | 100 | No variance | 75 | We started this quarter slightly behind due to route modifications and program overlap work. We have also experienced delays due to MN DOT and government offices preparing for State government shutdown. | 75 | We started this quarter slightly behind due to route modifications and program overlap work. We have also experienced delays due to government offices preparing for State government shutdown. | 75 | We started this quarter slightly behind due to route modifications and program overlap work. We have also experienced delays due to government offices preparing for State government shutdown. | 0 | No variance | 0 | This line only references CO and electronics equipment. We did not order this equipment yet. This line will continue to show a variance from baseline because other materials were included in that report. | 1 | Materials and invoice starting arriving early July, right after quarter end. We have now started construction, but this may continue to lag due to a delay due to a late start on construction and a potential delay in state permits. | 0 | We do not have any equipment yet. This milestone may continue to lag due to difficulty with getting CAI contracts signed. | 0 | No variance | 2011-08-10 16:34 | 2011-08-10 16:34 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2011 | Q3 | Q3 - 2011 | 4111 | 3899 | TRUE | 24 | Due to delays in beginning construction and lack of signed CAIs, we remain slightly behind our baseline. We continue to work diligently to catch up to the baseline. | 0 |  | N/A | 100 | No variance | 95 | Last quarter was started slightly behind and expected to be at this percentage of completion by now. We were able to achieve that goal. | 90 | Last quarter was slightly behind and we were able achieve our goal of 90% completion by this quarter. This is just slightly behind our baseline. | 75 | We remain behind on this milestone due to permit difficulties which consumed resources. Delays and infrequent meetings for some locations have delayed the permits. In addition one city required us to permit under 2 governing bodies. The city of St. Paul required us to segment our build into 3 distinct projects which were reviewed separately. Each of those permits required attendance at the utility board meetings and were denied during the first round. This exercise took 1 person 10 weeks, which was not planned in our timeline. Since the end of the reporting period, all required permits have been received for this segment. | 30 | We remain slightly behind on this milestone. Based on previous delays, we anticipated a 30% completion by this quarter and were able to achieve that. | 0 | This line only references CO and electronics equipment. We ordered equipment but will not receive it until next reporting quarter. This line will continue to show a variance from baseline because other materials were included in that report. | 27 | We were able to exceed our expected build goal. | 0 | We do not have any equipment deployed yet. This milestone will continue to lag due to difficulty with getting CAI contracts signed. | 0 | No variance | 2011-11-17 14:44 | 2011-11-17 14:44 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2011 | Q4 | Q4 - 2011 | 4993 | 4667 | TRUE | 53 | We are slightly ahead of our baseline. This will not change our anticipated completion date of July 31, 2013. | 0 |  | N/A | 100 | N/A | 95 | We have been working through an EA addendum. We will be able to complete the design once the addendum has been approved. We expect this to be complete by the next reporting quarter. | 90 | We need to wait for approval of the EA addendum before finalizing the remaining Rights of Way. We expect this to be complete by the next reporting quarter. | 75 | We cannot apply for the permits until the EA addendum is approved. We expect to apply for permits shortly after the EA addendum approval. | 50 | There is no variance from the baseline. | 20 | This line only references CO and electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. We have started ordering and receiving equipment but due to difficulty in securing CAI's, the amount of equipment ordered is less than originally anticipated for this quarter. We are on schedule for procurement of equipment for middle mile routes. Once CAI's are confirmed we will be working on a schedule for CAI equipment purchases. | 37 | This is slightly ahead of baseline. | 15 | This milestone continues to lag due to difficulty with getting CAI contracts signed. We are on schedule for deployment of equipment in the middle mile routes. Once the CAI's are confirme we will be wroking on a schedule for CAI deployments. We do not anticipate this will hinder our ability to be 2/3 complete by the end of year 2. | 5 | This is slightly ahead of the baseline since we were able to test equipment that had been installed. | 2012-02-14 11:18 | 2012-02-14 11:18 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2012 | Q1 | Q1 - 2012 | 6023 | 5611 | TRUE | 55 | We are just slightly behind our baseline but are working to catch up. This will not affect our completion date of July 31, 2013. | 0 |  | N/A | 100 | No variance | 100 | No variance | 95 | We are just slightly behind our baseline but where we expected to be as of our last report. We have received approval on our EA addendum and are working to finish this. | 90 | We are slightly behind our baseline but ahead of where we expected to be as or our last report. We have received approval on our EA addendum and are working to finalize these. | 50 | No variance | 20 | This line only references CO and the electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. We have started ordering and receiving equipment but due to difficulty in securing CAI's, the amount of equipment ordered is less than anticipated. | 41 | No variance (slightly ahead of baseline) | 15 | This milestone continues to lag due to difficulty with getting CAI contracts signed. We are on schedule for deployment of equipment in the middle mile routes. Once the CAI's are confirmed, we will be working on a schedule for CAI deployments. We do not anticipate this will hinder our ability to be 2/3 complete by the end of year 2. | 5 | This is slightly ahead of baseline. | 2012-05-10 15:40 | 2012-05-10 15:40 | 6162 | 6162 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2012 | Q2 | Q2 - 2012 | 7009 | 6132 | TRUE | 60 | This number is slightly behind baseline. We continue working to catch up to baseline and do not expect this to delay completion. | 0 |  | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 95 | We are slightly behind baseline and do not expect this to delay completion. | 50 | We are slightly behind baseline but are where we expected to be following our last quarter report. We continue working to catch up to baseline. | 31 | This line only references CO and the electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. They are actually part of the construction portion of the budget. We have started ordering, receiving and installing equipment but due to difficulty in securing CAIs, the amount of equipment ordered is less than originally anticipated. In addition, the needs of potential CAIs have changed resulting in less equipment. | 52 | We are slightly behind baseline but have ramped up construction and will be adding additional crews to catch up. | 15 | This milestone continues to lag due to difficulty in securing CAI contracts. We continue working to catch up. | 20 | This is ahead of our baseline, and where we expected to be following our last quarter report. | 2012-08-10 14:11 | 2012-08-10 14:11 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2012 | Q3 | Q3 - 2012 | 8113 | 6764 | TRUE | 76 | This is slightly behind baseline but where we expected to be following our last quarter report. We do not expect this to delay completion. | 0 |  | N/A | 100 | No variance | 64 | This is slightly behind baseline and different from previous reports due to a change in how this is calculated. This is now based solely on expenditure. Work continues and we expect no delay in completion. | 64 | This is slightly behind baseline and different from previous reports due to a change in how this is calculated. This is now based solely on expenditure. Work continues and we expect no delay in completion. | 64 | This is slightly behind baseline and different from previous reports due to a change in how this is calculated. This is now based solely on expenditure. Work continues and we expect no delay in completion. | 90 | This is slightly behind baseline but ahead of where we expected to be following our last quarter report. This will not delay completion. | 48 | This line only references central office and electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. In addition, the needs of potential CAIs have changed resulting in the need for less equipment. | 83 | This is slightly ahead of baseline. | 14 | This is behind baseline and different from previous reports due to a change in how this is calculated. This is now based solely on expenditure. This milestone will continue to lag, associated with the delay in securing CAI contracts. We continue to focus on this. | 44 | This is slightly behind baseline but ahead of where we expected to be following our last quarter report. We do not expect this to delay completion. | 2012-11-28 14:54 | 2012-11-28 14:54 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2012 | Q4 | Q4 - 2012 | 8783 | 7582 | TRUE | 83 | This is slightly behind baseline but where we expected to be following our last quarter report. We do not expect this to delay completion. | 0 |  | N/A | 100 | No variance | 65 | This is slightly behind baseline and different from previous reports due to a change in how this is calculated. This is now based solely on expenditure. Work continues and we expect no delay in completion. | 94 | This is just a few percentage points behind baseline and different from previous reports due to a change in how this is calculated. This is now based solely on expenditure. Work continues and we expect no delay in completion. | 94 | This is slightly behind baseline. Work continues and we expect no delay in completion. | 80 | This is slightly behind baseline and different from our previous report due to reclassifying some costs once the actuals were scrubbed. This will not delay completion. | 50 | This is behind baseline but ahead of where we expected to be from our last report. This will not delay completion. | 89 | This is one percentage point behind baseline. This will not delay completion. | 15 | This is behind baseline and different from previous reports due to a change in how this is calculated. This is now based solely on expenditure. This milestone will continue to lag, associated with the delay in securing CAI contracts. We continue to focus on this. | 90 | This is slightly ahead of baseline. | 2013-02-14 17:10 | 2013-02-14 17:10 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2013 | Q1 | Q1 - 2013 | 10015 | 8554 | TRUE | 84 | This is slightly below baseline, but where we expected to be. We do not expect this to delay completion. | 0 |  | N/A | 100 | No variance | 70 | This is below baseline but ahead of where we expected to be. Work continues and we expect no delay in completion. | 99 | This is just slightly behind baseline | 99 | This is just slightly behind baseline | 80 | This is just slightly behind baseline. We do not expect this to delay completion. | 54 | This is below baseline but do not expect this to delay completion. | 89 | This is just slightly behind baseline. | 28 | This is behind baseline. This milestone will continue to lag, associated with the delay in securing CAI contracts. We continue to focus on this. | 90 | This is slightly ahead of baseline. | 2013-05-30 16:55 | 2013-05-30 16:55 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2013 | Q2 | Q2 - 2013 | 10363 | 8808 | TRUE | 86 | We are slightly behind baseline, but have a month remaining in our project. This number will vary since we don't expect to spend all of the allotted budget due to cost savings. | 0 |  | N/A | 100 | No variance | 73 | We are slightly behind baseline, but have a month remaining in our project. This number will vary since we don't expect to spend all of the allotted budget due to cost savings. | 100 | We are reporting 100% for this milestone. Our spending for this category is higher than baseline but will not cause us to go over our total budget. | 100 | We are reporting 100% for this milestone. Our spending for this category is higher than baseline but will not cause us to go over our total budget. | 80 | We are slightly behind baseline, but have a month remaining in our project. This number will vary since we don't expect to spend all of the allotted budget due to cost savings. | 71 | We are behind baseline, but have a month remaining in our project. This number will vary since we don't expect to spend all of the allotted budget due to a decrease in the number of CAI's with signed contracts and cost savings. | 90 | We are slightly behind baseline, but have a month remaining in our project. This number will vary since we don't expect to spend all of the allotted budget due to cost savings. | 29 | We are behind baseline, but have a month remaining in our project. This number will vary since we don't expect to spend all of the allotted budget due to a decrease in the number of CAI's with signed contracts and cost savings. | 90 | We are slightly behind baseline, but have a month remaining in our project. This number will vary since we don't expect to spend all of the allotted budget due to cost savings. | 2013-07-30 15:27 | 2013-07-30 15:27 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2013 | Q3 | Q3 - 2013 | 11681 | 9803 | TRUE | 100 | All tasks are complete. Our spending is less than100% of the budget due to cost savings. | 0 |  | No variance | 100 | No variance | 100 | All tasks are 100% for this milestone. Our spending for this category is lower than baseline due to cost savings | 100 | We are reporting 100% for this milestone. Our spending for this category is higher than baseline but will not cause us to go over our total budget. | 100 | We are reporting 100% for this milestone. Our spending for this category is higher than baseline but will not cause us to go over our total budget. | 100 | All tasks are 100% for this milestone. Our spending for this category is lower than baseline due to cost savings | 100 | All tasks are 100% for this milestone. Our spending for this category is lower than baseline due to cost savings and a reduced number of CAI contracts | 100 | All tasks are 100% for this milestone. Our spending for this category is lower than baseline due to cost savings | 100 | All tasks are 100% for this milestone. Our spending for this category is lower than baseline due to cost savings and a reduced number of CAI contracts | 100 | All tasks are 100% for this milestone. Our spending for this category is lower than baseline due to cost savings | 2014-01-28 10:17 | 2014-01-28 10:17 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570087 | 2010 | Q4 | Q4 - 2010 | 1131 | 2169 | TRUE | 1 | Re-bid of engineering RFP delayed Engineering & permitting work. Rebid because of three (3) bridge attachments design requirements. | 0 |  | N/A | 50 | Draft EA submitted 12-31-10 | 25 | Preliminary Engineering completed 12-10. Design to be complete by Y1Q3. | 10 | Preliminary contract made with VDOT. Bridge design requirements necessitated re-bidding the design work; thereby, delaying Right of Way acquisition progress. | 10 | Preliminary contract made with VAMRC, CORP of Engineers. Bridge design requirements necessitated re-bidding the design work; thereby, delaying Right of Way acquisition progress. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-14 11:50 | 2011-02-14 11:50 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2011 | Q1 | Q1 - 2011 | 2095 | 2793 | TRUE | 1 | Re-design required in Smithfield, and Chesapeake, VA. | 0 |  | N/A | 60 | SHPO and Final Draft to be submitted Y2Q1(July -Sept 2011) | 70 | Design changes will cause delay. | 50 | Land use permits submitted by 6-15-11. | 40 | Permits to be submitted by 5-15-11. Negotiations with 2 utilities on joint use agreements and Town of Franklin, VA. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-05-17 15:11 | 2011-05-17 15:11 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2011 | Q2 | Q2 - 2011 | 2939 | 3227 | TRUE | 5 | Design changes delayed completion of EA which delayed the construction RFP being issued. Construction to begin in Y2Q1. | 0 |  | N/A | 90 | Awaiting SHPO consultation to be submitted for review. | 100 | N/A | 100 | N/A | 80 | Joint use utility agreements with 2 cities underway | 0 | Site prep will begin after EA is approved. | 7 | Received some network equipment ahead of schedule. | 0 | No construction can start until approval of EA. | 0 | N/A | 0 | N/A | 2011-08-05 16:56 | 2011-08-05 16:56 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2011 | Q3 | Q3 - 2011 | 4001 | 3840 | TRUE | 8 | Expected construction start date 12/2011. Awaiting EA approval. | 0 |  | N/A | 90 | Awaiting SHPO report approval. Expected 11/2011. Submission and approval of EA expected 11/2011. | 100 | Complete | 100 | Complete | 90 | Awaiting completion of conduit leases. | 0 | Awaiting approval of EA. Expected start in 12/2011. | 19 | Receipt and billing for materials ahead of schedule. | 0 | Construction start date delayed until 12/2011. | 0 | N/A | 0 | N/A | 2011-11-14 08:21 | 2011-11-14 08:21 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2011 | Q4 | Q4 - 2011 | 5409 | 5091 | TRUE | 42 | Expenditures for equipment, huts and fiber cable have been purchased. Expected construction start date January 2012. | 0 |  | N/A | 95 | SHPO approved 11-18-11. Final draft EA was submitted 12-9-11. Expected NTIA approval January 2012. | 100 | Complete | 100 | Complete | 90 | Awaiting completion of conduit leases. | 0 | RFP for site work issued in December 2011. Work to start Y2Q3 | 99 | Received all transport equipment & 97% cable. | 0 | EA approval expected January 2012. Network build to begin January 2012. | 0 | Equipment deployment delayed due to EA approval. | 0 | Network testing cannot start until equipment & cable can be placed | 2012-02-29 15:09 | 2012-02-29 15:09 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2012 | Q1 | Q1 - 2012 | 5963 | 5581 | TRUE | 46 | Construction started March 8, 2012. Start date delayed due to EA approval and VDOT permit approval. Majority of expenditures have been material and equipment. | 0 |  | N/A | 100 | EA and FONSI issued January 6, 2012 | 100 | Complete | 100 | Complete | 90 | Leases and permits for bridges still pending | 5 | Site work began on Franklin hut site | 100 | Complete | 9 | Placed 16 miles of cable in March 2012 | 0 | Equipment deployment delayed due to EA approval | 0 | Network testing cannot start until equipment and cable can be placed | 2012-05-08 14:23 | 2012-05-08 14:23 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2012 | Q2 | Q2 - 2012 | 7219 | 6237 | TRUE | 54 | Start date delayed until 3/8/12 due to EA approval. Majority expenditures have been for construction and material. Good weather has allowed us to make good progress in placing cable. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 40 | Completed one site; one in progress. All to be completed by end of the third quarter. | 100 | Complete | 48 | Completed 81 miles total | 0 | Equipment deployment delayed due to EA approval delay | 0 | Network testing cannot start until equipment and cable are placed | 2012-08-23 10:39 | 2012-08-23 10:39 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2012 | Q3 | Q3 - 2012 | 7749 | 6569 | TRUE | 64 | Start date was delayed until 3-8-12 due to the EA approval. Wet weather has slowed plowing progress in some areas. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 75 | Completed 2 sites; one 50% complete & one in progress; Complete by Y3Q4 (Y3Q2) | 100 | Complete | 77 | Completed 49 miles in Y3Q3 (Y3Q1) | 0 | Deployment delayed until completion of all huts(nodes) | 0 | Network testing cannot start until equipment and cable is placed | 2012-11-01 13:31 | 2012-11-01 13:31 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2012 | Q4 | Q4 - 2012 | 8997 | 7776 | TRUE | 68 | Start date was delayed until 3-8-12 due to EA approval. Awaiting approval of franchise agreements from Chesapeake and Surry | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 75 | Completed 3 of 4 sites. Easement has been delayed | 100 | Complete | 84 | Placed 13 miles this quarter Y3Q4 (Y3Q2) | 10 | Equipment deployed cannot be completed until all nodes are placed | 10 | Network testing cannot be completed until all equipment is installed | 2013-02-27 10:33 | 2013-02-27 10:33 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2013 | Q1 | Q1 - 2013 | 9673 | 8369 | TRUE | 72 | Awaiting approval of Suffolk Franchise Agreement to resume construction. Expected approval 4-17-13 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 75 | Completed 3 or 4 sites. 4th site work to begin 4-15-13 | 100 | Complete | 85 | Awaiting completion of huts and approval of Suffolk Franchise Agreement before resuming construction | 30 | Awaiting completion of huts | 40 | Awaiting completion of huts and cable placement | 2013-05-10 08:38 | 2013-05-10 08:38 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2013 | Q2 | Q2 - 2013 | 10601 | 8958 | TRUE | 76 | No-cost extension request until 8/31/13 applied for on 7/23/13 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 95 | Awaiting cable construction completion | 90 | Awaiting cable construction completion | 90 | Awaiting cable construction completion | 2013-08-15 11:17 | 2013-08-15 11:17 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2013 | Q3 | Q3 - 2013 | 12325 | 10499 | TRUE | 100 | Complete: 86% of Grant Funds Spent | 0 |  | N/A | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 2014-07-25 16:21 | 2014-07-25 16:21 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570088 | 2010 | Q4 | Q4 - 2010 | 519 | 1541 | TRUE | 1 | .5% of project is actually complete but entry only allows whole numbers. .5% is consistent with baseline. | 14 | Admin,Legal, Arch & Engineering Fees | Cash & In-Kind Match (Staff & Travel Expenses) | 90 | An EA draft was completed on time by consulting firm and is under review by Charlotte. Charlotte plans to submit EA Draft to NTIA on time per requirement, however possible changes to Charlotte's network design approach may change the final EA study required. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-01-25 08:46 | 2011-01-25 08:46 | 6166 | 6166 | Charlotte, City of | TRUE
NT10BIX5570088 | 2011 | Q1 | Q1 - 2011 | 1891 | 2691 | TRUE | 1 | Consistent with Baseline. | 24 | Admin,Legal, Arch & Engineering Fees | Off by 1% due to re-structuring of Project. (In-Kind Staff +Travel) | 90 | Will leave at 90% since an E/A draft was submitted based on original plan. Will change once a solution is chosen and construction plans identified outside the original plans. | 0 | No variance | 1 | Up 1% - EA Draft + unplanned Contractor for Declaratory Judgement | 0 | No variance | 0 | N/A | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-05-05 09:59 | 2011-05-05 09:59 | 6166 | 6166 | Charlotte, City of | TRUE
NT10BIX5570088 | 2011 | Q2 | Q2 - 2011 | 2929 | 3222 | TRUE | 1 | Not 6% because Charlotte took a step back and reissued a new RFP. | 57 | Admin,Legal,Arch & Engr. Fees | Not 33%. due to additional staff time to re-issue a new RFP. | 90 | Not 100%. Set at 90% since an E/A draft was submitted based on original plans that most likely will change once a solution is chosen and final design/construction plans identified. | 0 | No Variance | 1 | Not 0% because started payments for Technical Consultant to assist in RFP & Planning efforts not originally planned. | 0 | No Variance | 0 | N/A | 0 | Not 5% because Charlotte took a step back and reissued a new RFP. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-08-04 17:40 | 2011-08-04 17:40 | 6166 | 6166 | Charlotte, City of | TRUE
NT10BIX5570088 | 2011 | Q3 | Q3 - 2011 | 3477 | 3505 | TRUE | 1 | Not 20%. Just hire implementation vendor at end of this quarter. Charlotte is about 4 months behind baseline milestones. | 84 | a. Admin. & Legal, d. Arch & Engr. | Not 41%. Due to additional staff effort needed to re-issue 2nd RFP, evaluation & negotiations processes for a BTOP vendor. Includes Contracted Legal Council | 90 | Not 100%. At 90% because EA was submitted on original design. New design will require additional effort to complete. | 0 | Not 100%. Design is expected to be completed by end of next quarter | 1 | Not 0%. Hired Technical Consultant to assist project which was not part of original plan. | 0 | No Variance | 0 | N/A | 0 | Not 5%. Delayed by reissuance of 2nd BTOP RFP | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-10-26 14:14 | 2011-10-26 14:14 | 6166 | 6166 | Charlotte, City of | TRUE
NT10BIX5570088 | 2011 | Q4 | Q4 - 2011 | 4857 | 4555 | TRUE | 3 | Not 21%. First quarter working with selected vendor. Made large strides that are not reflected in this percentage mainly due to missing end date to pay invoices. See above note. | 20 | a. Admin. & Legal, d. Arch & Engr. | Not 50%. Mainly due to re-budgeting. Will see improvement in Q1 2012 | 95 | Not 100% Obtained Categorical Exclusion. Plan to complete in 1st quarter 2012. | 50 | Not 100%. High level Design was delivered in December. Plans to complete Design in 1st quarter 2012. | 15 | No Variance | 0 | No Variance | 0 | N/A | 0 | Not 5%. Phase 1 Equipment planned for 1st Quarter 2012 | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2012-02-01 13:31 | 2012-02-01 13:31 | 6166 | 6166 | Charlotte, City of | TRUE
NT10BIX5570088 | 2012 | Q1 | Q1 - 2012 | 5597 | 5396 | TRUE | 20 | Not 59%. Making much progress but due to re-budgeting and payment milestone plans we are not yet at original baseline projections. | 78 | a.Admin & Legal | Not 58%. More staff and time needed than realized with multi RFPs and Design | 95 | Not 100%. Changes to 4 Site Locations were recently made to finalize the Design. Plan to complete next quarter. | 100 | No Variance | 32 | Began signing tower leases and reviewing Tower mappings | 4 | Not 100%. Began submitting permits in April and Reviewing Towers needing Structural Modifications | 0 | No Variance. | 13 | Not 100%. Due to new budget and project approach. Phase 1 procurement will show next qtr. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2012-04-27 09:54 | 2012-04-27 09:54 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2012 | Q2 | Q2 - 2012 | 6921 | 6088 | TRUE | 21 | Not 66%. Project under suspension. | 92 |  | Not 66%. More staff and time was used when re-issue RFP and Project was redefined. | 95 | Not 100%. Project under suspension. | 100 | No Variance | 32 | Not 43%. Stopped signing leases due to suspension. | 4 | Not 100%. Suspended all project activities. | 0 | No Variance | 13 | Not 100% Suspended all project activities. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2012-08-08 09:33 | 2012-08-08 09:33 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2012 | Q3 | Q3 - 2012 | 7755 | 6572 | TRUE | 22 | Project Suspension | 99 | a. Admin. & Legal, d. Arch & Engr. | More staff required when re-issue RFP and Project was redefined. | 95 | Project Suspension | 100 | No Variance | 32 | Project Suspension | 4 | Project Suspension | 0 | No Variance | 13 | Project Suspension | 0 | Project Suspension | 0 | Project Suspension | 0 | No Variance | 2012-11-01 14:50 | 2012-11-01 14:50 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2012 | Q4 | Q4 - 2012 | 8651 | 7472 | TRUE | 22 | Project under suspension | 100 | a. Admin & Legal | More staff time on re-issued RFP and redefining Project. | 95 | Project under suspension | 100 | No Variance | 43 | Active tower leases signed before suspension | 4 | Project under suspension | 0 | No Variance | 13 | Project under suspension | 0 | Project under suspension | 0 | Project under suspension | 0 | Project under suspension | 2013-02-04 11:27 | 2013-02-04 11:27 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2013 | Q1 | Q1 - 2013 | 9677 | 8371 | TRUE | 24 | Project under suspension | 100 | a. Admin & Legal | More staff time required when original RFP was revised & reissued. | 95 | Project under suspension | 100 | No Variance | 57 | Active tower leases signed before suspension | 4 | Project under suspension | 0 | No Variance | 13 | Project under suspension | 0 | Project under suspension | 0 | Project under suspension | 0 | Project under suspension | 2013-05-10 10:37 | 2013-05-10 10:37 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2013 | Q2 | Q2 - 2013 | 10121 | 8624 | TRUE | 25 | Project is under suspension | 100 | a: Admin & Legal | extra staff time occurred when RFP process was repeated. | 95 | Project is under suspension | 100 | No variance | 59 | Active tower leases signed before suspension | 4 | Project is under suspension | 0 | No variance | 13 | Project is under suspension | 0 | Project is under suspension | 0 | Project is under suspension | 0 | Project is under suspension | 2013-07-23 11:37 | 2013-07-23 11:37 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2013 | Q3 | Q3 - 2013 | 10973 | 9203 | TRUE | 26 | Project is under suspension | 100 | a: Admin & Legal | Extra staff time when repeated RFP process | 95 | Project is under suspension | 100 | No variance | 59 | Obligated Tower Leases prior to suspension | 4 | Project is under suspension | 0 | No variance | 13 | Project is under suspension | 0 | Project is under suspension | 0 | Project is under suspension | 0 | Project is under suspension | 2013-10-28 16:06 | 2013-10-28 16:06 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2013 | Q4 | Q4 - 2013 | 11849 | 10022 | TRUE | 25 | Project was under suspension most of this period. See 2d. note below. | 100 | a:Admin & Legal | accrued as a result of repeated RFP process and project suspension | 95 | Project was under suspension most of this period. | 100 | No variance | 49 | Dropped because Tower Lease payments were refunded as per contract when lease agreements under LTE deployment were terminated. | 4 | Project was mostly under suspension this period. | 0 | No variance | 13 | Project was under suspension most of this period. | 0 | Project was under suspension most of this period. | 0 | Project was under suspension most of this period. | 0 | Project was under suspension most of this period. | 2014-02-20 09:06 | 2014-02-20 09:06 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570089 | 2010 | Q4 | Q4 - 2010 | 1087 | 2128 | TRUE | 1 | N/A | 6 |  | N/A | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | N/A | 0 | N/A | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-11 15:38 | 2011-02-11 15:38 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2011 | Q1 | Q1 - 2011 | 2079 | 2785 | TRUE | 1 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 10 |  | The indicated variance is due to the deferment of staffing program management and other project positions until the sites are finalized and nearer to their scheduled implementation, and other deferred related staffing expenses such as relocation, travel and other costs. | 12 | Motorola Solutions made significant progress in environmental assessments by performing 271 TCNS tribal notifications and performing Section 106 exemption determinations. Although these notifications and determinations were performed the indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 8 | Motorola Solutions made significant progress in network design by performing 200 site walks. Although these site walks were performed the indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | N/A | 0 | N/A | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. As a result of these delays, SAC #12 has not been completed. SAC #12 has been extended to 6/30/11. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-05-17 10:38 | 2011-05-17 10:38 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2011 | Q2 | Q2 - 2011 | 2983 | 3249 | TRUE | 2 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 13 |  | The indicated variance is due to the deferment of staffing program management and other project positions until the sites are finalized and nearer to their scheduled implementation, and other deferred related staffing expenses such as relocation, travel and other costs. | 15 | Motorola Solutions made significant progress in environmental assessments by completing the tribal notifications and performing Section 106 exemption determinations. Although these notifications and determinations were performed, the indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 10 | Motorola Solutions made significant progress in network design by supporting meetings with the BayWEB agencies to secure new fiber resources to enhance the system backhaul capacity and developing additional engineering designs to support these enhancements. Although these meetings and design work were performed the indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | N/A | 0 | N/A | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and Motorola's decision to competitively bid the LTE core equipment. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and Motorola's decision to competitively bid the LTE core equipment. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and Motorola's decision to competitively bid the LTE core equipment. | 0 | No variance. | 2011-08-09 15:46 | 2011-08-09 16:12 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2011 | Q3 | Q3 - 2011 | 3631 | 3599 | TRUE | 2 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 14 |  | The indicated variance is due to the deferment of staffing program management and other project positions until the sites are finalized and nearer to their scheduled implementation, and other deferred related staffing expenses such as relocation, travel and other costs. | 26 | Although notifications and determinations were performed, the indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 29 | Motorola Solutions made significant progress in network design by supporting meetings with the BayWEB agencies to secure new fiber resources and resources to enhance the system backhaul capacity, and sites and developing additional engineering designs to support these enhancements. Motorola Solutions also conducted system design reviews with the Technical Advisory Committee. In addition, more PM and Engineering resources were added to move the design forward. Although these meetings and design work were performed the indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | N/A | 0 | N/A | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and Motorola's decision to competitively bid the LTE core equipment. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and Motorola's decision to competitively bid the LTE core equipment. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and Motorola's decision to competitively bid the LTE core equipment. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and Motorola's decision to competitively bid the LTE core equipment. | 2011-10-28 15:10 | 2011-10-28 15:10 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2011 | Q4 | Q4 - 2011 | 4859 | 4558 | TRUE | 3 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 18 | true | The indicated variance is due to the deferment of staffing program management and other project positions until the sites are finalized and the start of scheduled implementation, and other deferred related staffing expenses such as relocation, travel and other costs. | 28 | Although notifications and determinations were performed in regards to the National Historic Preservation Act, the indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 59 | Motorola Solutions made significant progress in network design by supporting meetings with the BayWEB agencies to secure new fiber resources and resources to enhance the system backhaul capacity, and sites and developing additional engineering designs to support these enhancements. Motorola Solutions also conducted system design reviews with the Technical Advisory Committee. In addition, more PM and Engineering resources were added to move the design forward. Although these meetings and design work were performed the indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of agency provided backhaul, sites and other program delays. | 0 | N/A | 0 | N/A | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 2012-02-02 14:20 | 2012-02-02 14:26 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2012 | Q1 | Q1 - 2012 | 5933 | 5566 | TRUE | 4 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 21 |  | The indicated variance is due to the deferment of staffing program management and other project positions until the start of scheduled implementation, and other deferred related staffing expenses such as relocation, travel and other costs. | 28 | Although notifications and determinations were performed in regards to the National Historic Preservation Act, the indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 88 | As a result of site owners committing their sites to the network via executed SAUs, Motorola Solutions has been able to solidify the current system configuration which allowed the creation of equipment lists for the LTE system. The equipment lists are currently in review by Motorola and the LTE vendor. The baseline of current sites may be enhanced in the future as some owners complete their efforts to commit additional sites. The indicated variance from the baseline plan for the previous quarter continues as a result of previous delays in the finalization and readiness of agency provided backhaul, sites and other program delays. | 0 | N/A | 0 | N/A | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 2012-05-07 08:53 | 2012-05-07 08:53 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2012 | Q2 | Q2 - 2012 | 6885 | 6069 | TRUE | 6 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 24 |  | The indicated vairance is due to the deferment of staffing program management and other project positions until the start of scheduled implementation, now also impacted by the partial suspension of the LTE equipment portion of the program. Other deferred related staffing expenses such as relocation, travel and other costs are also pending the ramp up of staffing. | 28 | Although notifications and determinations were performed in regards to the National Historic Preservation Act, the indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. Zoning efforts are well underway, but none have completed their entire process as of report time. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | 2012-08-07 13:01 | 2012-08-07 13:03 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2012 | Q3 | Q3 - 2012 | 7803 | 6605 | TRUE | 7 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. There have been additional delays introduced to the program due to the partial suspension imposed upon all BTOP grantees. | 29 | Other | The indicated variance is due to the deferment of staffing program management and other project positions until the start of scheduled implementation, now also impacted by the partial suspension of the LTE equipment portion of the program. Other deferred related staffing expenses such as relocation, travel and other costs are also pending the ramp up of staffing. | 28 | Although notifications and determinations were performed in regards to the National Historic Preservation Act, the indicated variance from the baseline plan for the previous quarter occurred while awaiting approval of our Route Modification Request. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. Zoning efforts are well underway, six sites have completed their entire process as of report time. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 2012-11-08 16:23 | 2012-11-08 16:23 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2012 | Q4 | Q4 - 2012 | 8503 | 7225 | TRUE | 9 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. There have been additional delays introduced to the program due to the partial suspension imposed upon all BTOP grantees. | 31 | Other | The indicated variance is due to the deferment of staffing program management and other project positions until the start of scheduled implementation, now also impacted by the partial suspension of the LTE equipment portion of the program. Other deferred related staffing expenses such as relocation, travel, and other costs are also pending the ramp up of staffing. | 28 | Although notifications and determinations were performed in regards to the National Historic Preservation Act, the indicated variance from the baseline plan for the previous quarter occurred while awaiting approval of our Route Modification Request. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. Zoning efforts are well underway, 19 sites have completed their entire process as of report time. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 2013-01-30 15:29 | 2013-01-30 15:29 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2013 | Q1 | Q1 - 2013 | 9679 | 8372 | TRUE | 9 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. There have been additional delays introduced to the program due to the partial suspension imposed upon all BTOP grantees. | 34 |  | The indicated variance is due to the deferment of staffing program management and other project positions until the start of scheduled implementation, now also impacted by the partial suspension of the LTE equipment portion of the program. Other deferred related staffing expenses such as relocation, travel and other costs are also pending the ramp up of staffing. | 28 | Although notifications and determinations were performed in regards to the National Historic Preservation Act, the indicated variance from the baseline plan for the previous quarter occurred while awaiting approval of our Route Modification Request. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | n/a | 0 | n/a | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. Zoning efforts are well underway, 19 sites have completed their entire process as of report time. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 2013-05-10 12:26 | 2013-05-10 12:26 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2013 | Q2 | Q2 - 2013 | 10165 | 8659 | TRUE | 10 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. There have been additional delays introduced to the program due to the partial suspension imposed upon all BTOP grantees. | 35 | Other | The indicated variance is due to the deferment of staffing program management and other project positions until the start of scheduled implementation, now also impacted by the partial suspension of the LTE equipment portion of the program. Other deferred related staffing expenses such as relocation, travel and other costs are also pending the ramp up of staffing. | 28 | Although notifications and determinations were performed in regards to the National Historic Preservation Act, the indicated variance from the baseline plan for the previous quarter occurred while awaiting approval of our Route Modification Request. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 2013-07-26 09:45 | 2013-07-26 09:45 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2013 | Q3 | Q3 - 2013 | 11205 | 9392 | TRUE | 10 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. There have been additional delays introduced to the program due to the partial suspension imposed upon on this BTOP project. | 37 | Other | The indicated variance is due to the deferment of staffing program management and other project positions until the start of scheduled implementation, now also impacted by the partial suspension of the LTE equipment portion of the program. Other deferred related staffing expenses such as relocation. There was decreased in actual reported funds under the Miscellaneous cost classification on Infrastructure Budget Details section of this PPR, due to a correction from previous quarters. There were miscellaneous labor charges and facility recorded, but have now been determined to be indirect cost of the project that are not recoverable. | 28 | Throughout the quarter significant work was performed with regard to National Environmental Protection Act and Historical Preservation Act. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 2013-11-07 14:58 | 2013-11-07 14:58 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2013 | Q4 | Q4 - 2013 | 12169 | 10354 | TRUE | 12 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the ultimate expiration of the Broadband Technology Opportunity Program Grant | 41 |  | The indicated variance is due to the deferment of staffing program management and other project positions until the start of scheduled implementation, now also impacted by the partial suspension of the LTE equipment portion of the program. | 55 | Throughout the quarter significant work was performed with regard to National Environmental Protection Act and Historical Preservation Act. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of the partial suspension placed on the program. All LTE-equipment related tasks have been suspended indefinitely. | 2014-05-07 11:23 | 2014-05-07 11:23 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570090 | 2010 | Q4 | Q4 - 2010 | 1271 | 2298 | TRUE | 5 | On Schedule | 0 |  | N/A | 80 | On Schedule | 20 | On Schedule | 10 | On Schedule | 10 | On Schedule | 0 | N/A | 0 | On Schedule | 0 | On Schedule | 0 | On Schedule | 0 | On Schedule | 2011-02-22 10:09 | 2011-02-22 10:09 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2011 | Q1 | Q1 - 2011 | 2277 | 2884 | TRUE | 2 | Behind schedule due to Environmental Assessment. | 0 |  | N/A | 90 | Behind schedule due to TCNS comments and process. | 50 | On Schedule | 30 | On Schedule | 30 | On Schedule | 0 | N/A | 15 | Behind schedule, not an issue at this point. | 0 | On Schedule | 0 | Behind schedule, not an issue at this point. | 0 | On Schedule | 2011-05-24 12:39 | 2011-05-24 12:39 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2011 | Q2 | Q2 - 2011 | 3361 | 3444 | TRUE | 2 | Behind schedule due to Environmental Assessment. See #3 below. | 0 |  | N/A | 100 | Complete | 60 | On Schedule | 60 | On Schedule | 60 | On Schedule | 0 | N/A | 10 | Behind schedule, not an issue at this point. See #3 below. | 10 | On Schedule | 0 | Behind schedule, not an issue at this point. See #3 below. | 0 | On Schedule | 2011-08-29 17:50 | 2011-08-29 17:50 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2011 | Q3 | Q3 - 2011 | 4177 | 3937 | TRUE | 4 | Behind schedule due to Environmental Assessment. See #3 below. | 0 | true | N/A | 100 | Complete | 50 | Behind schedule due to Environmental Assessment. See #3 below. | 60 | On schedule | 60 | On schedule | 0 | N/A | 15 | Behind schedule; not an issue at this point. See #3 below. | 12 | Behind schedule. See #3 below. | 0 | Behind schedule; not an issue at this point. See #3 below. | 0 | Behind schedule. See #3 below. | 2011-11-21 10:56 | 2011-11-21 10:56 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2011 | Q4 | Q4 - 2011 | 5041 | 4712 | TRUE | 21 | Behind schedule due to Environmental Assessment. See #3 below. | 0 |  | N/A | 100 | Complete. | 60 | Behind schedule due to Environmental Assessment. See #3 below. | 60 | On schedule. | 60 | On schedule. | 0 | N/A | 45 | Behind schedule; not an issue at this point. See #3 below. | 23 | Behind schedule. See #3 below. | 30 | Behind schedule; not an issue at this point. See #3 below. | 0 | Behind schedule. See #3 below. | 2012-02-15 15:25 | 2012-02-15 15:25 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2012 | Q1 | Q1 - 2012 | 6293 | 5749 | TRUE | 34 | On schedule. (As revised) In PIP | 0 |  | N/A | 100 | Complete. | 80 | On Schedule.(As revised) In PIP | 80 | On Schedule. | 80 | On Schedule. | 0 | N/A | 90 | On Schedule.(As revised) In PIP | 26 | On Schedule.(As revised) In PIP | 50 | 95% of equipment on order-waiting for delivery. | 2 | On Schedule.(As revised) In PIP | 2012-05-25 10:08 | 2012-05-25 10:08 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2012 | Q2 | Q2 - 2012 | 7205 | 6230 | TRUE | 56 | 6% behind on expenditures. Ahead of schedule on miles and sites. | 0 |  | N/A | 100 | Complete | 90 | On schedule. (As revised) In PIP | 90 | On Schedule. | 90 | On Schedule. | 0 | N/A | 95 | On schedule. (As revised) In PIP | 50 | On schedule. (As revised) In PIP | 95 | 95% of equipment installed. | 60 | On schedule. (As revised) In PIP | 2012-08-22 12:45 | 2012-08-22 12:45 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2012 | Q3 | Q3 - 2012 | 8081 | 6747 | TRUE | 73 | 9% behind on expenditures. Sub-recipient's request came after third quarter. | 0 |  | N/A | 100 | Complete | 95 | On schedule. (As revised) In PIP | 95 | On schedule. | 95 | On schedule. | 0 | N/A | 95 | On schedule. (As revised) In PIP | 65 | On schedule. (As revised) In PIP | 95 | 95% of equipment installed. | 62 | On schedule. (As revised) In PIP | 2012-11-27 16:23 | 2012-11-27 16:23 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2012 | Q4 | Q4 - 2012 | 9059 | 7835 | TRUE | 84 | 5% behind on expenditures. Sub-recipient's request came after third quarter. | 0 |  | N/A | 100 | Complete | 95 | On schedule. (As revised) In PIP | 95 | On schedule. | 95 | On schedule. | 0 | N/A | 95 | On schedule. (As revised) In PIP | 78 | On schedule. (As revised) In PIP | 95 | 95% of equipment installed. | 75 | On schedule. (As revised) In PIP | 2013-02-28 11:47 | 2013-02-28 11:47 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2013 | Q1 | Q1 - 2013 | 9703 | 8385 | TRUE | 88 | 4% behind on expenditures. | 0 |  | N/A | 100 | Complete | 97 | On schedule. (As revised) In PIP | 97 | On schedule. | 97 | On schedule. | 0 | N/A | 100 | On schedule. (As revised) In PIP | 80 | On schedule. (As revised) In PIP | 97 | 97% of equipment installed. | 80 | On schedule. (As revised) In PIP | 2013-05-13 15:55 | 2013-05-13 15:55 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2013 | Q2 | Q2 - 2013 | 10577 | 8945 | TRUE | 89 | 11% behind on expenditures due to weather delays this spring. | 0 |  | N/A | 100 | Complete | 99 | On Schedule. (as revised) in PIP | 100 | On schedule | 100 | On schedule | 0 | N/A | 100 | On Schedule. (as revised) in PIP | 85 | On Schedule. (as revised) in PIP | 97 | 97% of equipment installed | 85 | On Schedule. (as revised) in PIP | 2013-08-14 11:12 | 2013-08-14 11:12 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2013 | Q3 | Q3 - 2013 | 11935 | 10104 | TRUE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-03-07 16:32 | 2014-03-07 16:32 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570091 | 2010 | Q4 | Q4 - 2010 | 1153 | 2195 | TRUE | 1 | Delayed due to structure of delayed payments to engineering/environmental firms. Percentage of work completed towards project is around 16%, but actual expenditure are only 1% of the budget. | 0 |  | None | 75 | Delay caused mainly by proposed route changes relating to exclusive right-of-ways. Small delay due to various firms/agencies. Our environmental firm has been working diligently to contact all firms/agencies required for the environmental assessment. | 85 | Design is almost completed while waiting on final route changes | 75 | None | 0 | None | 0 | delayed due to route changes relating to exclusive right-of-ways | 0 | None | 0 | None | 0 | None | 0 | None | 2011-02-15 17:13 | 2011-02-15 17:13 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2011 | Q1 | Q1 - 2011 | 2223 | 2857 | TRUE | 3 | Delayed due to structure of delayed payments to engineering/environmental firms and the delay caused by proposing route changes during Q1-2011. Percentage of work completed towards project is around 30%, but actual expenditure are only 2.8% of the budget. | 0 |  | Delay caused mainly by proposed route changes relating to exclusive right-of-ways. Software support system RFP was planned to be posted next quarter. | 90 | Delay caused mainly by proposed route changes relating to exclusive right-of-ways. Small delay due to various firms/agencies. Our environmental firm has been working diligently to contact all firms/agencies required for the environmental assessment. | 95 | None | 95 | None | 0 | Delay caused mainly by proposed route changes relating to exclusive right-of-ways. | 0 | Delay caused mainly by proposed route changes relating to exclusive right-of-ways. | 0 | Delay caused mainly by proposed route changes relating to exclusive right-of-ways. | 0 | Delay caused mainly by proposed route changes relating to exclusive right-of-ways. | 0 | None | 0 | Delay caused mainly by proposed route changes relating to exclusive right-of-ways. | 2011-05-20 16:00 | 2011-05-20 16:00 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2011 | Q2 | Q2 - 2011 | 2969 | 3242 | TRUE | 7 | Delay caused by approved route changes during Q1-2011. The route changes caused a delay in engineering costs and environmental assessment costs during Q1 and Q2 of 2011, delaying construction expenses to start in Q3 2011. | 0 |  | Software support systems RFP was posted during the present quarter. The delay was caused by reviewing several software support systems and Bluebird Media being unable to decide on a system prior to closing Q2-2011. | 95 | Bluebird Media was issued a Finding of Non Significant Impact on the environment during Q2 2011, continued environmental monitoring during construction will be the remaining 5 percent to complete. | 98 | Delay caused by approved route changes during Q1-2011. | 95 | Delay caused by approved route changes during Q1-2011. The Rights of Way will be completed during Q3 2011 once one more agreement has been signed with a state agency. | 6 | Delay caused by approved route changes during Q1-2011. Construction permits were delayed due to the changing routes while construction is slated to start during Q3-2011. | 0 | Delay caused by approved route changes during Q1-2011. Construction permits were delayed due to the changing routes causing site preparation to not start until Q3-2011. | 4 | Delay caused by approved route changes during Q1-2011. Equipment expenses were delayed due to the changing routes. An Increase in equipment purchasing will start in Q3-2011. | 0 | Network build was delayed by approved route changes during Q1-2011. The route changes caused a delay in engineering and the environmental assessment, delaying network build to start in Q3 2011. | 0 | Delay caused by approved route changes during Q1-2011. Equipment expenses were delayed due to the changing routes and will be purchased starting in Q3-2011. | 0 | Network build was delayed by approved route changes during Q1-2011. The route changes caused a delay in engineering and the environmental assessment, delaying network build and testing to start in Q3 2011. | 2011-08-09 12:22 | 2011-08-09 12:22 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2011 | Q3 | Q3 - 2011 | 4249 | 3975 | TRUE | 11 | Delay caused by approved route changes during Q1-2011. The route changes caused a delay in engineering costs and environmental assessment costs during Q1 and Q2 of 2011, delaying construction expenses to start in Q3 2011. Two percent behind revised baseline caused by 45 day delay in obtaining construction permits during the first part of Q3 2011 delaying construction startup. | 0 | OSS Software | Software support systems RFP was posted during the past quarter. The delay was caused by reviewing several software support systems and Bluebird Media being unable to decide on a system prior to closing Q2-2011. During Q3-2011 Bluebird Media contracted with a software company to implement software systems during Q4-2011. The plan is to catch up to the revised baseline during Q1-2012 once billing for the OSS Software commences. | 95 | Bluebird Media was issued a Finding of Non Significant Impact on the environment during Q2 2011, continued environmental monitoring during construction will be the remaining 5 percent to complete. Agrees to revised baseline. | 98 | Delay caused by approved route changes during Q1-2011. Two percent behind revised baseline due to delay in revised detailed route drawings provided by an engineering firm. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 41 | Ahead of Baseline schedule caused by obtaining a large amount of permits in August. 14 percent behind revised baseline. The plan is to catch up during Q4 2011. During the first month of Q4 2011, 52 permits were currently waiting to be approved which would catch us up to our revised baseline upon permit approvals. | 33 | Delay caused by approved route changes during Q1-2011. On schedule with revised baseline as all site layout have been completed. | 15 | Delay caused by the under estimated amount of time needed to negotiate final equipment contracts. One of two of these contracts were finalized during Q3 2011 and purchase orders have been put in place to procure equipment in Q4 2011. The plan is to catch up to the revised baseline during Q1-2012 once another contract is finalized during Q4-2011 and equipment is shipped during Q1-2012. | 7 | Delay caused by approved route changes during Q1-2011. The route changes caused a delay in engineering and environmental assessment during Q1 and Q2 of 2011, delaying construction to start in Q3 2011. One percent behind revised baseline caused by 45 day delay in obtaining construction permits during the first part of Q3 2011 delaying construction startup. The plan is to catch up to the revised baseline during Q4 2011. The construction permits will all be available during Q4 2011 allowing the construction of the network build to continuously carry on without delays. | 10 | No variance from baseline plan or subsequent written updates provided to the program officer. | 0 | No variance from baseline plan or subsequent written updates provided to the program officer. | 2011-11-23 12:39 | 2011-11-23 12:39 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2011 | Q4 | Q4 - 2011 | 5003 | 4677 | TRUE | 24 | One percent ahead of revised baseline due to the large amount of construction being completed and the large amount of equipment being purchased during the quarter. | 0 | OSS Software | Software support systems RFP was posted during the Q2-2011 quarter. The delay was caused by reviewing several software support systems and Bluebird Media being unable to decide on a system prior to closing Q2-2011. During Q3-2011 Bluebird Media contracted with a software company to implement software systems during Q4-2011. The plan is to catch up to the revised baseline during Q1-2012 once billing for the OSS Software commences. | 95 | Bluebird Media was issued a Finding of Non Significant Impact on the environment during Q2 2011, continued environmental monitoring during construction will be the remaining 5 percent to complete. Agrees to revised baseline. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 66 | Behind revised baseline schedule by 44 percent. The 66 percent of required permits included highway right-of-way permits, railroad crossing permits, and environmental permits. Virtually all permits that had been submitted had received approval. The remaining permits that have yet to be submitted are associated with portions of construction targeted late in the project plan. The plan is to catch up to the revised baseline during Q2-2012 once all permits have been submitted prior to the final construction being completed. | 50 | Behind revised baseline schedule by 5 percent. Focus during the quarter was on obtaining permits and performing due diligence work regarding shelter sites. The completion of these activities are required before physical preparation of the sites can be performed. The plan is to catch up to the revised baseline during Q1-2012 once several shelter sites are prepared for construction. | 41 | Behind revised baseline schedule by 43 percent. Delay caused by the under estimated amount of time needed to negotiate final equipment contracts. One of two of the large contracts were finalized during Q3 2011 and purchase orders have been put in place to procure equipment in Q4 2011. The other large contract was finalized during Q4 2011 with purchase orders being put in place to procure equipment in Q1 2012.The plan is to catch up to the revised baseline during Q2-2012 once equipment is shipped and billed during Q1-2012. | 23 | Behind revised baseline schedule by 5 percent. Delay caused by approved route changes during Q1-2011. The route changes caused a delay in engineering and environmental assessment during Q1 and Q2 of 2011, delaying construction to start in Q3 2011. Seven percent behind revised baseline caused by 45 day delay in obtaining construction permits during the first part of Q3 2011 delaying construction startup. The plan is to catch up to the revised baseline during Q1 2012. The construction permits will all be available during Q4 2011 allowing the construction of the network build to continuously carry on without delays. | 20 | No variance from baseline plan or subsequent written updates provided to the program officer. | 0 | Delay caused by approved route changes during Q1-2011, delaying construction to start in Q3 2011. Ten percent behind revised baseline with plans to complete network segments and begin testing during Q1 2012. The plan is to catch up to the revised baseline during Q2-2012 once route segments have been completed. | 2012-02-14 15:38 | 2012-02-14 15:38 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2012 | Q1 | Q1 - 2012 | 6115 | 5660 | TRUE | 38 | Eight percent behind of revised baseline due to the large amount of equipment being received but not paid for during the quarter. The plan is to catch up to the revised baseline in the next quarter once all the payments related to network equipment have been remitted. | 0 | OSS Software | Software support systems RFP was posted during the Q2-2011 quarter. The delay was caused by reviewing several software support systems and Bluebird Media being unable to decide on a system prior to closing Q2-2011. During Q3-2011 Bluebird Media contracted with a software company to implement software systems during Q4-2011. The plan is to catch up to the revised baseline during Q2-2012 once billing for the OSS Software commences. | 95 | Bluebird Media was issued a Finding of Non Significant Impact on the environment during Q2 2011, continued environmental monitoring during construction will be the remaining 5 percent to complete. Agrees to revised baseline. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 82 | Behind revised baseline schedule by 18 percent. The 82 percent of required permits included highway right-of-way permits, railroad crossing permits, and environmental permits. Virtually all permits that had been submitted had received approval. The remaining permits that have yet to be submitted are associated with portions of construction targeted late in the project plan. The plan is to catch up to the revised baseline during Q2-2012 once all permits have been submitted prior to the final construction being completed. | 70 | Behind revised baseline schedule by 30 percent. Focus during the quarter was on obtaining permits and performing due diligence work regarding shelter sites. The completion of these activities are required before physical preparation of the sites can be performed. The plan is to catch up to the revised baseline during Q2-2012 once several shelter sites are prepared for construction. | 51 | Behind revised baseline schedule by 43 percent. Delay caused by the under estimated amount of time needed to check in these large orders of equipment prior to remitting payment. The plan is to catch up to the revised baseline during Q2-2012 once the majority of the equipment is shipped and billed during Q1-2012. | 40 | Behind revised baseline schedule by eight percent. Delay caused by approved route changes during Q1-2011. The route changes caused a delay in engineering and environmental assessment during Q1 and Q2 of 2011, delaying construction to start in Q3 2011. Delay also caused by 45 day delay in obtaining construction permits during the first part of Q3 2011 delaying construction startup. The plan is to catch up to the revised baseline during Q2 2012. | 30 | No variance from baseline plan or subsequent written updates provided to the program officer. | 0 | Delay caused by approved route changes during Q1-2011, delaying construction to start in Q3 2011. 20 percent behind revised baseline with plans to complete network segments and begin testing during the start of Q2 2012. The plan is to catch up to the revised baseline during Q2-2012 once route segments have been completed and turned up. | 2012-05-15 17:27 | 2012-05-15 17:27 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2012 | Q2 | Q2 - 2012 | 6733 | 5993 | TRUE | 57 | 17 percent behind of revised baseline due to the large amount of equipment being received but not paid for during the quarter and for not recognizing the $10.5 million In-Kind Contribution until 7.31.12. The plan is to catch up to the revised baseline in the next quarter once all the payments related to network equipment have been remitted and the contribution has been recognized. | 0 | OSS Software | Software support systems RFP was posted during the Q2-2011 quarter. The delay was caused by reviewing several software support systems and Bluebird Media being unable to decide on a system prior to closing Q2-2011. During Q3-2011 Bluebird Media contracted with a software company to implement software systems during Q4-2011. The plan is to catch up to the revised baseline during Q3-2012 once billing for the OSS Software commences. | 95 | Bluebird Media was issued a Finding of Non Significant Impact on the environment during Q2 2011, continued environmental monitoring during construction will be the remaining 5 percent to complete. Agrees to revised baseline. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 90 | Behind revised baseline schedule by ten percent. The 90 percent of required permits included highway right-of-way permits, railroad crossing permits, and environmental permits. Virtually all permits that had been submitted had received approval. The remaining permits that have yet to be submitted are associated with portions of construction targeted late in the project plan. The plan is to catch up to the revised baseline during Q3-2012 once all permits have been submitted prior to the final construction being completed. | 77 | Behind revised baseline schedule by 23 percent. Focus during the quarter was on obtaining permits and performing due diligence work regarding shelter sites. The completion of these activities are required before physical preparation of the sites can be performed. The plan is to catch up to the revised baseline during Q3-2012 once several shelter sites are prepared for construction. | 74 | Behind revised baseline schedule by 24 percent. Delay caused by the under estimated amount of time needed to check in these large orders of equipment prior to remitting payment. The plan is to catch up to the revised baseline during Q3-2012 once the majority of the equipment is shipped and billed during Q2-2012. | 62 | No variance from baseline plan or subsequent written updates provided to the program officer. | 50 | No variance from baseline plan or subsequent written updates provided to the program officer. | 11 | Delay caused by approved route changes during Q1-2011, delaying construction to start in Q3 2011. 19 percent behind revised baseline. The plan is to catch up to the revised baseline during Q3-2012 once the majority of the route segments have been completed and turned up. | 2012-07-30 17:46 | 2012-07-30 17:46 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2012 | Q3 | Q3 - 2012 | 7985 | 6699 | TRUE | 87 | 1 percent behind revised baseline due to the large amount of construction being invoiced, but retainage being held until project completion. As all construction is completed, Bluebird will catch up to the revised baseline in the next quarter once all the final construction payments have been released. | 0 | OSS Software | Software support systems RFP was posted during the Q2-2011 quarter. The delay was caused by reviewing several software support systems and Bluebird Media being unable to decide on a system prior to closing Q2-2011. During Q3-2011 Bluebird Media contracted with a software company to implement software systems during Q4-2011. The plan is to catch up to the revised baseline during Q4-2012 once billing for the OSS Software commences. | 95 | Bluebird Media was issued a Finding of Non Significant Impact on the environment during Q2 2011, continued environmental monitoring during construction will be the remaining 5 percent to complete. The plan is to catch up to the revised baseline during Q4-2012 once all construction has been completed. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 95 | Behind revised baseline schedule by 5 percent. The 95 percent of required permits included highway right-of-way permits, railroad crossing permits, and environmental permits. Virtually all permits that had been submitted had received approval. The remaining permits that have yet to be submitted are associated with portions of construction targeted late in the project plan. The plan is to catch up to the revised baseline during Q4-2012 once all permits have been submitted prior to the final construction being completed. | 83 | Behind revised baseline schedule by 17 percent. Focus during the quarter was on obtaining permits and performing due diligence work regarding shelter sites. The completion of these activities are required before physical preparation of the sites can be performed. The plan is to catch up to the revised baseline during Q4-2012 once several shelter sites are prepared for construction. | 81 | Behind revised baseline schedule by 19 percent. Delay caused by the under estimated amount of time needed to check in these large orders of equipment prior to remitting payment. The plan is to catch up to the revised baseline during Q4-2012 once the majority of the equipment was shipped and billed during Q3-2012. | 76 | No variance from baseline plan or subsequent written updates provided to the program officer. | 60 | No variance from baseline plan or subsequent written updates provided to the program officer. | 33 | Delay caused by approved route changes during Q1-2011, delaying construction to start in Q3 2011. 17 percent behind revised baseline. The plan is to catch up to the revised baseline during Q4-2012 once the majority of the route segments have been completed and turned up. | 2012-11-20 16:18 | 2012-11-20 16:18 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2012 | Q4 | Q4 - 2012 | 8455 | 7176 | TRUE | 93 | 2 percent behind revised baseline due to the large amount of construction being invoiced, but retainage being held until project completion. As all construction is completed, Bluebird will catch up to the revised baseline in the next quarter once all the final construction payments have been released. | 0 | OSS Software | Software support systems RFP was posted during the Q2-2011 quarter. The delay was caused by reviewing several software support systems and Bluebird Media being unable to decide on a system prior to closing Q2-2011. During Q3-2011 Bluebird Media contracted with a software company to implement software systems during Q4-2011. The plan is to catch up to the revised baseline during Q1-2013 once billing for the OSS Software commences. | 95 | Bluebird Media was issued a Finding of Non Significant Impact on the environment during Q2 2011, continued environmental monitoring during construction will be the remaining 5 percent to complete. The plan is to catch up to the revised baseline during Q1-2013 once all construction has been completed. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 99 | Behind revised baseline schedule by 99 percent. The 99 percent of required permits included highway right-of-way permits, railroad crossing permits, and environmental permits. Virtually all permits that had been submitted had received approval. The remaining permits that have yet to be submitted are associated with portions of construction targeted late in the project plan. The plan is to catch up to the revised baseline during Q1-2013 once all permits have been submitted prior to the final construction being completed. | 92 | Behind revised baseline schedule by 8 percent. Focus during the quarter was on obtaining permits and performing due diligence work regarding shelter sites. The completion of these activities are required before physical preparation of the sites can be performed. The plan is to catch up to the revised baseline during Q1-2013 once several shelter sites are prepared for construction. | 82 | Behind revised baseline schedule by 18 percent. Delay caused by the under estimated amount of time needed to check in these large orders of equipment prior to remitting payment. The plan is to catch up to the revised baseline during Q1-2013 once the majority of the equipment was shipped and billed during Q4-2012. | 91 | No variance from baseline plan or subsequent written updates provided to the program officer. | 75 | No variance from baseline plan or subsequent written updates provided to the program officer. | 50 | Delay caused by approved route changes during Q1-2011, delaying construction to start in Q3 2011. 10 percent behind revised baseline. The plan is to catch up to the revised baseline during Q1-2013 once the majority of the route segments have been completed and turned up. | 2013-01-30 13:36 | 2013-01-30 13:36 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2013 | Q1 | Q1 - 2013 | 9935 | 8511 | TRUE | 98 | No variance from baseline plan or subsequent written updates provided to the program officer. | 0 | OSS Software | Software support systems RFP was posted during the Q2-2011 quarter. The delay was caused by reviewing several software support systems and Bluebird Media being unable to decide on a system prior to closing Q2-2011. During Q3-2011 Bluebird Media contracted with a software company to implement software systems during Q4-2011. The plan is to catch up to the revised baseline during Q2-2013 once billing for the OSS Software commences. | 95 | Bluebird Media was issued a Finding of Non Significant Impact on the environment during Q2 2011, continued environmental monitoring during construction will be the remaining 5 percent to complete. The plan is to catch up to the revised baseline during Q2-2013 once all construction has been completed. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 99 | Behind revised baseline schedule by 1 percent. The 99 percent of required permits include highway right-of-way permits, railroad crossing permits, and environmental permits. Virtually all permits that have been submitted have received approval. The remaining permits that have yet to be submitted are associated with portions of construction targeted late in the project plan. The plan is to catch up to the revised baseline during Q2-2013 once all permits have been submitted prior to the final construction being completed. | 95 | Behind revised baseline schedule by 5 percent. Focus during the quarter was on obtaining permits and performing due diligence work regarding shelter sites. The completion of these activities are required before physical preparation of the sites can be performed. The plan is to catch up to the revised baseline during Q2-2013 once several shelter sites are prepared for construction. | 85 | Behind revised baseline schedule by 15 percent. Delay caused by the under estimated amount of time needed to check in these large orders of equipment prior to remitting payment. The plan is to catch up to the revised baseline during Q2-2013 once the majority of the remaining equipment was shipped and billed during Q1-2013. | 95 | No variance from baseline plan or subsequent written updates provided to the program officer. | 85 | Behind revised baseline schedule by 5 percent. Delay caused by the under estimated amount of time needed to check in these large orders of equipment prior to remitting payment. The plan is to catch up to the revised baseline during Q2-2013 once the majority of the remaining equipment was shipped and billed during Q1-2013. | 75 | No variance from baseline plan or subsequent written updates provided to the program officer. | 2013-05-28 14:24 | 2013-05-28 14:24 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2013 | Q2 | Q2 - 2013 | 10477 | 8887 | TRUE | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 0 | OSS Software | Software support systems RFP was posted during the Q2-2011 quarter. The plan is to not allocate any grant funds to software as all software will be paid 100% by owner funds. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 95 | Behind revised baseline schedule by 5 percent. Delay caused by the under estimated amount of time needed to sign final IRU agreements. The plan is to catch up to the revised baseline during Q3-2013. | 95 | Behind revised baseline schedule by 5 percent. Delay caused by the under estimated amount of time needed to get CAIs signed up for service. The plan is to catch up to the revised baseline during Q3-2013 once the majority of the remaining equipment has been installed at CAI locations during Q3-2013. | 95 | Behind revised baseline schedule by 5 percent. Delay caused by the under estimated amount of time needed to get CAIs signed up for service. The plan is to catch up to the revised baseline during Q3-2013 once the majority of the remaining equipment has been installed at CAI locations during Q3-2013. | 2013-08-02 15:24 | 2013-08-02 15:24 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2013 | Q3 | Q3 - 2013 | 11583 | 9705 | TRUE | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 0 |  | Software support systems RFP was posted during the Q2-2011 quarter. The plan is to not allocate any grant funds to software as all software will be paid 100% by owner funds. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 100 | No variance from baseline plan or subsequent written updates provided to the program officer. | 2014-01-10 14:05 | 2014-01-10 14:05 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570093 | 2010 | Q4 | Q4 - 2010 | 893 | 1938 | TRUE | 0 | No Variance | 0 | N/A | No Variance | 90 | No Variance | 40 | No Variance | 40 | Citizens had anticipated having 90% of the rights of way secured be end of quarter 2. The major factors that have delayed this process are: (1) the unusual winter weather has slowed the preliminary field engineering, (2) scheduling meetings and negotiations with County officials and property owners was slowed due to the Holiday season ( Thanksgiving, Christmas, New Years), (3) additional right of way was identified to accommodate VDOT road projects. | 40 | Citizens had anticipated having 90% of the Permits and Agreements completed by the end of quarter 2. The major factors that have delayed this process are: (1) Working with the Virginia Department of Transportation on the MOU amendment has slowed the high way permit process, (2) the winter weather has delayed the firm (EEC) doing the Joint Permit Application (JPA) for stream cross from doing their field engineering, (3) completing the preliminary field engineering for Joint Use Applications has been slowed by the winter weather, (4) meeting and negotiating with locality officials for permits has been more difficult due to the Holiday season. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-01-29 10:54 | 2011-01-29 10:54 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2011 | Q1 | Q1 - 2011 | 2025 | 2758 | TRUE | 5 | no Variance | 0 | N/A | no Variance | 95 | The final approval of the EA has been delayed because Citizens had to make three changes in the original proposed construction routes. The route changes were (1) Pulaski County Corporate Park route change to accommodate moving existing waterline easement, (2) the original location for the Christiansburg hut site could not be obtained, therefore had to move location where private property could be purchased, (3) Blacksburg route had to be changed from buried to aerial on one portion because of additional utilities being placed in the planned corridor and another portion of the route was changed from aerial to buried because of extensive make ready cost. These changes required approval from BTOP/VTIA program office and then submitting these changes were added to the EA. This resulted in an additional 30 day wait for the FWS and other agencies to respond to the changes. Citizens is expecting a response from the agencies by April 21, based on the 30 day wait. | 80 | Citizens had anticipated having 90% of the network design completed by the end of quarter 3. Citizens had originally scheduled having the engineering firm approved and the contract agreement finalized by January 7, 2011. Due to the number of responses that Citizens received for engineering RFP, it took longer to make the final decision on selecting the engineering firm. The contract was finalized with Thompson & Litton, Inc. on January 20, 2011 and the firm began work on January 21, 2011, approximately 10 days later than the original schedule. The field engineering and design work got off to a slower start due to the winter weather and a longer than expected learning curve working with a new firm. The field engineering and staking was scheduled to be completed by March 18, 2011. This process will now be completed by April 15, 2011. This required adjusting the scheduled dates for sending out the bid packets, bid due date, and contract award date. These dates were adjusted so as | 80 | Citizens had anticipated having 100% of the five identified private rights of way secured by the end of quarter 3. Three of the rights of way have been negotiated and one pending final signing by the property owner. The final right of way with Montgomery County at Falling Branch Industrial Park is scheduled to be completed by May 31, 2011. | 90 | Citizens had anticipated have 100% of the VDOT and locality work permits completed by the end of quarter 3. All of the VDOT and locality work permits require a complete set of construction sheets of the proposed work before they can be completed. Finalizing these permit was delayed due to having to wait for the completed construction sheets. The construction sheets will be ready by April 15, 2011 and will be sent to VDOT and the localities for completion of the required permitting process for each agency. All permits will be complete by May 30, 2011. | 0 | no Variance | 0 | Citizens is working with Mid-Atlantic Broadband Cooperative and the Virginia Tech Foundation in order to procure equipment as on large order at a bulk rate for larger discount. Due to coordinating this bulk order between these 4 BTOP projects, we did not meet our expected goal for this quarter. We except for this order to happen in 2nd Quarter 2011. | 0 | no Variance | 0 | no Variance | 0 | no Variance | 2011-05-13 16:15 | 2011-05-13 16:15 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2011 | Q2 | Q2 - 2011 | 2993 | 3254 | TRUE | 5 | Due to the delay in having it's FONSI issued, Citizens Telephone has covered the cost of the project through June 30, 2011. No federal funds have been expended through the 2nd Quarter of 2011. | 0 |  | No Variance | 100 | No Variance | 100 | No Variance | 95 | Citizens had anticipated having 100% of the identified private rights of way to be secured by the end of the 4th quarter. All have been completed with the exception of the right of way for the Falling Branch Industrial Park which is still being negotiated with Montgomery County, Virginia. An additional right of way has been identified in Pulaski County with the Town of Pulaski. This agreement has been negotiated with the town and is currently waiting signature from the town and will be completed by early August, 2011. | 95 | Citizens had anticipated having 100% of all locality permits and agreements completed by the end of the 4th quarter. The Town of Blacksburg does not issue a project permit for construction in the town limits. The excavation permits and lane closure permits will be issued on a weekly basis requiring daily notification, so the permit process with the Town of Blacksburg will be ongoing during the construction phase. The right of way agreement with the Town of Pulaski has been completed and is waiting signature from the town by the 1st week of August. | 50 | No Variance | 13 | No Variance | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-08-10 11:20 | 2011-08-10 11:20 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2011 | Q3 | Q3 - 2011 | 4069 | 3878 | TRUE | 7 | The construction process has been delayed by 3.5 months thus far due to the unavailability and extended delivery lead times that the fiber cable manufacturers are currently experiencing. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 98 | Citizens had anticipated having 100% of the identified private right of ways needed for the project completed by the end of the 5th quarter. One additional right of way for Falling Branch Industrial Park in Christiansburg and one right of way from the Town of Pulaski in Pulaski County are awaiting final signatures for completion. These two agreements should be complete by the end of November, 2011. | 98 | Citizens had anticipated having 100% of the permits and agreements completed by the end of the 5th quarter. The Town of Blacksburg does not issue Work or Land Use Permits for the project. The Town of Blacksburg issues Excavation Permits and Lane Closure Permits on a weekly basis, so the permit process with the town is ongoing during the construction process. The Town of Pulaski Work Permit will be complete by the last week of October, 2011. The County of Pulaski has completed the approval process for the lease agreement for the Pulaski Telecommunication Hut site. Final signatures and recording should be complete by Mid-November, 2011. | 50 | No Variance | 95 | Citizens worked together with Mid-Atlantic Broadband Cooperative and the Virginia Tech Foundation in order to procure equipment on a large order at a bulk rate for a larger discount. Due to coordinating this bulk order between 4 BTOP projects, we were able to procure the majority of our equipment sooner than originally anticipated. The order was placed in the 5th quarter and received and paid for during the 6th quarter. | 5 | Citizens had anticipated having 20% of the network construction completed by the end of 5th quarter. Delay in the final approval of the Environmental Assessment and long lead times in obtaining fiber cable and other materials have impacted the timing of construction. | 0 | No Variance | 0 | No Variance | 2011-11-16 14:33 | 2011-11-16 14:33 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2011 | Q4 | Q4 - 2011 | 4637 | 4282 | TRUE | 13 | Citizens originally projected having 39% of the project complete by the end of the 6th quarter. The total delay in obtaining fiber cable was nearly 6 months from the time orders were place in June 2011 | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 99 | Citizens had anticipated having 100% of the identified private rights of way needed for the project completed by the end of the 6th quarter. One additional right of way for Falling Branch Industrial Park in Christiansburg is still outstanding. Citizens is negotiating with the one landowner and plans to have the issue resolved by the middle of February, 2012. | 99 | Citizens had anticipated having 100% of the permits and agreements completed by the end of the 6th quarter. The construction permit for the City of Radford is currently in the signing stage and should not cause any delays in the construction process. | 90 | Citizens had projected having 50% of the site work completed for the two telecommunication huts proposed in the project. The contractor expedited this work in order to beat the winter season. The Pulaski site has a small amount of cleanup work remaining to be completed at the end of the quarter. | 95 | Citizens worked together with Mid-Atlantic Broadband Cooperative and the Virginia Tech Foundation in order to procure equipment on a large order at a bulk rate for a larger discount. Due to coordinating this bulk order between 4 BTOP projects, we were able to procure the majority of our equipment sooner than originally anticipated. The order was placed in the 5th quarter and received in the 6th quarter. | 8 | Delay in the final approval of the Environmental Assessment and long lead times in obtaining fiber cable and other materials have impacted the timing of construction. | 0 | No Variance | 0 | No Variance | 2012-01-30 10:37 | 2012-01-30 10:37 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2012 | Q1 | Q1 - 2012 | 5811 | 5505 | TRUE | 23 | Citizens originally projected having 47% of the project complete by the end of the 7th quarter. The total delay in obtaining fiber cable was nearly 6 months from the time orders were place in June 2011. Starting construction at the beginning of the winter season has slowed progress also. | 0 |  | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 99 | Citizens had anticipated having 100% of the permits and agreements completed by the end of the 7th quarter. The construction permit for the City of Radford has been completed although Citizens has not received the permit to date. | 100 | Citizens had projected having 50% of the site work completed for the two telecommunication huts proposed in the project. The contractor expedited this work in order to beat the winter season and minimize moving construction equipment in at a later date. | 95 | Citizens worked together with Mid-Atlantic Broadband Cooperative and the Virginia Tech Foundation in order to procure equipment on a large order at a bulk rate for a larger discount. Due to coordinating this bulk order between 4 BTOP projects, we were able to procure the majority of our equipment sooner than originally anticipated. The order was placed in the 5th quarter and received in the 6th quarter. | 25 | Delay in the final approval of the Environmental Assessment and the long lead time in obtaining fiber cable and other materials have impacted the timing of construction. | 0 | Citizens had anticipated having 30% of the equipment installed at the end of the 7th quarter. Delays in starting construction due to the lead time of fiber cable and waiting for approval of the EA has limited the amount of Equipment Deployment. | 5 | Citizens had anticipated having 20% of the network testing complete at the end of the 7th quarter. Delays in starting construction due to the lead time of fiber cable and waiting approval for approval of the EA has limited the amount of Network facilities ready for testing. | 2012-04-30 16:37 | 2012-04-30 16:37 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2012 | Q2 | Q2 - 2012 | 7147 | 6201 | TRUE | 31 | Citizens originally projected having 69% of the project complete by the end of the 8th quarter. The total delay in obtaining fiber cable and receiving an approved Environmental Assessment was nearly 6 months. Although some construction did start in the 5th quarter, the main construction contracts did not get started until the 7th quarter due to the aforementioned delays. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 52 | Delay in the final approval of the Environmental Assessment and the long lead time in obtaining fiber cable and other materials have impacted the timing of construction. | 50 | Citizens had anticipated having 60% of the equipment installed at the end of the 8th quarter. Delays in starting construction due to the lead time of fiber cable and waiting approval for the EA limited the amount of Network facilities to be completed and thus equipment to be deployed. | 15 | Citizens had anticipated having 20% of the network testing complete at the end of the 7th quarter. Delays in starting construction due to the lead time of fiber cable and waiting for approval of the EA has limited the amount of Network facilities ready for testing. | 2012-08-20 09:57 | 2012-08-20 09:57 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2012 | Q3 | Q3 - 2012 | 7947 | 6679 | TRUE | 43 | Citizens originally projected having 77% of the project complete by the end of the 9th Quarter. Since this Milestone is calculated on Federal Funds that have been spent, the delay in percentage complete is due to the delay in invoicing from the Contractors performing the construction. Actual construction on the project is 77% complete at the end of the 9th Quarter. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 77 | No Variance - Citizens had projected having 77% of the project complete by the end of the 9th quarter. Citizens met this target by having the contractors bring in additional crews. | 60 | No Variance | 52 | Citizens had anticipated having 68% of the network testing complete at the end of the 9th quarter. Delays in starting construction due to the lead time of fiber cable and waiting approval for approval of the EA has limited the amount of Network facilities ready for testing. Construction target milestones are now catching up with the original milestones so testing should be back on target by the end of the 10th quarter. | 2012-11-19 08:56 | 2012-11-19 08:56 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2012 | Q4 | Q4 - 2012 | 8431 | 7129 | TRUE | 65 | Citizens originally projected having 93% of the project complete by the end of the 10th Quarter. Since this Milestone is calculated on Federal Funds that have been spent, the delay in percentage complete is due to the delay in invoicing from the Contractors performing the construction. Actual construction on the project is 96% complete at the end of the 10th Quarter. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 96 | Citizens had projected to be 93% of the project complete by the end of the 10th quarter. Citizens exceeded this target by having the contractors bring in additional crews and by starting work on a 4th contract with a third contractor. | 80 | No Variance | 80 | Citizens had anticipated having 77% of the network testing complete at the end of the 10th quarter. Problems found with attenuation loss in some locations has delayed some testing. However, solutions for this issue have been determined and is presently being utilized. This work will be completed in the upcoming weeks and all testing shall remain on target for the upcoming quarter. | 2013-01-30 10:52 | 2013-01-30 10:52 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2013 | Q1 | Q1 - 2013 | 10025 | 8563 | TRUE | 82 | Citizens originally projected having 95% of the project complete by the end of the 11th Quarter. Since this Milestone is calculated on Federal Funds that have been spent, the delay in percentage complete is due to the delay in invoicing from the Contractors performing the construction. Actual construction on the project was 96% complete at the end of the 11th Quarter. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 96 | No Variance | 80 | No Variance | 96 | No Variance | 2013-05-31 14:47 | 2013-05-31 14:47 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2013 | Q2 | Q2 - 2013 | 10773 | 9052 | TRUE | 85 | Citizens originally projected having 100% of the project complete by the end of the 12th Quarter. Since this Milestone is calculated on Federal Funds that have been spent, the delay in percentage complete is due to the delay in invoicing from the Contractors performing the construction. Actual construction on the project was 99% complete at the end of the 12th Quarter. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 99 | Citizens had originally projected having 100% of the network build complete by the end of the 12th quarter. Delays in construction due to aerial make-ready work needed by Verizon and AEP in Pearisburg prevented us from meeting this goal. Extra crews were brought in to complete (100%) by July 15, 2013. | 100 | No Variance | 99 | Citizens had anticipated having 100% of the network testing complete at the end of the 12th quarter. Delays in aerial construction in the town of Pearisburg due to make-ready issues prevented Citizens from meeting this deadline. The remainder of network testing was started immediately after the completion of construction and was completed on July 17th, 2013. | 2013-08-27 16:42 | 2013-08-27 16:42 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2013 | Q3 | Q3 - 2013 | 11469 | 9583 | TRUE | 100 | No Variance | 100 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-12-11 11:40 | 2013-12-11 11:40 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570094 | 2010 | Q4 | Q4 - 2010 | 555 | 1575 | TRUE | 0 | The accounting books were not set up last quarter. Therefore, no federal funds have been expended, and no state match funds have been reclassified for the project. | 0 | Engineering Services | The accounting books were not set up last quarter. Therefore, no federal funds have been expended, and no state match funds have been reclassified for the project. | 0 | The accounting books were not set up last quarter. Therefore, no federal funds have been expended, and no state match funds have been reclassified for the project. | 0 | The accounting books were not set up last quarter. Therefore, no federal funds have been expended, and no state match funds have been reclassified for the project. | 0 | The accounting books were not set up last quarter. Therefore, no federal funds have been expended, and no state match funds have been reclassified for the project. | 0 | The accounting books were not set up last quarter. Therefore, no federal funds have been expended, and no state match funds have been reclassified for the project. | 0 | The accounting books were not set up last quarter. Therefore, no federal funds have been expended, and no state match funds have been reclassified for the project. | 0 | The accounting books were not set up last quarter. Therefore, no federal funds have been expended, and no state match funds have been reclassified for the project. | 0 | The accounting books were not set up last quarter. Therefore, no federal funds have been expended, and no state match funds have been reclassified for the project. | 0 | The accounting books were not set up last quarter. Therefore, no federal funds have been expended, and no state match funds have been reclassified for the project. | 0 | The accounting books were not set up last quarter. Therefore, no federal funds have been expended, and no state match funds have been reclassified for the project. | 2011-01-26 16:14 | 2011-01-26 16:14 | 5293 | 5293 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2011 | Q1 | Q1 - 2011 | 2017 | 2754 | TRUE | 6 | Baseline for Q3 is 22%. Microwave equipment that was planned for deployment this quarter is in manufacturing and has not been invoiced. Site due diligence services on the first 28 sites is complete but not invoiced or paid. Construction (remodeling) activities at MS MEDCOM has been rescheduled as indicated below. | 3 | Engineering Services | Baseline for Q3 is 7%. Specific items in the initial baseline were reclassified and removed from this category. Engineering services for LTE and Microwave have commenced but have not been completed or invoiced. QA/QC Services paid from State Bond funds are included here as Match. | 0 | N/A | 0 | Baseline for Q3 is 21%. Site location, site lock and detailed network design for the first 28 sites has occurred but has not been invoiced. Invoicing should occur next quarter. | 0 | N/A | 0 | N/A | 0 | Baseline for Q3 is 100%. Site preparation for equipment at UMMC has been delayed until Year 2 Q1. | 4 | Baseline for Q3 is 20%. Microwave equipment for the backhaul for the first 28 sites is currently in manufacturing with expected testing in Q4. Delivery and invoicing should occur in Year 2 Q1. State Match for existing microwave to be used for broadband is included here. | 20 | Baseline for Q3 is 43%. Microwave equipment for the backhaul for the first 28 sites is currently in manufacturing with expected testing in Q4. Delivery and invoicing should occur in Year 2 Q1. State Match for site due diligence and leases is included here. | 0 | Baseline for Q3 is 4%. Microwave equipment for the backhaul for the first 28 sites is currently in manufacturing with expected testing in Q4. Delivery and invoicing should occur in Year 2 Q1. Proposals in response to RFP 3639 for LTE equipment and services are in evaluation. Award is expected in Q4. | 0 | Baseline for Q3 is 0% | 2011-05-13 14:49 | 2011-05-13 14:49 | 5293 | 5293 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2011 | Q2 | Q2 - 2011 | 3049 | 3282 | TRUE | 9 | Baseline for Q4 is 31%. Microwave equipment that was planned for deployment this quarter has been manufactured and factory tested but not received nor invoiced. Site due diligence services on the first 28 sites is complete but not invoiced or paid. Construction (remodeling) activities at MS MEDCOM has been rescheduled as indicated below. | 3 |  | Baseline for Q4 is 18%. Specific items in the initial baseline were reclassified and removed from this category. Engineering services for LTE and Microwave have commenced but have not been completed or invoiced. QA/QC Services paid from State Bond funds are included here as Match. | 0 | N/A | 0 | Baseline for Q4 is 30%. Site location, site lock and detailed network design for the first 28 sites has occurred but has not been invoiced. Invoicing should occur next quarter. | 0 | N/A | 0 | N/A | 0 | Baseline for Q4 is 100%. Site preparation for equipment at UMMC has been delayed until Year 2 Q1. | 5 | Baseline for Q4 is 30%. Microwave equipment that was planned for deployment this quarter has been manufactured and factory tested but not received nor invoiced. Delivery and invoicing should occur in Year 2 Q1. State Match for existing microwave to be used for broadband is included here. | 29 | Baseline for Q4 is 53%. Microwave equipment that was planned for deployment this quarter has been manufactured and factory tested but not received nor invoiced. Delivery and invoicing should occur in Year 2 Q1. State Match for site due diligence and leases is included here. | 0 | Baseline for Q4 is 9%. Microwave equipment that was planned for deployment this quarter has been manufactured and factory tested but not received nor invoiced. Delivery and invoicing should occur in Year 2 Q1. State Match for site due diligence and leases is included here. The evaluation of the three proposals in response to our LTE Broadband Request for Proposals was completed during second quarter 2011. The MS Department of Information Technology Services Board, the Stateâ€™s Information Technology contracting agent, approved the award of the LTE contract to Motorola Solutions, Inc. on June 23, 2011. Contract negotiations will commence in July with anticipated execution prior to September 1, 2011. | 0 | Baseline for Q4 is 0% | 2011-08-12 15:14 | 2011-08-12 15:14 | 5293 | 5293 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2011 | Q3 | Q3 - 2011 | 4367 | 4040 | TRUE | 13 | Baseline for Q5 is 47%. Microwave equipment for Phase 2 sites has been factory tested and is in installation. Invoices were paid during the quarter for detailed MW design and factory testing of the Phase 2 MW equipment. MW installation milestones for 24 new microwave paths have not been invoiced. | 36 |  | Baseline for Q5 is 35%. Specific items in the initial baseline were reclassified and removed from this category. Engineering services for MW design and factory test have been completed or invoiced. QA/QC Services paid from State Bond funds are included here as Match. | 0 | N/A | 3 | Baseline for Q5 is 50%. Invoices were paid during the quarter for detailed MW design and factory testing of the Phase 2 MW equipment. MW installation milestones for 24 new microwave paths have not been invoiced. | 0 | N/A | 0 | N/A | 0 | Baseline for Q5 is 100%. Site preparation for equipment at UMMC has been delayed until Year 2 Q1. | 10 | Baseline for Q5 is 47%. Microwave equipment for Phase 2 sites has been factory tested and is in installation. Invoices were paid during the quarter for detailed MW design and factory testing of the Phase 2 MW equipment. MW installation milestones for 24 new microwave paths have not been invoiced. State Match for existing microwave to be used for broadband is included here. | 37 | Baseline for Q5 is 67%. Microwave equipment for Phase 2 sites has been factory tested and is in installation. Invoices were paid during the quarter for detailed MW design and factory testing of the Phase 2 MW equipment. MW installation milestones for 24 new microwave paths have not been invoiced. State Match for existing microwave to be used for broadband is included here. | 0 | Baseline for Q5 is 21%. Microwave equipment for Phase 2 sites has been factory tested and is in installation. Invoices were paid during the quarter for detailed MW design and factory testing of the Phase 2 MW equipment. MW installation milestones for 24 new microwave paths have not been invoiced | 0 | Baseline for Q5 is 13%. Microwave equipment for Phase 2 sites has been factory tested and is in installation. Invoices were paid during the quarter for detailed MW design and factory testing of the Phase 2 MW equipment. MW installation milestones for 24 new microwave paths have not been invoiced. | 2011-12-02 09:56 | 2011-12-02 09:56 | 5293 | 5293 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2011 | Q4 | Q4 - 2011 | 5043 | 4718 | TRUE | 24 | Baseline for Q6 is 70%. Microwave backhaul equipment for Phase 2C and 2D sites was installed and tested. The contractor completed factory acceptance testing for microwave backhaul equipment for all of the Phase 3 sites. The LTE Core equipment was delivered to the Motorola facility in Shaumburg, IL for assembly, configuration and testing. Installation of LTE antenna arrays began during the quarter with completion of 12 sites. The State had anticipated more MSWIN LMR sites being available for microwave and LTE installations than actually became available. UMMC acquired ambulance data transmission equipment during the quarter. | 24 |  | Baseline for Q6 is 49%. Specific items in the initial baseline were reclassified and removed from this category. Engineering services for MW design and factory test have been completed or invoiced. QA/QC Services paid from State Bond funds are included here as Match. | 0 | N/A | 7 | Baseline for Q6 is 58%. Microwave backhaul equipment for Phase 2C and 2D sites was installed and tested. The State had anticipated more MSWIN LMR sites being available for microwave and LTE installations than actually became available. | 0 | N/A | 0 | N/A | 0 | Baseline for Q6 is 100%. Site preparation for equipment at UMMC has been delayed until Year 2 Q3. | 25 | Baseline for Q6 is 76%. Microwave backhaul equipment for Phase 2C and 2D sites was installed and tested. The contractor completed factory acceptance testing for microwave backhaul equipment for all of the Phase 3 sites. The LTE Core equipment was delivered to the Motorola facility in Shaumburg, IL for assembly, configuration and testing. Installation of LTE antenna arrays began during the quarter with completion of 12 sites. The State had anticipated more MSWIN LMR sites being available for microwave and LTE installations than actually became available. UMMC acquired ambulance data transmission equipment during the quarter. | 46 | Baseline for Q6 is 81%. Microwave backhaul equipment for Phase 2C and 2D sites was installed and tested. The LTE Core equipment was delivered to the Motorola facility in Shaumburg, IL for assembly, configuration and testing. Installation of LTE antenna arrays began during the quarter with completion of 12 sites. The State had anticipated more MSWIN LMR sites being available for microwave and LTE installations than actually became available. | 0 | Baseline for Q6 is 33%. The LTE Core equipment was delivered to the Motorola facility in Shaumburg, IL for assembly, configuration and testing. Installation of LTE antenna arrays began during the quarter with completion of 12 sites. The State had anticipated more MSWIN LMR sites being available for microwave and LTE installations than actually became available. Although this LTE equipment was installed during the quarter, the state has not been invoiced. | 0 | Baseline for Q6 is 25%. The LTE Core equipment was delivered to the Motorola facility in Shaumburg, IL for assembly, configuration and testing. Installation of LTE antenna arrays began during the quarter with completion of 12 sites. The State had anticipated more MSWIN LMR sites being available for microwave and LTE installations than actually became available. Although this LTE equipment was installed during the quarter, the state has not been invoiced. | 2012-02-15 16:36 | 2012-02-15 20:16 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2012 | Q1 | Q1 - 2012 | 5831 | 5515 | TRUE | 36 | Baseline for Q7 is 78%. The Detailed Design Review for the LTE system was approved by the WCC. 24 sets of LTE antenna arrays were installed on MSWIN sites during the quarter. The eNodeB equipment for 61 sites was delivered to the warehouse in Mississippi with eNodeB equipment being delivered directly to 48 sites. The eNodeB equipment for 31 sites was delivered to the shelter manufacturer in Georgia. They will arrive within the shelter upon a respective Phase 3 site being ready for receipt. The equipment for the LTE core was initially staged and tested in Motorola's Schaumburg, IL facility and was delivered to the ITS data center at the end of March. The State is currently in the process of installing the Core. The State's vendor began the construction of seven tower sites in North Mississippi that will be paid for by state bond funds and used as match. MEDCOM finalized and published the RFP for the Medical LTE data system per ITS guidelines. A mandatory vendor conference | 38 |  | Baseline for Q7 is 60%. Specific items in the initial baseline were reclassified and removed from the category. Engineering services for training have been completed or invoiced. QA/QC Services paid with State Bond funds are included here as match. | 0 | N/A | 24 | Baseline for Q7 is 66%. System integration for the eNodeB equipment at the tower sites was completed. Microwave path engineering for new tower sites in Phase 3 was completed. The State had anticipated more MSWIN LMR sites being available for MW and LTE installations than actually became available. The current timeline for completion of statewide build-out of LMR tower sites is expected by 4th QTR, 2012. | 0 | N/A | 0 | N/A | 0 | Baseline for Q7 is 100%. Site Preparation construction started in March 2012. With space being limited in the adjacent area(s) of Med-Com, employees and staff from a neighboring department were relocated and additional space was allocated for site preparation construction. This work included expansion and redundancy upgrades to electrical and network utilities as well as physical renovation of the Med-Com center. The project entailed expansion of the operations center, repurposing of the conference room, addition of a second network room and revision of technical support space. Site preparation is expected to be complete in Q3 2012. | 32 | Baseline for Q7 is 83%. The LTE Core was delivered to the ITS State Data Center and is in the process of being installed. 24 sets of LTE antenna arrays were installed on MSWIN sites. EnodeB equipment delivered directly to 48 tower sites. The State had anticipated more MSWIN LMR sites being available for MW and LTE installations than actually became available. The current timeline for completion of statewide build-out of LMR tower sites is expected by 4th QTR, 2012. | 57 | Baseline for Q7 is 86%. The LTE Core was delivered to the ITS State Data Center and is in the process of being installed. 24 sets of LTE antenna arrays were installed on MSWIN sites. EnodeB equipment delivered directly to 48 tower sites. The State had anticipated more MSWIN LMR sites being available for MW and LTE installations than actually became available. The current timeline for completion of statewide build-out of tower sites is expected by 4th QTR, 2012. The State's vendor began construction of seven tower sites in North Mississippi that will be used as Match. | 29 | Baseline for Q7 is 46%. The LTE Core was delivered to the ITS State Data Center and is in the process of being installed. 24 sets of LTE antenna arrays were installed on MSWIN sites. EnodeB equipment delivered directly to 48 tower sites. The State had anticipated more MSWIN LMR sites being available for MW and LTE installations than actually became available. The current timeline for completion of statewide build-out of tower sites is expected by 4th QTR, 2012. | 0 | Baseline for Q7 is 38%. The LTE Core was delivered to the ITS State Data Center and is in the process of being installed. 24 sets of LTE antenna arrays were installed on MSWIN sites. EnodeB equipment delivered directly to 48 tower sites. The State had anticipated more MSWIN LMR sites being available for MW and LTE installations than actually became available. The current timeline for completion of statewide build-out of tower sites is expected by 4th QTR, 2012. | 2012-04-30 17:21 | 2012-04-30 17:21 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2012 | Q2 | Q2 - 2012 | 7043 | 6149 | TRUE | 41 | Baseline for Q8 is 83%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Mississippi was on target to meet the 67% completion deadline set forth by the BTOP award requirements. As of May 11, Mississippi has accepted receipt of and installed the LTE core at the State Data Center. All eNodeB equipment for the 135 MSWIN tower sites has been received by the State and has either been delivered to the site or the placed in the shelters for delivery to the site once construction has been completed. The installation of eNodeB equipment has been completed at 73 of the MSWIN tower sites. 69 sets of LTE antenna arrays have been installed on MSWIN sites. The installation of the microwave backhaul was completed for all Phase 2C & 2D sites in Q4 2011. Mississippi also completed the construction and acceptance of all 9 match towers during this quarter. | 40 |  | Baseline for Q8 is 68%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Mississippi was on target to meet the 67% completion deadline set forth by the BTOP award requirements. Specific items in the initial baseline were reclassified and removed from the category. Engineering services for training have been completed or invoiced. QA/QC Services paid with State Bond funds are included here as match. | 0 | N/A | 25 | Baseline for Q8 is 75%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Mississippi was on target to meet the 67% completion deadline set forth by the BTOP award requirements. As of May 11, Microwave path engineering for new tower sites in Phase 3 was completed. The State had anticipated more MSWIN LMR sites being available for MW and LTE installations than actually became available. The current timeline for completion of statewide build-out of LMR tower sites is expected by 4th QTR, 2012. | 0 | N/A | 0 | N/A | 0 | Baseline for Q8 100%. Med-Com site construction nears completion, this includes expansion and redundancy upgrades to electrical and network utilities as well as expansion of the operations center and addition of a second network room. The improved infrastructure design was also started, this work included installation of new console furniture, implementation of the PSAP phone system and connection of the PTP for MSWIN. Vendor training of the Med-Com communication specialists has been completed and the PSAP phone system is operational. | 37 | Baseline for Q8 is 87%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Mississippi was on target to meet the 67% completion deadline set forth by the BTOP award requirements. As of May 11, the LTE Core has been delivered and installed in the ITS State Data Center. All eNodeB equipment for the 135 MSWIN tower sites has been received by the State and has either been delivered to the site or the placed in the shelters for delivery to the site once construction has been completed. The installation of eNodeB equipment has been completed at 73 of the MSWIN tower sites. 69 sets of LTE antenna arrays have been installed on MSWIN sites. The current timeline for completion of statewide build-out of LMR tower sites is expected by 4th QTR, 2012. | 68 | Baseline for Q8 is 89%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Mississippi was on target to meet the 67% completion deadline set forth by the BTOP award requirements. As of May 11, the LTE Core has been delivered and installed in the ITS State Data Center. All eNodeB equipment for the 135 MSWIN tower sites has been received by the State and has either been delivered to the site or the placed in the shelters for delivery to the site once construction has been completed. The installation of eNodeB equipment has been completed at 73 of the MSWIN tower sites. 69 sets of LTE antenna arrays have been installed on MSWIN sites. The current timeline for completion of statewide build-out of LMR tower sites is expected by 4th QTR, 2012. | 40 | Baseline for Q8 is 57%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Mississippi was on target to meet the 67% completion deadline set forth by the BTOP award requirements. As of May 11, the LTE Core has been delivered and installed in the ITS State Data Center. All eNodeB equipment for the 135 MSWIN tower sites has been received by the State and has either been delivered to the site or the placed in the shelters for delivery to the site once construction has been completed. The installation of eNodeB equipment has been completed at 73 of the MSWIN tower sites. 69 sets of LTE antenna arrays have been installed on MSWIN sites. The current timeline for completion of statewide build-out of LMR tower sites is expected by 4th QTR, 2012. | 0 | Baseline for Q8 is 50%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Mississippi was on target to meet the 67% completion deadline set forth by the BTOP award requirements. As of May 11, the LTE Core has been delivered and installed in the ITS State Data Center. All eNodeB equipment for the 135 MSWIN tower sites has been received by the State and has either been delivered to the site or the placed in the shelters for delivery to the site once construction has been completed. The installation of eNodeB equipment has been completed at 73 of the MSWIN tower sites. 69 sets of LTE antenna arrays have been installed on MSWIN sites. The current timeline for completion of statewide build-out of LMR tower sites is expected by 4th QTR, 2012. | 2012-08-13 14:36 | 2012-08-13 14:36 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2012 | Q3 | Q3 - 2012 | 7863 | 6636 | TRUE | 45 | Baseline for Q9 is 88%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. During Q3, 2012, payment milestones were met for the completion of installation services of the LTE Core in the State Data Center for work completed prior to May 11, 2011. Payment milestones were also met for microwave services performed for Phase 2C & 2D of the MSWIN Network. | 44 |  | Baseline for Q9 is 76%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. During Q3, 2012, Payment milestones were met for microwave services performed for Phase 2C & 2D of the MSWIN Network. Specific items in the initial baseline were reclassified and removed from the category. Engineering services for training have been completed or invoiced. QA/QC Services paid with State Bond funds are included here as match. | 0 | N/A | 28 | Baseline for Q9 is 83%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. During Q3, 2012, Payment milestones were met for microwave services performed for Phase 2C & 2D of the MSWIN Network. | 0 | N/A | 0 | N/A | 0 | Baseline for Q9 is 100% After further review of the construction required to accommodate the BTOP program, UMMC opted to pay for the bulk of the physical plant renovation out of UMMC funds. | 39 | Baseline for Q9 is 92%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. During Q3, 2012, Payment milestones were met for microwave services performed for Phase 2C & 2D of the MSWIN Network. | 73 | Baseline for Q9 is 92%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. During Q3, 2012, Payment milestones were met for microwave services performed for Phase 2C & 2D of the MSWIN Network. | 43 | Baseline for Q9 is 67%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. During Q3, 2012, payment milestones were met for the completion of installation services of the LTE Core in the State Data Center for work completed prior to May 11, 2011. | 0 | Baseline for Q9 is 63%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. | 2012-11-14 09:36 | 2012-11-14 09:36 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2012 | Q4 | Q4 - 2012 | 8841 | 7626 | TRUE | 45 | Baseline for Q10 is 93%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Payment milestones related to microwave installation in Phase 3 have been achieved during Q4, 2012, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | 44 |  | Baseline for Q10 is 84%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Payment milestones related to microwave installation in Phase 3 have been achieved during Q4, 2012, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act.Specific items in the initial baseline were reclassified and removed from the category. Engineering services for training have been completed or invoiced. QA/QC Services paid with State Bond funds are included here as match. | 0 | N/A | 28 | Baseline for Q10 is 92%. Payment milestones related to microwave installation in Phase 3 have been achieved during Q4, 2012, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | 0 | N/A | 0 | N/A | 1 | Baseline for Q10 is 100% The site preparation of MedCom was completed. While the vast majority of the physical plant renovation was paid from UMMC funds, smaller project costs were filed under the BTOP grant. An example of project components include but is not limited to core drilling costs | 39 | Baseline for Q10 is 96%. Payment milestones related to microwave installation in Phase 3 have been achieved during Q4, 2012, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | 76 | Baseline for Q10 is 94%. Payment milestones related to microwave installation in Phase 3 have been achieved during Q4, 2012, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | 43 | Baseline for Q10 is 78%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. | 0 | Baseline for Q10 is 75%. Specific items in the initial baseline were reclassified and removed from the category. | 2013-02-19 14:59 | 2013-02-21 10:36 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2013 | Q1 | Q1 - 2013 | 9693 | 8380 | TRUE | 46 | Baseline for Q11 is 98%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Payment milestones related to microwave installation in Phase 3 have been achieved during Q1, 2013, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | 44 |  | Baseline for Q11 is 92%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Payment milestones related to microwave installation in Phase 3 have been achieved during Q4, 2012, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act.Specific items in the initial baseline were reclassified and removed from the category. Engineering services for training have been completed or invoiced. QA/QC Services paid with State Bond funds are included here as match. | 0 | N/A | 28 | Baseline for Q11 is 100%. Payment milestones related to microwave installation in Phase 3 have been achieved during Q1, 2013, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | 0 | N/A | 0 | N/A | 1 | Baseline for 11 is 100. LMR radio installation has continued. Additional MOUs have been received from hospitals and emergency medical agencies requesting LMR installation. | 39 | Baseline for Q11 is 100%. Payment milestones related to microwave installation in Phase 3 have been achieved during Q1, 2013, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | 83 | Baseline for Q11 is 97%. Payment milestones related to microwave installation in Phase 3 have been achieved during Q4, 2012, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | 43 | Baseline for Q11 is 89%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. | 0 | Baseline for Q11 is 88%. Specific items in the initial baseline were reclassified and removed from the category. | 2013-05-13 14:43 | 2013-05-13 14:43 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2013 | Q2 | Q2 - 2013 | 10299 | 8766 | TRUE | 49 | Baseline for Q12 is 100%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Payment milestones for the installation of 20 LTE antenna arrays on MSWIN sites, the delivery of the LTE core to the ITS data center in MS, the installation of 20 new microwave links, the acceptance of the Detailed Design Plan for Phase 3 of the MSWIN system. | 62 |  | Baseline for Q12 is 100%. Payment milestones for the installation of 20 LTE antenna arrays on MSWIN sites and the installation of 20 new microwave links. | 0 | N/A | 51 | Baseline for Q12 is 100%. Payment milestones for the installation of 20 LTE antenna arrays on MSWIN sites, the installation of 20 new microwave links, the acceptance of the Detailed Design Plan for Phase 3 of the MSWIN system. | 0 | N/A | 0 | N/A | 1 | Baseline for Q12 is 100%.Disassemble work station and glass wall | 41 | Baseline for Q12 is 100%. WCC: Payment Milestones were met for the delivery of the LTE core to the ITS data center in MS MedCom: - Modems and fees for RFP development, Nice recorder. | 86 | Baseline for Q12 is 100%. Payment milestones for the installation of 20 LTE antenna arrays on MSWIN sites and the installation of 20 new microwave links, | 44 | Baseline for Q12 is 100%. Payment Milestones were met for the delivery of the LTE core to the ITS data center in MS | 0 | Baseline for Q12 is 100%. Specific items in the initial baseline were reclassified and removed from the category. | 2013-07-30 10:56 | 2013-07-30 10:56 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2013 | Q3 | Q3 - 2013 | 11409 | 9522 | TRUE | 54 | Baseline is 100%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Payment milestones for work accomplished prior to May 11, 2012, were processed. This includes payment for the installation of 29 new microwave links, microwave integration milestones for 43 sites and the acceptance of the microwave for Phase 3 of the MSWIN system. | 78 |  | Baseline is 100%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Payment milestones for work accomplished prior to May 11, 2012, were processed. This includes payment for the installation of 29 new microwave links, microwave integration milestones for 43 sites and the acceptance of the microwave for Phase 3 of the MSWIN system. | 0 | N/A | 61 | Baseline is 100%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Payment milestones for work accomplished prior to May 11, 2012, were processed. This includes payment for the installation of 29 new microwave links, microwave integration milestones for 43 sites and the acceptance of the microwave for Phase 3 of the MSWIN system. | 0 | N/A | 0 | N/A | 1 | Baseline is 100%. MedCom: Physical site upgrades continue. Lighting and power plugs converted to emergency power. Quotes obtained for fire-caulking for wall penetrations. | 45 | Baseline is 100%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Payment milestones for work accomplished prior to May 11, 2012, were processed. This includes payment for the installation of 29 new microwave links, microwave integration milestones for 43 sites and the acceptance of the microwave for Phase 3 of the MSWIN system. | 95 | Baseline is 100%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Payment milestones for work accomplished prior to May 11, 2012, were processed. This includes payment for the installation of 29 new microwave links, microwave integration milestones for 43 sites and the acceptance of the microwave for Phase 3 of the MSWIN system. | 44 | Baseline is 100%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. As a result of this suspension, no equipment was deployed during this quarter. | 0 | Baseline is 100%.Budget modification removed this category as a tracking component of the Grant reporting. | 2013-11-26 16:50 | 2013-11-26 16:50 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2013 | Q4 | Q4 - 2013 | 11707 | 9846 | TRUE | 54 | Baseline is 100%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. No payment milestones for work accomplished prior to May 11, 2012, were processed. | 78 |  | Baseline is 100%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. No payment milestones for work accomplished prior to May 11, 2012, were processed. | 0 | N/A | 61 | Baseline is 100%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. No payment milestones for work accomplished prior to May 11, 2012, were processed. | 0 | N/A | 0 | N/A | 2 | Baseline is 100%. Installation of door, firecaulking of wall penetrations and electrical upgrades | 45 | Baseline is 100%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. No payment milestones for work accomplished prior to May 11, 2012, were processed. Med-Com: Med-Com: Revision of drawdowns 7 and 8 to include PSAP phone system and additional phone line cards, radio programming, console purchase and installation, legal counsel fees for RFP development, Microwave purchase and installation. | 95 | Baseline is 100%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. No payment milestones for work accomplished prior to May 11, 2012, were processed. | 44 | Baseline is 100%. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. No payment milestones for work accomplished prior to May 11, 2012, were processed. | 0 | Baseline is 100%. Budget modification removed this category as a tracking component of the Grant reporting. | 2014-01-30 10:45 | 2014-01-30 10:45 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570095 | 2010 | Q4 | Q4 - 2010 | 1019 | 2064 | TRUE | 3 | N/A | 0 | N/A | N/A | 50 | N/A | 50 | N/A | 50 | N/A | 50 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-09 12:25 | 2011-02-09 12:25 | 5990 | 5990 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2011 | Q1 | Q1 - 2011 | 1923 | 2707 | TRUE | 4 | Finding of No Significant Impact (FONSI) has been delayed beyond the projected time, decreasing the activities that could be undertaken. | 0 | N/A | N/A | 50 | Miscommunication delayed Tribal notification of proposed antennae collocations. Responses to initial Environmental Assessment (EA) draft were slower being returned than anticipated and significant volumes of redundant data was requested to be presented in different formats. 50% of the Environmental Assessment budget has been expended to match with the 50% completion during this 1st quarter 2011. The remaining 50% will be billed upon receipt of FONSI. | 75 | Request by the Federal Communications Commission (FCC) for a structural analysis to the proposed in kind towers and research required to determine if Federal Emergency Management Agency (FEMA) had completed the required EA at time of construction caused delays in finalization of the wireless network. | 50 | 50% of funds have been expended at the end of March 2011. The variance is weighed upon delays from the Engineering Firm and the Alabama Department of Transportation redline responses and requirements. | 50 | US Forestry Service lost our initial application, delays in acquiring permits to cross National Forrest property on existing state highway. | 0 | N/A | 0 | Delay in FONSI has delayed this activity. RFP's have been completed and vendors identified. Recent guidance from the BTOP Program Manager will allow pre-budget amendments. These amendments will allow JKM to order and secure materials and equipment during the April 1, 2011-June 30, 2011 quarter. | 1 | Delay in FONSI has delayed this activity. RFP's have been issued and vendors are preparing responses. If FONSI is delayed more than 30 additional days and if lead time on the fiber continues to increase, we may have to award bid to multiple contractors in order to insure on time completion. | 0 | N/A | 0 | N/A | 2011-05-10 11:56 | 2011-05-10 11:56 | 5990 | 5990 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2011 | Q2 | Q2 - 2011 | 2953 | 3234 | TRUE | 7 | Finding of No Significant Impact (FONSI) has been delayed beyond the projected time, decreasing the activities that could be undertaken. | 0 |  | N/A | 100 | N/A | 85 | N/A | 75 | Engineering issues have delayed some Alabama Department of Transportation (AlDOT) right of way (ROW) approvals and a requirement to make minor route adjustments. | 50 | Engineering issues have delayed some Alabama Department of Transportation (AlDOT) right of way (ROW) approvals and a requirement to make minor route adjustments. Additionally, US Forestry Service failed to advertise for public comment and had to start approval perios over as well as requesting additional data causing delays in receiving this permit. | 0 | N/A | 0 | N/A | 2 | Finding of No Significant Impact (FONSI) has been delayed beyond the projected time, decreasing the activities that could be undertaken. | 0 | N/A | 0 | N/A | 2011-08-08 13:44 | 2011-08-08 13:44 | 5990 | 5990 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2011 | Q3 | Q3 - 2011 | 4197 | 3947 | TRUE | 9 | Delays associated with receipt of the FONSI decreased the activities that could be undertaken up to this point. Worldwide fiber shortage has delayed start of fiber construction - we also suffered delays due to another default by our fiber supplier. Equipment procurement was initiated this quarter. | 0 |  | N/A | 100 | Complete | 85 | Changes in network design are pending engineering review. A new engineering firm was sought to correct the poor performance of the initial engineering firm selected. | 76 | US Forestry Service required additional environmental impact study in addition to the Environmental Assessment. Due to additional requirements for National Forest public right of way and corrections required for engineering, the percentage in this area will not reflect a significant change until next quarter. | 77 | Several permit applications are requiring additional work due to poor quality from the original engineering firm. Additional delays in permitting due to the US Forestry Service. Engineering revisions will speed this process in the upcoming quarter. | 0 | N/A | 0 | First delivery of fiber construction equipment arrived on site September 27, 2011. However, the Request for Proposal on Optronics is scheduled for next quarter. | 2 | Network builds have been delayed due to the shortage of fiber availability. IRU agreements have been delayed due to significant partner changes this quarter and the time leading up to the announcement of these changes. | 0 | Worldwide fiber shortage has delayed start of fiber construction. | 0 | N/A | 2011-11-21 17:01 | 2011-11-21 17:01 | 5990 | 5990 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2011 | Q4 | Q4 - 2011 | 4899 | 4588 | TRUE | 24 | Previous reports detailed the delays with Finding of No Significant Impact (FONSI) and tsunami issues for fiber delivery. Additionally, even the new fiber vender was 2 weeks late delivering the fiber. Winter weather delays have slightly effected progress. | 0 |  | N/A | 100 | N/A - complete | 90 | Previous reports detailed the delays with FONSI and tsunami issues. Design is being held open to accommodate changes required by construction issues. Additional changes may be driven by Community Anchor Institutions (CAI) changes and Federal Communications Commission (FCC) rule changes to the wireless component. | 85 | Previous reports detailed the delays with FONSI and tsunami issues. Additional delays in permitting have been driven by poor performance of original engineering firm; staff shortages in Alabama Department of Transportation (DOT); previously unplanned road construction and construction driven changes. | 85 | Previous reports detailed the delays with FONSI and tsunami issues. Additional delays in permitting have been driven by staff shortages in Alabama DOT; previously unplanned road construction and construction driven changes. | 0 | n/a | 0 | Network construction has been delayed as noted above reducing the requirement to purchase equipment earlier. However, equipment Request for Proposals were initiated and closed this quarter. Selection has been narrowed to three vendors. | 19 | Previous reports detailed the delays with FONSI and tsunami issues. Additional delays in permitting have been driven by staff shortages in Alabama DOT; unplanned road construction and construction driven changes. | 0 | N/A | 0 | N/A | 2012-02-07 12:02 | 2012-02-07 12:02 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2012 | Q1 | Q1 - 2012 | 6261 | 5733 | TRUE | 33 | Previous reports detailed the delays with Finding of No Significant Impact (FONSI) and tsunami issues for fiber delivery. Additionally, even the new fiber vender was 2 weeks late delivering the fiber. Winter weather delays have slightly effected progress | 0 | N/A | N/A | 100 | N/A - complete | 90 | Previous reports detailed the delays with FONSI and tsunami issues. Design is being held open to accommodate changes required by construction issues. Additional changes may be driven by Community Anchor Institutions (CAI) changes and Federal Communications Commission (FCC) rule changes to the wireless component. | 85 | Previous reports detailed the delays with FONSI and tsunami issues. Additional delays in permitting have been driven by poor performance of original engineering firm; staff shortages in Alabama Department of Transportation (DOT); previously unplanned road construction and construction driven changes. | 85 | Previous reports detailed the delays with FONSI and tsunami issues. Additional delays in permitting have been driven by poor performance of original engineering firm; staff shortages in Alabama Department of Transportation (DOT); previously unplanned road construction and construction driven changes. | 0 | N/A | 8 | Network construction has been delayed as noted above reducing the requirement to purchase equipment earlier. Purchase orders have been issued. Equipment delivery and invoicing will be reflected in 2nd quarter reporting for significant changes to this milestone. | 45 | Previous reports detailed the delays with FONSI and tsunami issues. Additional delays in permitting have been driven by staff shortages in Alabama DOT; unplanned road construction and construction driven changes. Second quarter reporting will reflect IRU of 26 miles, following acceptance testing incomplete at end of 1st quarter. | 0 | Delays in network construction have delayed equipment deployment. Equipment has been order and deployment will commence in 2nd quarter 2012. | 0 | N/A | 2012-05-23 11:09 | 2012-05-23 11:09 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2012 | Q2 | Q2 - 2012 | 6837 | 6045 | TRUE | 65 | On track with PIP filed in first quarter | 0 |  | N/A | 100 | N/A | 90 | On track with PIP filed in first quarter | 90 | On track with PIP filed in first quarter | 85 | On track with PIP filed in first quarter | 0 | N/A | 30 | On track with PIP filed in first quarter | 70 | On track with PIP filed in first quarter | 30 | On track with PIP filed in first quarter | 10 | On track with PIP filed in first quarter | 2012-08-02 12:22 | 2012-08-02 12:22 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2012 | Q3 | Q3 - 2012 | 7773 | 6584 | TRUE | 80 | On track with PIP filed in first quarter | 0 |  | N/A | 100 | N/A | 95 | On track with PIP filed in first quarter | 95 | On track with PIP filed in first quarter | 90 | On track with PIP filed in first quarter | 0 | N/A | 35 | On track with PIP filed in first quarter | 75 | On track with PIP filed in first quarter | 35 | On track with PIP filed in first quarter | 25 | On track with PIP filed in first quarter | 2012-11-06 12:02 | 2012-11-06 12:02 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2012 | Q4 | Q4 - 2012 | 8983 | 7762 | TRUE | 92 | On track with PIP filed in first quarter | 0 |  | N/A | 100 | N/A | 99 | On track with PIP filed in first quarter | 99 | On track with PIP filed in first quarter | 98 | On track with PIP filed in first quarter | 0 | N/A | 65 | On track with PIP filed in first quarter | 80 | On track with PIP filed in first quarter | 50 | On track with PIP filed in first quarter | 50 | On track with PIP filed in first quarter | 2013-02-26 15:09 | 2013-02-26 15:09 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2013 | Q1 | Q1 - 2013 | 9951 | 8520 | TRUE | 97 | On track with PIP filed in first quarter | 0 |  | N/A | 100 | N/A | 100 | On track with PIP filed in first quarter | 100 | On track with PIP filed in first quarter | 100 | On track with PIP filed in first quarter | 0 | N/A | 99 | On track with PIP filed in first quarter | 98 | On track with PIP filed in first quarter | 92 | On track with PIP filed in first quarter | 75 | On track with PIP filed in first quarter | 2013-05-28 20:29 | 2013-05-28 20:29 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2013 | Q2 | Q2 - 2013 | 10549 | 8929 | TRUE | 99 | On track to complete project on time | 0 |  | N/A | 100 | On track to complete project on time | 100 | On track to complete project on time | 100 | On track to complete project on time | 100 | On track to complete project on time | 0 | N/A | 99 | On track to complete project on time | 99 | On track to complete project on time | 99 | Due to issues with radio equipment manufacturer, WiMax equipment deployment may be in jeopardy of completion . | 99 | On track to complete project on time | 2013-08-09 18:22 | 2013-08-09 18:22 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2013 | Q3 | Q3 - 2013 | 11947 | 10117 | TRUE | 100 | N/A | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 2014-03-13 17:04 | 2014-03-13 17:04 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570096 | 2010 | Q4 | Q4 - 2010 | 1379 | 2392 | TRUE | 0 | N/A | 0 |  | N/A | 0 | The EA has progressed extremely well. All FAP locations and conduit routes that will require road work have been verified. Modifications to place most FAP sites on Government of the Virgin Islands' property has been made. Historical and Cultural analysis is underway and approximately more than 50% complete. We are on schedule to complete the draft EA by the scheduled deadline of January 31, 2011 or sooner. No funds has been spent since the contract with the EA consultant has not been finalized, however, the EA consultant continued to work towards completion of the EA draft by January 31st. We fully expect to finalize this contract by next month. | 0 | Field verification of FAP sites and fiber routes verified by the EA consultant has begun. Engineering Design Consultant has begun collecting and verifying data from WAPA on in-kind assets (conduits and poles spaces) that are to contributed by WAPA. Engineering firm has developed preliminary grid maps for further detailing into 11x17 full street level detail maps for the network. No funds has been spent since the contract with the Engineering & Design consultant has not been finalized, however, we fully expect to finalize this contract by next month. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-25 16:57 | 2011-02-25 16:57 | 5238 | 5238 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2011 | Q1 | Q1 - 2011 | 2235 | 2863 | TRUE | 2 | Invoices for March 2011 were not yet received from the Engineering Consultant for their construction design activities. However, we will make up any variance since most of the field verification activities have been completed. This information has been passed onto to the design team to update the construction drawings. | 0 |  | No variance from baseline plan | 100 | The final EA has been submitted and we are awaiting a FONSI. | 7 | The field verification process has progressed slower than anticipated due to the time taken to negotiate the contract with the engineering firm and for them to fully mobilize their work crews from the mainland and hire additional local staff. However, we will make up the variance during the quarter by adding more manpower on the ground doing the field engineering work. We are executing as many tasks in parallel as our current man-power can sustain. | 0 | Access to a vast majority of properties owned by the Virgin Islands government has been granted and at no cost since the network and FAPs are primarily located on Government of the Virgin Islands properties. 100% of the underground network is on central Government of the Virgin Islands properties. About 50% of the FAPs are on central Government of the Virgin Islands properties. About 45% of the FAPs are on semiautonomous Government Agency properties. About 5% of the FAPs are on private properties. 100% of the aerial network is on WAPA poles that have been granted to viNGN/PFA through their in-kind contribution. All of the underground routes and all of the central GVI FAP sites have been memorialized via MOUs. The other FAP sites are in the process of being granted ROW access through MOUs, easement, or outright purchase in the case of the private owner properties. To the extent possible, we may seek to have the cost savings from the rights-of-way reclassified as in-kind contribution fr | 0 | FAP sites are currently being surveyed. Once completed, this information will be turned over to the FAP Architect who will complete the permitting application for construction of the FAPs. Construction permits for the main underground conduit systems are underway; however, the construction engineering drawings have not yet been received. Despite the delays in receiving the construction engineering drawings we are following a batch approach to submitting our permits for the process. This will also quickly allow us to make up this deficit and get back on track and possibly get ahead. We are also trying to minimize the need for Tier 1 CZM process for a couple of small sections of the network. We will have a determination by May 23, 2011. All of the road construction permits are being submitted on May 23, 2011. The FAP permits will be submitted as the designs and site plans are completed on a FAP by FAP basis; however hopefully we can batch the FAP sites as much as possible. We will anti | 0 | FAP sites are currently being surveyed. Once completed, this information will be turned over to the FAP Architect who will complete the permitting application for construction of the FAPs and site preparation can begin. The delays were caused from using a batching approach to obtaining ROW for groups of properties for the roads and the FAP sites. We anticipate having most of this in place in the upcoming quarter which will allow us to meet or exceed planned objectives. | 2 | We have not yet finalized our collocation agreements that will allow us to place some of our network switch gear in the respective cages as we had anticipated. We also do not want to place our equipment prematurely since the monthly cost for leasing space and other monthly costs will begin to impact the network long before we can generate income. Once the construction of the local FAPs begin we also anticipate that we will make up this variance very easily with the placement of network equipment in our own FAPs. A lot of work went into first verifying and validating the cost per MG that was a result of the original interconnection approach submitted in the grant application. Once it was determined that the original approach would no longer have allowed us to implement a successful wholesale broadband strategy at a price point to attract local or new last mile providers, we had to quickly scramble to devise an alternative approach. We expect to present our IRU/Lease/Construction contr | 0 | No variance from baseline plan | 0 | No variance from baseline plan | 0 | No variance from baseline plan | 2011-05-20 22:56 | 2011-05-20 22:56 | 5238 | 5238 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2011 | Q2 | Q2 - 2011 | 3375 | 3451 | TRUE | 4 | The major reasons for the variance from the base plan include the process time required for documentation justifying the route change modifications we submitted. Also, we have not yet concluded our negotiation with VIWAPA for the use of their in-Kind assets. | 0 |  | The baseline plan states 15%. Achievement against this milestone is directly related to supporting activities for the direct build out, equipment deployment, and IRU purchase completion. Once these related items are back on track, then activities under this category will be once again on schedule. | 100 | No Variance from the base line plan. | 22 | Billings from our Engineering Firm, AEG are lagging. With the constriction of cash flow, we have been slow to fund some tasks. | 0 | We have a reduction in expenditures in this category since a decision has been made to locate over 80% of FAP sites on Government property. this will reduce the need to expend major funds in this category. From a project perspective this indicator is not behind but the project is behind financially for this category. | 95 | Our ability to submit many of the permits requests together has put us ahead of schedule on this milestone. | 0 | Although we are behind in this category (0% versus the 35% planned completion), we intend to be on pace over the next quarter, since these site preparations were submitted and in batches. | 2 | Contract negotiations with the major equipment vendor were delayed due to several factors including scope of work finalization, delivery milestones, and carrier ethernet equipment orders. | 0 | Although there is a variance here (0% versus the planned 15%), we will catch up once construction starts due to the many existing facilities that will come on board once the WAPA MOU is executed. | 0 | This variance of 10% is directly attributable to the delays in equipment negotiations and ordering. We expect to erase the variance in the upcoming quarter. | 0 | Our baseline plan of 10% has been impacted by the equipment and network build delays. Achievement of this milestone will ameliorate as milestones 2h and 2i progress. | 2011-08-30 12:45 | 2011-08-30 12:45 | 5238 | 5238 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2011 | Q3 | Q3 - 2011 | 4363 | 4038 | TRUE | 10 | Though our overall percentage completion improved from Quarter 2, CY 2011, we have under performed against this baseline milestone mainly due to general delays in procurements related to construction activities and delays in issuing RFPs for services. These delays were cumulative and were further exacerbated by the effects of the stop work order. Despite these challenges, progress has been made under the project, as reflected in the accomplishments that are outlined in Item #1 above and based on total expenditures incurred to date. | 0 |  | We have under performed against this baseline milestone due to the reasons noted in 2a. through 2j above. | 95 | The percentage of completion has been modified from what was reported during Quarter 2, CY 2011 due to minor location changes for a few FAPs and location finalization needed for a few beach manhole landings. | 75 | Though our percentage completion improved from Quarter 2, CY 2011, we have under performed against this baseline milestone because additional design work is required for the FAP and beach manhole landing relocations. | 75 | No variance from the baseline plan | 90 | We have over performed against the baseline milestone; however, the percentage of completion has been modified from what was reported during Quarter 2, CY 2011 due to the few FAP and beach manhole landing relocations. | 0 | We have under performed against this baseline milestone primarily due to impediments in the procurement process which led to construction delays, which were, in turn, exacerbated by the stop work order. The general delay in all aspects of construction impacted our ability to perform any site preparation during this reporting period. Construction documents have been finalized for the two super Fiber Access Points (FAPS), and RFPs have been issued and accepted for the construction of these facilities. The evaluation of these bids has been suspended and will resume, once remaining issues related to the CAP are addressed. Final design of the first ten regular FAPs has also been completed, and further design work has been suspended also until the issues related to the CAP are addressed. | 3 | Though our percentage completion improved from Quarter 2, CY 2011,we have under performed against this baseline milestone primarily due to delays in finalizing contract negotiations, related largely to delivery milestones. Negotiations were further delayed by the stop work order. | 5 | Our percentage completion improved from Quarter 2, CY 2011 due to the full execution of the comprehensive MOU with WAPA. Though our percentage completion improved from Quarter 2, CY 2011, we have under performed against this baseline milestone due to delays in finalizing IRU negotiations and delays related to the commencement of trenching activities. | 0 | We have under performed against this baseline milestone primarily due to impediments in the procurement process which led to construction delays, which were, in turn, exacerbated by the stop work order. The general delay in all aspects of construction impacted our ability to deploy any equipment under this project during this reporting period. | 2 | Though our percentage completion improved from Quarter 2, CY 2011, we have under performed against this base line milestone due to delays in sourcing a vendor and finalizing a contract. We now have a fully executed contract with the vendor, UDT. | 2011-11-30 22:11 | 2011-11-30 22:11 | 6449 | 6449 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2011 | Q4 | Q4 - 2011 | 5421 | 5108 | TRUE | 30 | Though VIPFA/viNGN's overall percentage completion improved from Quarter 3, CY 2011, under performance against this baseline milestone is due to 1) the simultaneous transition of the implementation of the VIPFA/viNGN's four BTOP projects to a new management team, the majority of whose members are new to the VIPFA and viNGN, 2) restarting the projects during an implementation period that was shorter by nearly three weeks due to the stop work order that was not lifted until October 17, 2011, 3) resulting delays in procurement activities related to construction activities and services, and 4) the need to relocate a few FAPS. Despite these challenges, the team has mobilized and made progress towards meeting the baseline milestone targets. The combination of the accomplishments that are outlined in Item #1 above and total expenditures incurred to date document the achievements made by the new management team during a very short period of time. Significant progress is expected during the nex | 0 |  | The VIPFA/viNGN team has mobilized and made progress towards meeting the Baseline milestone targets. The combination of the accomplishments that are outlined in Item #1 above and total expenditures incurred to date document the achievements made by the new management team during a very short period of time, despite facing the many challenges outlined in 2a. through 2j. above. Significant progress is expected during the next two quarters. | 95 | The VIPFA/viNGN team is very near to meeting the baseline milestone of 100%. The team is awaiting the finalization of the engineering design plans and approvals and the environmental assessments for the location changes for a few of the FAPs. The team anticipated a need to also relocate beach manhole landings, which would have led to the need for additional environmental assessments and further delays; however, a determination was made that there was no need to move beach landing sites. Given the need to still relocate a few FAPs, some delays are still anticipated. | 90 | Though the percentage completion improved from Quarter 3, CY 2011, the VIPFA/viNGN team is still awaiting the finalization of the engineering design plans and approvals and the environmental assessments for the location changes for a few of the FAPs, make-ready pole design engineering, and engineering associated with the "meet-me points" at the beach manholes (BMHs). The team anticipated a need to also relocate beach manhole landings, which would have led to further delays; however, a determination was made that there was no need to move beach landing sites. Given the need to still relocate a few FAPS, delays are still anticipated. | 75 | The team is in the process of obtaining the rights of way between the FAPs (including those that must be relocated), beach manholes (BMHs) and the community anchor institutions (CAIs) / anchor tenants. | 90 | The VIPFA/viNGN team is still awaiting the finalization of the engineering design plans and approvals and the environmental assessments for the location changes for a few of the FAPs, make-ready pole design engineering, and engineering associated with the "meet-me points" at the beach manholes (BMHs). The team anticipated a need to also relocate beach manhole landings, which would have led to further delays; however, a determination was made that there was no need to move beach landing sites. Given the need to still relocate a few FAPs, delays are still anticipated. | 0 | Contracts have been signed, and limited notices to proceed have been issued for the two SuperFAPs, one on St. Croix and one on St. Thomas. The procurement process has commenced for the first six (6) regular FAPs, with three (3) on St. Thomas and three (3) on St. Croix, and engineering designs have been completed for an additional four (4) regular FAPs. Under performance against this baseline indicator is due to 1) restarting the projects during an implementation period that was shorter by nearly three weeks due to the stop work order that was not lifted until October 17, 2011, 2) resulting delays in procurement, construction and other project implementation activities, and 3) the simultaneous transition of the implementation of the VIPFA/viNGN's four BTOP projects to a new management team. As VIPFA/viNGN begins its excavation, trenching and fiber pulling activities and continues with the SuperFAP and regular FAP construction through Quarter 2, CY 2012, the team will coordinate with | 10 | The percentage completion against this baseline milestone target improved from Quarter 3, CY 2011, as the team purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network. Delays have been experienced in finalizing contract negotiations for sourcing fiber, as suppliers of fiber face difficulties in meeting delivery milestones. | 10 | The percentage completion against this baseline milestone target improved from Quarter 3, CY 2011, as a fifteen (15) year IRU and collocation agreements for New York City and Miami were signed with Global Crossing/Level 3. Delays are anticipated in the core network build out until excavation and trenching activities commence during the next two quarters. As VIPFA/viNGN begins its excavation, trenching and fiber pulling activities and continues with the SuperFAP and FAP construction through Quarter 2, CY 2012, the team will coordinate with contractors to work on accelerated schedules. Contractor oversight will include, at a minimum, weekly site visits and meetings with individual contractors and monthly meetings with all contractors who are working through VIPFA/viNGN's CCI project. Meeting discussion topics will include construction status against the implementation schedule, performance against the Baseline Milestones and Indicators, approaches to accelerate construction activities, | 0 | Under performance against this baseline indicator is due to 1) restarting the projects during an implementation period that was shorter by nearly three weeks due to the stop work order that was not lifted until October 17, 2011, 2) resulting delays in procurement, construction and other project implementation activities, and 3) the simultaneous transition of the implementation of the VIPFA/viNGN's four BTOP projects to a new management team. As VIPFA/viNGN begins its excavation, trenching and fiber pulling activities and continues with the SuperFAP and FAP construction through Quarter 2, CY 2012, the team will coordinate with contractors to work on accelerated schedules to build out the network and deploy eequipment. | 3 | The percentage completion against the baseline milestone target improved from Quarter 3, CY 2011, as the initial alpha testing of the network's core gateway routers in a lab environment was completed. Network testing will be ongoing in alignment with equipment purchases and network build out. | 2012-02-29 19:00 | 2012-02-29 19:00 | 7323 | 7323 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2012 | Q1 | Q1 - 2012 | 6349 | 5777 | TRUE | 31 | The VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite experiencing delays in the build-out of the infrastructure during Quarter 1, CY 2012, which resulted in a very modest improvement in its overall percentage completion from Quarter 4, CY 2011. Under performance against this baseline milestone is due to the fact that the new management team is reviewing the project schedule and reassessing some of the business decisions that were made by the former management team, including: 1) the phasing of the construction; 2) the type and number of manholes to be utilized and installed; and 3) the timing of the procurement of long lead items, e.g. additional fiber. As a result of this reassessment, the issuance of the solicitations for construction administration and inspection services, trenching, fiber pulling and splicing for existing underground conduit, and aerial fiber pulling and splicing was delayed. The team also experienced delays in fi | 0 |  | The VIPFA/viNGN team has made progress towards meeting the Baseline milestone targets. The combination of the accomplishments that are outlined in Item #1 above and total expenditures incurred to date document the achievements made by the new management team during a very short period of time, despite facing some delays in the implementation, as outlined in 2a. through 2h. above. Significant progress is expected during the next two quarters. | 95 | The VIPFA/viNGN team is very near to meeting the baseline milestone of 100%. The team is awaiting final engineering design plans and approvals and related environmental assessments for minimal location changes for a few of the FAPs and beach manhole landings. The assessment of the final location of a few FAPs and beach manhole landings is in the final stages, and completion of the assessment and the related designs are anticipated during Quarter 2, CY 2012. | 90 | The VIPFA/viNGN team is in the final stages of making adjustments in the design of the network to include reducing the number of FAPs and the number of underground conduits. These changes will not impact the capacity of the network or its effectiveness, and no additional route changes are anticipated. These changes will positively impact the implementation of the project and its "sustainability" by reducing the time needed to build the network, construction costs, and ongoing operational and maintenance costs. | 75 | The team is in the process of obtaining the rights of way between the FAPs (including those that must be relocated), beach manholes (BMHs) and the community anchor institutions (CAIs) / anchor tenants. Because a few FAP locations and BMH landings are being reassessed and designed, the rights of way will be adjusted once the designs have been approved and any environmental assessments completed. Completion of the assessment and the related designs are anticipated during Quarter 2, CY 2012, and the rights of way should be finalized during the following quarter. | 91 | The VIPFA/viNGN team has obtained 25% of the construction permits for the FAPs; an additional 40% of the approvals are expected during Quarter 2, CY 2012. The team is awaiting the final engineering design plans and approvals and the environmental assessments for the location changes for a few of the FAPs and Beach manhole landings. Construction permits and other approvals will be obtained after these are finalized and approved. | 1 | Contracts have been signed, and construction has begun on the two (2) SuperFAPS, one on St. Croix and one on St. Thomas. Significant progress has been made. The site preparation for both of these FAPs is complete. Construction of the St. Thomas FAP is more than 60% complete, and the St. Croix FAP is more than 20% complete. Completion of the St. Croix FAP was expected to take longer, as there is considerably more site preparation and there are special design and construction requirements that were mandated by the State Historic Preservation Officer (SHPO). Completion of the construction of both of the SuperFAPS is expected by late Quarter 2, CY 2012/early Quarter 3, CY 2012. VIPFA/viNGN also concluded a competitive procurement process to select contractors to construct six FAPs, three each on St. Thomas and St. Croix. The team obtained the building permits and is prepared to issue Notices to Proceed immediately after the construction contracts have been finalized. Construction is exp | 85 | The VIPFA/viNGN team has made significant progress in its equipment procurement activities and has now exceeded the percentage completion against this baseline milestone target. The team has purchased more than 90% of the network management equipment needed for the build-out of the network. The team is awaiting delivery and final testing of these routers and switches to begin the staging for the placement of the equipment. Once the SuperFAPs and FAPs are built, the routers and switches will be installed to await final connection to the fiber to bring the network on line. Further, the team purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network during the past quarter. | 10 | Significant progress has been made with the construction of the two SuperFAPs; completion of the construction of the SuperFAPs is expected during late Quarter 2, CY 2012/early Quarter 3, CY 2012. Once they are completed, progress against this milestone will improve. Delays are anticipated in the core network build out until excavation and trenching and aerial and underground fiber pulling and splicing activities commence during the next two quarters and until the lease agreement for the SONET OC-48 with AT&T to connect St. Thomas and St. Croix is executed. Based on the status of current negotiations with AT&T, the agreement is expected to be fully executed during Quarter 2, CY 2012. A fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami were signed with Global Crossing/Level 3 during the past quarter. | 0 | Given that 1) VIPFA/viNGN has purchased a large portion of the network management equipment, 2) significant progress has been made with the construction of the two SuperFAPs, 3) the construction of the SuperFAPs is expected to be completed during late Quarter 2, CY 2012/early Quarter 3, CY 2012, 4) construction of the remaining FAPs is expected to begin during Quarter 2, CY 2012, 5) fiber pulling and splicing in underground conduit is expected to begin during Quarter 3, CY 2012, and 6) aerial fiber pulling and splicing is expected to begin during Quarter 3, CY 2012, progress against this milestone will improve during the next two quarters, as the equipment can be deployed with the start and completion of these activities. | 3 | Network testing will be ongoing in alignment with equipment purchases and network build out. The initial alpha testing of the network's core gateway routers in a lab environment was completed during Quarter 4, CY 2011. No testing was carried out during Quarter 1, CY 2012; however, with the purchase of a large portion of the network management equipment during Quarter 1, CY 2012 and the planned completion of construction of the SuperFAPs by late Quarter 2, CY 2012/early Quarter 3, CY 2012, final testing and staging for placement of the routers and switches will begin during the latter part of Quarter 2, CY 2012 or early in Quarter 3, CY 2012. Once the FAPs are built, the routers and switches will be installed to await final connection to the fiber to bring the network on line. | 2012-05-30 13:06 | 2012-05-30 13:06 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2012 | Q2 | Q2 - 2012 | 7257 | 6256 | TRUE | 32 | The current VIPFA/viNGN team has implemented a recovery plan to address delays in the construction schedule and to ensure that the network will be built-out by June/July 2013. In addition, with increased communication between supporting entities, the RFPs for Trenching, the RFPs for Pulling and Splicing Fiber in new and existing conduits and the RFPs for Aerial Construction will be released during Quarter 3, CY 2012. Additionally, AEG's contract is being amended to restore the overall project management support that was removed from the contract scope of work earlier this year. The team intends to implement strategies discussed during Quarter 2, CY 2012 to accelerate the network build without creating a cost-prohibitive environment. Significant progress is expected during the next two quarters, as the team finalizes several key solicitations, implements resolutions to the past impediments to the network build-out, executes contracts more expeditiously, begins the excavation, begins tr | 0 |  | The VIPFA/viNGN team has made progress towards meeting the Baseline Milestone targets. The combination of the accomplishments that are outlined in Item #1 above and total expenditures incurred to date document the achievements made by the new management team during a very short period of time, despite facing some delays in the implementation, as outlined in 2a. through 2h. above. Significant progress is expected during the next two quarters. | 95 | The VIPFA/viNGN team began to renegotiate a Survey Company Contract during Quarter 2, CY 2012 and expects to finalize it during Quarter 3, CY 2012. The team is also awaiting final engineering design plans and approvals and related environmental assessments for location changes for a few of the FAPs. These assessments are scheduled to be completed during Quarter 3, CY 2012. | 98 | The VIPFA/viNGN team completed its reassessment of the network design and made final decisions regarding adjustments in the design during Quarter 2, CY 2012. The design changes, including reductions in the number of FAPs, reductions in the number of conduits and a reduction in the size of the manholes will not impact the capacity of the network or its effectiveness. The changes will, however, positively impact the implementation of the project by 1) reducing the time needed to build the network and address points of failure and 2) reducing construction costs, as well as ongoing operational and maintenance costs. | 90 | During Quarter 2, CY 2012, FAP locations were being reassessed and the network redesigned. VIPFA/viNGN was in the process of renegotiating a Survey Company Contract during late Quarter 2, CY 2012. The remainder of Environmental assessments are anticipated to be completed during Quarter 3, CY 2012. | 91 | No additional FAP Building Permits were received during Quarter 2, CY 2012. During the quarter, a a few FAPs were identified as needing to be re-located which required the preparation of new surveys and architectural drawings. During the quarter, the company also completed a FAP Rationalization Study which led the team to decide to reduce the total number of FAPs from 38 to 26. The reduction in the number of FAPs will not impact the operational efficiency of the network but will reduce costs and improve the schedule to completion. The reduction in the number of FAPs will also result in fewer FAP Building Permits being required. | 12 | Construction of the two Super FAPs (Facility Access Points), one on St. Thomas and one on St. Croix, is well underway and near completion. Final details, such as adding permanent power, alarms system, and landscape details, are in process and will be completed during Quarter 3, CY 2012 for both Super FAPs. Construction has also begun on one (1) regular FAP on St. Croix, with anticipated completion during Quarter 3, CY 2012. At the end of the quarter, the team was reviewing Requests for Proposals (RFPs) for six (6) FAPs and expects to award these contracts during Quarter 3, CY 2012. RFPs for the installation of underground conduit, excavation, aerial and underground fiber pulling and spicing will be released during Quarter during Quarter 3, CY 2012, and site preparation for all of these activities will follow shortly thereafter. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules. The team will also continue to engage in active oversight of all proj | 90 | The VIPFA/viNGN team has made significant progress in its equipment procurement activities and has now exceeded the percentage completion against this Baseline Milestone target. During Quarter 2, CY 2012, the team received the routers and switches needed to begin the staging for the placement of the equipment. Once permanent power is installed in the Super FAPs and the other FAPs are built, the routers and switches will be installed to await final connection to the fiber to bring the network on line. Further, the team has purchased all of the needed fiber optic cable and is awaiting delivery of the final order, which is expected during Quarter 3, CY 2012. | 15 | The lease agreement for the SONET OC-48 with AT&T to connect St. Thomas and St. Croix was executed during Quarter 2, CY 2012. RFPs for trenching and aerial and underground fiber pulling and splicing activities are scheduled to be posted during early Quarter 3, CY 2012. Significant progress has been made with the construction of the two Super FAPs; completion of the construction of the Super FAPs is expected during Quarter 3, CY 2012. Once they are completed, progress against this milestone will improve. A fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami were signed with Global Crossing/Level 3 during Quarter 4, CY 2011. | 0 | Given that 1) VIPFA/viNGN has purchased a large portion of the network management equipment, 2) the construction of the two SuperFAPs is near completion, and 3) the remaining FAPs are targeted for completion during Quarter 3, CY 2012/early Quarter 4 CY 2012, progress against this milestone will improve during the next two quarters, as the equipment can be deployed with the start and completion of these activities. | 20 | Network testing will be ongoing in alignment with equipment purchases and network build out. The initial alpha testing of the network's core gateway routers in a lab environment was completed during Quarter 4, CY 2011. Testing was also completed from Proof of Design from the NAPs to the Super FAPs to Community Anchor Institutions (CAIs). No testing was carried out during Quarter 2, CY 2012; however, with the purchase of a large portion of the network management equipment during Quarter 1, CY 2012 and the planned completion of construction of the Super FAPs by Quarter 3, CY 2012, final testing and staging for placement of the routers and switches will now begin during the latter part of late Quarter 3, CY 2012 or early in Quarter 4, CY 2012. Once connection of the FAPs is completed, the routers and switches will be installed and will await final activation to the fiber to bring the network on line. | 2012-08-27 17:33 | 2012-08-27 17:33 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2012 | Q3 | Q3 - 2012 | 8093 | 6754 | TRUE | 34 | Please refer to the response to Question 1 above. The current VIPFA/viNGN team has implemented a recovery plan to address delays in the construction schedule and to ensure that the network will be built-out by June/July 2013. Construction of three FAPs is completed. One is a Super FAP on St. Thomas; another is a Super FAP St. Croix, and the third one is a regular FAP on St. Croix. Final details, such as adding permanent power, alarm systems, and landscape details, are in progress and will be completed during the first half of Quarter 4, CY 2012. In addition, key project goals were completed for the island of St. John. Site visits were conducted with property owners on St. John to confirm/re-confirm FAP sites. After the site visits, viNGN conducted land survey activities at the three sites. The land survey is an important milestone in completing the FAPs design activities for the island of St. John. Significant progress is expected during the next two quarters, as the team finalizes | 0 |  | The VIPFA/viNGN team continues to make progress towards meeting the Baseline Milestone targets. The progress outlined in Item #1 above and total expenditures incurred to date document the achievements made by the new management team during a very short period of time, despite facing some delays in the implementation. Significant progress is expected during the next two quarters. | 96 | The VIPFA/viNGN team has negotiated and executed two land survey contracts with two surveying companies, one on St. Thomas and one on St. Croix. VIPFA/viNGN has also contracted with an environmental assessment company to evaluate the site conditions at relocated FAP sites. These FAP sites will be evaluated for endangered flora and fauna that may impact the construction process. | 98 | As part of the network design, VIPFA/viNGN will add an "express route" to provide unhindered 10 gigabyte bandwidth to the farthest reaches of the islands. For example, an express route will be constructed from the Super FAP location to the farthest located FAP. Thus providing bandwidth to CAIs (Community Anchor Institutions) and ISP (Internet Service Providers) that might be located great distances from the Super FAP. VIPFA/viNGN is in the process of revising the logical network design and finalizing and adjusting network routing protocol. This process has increase/balance the network to accommodate for physical design changes implemented in Quarter 3, CY 2012. In addition, VIPFA/viNGN is updating fiber splicing and distribution maps which will be used for vendors and maps out express routes. In Quarter 3, CY 2012, engineering design plans were received but the remaining final design plans and approvals for FAP location changes are scheduled to be completed during Quarter 4, CY 201 | 91 | VIPFA/viNGN team has an agreement with the local Department of Public Works for the trenching of four segments of highway, two on St. Thomas and St. Croix. As a result of arrangement, VIPFA/viNGN is about to begin trench work in the first half of the fourth quarter. Once the trench work (backbone) is complete, a major milestone will be completed. | 95 | During Quarter 3, CY 2012, VIPFA/viNGN submitted application for additional building permits and in some cases VIPFA/viNGN are awaiting final approval based on the permit application process. VIPFA/viNGN is anticipating all building permits for FAP construction to be issued by the third week of the next quarter. | 30 | VIPFA/viNGN and its contractors travelled on the roads which the trench work will be performed. As a result, VIPFA/viNGN and its contractors noted traffic patterns, road constructions and other potential road obstructions to include unsafe conditions that may impact work progress. In addition, VIPFA/viNGN and its contractors made contact with existing contractors to secure plans of on-going construction and to discuss procedures and methods so that both construction teams will have limited impact on each others construction. On a separate occasion, VIPFA/viNGN and its contractors marked out the location of underground drainage culvert that is in the path of trench work to be undertaken. VIPFA/viNGN also identified critical location for vault placement. | 93 | The VIPFA/viNGN team continues to make significant progress in its equipment procurement activities and remains above the percentage defined in our Baseline Milestone. During Quarter 2, CY 2012, the team received the routers and switches needed to begin the staging for the placement of the equipment. Further, the team has purchased all of the needed fiber optic cable and is awaiting delivery of the final order. During Quarter 3, CY 2012, the team procured traffic rated vaults for installation during the trench work on both St. Thomas and St. Croix. In addition, VIPFA/viNGN purchased about 30,000 linear feet of PVC conduit for underground fiber optic installation. Some miscellaneous items purchased are couplings, spacers, adapters, cable racks and supports. VIPFA/viNGN also procured 51 reels (408,000 linear feet) of inner ducts for both islands. | 20 | VIPFA/viNGN installed a ASR 9006 (Core Aggregation Services Router) at level (3) co-location facilities in Miami. Our additional ASR 9006 will be installed in New York and completed prior to the end of Quarter 4, CY 2012. Currently, AT&T has a co-location connection point at its facility on St. Thomas. VIPFA/viNGN will install an hand hole near the AT&T co-location facility and run aerial fiber optics to its Super FAP location. Similarly, on St. Croix, VIPFA/viNGN will construct a hand hole near AT&T facility and run underground fiber optic to its Super FAP location. this will create a redundancy in the network system, that will allow VIPFA/viNGN to offer middle service to its customers sooner than its network completion. | 1 | At our Level 3 facility in Miami, the ASR 9006 installation process is complete. At our Level 3 facility in New York, the ASR 9006 was purchased and shipped and is awaiting installation. | 20 | Network testing will be ongoing in alignment with equipment purchases and network build out. The initial alpha testing of the network's core gateway routers in a lab environment was completed during Quarter 4, CY 2011. Testing was also completed from Proof of Design from the NAPs to the Super FAPs to Community Anchor Institutions (CAIs). No testing was carried out during Quarter 3, CY 2012; however, with the purchase of a large portion of the network management equipment during Quarter 1, CY 2012 and the completion of the Super FAPs in Quarter 3, CY 2012, final testing and staging for placement of the routers and switches will now begin during the latter part of late Quarter 1, CY 2013. Once connection of the FAPs are complete, the routers and switches will be installed and will await final activation to the fiber to bring the network on line. | 2012-11-28 09:58 | 2012-11-28 09:58 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2012 | Q4 | Q4 - 2012 | 9051 | 7825 | TRUE | 35 | Please refer to the response to Question 1 above. The VIPFA/viNGN team is confident that the network will be built out by the deadline of July 31, 2013. The team has implemented a recovery plan to address the delays experienced in the construction schedule through Quarter 4, CY 2012. VIPFA/viNGN trenched approximately 7 miles during Quarter 4, CY 2012, which was limited largely due to the impact of the holiday season during November 2012 and December 2012. Trenching occurred on St. Thomas and St. Croix. VIPFA/viNGN plans to complete the remaining 39 miles, with four trenching teams operating simultaneously, two on St. Thomas and two on St. Croix. Construction of three FAPs is completed. One is a Super FAP on St. Thomas; another is a Super FAP on St. Croix, and the third one is a regular FAP on St. Croix. Final details, such as adding permanent power, security systems and telephone service, were added during Quarter 4, CY 2012. In addition, key project goals were completed for the i | 0 |  | The VIPFA/viNGN team continues to make progress towards meeting the Baseline Milestone targets. The progress outlined in Item #1 above and total expenditures incurred to date document the achievements made by the new management team during a very short period of time, despite facing some delays in the implementation. Significant progress is expected during the next two quarters. | 96 | An addendum to the Phase 1 Archaeological Survey was completed to address ten FAP relocations. The report detailed changes, based on the relocation of the FAPs. The impact of the proposed relocations on the natural and human environments is reported as minor. The projected changes are minor in nature, and although they do include changes in earth moving activities, all represent equivalent impact or in several cases even a reduction of impact. No potentially significant cultural resources were identified during the Phase I Archaeological Survey for the Fiber Access Point locations on both islands. From the archaeological perspective, it was recommended that the State Historic Preservation Office issues a conditioned finding of no objection to the proposed construction activities. The VIPFA/viNGN team continues to monitor its construction site during the build-out process for any endangered species that viNGN or its contractors might encounter, such as the Ameiva polops, Epicrates mon | 98 | VIPFA/viNGN trenched approximately 7 miles during Quarter 4, CY 2012, which was limited due to the impact of the holiday seasons during November 2012 and December 2012. VIPFA/viNGN plans to complete the remaining 39 miles of trenching, with four trenching teams operating simultaneously. As part of the network design, VIPFA/viNGN will add an "express route" to provide unhindered 10 gigabyte bandwidth to the farthest reaches of the islands. For example, an express route will be constructed from the Super FAP location to the farthest located FAP. Thus providing bandwidth to CAIs (Community Anchor Institutions) and ISP (Internet Service Providers) that might be located great distances from the Super FAP. VIPFA/viNGN is in the process of revising the logical network design and finalizing and adjusting network routing protocol. This process has increased/balanced the network to accommodate physical design changes that were implemented during Quarter 3, CY 2012. In addition, VIPFA/viNGN i | 91 | VIPFA/viNGN team has an agreement with the U.S. Virgin Islands Department of Public Works (DPW) for the trenching of four segments of highway, two on St. Thomas and St. Croix. During the fourth quarter, VIPFA/viNGN began trenching on both St. Croix and St. Thomas. VIPFA/viNGN continues to work with the U.S. Virgin Islands Department of Planning and Natural Resources (DPNR) to ensure that VIPFA/viNGN's permits are updated and in compliance with the previous permits issued. The team also engaged with the State Historic Preservation Office and current land owners to ensure that FAPs are constructed within the approved rights of way. VIPFA/viNGN trenched approximately 7 miles during Quarter 4, CY 2012, which was limited due to the impact of the holiday seasons during November 2012 and December 2012. VIPFA/viNGN expects to trench the remaining 39 miles, with four trenching teams operating simultaneously. | 96 | VIPFA/viNGN continues to work with the local Planning and Natural Resources Department to ensure that VIPFA/viNGN's permits are updated and in compliance with the previous permits issued. The team also engaged with the State Historic Preservation office and current land owners to ensure that FAPs are constructed within the approved right of way. During Quarter 4, CY 2012, VIPFA/viNGN received seventeen (17) building permits for FAP construction. VIPFA/viNGN anticipates that all building permits for FAP construction will be issued by the end of Quarter 1, CY 2013. | 35 | VIPFA/viNGN and its contractors continue to assess the roads on which trenching work is being and will be performed. Traffic patterns, road construction and other potential obstructions that may cause unsafe conditions or impact work progress have been noted. VIPFA/viNGN and its contractors also made contact with existing contractors to secure plans of on-going construction and to discuss procedures and methods so that both construction teams will have limited impact on the work of the other. For example, on Dorothea/Route 33 road on St. Thomas, the U.S. Virgin Islands Department of Public Works (DPW) is doing a bridge repair that is in the path of the underground fiber placement. A coordination meeting was conducted. As a result, VIPFA/viNGN and its contractor skipped this section of road to return at a later date when DPW's contractor is nearer to completion. At a predetermined point prior to construction, VIPFA/viNGN and its contractors marked out the location of an underground d | 94 | VIPFA/viNGN team is currently over performing against the Baseline Milestone and exceeds the target that was set at 90% completion for the projected percent for Quarter 4, CY 2012. During Quarter 4, CY 2012, VIPFA/viNGN and its contractors decided to install underground fiber optic conduits on all four segments of the project. With the aim to reduce traffic interference, conduits were installed without traffic vaults. This allows the manufacturer ample time for vault construction. The vaults are expected to arrive during Quarter 2, CY 2013. Some miscellaneous items were procured during Quarter 4, CY 2012, such as couplings, spacers, adapters, cable racks and supports. All fiber optic cable, other major equipment, and conduit were purchased during prior quarters. | 21 | VIPFA/viNGN trenched approximately 7 miles during Quarter 4, CY 2012, which was limited due to the impact of the holiday seasons during November 2012 and December 2012. VIPFA/viNGN expects to trench the remaining 39 miles with four trenching teams operating simultaneously. VIPFA/viNGN plans to install 46.6 miles of aerial construction on St. Thomas and St. John combined and 36.6 miles on St. Croix. VIPFA/viNGN installed an ASR 9006 (Core Aggregation Services Router) at the Level (3) collocation facility in Miami. The ASR 9006 in Miami is 100% installed, is powered up and has been tested. Currently, AT&T has a collocation connection point at its facility on St. Thomas. VIPFA/viNGN will install an hand hole near the AT&T collocation facility and run aerial fiber optics to its Super FAP location. Similarly, on St. Croix, VIPFA/viNGN will construct a hand hole near AT&T's facility and run underground fiber optic to its Super FAP location. This will create redundancy in the network s | 2 | Under performance against the Baseline Indicator is due to the fact that VIPFA\viNGN has not completed the build-out of the network segments that will enable the team to provide improved access to providers. By the end of Quarter 4, CY 2012, trenching began on St. Thomas and St. Croix, the two SuperFAPS were constructed, and one additional FAP was constructed. As the FAP construction is completed, as the Community Anchor Institutions are connected and as all backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. At the Global Crossing/Level 3 facility in Miami, the ASR 9006 installation process is complete. It is 100% installed, power up and tested. | 20 | No fiber optic testing was done during the Quarter 4, CY 2012. The aerial installation contractor will begin testing of the fiber optic reel at the warehouse location prior to installation during Quarter 1, CY 2013. Network testing will be ongoing in alignment with equipment purchases and network build out. The initial alpha testing of the network's core gateway routers in a lab environment was completed during Quarter 4, CY 2011. Testing was also completed from Proof of Design from the NAPs (Network Access Point) to the Super FAPs to Community Anchor Institutions (CAIs). No testing was carried out during Quarter 4, CY 2012; however, with the purchase of a large portion of the network management equipment during Quarter 1, CY 2012 and the completion of the Super FAP construction during Quarter 3, CY 2012, final testing and staging for placement of the routers and switches will begin during late Quarter 1, CY 2013. Once connection of the FAPs is complete, the routers and switches will | 2013-02-28 08:29 | 2013-02-28 08:29 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2013 | Q1 | Q1 - 2013 | 9995 | 8542 | TRUE | 36 | Please refer to the response to Question 1 above. The VIPFA/viNGN team continued to implement its recovery plan to address the delays experienced in the construction. As of March 31, 2013, VIPFA/viNGN trenched approximately 32 miles and plans to complete the remaining 12.5 miles of trenching operations with four trenching teams operating simultaneously. Underground construction with fiber pulling and aerial fiber installation began during Quarter 1, CY 2013. These activities are being executed concurrently on both St. Thomas and St. Croix. During Quarter 1, CY 2013, VIPFA/viNGN installed 6,900 ft. of aerial fiber and pulled 63,358 ft. of innerduct on St. Croix. On St. Thomas, aerial fiber hardware and innerduct were installed in preparation for aerial fiber installation. Construction of three FAPs was completed as of the end of Quarter 4, CY 2012. Two Super FAPs were constructed, one on St. Thomas and St. Croix. The third FAP that was constructed is a Type B FAP on St. Croix. A f | 0 |  | The VIPFA/viNGN team continues to make progress towards meeting the Baseline Milestone targets. The progress outlined in Item #1 above and total expenditures incurred to date document the achievements made by the new management team during a very short period of time, despite facing some delays in the implementation. Significant progress is expected during the next two quarters. | 96 | During Quarter 4, CY 2012, an addendum to the Phase 1 Archaeological Survey was completed to address FAP relocations. The report detailed changes, based on the relocation of the FAPs, and the impact of the proposed relocations on the natural and human environments is reported as minor. The projected changes are minor in nature, and although they do include changes in earth moving activities, all represent equivalent impact or in several cases even a reduction of impact. No potentially significant cultural resources were identified during the Phase I Archaeological Survey for the Access Point locations on both islands. From the archaeological perspective, it was recommended that the State Historic Preservation Office issues a conditioned finding of no objection to the proposed construction activities. During Quarter 1, CY 2013, six FAPs on St. Thomas and six FAPs on St. Croix were re-evaluated by the U.S. Virgin Islands State Historic Preservation Office (VISHPO). For example, FAP ST | 98 | As of March 31, 2013, VIPFA/viNGN trenched approximately 32 miles in total on St. Thomas and St. Croix. VIPFA/viNGN plans to complete the remaining 12.5 miles of trenching, with four trenching teams operating simultaneously. As part of the network design, VIPFA/viNGN will add "express routes" to provide unhindered 10 gigabyte bandwidth to the farthest reaches of the islands. For example, an express route will be constructed from the Super FAP location to the farthest located FAP, on both St. Thomas and St. Croix. Thus providing unhindered bandwidth to CAIs (Community Anchor Institutions) and ISPs (Internet Service Providers) that might be located great distances from the Super FAPs on St. Thomas and St. Croix. VIPFA/viNGN has selected and designed the interior network routing protocol. Once the FAPs (Fiber Access Points) are built and the network equipment is installed, the network is expected to be ready to "go live". | 91 | VIPFA/viNGN team has an agreement with the United States Virgin Islands (USVI) Department of Public Works and the USVI Department of Planning and Natural Resources for the trenching of four segments of highway, two on St. Thomas and two on St. Croix. During Quarter 4, CY 2012, VIPFA/viNGN began trenching on St. Croix and on St. Thomas. As of March 31, 2013, VIPFA/viNGN trenched approximately 32 miles in total on St. Thomas and St. Croix. VIPFA/viNGN plans to complete the remaining 12.5 miles of trenching, with four trenching teams operating simultaneously. VIPFA/viNGN continues to engage the U.S. Virgin Islands State Historic Preservation office (VISHPO) and current land owners to insure that the FAPs are constructed with sensitivity for historic districts and the approval of the land owners. During Quarter 1, CY 2013, VISHPO re-assessed the Dorothea FAP site on St. Thomas and proposed a minor, horizontal shift of the direction of the FAP to increase the space between the existing | 96 | VIPFA/viNGN continued to work with the local U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and in compliance with the previous permits issued. The team also continued to engage with the VIHSPO and current land owners to ensure that FAPs are constructed in the approved rights of way. During Quarter 4, CY 2012, VIPFA/viNGN received seventeen (17) building permits for FAP construction. VIPFA/viNGN anticipates that all building permits for FAP construction will be issued by the end of Quarter 2, CY 2013. | 36 | VIPFA/viNGN and its contractors continue to assess the roads on which trenching work will be performed. Traffic patterns, road construction and other potential obstructions that may cause unsafe conditions or impact work progress have been noted. VIPFA/viNGN and its contractors also made contact with other contractors to secure plans of on-going construction and to discuss procedures and methods, so that the construction teams will have limited impact on the work of the others. For example, the VIPFA/viNGN team submitted a weekly projected schedule for St. Thomas and St. Croix to the local telephone company which is also building and expanding its network. Because of these coordinating efforts, VIPFA/viNGN and its contractors were able to plan a date during Quarter 2, CY 2013 when VIPFA/viNGN's contractors can return to trench an area that was skipped along Route 33 on St. Thomas. Also, because of the negative impact that trenching would have on a main thoroughfare on St. Thomas, V | 94 | The VIPFA/viNGN team is currently performing slightly under the Baseline Milestone that was set at 100% complete for Quarter 1, CY 2013. During Quarter 4, CY 2012, VIPFA/viNGN and its contractors decided to install underground fiber optic conduits on all four segments of the project, two on St. Thomas and two on St. Croix, without manholes/traffic vaults. With the aim to reduce traffic interference, conduits were installed without traffic vaults which allowed the manufacturer ample time for vault construction. Further, traffic vaults were purchased, rather than concrete manholes, to reduce the time to complete the build out. VIPFA/viNGN was successful in procuring and receiving traffic vaults from a United States manufacturer near the end of Quarter 1, CY 2013. The trenching contractors on both islands (St. Thomas and St. Croix) were more than 70% complete when the vaults arrived, and the decision was made to begin vault installation during early Quarter 2, CY 2013. | 23 | As of March 31, 2013, VIPFA/viNGN trenched approximately 32 miles in total on St. Thomas and St. Croix. VIPFA/viNGN plans to complete the remaining 12.5 miles of trenching, with four trenching teams operating simultaneously. During Quarter 1, CY 2013,VIPFA/viNGN also installed 6,900 ft. of aerial fiber and pulled 63,358 ft. of innerduct on St. Croix. On St. Thomas, aerial fiber hardware and innerduct were installed in preparation for aerial fiber installation. In addition, VIPFA/viNGN installed two ASR 9006 (Core Aggregation Services Router) at Level 3 co-location facilities in Miami and New York as of March 31, 2013. Further, AT&T has a collocation connection point at its facility on St. Thomas. VIPFA/viNGN will connect to the AT&T link near the AT&T co-location facility and run aerial fiber optics to its SuperFAP location near the U.S. Virgin Islands Territorial Emergency Management Agency (VITEMA) building on St. Thomas. On St. Croix, VIPFA/viNGN will install a hand hole near AT | 3 | Under performance against the Baseline Indicator is due to VIPFA/viNGN not completing the build-out of the network segments that will enable VIPFA/viNGN to provide new or improved access to providers. However, as the FAP construction is completed, the Community Anchor Institutions are connected and all backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. At the Level 3 facility in Miami and New York, the ASR 9006 core router installation process was complete. Equipment will be deployed as soon as FAPs are built and racks are installed. | 30 | During March, CY 2013, the awarded contractor began testing the fiber optic reels at the warehouse location prior to installation. This will be a typical process for all newly-acquired fiber before it is installed. Network testing will be ongoing in alignment with equipment purchases and network build out. The initial alpha testing of the network's core gateway routers in a lab environment was completed during Quarter 4, CY 2011. Testing was also completed from Proof of Design from the NAPs (Network Access Point) to the Super FAPs to Community Anchor Institutions (CAIs). No testing was carried out during Quarter 1, CY 2013; however, with the purchase of a large portion of the network management equipment during Quarter 1, CY 2012 and the completion of the Super FAPs during Quarter 3, CY 2012, final testing and staging for placement of the routers and switches is expected to begin during late Quarter 2, CY 2013 or early Quarter 3, CY 2013. Once connection of the FAPs is complete, the r | 2013-05-29 23:15 | 2013-05-29 23:15 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2013 | Q2 | Q2 - 2013 | 10669 | 8996 | TRUE | 49 | The VIPFA/viNGN team made tremendous progress with the construction of its middle mile network during Quarter 2, CY 2013. Refer to the response to Question 1 above for a summary of the significant accomplishments made during the reporting quarter. The progress outlined in the response to Question 1 above, combined with the total expenditures incurred to date, document the significant achievements made by the new management team at VIPFA/viNGN during a very short period of time. Also, much of the construction work that was completed has not been invoiced by construction contractors; thus, the actual percentage of completion of the project is underrepresented at 49%, i.e. when considering total federal expenditures plus allowable matching contributions alone. Expenditures are expected to increase significantly, starting in Quarter 3, CY 2013, as construction contractors begin to invoice for work that is confirmed as completed by the team's engineers and architects. | 0 |  | N/A | 97 | During Quarter 2, CY 2013, an addendum to the Environmental Assessment and an update to the Phase I Archeological Survey were completed to address FAP relocations and aesthetic modifications to FAPs. During various stages of the construction planning process, including consultations with the U.S. Virgin Islands State Historic Preservation Office (VISHPO), and during construction, the team determined that two (2) additional FAPs needed to be relocated to provide better access to the sites, to lessen the environmental and other impacts of locating FAPs in the previously-approved locations, and/or to ensure that each new site location is in alignment with current and adjacent property uses. The U.S. Virgin Islands State Historic Preservation Office (VISHPO) requested a minor relocation of the STT FAP-05 in Estate Dorothea on St. Thomas to increase the space between the new FAP construction site and the historical structure, and the VISHPO requested a minor modification to the exterior o | 100 | The core network design is complete. A minor modification was made to the network design on the island of St. Croix in Christiansted. Along the path on King Street, there are many utility connections, shallow conduit, deep storm water lines and poured concrete that blocked the network path. Because of these obstructions and though on the same network route, fiber traffic was diverted around a one block area along West Street to Strand Street, thence along Strand Street to Prince Street for the connection to FAP STX-09. Further, a connection was made in the same area along the short path between North Street and King Street. The length of the trenches and the fiber installations did not change, and the network path remains in the same area as originally planned. As part of the network design, VIPFA/viNGN will add "express routes" to provide unhindered 10 gigabyte bandwidth to the farthest reaches of the islands. For example, an express route will be constructed from the SuperFAP locat | 91 | The VIPFA/viNGN team has an agreement with the United States Virgin Islands (U.S.V.I.) Department of Public Works and the U.S.V.I. Department of Planning and Natural Resources for the trenching of four segments of highway, two on St. Thomas and two on St. Croix. During Quarter 2, CY 2013, VIPFA/viNGN completed trenching of the backbone on St. Croix and on St. Thomas. The minor modification referenced above required a change in the Right of Way for the network on the island of St. Croix in Christiansted. The team also continued to engage with the VIHSPO and current land owners to ensure that FAPs are constructed in the approved Rights of Way. | 96 | VIPFA/viNGN continued to work with the local U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and in compliance with the previous permits issued. During Quarter 2, CY 2013, VIPFA/viNGN prepared two (2) additional permit applications for FAPs to be constructed on St. John. The two permits are anticipated to be approved during early Quarter 3, CY 2013. | 40 | VIPFA/viNGN and its contractors continued to assess the roads on which road work will be performed. Traffic patterns, road construction and other potential obstructions that may cause unsafe conditions or impact work progress were noted. This activity required upfront planning and coordination with other local government departments and agencies and private entities doing road work. Public notifications were issued. Following these coordinated planning efforts, during Quarter 2, CY 2013, trenching and paving/road repair work occurred nightly along busy thoroughfares on both St. Thomas and St. Croix to minimize the impact on traffic flow. Further, the VIPFA/viNGN team submitted a weekly schedule update for St. Thomas and St. Croix to the local telephone company, the U.S.V.I. Department of Public Works (DPW), the Virgin Islands Territorial Emergency Management Agency (VITEMA) and other government agencies and their contractors who are engaging in work in the same zones. VIPFA/viNGN | 95 | The VIPFA/viNGN team is currently performing slightly under the Baseline Milestone that was set at 100% complete for Quarter 1, CY 2013. During Quarter 2, CY 2013, VIPFA/viNGN procured additional support/hanging materials for its aerial fiber installation. These materials are anticipated to arrive during Quarter 3, CY 2013. Once these materials arrive, it is anticipated that the aerial fiber installation will be completed during Quarter 3, CY 2013. | 49 | During Quarter 2, CY 2013, VIPFA/viNGN completed backbone trenching operations in preparation for underground backbone fiber optic cable installation on St. Thomas and St. Croix. With the completion of the trenching, a key milestone, a cumulative total of 88.8 miles of underground backbone, aerial backbone and later fiber installations across St. Croix, St. Thomas, Water Island and St. John were deployed during Quarter 2, CY 2013. Further, as of June 30, 2013, the construction of FAP (Fiber/Facility Access Point) STX-05 at Estate La Reine on St. Croix was approximately 90% complete. The brick and mortar construction was 95% complete, while the AC (Air Conditioning) units, racking equipment and DC Power installation were pending. Also, FAP STX-06, located near the John Woodson School, was approximately 85% complete, and FAP STX-12 in Cotton Valley was nearly 80% complete. At FAP STX-06 and FAP STX 12, the Cisco System routers, AC unit, and DC backup power are pending installation. A | 5 | Under performance against the Baseline Indicator is due to VIPFA/viNGN not completing the build-out of the network segments that will enable VIPFA/viNGN to provide new access to Internet Service Providers and other service providers. As the FAP construction is completed, the Community Anchor Institutions are connected and all backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. Equipment will be deployed as FAPs are built and equipment racks are installed. During Quarter 2, CY 2013, VIPFA/viNGN installed a core distribution switch in the Level 3 facilities on St. Croix to provide bandwidth to customers, with the anticipation of providing service on the portion of the network that will be completed as of Quarter 3, CY 2013, as an alternate way for customers to access VIPFA/viNGN's network prior to the complete build-out of the network. | 30 | Under performance against the Baseline Indicator is due to the fact that VIPFA/viNGN has not completed the build-out of the additional network segments that will enable additional network testing. As the FAP construction is completed, the Community Anchor Institutions are connected and all backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. Network testing will be ongoing in alignment with network build out and equipment deployment. With the completion of the SuperFAPs during CY 2012, final testing and staging for placement of the routers and switches were completed during Quarter 2, CY 2013. The Network Technicians and Engineers designed initial configurations in preparation for the "turn up" of the network. These configurations served as templates that can be applied directly to future customer installations. As the construction of all other FAPs is completed, the routers and switches will be installed, and final t | 2013-08-20 19:17 | 2013-08-20 19:17 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2013 | Q3 | Q3 - 2013 | 11299 | 9449 | TRUE | 65 | The VIPFA/viNGN team continued to make progress with the construction of its middle mile network during Quarter 3, CY 2013. Refer to the response to Question 1 above for a summary of the significant accomplishments made during the reporting quarter. The progress outlined in the response to Question 1 above, combined with the total expenditures incurred to date, document the significant achievements made by the VIPFA/viNGN team. Also, much of the construction work that was completed has not been invoiced by construction contractors; thus, the actual percentage of completion of the project is underrepresented at 65%, i.e. when considering total federal expenditures plus allowable matching contributions alone. Payments against invoices for work completed through Quarter 3, CY 2013 through to the end of the project are expected to continue through close-out, as construction contractors begin to invoice for work that is confirmed as completed by the team's engineers and architects. | 0 |  | N/A | 97 | During Quarter 2, CY 2013, an addendum to the Environmental Assessment and an update to the Phase I Archeological Survey were completed to address two FAP relocations. The FAP relocations and modifications were deemed to be minor changes, and no potentially significant cultural resources were identified during the archaeological survey. With these findings from the environmentalist and the archeologist, the U.S. Virgin Islands State Historic Preservation Office (VISHPO) evaluated and approved the new locations, and the design drawings were modified and reissued to the contractors during Quarter 3, CY 2013. The VIPFA/viNGN team continued to monitor its construction sites for artifacts as work was performed near sensitive archaeological sites and for any endangered species that viNGN or its contractors might encounter. To date, viNGN and its contractors have not encountered any artifacts or any endangered species and their habitat on any of the construction sites. | 100 | The core network design is complete. | 99 | Agreements are in place with all land owners for rights of way for the construction of FAP. As a result, all FAP contracts have been executed. However, as work was underway on the East end of St. Croix, an owner of a property along the planned route notified the team that he prefers not to have an obstruction of his views. The area of concern is only 500 feet. The VIPFA/viNGN team is currently considering the range of fast and network optimal solutions to address with the NTIA and NOAA team during Quarter 4, CY 2013. | 97 | VIPFA/viNGN continues to work with the local U.S. Virgin Islands Department of Planning and Natural Resources (DPNR) to ensure that VIPFA/viNGN's permits are updated and in compliance with the previous permits issued. During Quarter 3, CY 2013, DPNR approved two permits for FAPs to-be-constructed on the island of St. John. The construction of both FAPs on St. John are 100% completed. In addition, the Board of Directors and management of the West Indian Company Limited (WICO) approved the construction of FAP STT-13 Havensight, and construction started. | 50 | VIPFA/viNGN and its contractors continued to assess the roads on which road work will be performed. Traffic patterns, road construction and other potential obstructions that may cause unsafe conditions or impact work progress were noted. This activity required upfront planning and coordination with other local government departments and agencies and private entities performing road work. As a result, on a weekly basis, public notifications were issued. Some of the agencies to which public notices were issued are the local telephone company, the U.S.V.I. Department of Public Works (DPW), the Virgin Islands Territorial Emergency Management Agency (VITEMA) and other government agencies and their contractors who are engaging in work in the same zones. In addition, as a part of the daily site preparation activities for FAP construction, VIPFA/viNGN contractors installed construction fencing and storm water pollution control measures as a typical safety process. | 96 | The VIPFA/viNGN team is currently performing slightly under the Baseline Milestone that was set at 100% complete for Quarter 3, CY 2013. During Quarter 3, CY 2013, VIPFA/viNGN procured additional support/hanging materials for its aerial fiber installation. These materials arrived during Quarter 3, CY 2013, and fiber installation continued. | 65 | During Quarter 3, CY 2013, VIPFA/viNGN completed a cumulative total of 246.96 miles of underground backbone, aerial backbone and lateral fiber installations across St. Croix, St. Thomas, Water Island and St. John. As of September 30, 2013, the construction of two Type C FAPs (Facility Access Points) on St. Croix (Estate La Reine FAP STX-05 and Woodson/VI Corporate Lands FAP STX-06) is 100% completed. Furthermore, construction of the Estate Diamond/The Boys' and Girls' Club FAP STX-03, the University of the Virgin Islands (UVI) FAP STX-04, and the Roebuck Industrial Park FAP STX-16 FAP is approximately 95% complete, and construction of the Cotton Valley FAP STX-12 is approximately 90% complete. Additionally, the construction of the La Grande Princess/U.S. Virgin Islands Department of Education FAP STX-07 is approximately 75% complete, the U.S. Virgin Islands Water and Power Authority (WAPA) Richmond FAP STX-17 is approximately 15% complete, and the Juan Luis Hospital FAP STX-15 is appr | 11 | During Quarter 3, CY 2013, VIPFA/viNGN installed all network equipment in Super FAP STX-02, at Level 3 in New York, at Level 3 in Miami and at the Althalie McFarlane Petersen Library in Frederiksted, St. Croix. As the remaining FAP construction is completed, the equipment racks are installed in the FAPs, the Community Anchor Institutions are connected and all backbone node equipment is installed, equipment is being deployed, and the team will be positioned to come in line with the Baseline Indicator targets. | 35 | As the remaining FAP construction is completed, the equipment racks are installed in the FAPs, Community Anchor Institutions are connected and the remaining backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. Network testing will be ongoing in alignment with network build out and equipment deployment. The connections through Level 3 in New York and Miami to St. Croix were activated and tested, and a connection was successfully made to the Super FAP STX-02. Also, the connection for the Althalie McFarlane Petersen Library in Frederiksted, St. Croix was activated, and it has been successfully serving the community as a CAI and PCC since early September, CY 2013. As the construction of all other FAPs is completed, the routers and switches will be installed, and final testing and activation will bring the network fully on line. | 2013-11-19 16:37 | 2013-11-19 16:37 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2013 | Q4 | Q4 - 2013 | 11919 | 10084 | TRUE | 72 | The VIPFA/viNGN team continued to make progress with the construction of its middle mile network during Quarter 4, CY 2013. Refer to the response to Question 1 above for a summary of the significant accomplishments made during the reporting quarter. The progress outlined in the response to Question 1 above, combined with the total expenditures incurred to date, document the significant achievements made by the VIPFA/viNGN team. Also, much of the construction work that was completed has not been invoiced by construction contractors; thus, the actual percentage of completion of the project is underrepresented at 72%, i.e. when considering total federal expenditures plus allowable matching contributions alone. Payments against invoices for work completed through Quarter 4, CY 2013 through to the end of the project are expected to continue through close-out, as construction contractors begin to invoice for work that is confirmed as completed by the team's engineers and architects. | 0 |  | N/A | 98 | The VIPFA/viNGN team continued to monitor its construction sites for artifacts as work was performed near sensitive archaeological sites and for any endangered species that viNGN or its contractors might encounter. To date, viNGN and its contractors have not encountered any artifacts or any endangered species and their habitat on any of the construction sites. | 98 | The core network design is complete. As a part of the network design, VIPFA/viNGN will add "express routes" to provide unhindered 10 gigabyte bandwidth to the farthest reaches of the islands. For example, an express route will be constructed from the SuperFAP location to the farthest located FAP on both St. Thomas and St. Croix, thus providing unhindered bandwidth to CAIs (Community Anchor Institutions) and ISPs (Internet Service Providers) and other broadband service providers that might be located great distances from the SuperFAPs on St. Thomas and St. Croix. During Quarter 4, CY 2013, the VIPFA/viNGN team requested approval of the following project modifications for St. Croix and St. Thomas: 1. On St. Croix, approximately 800 feet of aerial network needs to be changed from aerial to underground. This change is necessary because it was determined that the Virgin Islands Water and Power Authority (WAPA) does not have a right of way for aerial installation along this section of th | 99 | Agreements are in place with all land owners for rights of way for property on which FAPs have been and are being constructed. However, as referenced in 2c. above, as fiber installation was underway on the east end of St. Croix, an owner of a property along the planned route notified the team that he prefers not to have an obstruction of his views. The area of concern is only 500 feet. The VIPFA/viNGN team proposed trenching and burying conduit at the location. Approval of this project modification is pending guidance from the U.S. Virgin Islands State Historic Preservation Office (VISHPO) and then final approval from NTIA. | 98 | VIPFA/viNGN continues to work with the U.S. Virgin Islands Department of Planning and Natural Resources (DPNR) to ensure that VIPFA/viNGN's permits are updated and in compliance with the previous permits issued. During Quarter 4, CY 2013, DPNR approved the permit for the last FAP to be constructed on the island of St. Thomas [FAP STT-05 (Dorothea)]. Despite significant flooding from heavy rains during the past three months, progress was made with the construction of FAP STT-05 (Dorothea) which is 10% complete. | 55 | The VIPFA/viNGN team and its contractors continued the build out of the middle mile, 100% fiber optic network, placing greater emphasis on completing the construction of FAPs and completing lateral drop installations which will allow for the connection of more CAIs. Site preparations for these activities will continue until completion. As a part of the daily site preparation activities for FAP construction, VIPFA/viNGN's contractors continue to install construction fencing and storm water pollution control measures as a typical safety process. In addition, the team shifted its efforts from making general public notices and participating in viNGN-hosted Broadband Business and Technology/Broadband Coalition meetings to contacting CAIs individually to provide updates on the status of the network build-out and the next steps for the connection of their CAIs to viNGN's network. viNGN's staff and viNGN's contractors are visiting each CAI site to reconfirm locations and to assess each sit | 97 | The VIPFA/viNGN team is currently performing slightly under the Baseline Milestone that was set at 100% complete for Quarter 4, CY 2013, as equipment procurement activities are continuing as the network is being built out. During Quarter 4, CY 2013, VIPFA/viNGN continued to procure equipment, such as plenum rated cable, stackable tangents and rack-mounted splice trays that are being used to connect the fiber installed to the core of the network. Also, equipment was purchased that will aid in "terminating" services at the CAIs. | 75 | During Quarter 4, CY 2013, VIPFA/viNGN installed a cumulative total of 119.79 miles of underground backbone, aerial backbone and lateral fiber installations across St. Croix, St. Thomas, Water Island and St. John. From the inception of the grant through December 31, 2013, the team installed a total of 366.75 miles of fiber (not strand miles), with 187.53 miles installed on St. Croix and 179.22 miles installed between St. Thomas, St. John, and Water Island. These numbers include the installation of 1) Aerial Backbone Fiber, 2) Underground Backbone Fiber, and 3) forty-two (42) Lateral Drops to the outside premises of Community Anchor Institutions (CAIs) since the inception of the grant through December 31, 2013. Also, as of December 31, 2013, on St. Thomas, construction was completed for seven FAPs (Facility Access Points) which were under construction. FAP STT-02 (University of the Virgin Islands), FAP STT-09 (Eudora Kean), FAP STT-10 (Rt. 10 & 32)/Nadir, FAP STT-11 (Fort Mylner), FA | 15 | During Quarter 4, CY 2013, VIPFA/viNGN began the installation of patch panels and routers in the CAIs on an aggressive schedule, in preparation for each FAP to be lit. Patch panels were also installed in all of the constructed FAPs throughout St. Croix, St. Thomas, and St. John. | 35 | The connections through Global Crossing/Level 3 in New York and Miami from St. Croix were activated and tested, and a connection was successfully made to the SuperFAP on St. Croix (FAP STX-02). The team is also testing its network as it is being built out and connected to ISPs and other broadband service providers who enter into Master Services Agreements (MSAs). For example, the connection to the Althalie McFarlane Petersen Library in Frederiksted, St. Croix was connected, tested and activated, and it has been successfully serving the community as a CAI and PCC since early September, CY 2013, providing broadband capacity at up to 10 times the levels it previously experienced. In addition, the U.S. Virgin Islands Legislature building on St. Croix was connected and tested and is now ready to be activated by its selected broadband service provider which has already entered into a Master Services Agreement (MSA) with viNGN. | 2014-02-28 11:50 | 2014-02-28 11:50 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570097 | 2010 | Q4 | Q4 - 2010 | 989 | 2033 | TRUE | 1 | N/A | 50 | Procurement of contractors | Procurement of contractors to perform high speed internet access work on state tower sites. 50% complete by end of December. | 0 | Environmental special award condition amended in December. Coordinator engaged to oversee Environmental assessments performed by contractors for the purpose of drafting the single final report for acceptance by NTIA. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-07 11:56 | 2011-02-07 11:56 | 6064 | 6064 | Department of Information Technology | TRUE
NT10BIX5570097 | 2011 | Q1 | Q1 - 2011 | 1467 | 2447 | TRUE | 3 | N/A | 18 | Administer and oversee performance in all aspects of grant | Responses to the DMW RFP have been evaluated, Price Agreements have been drafted, and a final legal review is being performed before making the award announcements. Four contracts have been awarded to perform environmental survey work. | 30 | Three of the four contracts for performing EA activities have been executed. Vendors began doing site visits and other analysis as required. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-04-25 17:46 | 2011-04-25 17:46 | 6064 | 6064 | Department of Information Technology | TRUE
NT10BIX5570097 | 2011 | Q2 | Q2 - 2011 | 3145 | 3333 | TRUE | 5 | Project is somewhat delayed due to extended contract negotiations on the DMW RFP. | 20 | Administer and oversee performance in all aspects of grant | The Price Agreements for the Digital Microwave (DMW) RFP have been awarded. DMW contracts are being drafted. The final $11.6M calculations have not been completed. | 90 | All four contracts were executed for Environmental Assessment activities. Vendors completed site visits and other analysis as required. Environmental Assessment draft report will be submitted to NTIA pending FONSI approval. (submitted on 07/13) | 0 | Contracts for DMW design and construction (including network design) have not yet been finalized. | 0 | N/A | 0 | no variance | 0 | no variance | 0 | Equipment will/can not be purchased until site design is completed. | 0 | no variance | 0 | no variance | 0 | no variance | 2011-08-17 11:36 | 2011-08-17 11:36 | 7092 | 7092 | Department of Information Technology | TRUE
NT10BIX5570097 | 2011 | Q3 | Q3 - 2011 | 4365 | 4039 | TRUE | 3 | Have not received FONSI, DMW contracts have not been signed, therefore, no payments have been made or equipment purchased. | 78 | Administer and oversee performance in all aspects of grant | Price aggrements have been awarded, contracts are being drafted. Full $11.6 million in-kind is being reported. | 99 | Draft Environment Assessment report submitted to NTIA on 7/13/11. Programmatic Agreement drafted by NTIA allowing provisional FONSI to be issued allowing site construction. PA currently being coordinated with interested agencies | 10 | Detailed DMW system planning accomplished. Contractor SOWs being prepared | 0 | N/A | 0 | Construction contracts have not been executed | 0 | No Variance | 0 | Construction contracts have not been executed, the design has not been completed, therefore no hardware has been purchased. | 0 | Construction contracts have not been executed, the design has not been completed, therefore no part of network built. | 0 | No Variance | 0 | No Variance | 2011-12-01 12:17 | 2011-12-01 12:17 | 7092 | 7092 | Department of Information Technology | TRUE
NT10BIX5570097 | 2011 | Q4 | Q4 - 2011 | 4433 | 4083 | TRUE | 3 | Middle Mile Project 1. Activated design-build contract activities with three contractors -- Aviat, TowerCom, and Crestino -- on November, 16, 2011. Contractors began immediate site surveys and path analyses for 59 sites. 80% of site surveys and path analyses completed by December, 31, 2011. 2. Selected vendors for major site upgrade systems: Aviat of all RF Kits (radios, antennas, and waveguides), Sabre for towers, Modular Connections for shelters (combined communications & emergency generator), NGH for battery/rectifier systems. 3. Prepared and executed design-build contractor contract modifications for system design, civil construction, and RF system installation, integration, and test. 4. Cisco completed a network system-level design for network router architecture (done gratis). DOIT will competitively procure router in January 2012 5. Aviat (w/ Comsearch) prepared all PCNs to be sent to the FCC for frequency assignments; to be submitted to the FCC in January 2012 700 MHz LT | 50 | Administer and oversee performance in all aspects of grant | Assumes management, administrative, and legal effort is linear across 36 month grant period. Percent was reduced from previous quarterly report due to alignment of the completion with expensed amounts. | 100 | Provisional FONSI issued on November 2011 | 20 | 1. DMW site surveys and path analyses 90% complete 2. DMW FCC PCNs 90% complete 3. DMW RF system designs 30% complete 4. DMW Civil construction designs 10% complete 5. DMW network architecture prepared by Cisco 100% complete. Vendor solicitation for network routers initiated | 0 | N/A | 0 | Contractors has not requested permits | 0 | Civil construction has not commenced. Pre-construction coordination meetings held for Site 47: Santa Fe Radio Communication Bureau (RCB), Site 2: Albuquerque NOAA, and Site 3: Albuquerque RCB. Construction to begin in January 2012 on Site 47. | 0 | Hardware purchase orders not yet executed. Negotiating on data needed to prepare and execute purchase orders. | 0 | No network equipment yet installed. | 0 | No equipment yet deployed. | 0 | No network equipment yet installed. | 2012-01-24 19:50 | 2012-01-24 19:50 | 7092 | 7092 | Department of Information Technology | TRUE
NT10BIX5570097 | 2012 | Q1 | Q1 - 2012 | 6199 | 5702 | TRUE | 32 | All equipment was ordered (over $14M encumbered), but only 30% has been accepted and paid for during the quarter. Construction has been delayed awaiting final design completion and approvals. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $30,018,996 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $47,018,999 Expended $17,818,693 Percentage 38% 700MHz LTE Percentage Completed is based on: LTE $8,681,001 Cash Match $0.00 Total $8,681,001 Expended $0.00 Percentage 0% Overall Percentage Completed is based on: Middle Mile $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $17,818,693 Percentage 32% | 58 |  | Assumes management, administrative, and legal effort is linear across 36 month grant period. | 100 | No Variance | 82 | 100% of the DMW design has been completed, no design for LTE can start until an equipment decision has been made/directed. | 0 | N/A | 45 | Permits have been obtained for 13 of the 29 construction sites. Paperwork for remaining permits are in process. | 0 | Civil construction has not commenced. Pre-construction meetings have been held for Milan, Roswell, and Las Vegas SP sites. Construction can begin once contract amendments receive final approval. | 45 | All routers, radio's, antenna's, shelters and generators for DMW have been ordered. Of that 82% has been paid for. | 0 | No network equipment yet installed. Network implementation will proceed with the radio installation. Final network components for DMW should be completed in Q3Y3. | 1 | Batteries have been deployed to two sites final installs are scheduled for Q2Y3. Delays in contract processing has pushed out construction start dates. DMW Equipment (antennas, radios & routers) deployment will begin Q4Y2 and completed Q3Y3. | 0 | No network equipment yet installed. Testing will begin with the equipment deployment starting in Q4Y2 and should be completed in Q3Y3. | 2012-05-18 15:39 | 2012-05-18 15:39 | 7310 | 7310 | Department of Information Technology | TRUE
NT10BIX5570097 | 2012 | Q2 | Q2 - 2012 | 7021 | 6138 | TRUE | 54 | All equipment was ordered and has been accepted and paid for during the quarter. Construction has been started at over 20 sites: Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $30,018,996 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $47,018,999 Expended $29,817,370 Percentage 63% 700MHz LTE Percentage Completed is based on: LTE $8,681,001 Cash Match $0.00 Total $8,681,001 Expended $0.00 Percentage 0% Overall Percentage Completed is based on: Overall $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $29,817,370 Percentage 54% | 64 |  | Assumes management, administrative, and legal effort is linear across 36 month grant period. | 100 | No Variance | 82 | 100% of the DMW design has been completed, LTE has been put on hold until final resolution regarding LTE funding. | 0 | N\A | 83 | Permits have been obtained for 24 of the 29 construction sites. Paperwork for remaining permits are in process. | 75 | Site prep work has begun at 22 of the 29 sites. Several sites are nearing completion. | 57 | Area New Budget Amt. Spent %Spent Remaining % Remaining DMW 16,085,957.00 13,251,129.58 82% 2,834,827.42 18% LTE 7,117,501.00 0 0% 7,117,501.00 100% Overall 23,203,458.00 13,251,129.58 57% 9,952,328.42 43% Additional routers and network interface cards for redundancy will be ordered. | 0 | No network equipment yet installed. Network implementation will proceed with the radio installation. Final network components for DMW should be completed in Q3Y3. | 4 | Batteries have been deployed to five sites, final installs are scheduled for Q2Y3. Construction has started with several shelter and tower installations already being completed. DMW Equipment (antennas, radios & routers) deployment will begin Q3Y2 and completed Q3Y3. | 0 | No network equipment yet installed. Testing will begin with the equipment deployment starting in Q4Y2 and should be completed in Q3Y3. | 2012-08-10 16:56 | 2012-08-10 16:56 | 7310 | 7310 | Department of Information Technology | TRUE
NT10BIX5570097 | 2012 | Q3 | Q3 - 2012 | 7791 | 6597 | TRUE | 58 | All equipment was ordered and has been accepted and paid for during the quarter. Construction has been started at 24 sites. The numbers following are based on the new approved budget. Additional funds for Middle Mile have not been expended since the Route Modification is still in the approval process. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $32,374,810 Percentage 62.6% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0% Overall Percentage Completed is based on: Overall $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $32,374,810 Percentage 58% | 72 |  | Assumes management, administrative, and legal effort is linear across the 36 month grant period. | 100 | No variance. (note: a Route Modification Request has been submitted. Additional Environment Assessments may be required.) | 82 | 100% of DMW design has been completed. LTE is on hold. | 0 | NA | 83 | Permits for 24 sites have been received. Paperwork for remaining sites are in process. | 83 | Site preparation has been completed at 24 sites. | 67 | Area Budget Amt. Amt. Spent % Spent DMW $17,293,715.62 $13,147,457.53 76 LTE $ 2,443,000.00 $ 0.00 0 Overall $19,736,715.62 $13,147,457.53 67 Amounts are predicated on the new approved budget. | 0 | No network equipment has been installed yet. Network implementation will proceed with the radio installation. Final network components for DMW should be completed Q3Y3. | 40 | Shelters and generators have been installed at 15 sites. Batteries have been installed at 10 sites. Antennas and waveguides are being installed. Radio and routers for three regions have been shipped to Albuquerque for installation. | 0 | No network equipment has been installed. Testing will begin with the equipment deployment starting in Q4Y2 and should be completed in Q4Y3. | 2012-11-07 16:29 | 2012-11-07 16:29 | 7599 | 7599 | Department of Information Technology | TRUE
NT10BIX5570097 | 2012 | Q4 | Q4 - 2012 | 8337 | 7010 | TRUE | 68 | All equipment was ordered and has been accepted and paid for during the quarter. Construction has been started at 26 sites. The numbers following are based on the new approved budget. The Route Modification request has been approved adding 9 new sites to DMW. Equipment needed has been identified and we are receiving quotes. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $37,883,470 Percentage 73.3% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0% Overall Percentage Completed is based on: Overall $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $37,883,470 | 80 |  | Assumes management, administrative, and legal effort is linear across the 36 month grant period. | 100 | No Variance | 90 | Nine new sites for DMW were approved; currently working on the design changes. No LTE design has been done. | 0 | NA | 90 | Permits for two United State Forest Services Sites are pending | 90 | Site prep has been completed at all but two sites. | 75 | Area Budget Amt. Amt. Spent % Spent DMW $17,293,715.62 $14,908,008.41 86 LTE $ 2,443,000.00 $ 0.00 0 Overall $19,736,715.62 $14,908,008.41 75 | 0 | Some network equipment has been installed, but has not been brought up to an operational level yet. Network implementation will proceed with the radio installation. Final network components for DMW should be completed second quarter CY2013. | 70 | The following equipment has been installed: Shelters - 21 of 24 Towers - 21 of 25 Batteries - 22 of 37 Radio & network equipment has been deployed for installation. | 0 | Network equipment has been installed at a number of sites and been turned up for initial testing. Final testing will be completed in the second quarter of CY2013. | 2013-01-29 12:23 | 2013-01-29 12:23 | 7599 | 7599 | Department of Information Technology | TRUE
NT10BIX5570097 | 2013 | Q1 | Q1 - 2013 | 9189 | 8023 | TRUE | 72 | Additional equipment for the new approved sites was ordered. All previously ordered equipment has been accepted and paid for. Construction has been started and is ongoing at 26 sites. The numbers following are based on the last approved budget. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $40,031,426.99 Percentage 77.4% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0% Overall Percentage Completed is based on: Overall $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $40,031,426.99 Percentage 71.9% | 88 |  | Assumes management, administrative, and legal effort is linear across the 36 month grant period. | 100 | no variance | 100 | no variance | 0 | NA | 90 | Permits for two USFS sites are still pending | 90 | Site prep has been completed at all but two sites. | 75 | Area Budget Amt. Amt. Spent % Spent DMW $17,293,715.62 $14,931,987.53 86 LTE $ 2,443,000.00 $ 0.00 0 Overall $19,736,715.62 $14,931,987.53 75 Equipment for newly approved sites has been ordered, but not yet paid. | 7 | 126 DMW miles have been turned up for "burn in" and testing | 74 | The following equipment has been installed: Shelters - 21 of 24 Towers - 21 of 25 Batteries - 21 of 36 Radio & network equipment has been deployed for installation. | 0 | Network equipment has been installed at a number of sites and been turned up for initial testing. Final testing will be completed in the second quarter of CY2013. | 2013-04-18 15:19 | 2013-04-18 15:19 | 7599 | 7599 | Department of Information Technology | TRUE
NT10BIX5570097 | 2013 | Q2 | Q2 - 2013 | 10455 | 8874 | TRUE | 78 | Additional equipment for the new approved sites was ordered. All previously ordered equipment has been accepted and paid for. Construction has been started and is ongoing at 26 sites. The numbers following are based on the last approved budget. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $43,486,149 Percentage 84.1% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0% Admin & Legal Percentage Completed is based on: Total $2,708,999 Expended $1,464,819 Percentage 54% Admin funds have been expended for general project support to include legal support for LTE Spectrum Lease Agreement negotiations. Overall Percentage C | 97 |  | Assumes management, administrative, and legal effort is linear across the 36 month grant period. | 100 | No variance | 100 | No variance | 0 | NA | 90 | Permits for two USFS sites are still pending (insurance requirements). | 90 | Site prep has been completed at all but the two USFS sites. | 85 | Area Budget Amt. Amt. Spent % Spent DMW $17,293,715.62 $16,914,463.69 97.8 LTE $ 2,443,000.00 $ 0.00 0.0 Overall $19,736,715.62 $16,914,463.69 85.7 | 51 | Over 900 DMW miles have been turned up for "burn in" and testing. | 78 | The following equipment has been installed: Shelters - 21 of 24 Towers - 21 of 25 Batteries - 21 of 36 Radio & network equipment has been deployed for installation. | 0 | Network equipment has been installed at a number of sites and been turned up for initial testing. Final testing will be completed in the third quarter of CY2013. | 2013-07-31 11:48 | 2013-07-31 11:48 | 7599 | 7599 | Department of Information Technology | TRUE
NT10BIX5570097 | 2013 | Q3 | Q3 - 2013 | 11221 | 9401 | TRUE | 80 | Additional equipment for the new approved sites was ordered. All previously ordered equipment has been accepted and paid for. Construction has been started and is ongoing at 26 sites. The numbers following are based on the last approved budget. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $31,984,498 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $48,984,501 Expended $43,057,388 Percentage 87.9% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0.0% Admin & Legal Percentage Completed is based on: Total $2,708,999 Expended $1,464,819 Percentage 58.7% Admin funds have been expended for general project support to include legal support for LTE Spectrum Lease Agreement negotiation | 58 |  | Assuming management, administrative, and legal effort is linear across the 60 month grant period, this would be considered 65% complete. Based on actual expenditures, the percentage complete would be 58.7% | 100 | No variance | 100 | No variance | 0 | NA | 88 | No variance; permission to begin/permits from USFS Santa Fe were received in September. There are no planned construction permits for LTE since we will be utilizing existing infrastructure. There may be af few individual permits for the new antennas/systems. | 90 | Site prep has been completed at all by the two USFS sites | 85 | Area Budget Amt. Amt. Spent % Spent DMW $17,293,715.62 $17,331,460.97 100.22 LTE $ 2,443,000.00 $ 000000000.00 0.0 Overall $19,736,715.62 $17,331,460.97 87.81 | 64 | Nearly 1300 DMW miles have been turned up for "burn in" and testing | 88 | The following DMW equipment has been installed: Shelters - 22 of 24 Towers - 23 of 25 Batteries - 34 of 36 Radio & network equipment has been installation at all but three sites. | 83 | Network equipment has been installed at all but 4 DMW sites and been turned up for initial testing. Three DMW sites and and estimated 9 LTE remain to be finished. Final testing of DMW sites will be completed in the second quarter of CY2014. | 2013-11-08 10:59 | 2013-11-08 10:59 | 7599 | 7599 | Department of Information Technology | TRUE
NT10BIX5570097 | 2013 | Q4 | Q4 - 2013 | 11875 | 10046 | TRUE | 82 | Additional equipment for the new approved sites was ordered. All previously ordered equipment has been accepted and paid for. Construction has been started and is ongoing at 26 sites. The numbers following are based on the last approved budget. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $31,984,498 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $48,984,501 Expended $43,760,075 Percentage 89.3% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0 Total $4,006,500 Expended $0 Percentage 0.0% Admin. & Legal Percentage Completed is based on: Total $2,708,999 Expended $2,358,455 Percentage 87.1% Admin. funds have been expended for general project support | 63 |  | Assuming management, administrative, and legal effort is linear across the 60 month grant period, this would be considered 68% complete. Based on actual expenditures, the percentage complete would be 63.0%. | 100 | No variance | 100 | No variance | 0 | NA | 88 | No variance; permission to begin/permits from USFS Santa Fe were received in September. There are no planned construction permits for LTE since we will be utilizing existing infrastructure. There may be a few individual permits for the new antennas/systems. | 90 | Site prep has been completed at all but two of the USFS sites. | 87 | Area Budget Amt. Amt. Spent % Spent DMW $17,293,715 $16,687,691 96.5 LTE $ 2,443,000 $0 0.0 Overall $19,736,715 $16,687,691 84.5 | 64 | Nearly 1400 DMW miles have been turned up for "burn in" and testing. | 90 | The following DMW equipment has been installed: Shelters - 22 of 24 Towers - 23 of 25 Batteries - 36 of 36 Radio & network equipment has been installed at all but two sites. | 83 | Network equipment has been installed at all but 2 DMW sites and been turned up for initial testing. Two DMW sites and estimated 9 LTE remain to be finished. Final testing of DMW sites will be completed in the second quarter of CY2014. | 2014-02-24 13:05 | 2014-02-24 13:05 | 7599 | 7599 | Department of Information Technology | TRUE
NT10BIX5570098 | 2010 | Q4 | Q4 - 2010 | 1205 | 2237 | TRUE | 2 | N/A | 0 | N/A | N/A | 65 | N/A | 3 | N/A | 0 | N/A | 3 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-17 13:25 | 2011-02-17 13:25 | 6104 | 6104 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2011 | Q1 | Q1 - 2011 | 2083 | 2787 | TRUE | 3 | Project is under running view by 2%, largely due to deferral of some key environmental work as noted below. | 0 |  | NA | 76 | Environmental work is under running by 14% due to accessibility to some federal lands. These studies were deferred until next quarter once a Programmatic Agreement is in place and work can complete. An additional 5% spent in this period was not booked in this quarter, due to late billing by vendor. | 22 | Network design work is exceeding view by 1%, due to a slight increase in start up effort to route alignment for input to environmental studies. | 2 | Right of Way work is under running view due to dependency on a final route alignment before negotiations begin. We expect to see this gap close over the next quarter as resources are brought to bear. The delay is consistent with the delayed FONSI / CEQA date. | 20 | Permits are under-running view by 20%, in part due to delays by Federal and State Agencies in determining their assessments. (10% of this budget was actually booked the week following the quarter.) Permits from Fish and Wildlife and California Department of Fish and Game are expected once the Area of Potential Effect (APE) is determined in critical habitats. Again, this is tied to delays in the completed environmental assessment | 0 | No Variance | 1 | This line item is under running by 4%. Equipment procurement has been largely confined to motor vehicles and office and engineering equipment. We delayed purchase of motor vehicles until the next quarter. | 0 | No Variance | 0 | Equipment will not be deployed until FONSI is issued. The initial 5% was intended to supply electronics to the node manufacturer, which has been delayed into the next two quarters. | 0 | No Variance | 2011-05-17 11:27 | 2011-05-17 11:27 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2011 | Q2 | Q2 - 2011 | 2991 | 3253 | TRUE | 5 | Underrun by 7%. While there had been an acceleration of spending from the previous quarter, overall project under ran this quarter largely due to withholding activities (such as permits and initial materials orders) that are dependent on the issuance of a FONSI | 0 |  | NA | 98 | Underrun by 2%. Revisions to the environmental assessment extended through June with agency and public commentary beginning in July. Field work continued into June due to delays in survey permits from Federal agencies and requirements to refine alignment. A Programmatic Agreement was circulated in May. Expenditures for the draft EA is expected in July-August timeframe. | 34 | Underrun by 3% - Due to route modifications to accommodate preliminary feedback on environmental assesment. Detailed design of alignment completed, with all engineering staffing in place, trained and equipped. Digital base maps completed and alignment fielded. Sample Working Drawings socialized with Agencies for Permit requirements on backbone route. Distribution designs completed for two communities. | 15 | Underrun by 45%. Title searches completed on private lands. Legal descriptions initiated and largely completed for major federal land management agencies (BLM, USFS). Tribal lands identified. Requirements for DOT agencies defined. No ROWs have been purchased, pending FONSI. | 25 | Underrun by 48%. Construction permits from key state and federal agencies will require the issuance of the FONSI. Permits that can be issued prior to that have been paid. Payment for DOT permits will occur as they are submitted and approved. | 1 | Underrun by 27%. No site preparation until occur until after FONSI has been issued. Expenditures to date have been for options on sites in Barstow, Ridgecrest, Kramer Junction, and Carson City | 0 | Underrun by 12%. The baseline plan called for the initial acquisition of Node buildings in this Quarter. This has been deferred until the September timeframe to meet permitting objectives in October. There is no need to acquire structures at this time only to store them. The equipment RFP will be issued in August for electronics and nodes. | 0 | No Variance | 8 | No Variance | 0 | No Variance | 2011-08-09 18:10 | 2011-08-09 18:10 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2011 | Q3 | Q3 - 2011 | 3965 | 3821 | TRUE | 7 | 25% Variance. Environmental Assessment delayed until December. Cable, conduit & vault contracts awarded, in final stages of construction Request for Proposals evaluation. | 0 |  | NA | 98 | 2% Variance. All studies submitted, public comments submitted, compiled and analyzed. Programmatic Agreement fully signed and waiting execution. Certificate of Public Convenience and Necessity documentation prepared for California Public Utilities Commission submission. Biological technical reports prepared. | 60 | Ahead 7%. Backbone field work complete. Digital maps finalized. Ortho complete. Working drawings 80% complete. CAD work in progress. Distribution design work started. | 89 | No Variance. All federal & state applications submitted. In negotiation with counties. Resolving private Right of Way issues. | 60 | 40% Variance. Permit requirements known & processes in place for review prior to Certificate of Public Convenience and Necessity issuance. | 6 | 60% Variance. Node locations identified, pre-surveyed and mapped. Request for Proposals Statement of Work prepared for site improvements. | 12 | 10% Variance. Vendor review & Request for Information completed for electronics. | 0 | 25% Variance. Initiation of Construction pending Finding of No Significant Impact, Mitigated Negative Declaration and permits. | 8 | 14% Variance. Equipment deployment pending Finding of No Significant Impact. | 0 | No Variance. Construction not Started | 2011-11-10 15:34 | 2011-11-10 15:34 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2011 | Q4 | Q4 - 2011 | 5127 | 4794 | TRUE | 14 | 34% Variance - In the areas we control, we've made significant progress. In areas where others control (permits) we have been restrained. | 0 |  | NA | 95 | 5% Variance- 110 additional cultural sites identified and three signatories added to Programmatic Agreement that increases scope of work. Potential requirement to recirculate the Master Cultural Resources Report of complete cycle of signatories after a 30 day review period. Due to the additional work added our overall percentage decreased 3% since last quarter. | 85 | Ahead 22% - Backbone cable design completed, distribution engineering 60% complete and 67% of anchor site surveys completed. | 95 | 5% Variance - Private ROW issues, BIA and Tribal issues to be resolved . | 75 | 25% Variance - Backbone pending 30-60 day agency review cycle. Most construction permits are formerly issued "at the counter" immediately before segment construction begins. | 25 | 75% Variance - Architectural renderings and site engineering complete and site prep RFP issued. No construction has begun due to lack of FONSI. | 60 | Ahead 6% - All major items to build backbone (conduit, cable, and vaults) have been contracted. | 10 | 34% Variance - Material deliveries substantially underway. All depots sites established and fully operational. | 12 | 33% Variance - Receiving deliveries of cable, conduit and vaults in northern construction zone. Tools, equipment and motor vehicles acquired. | 0 | 6% Variance - Construction Not Started | 2012-02-17 18:59 | 2012-02-17 18:59 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2012 | Q1 | Q1 - 2012 | 6333 | 5769 | TRUE | 19 | 39% Variance - As reported last quarter we are successful acquiring project resources , e.g. materials, personnel and equipment but inhibited by the Finding of No Significant Impact/National Environmental Policy Act process still underway during the quarter, preventing significant physical process and spending. | 0 |  | NA | 95 | 5% variance - Several Mitigation Monitoring & Reporting Plan revisions conducted, US Fish and Wildlife Service Biological Opinion delayed until March 1. Programmatic Agreement Segment Reporting Processes resolved. Initial Segment Reports released for review by Agencies. Added more resources to assist in final efforts to complete Environmental Assessment and prepare Monitoring Plan. | 88 | Ahead by 14% - Backbone cable design complete, (3) segments being revised due to closure on conduit arrangements, distribution engineering 70% complete, construction distribution Request for Proposal pending and 85% of anchor site surveys completed. | 97 | 3% variance - private Right of Way issues resolved, Bureau of Indian Affairs and Tribal issues still pending. Waiting for Finding of No Significant Impact so that United States Forest Service and Bureau of Land Management can issue Licenses. Complete agreements with Counties, LA Department of Water and Power, Navy, and State Lands Commission. | 75 | 25% Variance - Agency reviews of permit applications under way, requiring additional details and information requests. Most permits are expected in April. | 35 | 65% variance - All architectural drawings and site engineering complete. Decision made to do site preparation in house. No construction work has commenced due to lack of Finding of No Significant Impact. | 65 | Ahead by 1% -. Equipment Request for Proposals issued, vendors responded, awards pending. All materials (conduit, vaults and cable) arriving per schedule. | 10 | 42% Variance - Project start pending Finding of No Significant Impact, and various California Agency Permits. | 20 | 36% variance - tools, equipment, motor vehicles and project materials continue to be accrued for project start. Fiber electronics not deployed due to delays in Finding of No Significant Impact, node construction and site preparation. | 0 | 15% variance - Construction not started. | 2012-05-29 16:09 | 2012-05-29 16:09 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2012 | Q2 | Q2 - 2012 | 6847 | 6050 | TRUE | 30 | 45% Variance - Once the Programmatic Agreement is signed by all Stakeholders, the variance will significantly decrease due acquiring the final permits and the commencement of underground construction. | 0 |  | NA | 96 | 4% Variance - Completed 40% of the work on the Programmatic Agreement. | 90 | Ahead by 5% - All backbone and design work has been completed in California and working drawings three segments in Carson City in development. Remaining engineering expected to continue through construction phase as issues arise. | 98 | 2% Variance - Rights of Way have been acquired throughout the entire route with the exception. Currently awaiting final resolution with three tribal groups and Rights Of Way from the United States Navy and United States Air Force. | 80 | 20% Variance - Construction plans have been review by all agencies, including Department of Transportation. Issuance of Notice to Proceed by the agencies will be based upon the release of the Programmatic Agreement Segment Groups. | 35 | 65% Variance - All architectural drawings and site engineering complete. No construction work has commenced due to lack of Programmatic Agreement approval. | 90 | Ahead by 12% - All Request for Proposals have been issued and awaiting delivery. All materials (conduit, vaults and cable) arriving per schedule. | 10 | 65% Variance - Project start pending Programmatic Agreement and obtaining various permits. | 20 | 54% Variance - Tools, equipment, motor vehicles and project materials are in place for project start. Equipment will be deployed once the programmatic agreement is approved. | 0 | 25% Variance - Construction not started. | 2012-08-03 12:00 | 2012-08-03 12:00 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2012 | Q3 | Q3 - 2012 | 8123 | 6769 | TRUE | 37 | (53% Variance) Section 106 approval and execution of the Programmatic Agreement schedule delayed initiation of construction. | 0 | true | NA | 97 | (3% Variance) Programmatic Group Segment approvals needed from Groups 5, 6, 7, 8, 9, and 10. | 92 | (5% Variance) Working drawings for distribution to be finalized, as well as Community Anchor Institutions and Points of Interconnection designs. | 99 | (1% Variance) Tribal allotments in Nevada are to be finalized and issued by the Bureau of Indian Affairs. | 90 | (10% Variance) Awaiting encroachment/building permits as Programmatic Agreement approvals commence. | 50 | (50% Variance) Node site preparation for 6 sites awaiting | 92 | No Variance | 20 | (73% Variance) Conduit construction and nodes aggressively began in August, when Section 106 permission was obtained. Project is about 120 days late beginning. | 40 | (52% Variance) Once node construction is finalized in approved segments, the equipment will be deployed. | 0 | (41% Variance) Insufficient cable and equipment placed for testing. | 2012-11-28 16:09 | 2012-11-28 16:09 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2012 | Q4 | Q4 - 2012 | 9025 | 7796 | TRUE | 46 | 49% Variance - Due to delayed permit and winter conditions. This gap will be closed rapidly Q1 2013. | 0 |  | NA | 98 | 2% Variance - Due to final approval of Segment Groups 8 through 10, and three remaining on Group Segment 6. All are currently planned to finalize in current quarter | 95 | No Variance - Final anchor designs underway | 99 | 1% Variance - Tribal agreements in place, waiting for final Bureau of Indian Affairs documentation, to be attained in February | 95 | 5% Variance - Still need 19 Caltrans Encroachment permits, City of Ridgecrest, and Bishop. Caltrans permits dependent on Programmatic Agreement Group Segment approvals. City permits in progress. | 50 | 50% Variance - Waiting for Programmatic Agreement approvals for 4 node sites, and City of Barstow building permit | 98 | Ahead by 1% - Waiting on last requirements as construction enters final phase to avoid excess inventory. | 35 | 62% Variance - Cable and conduit in 33% of the backbone, 50% nodes, no distribution and anchors yet completed. Fourth Quarter presented weather and holiday setbacks. Most work completed were in challenging areas. | 45 | 53% Variance - Due to holdup of electronics deployment. Have installed alarms and other supporting gear in nodes. Validating electronics and OSS integration before deploying fiber gear. | 30 | 40% Variance - Have tested 99 miles of fiber, and 50% of environmental support equipment in 5 nodes. | 2013-02-27 15:37 | 2013-02-27 15:37 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2013 | Q1 | Q1 - 2013 | 9937 | 8512 | TRUE | 58 | Variance 40% - Due to late permitting and heavy winter. | 0 |  | NA | 99 | Variance 1% - Due to requirement by Inyo National Forest to resurvey two segments (approximately 8 miles) | 99 | No Variance | 100 | No Variance - All rights-of-way completed | 99 | Variance of 1% - Due to six segments waiting for Caltrans Encroachment permits and the two segment approvals on Inyo National Forest Land. | 100 | No Variance - All completed | 98 | Ahead by 1% - Waiting on last requirements as construction enters final phase to avoid excess inventory. | 52 | Variance of 48% - Due to late Programmatic Agreement approvals(permitting), Nevada Department of Transportation special requirements and heavy winter. A total of 302 trench miles have completed. | 90 | Variance of 9% - Due to two nodes not deployed | 50 | Variance of 35% - Due inability to complete end-to-end testing between nodes as a result of winter conditions and environmentally sensitive areas that still require boring. | 2013-05-28 15:08 | 2013-05-28 15:08 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2013 | Q2 | Q2 - 2013 | 10535 | 8922 | TRUE | 83 | 17% Variance - Due to late construction start due to Programmatic Agreement requirements and execution, delays in permit issuance and route changes. The latter consist of anchor routes and five changes required on the backbone. | 0 |  | NA | 99 | 1% Variance - Due to required special studies for Inyo National Forest Service and to acquire approvals for route changes on distribution and anchor work. | 99 | 1% Variance - Due to pending approval of distribution/anchor route changes, approval of revised environmental plan for the Inyo National Forest Service and new design work needed to comply with the revised California Public Utilities Commission pole loading parameters. | 100 | No Variance - All rights-of-way completed | 99 | 1% Variance - Due to pending approval of distribution/anchor route changes and approval of revised environmental plan required by the Inyo National Forest Service. | 100 | No Variance - All Site Preparation completed | 100 | No variance from baseline plan | 88 | 12% Variance - Due to P.A. Segment approval for Segment M122, only 50% of distribution cabling being completed and remaining Community Anchor Institution service entrance facilities being completed. | 100 | No variance from baseline plan | 65 | 35% Variance - Due to incomplete end to end fiber spans held up by multiple NDOT parallel drainage variance approvals, multiple ESA long bores and delayed P.A. segment approval for M122. | 2013-08-09 11:43 | 2013-08-09 11:43 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2013 | Q3 | Q3 - 2013 | 11325 | 9463 | TRUE | 95 | 5% Variance - The overall project has been delayed by the completion of Segment M122 and the outcome of the supplemental funding request made to the California Public Utility Commission that was just approved. | 0 |  | NA | 99 | 1% Variance - Resurveyed and are awaiting approval of Segment M122 delayed construction by the Inyo National Forest Service. | 100 | No Variance | 100 | No Variance | 99 | 1% Variance - All permits acquired except for the Round Valley School Extension, Lone Pine Tribe Tribal Office and AT&T Poverty Hills Rd connections that are pending CEQA approval. | 100 | No Variance | 100 | No Variance | 95 | 5% Variance - Due to Completing all remaining distribution cable placing, splicing and anchor service connections in the Bishop, Lone Pine, Mammoth Lakes, June Lake and Walker communities that were delayed pending the outcome of the additional project funding request . | 100 | No Variance | 85 | 15% Variance - The pending construction of M122 is preventing us from testing the the backbone segments from Mammoth Lakes south to Bishop. When done all fiber conformance and characteristic testing will be completed. As the remaining Anchor and Points of Interconnections are completed they are also tested and built into the Network Operations System. | 2013-11-21 13:02 | 2013-11-21 13:02 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2013 | Q4 | Q4 - 2013 | 11873 | 10045 | TRUE | 100 | Late permitting for the Johannesburg Community work and a ROW private property issue in Benton did not get resolved until late December 2013. Construction work was carried over into 2014 because of it. We have expended 101% of our overall budget. | 0 |  | NA | 99 | 1% Variance - Anchor service connection re-routes still pending approval by the NTIA. | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 99 | 1% Variance - Service connections to Community Anchor Institutions and Points of Interconnections are still being tested due to the earlier delays in completing project construction. | 100 | No Variance | 95 | 5% Variance - An issue has surfaced with the Network Interface Device and the Operational Support System that has delayed Community Anchor Institutions and Points of Interconnection service activation. The problem has been escalated to the equipment providers for resolution. | 2014-02-24 12:23 | 2014-02-24 12:23 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570099 | 2010 | Q4 | Q4 - 2010 | 1327 | 2350 | TRUE | 0 | We originally projected to be 2% complete with the overall project in Q4 2010. However, to comply with competitive procurement requirements, we released RFP for EA support and worked on development of an RFP for Engineering. We have also been working with Merit Network to coordinate logistics of a shared portion of our route with their Round 1 project. These processes took longer than anticipated. We plan to be back on schedule by Q2 2011. | 0 |  | N/A | 0 | We originally projected to be 95% complete with the Environmental Assessment in Q4 2010. However, to comply with competitive procurement requirements, we released an RFP for EA support, and the RFP process took longer than anticipated. We plan to submit our draft EA on time and be back on schedule by next quarter | 0 | We originally projected to be 20% complete with the network design in Q4 2010. However, to comply with competitive procurement requirements, we worked on development of an RFP for Engineering. We have also been working with Merit Network to coordinate logistics of a shared portion of our route with their Round 1 project. These processes have taken longer than anticipated. We plan to be back on schedule by Q2 2011. | 0 | We originally projected to be 15% complete with the rights of way in Q4 2010. However, to comply with competitive procurement requirements, we worked on development of an RFP for Engineering. We have also been working on revisions to our route for efficiencies. These processes have taken longer than anticipated. We plan to be back on schedule by Q3 2011. | 0 | We originally projected to be 15% complete with the construction permits in Q4 2010. However, to comply with competitive procurement requirements, we worked on development of an RFP for Engineering. We have also been working on revisions to our route for efficiencies. These processes have taken longer than anticipated. We plan to be back on schedule by Q2 2011. | 0 | We originally projected to be 25% complete with the site preparation in Q4 2010. However, development of an RFP for Engineering has taken longer than anticipated, and we are still working to finalize our route. We plan to be back on schedule by Q3 2011. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-23 11:36 | 2011-02-23 11:36 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2011 | Q1 | Q1 - 2011 | 1965 | 2728 | TRUE | 1 | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 6% completion of the overall project. However, as stated last quarter, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to make significant overall project progress by the end of Quarter 2, 2011. | 0 |  | N/A | 95 | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the Environmental Assessment. However, as stated last quarter, there were some initial delays due to procurement requirements. Bloomingdale Communications, Inc. did select the Environmental Assessment firm through the Request for Proposals process in this quarter therefore the draft Environmental Assessment was submitted on time. However, National Telecommunications and Information Administration provided Bloomingdale Communications, Inc. with a list of items to address for the final Environmental Assessment Most of these items have been addressed, however Bloomingdale Communications, Inc. is awaiting for the Section 106 completion. Bloomingdale Communications, Inc. plans to be back on schedule by the end of Quarter 2, 2011. | 5 | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 70% completion of the Network Design. However, as stated last quarter, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to make significant network design progress by the end of Quarter 2, 2011. | 0 | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 90% completion of the Rights of Way. However, as stated last quarter, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to make significant rights of way progress by the end of Quarter 2, 2011. | 0 | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 90% completion of the Construction Permits and Other Approvals. However, as stated last quarter, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering RFP process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to make significant construction permits and other approval progress by the end of Quarter 2, 2011. | 0 | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 40% completion of the Site Preparation. However, as stated last quarter, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to make significant site preparation progress by the end of Quarter 2, 2011. | 0 | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 0% completion of the Equipment Procurement, therefore on target as projected in the baseline plan. | 0 | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 5% completion of the Network Build. However, as stated last quarter, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. anticipates the network build to be pushed back one quarter later than initially projected. | 0 | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 0% completion of the Equipment Deployment, therefore on target as projected in the baseline plan. | 0 | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 0% completion of the Network Testing, therefore on target as projected in the baseline plan. | 2011-05-12 12:04 | 2011-05-12 12:04 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2011 | Q2 | Q2 - 2011 | 2979 | 3247 | TRUE | 6 | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 20% completion of the overall project. However, the projected percent complete goal that was submitted last quarter was met this quarter and the project will begin to move rapidly now the Finding of No Significant Impact has been issued, the engineering staking was completed, the fiber vendor selected, and with warmer weather here, Bloomingdale Communications, Inc. plans to make significant overall project progress by the end of Quarter 3 in 2011. | 0 |  | N/A | 100 | Completed this period, therefore on target as projected last quarter. | 60 | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the Network Design. However, the projected percent complete goal that was submitted last quarter was met this quarter and the project will begin to move rapidly now the Finding of No Significant Impact has been issued, the engineering staking was completed, the fiber vendor selected, and with warmer weather here, Bloomingdale Communications, Inc. plans to make significant network design progress by the end of Quarter 3 in 2011. | 50 | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the Rights of Way. However, the projected percent complete goal that was submitted last quarter was met this quarter and the project will begin to move rapidly now the Finding of No Significant Impact has been issued, the engineering staking was completed, the fiber vendor selected, and with warmer weather here, Bloomingdale Communications, Inc. plans to make significant rights of way progress by the end of Quarter 3 in 2011. | 50 | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the Construction Permits and Other Approvals. However, the projected percent complete goal that was submitted last quarter was met this quarter and the project will begin to move rapidly now the Finding of No Significant Impact has been issued, the engineering staking was completed, the fiber vendor selected, and with warmer weather here, Bloomingdale Communications, Inc. plans to make significant construction permits and other approvals progress by the end of Quarter 3 in 2011. | 0 | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 75% completion of the Site Preparation. However, the projected percent complete goal that was submitted last quarter was met this quarter and the project will begin to move rapidly now the Finding of No Significant Impact has been issued, the engineering staking was completed, the fiber vendor selected, and with warmer weather here, Bloomingdale Communications, Inc. plans to make significant site preparation progress by the end of Quarter 3 in 2011. | 0 | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 5% completion of the Equipment Procurement. However, the projected percent complete goal that was submitted last quarter was met this quarter and the project will begin to move rapidly now the Finding of No Significant Impact has been issued, the engineering staking was completed, the fiber vendor selected, and with warmer weather here, Bloomingdale Communications, Inc. plans to make significant equipment procurement progress once the outside plant construction contract is awarded. | 0 | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 25% completion of the Network Build. However, the projected percent complete goal that was submitted last quarter was met this quarter and the project will begin to move rapidly now the Finding of No Significant Impact has been issued, the engineering staking was completed, the fiber vendor selected, and with warmer weather here, Bloomingdale Communications, Inc. plans to make significant network build progress by the end of Quarter 3 in 2011. | 0 | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 0% completion of the equipment deployment, therefore on target as projected in the baseline plan. | 0 | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 0% completion of the network testing, therefore on target as projected in the baseline plan. | 2011-08-09 14:53 | 2011-08-09 16:50 | 5995 | 5994 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2011 | Q3 | Q3 - 2011 | 3907 | 3792 | TRUE | 4 | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 40% completion of the overall project. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 75 | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the network design. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 80 | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the rights of way. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 80 | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the construction permits and other approvals. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 0 | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the site preparation. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 0 | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 90% completion of the equipment procurement. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 0 | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 75% completion of the network build. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 0 | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 0% completion of the network deployment, therefore on target as projected in the baseline plan. | 0 | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 25% completion of the network testing. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 2011-11-07 14:15 | 2011-11-07 14:15 | 5994 | 5994 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2011 | Q4 | Q4 - 2011 | 4987 | 4662 | TRUE | 9 | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the overall project. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. The contractor has now been selected and is expected to start construction Spring of 2012. Merit did begin installing conduit in the overlapping portion of the project. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 80 | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the network design. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 90 | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the rights of way. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 80 | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the construction permits and other approvals. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 0 | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the site preparation. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 0 | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the equipment procurement. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 0 | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the network build. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 0 | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the equipment deployment. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion.. | 0 | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the network testing. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 2012-02-14 07:58 | 2012-02-14 07:58 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2012 | Q1 | Q1 - 2012 | 6197 | 5701 | TRUE | 12 | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. The contractor has now been selected and construction began this quarter. Merit continued installing conduit in the Merit/Bloomingdale joint build portion of the project. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 80 | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the network design. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 95 | For Year 2 Quarter 3 of the award period which is this quarter (Quarter1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the rights of way. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 95 | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the construction permits and other approvals. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 15 | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the site preparation. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 0 | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the equipment procurement. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing the Request for Proposals and reissuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. The equipment Request for Proposal is scheduled to go out by the end of May in next quarter, therefore this will begin to move forward as the project is taking off since construction began this quarter. | 11 | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the network build. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 0 | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the equipment deployment. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and reissuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion.. | 0 | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the network testing. Variance from baseline projection is due to Finding of No Significant Impact that took longer than expected as well as completing all the Request for Proposals and re-issuing of the construction proposal due to budget constraints, which lengthened the construction timeline for completion. | 2012-05-18 14:13 | 2012-05-18 14:13 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2012 | Q2 | Q2 - 2012 | 6973 | 6114 | TRUE | 28 | Based on expenditures, BCI is 28% complete with the overall project. This is not as high of a percent as projected last quarter of 35% mainly due to not receiving invoices regarding the joint build portion of the project. Only a small percentage of that budget has been paid out to date for the joint build. The BCI project is moving along rapidly as expected. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 98 | N/A, this is the percentage predicted at the end of last quarter for this quarter. | 98 | N/A, this is the percentage predicted at the end of last quarter for this quarter. | 100 | N/A, this is the percentage predicted at the end of last quarter for this quarter. | 20 | This percentage is lower than predicted at the end of last quarter of 50%. The RFP for the two huts was not released as early in this quarter as BCI predicted, therefore the contract will not be executed until early next quarter. This portion will be back on schedule shortly as the contract has been awarded and the huts are being constructed and should be delivered middle of next quarter. | 5 | This percentage is slightly ahead of the prediction of 0% last quarter. The necessary equipment for the project was analyzed, the RFP was finalized, and responses are being reviewed. The vendor will be selected early next quarter after a technical presentation and then the equipment ordering will take place and begin moving along. | 34 | This percentage is lower than predicted last quarter of 43% mainly due to not receiving invoices regarding the joint build portion of the project. BCI had estimated this portion of the project being completed by now, however is still in the process and only one invoice had been received by the end of this quarter for the joint build. | 0 | N/A, this is the percentage predicted at the end of last quarter for this quarter. | 0 | N/A, this is the percentage predicted at the end of last quarter for this quarter. | 2012-08-09 15:03 | 2012-08-09 15:03 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2012 | Q3 | Q3 - 2012 | 8131 | 6773 | TRUE | 51 | Based on expenditures, BCI is 51% complete with the overall project. This is not as high of a percent as projected last quarter of 69% mainly due to not paying for any transport equipment as expected this quarter. The BCI project is moving along rapidly as expected. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 98 | N/A, this is the percentage predicted at the end of last quarter for this quarter. | 99 | Expected to be 100% complete by the end of this quarter, however still finishing up the signing of Covert Public Schools easement and working on the Gobles easement. These easements should be completed early next quarter. Also, the pole attachment permit in Gobles should be obtained next quarter. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 90 | N/A, this is the percentage predicted at the end of last quarter for this quarter. | 5 | The vendor was selected this quarter. Transport equipment was ordered, however the equipment has not been paid for yet by BCI, therefore this percentage is behind last quarter's prediction. Next quarter it should be caught back up as the equipment should be paid for then and installed. | 66 | N/A, this is the percentage predicted at the end of last quarter for this quarter. | 0 | N/A, this is the percentage predicted at the end of last quarter for this quarter. | 0 | N/A, this is the percentage predicted at the end of last quarter for this quarter. | 2012-11-29 10:09 | 2012-11-29 10:09 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2012 | Q4 | Q4 - 2012 | 8995 | 7775 | TRUE | 65 | Based on expenditures, BCI is 65% complete with the overall project. This is not as high of a percent as projected last quarter of 88% mainly due to paying for only a small portion of the equipment which is less than expected this quarter. The BCI project is moving along rapidly as expected and is nearing completion where contracts will be closed out and paid in full. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 98 | N/A, this is the percentage predicted at the end of last quarter for this quarter. Network Design is complete until final stage just before network deployment. | 100 | N/A, this is the percentage predicted at the end of last quarter for this quarter. All rights of ways for easements were obtained this quarter. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | N/A, this is the percentage predicted at the end of last quarter for this quarter. The initial site preparation was complete this quarter with all fiber complete and cement pads poured. | 5 | The equipment has not been paid for yet by BCI, therefore this percentage is behind last quarter's prediction of 83%. The transport equipment has been received, therefore next quarter this category should be caught back up as the equipment will be installed and majority should be paid. Significant progress is expected for Equipment Procurement and Equipment Deployment next quarter. | 90 | N/A, this is the percentage predicted at the end of last quarter for this quarter. Network Build is continuing rapidly and a lot of progress has been made. | 45 | The cabinets have been placed and the CAI CPE has began to be installed, however transport equipment as notated above has not been installed at this point. The transport equipment has been received and will have significant progress next quarter being installed. | 75 | N/A, this is the percentage predicted at the end of last quarter for this quarter. Network Testing is well underway. As noted above, a few areas of the network needed new fiber re-buried and re-testing taking place. | 2013-02-27 08:29 | 2013-02-27 08:29 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2013 | Q1 | Q1 - 2013 | 9811 | 8441 | TRUE | 82 | Based on expenditures, BCI is 82% complete with the overall project. This is not as high of a percent as projected last quarter of 96% mainly due to the equipment purchased to date being less expensive as initially budgeted. he BCI project is moving along rapidly as expected and is nearing completion where contracts will be closed out and paid in full. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 99 | N/A, this is the percentage predicted at the end of last quarter for this quarter. Network Design is complete until final stage just before network deployment. | 100 | N/A, this is the percentage predicted at the end of last quarter for this quarter. All rights of ways for easements were obtained this quarter. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | N/A, this is the percentage predicted at the end of last quarter for this quarter. The initial site preparation was complete this quarter with all fiber complete and cement pads poured. | 72 | The equipment was installed this quarter and has begun to be paid for by BCI. This percentage is behind last quarter's prediction of 95% mainly due to the equipment purchased to date being less expensive than initallly budgeted. | 95 | N/A, this is the percentage predicted at the end of last quarter for this quarter. Network Build is continuing rapidly and a lot of progress has been made. | 95 | N/A, this is the percentage predicted at the end of last quarter for this quarter. Equipment deployment is continuing rapidly and a lot of progress has been made. | 98 | N/A, this is the percentage predicted at the end of last quarter for this quarter. Network Testing is well underway. As noted above, one area of the network needed re-spliced and re-testing taking place. | 2013-05-20 09:32 | 2013-05-20 09:32 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2013 | Q2 | Q2 - 2013 | 10647 | 8984 | TRUE | 89 | Based on expenditures, BCI is 89% complete with the overall project. This is not as high of a percent as projected last quarter of 99% mainly due to the amended contract for additional equipment. This equipment will be installed next quarter and paid for then. The BCI project is moving along rapidly as expected and is nearing completion where contracts will be closed out and paid in full. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 99 | N/A, this is the percentage predicted at the end of last quarter for this quarter. Network Design is not complete until final stage just before network deployment of all project equipment, etc. | 100 | Completed Year 3 in 3rd Quarter, which was Quarter 1 of 2013. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | Completed Year 3 in 3rd Quarter, which was Quarter 1 of 2013. | 71 | The initial contract equipment was installed this quarter and paid for by BCI, however the budget was revised during the quarter and money moved into this budget item from another for the amended equipment contract. This budget change caused the overall percentage to decrease by 1% from last quarter even though additional money was expended in this budget category throughout this quarter. During the next quarter, the additional amended contract equipment will be received and installed as well as paid for in full. | 99 | N/A, this is the percentage predicted at the end of last quarter for this quarter. Network Build is continuing rapidly and a lot of progress has been made as CAIs have been connected. | 98 | Equipment deployment is continuing rapidly and a lot of progress has been made. CAIs are connected and utilizing the new network, however this percentage is slightly lower than last quarters prediction due to the DC power, HVAC upgrade, and amended additional Cyan equipment being installed next quarter. | 99 | N/A, this is the percentage predicted at the end of last quarter for this quarter. Network Testing is complete for the new transport network, however additional testing well be necessary once the amended contract Cyan equipment is installed next quarter. | 2013-08-20 09:36 | 2013-08-20 09:36 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2013 | Q3 | Q3 - 2013 | 11907 | 10077 | TRUE | 100 | Based on expenditures, BCI is 95% complete with the overall project. Through the close out period, BCI will close out remaining contracts by paying in full. BCI anticipates completing the project under budget. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 100 | N/A, this is the percentage predicted at the end of last quarter for this quarter. | 100 | Completed Year 3 in 3rd Quarter, which was Quarter 1 of 2013. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | Completed Year 3 in 3rd Quarter, which was Quarter 1 of 2013. | 100 | All equipment has been installed, however not all paid for by the end of this quarter. During the close out period, the contracts will be paid in full. | 100 | The network has been built, tested, and is in service, however a small percentage of the construction budget remains. | 100 | N/A, this is the percentage predicted at the end of last quarter for this quarter. | 100 | N/A, this is the percentage predicted at the end of last quarter for this quarter. | 2014-02-27 15:46 | 2014-02-27 15:46 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570100 | 2010 | Q4 | Q4 - 2010 | 1229 | 2259 | TRUE | 7 | Baseline is 6%. Slightly ahead of schedule on Environmental Assessment, Network Design, and Rights of Way work. | 0 | N/A | No variance | 80 | Baseline is 50%. Ahead of schedule for work being completed. | 65 | Baseline is 60%. Slightly ahead of schedule for work being completed. | 5 | Baseline is 0%. Ahead of schedule for work being completed. | 0 | No variance | 0 | No variance | 0 | Baseline is 35%.Purchase Orders have been issued but payments will not be made until next quarter. After payments are made this line item will be back on baseline plan. | 5 | No variance | 0 | No variance | 0 | No variance | 2011-02-18 16:18 | 2011-02-18 16:18 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2011 | Q1 | Q1 - 2011 | 1931 | 2711 | TRUE | 38 | Baseline was 21%. We are slightly ahead on equipment purchases in orders, and we able to start construction sooner than projected in the baseline. | 0 |  | N/A | 100 | In line with baseline | 100 | In line with baseline | 20 | Baseline was 10%. Because we were able to start construction, we needed to accelerate obtaining rights of way. | 15 | Baseline was 10%. Because we were able to start construction, we needed to accelerate obtaining permits. | 0 | N/A | 57 | Baseline was 50%. In order to obtain price breaks and to make sure we would not be delayed in receiving equipment we accelerated our equipment orders. | 19 | Baseline was 10%. We were able to begin construction ahead of what we projected in the baseline. | 0 | In line with baseline | 0 | In line with baseline | 2011-05-10 15:40 | 2011-05-10 15:40 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2011 | Q2 | Q2 - 2011 | 3047 | 3281 | TRUE | 48 | Baseline was 35%. We have pre-ordered and warehoused a significant amount of our equipment and we have over 100 miles of conduit in the ground. | 0 |  | N/A | 100 | In line with baseline | 100 | In line with baseline | 56 | Baseline was 34% | 34 | Baseline was 22% | 0 | N/A | 66 | Baseline was 65% Slightly ahead of baseline. | 32 | Baseline was 19%. 115 miles of conduit deployed. Construction has been in the more difficult and more expensive routes to construct. | 0 | Baseline was 10%. Taken longer to get through the collocation application phase with Frontier and AT&T than we expected. Should be on track by next quarter. | 0 | In line with baseline | 2011-08-12 14:36 | 2011-08-12 14:36 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2011 | Q3 | Q3 - 2011 | 4031 | 3856 | TRUE | 61 | Baseline was 41% | 0 | NA | NA | 100 | On Baseline | 100 | On Baseline | 68 | Baseline was 47% In order to keep ahead of construction we have gotten ahead of schedule on obtaining Rights of Way. | 59 | Baseline was 34%. In order to keep ahead of construction we have gotten ahead of schedule on obtaining construction permits. | 0 | NA | 68 | Baseline was 80% We have experienced some cost savings in the equipment purchases we have made to date. | 45 | Baseline was 30% Continue to be ahead of schedule regarding conduit installed. Also ahead of schedule on laterals going to anchors. | 39 | Baseline was 23%. Equipment deployed in 13 collocations as well as our Network Operations Center. | 0 | Baseline was 20%. Network testing has not yet been started. All efforts have been concentrating on construction while the weather has been unseasonably warm and dry. We will begin network testing in the months of October and November and be back on track by the end of next quarter. We do not anticipating this change in schedule to adversely impact the progress of the project. | 2011-11-14 15:08 | 2011-11-14 15:08 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2011 | Q4 | Q4 - 2011 | 4973 | 4648 | TRUE | 76 | Ahead of baseline which is 52 | 0 | None | N/A | 100 | In line with baseline | 100 | In line with baseline | 80 | Ahead of baseline which is 62. In order to keep ahead of construction we have gotten ahead of schedule on obtaining Rights of Way. | 75 | Ahead of baseline which is 47. In order to keep ahead of construction we have gotten ahead of schedule on obtaining construction permits. | 0 | N/A | 73 | Baseline is 100. We still have some equipment to purchase, but the main reason for the lower figure is being able to acquire equipment below budgeted costs. | 64 | Ahead of baseline which is 40 | 70 | Ahead of baseline which is 42 | 38 | Ahead of baseline which is 33 | 2012-02-13 12:44 | 2012-02-13 12:44 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2012 | Q1 | Q1 - 2012 | 5995 | 5597 | TRUE | 90 | Baseline is 60 | 0 |  | N/A | 100 | Baseline is 100 | 100 | Baseline is 100 | 88 | Baseline is 72. In order to keep ahead of construction we have gotten ahead of schedule on obtaining Rights of Way. | 82 | Baseline is 62. In order to keep ahead of construction we have gotten ahead of schedule on obtaining construction permits. | 0 | N/A | 79 | Baseline is 100. We still have some equipment to purchase, but the main reason for the lower figure is being able to acquire equipment below budgeted costs. | 83 | Baseline is 51, staying ahead of schedule. | 75 | Baseline is 50, staying ahead of schedule. | 55 | Baseline is 52, slightly ahead of schedule. | 2012-05-09 17:12 | 2012-05-09 17:12 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2012 | Q2 | Q2 - 2012 | 7145 | 6200 | TRUE | 99 | Remain ahead of baseline of 68 | 0 |  | N/A | 100 | In line | 100 | In line | 93 | Ahead of baseline of 84 | 87 | Ahead of baseline of 72 | 0 | N/A | 84 | Baseline is 100. We still have some equipment to purchase, but the main reason for the lower figure is being able to acquire equipment below budgeted costs. | 95 | Ahead of baseline of 64 | 79 | Ahead of baseline of 63 | 66 | Ahead of baseline of 60 | 2012-08-20 09:44 | 2012-08-20 09:44 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2012 | Q3 | Q3 - 2012 | 7849 | 6629 | TRUE | 100 | Actual is 111% due to running over budget. Remaining costs are being covered by private funds. | 0 | NA | NA | 100 | In line with baseline | 100 | In line with baseline | 96 | In line with baseline | 92 | Ahead of baseline of 84 | 0 | NA | 84 | Baseline is 100. We still have some equipment to purchase, but the main reason for the lower figure is being able to acquire equipment below budgeted costs. | 95 | Actual is 108% Incurred higher than expected engineering costs. | 82 | Ahead of baseline of 74 | 73 | In line with baseline | 2012-11-13 17:02 | 2012-11-13 17:02 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2012 | Q4 | Q4 - 2012 | 8719 | 7522 | TRUE | 100 | Actual is over 100% due to running over budget. Remaining costs are being covered by private funds. | 0 | NA | NA | 100 | In line with baseline | 100 | In line with baseline | 96 | Additional Rights of Way costs are being covered by private funds | 92 | Actual at 96. Additional permitting costs are being covered by private funds. | 0 | NA | 84 | Baseline is 100. We will still have some equipment to purchase using private funds, but the main reason for the lower figure is being able to acquire equipment below budgeted costs. | 95 | Actual is over 100% due to running over budget. Remaining costs are being covered by private funds. | 82 | Actual is at baseline of 85%. Additional equipment deployment costs are being covered by private funds. | 73 | Actual is in line with baseline of 87%. Additional network testing costs are being covered by private funds. | 2013-02-12 10:13 | 2013-02-12 10:13 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2013 | Q1 | Q1 - 2013 | 9961 | 8525 | TRUE | 100 | Actual spend is 126% of original budget due to cost overruns in engineering. | 0 | NA | NA | 100 | Actual spend is 143% due to much higher engineering costs required to complete EA. | 100 | Actual spend is 272% due to much higher engineering costs required to complete the network design. | 0 | NA. | 100 | Actual spend is 243% due to much higher costs of railroad and various permits than originally budgeted for. | 0 | NA | 86 | Actual spend is 86% due to lower costs of equipment than originally budgeted. | 100 | Actual spend is 137% as we continue to complete our build. | 0 | NA. Costs were included in Network Build. | 0 | NA. Costs were included in Network Build. | 2013-05-29 14:17 | 2013-05-29 14:17 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2013 | Q2 | Q2 - 2013 | 10759 | 9045 | TRUE | 100 | Actual spend is 127% of original budget due to cost overruns in engineering. | 0 | NA | NA | 100 | Actual Spend is 143% due to much higher engineering costs required to complete EA. | 100 | Actual spend is 272% due to much higher engineering costs required to complete the network design. | 0 | NA | 100 | Actual spend is 243% due to much higher costs of railroad and various permits than originally budgeted | 0 | NA | 86 | Lower costs of equipment than originally budgeted. | 100 | Actual spend is 138% due to higher construction costs than expected. | 0 | NA. Costs were included in Network Build | 0 | NA. Costs were included in Network Build | 2013-08-27 11:48 | 2013-08-27 11:48 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2013 | Q3 | Q3 - 2013 | 11857 | 10028 | TRUE | 100 | Actual spend is 121% of original budget due to higher costs in engineering and permitting. We underestimated the amount of Professional Services we would need for engineering and underestimated the amount and cost of Railroad Permits. | 0 | NA | NA | 100 | Actual spend is 143% due to much higher engineering costs required to complete EA. Needed to use additional Professional Services to get completed. | 100 | Actual spend is 272% due to much higher engineering costs required to complete the network design. Underestimated the amount of time and Professional Services required to complete the network design. | 0 | NA | 100 | Actual spend is 243% due to much higher costs of railroad and various permits than originally budgeted. Greatly underestimated the amount and cost of railroad permits. We ended up with over 80. | 0 | NA | 100 | Actual spend was 86% due to lower costs of equipment than originally budgeted | 100 | Actual spend is 129% due to higher construction costs than budgeted. All of our construction was buried and we underestimated the cost of construction in certain areas where we drilling costs were higher. | 0 | NA. Costs were included in Network Build. | 0 | NA. Costs were included in Network Build. | 2014-02-21 09:24 | 2014-02-21 09:24 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570101 | 2010 | Q4 | Q4 - 2010 | 975 | 2021 | TRUE | 8 | No variance | 7 | Admin, Legal | No variance | 20 | No variance | 20 | No variance | 20 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-02-04 14:28 | 2011-02-04 14:28 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2011 | Q1 | Q1 - 2011 | 2175 | 2833 | TRUE | 6 | Our original baseline goal was to be 17% complete with the overall project by end of Q1 (March 2011), but this was based on task completion, not spend. Our percent complete (based on spend) for this quarter is at 6%. | 21 | Admin & Legal | We are meeting or exceeding our baseline goal for this milestone. | 16 | Our original baseline goal was to be 100% complete with EA by end of Q1 (March 2011), but this was based on task completion, not spend. Our percent complete (based on spend) for this quarter is at 16%. This is based on the terms of our agreement with our EA consultant. | 25 | Our original baseline goal was to be 81% complete with network design by the end of Q1 (March 2011), but this was based on task completion, not spend. Our percent complete (based on spend) for this quarter is at 25%. This is based on the terms of our agreement with our network design consultant. | 0 | Our original baseline goal was to be 44% complete with rights of way by the end of Q1 (March 2011), but this was based on task completion, not spend. Our percent complete (based on spend) for this quarter is at 0%. We expected to be able to book ~$1.1M in-kind contribution for this milestone by Q3, however this request is still under review. | 0 | Our original baseline goal was to be 20% complete with construction permits by the end of Q1 (March 2011), but this was based on task completion, not spend. Our percent complete (based on spend) for this quarter is at 0%. We have been seeking a certificate authority called Other Common Carrier (OCC) from the state of Georgia, and until that certificate is granted, we are unable to process our full permit applications. We expect to have this accomplished in Q4. | 0 | We are meeting or exceeding our baseline goal for this milestone. | 1 | Our original baseline goal was to be 88% complete with equipment procurement by the end of Q1 (March 2011), but this was based on task completion, not spend. Our percent complete (based on spend) for this quarter is at 1%. We expected to be able to book ~$3.5M in-kind contribution for this milestone by Q3, however this request is still under review. | 4 | We are meeting or exceeding our baseline goal for this milestone. | 0 | We are meeting or exceeding our baseline goal for this milestone. | 0 | We are meeting or exceeding our baseline goal for this milestone. | 2011-05-19 14:43 | 2011-05-19 14:43 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2011 | Q2 | Q2 - 2011 | 3009 | 3262 | TRUE | 9 | Our original baseline goal was to be 21% complete with the overall project by end of Q2 (June 2011). We are at 9% and the reasons are cumulative per the below breakdown. | 27 | Admin & Legal | Our original baseline goal was to be 32% complete with this milestone by the end of Q2 (June 2011). We are at 27% as of this quarter. | 62 | Our original baseline goal was to be 100% complete with this milestone by the end of Q2 (June 2011). Our percent complete for this quarter is at 62%. We have had delays with our Environmental Assessment, but since our EA is currently under review with NTIA, we expect to complete our EA in the next quarter. Based on the remaining costs we expect to incur to obtain our FONSI, we expect to only spend/achieve 76% of our forecasted spend for this baseline category. | 54 | Our original baseline goal was to be 100% complete with this milestone by the end of Q2 (June 2011). Our percent complete for this quarter is at 54%. This is based on the timing and payment terms of our agreement with our consultants/engineers and the pace of our spend with the NW Georgia Regional Commission. | 0 | Our original baseline goal was to be 100% complete with this milestone by the end of Q2 (June 2011). Our percent complete for this quarter is at 0%. This is due to the fact that we did not receive approval (as originally planned) for our ~$1.1M in-kind contribution in this quarter. It is also because we have not started construction yet, and therefore, we have not incurred joint use (pole attachment) fees as expected. And finally, it is because we have not incurred the estimate $300k in right of way perfection costs at this time. We expect to catch up in this category over the next two quarters as we commence with construction activity. | 7 | Our original baseline goal was to be 48% complete with this milestone by the end of Q2 (June 2011). Our percent complete for this quarter is at 7%. We have been seeking a certificate authority called Other Common Carrier (OCC) from the state of Georgia, and until that certificate is granted, we are unable to process our full permit applications. We expect to have this accomplished in August 2011. At this point, our pace of permitting will increase to catch up with our original projections. | 0 | AVFN has no $ allocated in its budget to this baseline category, so the % complete is irrelevant. | 39 | Our original baseline goal was to be 100% complete with this milestone by the end of Q2 (June 2011). Our percent complete for this quarter is at 39%. Once our construction commences next quarter, we expect to be able to catch up on this milestone. | 4 | Our original baseline goal was to be 28% complete with the overall project by end of Q2 (June 2011). This is due to the fact that we were not able to recognize our ~$3.5M in-kind contribution for this quarter (request under review by NTIA). | 0 | AVFN has no $ allocated in its budget to this baseline category, so the % complete is irrelevant. | 0 | Given that Network Testing relates directly to Network Build we did not meet ourr original baseline goal of 28% complete with the overall project by end of Q2 (June 2011). This is due to the fact that we were not able to recognize our ~$3.5M in-kind contribution for this quarter (request under review by NTIA) nor begin construction due to Environmental Assessment delays. However, it is our expectations that both the in kind match and the Environmental Assessment will approved in next quarter and we will be back on schedule by the end of that quarter. | 2011-08-11 10:56 | 2011-08-11 10:56 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2011 | Q3 | Q3 - 2011 | 3921 | 3799 | TRUE | 39 | Our baseline goal was to be 44%. Due to delays with our EA process, we have had a slight delay in meeting this goal and are at only 39%. Now that we are in the construction phase, and with two contractors deploying conduit on an aggressive schedule, we are confident we can recover and reach our overall project percent complete goal for next quarter (which is 55%). We have calculated that we need to average 4 miles per week during the next quarter in order to recover and reach our goal. | 38 |  | Our baseline goal was to be 43%. The small variance is due mainly to our general liability insurance costs being lower than expected due to the delay in starting construction. | 78 | Our baseline goal was to be 100%. We completed our environmental assessment under budget. We expect no more costs to be incurred in this category unless issues related to our SAC come up. | 64 | Our baseline goal was to be 100%. At this point we are under budget in this category and this explains the reason for the variance. | 0 | Our baseline goal was to be 100%. The $878k for this category is a relatively small portion of our overall budget. $548k of this was for joint use (pole attachment) fees. The constraints on setting new poles imposed in our EA SAC has discouraged the use of poles altogether. | 9 | Our baseline goal was to be 77%. The $279k for this category is a relatively small portion of our overall budget. Costs have been lower than expected to date, however we expect these costs to increase as we move forward with more expensive permits like our railroad crossings. | 0 | We had $0 allocated to this category and therefore have no variance. | 48 | Our baseline goal was to be 100%. This is a relatively small portion of our overall budget. These costs are occurring later than expected due to the delay in the start of our construction. | 40 | Our baseline goal was to be 38% and therefore we have no variance. | 0 | Even though we had $0 allocated to this category in our detailed budget, we still recorded projections for % complete for each quarter in our original baseline. In hindsight, it would have been more appropriate to record 0% or N/A in our baseline projections. At this point, we have spent $0.00 on this category, and since our original projection was to spend $0.00, we feel it is appropriate to record this as "no variance." Alternatively, we could record our % complete each quarter to be the same as our baseline projections, but this would be "X% complete of $0.00." | 0 | Even though we had $0 allocated to this category in our detailed budget, we still recorded projections for % complete for each quarter in our original baseline. In hindsight, it would have been more appropriate to record 0% or N/A in our baseline projections. At this point, we have spent $0.00 on this category, and since our original projection was to spend $0.00, we feel it is appropriate to record this as "no variance." Alternatively, we could record our % complete each quarter to be the same as our baseline projections, but this would be "X% complete of $0.00." | 2011-11-08 13:36 | 2011-11-08 13:36 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2011 | Q4 | Q4 - 2011 | 4873 | 4569 | TRUE | 45 | Our original baseline plan projected us to be 55% complete. Lack of fiber availability is primary reason for variance. | 44 |  | Our original baseline plan projected us to be 56% complete. Lower than expected admin, legal and other professional services costs so far is primary reason for variance. These costs are still expected to be incurred, but they will be more back-loaded/deferred than we original expected. | 78 | Our original baseline plan projected us to be 100% complete. The work related to our EA is essentially complete, but since we ended up under budget from what we original projected to spend on this milestone, we will show a "variance" for the remainder of the program.. | 64 | Our original baseline plan projected us to be 100% complete. Lower than expected costs so far from NW Georgia Regional Commission is the primary reason for this variance. | 0 | Our original baseline plan projected us to be 100% complete. Lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for variance. These costs are still expected to be incurred, but they will be more back-loaded/deferred than we original expected. Despite the large % variance, this is a very small part of our overall project/budget. | 18 | Our original baseline plan projected us to be 100% complete. Lower than expected railroad permits so far is primary reason for variance. These costs are still expected to be incurred, but they will be more back-loaded/deferred than we original expected. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. | 77 | Our original baseline plan projected us to be 100% complete. Primary reason for variance from our baseline is lower than expected costs for budgeted equipment. | 46 | Our original baseline plan projected us to be 47% complete. Lack of fiber availability is primary reason for this small variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. | 0 | We had no costs allocated in our budget specifically for this baseline category. | 2012-02-05 19:06 | 2012-02-05 19:06 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2012 | Q1 | Q1 - 2012 | 6297 | 5751 | TRUE | 55 | Original baseline goal was to be 66% complete. Delayed fiber availability and lower than expected costs in some categories are the primary reasons for the variance. | 48 |  | Original baseline goal was to be 79% complete. Lower than expected admin, legal and other professional services costs so far is primary reason for variance. These costs are still expected to be incurred, but they will be more back-loaded/deferred than we original expected. | 78 | Original baseline goal was to be 100% complete. At this point, we are under budget, however due to current activities to conduct cultural and archeological monitoring under our FONSI and SAC obligations, we expect additional spend between now and the end of the program. | 65 | Original baseline goal was to be 100% complete. Lower than expected costs so far from NW Georgia Regional Commission is the primary reason for this variance. | 0 | Original baseline goal was to be 100% complete. Lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for variance. These costs are still expected to be incurred, but they will be more back-loaded/deferred than we original expected. Despite the large % variance, this is a very small part of our overall project/budget. | 25 | Original baseline goal was to be 100% complete. Lower than expected railroad permits so far is primary reason for variance. These costs are still expected to be incurred, but they will be more back-loaded/deferred than we original expected. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 72 | Original baseline goal was to be 100% complete. Primary reason for variance from our baseline is lower than expected costs for budgeted equipment. | 56 | Original baseline goal was to be 70% complete. Delayed fiber availability is primary reason for this small variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 2012-05-25 11:38 | 2012-05-25 11:38 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2012 | Q2 | Q2 - 2012 | 6871 | 6062 | TRUE | 68 | Original baseline goal was to be 66% complete. No variance. | 58 |  | Original baseline goal was to be 79% complete. Lower than expected admin, legal and other professional services costs so far is primary reason for variance. These costs are still expected to be incurred, but they will be more back-loaded/deferred than we original expected. | 78 | Original baseline goal was to be 100% complete. The variance is because we are under budget in this category. We expect additional spend between now and the end of the program. | 75 | Original baseline goal was to be 100% complete. Lower than expected costs so far from NW Georgia Regional Commission is the primary reason for this variance. | 0 | Original baseline goal was to be 100% complete. Lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for variance. These costs are still expected to be incurred, but they will be more back-loaded/deferred than we original expected. Despite the large % variance, this is a very small part of our overall project/budget. | 27 | Original baseline goal was to be 100% complete. Lower than expected railroad permits so far is primary reason for variance. These costs are still expected to be incurred, but they will be more back-loaded/deferred than we original expected. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 75 | Original baseline goal was to be 100% complete. Primary reason for variance is due lower than expected costs to date for truck expense. | 71 | Original baseline goal was to be 70% complete. No variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 2012-08-06 15:58 | 2012-08-06 15:58 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2012 | Q3 | Q3 - 2012 | 8049 | 6731 | TRUE | 78 | Original baseline goal was to be 75% complete. | 63 |  | Original baseline goal was to be 88% complete. Continued lower than expected admin, legal and other professional services costs is primary reason for variance. | 78 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however due to current activities to conduct cultural and archeological monitoring under our FONSI and SAC obligations, we expect additional spend between now and the end of the program. | 84 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the expected variance. | 0 | Original baseline goal was to be 100% complete. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 53 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 96 | Original baseline goal was to be 100% complete. | 82 | Original baseline goal was to be 79% complete. No variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 2012-11-26 16:37 | 2012-11-26 16:37 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2012 | Q4 | Q4 - 2012 | 9123 | 7899 | TRUE | 84 | Original baseline goal was to be 81% complete. No variance. | 69 |  | Original baseline goal was to be 90% complete. Continued lower than expected admin, legal and other professional services costs is primary reason for variance. | 79 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however due to current activities to conduct cultural and archeological monitoring under our FONSI and SAC obligations, we expect additional spend between now and the end of the program. | 90 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the expected variance. | 0 | Original baseline goal was to be 100% complete. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 54 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 97 | Original baseline goal was to be 100% complete. | 88 | Original baseline goal was to be 88% complete. No variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 2013-03-04 17:30 | 2013-03-04 17:30 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2013 | Q1 | Q1 - 2013 | 9709 | 8388 | TRUE | 87 | Original baseline goal was to be 94% complete. Delayed start to Alabama construction is primary reason for variance. | 76 |  | Original baseline goal was to be 100% complete. Delayed start to Alabama construction is primary reason for variance. Our costs for UCC filing attorneys is also shifted towards the back of the project in order to make sure that plant is fully constructed. | 79 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however due to current activities to for route modifications for 7 CAIs, we expect additional spend between now and the end of the program. | 90 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the expected variance. | 0 | Original baseline goal was to be 100% complete. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 67 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 97 | Original baseline goal was to be 100% complete. | 90 | Original baseline goal was to be 96% complete. Delayed start to Alabama construction is primary reason for variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 2013-05-13 17:04 | 2013-05-13 17:04 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2013 | Q2 | Q2 - 2013 | 10695 | 9010 | TRUE | 92 | Original baseline goal was to be 100% complete. Remaining budget will be spent on eligible close-out activities. | 83 |  | Original baseline goal was to be 100% complete. Delayed start to Alabama construction is primary reason for variance. Our costs for UCC filing attorneys is also shifted towards the back of the project in order to make sure that plant is fully constructed. | 88 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however remaining funds in this category will be spent on eligible close-out activities. Funds moved to other categories to support close-out activities will amount to less than 10% of our budget. | 92 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the variance. | 0 | Original baseline goal was to be 100% complete. Lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for the variance. Despite the large % variance, this is a very small part of our overall project/budget. | 87 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 98 | Original baseline goal was to be 100% complete. Delayed start to Alabama construction is primary reason for variance. | 96 | Original baseline goal was to be 100% complete. Delayed start to Alabama construction is primary reason for variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 2013-08-22 14:51 | 2013-08-22 14:51 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2013 | Q3 | Q3 - 2013 | 11253 | 9417 | TRUE | 100 | Original baseline goal was to be 100% complete. No variance. | 100 |  | Original baseline goal was to be 100% complete. No variance. | 100 | Original baseline goal was to be 100% complete. No variance. | 100 | Original baseline goal was to be 100% complete. No variance. | 100 | Original baseline goal was to be 100% complete. No variance. | 100 | Original baseline goal was to be 100% complete. No variance. | 100 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 100 | Original baseline goal was to be 100% complete. No variance. | 100 | Original baseline goal was to be 100% complete. No variance. | 100 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 100 | We had no costs allocated in our budget specifically for this baseline category. No variance. | 2013-11-14 16:07 | 2013-11-14 16:07 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570102 | 2010 | Q4 | Q4 - 2010 | 625 | 1651 | TRUE | 0 | The Baseline Report assumed IRUs would have been in place by the end of the fourth quarter of 2010, but those negotiations are still on-going at this time. We anticipate completing Indefeasible Rights of Use (IRU) agreements in the the first reporting of 2011. Without those agreements, our expenditures were a fraction of a percent. | 0 |  | The Baseline Report assumed about 1% of the "other"category to be complete due to payment of salaries of personnel scheduled to start employment within the fourth quarter of 2010. However, most of these employees started very late within the fourth quarter of 2010, while others commenced employment in the first quarter of 2011. Due to a later start than expected, their salaries did not require as much funding during the course of the fourth quarter of 2010. These salaries are now active in the first quarter of 2011. | 0 | The Baseline Report assumed that UAMS would have received an invoice from the contracted engineering firm undertaking development of the EA. However, though the contractor had almost completed the Environmental Assessment (EA) as of the close of the fourth quarter of 2010, UAMS did not receive an invoice during this time. The EA is now complete and submitted in the first quarter of 2011, so payment for the EA should be forthcoming in the next quarter. | 0 | --- | 0 | --- | 0 | --- | 0 | N/A | 0 | --- | 0 | The Baseline Report assumed IRUs would have been in place by the end of the fourth quarter of 2010, but those negotiations are still on-going at this time. We anticipate completing IRU agreements in the first reporting of 2011. | 0 | The UAMS grant contributes a large amount of in-kind equipment toward its match amount. The Baseline Report reflected this match contribution proportional to the expenses we anticipated at the time, as indicated above: Purchase of IRUs and Payment of EA services. Without those expenditures, our match contributions were a fraction of a percent. | 0 | --- | 2011-01-27 16:56 | 2011-01-27 16:56 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2011 | Q1 | Q1 - 2011 | 2285 | 2888 | TRUE | 1 | Two assumptions in the Baseline Report have primarily resulted in a variance in the percent completion for the overall project. The Baseline Report assumed Indefeasible Right-of-Use (IRU) agreements would have been in place by the end of the fourth quarter of 2010, but those negotiations are still ongoing at this time. Additionally, the Baseline Report assumed that in the first quarter of 2011, the home health and public safety components of the project would have been deployed; however, the Environmental Assessment still awaits approval, thus these projects are not possible to undertake at this time. We anticipate completing IRU agreements and receiving a Finding of No Significant Impact (FONSI) in the next quarter, which will help propel the project forward toward meeting its baseline goals. | 2 | -- | The Baseline report assumed all 12 employees would be hired by the start of the first quarter of 2011. However, the project's three remaining employees were added in February, the second month of the quarter. As such, a lesser percentage of these staff salaries were paid out due to the fact the employment of the full staff was not finalized until February 2011. For the second quarter of 2011, the salaries of all 12 employees will be reflected. Due the fact these salaries were not fully active during the first quarter of 2011, indirect charges were also less than expected. | 16 | The Baseline Report assumed that UAMS would have received and paid the final invoice from the contracted engineering firm undertaking development of the EA. However, UAMS only paid a portion of these costs to-date. The first draft of the EA was submitted in the first quarter of 2011; however, revisions and further details were requested by the National Telecommunications and Information Administration (NTIA), SHPO, and USFWS. The engineering firm contracted for this project will prepare a revised EA draft, a Cultural Resources Survey Report, and a Biological Studies Report in the next reporting quarter. It is anticipated the final EA draft will be submitted in the second quarter of 2011, which is anticipated to result in a FONSI. | 0 | The Baseline Report assumed that UAMS would pay 75% of the network design fees this first quarter of 2011, but the network design is now anticipated to be completed and paid in the second quarter of 2011. | 0 | N/A | 0 | --- | 0 | N/A | 0 | The Baseline Report assumed that in the first quarter of 2011, the home health and public safety components of the project would have been procured and deployed; however, the Environmental Assessment still awaits approval, thus affecting the project's full capacities to procure and deploy such items. The equipment procurement process, however, will commence in the second quarter of 2011, when equipment Request for Proposals will be issued. The project has elected to minimize the time equipment is "warehoused" while the EA is still under review, as equipment warranties would be active during the warehouse time when this equipment is not being tested or employed. We anticipate receiving a FONSI in the next quarter, which will help propel the project forward toward meeting its baseline goals. | 0 | The Baseline Report assumed IRUs would have been in place by the end of the fourth quarter of 2010, but those negotiations are still ongoing at this time. There exists one conflict protest pending resolution. The University of Arkansas Counsel has worked with the Office of State Purchasing in this quarter, and continues to work collaboratively to address and resolve this protest. Resolution is expected in the next reporting quarter, which will allow completion of the IRU agreements. | 1 | This project contributes a large amount of in-kind equipment toward its match amount. The Baseline Report reflected this match contribution proportional to the expenses anticipated at the time, as indicated above: Purchase of IRUs and Payment of EA services. Without these expenditures, match contributions measure 1% for this quarter. | 0 | --- | 2011-05-24 17:32 | 2011-05-24 17:32 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2011 | Q2 | Q2 - 2011 | 2603 | 3050 | TRUE | 2 | This section of the Performance Progress Report compares actual expenditures to the Year 1 Quarter 4 figures on the revised baseline submitted to the project's Federal Program Officer on May 24, 2011.The revised Baseline Report assumed Indefeasible Rights of Use fiber agreements would have been in place by the close of this quarter; however, a delay in finalizing these negotiations and the associated, proportional match contribution have resulted in variance from the revised baseline. | 4 | Indirect costs, huts, easements, project management costs | There is no material difference from the revised Baseline Report, which projected 3.43% compared to quarter's actual 3.51%. | 64 | The revised Baseline Report assumed that UAMS would continue employing the services of the Environmental Assessment (EA) contractor over the course of the grant to accommodate any environmental concerns that may arise during the implementation phase. The revised Baseline Report assumed these expenses may be paid more rapidly than currently planned. As such, the project will continue to incur EA expenses throughout the remainder of the project with 100% completion of the Environmental Assessment milestone at the end of the grant period. | 98 | The revised Baseline Report correctly assumed that UAMS would pay the remaining network design fees in this quarter. Although these fees have been paid in full, the invoice total cost was slightly less than projected in the revised Baseline Report, resulting in a 2% discrepancy. | 0 | N/A | 3 | The revised Baseline Report assumed that in second quarter of 2011 construction permits would be obtained; however, there have been unforeseen processing delays in obtaining railroad crossing permits. The related funds are expected to be expended in the upcoming quarter. | 0 | N/A | 0 | --- | 1 | The revised Baseline Report assumed IRUs would have been in place by the end of the fourth quarter of 2010, but those negotiations are still ongoing. Progress has been made in that one agreement has been signed and three are pending. There exists one conflict protest that has progressed to legal action. The University of Arkansas Counsel continues to work corroboratively with the Office of State Purchasing to address and resolve this legal action. The 1% represented here is contributed to network build management costs, and a substantial portion of IRU funds are expected to be expended in the following quarter. | 3 | The project contributes a large amount of in-kind equipment toward its match amount. The revised Baseline Report reflected this match contribution proportional to the grant funds expected to expended within each quarter. Since delays in the finalization of IRU agreements have resulted in fewer funds being expended this quarter, fewer equipment matching funds were contributed. | 0 | -- | 2011-07-28 14:51 | 2011-07-28 14:51 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2011 | Q3 | Q3 - 2011 | 4035 | 3858 | TRUE | 6 | This section of the Performance Project Report compares actual expenditures to the Year 2 Quarter 1 figures on the revised baseline submitted to the project's Federal Program Officer on May 24, 2011. ARE-ON, the program's sub-recipient, has contracted for Indefeasible Rights of Use (IRUs) from four (4) providers over 17 intercity fiber routes. Most of the IRU contracts have milestone payments based on completion of engineering and construction for any new routes, with the final milestone payment planned once the fiber has been delivered and tested. There are 690.14 miles total of contracted fiber for the four (4) IRUs. It is projected that the final milestone payment for all IRUs will not be reached until Year 3 Quarter 2. Additionally, the ATOM portion of the project has distributed Requests for Proposals (RFPs), awarded bids negotiated contracts, and placed orders for personal computers (PCs) and interactive video equipment (IAV). However, invoices were not paid in this quarter, a | 5 | Indirect costs, huts, easements, project management costs | The revised Baseline Report assumed that costs for shipping huts would be greater; value engineering to reduce costs necessitated some rebidding resulting in a variance of 3% for this reporting quarter. Contracts were negotiated for hub/hut facilities. | 77 | The revised Baseline Report assumed that UAMS would continue employing the services of the Environmental Assessment (EA) contractor over the course of the grant to accommodate any environmental concerns that may arise during the implementation phase. The revised Baseline Report assumed these expenses may be paid more rapidly than currently planned. As such, the project will continue to incur EA expenses throughout the remainder of the project with 100% completion of the Environmental Assessment milestone at the end of the grant period. The variance for this reporting quarter is 9%. | 98 | Although these fees have been paid in full, the invoice total cost varied from projections in the revised Baseline Report, resulting in a 2% variance. | 0 | N/A | 9 | Fewer miles of fiber are being constructed; therefore, there were fewer railroad crossings and, thus, fewer required permits. However, other permit fees may be incurred in coming quarters for fiber construction. Cost savings from this budget item will be applied in other areas where costs are higher than anticipated. The variance for this reporting quarter is 91%. | 0 | N/A | 1 | The revised Baseline Report assumed that infrastructure management equipment procurement would occur this reporting quarter, however, contract negotiations are ongoing and are anticipated to be finalized by next quarter. Although procurement commenced, invoices were not paid in this quarter, as invoices were not issued at such a time that they could be paid with respect to ASAP system's scheduled down time resulting in a 24% variance. | 7 | The revised Baseline Report assumed Indefeasible Rights of Use (IRUs) payments to be completed by Year 2 Quarter 1. ARE-ON has contracted for IRUs from four (4) providers over 17 intercity fiber routes. Most of the IRU contracts have milestone payments based on completion of engineering and construction for any new routes, with the final milestone payment planned once the fiber has been delivered and tested. There are 690.14 miles total of contracted fiber for the four (4) IRUs. It is projected that the final milestone payment for all IRUs will not be reached until Year 3 Quarter 2. The variance for this reporting quarter is 11%. The legal action involving one of the unsuccessful IRU vendors and the University is still pending but is expected to be resolved by Year 2 Quarter 3. | 8 | The project contributes a large amount of in-kind equipment toward its match amount. The revised Baseline Report reflected this match contribution proportional to the grant funds expected to expended within each quarter. Since delays in the finalization of IRU agreements have resulted in fewer funds being expended this quarter, fewer equipment matching funds were contributed resulting in a 20% variance. | 0 | The revised Baseline Report assumed that infrastructure management equipment would have been installed and tested. However, contract negotiations were protracted longer than anticipated resulting in a 82% variance. | 2011-11-14 15:47 | 2011-11-14 15:47 | 6618 | 6618 | University of Arkansas System | TRUE
NT10BIX5570102 | 2011 | Q4 | Q4 - 2011 | 5025 | 4697 | TRUE | 20 | This section of the Performance Project Report compares actual expenditures to the Year 2 Quarter 2 figures on the revised baseline submitted to the project's Federal Program Officer on May 24, 2011. ARE-ON, the program's sub-recipient, has contracted for Indefeasible Rights of Use (IRUs) from four (4) providers over 17 intercity fiber routes. Most of the IRU contracts have milestone payments based on completion of engineering and construction for any new routes, with the final milestone payment planned once the fiber has been delivered and tested. There are 690.14 miles total of contracted fiber for the four (4) IRUs. It is projected that the final milestone payment for all IRUs will not be reached until Year 3 Quarter 2. Additionally, the telemedicine portion of the project has distributed Requests for Proposals (RFPs), awarded the bid negotiated contract, and placed orders for infrastructure equipment. However, invoices were not paid in this quarter, as invoices were not issued by | 12 | Indirects, huts, easements, project management costs | --- | 78 | The revised Baseline Report assumed that UAMS would continue employing the services of the Environmental Assessment (EA) contractor over the course of the grant to accommodate any environmental concerns that may arise during the implementation phase. The revised Baseline Report assumed these expenses may be paid more rapidly than currently planned. As such, the project will continue to incur EA expenses throughout the remainder of the project with 100% completion of the Environmental Assessment milestone at the end of the grant period. The variance for this reporting quarter is 11%. | 98 | Although these fees have been paid in full, the invoice total cost varied from projections in the revised Baseline Report, resulting in a 2% variance. | 0 | N/A | 9 | Fewer miles of fiber are being constructed; therefore, there were fewer railroad crossings and, thus, fewer required permits. However, other permit fees may be incurred in coming quarters for fiber construction. Cost savings from this budget item will be applied in other areas where costs are higher than anticipated. The variance for this reporting quarter is 91%. | 0 | N/A | 30 | The revised Baseline Report assumed that infrastructure management equipment procurement would occur this reporting quarter. However, invoices were not paid in this quarter as invoices were not issued in time by the vendor. This resulted in a 7% variance. | 16 | The revised Baseline Report assumed Indefeasible Rights of Use (IRUs) payments to be completed by Year 2 Quarter 1. ARE-ON has contracted for IRUs from four (4) providers over 17 intercity fiber routes. Most of the IRU contracts have milestone payments based on completion of engineering and construction for any new routes, with the final milestone payment planned once the fiber has been delivered and tested. There are 690.14 miles total of contracted fiber for the four (4) IRUs. It is projected that the final milestone payment for all IRUs will not be reached until Year 3 Quarter 2. The variance for this reporting quarter is 11%. | 28 | The project contributes a large amount of in-kind equipment toward its match amount. The revised Baseline Report reflected this match contribution proportional to the grant funds expected to be expended within each quarter. Since delays in the finalization of IRU agreements have resulted in fewer funds being expended this quarter, fewer equipment matching funds were contributed resulting in a 13% variance. | 0 | The revised Baseline Report assumed that infrastructure management equipment would have been installed and tested. However, contract negotiations were protracted longer than anticipated resulting in a 82% variance. | 2012-02-15 11:00 | 2012-02-15 11:00 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2012 | Q1 | Q1 - 2012 | 6051 | 5625 | TRUE | 43 | This section of the Performance Project Report compares actual expenditures to the Quarter 1 2012 figures on the revised baseline submitted to the project's Federal Program Officer on May 24, 2011. ARE-ON, the program's sub-recipient, has contracted for Indefeasible Rights of Use (IRUs) from four (4) providers over 17 intercity fiber routes. Most of the IRU contracts have milestone payments based on completion of engineering and construction for any new routes, with the final milestone payment planned once the fiber has been delivered and tested. There are 690.14 miles total of contracted fiber for the four (4) IRUs. It is projected that the final milestone payment for all IRUs will not be reached until Quarter 4 2012. Additionally, the telemedicine portion of the project experienced delays in contract negotiations for Mobile Virtual Physician (MVP) and acquisition of components necessary to complete installation of video infrastructure management equipment. Collectively, these cir | 24 | Indirects, huts, easements, project management costs | The revised Baseline assumed that progress of hut construction would be more advanced, however, heavy rain has interfered with construction resulting in a -2% variance during Quarter 1 2012. | 100 | No additional charges are anticipated for Environmental Assessment resulting in a +8% variance against the revised Baseline projections. | 98 | Although these fees have been paid in full, the invoice total cost varied from projections in the revised Baseline, resulting in a -2% variance. We anticipate no additional charges for Network Design. | 0 | N/A | 9 | There are approximately 700 fewer miles of fiber being constructed than was projected in the revised Baseline; therefore, there were fewer railroad crossings and, thus, fewer required permits. However, other permit fees may be incurred in coming quarters for fiber construction. Cost savings from this budget item will be applied in other areas where costs are higher than anticipated. We anticipate no additional charges for construction permits. The variance for this reporting quarter is -91%. | 0 | N/A | 69 | We were able to procure equipment more expeditiously than the revised Baseline projected, resulting in a +13% variance. | 31 | The revised Baseline assumed Indefeasible Rights of Use (IRUs) payments to be completed by Quarter 3 2011. ARE-ON has contracted for IRUs from four (4) providers over 17 intercity fiber routes. Most of the IRU contracts have milestone payments based on completion of engineering and construction for any new routes, with the final milestone payment planned once the fiber has been delivered and tested. There are 690.14 miles total of contracted fiber for the four (4) IRUs. It is projected that the final milestone payment for all IRUs will not be reached until Quarter 4 2012. The variance for this reporting quarter is -16%. | 60 | The project contributes a large amount of in-kind equipment toward its match amount. The revised Baseline reflected this match contribution proportional to the grant funds expected to be expended within each quarter. Since delays in the finalization of IRU agreements have resulted in fewer funds being expended this quarter, fewer equipment matching funds were contributed resulting in a -9% variance. | 0 | The revised Baseline assumed that video infrastructure management equipment would have been installed and tested, however contract negotiations were protracted longer than expected causing delays in procurement and installation. There were also delays in hut construction which delayed Leased Broadband implementation (to begin Q2 2012). Overall, these circumstances resulted in a -82% variance. | 2012-05-14 09:45 | 2012-05-14 09:45 | 6618 | 6618 | University of Arkansas System | TRUE
NT10BIX5570102 | 2012 | Q2 | Q2 - 2012 | 7209 | 6232 | TRUE | 71 | This section of the Performance Project Report compares actual expenditures to the Quarter 2 2012 figures on the revised Baseline submitted to the project's Federal Program Officer on May 24, 2011. ARE-ON, the program's sub-recipient, has contracted for Indefeasible Rights of Use (IRUs) from four providers over 17 intercity fiber routes. Most of the IRU contracts have milestone payments based on completion of various tasks, with the final milestone payment planned once the fiber has been delivered and tested. The final milestone payment for all IRUs is expected to be reached Q4 2012. Note: Previous reports indicated 690.14 miles total of contracted fiber for the four IRUs. However, the route between two cities was re-engineered by our telecommunications vendor which lengthened the distance by 25.49 miles for a total of 715.89 miles. Additionally, the telemedicine portion of the project experienced delays in contract negotiations for Mobile Virtual Physician (MVP) and delays in inst | 52 | Indirects, huts, easements, project management costs | The revised baseline was conservative in projecting progress of hut construction during Q2 2012. Five new fiber huts were placed and four existing huts were upgraded, resulting in a +12% variance. | 100 | No additional charges are anticipated for Environmental Assessment resulting in a +5% variance against the revised Baseline projections. | 98 | Although these fees have been paid in full, the invoice total cost varied from projections in the revised Baseline, resulting in a -2% variance. We anticipate no additional charges for Network Design. | 0 | N/A | 9 | Because more IRUs are being used than originally projected, there are fewer railroad crossings and, thus, fewer required permits. However, other permit fees may be incurred in coming quarters for fiber connectivity. Cost savings from this budget item will be applied in other areas where costs are higher than anticipated. We anticipate no additional charges for permits. The variance for this reporting quarter is -91%. | 0 | N/A | 81 | Procurement of clinical assessment tools (peripherals), IAV management devices, and video infrastructure systems required more time than anticipated. Procurement of these items are expected to be complete by the end of the next reporting quarter. The variance for Q2 2012 is -12%. | 63 | ARE-ON, the sub-recipient, placed 46.36 of 47.05 total route miles of fiber optic cable. Local approvals and weather-related conditions delayed these efforts somewhat. IRU providers have completed 483.95 of 715.89 miles of fiber. The totals of ARE-ON fiber and IRU fiber bring the project total to 516.25 of 749.13 miles. The variance for Q2 2012 is -4%. Significant progress and near completion is expected by the end of Q3 2012. | 99 | The project contributes a large amount of in-kind equipment toward its match amount. The revised Baseline reflected this match contribution proportional to the grant funds expected to be expended within each quarter. Since more funds were expended than anticipated, more equipment matching funds were contributed resulting in a +6% variance. | 40 | The revised Baseline assumed that video infrastructure management equipment would have been installed and tested, however contract negotiations were protracted longer than expected causing delays in procurement and installation. We expect the contract to be finalized and installation of the video infrastructure management equipment completed by the end of the next reporting quarter. Additionally, fiber network testing cannot begin until the optical network is completed. The remaining optical and router equipment is expected to be deployed over the next two quarters as lateral construction, hut construction, and IRU routes are completed. Overall, these circumstances resulted in a -42% variance. | 2012-08-22 13:30 | 2012-08-22 13:30 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2012 | Q3 | Q3 - 2012 | 7987 | 6700 | TRUE | 76 | This section of the Performance Project Report compares actual expenditures to the Quarter 3 2012 figures on the revised Baseline submitted to the project's Federal Program Officer on May 24, 2011. Due to the temporary suspension order by NTIA on July 11, 2012, the telemedicine portion of the project experienced delays in contract negotiations for Mobile Virtual Physician (MVP), installation/testing of video infrastructure management equipment and deployment of interactive video equipment (IAV) to the remaining Telemedicine CAIs. We expect the contract to be finalized, installation/testing of the video infrastructure management equipment and deployment of IAVs to remaining CAIs to be completed by the end of the next reporting quarter. ARE-ON, the program's sub-recipient, has contracted for Indefeasible Rights of Use (IRUs) from four providers over 17 intercity fiber routes. Most of the IRU contracts have milestone payments based on completion of various tasks, with the final milesto | 65 | Indirects, huts, easements, project management costs | No progress was made on the number of hut placements due to the temporary suspension resulting in a -6% variance. | 100 | --- | 98 | Although these fees have been paid in full, the invoice total cost varied from projections in the revised Baseline, resulting in a -2% variance. We anticipate no additional charges for Network Design. | 0 | N/A | 9 | Because more IRUs are being used than originally projected, there are fewer railroad crossings and, thus, fewer required permits. Cost savings from this budget item will be applied in other areas where costs are higher than anticipated. We believe that we have completed 100% of all construction permits, ROW permits, railroad crossing permits, city permits, and highway permits. We anticipate no additional charges for permits. | 0 | N/A | 89 | Due to the temporary suspension order by NTIA on July 11, 2012, procurement of clinical assessment tools (peripherals), IAV management devices, and video infrastructure systems were delayed. However, some payments occurred during the quarter but outside the stop-work order period. Procurement of these items are expected to be complete by the end of the next reporting quarter. The variance for Q3 2012 is -8%. | 68 | Construction was halted with the temporary suspension order by NTIA on July 11, 2012. ARE-ON's IRU providers have completed and invoiced 565.80 of 715.89 miles of IRU fiber. The totals of both bring the project to 598.10 of 749.13 miles. The variance for Q3 2012 is -13%. | 89 | At this point, deployment of equipment has consisted of: optical equipment at 3 of 39 sites (~8%), 2 of 10 core network routers (20%), 0 of 2 access routers (0%), 0 of 16 Ethernet switches (0%), 0 of 28 security gateways, 0 of 1 remote access servers (0%), 0 of 2 network management servers (0%), and 0 of 2 iSCSI storage arrays (0%). The project contributes a large amount of in-kind equipment toward its match amount. The revised Baseline reflected this match contribution proportional to the grant funds expected to be expended within each quarter. Last quarter, we reported a 99% actual and we since discovered that should have been 89%. The variance is -5%. | 60 | The revised Baseline assumed that video infrastructure management equipment would have been installed and tested, however the temporary suspension of July 11, 2012 caused delays in procurement and installation. We expect the contract to be finalized and installation of the video infrastructure management equipment completed by the end of the next reporting quarter. Additionally, ARE-ON had begun preliminary testing of optical equipment and the two core network routers deployed at Dallas and Hope prior to the temporary suspension. The remaining optical and router equipment is expected to be deployed over the next two quarters as lateral construction, hut construction, and IRU routes are completed. Overall, these circumstances resulted in a -6% variance. | 2012-11-20 16:35 | 2012-11-20 16:35 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2012 | Q4 | Q4 - 2012 | 8809 | 7603 | TRUE | 80 | This section of the Performance Project Report compares actual expenditures to the Quarter 4 2012 figures on the revised Baseline submitted to the project's Federal Program Officer on May 24, 2011. The temporary suspension order by NTIA on July 11, 2012 profoundly impacted sub-recipient ARE-ON's project progress. The suspension,lifted November 14, 2012, left only six weeks in the reporting quarter for ARE-ON to ramp-up their schedule. While striving to build momentum to recoup lost time, ARE-ON successfully completed delivery and testing of the remaining fiber from all four IRU providers. This achievement resulted in completion of the final milestone payment finishing 715.89 miles of contracted fiber consistent with projections for this quarter. These circumstances resulted in a -10% variance. | 74 | Indirects, huts, easements, project management costs | The temporary suspension order by NTIA on July 11, 2012 impacted sub-recipient ARE-ON's progress on placement of huts. Although ARE-ON reports having completed 13 of 16 total huts this reporting quarter, we fell short of the projection due to the suspension. The variance is -3%. | 100 | --- | 100 | --- | 0 | N/A | 9 | Because more IRUs are being used than originally projected, there are fewer railroad crossings and, thus, fewer required permits. Cost savings from this budget item will be applied in other areas where costs are higher than anticipated. It is believed that 100% of all construction permits, ROW permits, railroad crossing permits, city permits, and highway permits have been completed and that no additional permit charges are expected. However, the impact of the Corrective Action Plan (CAP) and subsequent AAR submissions for route changes by sub-recipient ARE-ON is uncertain. Hence, it is possible there may be permit costs in future quarters. The variance for this reporting quarter is -91%. | 0 | N/A | 93 | The variance is related to the NTIA temporary suspension order and the impact of financial timing. The variance is -6%. | 72 | ARE-ON IRU providers have completed and invoiced 715.89 of 715.90 miles of fiber optic cable. The totals of both bring the project to 748.19 of 749.13 miles overall network build completion. The temporary suspension order by NTIA on July 11, 2012 heavily impacted sub-recipient ARE-ON's network build progress, thus no construction progress was made. The variance is -16% | 89 | The temporary suspension order by NTIA on July 11, 2012 negatively impacted sub-recipient ARE-ON's equipment deployment progress: - optical equipment to 3 of 39 sites - 2 of 10 core network routers - 1 of 2 access routers - 1 of 16 Ethernet switches - 2 of 28 security gateways - 1 remote access server No progress was made in deployment of two network management servers nor iSCSI storage arrays. ARE-ON continues to achieve momentum to recoup the time lost during the suspension. These circumstances resulted in a variance of -7%. | 87 | The temporary suspension order negatively impacted sub-recipient ARE-ON's network testing progress resulting in a variance of -13%. | 2013-02-15 16:00 | 2013-02-15 16:00 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2013 | Q1 | Q1 - 2013 | 9395 | 8189 | TRUE | 81 | This section of the Performance Project Report (PPR) compares actual expenditures to the Q1 2013 figures on the revised Baseline submitted to the project's Federal Program Officer on May 24, 2011. The underlying milestones of the actual expenditures have been revised based on the approved modified budget of March 2013. These milestones were revised based on budget modifications and timing resulting from the Corrective Action Plan (CAP) relative to the sub-recipient. The CAP and cost increases affected budget and expenditure timing resulting in budget modifications. NTIA gave guidance for this budget modification. In compliance with NTIA guidelines, the budget modification does not exceed 10% variance and there is no change in scope of work for Q1 2013. These situations have resulted in adjusted completion metrics going forward. These adjustments will be reflected throughout this report. These circumstances resulted in a variance of -15%. | 80 | Indirects, huts, easements, project management costs | Fourteen (14) of 16 total huts have been placed. Because of the March 2013 modified budget comparison to the May 24, 2011 revised baseline, the impact to this milestone has resulted in a -10% variance. | 100 | --- | 98 | The initial network design was completed in Q1 2012, resulting in purchases of optical equipment and routers at the end of March 2012. The initial design was revised resulting in additional equipment purchases during Q1 2013. Because of the March 2013 modified budget comparison to the May 24, 2011 revised baseline, the impact to this milestone has resulted in a -2% variance. | 0 | N/A | 9 | Because more IRUs are being used than originally projected, there are fewer railroad crossings and, thus, fewer required permits. Cost savings from this budget item will be applied in other areas where costs are higher than anticipated. It is believed that 100% of all construction permits, ROW permits, railroad crossing permits, city permits, and highway permits have been completed and that no additional permit charges are expected. However, the impact of the Corrective Action Plan (CAP) and subsequent AAR submissions for route changes by sub-recipient ARE-ON is uncertain. Hence, it is possible there may be permit costs in future quarters. The variance for this reporting quarter is +91%. | 0 | N/A | 95 | ARE-ON completed its major networking equipment procurement at the end of March 2012. The network design was revised requiring purchase of an additional router and optical equipment. Because of the March 2013 modified budget comparison to the May 24, 2011 revised baseline, the impact to this milestone has resulted in a -5% variance. | 73 | Construction is completed on 33.25 miles of 33.29 total miles of conduit for laterals, into which 46.71 of 47.28 total route miles of fiber optic cable has been placed. IRU providers have completed and invoiced 715.89 of 715.89 (100%) miles of fiber optic cable. The totals of both bring the project to 762.60 of 763.17 miles, or 99.93% overall network build completion. Because of the March 2013 modified budget comparison to the May 24, 2011 revised baseline, the impact to this milestone has resulted in a -23% variance. | 89 | Optical equipment has been deployed at 7 of 39 sites, 2 of 10 core network routers, 1 of 2 access routers, 1 of 16 Ethernet switches, 2 of 28 security gateways, 1 of 1 remote access servers, 0 of 2 network management servers, and 0 of 2 iSCSI storage arrays. Because of the March 2013 modified budget comparison to the May 24, 2011 revised baseline, the impact to this milestone has resulted in a -9% variance. | 100 | Testing of the optical and router equipment during hot staging is complete. Fiber optic cable testing is complete. Further network testing still remains to be completed. Because of the March 2013 modified budget comparison to the May 24, 2011 revised baseline, the impact to this milestone has resulted in a +51% variance. There is still effort and related expenditures remaining. | 2013-04-29 18:03 | 2013-04-29 18:03 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2013 | Q2 | Q2 - 2013 | 10611 | 8964 | TRUE | 84 | As projected in our last PPR, this section compares actual expenditures through Q2, 2013 to the original baseline milestones. The project milestone timing was extended as a result of the budget modifications submitted in March 2013. In compliance with the NTIA guidelines, the budget modification does not exceed 10% variance and there is no change in the scope of work. The timing issue led to the request for a no cost extension through September 30, 2013. NTIA has approved the extension. The budget modification in March 2013 and project extension resulted in a variance of -16% compared to the original baseline projections. | 81 | Indirects, huts, easements, project management costs | Sixteen (16) of 16 total huts have been placed. Renovations were completed at one existing hut site. The approved budget modification of March 2013 and project extension resulted in a variance of -19% to the original baseline projections. | 100 | --- | 98 | Due to a revision, additional purchases were required during Q1 2013. Installation of all network equipment is in final stages of completion. The approved budget modification of March 2013 and project extension resulted in a variance of -2% to the original baseline projections. | 0 | N/A | 100 | --- | 0 | N/A | 98 | All optical network equipment has been procured, however, the approved budget modification of March 2013 and project extension resulted in a variance of -2% to the original baseline projections. | 79 | Construction is completed, including 34.31 miles of conduit with *49.32 miles of fiber optic cable. IRU fiber providers have completed and invoiced for 100% (715.89 miles) of fiber optic cable. The totals of both bring the project to 765 miles of fiber optic cable deployed during the project. *Upon review of numbers, it was found that the original (total) 47 miles omitted one of the routes from Malvern, which corrected to approximately 1.2 miles. It is emphasized that this was not a new route, but a factual inconsistency (the field in the calculation was "zero" when it should have been "1.2"). Hence, the correct number was 48.4 miles rather than 47.2 miles as originally estimated. Secondly, the projectâ€™s engineering firm reconciled field records collected during construction and counts for feet of fiber and conduit with units placed during construction. Reconciliation of these records resulted in the correction of +0.75 mile to the overall length. These circumstances resulted in a | 83 | Optical equipment has been deployed at 31 of 36 sites, backbone routers at 3 of 9 sites, and other equipment staged and/or awaiting power at all remaining sites. The approved budget modification of March 2013 and project extension resulted in a variance of -17% to the original baseline projections. | 100 | --- | 2013-08-15 14:10 | 2013-08-15 14:10 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2013 | Q3 | Q3 - 2013 | 11519 | 9647 | TRUE | 100 | --- | 100 | Indirects, huts, easements, project management costs | --- | 100 | --- | 100 | --- | 0 | N/A | 100 | --- | 0 | N/A | 100 | --- | 100 | --- | 100 | --- | 100 | --- | 2013-12-23 09:51 | 2013-12-23 09:51 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570103 | 2010 | Q4 | Q4 - 2010 | 1227 | 2257 | TRUE | 3 | A formal RFP was issued and subrecipient was selected to operate/manage project implementation, however the formal contract was not executed until 1Q11. | 0 | Network Management/Operations | No activity this quarter. | 0 | A formal RFP was issued and an EA firm tentatively selected, however formal contract was not finalized until 1Q11. | 1 | Final route designs pursuant to Final EA appoval. | 0 | No activity this quarter. | 0 | No activity this quarter. | 0 | No activity this quarter. | 0 | No activity this quarter. | 0 | No activity this quarter. | 0 | No activity this quarter. | 0 | No activity this quarter. | 2011-02-18 15:54 | 2011-02-18 15:54 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2011 | Q1 | Q1 - 2011 | 2391 | 2941 | TRUE | 5 | Progress pending submission of proposed project route modifications affecting final FONSI approval. | 0 | Network Management/Operations | No activity this quarter. No variance from Baseline Plan. | 8 | Progress pending submission of proposed project route modifications. | 36 | Progress pending finalizing agreements with fiber providers and submission of proposed project route modifications. | 0 | Progress pending above noted final network/route designs. | 0 | Progress pending above noted final network/route designs. | 0 | Progress pending above noted final network/route designs. | 0 | Progress pending above noted final network/route designs. | 0 | Progress pending above noted final network/route designs. | 0 | Progress pending above noted final network/route designs. | 0 | No activity this quarter. No variance from Baseline Plan. | 2011-05-27 15:47 | 2011-05-27 15:47 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2011 | Q2 | Q2 - 2011 | 2935 | 3225 | TRUE | 7 | Progress pending final approval of proposed project route modifications affecting final FONSI approval. | 0 | Network Management/Operations | Progress pending final approval of proposed project route modifications. | 26 | Progress pending final approval of proposed project route modifications. | 71 | Progress pending finalizing agreements with fiber providers and final approval of proposed project route modifications. | 0 | Progress pending final approval of proposed project route modifications. | 0 | Progress pending final approval of proposed project route modifications. | 0 | Progress pending final approval of proposed project route modifications. | 0 | Progress pending final approval of proposed project route modifications. | 0 | Progress pending final approval of proposed project route modifications. | 0 | Progress pending final approval of proposed project route modifications. | 0 | Progress pending final approval of proposed project route modifications. | 2011-08-05 14:50 | 2011-08-05 14:50 | 6961 | 6961 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2011 | Q3 | Q3 - 2011 | 4123 | 3905 | TRUE | 9 | Progress pending final FONSI approval. | 0 | Network Management/Operations | Progress pending final FONSI approval. | 43 | Progress pending final review from State and Federal agencies. | 90 | Progress pending finalized agreements with fiber providers. | 0 | Progress pending final FONSI approval. | 0 | Progress pending final FONSI approval. | 0 | Progress pending final FONSI approval. | 0 | Progress pending final FONSI approval. | 0 | Progress pending final FONSI approval. | 0 | Progress pending final FONSI approval. | 0 | Progress pending final FONSI approval. | 2011-11-17 18:46 | 2011-11-17 18:46 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2011 | Q4 | Q4 - 2011 | 5351 | 5023 | TRUE | 13 | Progress pending final FONSI approval | 0 |  | N/A | 59 | Progress pending final FONSI approval | 100 | No variance from Baseline Plan | 0 | Progress pending final FONSI approval | 0 | Progress pending final FONSI approval | 0 | Progress pending final FONSI approval | 0 | Progress pending final FONSI approval | 0 | Progress pending final FONSI approval | 0 | Progress pending final FONSI approval | 0 | Progress pending final FONSI approval | 2012-02-28 14:20 | 2012-02-28 14:28 | 7311 | 7311 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2012 | Q1 | Q1 - 2012 | 6167 | 5686 | TRUE | 17 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 |  | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 71 | Progress pending processing of federal agency, Walker River Paiute Tribe, and Timbisha Shoshone Tribe easements. | 100 | No variance from Baseline Plan. | 10 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 2012-05-17 19:07 | 2012-05-17 19:07 | 7311 | 7311 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2012 | Q2 | Q2 - 2012 | 7083 | 6169 | TRUE | 19 | Progress pending execution of agreements, specifically with utility providers, and fiber delivery in 3Q12. | 0 |  | N/A | 80 | Progress pending processing of federal agency, Walker River Paiute Tribe, and Timbisha Shoshone Tribe easements. | 90 | The budget for "Network Design" activities are part of the "Professional Engineering Services" budget line item. This budget line also covers project management costs. Therefore, network design has been a qualitative, estimated percentage complete, not a budget consumption calculation. A revised estimate for network design is 90% which reflects current pending route modifications, as well as changes in design requirements from utility companies and state agencies. | 18 | Progress pending approval of Rights of Way from Bureau of Land Management, various Tribal entities, and acceptance of attachment applications. | 0 | New requirements, such as stationing on drawing and traffic control plans, needed from contractors doing work. Also, ongoing negotiations with landowners, some of which are out of state and slow to respond. | 0 | Pending approval of engineering re-design (route modifications) due to a utility not allowing use of substations for shelter placement. | 0 | Time frame of procurement modified to ensure the extension of equipment warranty period during actual deployment. | 0 | Progress pending execution of agreements, specifically with utility providers, and fiber delivery in 3Q12. | 0 | Pending granting of access to member hospitals, as well as installation of shelters at sites near substations. | 0 | Network testing not feasible until network has been deployed and activated. | 2012-08-15 15:33 | 2012-08-15 15:33 | 7311 | 7311 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2012 | Q3 | Q3 - 2012 | 8025 | 6719 | TRUE | 34 | Progress pending network design modifications, completion of fiber delivery in 4Q12, and finalization of Right-of-Way agreements with agencies and Tribal entities. | 0 |  | N/A | 95 | Progress pending issuance of federal agency and Bureau of Indian Affairs easements and Right-of-Way agreements. | 95 | The budget for "Network Design" activities are part of the "Professional Engineering Services" budget line item. This budget line also covers project management costs. Therefore, network design has been a qualitative, estimated percentage complete, not a budget consumption calculation. A revised estimate for network design is 95% which reflects current pending route modifications, as well as changes in design requirements from utility companies and state agencies. | 38 | Progress pending approval of Rights-of-Way from Bureau of Land Management, various Tribal entities, and acceptance of attachment applications. | 20 | Progress pending ongoing negotiations with landowners, some of which are out of State and slow to respond. | 5 | Pending approval of engineering redesign (route modifications). | 62 | Time frame of procurement modified to ensure the extension of equipment warranty period during actual deployment. | 1 | Progress pending acceptance of necessary attachment applications and completion of fiber delivery in 4Q12. | 8 | Progress pending granting of access to member hospitals, as well as installation of shelters at sites near substations. | 5 | Network testing timeline substantially impacted by project deployment schedule. | 2012-11-23 17:15 | 2012-11-23 17:15 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2012 | Q4 | Q4 - 2012 | 8823 | 7610 | TRUE | 36 | Progress pending approval of permits with utility providers related to fiber installation, and slow process in executing final agreements with federal agencies and Tribes related to Right-of-Way. | 0 |  | N/A | 95 | Progress pending issuance of Rights-of-Way from federal agencies and Tribes. | 95 | The budget for "Network Design" activities are part of the "Professional Engineering Services" budget line item. This budget line also covers project management costs. Therefore, network design has been a qualitative, estimated percentage complete, not a budget consumption calculation. An estimate for network remains 95% which reflects current pending route modifications. | 28 | Progress pending approval of Rights-of-Way from Bureau of Land Management, Bureau of Reclamation, U.S. Forest Service and Tribal entities. The ROA percent went down from 38% in Q3 2012 to 28% in Q4 2012 because of the grant funds being returned related to Zayo - Reno IRU. | 40 | Progress pending approval of permits with utility providers and other Federal agencies. | 18 | Pending approval of engineering re-designed (route modifications). | 79 | Time frame of procurement modified to ensure the extension of the equipment warranty period during actual deployment. | 4 | Progress pending approval of permits with utility providers related to fiber installation. | 8 | Time frame of equipment deployment modified due to pending approval of permits with utility providers, federal agencies and Tribal entities. | 20 | Network testing time line substantially impacted by the delay in project deployment schedule during the previous previous quarter. Pending approval of permits with utility providers, federal agencies and Tribal entities also meaningfully altered the project progress. | 2013-02-15 16:50 | 2013-02-15 16:50 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2013 | Q1 | Q1 - 2013 | 9929 | 8508 | TRUE | 41 | Progress pending approval of permits with utility providers related to fiber installation, and slow process in executing final agreements with federal agencies and Tribes related to Right-of-Way (ROW) and easements. | 0 |  | N/A | 95 | Progress pending issuance of ROW and easements from federal agencies and Tribes. | 95 | The budget for "Network Design" activities are part of the "Professional Engineering Services" budget line item. This budget line also covers project management costs. Therefore, network design has been a qualitative, estimated percentage complete, not a budget consumption calculation. An estimate for network remains 95% which reflects current pending route modifications. | 95 | No variance from baseline plan. | 40 | Progress pending approval of permits with utility providers and other Federal agencies. | 30 | Pending approval of engineering re-designed (route modifications). | 79 | Time frame of procurement modified to ensure the extension of the equipment warranty period during actual deployment. | 12 | Progress pending approval of permits with utility providers related to fiber installation. | 8 | Time frame of equipment deployment modified due to pending approval of permits with utility providers, federal agencies and Tribal entities. | 20 | Network testing time line substantially impacted by the delay in project deployment schedule during the previous previous quarter. Pending approval of permits with utility providers, federal agencies and Tribal entities also meaningfully altered the project progress. | 2013-05-28 13:50 | 2013-05-28 13:50 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2013 | Q2 | Q2 - 2013 | 10643 | 8982 | TRUE | 36 | Progress pending approval of permits with utility providers related to fiber installation, and slow process in executing final agreements with federal agencies and Tribes related to Rights of Way (ROW) and easements. Project progress continues although Federal funds have been withheld. If all qualifying expenses were able to be submitted for draw down the percent complete would be 53%, including just Draws 39 & 40. | 0 |  | N/A | 95 | Progress pending issuance of ROW and easements from Federal agencies and Tribal entities. | 95 | The budget for "Network Design" activities are part of the "Professional Engineering Services" budget line item. This budget line also covers project management costs. Therefore, network design has been a qualitative, estimated percentage complete, not a budget consumption calculation. An estimate for network remains 95% which reflect current pending route modifications. | 95 | Project funding hold preventing completion. | 40 | Progress pending approval of permits with utility providers and other Federal agencies. | 30 | Pending approval of engineering re-design (route modifications). | 85 | Time frame of procurement modified to ensure the extension of the equipment warranty period during actual deployment. | 14 | Progress pending approval of permits with utility providers related to fiber installation. | 8 | Time frame of equipment deployment modified due to pending approval of permits with utility providers, Federal agencies and Tribal entities. | 20 | Network testing time line substantially impacted by the delay in project deployment schedule during the previous quarter. Pending approval of permits with utility providers, Federal agencies and Tribal entities. | 2013-08-19 19:06 | 2013-08-19 19:06 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2013 | Q3 | Q3 - 2013 | 11243 | 9412 | TRUE | 45 | Progress pending approval of permits with utility providers related to fiber installation and slow process in executing final agreements with federal agencies and tribes related to Rights of Way (ROW) and easements. Q3 2013 activity was limited because of uncertainty of the future of the project and federal approval. |  |  | N/A | 95 | Progress pending issuance of ROW and easements from federal agencies and tribal entities. | 95 | Network design is near completion but was put on hold pending federal approval | 95 | Progress pending approval of permits with utility providers and other federal/state/tribal agencies; funding hold preventing further completion | 40 | Progress pending approval of permits with utility providers and other federal/state/tribal agencies; funding hold preventing further completion | 30 | Pending approval of engineering re-design (route modifications) | 85 | Timeframe of procurement modified to ensure the extension of the equipment warranty period during actual deployment | 14 | Progress pending approval of permits with utility providers related to fiber installation | 8 | Timeframe of equipment deployment modified due to pending approval of permits with utility providers, federal agencies and tribal entities | 20 | Network testing timeline substantially impacted by the delay in project deployment schedule during the previous quarter. Pending approval of permits with utility providers, federal agencies, and tribal entities | 2013-11-13 18:03 | 2013-11-13 18:03 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2013 | Q4 | Q4 - 2013 | 11829 | 10006 | TRUE | 45 | Progress pending approval of permits with utility providers related to fiber. Progress pending issuance of ROW and easements from federal agencies and tribal entities. Installation and slow process in executing final agreements with federal agencies and tribes related to Rights of Way (ROW) and easements. Q4 2013 activity was limited because of uncertainty of the future of the project and federal approval. | 0 |  | N/A | 95 | Progress pending issuance of ROW and easements from federal agencies and tribal entities. | 95 | Network design is near completion but was put on hold pending federal approval | 95 | Progress pending approval of permits with utility providers and other federal/state/tribal agencies; funding hold preventing further completion | 40 | Progress pending approval of permits with utility providers and other federal/state/tribal agencies; funding hold preventing further completion | 30 | Pending approval of engineering re-design (route modifications) | 85 | Timeframe of procurement modified to ensure the extension of the equipment warranty period during actual deployment | 14 | Progress pending approval of permits with utility providers related to fiber installation | 8 | Timeframe of equipment deployment modified due to pending approval of permits with utility providers, federal agencies and tribal entities | 20 | Network testing timeline substantially impacted by the delay in project deployment schedule during the previous quarter. Pending approval of permits with utility providers, federal agencies, and tribal entities | 2014-02-14 19:27 | 2014-02-14 19:27 | 7786 | 7786 | Nevada Hospital Association | TRUE
NT10BIX5570104 | 2010 | Q4 | Q4 - 2010 | 993 | 2036 | TRUE | 1 | Environmental Assessment is not complete therefore, no funds have been spent other than allowable funds as described in the Environmental Assessment Special Award Condition. | 0 |  | No Variance | 85 | No Variance | 75 | Unforeseen variables arose during the quarter due to additional needs surrounding the Environmental Assessment. Resources that would have been used to design the network had to be pulled and used for Environmental Assessment needs. | 15 | After discussions with several of the entities involved in Rights Of Way, Contact Network Inc. now sees that Rights of Way need to be submitted on a county/service area basis. Therefore our percent complete as reported in the baseline will not be accurate based on how the Rights Of Way are currently being processed. | 0 | Environmental Assessment is not complete therefore, no funds have been spent other than allowable funds as described in the Environmental Assessment Special Award Condition. | 0 | No Variance | 1 | We are in the process of negotiating additional equipment to purchase. Not all vendor meetings or equipment evaluation has taken place, therefore we have not purchased all equipment anticipated when baseline was completed. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-02-07 13:04 | 2011-02-07 13:04 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2011 | Q1 | Q1 - 2011 | 2103 | 2797 | TRUE | 2 | During this quarter it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 0 |  | No variance from baseline | 85 | The final draft of the Environmental Assessment was submitted during this quarter. We expect to receive the Finding of No Significant Impact during the next quarter. Likewise, we will also receive the final invoice from the Environmental Firm during the next quarter. | 75 | During this quarter it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs are held with various utilities and permits are negotiated with various entities the network design may need to be updated/changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 15 | During this quarter it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 8 | During this quarter it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict timelines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 19 | During this quarter it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 1 | During this quarter it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Also, delays caused by the Environmental Assessment and the need to pull resources that would have focused on material and equipment RFP's hindered our progress. The equipment RFP was not posted as anticipated during this quarter, therefore the procurement is behind versus the baseline projections. | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 2011-05-17 17:46 | 2011-05-17 17:46 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2011 | Q2 | Q2 - 2011 | 2927 | 3221 | TRUE | 14 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No Variance from Baseline | 100 | No Variance from Baseline | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 13 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 29 | During this quarter a total of thirty seven Community Anchor Institutions were connected to our network. The site preparation was complete for these thirty seven entities. Our projections for this quarter were to connect a total of forty seven Community Anchor Institutions. The construction and site preparation for the remaining ten institutions were not complete as of June 30, 2011 causing a variance in our projections. | 12 | Equipment is being purchased on an as needed basis. We expect significant purchases to be made during the next quarter. | 14 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 29 | During this quarter a total of thirty seven Community Anchor Institutions were connected to our network. The equipment deployment was complete for these thirty seven entities. Our projections for this quarter were to connect a total of forty seven Community Anchor Institutions. The equipment deployment for the remaining ten institutions were not complete as of June 30, 2011 causing a variance in our projections. | 7 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 2011-08-04 17:12 | 2011-08-04 17:12 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2011 | Q3 | Q3 - 2011 | 3903 | 3790 | TRUE | 26 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline. | 100 | No Variance from baseline. | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 37 | Since construction began we have been able to connect a total of foty-seven community anchor institutions which is significantly more than our baseline projections thus causing a variance in this category. | 13 | Equipment is being purchased on an as needed basis. | 28 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 37 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 37 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2011-11-07 11:44 | 2011-11-07 11:44 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2011 | Q4 | Q4 - 2011 | 5345 | 5019 | TRUE | 33 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline. | 100 | No Variance from Baseline. | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 23 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 23 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 37 | A total of forty seven Community Anchor Institutions are now connected to our network. The site preparation has been completed for these entities. Our projections for this quarter were to have a total of thirty-five Community Anchor Institutions thus causing a variance in our projections. | 24 | Equipment is being purchased on an as needed basis. | 28 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 37 | A total of forty seven Community Anchor Institutions are now connected to our network. The site preparation has been completed for these entities. Our projections for this quarter were to have a total of thirty-five Community Anchor Institutions thus causing a variance in our projections. | 37 | A total of forty seven Community Anchor Institutions are now connected to our network. The site preparation has been completed for these entities. Our projections for this quarter were to have a total of thirty-five Community Anchor Institutions thus causing a variance in our projections. | 2012-02-28 13:42 | 2012-02-28 13:42 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2012 | Q1 | Q1 - 2012 | 5943 | 5571 | TRUE | 36 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category varies from our initial baseline report. |  |  | No variance from baseline. | 100 | No variance from baseline. | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 23 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 23 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 37 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 27 | Equipment is being purchased on an as needed basis. | 28 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 37 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 37 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 2012-05-07 15:06 | 2012-05-07 15:06 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2012 | Q2 | Q2 - 2012 | 6739 | 5996 | TRUE | 47 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline | 100 | No variance from baseline | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 32 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 32 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 45 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 37 | Equipment is being purchased on an as needed basis. | 47 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 45 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 45 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 2012-07-30 17:49 | 2012-07-30 17:49 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2012 | Q3 | Q3 - 2012 | 8047 | 6730 | TRUE | 61 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline | 100 | No variance from baseline | 80 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 80% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 43 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 43 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 47 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 47 | Equipment is being purchased on an as needed basis. | 61 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 47 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 47 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 2012-11-26 16:11 | 2012-11-26 16:11 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2012 | Q4 | Q4 - 2012 | 8849 | 7632 | TRUE | 72 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline | 100 | No variance from baseline | 85 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 85% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 52 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 52 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 50 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 48 | Equipment is being purchased on an as needed basis. | 72 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 50 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 50 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 2013-02-19 16:16 | 2013-02-19 16:16 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2013 | Q1 | Q1 - 2013 | 9837 | 8455 | TRUE | 74 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline | 100 | No variance from baseline | 90 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 90% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 60 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 60 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 50 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 49 | Equipment is being purchased on an as needed basis. | 74 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build | 50 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 50 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 2013-05-20 16:52 | 2013-05-20 16:52 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2013 | Q2 | Q2 - 2013 | 10659 | 8990 | TRUE | 89 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline. | 100 | No variance from baseline. | 95 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 95% complete, as ride outs and meetings are held with various agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 95 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 95% complete, as ride outs and meetings are held with various agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 82 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 82% complete, as ride outs and meetings are held with various agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 60 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 78 | Equipment is being purchased on an as needed basis. | 89 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category varies from our initial baseline report. | 60 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 60 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 2013-08-20 13:11 | 2013-08-20 13:11 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2013 | Q3 | Q3 - 2013 | 11181 | 9372 | TRUE | 96 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 98 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 98% complete, as ride outs and meetings are held with various agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 85 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 85% complete, as ride outs and meetings are held with various agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 63 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 92 | Equipment is being purchased on an as needed basis | 92 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. As a result the actual percent complete in this category varies from our initial baseline report. | 63 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 63 | There is a variance from our baseline in this milestone category simply based on the number of Community Anchor Institutions connected. | 2013-11-04 14:05 | 2013-11-04 14:05 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2013 | Q4 | Q4 - 2013 | 11905 | 10075 | TRUE | 100 | No variance from baseline. | 0 |  | No variance from baseline. | 100 | No variance from baseline | 100 | No variance from baseline | 99 | We are still connecting CAI's via laterals and will have to continue to obtain rights of way etc. during the next quarter. | 99 | We are still connecting CAI's via laterals and will have to continue to obtain additional permits and permission from land owners during the next quarter. | 99 | We are still connecting CAI's and site preparation for these CAI's will continue during the next quarter. | 100 | No variance from baseline | 99 | We will have to construct a few laterals to connect CAI's, thus the network build will continue into next quarter. | 99 | We are still connecting CAI's therefore the equipment deployment for these CAI's will continue during the next quarter. | 99 | We are still connecting CAI's therefore the network testing for these laterals/CAI's will continue during the next quarter. | 2014-02-27 11:17 | 2014-02-27 11:17 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570105 | 2010 | Q4 | Q4 - 2010 | 1001 | 2047 | TRUE | 5 | The Environmental Assessment is not yet completed. | 0 |  | N/A | 60 | The State of New Jersey has not yet engaged a vendor to finalize the path of the 100 mile backhaul; as a result, an assessment of the fiber route has yet to be assessed. | 25 | The State of New Jersey has not yet awarded a contract to finalize the network design. | 20 | N/A | 5 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-08 10:11 | 2011-02-08 10:11 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2011 | Q1 | Q1 - 2011 | 2227 | 2859 | TRUE | 5 | Environment assessments are almost complete and RFP will be release next Qtr. | 0 |  | No change from baseline | 70 | Design scope was reworked to remove 100 mile back haul from design. Progress was delayed because we added 40 additional sites to the tower inventory. Assessments will be complete by end of April. | 25 | The back-haul network design has been reconfigured to remove 100 miles of fiber. As a result the percent complete has been revised from 100% to 25%. | 0 | Right of Way is no longer needed since fiber construction has been removed from the project | 5 | In line with baseline report | 0 | No change from baseline | 0 | No change from baseline | 0 | No change from baseline | 0 | No change from baseline | 0 | No change from baseline | 2011-05-20 16:23 | 2011-05-20 16:23 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2011 | Q2 | Q2 - 2011 | 3223 | 3373 | TRUE | 1 | Environment assessments are complete. RFP will be release in within a few day of the end of this Qtr. | 0 |  | No change from baseline | 80 | The environmental assessments are complete. In addition we have letters of compliance from Fish and Wildlife, Tribal. We are awaiting a programmatic agreement from Historic Preservation Society. | 5 | The back-haul network design has been reconfigured to remove 100 miles of fiber. As a result the percent complete has been revised from 100% to 5%. | 0 | Right of Way is no longer needed since fiber construction has been removed from the project | 0 | With the removal of the 100 mile backhaul there is no need for construction permits at this time. | 0 | No change from baseline | 0 | No change from baseline | 0 | No change from baseline | 0 | No change from baseline | 0 | No change from baseline | 2011-08-19 09:59 | 2011-08-19 09:59 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2011 | Q3 | Q3 - 2011 | 3899 | 3788 | TRUE | 1 | Environment assessments are complete. RFP has been release and responses are due on 10/25/11. | 0 |  | No change from baseline | 90 | The environmental assessments are complete and we have received a categorical exclusion. In addition we received letters of compliance from Fish and Wildlife, Tribal and a programmatic agreement from Historic Preservation Society. | 5 | The network design will not be complete until after the RFP process is complete and a vendor is selected. No change from previous quarter. | 0 | Right of Way is no longer needed since fiber construction has been removed from the project. | 0 | In addition to State owned towers, the State is open to using commercial sites which should minimize the required number of construction permits. No change from previous quarter. | 0 | As with Site preparation, the State's willingness to use commercial sites should reduce the amount of site prep needed. No change from previous quarter. | 0 | No change from baseline | 0 | No change from baseline | 0 | No change from baseline | 0 | No change from baseline | 2011-11-04 16:15 | 2011-11-04 16:15 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2011 | Q4 | Q4 - 2011 | 4721 | 4370 | TRUE | 1 | The overall completion is not in line with the baseline projection due to route modifications, and subsequent delays needed to change the RFP. | 0 |  | No change from baseline | 90 | The environmental assessments were done on the original site list. The State received a categorical exclusion. Letters of compliance we received form Fish and Wildlife, Tribal entities. In addition the Historic Preservation Society issued a programmatic agreement. | 5 | A preliminary network design is expected to be complete by the contractor by the end of Q1-2012. The final design should be complete in Q2-2012 after all sites are fully qualified. | 0 | At this time there are no right of way requirements. Fiber construction which was part of the original design has been removed from the project scope. | 0 | The project scope does not call for construction of any new towers. Any permits needed for attachment will be obtained by the contractor starting in the second quarter of 2012 | 0 | Site preparation is expected to commence in the second quarter of 2012. | 0 | At this time no equipment has been purchased or deployed. The State expects to make equipment purchases for Microwave Radios and eNodeB's by the end of the second quarter of 2012. | 0 | No Change from baseline | 0 | No change from baseline | 0 | No change from baseline | 2012-01-30 16:15 | 2012-01-30 16:15 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2012 | Q1 | Q1 - 2012 | 5953 | 5576 | TRUE | 1 | See narrative in section (3) | 0 | N/A | The State was unable to award, as a result construction activities have been delayed. | 90 | The environmental assessments were done on the original site list. The State received a categorical exclusion. Letters of compliance were received form Fish and Wildlife, Tribal entities. In addition the Historic Preservation Society issued a programmatic agreement. | 5 | The network design was not completed because a vendor was not selected through the RFP process | 0 | At this time there are no right of way requirements. Fiber construction which was part of the original design has been removed from the project scope. | 0 | The project scope does not call for construction of any new towers. Any permits needed for attachment will be obtained by the contractor. | 0 | Site preparation was not started because a vendor was not selected through the RFP process | 0 | At this time no equipment has been purchased or deployed because a vendor was not selected through the RFP process | 0 | The State was unable to award a contract with the RFP and as a result the build out has been delayed. | 0 | The State was unable to award a contract with the RFP and as a result the installation of equipment has been delayed. | 0 | Since the State has not deployed any equipment, testing has not begun. | 2012-05-08 10:07 | 2012-05-08 10:07 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2012 | Q2 | Q2 - 2012 | 6375 | 5796 | TRUE | 1 | See narrative in section (1) | 0 |  | The entire project has been delayed due to issues surrounding the response to NTIA/NOAA PIP & CAP as well as LTE suspension | 90 | The environmental assessments were done on the original site list. The State received a categorical exclusion. Letters of compliance were received form Fish and Wildlife, Tribal entities. In addition the Historic Preservation Society issued a programmatic agreement. | 5 | The network design was not completed because a vendor was not selected through the RFP process. The LTE suspension has impeded the network design portion of the project. | 0 | At this time there are no right of way requirements. Fiber construction which was part of the original design has been removed from the project scope. | 0 | The project scope does not call for construction of any new towers. Any permits needed for attachment will be obtained by the contractor. | 0 | Site preparation was not started because a vendor was not selected through the RFP process, and changes resulting from the LTE suspension. | 0 | Equipment procurement has not started and was delayed due to the LTE suspension. | 0 | Construction of the network is suspended at this time due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 0 | Equipment deployment has not started and will be delayed due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 0 | Network testing will be delayed due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 2012-07-10 16:05 | 2012-07-10 16:05 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2012 | Q3 | Q3 - 2012 | 7869 | 6639 | TRUE | 1 | See narrative for question 1 | 0 |  | N/A | 90 | The environmental assessments were done on the original site list. The State received a categorical exclusion. Letters of compliance were received form Fish and Wildlife, Tribal entities. In addition the Historic Preservation Society issued a programmatic agreement. | 5 | The network design was not completed because a vendor was not selected through the RFP process. The LTE suspension has impeded the network design portion of the project. | 0 | At this time there are no right of way requirements. Fiber construction which was part of the original design has been removed from the project scope. | 0 | The project scope does not call for construction of any new towers. Any permits needed for attachment will be obtained by the contractor. | 0 | Site preparation was not started because a vendor was not selected through the RFP process, and changes resulting from the LTE suspension. | 0 | Equipment procurement has not started and was delayed due to the LTE suspension. | 0 | Construction of the network is suspended at this time due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 0 | Equipment deployment has not started and will be delayed due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 0 | Network testing will be delayed due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 2012-11-14 11:50 | 2012-11-14 11:50 | 7541 | 7541 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2012 | Q4 | Q4 - 2012 | 8639 | 7453 | TRUE | 1 | See narrative for question 1 | 0 |  | N/A | 90 | The environmental assessments were done on the original site list. The State received a categorical exclusion. Letters of compliance were received form Fish and Wildlife, Tribal entities. In addition the Historic Preservation Society issued a programmatic agreement. | 5 | The network design was not completed because a vendor was not selected through the RFP process. The LTE suspension has impeded the network design portion of the project. | 0 | At this time there are no right of way requirements. Fiber construction which was part of the original design has been removed from the project scope. | 0 | The project scope does not call for construction of any new towers. Any permits needed for attachment will be obtained by the contractor. | 0 | Site preparation was not started because a vendor was not selected through the RFP process, and changes resulting from the LTE suspension. | 0 | Equipment procurement has not started and was delayed due to the LTE suspension. | 0 | Construction of the network is suspended at this time due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 0 | Equipment deployment has not started and will be delayed due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 0 | Network testing will be delayed due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 2013-01-31 15:38 | 2013-01-31 15:38 | 7645 | 7645 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2013 | Q1 | Q1 - 2013 | 9681 | 8373 | TRUE | 2 | See narrative for question 1 | 0 | n/a | n/a | 90 | The environmental assessments were done on the original site list. The State received a categorical exclusion. Letters of compliance were received form Fish and Wildlife, Tribal entities. In addition the Historic Preservation Society issued a programmatic agreement. | 5 | The network design was not completed because a vendor was not selected through the RFP process. The LTE suspension has impeded the network design portion of the project. | 0 | At this time there are no right of way requirements. Fiber construction which was part of the original design has been removed from the project scope. | 0 | The project scope does not call for construction of any new towers. Any permits needed for attachment will be obtained by the contractor. | 0 | Site preparation was not started because a vendor was not selected through the RFP process, and changes resulting from the LTE suspension. | 0 | Equipment procurement has not started and was delayed due to the LTE suspension. | 0 | Construction of the network is suspended at this time due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 0 | Equipment deployment has not started and will be delayed due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 0 | Network testing will be delayed due to the LTE suspension and uncertainty of the 700 MHz spectrum lease | 2013-05-10 13:40 | 2013-05-13 12:55 | 7645 | 7645 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2013 | Q2 | Q2 - 2013 | 10181 | 8669 | TRUE | 3 | See Narrative in Question 1 | 100 | Site Identification/Initial Coverage Design | Site identification resources onboarded and began site identification work; initial coverage design completed | 90 | The environmental assessments were done on the original site list. The State received a categorical exclusion. Letters of compliance were received form Fish and Wildlife, Tribal entities. In addition the Historic Preservation Society issued a programmatic agreement. | 5 | The network design was not completed because a vendor was not selected through the RFP process. The LTE suspension has impeded the network design portion of the project. | 0 | At this time there are no right of way requirements. Fiber construction which was part of the original design has been removed from the project scope. | 0 | The project scope does not call for construction of any new towers. Any permits needed for attachment will be obtained by the contractor. | 0 | Site preparation was not started because a vendor was not selected through the RFP process, and changes resulting from the LTE suspension. | 0 | Equipment procurement has not started and was delayed due to the LTE suspension. | 0 | Construction of the network is suspended at this time due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 0 | Equipment deployment has not started and will be delayed due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 0 | Network testing will be delayed due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 2013-07-26 13:34 | 2013-07-26 13:34 | 7645 | 7645 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2013 | Q3 | Q3 - 2013 | 11179 | 9371 | TRUE | 4 | See Narrative in Question 1 | 100 | Site Identification/Initial Coverage Design | Site identification completed in August; initial coverage design completed. | 90 | The environmental assessments were done on the original site list. The State received a categorical exclusion. Letters of compliance were received form Fish and Wildlife, Tribal entities. In addition the Historic Preservation Society issued a programmatic agreement. | 5 | The network design was not completed because a vendor was not selected through the RFP process. The LTE suspension has impeded the network design portion of the project. | 0 | At this time there are no right of way requirements. Fiber construction which was part of the original design has been removed from the project scope. | 0 | The project scope does not call for construction of any new towers. Any permits needed for attachment will be obtained by the contractor. | 0 | Site preparation was not started because a vendor was not selected through the RFP process, and changes resulting from the LTE suspension. | 0 | Equipment procurement has not started and was delayed due to the LTE suspension. | 0 | Construction of the network is suspended at this time due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 0 | Equipment deployment has not started and will be delayed due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 0 | Network testing will be delayed due to the LTE suspension and uncertainty of the 700 MHz spectrum lease. | 2013-11-01 17:43 | 2013-11-01 17:43 | 7645 | 7645 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2013 | Q4 | Q4 - 2013 | 11845 | 10019 | TRUE | 4 | See Narrative in Question 1. | 100 | Site Identification/Initial Coverage Design | Based on the the previously approved project scope in the UASI region, site identification was completed in August 2013 and the initial coverage design was completed in September 2013. Site identification for deployable assets in the Route 21 Corridor, Camden, and Atlantic City have begun and reflected in Site Preparation (2f). | 90 | The project team submitted the revised EHP Pre-Screening list to NTIA; currently under review with NTIA Environmental team. | 25 | Preliminary coverage design was completed for potential placement of deployables; final coverage design will depend on final vendor selection and finalized locations for deployables. | 0 | The newly approved project scope does not call for right of way requirements. | 0 | The newly approved project scope does not call for construction of any new towers. Any permits needed for attachment will be obtained by the contractor. | 5 | Potential sites have been identified for deployable assets; site visits are currently in process. | 0 | Equipment procurement has not started and was delayed due to the LTE suspension and change in project scope. | 0 | Construction of the network has not started and was delayed due to the LTE suspension and change in project scope. | 0 | Equipment deployment has not started and was delayed due to the LTE suspension and change in project scope. | 0 | Network testing has not started and was delayed due to the LTE suspension and change in project scope. | 2014-02-19 14:26 | 2014-02-19 14:26 | 7645 | 7645 | Treasury, New Jersey Department of | TRUE
NT10BIX5570106 | 2010 | Q4 | Q4 - 2010 | 1025 | 2070 | TRUE | 0 | This is in line with baseline plan. Estimate is less than 1% complete | 10 |  | We have attorneys reviewing the IRU dark fiber lease. Delays have resulted in no federal funds spent on this. | 50 | We have had a late notification from the SHPO that due to the scale of the project, they will now require a Class 1 and Class 3 survey by a cultural resource specialist. There is a variance from the 85% projected in the baseline. This should be made up in the following quarter | 30 | We are on schedule with our network design. | 10 | We have made progress in estimating that the tribe owns 70% (30 of the 40 miles) of the right of way for the project and that the BIA will not be requiring anything concerning that portion of the project because the tribe will be the owner of the fiber asset. | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 2011-02-09 17:32 | 2011-02-09 17:32 | 6703 | 6703 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2011 | Q1 | Q1 - 2011 | 2281 | 2886 | TRUE | 1 | Delays in the environmental work have pushed back the final network designs and procurement process. We are advancing work on the tribal and highway right of ways and easments, accelerating the contractor's work on network design prior to the overall contract completion, and hiring a project manager to assist with the multi-tasking for this project. | 60 |  | We have attorneys reviewing the dark fiber lease. We are slightly behind in our baseline projection because of federal government requirements and attorney commitments to other business. We have made significant progress however. The tribe's fiber rights will be honored and the extension to a 20 year time frame has been agreed to in principle. | 80 | Delays caused by the state historical preservation office's requirement for a complete cultural survey have prevented us from completing the environmental assessment as projected in the baseline. We are accelerating the preliminary report through the SHPO and NTIA to speed up the process. | 50 | final detailed network design depends upon the cultural survey having no significant findings. At the time of this report, that survey hadn't progressed enough for us to begin the final detailed design. We do have the fiber route maps completed. We have asked the primary contractor to begin work on the final designs in advance of the overall construction contract being completed. | 20 | Because we haven't been able to complete the survey so as to know the fiber route will make it through the environmental assessment, final detailed designs of the route haven't been completed. These are necessary for the application process for rights of way on the highway. Rights of way approvals on tribal properties can't begin until we know the route will not have any significant findings from the cultural survey. Indications are that the projected fiber route will stand so we are speeding up the process of getting clearance on all right of ways and easements through the realty department. | 20 | We have delays on this due to the slow progress on the environmental work. We are accelerating the combination of right of ways by the realty department and final network route design to begin the permit and approval process. | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 2011-05-24 15:47 | 2011-05-24 15:47 | 6703 | 6703 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2011 | Q2 | Q2 - 2011 | 3207 | 3365 | TRUE | 1 | We are significantly behind on the overall project. The primary detractions are the tribe's fiber agreement, the environmental assessment, and the lack of a completed and council approved contract with our vendor / partner so that we can begin the formal engineering designs and the material procurement. Minor details on the fiber agreement are still being worked out by the attorneys so we are very close to completing this agreement. However, the appraiser for the value was brought on board and the appraisal will be completed early in the next quarter. The environmental assessment is the biggest detractor, because the cultural survey work has taken significantly longer than planned. With the help of BTOP after our site visit, we have implemented target dates to remove these obstacles. The cultural survey work and concurrence letter is expected during the next quarter and the construction contract with our vendor will be completed by the middle of the next quarter. We also will have our | 98 |  | Because of some issues involving tribal sovereignty and indemnity clauses, we were not able to finalize the fiber agreement the telecommunications company. However, we had enough progress on the document to begin the appraisal, and an appraiser was selected before the end of this quarter. We expect the appraisal to be completed early in the next quarter. The final contract issues should be resolved by the middle of next quarter and this will put us back on schedule with our fiber agreement and the establishment of the in kind match. | 80 | There has been no progress on this because the cultural survey preliminary report was deemed insufficient by the State Historical Preservation Office for their issuance of a letter of concurrence. They are requiring the complete inventory report which will not be completed until the middle of the next quarter. We have made arrangements with the cultural survey specialist to bring in additional help and expedite this report. | 50 | We have not been able to make progress on this. The primary fiber route does appear to be finalized, but without the engineering contracts we can't provide the department of transportation the network designs in the manner they require. We are expediting the contract with the partner vendor to get this done by modifying the shortterm budget and pushing for a mid quarter completion of this contract. | 40 | We are slightly behind on this, as the lack of engineering designs for the network is preventing us from completing the state department of transportation from issuing the right of way clearances. We anticipate that this can get back on track with the push on our engineering designs so that an approval could be pending by the end of the next quarter. | 20 | Because of the dependency of this category on the rights of way, we have not been able to make any progress on this category. We have projected a completion date of late next quarter for the tribal rights of way. Because the amount of time projected for acquisition of these permits appears to be less, we should be near completion by the end of next quarter. | 0 | We have not been able to begin site preparation because the environmental assessment has not been completed. We expect the completion of the environmental assessment by the end of next quarter. This will not allow us enough time to complete site preparation for the nodes, however we expect to have the acquisition and appraisals completed by next quarter. | 0 | Because we have not been able to finalize the contract with our vendor, we have not been able to proceed on procurement. However, we have modified the short term budget with BTOP's approval, and with the acceleration on the delivery date for contract approval in the middle of next quarter, we expect to be close to schedule on this by the end of next quarter. | 0 | No Variance from baseline | 0 | No Variance from baseline | 0 | No variance from baseline | 2011-08-18 17:30 | 2011-08-18 17:30 | 6703 | 6703 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2011 | Q3 | Q3 - 2011 | 4119 | 3903 | TRUE | 1 | We are are planing to be back on track with the baseline plan in the next couple of months. The contract with Praxis is going before council on November 4th. We expect to start the procurement of materials and construction within 60 days of the councils approval. We may be able to hit the baseline goal of having 6 miles of fiber deployed by the end of December 2011. | 98 |  | The Sovereign Immunity issue has been resolved. Through this process we discovered that the original easement was not recorded. We are resolving this issue and will push the completion of this task into next quarter. | 100 | Completed | 50 | The primary fiber route has been finalized by the submittal of the Environmental Assessment and the clearance of the Tribal Rights of Way and Easementsâ€™. Without the engineering contracts we can't provide the department of transportation the network designs in the format they require for their Right of Ways. The remaining 50 percent consists of the outside plant design and the inside plant design. | 100 | We have finalized the fiber route and are able to use the Nevada Department of Transportation rights of way. | 25 | We have the application for the NDOT permits and after the contract with Praxis is signed they will be filed. Getting the permit will take 30 - 45 days but we do not expect any issues. | 5 | The sites have been identified and we will be preparing them for construction in the next quarter. | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 2011-11-17 16:53 | 2011-11-17 16:53 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2011 | Q4 | Q4 - 2011 | 5291 | 4958 | TRUE | 1 | We are are planing to be back on track with the baseline plan in the next couple of months. The contract with Praxis was approved by the council on November 4th. The contract is unsigned at this point due to the difficulty Praxis is having with the bonding requirement. They have been denied bonding by several companies due to lack of bonding history, and perceived problems with the tribes sovereign immunity. They have submitted the necessary financial documents to additional surety companies and are waiting for final approval. If they are still unable to get bonded we will submit a waiver request with the NTIA in the next quarter. | 100 |  | The Sovereign immunity issue has been resolved. | 100 | Complete | 50 | The ability to complete the design is reliant on the signing of the praxis contract. We are expecting to have the mid level design completed within 30 days of the signing. | 100 | We have finalized the fiber route and are able to use the Nevada Department of Transportation rights of way. | 35 | We have the application for the NDOT permits and after the contract with Praxis is signed they will be filed. Getting the permit will take 30 - 45 days but we do not expect any issues. | 10 | The sites have been staked out and we will be preparing them for construction in the next quarter. | 0 | Equipment procurement is part of the construction contract with Praxis. They have started to place orders and are expecting deliveries to start around the end of January. We can not book any percent complete as the contract with Praxis is not signed and they cannot invoice us yet. | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 2012-02-27 13:33 | 2012-02-27 13:43 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2012 | Q1 | Q1 - 2012 | 6133 | 5669 | TRUE | 1 | We are are planing to be back on track with the baseline plan in the next couple of months. The contract with Praxis is ready to be signed as soon as the bonding issues are resolved. Praxis has set an aggressive construction schedule and once the contract is signed we are looking at being back on track with the base line in the next quarter. | 100 |  | The Sovereign immunity issue has been resolved. | 100 | Complete | 50 | The ability to complete the design is reliant on the signing of the praxis contract. | 100 | Complete | 45 | We have the application for the NDOT permits and after the contract with Praxis is signed they will be filed. Getting the permit will take 30 - 45 days but we do not expect any issues. | 10 | The sites have been staked out and we will be preparing them for construction in the next quarter. | 0 | Equipment procurement is part of the construction contract with Praxis. We can not book any percent complete as the contract with Praxis is not signed. | 0 | We are behind because of the delays in the signing of the Praxis contract and are unable to construct until the contract is signed. The IRU is being worked on and we should have it completed in the next quarter. | 0 | We are behind because of the delays in the signing of the Praxis contract and are unable to deploy any equipment until the contract is signed. | 0 | No variance from baseline | 2012-05-16 13:02 | 2012-05-16 13:02 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2012 | Q2 | Q2 - 2012 | 7091 | 6173 | TRUE | 4 | We are are planing to be back on track with the baseline plan in the next couple of months. The construction contract with the contractor is signed and we are finishing up the permitting in the beginning of the next quarter. We have set an aggressive construction schedule and expect to be back on track with the base line in the next quarter. | 100 |  | The Sovereign immunity issue has been resolved. | 100 | Complete | 75 | The outside plant, fiber route, and node engineering is complete. We are expecting the inside plant and electronic engineering to be complete in the next quarter. | 100 | Complete | 75 | The Storm Water Pollution Prevention Plan is the last permit to be obtained and we are expecting to have that back in the beginning of the next quarter. | 15 | The node sites have been staked out and are ready to be prepared in the next quarter. | 10 | The requests for proposals are posted and we are expecting to see results in the beginning of the next quarter. | 25 | The Indefeasible Right to Use has been written and we expect to have it approved by the tribal council in the next quarter. | 0 | Delays in the construction contract signing have prevented us from deploying any equipment. | 0 | No variance from baseline. | 2012-08-15 15:50 | 2012-08-15 15:50 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2012 | Q3 | Q3 - 2012 | 7959 | 6686 | TRUE | 31 | Construction has started and we have deployed twenty six miles of inter duct and eleven miles of fiber. We expect to have most if not all of the inter duct placed by the end of the next quarter. | 100 |  | The Sovereign immunity issue has been resolved. | 100 | Complete | 75 | The outside plant, fiber route, and node engineering is complete. We are expecting the inside plant and electronic engineering to be complete in the next quarter. | 100 | Complete | 100 | Complete | 100 | The node sites have the concrete slabs in place and are waiting for the nod buildings to be delivered. | 50 | The result of the request for proposals have us using Ericsson equipment and the procurement is dependant on the completion of the network design. | 35 | The Easement has been written and we expect to have it approved by the tribal council in the next quarter. | 25 | We have deployed about 25 percent of the equipment. | 0 | No variance from baseline. | 2012-11-19 16:49 | 2012-11-19 16:49 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2012 | Q4 | Q4 - 2012 | 8807 | 7601 | TRUE | 52 | Construction has continued and we are 10.45 away from having all of the substructure for the back bone in the ground. We have had some challenges with the various types of soil and rock along the route that has slowed our expected progress. | 100 |  | The Sovereign immunity issue has been resolved. | 100 | Complete | 80 | The outside plant, fiber route and node engineering is complete. We have the node buildings on order and expect to have them installed in the next quarter. | 100 | Complete | 100 | Complete | 100 | Complete | 60 | Due to the time that has passed since our last request for quote another request for quote will be posted and based on the replies received, procurement will continue. We are expecting to have our order for equipment finished in the next quarter. | 35 | The easement has been written and we expect to have it approved by the tribal council in the next quarter. | 35 | We have deployed about 35 percent of the equipment. | 0 | We expect to start testing the fiber in the next quarter | 2013-02-15 15:10 | 2013-02-15 15:10 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2013 | Q1 | Q1 - 2013 | 9945 | 8517 | TRUE | 57 | We are approximately 57 percent complete. | 100 |  | Complete | 100 | Complete | 90 | The outside plant, backbone fiber and node engineering are completed. The node buildings have been installed and we expect the inside plant and outside plant engineering and installation to be completed in the next quarter. | 100 | Complete | 100 | Complete | 100 | Complete | 75 | We are receiving the proposals back and expect to select a vendor in the beginning of the next quarter. | 60 | We are finishing up the IRU and are scheduled to take it before council on the third of May 2013 | 40 | We have deployed about 40 percent of the equipment | 0 | We expect to start testing in the next quarter as the backbone fiber and node sites are finished being installed. | 2013-05-28 17:10 | 2013-05-28 17:10 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2013 | Q2 | Q2 - 2013 | 10605 | 8961 | TRUE | 63 | We are approximately 63 percent complete. | 100 |  | Complete | 100 | Complete | 90 | The outside plant, backbone fiber and node engineering are completed. The node buildings have been installed and we expect the inside plant and outside plant engineering and installation to be completed in the next quarter. | 100 | Complete | 100 | Complete | 100 | Complete | 90 | The equipment has begun to be delivered and we expect all of the equipment to be received in the begining of the next quarter. | 90 | The IRU has been completed and approved by council. | 45 | We have deployed about 45 percent of the equipment. As we recieve more equipment it will be installed. | 0 | We expect to start testing in the next quarter as the backbone fiber and node sites are finished being installed. | 2013-08-15 12:00 | 2013-08-15 12:00 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2013 | Q3 | Q3 - 2013 | 11257 | 9419 | TRUE | 82 | We still need the network routers and switches to be delivered and the connection to the internet is not completed. Without this, the data center server software cannot be downloaded, installed and configured. | 100 |  | Complete | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 95 | The network router and switches have not been ordered due to the contractor waiting for invoices to be paid | 100 | NA | 75 | All fiber electronics have been deployed. The network routers, switches and data center servers have not been deployed yet due delays caused in getting network connectivity through our network provider and the impact to scheduling deployment of the data center servers requiring internet connectivity for the vendor to come out and setup. | 50 | Network testing of the splicing is nearly complete. Testing of the fiber electronics is nearly complete. Testing of the CAI connections is ongoing and faulty location equipment is being replaced as needed. The delay in a connection to the POP in Reno has impacted the testing of the fiber electronics along the route. | 2013-11-14 19:13 | 2013-11-14 19:13 | 6703 | 6703 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2013 | Q4 | Q4 - 2013 | 11883 | 10051 | TRUE | 85 | We are still configuring the network and installing network management systems. | 100 |  | Complete | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 80 | Some switches and servers are not deployed yet. | 75 | Testing of network fiber to CAIs still shows some configuration or splicing issues. Final test results not completed | 2014-02-25 12:33 | 2014-02-25 12:33 | 6703 | 6703 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2014 | Q1 | Q1 - 2014 | 12289 | 10460 | TRUE | 100 | NA | 100 |  | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 2014-06-24 12:37 | 2014-06-24 12:37 | 6703 | 6703 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570107 | 2010 | Q4 | Q4 - 2010 | 937 | 1985 | TRUE | 1 | N/A | 0 |  | N/A | 50 | N/A | 3 | Our schedule for network design has varied from the baseline estimate because finalizing the contract for engineering work has taken more time than originally planned. We anticipate the network design will be substantively complete in the next quarter. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-01-30 16:40 | 2011-01-30 16:40 | 6748 | 6748 | Texas A&M University | TRUE
NT10BIX5570107 | 2011 | Q1 | Q1 - 2011 | 2317 | 2904 | TRUE | 4 | On schedule | 0 |  | On schedule | 99 | We anticipated completion by this time but have been delayed by Wildlife and Fisheries approval. | 72 | Our schedule for network design has varied from the baseline estimate because finalizing the contract for engineering work took more time than originally planned. We have made substantial progress in the last quarter towards completing the network design. | 15 | On schedule | 15 | On schedule | 0 | We anticipated some construction by this time but were delayed due to lack of FONSI. | 0 | Equipment procurement has been delayed pending the receipt of the FONSI. We have initiated orders for some equipment and will have progress to report in the next quarter. | 0 | On schedule | 0 | On schedule | 0 | On schedule | 2011-05-25 17:47 | 2011-05-25 17:47 | 6973 | 6973 | Texas A&M University | TRUE
NT10BIX5570107 | 2011 | Q2 | Q2 - 2011 | 3191 | 3356 | TRUE | 13 | On Schedule (See Note Below) | 0 |  | N/A | 100 | FONSI Received 06/07/2011 | 85 | Emphasis on construction kept us from finishing the Network Design | 70 | On Schedule exception noted below | 70 | On Schedule exception noted below | 8 | We are behind schedule due to delays in the receipt FONSI. | 30 | Orders initiated after receipt of FONSI some materials received | 1 | We anticipated building 4% completion but only completed 1% | 0 | Equipment for two systems are on order and awaiting installation. | 0 | Installation completion did not allow time for final testing | 2011-08-18 11:52 | 2011-08-18 11:52 | 6973 | 6973 | Texas A&M University | TRUE
NT10BIX5570107 | 2011 | Q3 | Q3 - 2011 | 4359 | 4036 | TRUE | 19 | No Variance | 0 |  | N/A | 100 | No Variance | 88 | Behind schedule due to re-engineering Killeen Route | 95 | We are behind schedule as noted below | 95 | We are behind schedule as noted below | 16 | On schedule except as noted below | 45 | Behind schedule as noted below | 5 | Behind schedule as noted below | 8 | Behind schedule as noted below | 6 | Behind schedule as noted below | 2011-11-30 17:55 | 2011-11-30 17:55 | 6973 | 6973 | Texas A&M University | TRUE
NT10BIX5570107 | 2011 | Q4 | Q4 - 2011 | 5181 | 4845 | TRUE | 10 | Behind schedule as noted below | 0 |  | N/A | 100 | No Variance | 95 | Behind schedule as noted below | 95 | Behind schedule as noted below | 95 | Behind schedule as noted below | 18 | Behind schedule as noted below | 80 | Behind schedule as noted below | 8 | Behind schedule as noted below | 10 | Behind schedule as noted below | 8 | Behind schedule as noted below | 2012-02-21 18:09 | 2012-02-21 18:09 | 6973 | 6973 | Texas A&M University | TRUE
NT10BIX5570107 | 2012 | Q1 | Q1 - 2012 | 6363 | 5787 | TRUE | 32 | The DWDM, radio gateways and routers were purchased this quarter.Overall project progress has been slower due to the lack of availability of materials to manufacturers and suppliers to our chosen vendors. This has been resolved in recent quarters but the delays impacted the overall project schedule. Additionally, the effort required for a non utility agency such as Texas A&M University, to obtain the required lease agreements for right of way access was underestimated and this continues to be the largest factor regarding scheduling the construction. We have established a plan of action that includes twice weekly follow-ups with the permitting agencies as well as pre-construction meetings at the agency locations. This will continue until all permitting requirements have been met. | 0 |  | n/a | 100 | No variance | 100 | No variance | 97 | The effort required for a University to obtain the required lease agreements for right of way access was underestimated and this continues to be the largest factor regarding scheduling the construction. We have established a plan of action that includes twice weekly follow-ups with the permitting agencies as well as pre-construction meetings at the agency locations. This will continue until all permitting requirements have been met. | 97 | The effort required for a University to obtain the required lease agreements for right of way access was underestimated and this continues to be the largest factor regarding scheduling the construction. We have established a plan of action that includes twice weekly follow-ups with the permitting agencies as well as pre-construction meetings at the agency locations. This will continue until all permitting requirements have been met. | 100 | no variance | 30 | For this section we are considering equipment as that which falls under Network and Access Equipment. Our intention is to order equipment 30-60 days prior to turning-up fiber to prevent the warranty from being in effect long before deployment . Delays caused by supplier problems have cleared up with major part of the equipment and materials received. | 20 | We intend to catch up the baseline project schedule by February 1, 2013. The effort required for TAMU to obtain the required lease agreements for right of way access was underestimated and this continues to be the largest factor regarding scheduling the construction In turn that impacts the network build progress. We have established a plan of action that includes twice weekly follow-ups with the permitting agencies as well as pre-construction meetings at the agency locations. This will continue until all permitting requirements have been met. | 30 | We intend to catch up to the baseline project schedule by March 1, 2013. Equipment deployment is dependent on fiber miles placed and specific innerconnections being made. | 12 | We intend to catch up to the baseline project schedule by March 1, 2013. Network testing commences after fiber terminations are completed (dependency on fiber placing which has seen delays).If the network is behind in construction, it will be behind in testing. The network testing can not be accomplished until network segments are terminated. | 2012-05-31 14:44 | 2012-05-31 14:44 | 6171 | 6171 | Texas A&M University | TRUE
NT10BIX5570107 | 2012 | Q2 | Q2 - 2012 | 7097 | 6176 | TRUE | 42 | Baseline anticipated almost 100% completion at this point. Due to delays in EA, and permitting issues we are anticipating completion in February of 2013. Aggressive construction is currently underway on our two major segments, Texarkana and Stephenville. | 0 |  | n/a | 100 | No Variance | 100 | No Variance | 99 | One remaining right of way to negotiate with City of Waco which we anticipate receiving within the next 60 days. This segment is not scheduled for construction until November of 2012 | 98 | City of Waco Permit is pending resolution of Franchise agreement for ROW access | 100 | No Variance | 75 | Delays caused by supplier problems have resolved with major part of materials and equipment received. In order to optimize equipment warranty for Network access equipment it is our intention to order 30-60 days prior to turn up. We are currently ordering all of the final routers, and doing final engineering on the balance of the DWDM systems. | 44 | Baseline anticipated being at about 98% at this time but for the same reasons as above we are at 44%. All permits other than Waco are now complete. We have doubled our construction crew size in Stephenville and we are not installing at a rate faster than originally scheduled. As above, we anticipate completion of all fiber segments by February of 2013. | 30 | The delays in construction have delays in the equipment deployment since it is dependant upon fiber completion. We anticipate final equipment deployment no later than March of 2013 | 15 | Delays caused by supplier problems have resolved with major part of materials and equipment received. Testing will be done as rapidly as we can deploy fiber and equipment. | 2012-08-15 17:36 | 2012-08-15 17:36 | 6973 | 6973 | Texas A&M University | TRUE
NT10BIX5570107 | 2012 | Q3 | Q3 - 2012 | 8161 | 6791 | TRUE | 60 | We have completed the majority of both the Stephenville and Texarkana construction. In addition, the TAMU CIS core routers are being installed, all of the access routers have been received. | 0 |  | n/a | 100 | No Variance | 100 | No Variance | 99 | Meetings with City of Waco went well and Franchise Agreements and permitting have progressed slower than anticipated. | 100 | Resolution with City of Waco and Permit approvals granted thereafter | 100 | No Variance | 80 | Remaining equipment will continue to be ordered in the 30-60 day window prior to deployment for warranty purposes. | 70 | The 70% completion rate will keep us on track for completing by the revised February 2013 date. | 35 | This remains dependent on fiber terminations, testing and specific interconnections being completed. We are aggressively pursuing our established project goals for deployment. | 25 | Network Testing remains dependent on fiber placing/splicing/terminations and will follow a close schedule behind equipment deployment. | 2012-11-29 19:54 | 2012-11-29 19:54 | 6186 | 6186 | Texas A&M University | TRUE
NT10BIX5570107 | 2012 | Q4 | Q4 - 2012 | 8957 | 7733 | TRUE | 64 | A portion of the Texarkana segment is being constructed by the City Water Utilities group. Agreements are being negotiated. Negotiations are ongoing with the City of Waco for that segment. Permits and construction to follow. | 0 |  | n/a | 100 | No Variance | 100 | No Variance | 99 | Obtaining permits and agreements with the City of Waco is taking longer than anticipated. | 100 | Resolution with City of Waco and Permit approvals granted thereafter | 100 | No Variance | 100 | The generator purchased was the only item within the project that fit the category of "equipment". The generator has been purchased and installed. | 70 | The 70% completion rate will keep us on track for completing by the revised February 2013 date. | 100 | The generator has been installed. | 25 | Network Testing remains dependent on fiber placing/splicing/terminations. | 2013-02-25 19:19 | 2013-02-25 19:19 | 6186 | 6186 | Texas A&M University | TRUE
NT10BIX5570107 | 2013 | Q1 | Q1 - 2013 | 9919 | 8501 | TRUE | 78 | 78% is based on billing. 97% of the fiber has been placed. At this point we anticipate a total of 150.82 miles upon project completion. This is slightly higher than our estimate when we submitted the PIP at which time we estimated 141. This is due to conditions faced once the contractor got on site and began construction. | 0 |  | n/a | 100 | No Variance | 100 | No Variance | 99 | Obtaining permits and agreements with the City of Waco is taking longer than anticipated. | 100 | Resolution with City of Waco and Permit approvals granted thereafter | 100 | No Variance | 100 | The generator purchased was the only item within the project that fit the category of "equipment". The generator has been purchased and installed. | 80 | Network build occurs subsequent to fiber placing/splicing/terminations. | 100 | The generator has been installed. | 80 | Network Testing occurs subsequent to fiber placement/splicing/termination and the network build. | 2013-05-28 11:00 | 2013-05-28 11:00 | 6777 | 6777 | Texas A&M University | TRUE
NT10BIX5570107 | 2013 | Q2 | Q2 - 2013 | 10811 | 9078 | TRUE | 88 | We are 99% complete with fiber placement; however, since the overall percent complete is based on draw downs and given how our billing cycle works, we only show 88% complete. | 0 |  | n/a | 100 | No Variance | 100 | No Variance | 100 | All Right of Way issues resolved late June with City of Waco | 100 | No Variance | 100 | No Variance | 100 | No Variance | 99 | No Variance | 100 | No Variance | 99 | Network Testing occurs subsequent to fiber placement/splicing/termination and the network build. | 2013-08-29 15:39 | 2013-08-30 22:55 | 6186 | 6186 | Texas A&M University | TRUE
NT10BIX5570107 | 2013 | Q3 | Q3 - 2013 | 12001 | 10166 | TRUE | 100 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2014-03-28 12:31 | 2014-03-28 12:31 | 6186 | 6186 | Texas A&M University | TRUE
NT10BIX5570108 | 2010 | Q4 | Q4 - 2010 | 1231 | 2262 | TRUE | 0 | No variance | 1 | Administrative | Project staff | 0 | Work started. On track to submit by Jan. 31. | 0 | Work started | 0 | No variance | 0 | NA. Costs are included in 2h Network Build. | 0 | No variance | 0 | Lab equipment ordered. | 0 | Several fiber IRUs in negotiations. Drafting RFPs for other leases and construction. | 0 | No variance | 0 | NA. Using existing staff not charged to project plus contractual resources reported in 2k Other. | 2011-02-18 17:08 | 2011-02-18 17:08 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2011 | Q1 | Q1 - 2011 | 1925 | 2708 | TRUE | 4 | Target was 3%. CMS was able to finalize fiber lease agreements ahead of schedule. By securing these routes ahead of schedule, CMS anticipates lighting a major fiber route (Collinsville to Chicago) sooner then originally anticipated. | 5 |  | Target was 6%. The budgeted amount for this milestone is $2,922,971. This is a slight change from the original amount of $2,518,872. Costs for office equipment were lower then expected and project staff started later then expected. | 89 | Target was 100%. The total amount budgeted for this milestone is $890,000. The SHPO approval has taken longer then anticipated. CMS submitted the final EA on April 12 and received a FONSI on April 22. Delays in completing the Environment Assessment have not yet impacted the overall project timeline as construction is not scheduled to begin until July. | 8 | Target was 15% and the total amount budgeted for this milestone is $4,390,444. This amount has changed from the original budgeted amount of $4,419,739 and will likely be decreased again to $3,453,800. The costs for Network Design are looking to be less than anticipated. We are on track to complete detailed design for 25% of the backbone and 25% of the lateral network miles at the end of Year 1 Quarter 4. We anticipate the difference between the budgeted amount and revised projection to be moved to the Network Build milestone in the future. | 6 | Target was 2%. The budgeted amount for this milestone is $1,051,729. The engineering firm is making faster than anticipated progress on researching and preparing right of way permits. CMS established conservative targets through Y2Q2 with all Rights of Way permits scheduled to be completed by Y2Q3. As the project is moving forward we have better insight into the time needed for this activity and have adjusted our forecasts accordingly. | 0 | NA - included in 2h Network Build. | 1 | No variance. The budgeted amount for this milestone is $3,457,000. | 6 | Target was 8%. The budgeted amount for this milestone is $11,275,418. So far, equipment costs are lower than anticipated. CMS also planned to purchase fiber test equipment during this quarter but experienced delays with the procurement process. CMS received questions from vendors regarding the bid specifications and issued clarifications accordingly. As a result, the due date was extended to allow vendors time to adjust their proposals. Additionally, CMS needed to seek clarifications on vendor proposals prior to award. These two issues combined to delay the award by several weeks. The procurement was awarded March 30. We are in the process of issuing orders to the successful vendor. We anticipate the equipment will be received and paid for by the end of the next reporting period. The delay for the fiber test equipment does not impact the overall project timeline. | 3 | Target was 0%. The budgeted amount for this milestone is $71,316,055. CMS secured fiber leases for 281 miles ahead of schedule and transferred another 271 miles of existing leased fiber to the project. We are working to secure additional leases along a main fiber route. These efforts will enable CMS to light a major fiber route (Collinsville to Chicago) sooner then originally anticipated. | 0 | No variance. The budgeted amount for this milestone is $1,049,901. This is a slight change from the original amount of $1,454,000. | 0 | NA - using existing staff not charged to project plus contractual resources reported in 2K Other. | 2011-05-10 13:45 | 2011-05-10 13:45 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2011 | Q2 | Q2 - 2011 | 3081 | 3298 | TRUE | 5 | Baseline target is 6%. Previous PPR set a target of 8%. | 9 |  | Baseline is 10%. Previous PPR set a target of 9%. The budgeted amount for this milestone is $2,925,971 this is a slight increase from $2,922,971. Equipment costs are tracking slightly below our original estimates which is why the forecast for this milestone was set at 9% which is 1% less then the baseline. | 97 | Baseline target is 100%. Previous PPR set a target of 92%. The total amount budgeted for this milestone is $918,510 which is a slight increase from $890,000. The EA is complete and the project has received it's FONSI. Total costs for the EA came in slightly below projections. However, we anticipate unplanned costs for EA modifications associated with revised tower locations and CAI changes. | 17 | Baseline target is 35%. Previous PPR set a target of 32%. The total amount budgeted for this milestone has been reduced to $4,387,444 from $4,390,444 as cost projections for wireless consulting were less then budgeted. The 17% complete is based upon an actual cumulative spend of $734,141 at the end of this quarter. Invoices for an additional $182,617 were received for work complete, but not in time to process payments by the end of the quarter. With this additional spend, we would have achieved 21% complete for this quarter. In terms of actual activity, 42% of the network design (64% laterals and 38% backbone) and 26% of the bidding documents are complete as of June 1, 2011. | 12 | Baseline target is 2%. Previous PPR set a target of 15%. The budgeted amount for this milestone is $1,051,729. The 12% complete is based upon an actual cumulative spend of $127,252 at the end of this quarter. Invoices for an additional $44,985 were received for work complete, but not in time to process payments by the end of the quarter. With this additional spend, we would have achieved 16% complete for this quarter. | 0 | NA - included in 2h Network Build. | 1 | Baseline target is 11%. Previous PPR set a target of 11%. The budgeted amount for this milestone category is $3,457,000. We anticipated electrical upgrades in multiple POP sites; however, we have experienced delays. Several of the POP sites are in leased facilities. The contracts needed to be amended to address costs associated with the electrical upgrades. An engineering assessment is needed at another site to determine the overall electrical needs. As for the work at state owned sites, we are finalizing a contract to perform the electrical work. This same contract will be used to purchase new UPS equipment. By the end of next quarter we expect to have amended the POP site contracts to address the electrical upgrades, started the engineering assessment, and finalized the vendor contract for electrical and UPS.There is no negative impact to the project schedule as these activities do not need to be completed until the fiber is installed. The work will continue in parallel to the fiber | 6 | Baseline target is 26%. Previous PPR set a target of 25%. The budgeted amount for this milestone category is $11,275,418. The 6% complete is based upon an actual cumulative spend of $714,172 at the end of this quarter. Invoices for an additional $1,849,878 were received for equipment received by the end of the quarter, but not in time to process payment. With this additional spend, we would have achieved 16% completion. We anticipated upgrading UPS equipment at multiple POP sites; however due to delays with the electrical upgrades the purchases have been pushed back to next quarter. There is no negative impact to the project schedule. | 3 | Baseline target is 0%. Previous PPR set a target of 3%. The budgeted amount for this milestone is $71,316,055. Project activities include the completion of fiber leases ahead of schedule as reported in the previous PPR. | 0 | No variance. The budgeted amount for this milestone is $1,049,901. | 0 | NA - using existing staff not charged to project plus contractual resources reported in 2k Other. | 2011-08-15 13:49 | 2011-08-15 13:49 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2011 | Q3 | Q3 - 2011 | 4023 | 3852 | TRUE | 9 | Baseline target is 12%. Previous PPR set a target of 10%. The actual spend is $720,000 less then anticipated. We had planned to complete $500,000 in archeological field surveys during this quarter. The surveys were postponed pending discussions between SHPO and IDOT as described above. In the end, the survey scope was significantly reduced and the work completed by the end of the quarter but not billed. The remaining difference is due to to optical cards placed on hold pending results from fiber characterization tests. | 24 | Professional services such as Project Management, Web Design, Project Engineering | Baseline target is 21%. Previous PPR set a target of 15%. The 24% complete is based upon an actual cumulative spend of $389,088 of the total budgeted $1,634,219. The budgeted amount for this milestone has been decreased from $2,925,971 in order to remove ineligible costs associated with fiber maintenance. | 100 | Baseline target is 100%. Previous PPR set a target of 109%. The 100% complete is based on an actual cumulative spend of $917,858 of the total budgeted $920,322. The budgeted amount has been increased from $918,510. Actual spend was less than anticipated this quarter due to the scope reduction for archeological surveys required by SHPO. | 39 | Baseline target is 55%. Previous PPR set a target of 36%. The 39% complete is based on an actual cumulative spend of $1,429,007 of the total budgeted $3,651,313. The budgeted amount has been reducted from $4,387,444. Estimated costs associated with construction phase A/E activities have been moved to the Network Build milestone. In terms of actual activity, 59% of the network design and 42% of the bidding documents are complete. | 18 | Baseline target is 2%. The previous PPR set a target of 27%. The 18% complete is based upon an actual cumulative spend of $194,588 of the total budgeted $1,076,929. The budgeted amount has been increased from $1,051,729 to address revised cost estimates for A/E rights of way permitting activities. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 4 | Baseline target is 36%. Previous PPR set a target of 6%. The 4% complete is based upon an actual cumulative spend of $144,381 of the total budgeted $3,457,000. The budgeted expenditures address electrical, UPS and generator needs at existing POP sites. CMS has amended the contracts with the host facility (higher education customers) to accommodate these upgrades at leased facilities and are working to place orders for the electrical work. We have executed a master contract for electrical work at state-owned facilities and are working to place orders as well. An engineering analysis is underway for another POP site to determine the overall facility needs. There is no negative impact to the project schedule as these activities do not need to be completed until the fiber is installed. The work will continue in parallel to the fiber construction. | 28 | Baseline target is 26%. Previous PPR set a target of 33%. The 28% complete is based upon an actual cumulative spend of $3,363,817 of the total budgeted $11,875,418. The budgeted amount for this milestone has been increased from $11,275,418. The percent complete shortfall is due to optical cards placed on hold pending results from fiber characterization tests and the overall milestone budget increase. | 3 | Baseline target is 5%. Previous PPR set a target of 3%. The 3% complete is based upon an actual cumulative spend of $2,250,293 of the total budgeted $72,716,925. The budgeted amount for this milestone has been increased from $71,316,055. This increase includes the estimated A/E costs for construction phase activities. Project activities accomplished to date include the fiber leases as well as construction activity to interconnect the leased Level 3 fiber to POP sites along the Collinsville to Springfield network segment. | 0 | No variance. The budgeted amount for this milestone is $1,049,901. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2011-11-14 13:13 | 2011-11-14 13:13 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2011 | Q4 | Q4 - 2011 | 4995 | 4669 | TRUE | 12 | Baseline target is 20%. Previous PPR set a target of 13%. The actual spend is $11,441,431 which is $1M shy of the previous PPR's projections. Invoices for engineering work completed and equipment purchased were received to close to the end of the quarter and were not processed by the cutoff date. Overall, the project is behind the baseline projections due to the unanticipated time needed for the Environmental Assessment. | 28 | Professional Services such as Project Managment, Web Design, Project Engineer | Baseline target is 31%. Previous PPR set a target of 35%. Actual cumulative spend is $462,304 of $1,626,439. The sub recipient experienced delays in hiring staff which put them behind their projections. | 96 | Baseline target is 100%. Previous PPR set a target of 100% and reported 100% had been achieved. This past quarter we reallocated money to this budget item to cover future costs associated with an amendment to the Environmental Assessment for necessary route modifications. The budgeted amount increased from $920,322 to $984,627. Actual cumulative spend is $947,983. | 54 | Baseline target is 70%. Previous PPR set a target of 68%. Activity that aligns with the Network Design milestone includes Detailed Network Design, Bidding Documents, and Bidding Phase work. In terms of actual activity, 100% of the Detailed Network Design, 87% of the Bidding Documents, and 41% of the Bidding Phase are complete as of December 31, 2011. | 25 | Baseline target is 100%. Previous PPR set a target of 24%. Actual cumulative spend is $270,787 of the total budgeted $1,076,929. The Environmental Assessment put CMS behind in applying for permits. Permits are also taking longer then originally anticipated. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 8 | Baseline target is 36%. Previous PPR set a target of 7%. Actual cumulative spend is $276,588 of $3,457,000. Nearly half of this milestone category is for an in kind contribution of space for network equipment within the sub recipient's portion of the project. CMS originally anticipated that the sub recipient would have secured the space at this point in the project; however, the sub is forecasting this activity for later this calendar year. | 44 | Baseline target is 26%. Previous PPR set a target of 45%. Actual cumulative spend is $5,267,616 of $11,911,943. An invoice for equipment was received to close to the end of the quarter and was not processed by the cutoff date. | 3 | Baseline target is 13%. Previous PPR set a target of 4%. Actual cumulative spend is $2,250,293 of $72,603,876. While construction activities started in November, the invoice was received to close to the end of the quarter and was not processed by the cutoff date. | 0 | Baseline target is 30%. Previous PPR set a target of 5%. CMS originally anticipated utilizing contractual services for equipment deployment. So far, we are primarily using in-house staff that are not billed to the project. We do anticipate using a limited amount of contractual services in the next quarter. The savings will be re-budgeted to another milestone category. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2012-02-14 11:33 | 2012-02-14 11:33 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2012 | Q1 | Q1 - 2012 | 6009 | 5604 | TRUE | 20 | Baseline target is 42%. Previous PPR set a target of 19%. The actual spend is $19,103,284. While the project is behind the baseline due to unanticipated delays with the Environmental Assessment and establishing construction contracts, the project is on schedule to be fully completed by the end of year three. In the revised project schedule provided to NTIA, CMS set a target for this quarter of 18%. | 38 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 40%. In the revised project schedule provided to NTIA, CMS set a target of 36%. CMS anticipated a cumulative spend of $585,921. Actual spend was $607,363. Most of the costs associated with this milestone are based on the number of hours non full-time contractual staff spend working on the project. The difference in projected versus actual is due to difficulties anticipating the exact number of hours that will be worked in a quarter. | 96 | Baseline target is 100%. In the revised project schedule provided to NTIA, CMS set a target of 99%. The EA is complete and a FONSI received. CMS has reserved an additional $22,500 for EA work associated with pending route changes which resulted in a lower percent complete. The targeted spend was $948,532 and actual spend was $962,482. | 74 | Baseline target is 100%. In the revised project schedule provided to NTIA, CMS set a target of 80%. The network design for the outside plant is complete. The sub recipient is working with its vendor on completion of the tower network design and inside plant design. The targeted spend was $3,898,019 and actual spend was $3,633,690. CMS forecasted spending an additional $400,000 for network design associated with route changes. While some initial design work needed for AAR and EA approvals is proceeding, final design work is pending NTIA approval of the requested changes. | 54 | Baseline target is 100%. In the revised project schedule provided to NTIA, CMS set a target of 38%. The targeted spend was $413,766 and actual spend was $579,480. The difference is a result of better then anticipated progress made on securing permits this quarter. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 8 | Baseline target is 61%. In the revised project schedule provided to NTIA, CMS set a target of 8%. | 58 | Baseline target is 46%. In the revised project schedule provided to NTIA, CMS set a target of 69%. CMS anticipated a cumulative spend of $8,173,809. Actual spend was $6,936,014. An additional $987,489 of equipment was received during the quarter; however, the invoice was not paid until a few days past the end of the quarter. | 8 | Baseline target is 35%. In the revised project schedule provided to NTIA, CMS set a target of 5%. The targeted spend was $3,360,530 and actual spend was $6,044,369. Construction activities where ahead of schedule. | 5 | Baseline target is 40%. In the revised project schedule provided to NTIA, CMS set a target of 7%. The targeted spend was $51,864 and actual spend was $31,527. An additional $27,116 in work was performed but the invoice was not processed by the end of the quarter. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2012-05-10 12:49 | 2012-05-10 12:49 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2012 | Q2 | Q2 - 2012 | 7133 | 6194 | TRUE | 32 | Baseline target is 68%. Previous PPR set a target of 32%. The revised project schedule provided to NTIA set a target of 33%. The actual spend is $30,672,180. The difference between the revised projection and actual spend is $874,865 or 1% and explained below. | 44 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 46%. Previous PPR set a target of 49%. The revised project schedule provided to NTIA set a target of 49%. CMS engineering staff completed a training class this quarter; however, the invoice will not be paid until next quarter. The public relations contractual resource working for the sub recipient rolled off earlier then anticipated. The sub recipient plans to reassign these duties to existing resources which will result in overall lower spend for this milestone. | 98 | Baseline target is 100%. Previous PPR set a target of 98%. The revised project schedule provided to NTIA set a target of 99%. The EA is complete and a FONSI received. The remaining funds may be used for EA work associated with pending and future route change requests. | 76 | Baseline target is 100%. Previous PPR set a target of 77%. The revised project schedule provided to NTIA set a target of 98%. All design work for the fiber routes is complete and paid. The sub recipient anticipates completing the design work for wireless towers and inside plant at the end of next quarter, although some of the payments may lag into the following quarter. Any additional spend for this category will be associated with routes changes. Overall we expect to come in under budget. | 55 | Baseline target is 100%. Previous PPR set a target of 54%. The revised project schedule provided to NTIA set a target of 88%. The revised project schedule forecasted spend of $200,000 (20% of the milestone budget) for A/E on site observations which should have been mapped to the Network Build milestone. CMS has secured 90% of the permits. Overall costs are much lower then budgeted. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 15 | Baseline target is 61%. Previous PPR set a target of of 8%. The revised project schedule provided to NTIA set a target of 8%. The sub recipient (Illinois State University) is ahead of schedule on securing leased space for network equipment. | 68 | Baseline target is 46%. Previous PPR set a target of 68%. The revised project schedule provided to NTIA set a target of 71%. CMS has purchased and installed about 80% of the optical, switching and routing equipment. We had planned to purchase the remaining 3 optical switches in this quarter but are holding off while we evaluate the feasibility of upgrading the equipment from 40G to 100G. Overall, equipment costs are less then budgeted. The sub recipient anticipates awarding bids for generators, wireless equipment, servers, racks and fiber panels next quarter. | 22 | Baseline target is 70%. Previous PPR set a target of 23%. The revised project schedule provided to NTIA set a target of 22%. Network builds for this quarter aligned with the revised project schedule. | 5 | Baseline target is 60%. Previous PPR set a target of 7%. The revised project schedule provided to NTIA set a target of 7%. Fiber characterization work by the optical equipment vendor is on hold until CMS takes receipt of a 3 mile fiber segment which will complete a backbone route. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2012-08-17 17:46 | 2012-08-17 17:46 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2012 | Q3 | Q3 - 2012 | 7929 | 6669 | TRUE | 41 | Baseline target is 72%. Previous PPR set a target of 47%. T$3.9M in payments to vendors occurred on October 1 just missing the quarter targets. | 57 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 52%. Previous PPR set a target of 58%. The public relations contractual resource working for the sub recipient rolled off earlier then anticipated. The sub recipient plans to reassign these duties to existing resources which will result in overall lower spend for this milestone. | 100 | Baseline target is 100%. Previous PPR set a target of 98%. The EA is complete and a FONSI received. CMS will have some additional spend for EA work associated with the pending route change, if approved. | 78 | Baseline target is 100%. Previous PPR set a target of 81%. All design work for the fiber routes is complete and paid. The sub recipient has completed the design work for wireless towers and inside plant but has not yet received all the invoices. Any additional spend for this category will be associated with routes changes. | 77 | Baseline target is 100%. Previous PPR set a target of 83%. CMS has secured 95% of the permits. Permit preparation is complete for the original project scope. Additional charges will be associated with permit fees to the remaining 17 railroad permits and permit preparation/fees for the aproved and pending route changes. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 22 | Baseline target is 61%. Previous PPR set a target of of 20%. Inside plant work is behind schedule. The time required to finalize the scope of work, secure vendor quotes, place orders, receive materials and complete the work is taking longer then anticipated. Inside plant work has started and will continue through the remainder of the project. | 68 | Baseline target is 46%. Previous PPR set a target of 71%. CMS has purchased and installed about 80% of the optical, switching and routing equipment. We had planned to purchase the remaining 3 optical switches in this quarter but are holding off while we evaluate the feasibility of upgrading the equipment from 40G to 100G. Overall, equipment costs are less then budgeted. | 34 | Baseline target is 75%. Previous PPR set a target of 40%. $3.9M in construction invoices were paid October 1 just missing the quarterly cut off date. Considering these invoices, spend for network build is at 40%. The difference between actual and the revised project schedule is due to late starts and costs for the early construction routes coming in below budget. 76% of the conduit and 30% of the fiber is complete. | 6 | Baseline target is 75%. Previous PPR set a target of 5%. $600,00 of $699,000 budgeted for this milestone is for fiber characterization work by the optical equipment vendor. The work has been on hold until CMS takes receipt of a 3 mile leased fiber segment which will complete a backbone route. In the meantime, CMS is in process of purchasing the tools to perform this work internally. Depending on timing, CMS may not require the services of the optical equipment vendor. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2012-11-16 15:39 | 2012-11-16 15:39 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2012 | Q4 | Q4 - 2012 | 9055 | 7831 | TRUE | 59 | Baseline target is 81%. Previous PPR set a target of 64%. $1.2M in payments to vendors occurred after December 31st. | 72 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 62%. Previous PPR set a target of 69%. The public relations contractual resource working for the sub recipient rolled off earlier then anticipated. The sub recipient plans to reassign these duties to existing resources which will result in overall lower spend for this milestone. We expect to exceed the budgeted in kind match for project staff salaries which will make up for the lower network node space contribution. The project is completing a third party assessment of the space valuation and will work with NTIA to update the budget once complete. | 100 | Baseline target is 100%. Previous PPR set a target of 100%. The EA is complete and a FONSI received. CMS will have some additional spend for EA work associated with the pending route change, if approved. | 88 | Baseline target is 100%. Previous PPR set a target of 81%. All design work for the fiber routes is complete and paid. The sub recipient has completed the design work for wireless towers and inside plant but has not yet received all the invoices. Any additional spend for this category will be associated with routes changes. | 83 | Baseline target is 100%. Previous PPR set a target of 100%. CMS has secured 99% of the permits. Additional charges will be associated with permit preparation/fees for the pending route changes. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 39 | Baseline target is 80%. Previous PPR set a target of of 44%. Inside plant work started later than originally forecasted but is underway and making good progress. Fifty percent of the money budgeted to this milestone category is for an in kind match of network node space contributed by CAI participants. The space value will be reduced due to the timing the space was put into service. The project will make up the difference for the in kind contribution within the Other milestone category. The sub recipient is completing a third party assessment of the space valuation and we will work with NTIA to update the budget once complete. | 74 | Baseline target is 46%. Previous PPR set a target of 71%. CMS has purchased and installed 80% of the optical, switching and routing equipment. | 55 | Baseline target is 85%. Previous PPR set a target of 62%. $1.2M in construction invoices were paid after December 31st missing the quarterly cut off date. The difference between actual and the baseline project schedule is due to late starts and costs for the early construction routes coming in below budget. 93% of the conduit and 50% of the fiber is complete. | 7 | Baseline target is 90%. Previous PPR set a target of 6%. $600,00 of $699,000 budgeted for this milestone is for fiber characterization work by the optical equipment vendor. CMS is in process of purchasing the tools to perform this work internally. CMS anticipates that the remaining money budgeted for Equipment Deployment will be reallocated to other expenses. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2013-02-28 11:04 | 2013-02-28 11:04 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2013 | Q1 | Q1 - 2013 | 10007 | 8548 | TRUE | 69 | Baseline target is 96%. Previous PPR set a target of 72%. | 54 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 81%. Last quarter the PPR reported 72% which was based on the revised forecasted spend for this category. CMS is now accurately reporting milestone completions by calculating them against the most recent approved budget. The approved budgeted amount includes ineligible expenses associated with fiber maintenance costs. Final spend will be less than the approved budgeted amount. | 100 | Actual spend is 120% due to higher engineering costs required to complete EA. | 89 | Baseline target is 100% All design work for the original scope fiber routes is complete and paid. Additional charges will be associated with recently approved route changes. Final spend will be less than originally budgeted. | 100 | Actual spend is 106% due to higher engineering costs required to prepare permits. CMS has secured 99% of the permits. Additional charges will be associated with permit preparation/fees for recently approved route changes. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 44 | Baseline target is 100%. Fifty percent of the money budgeted to this milestone category is for an in kind match of network node space contributed by CAI participants. The space value will be reduced due to the timing the space was put into service. The project will make up the difference for the in kind contribution within the Other milestone category. | 84 | Baseline target is 100%. CMS will have additional spend for customer premise equipment associated with recently approved route changes; however, we anticipate final costs will be less than budgeted. | 67 | Baseline target is 95%. The difference between actual and the baseline project schedule is due to late starts and costs for the early construction routes coming in below budget. 100% of the conduit and 86% of the fiber is complete. | 3 | Baseline target is 100%. CMS is using in house staff to deploy equipment and does not anticipate any additional spend in this category. The money is being reallocated to other expenses. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2013-05-30 13:24 | 2013-05-30 13:24 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2013 | Q2 | Q2 - 2013 | 10821 | 9083 | TRUE | 80 | Baseline target is 100%. Previous PPR set a target of 80%. | 73 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 100%. The original budget included ineligible expenses associated with fiber maintenance costs. CMS has submitted a revised project budget. Based on the revised budget, the project has spent 87% of the funds allocated to Other. | 100 | Actual spend is 123% due to higher engineering costs required to complete EA. | 100 | All design work for the original scope fiber routes is complete and paid. Additional charges will be associated with recently approved and pending route changes. | 100 | Actual spend is 122% due to higher engineering costs required to prepare permits. CMS has secured 99% of the permits. Additional charges will be associated with permit preparation/fees for recently approved and pending route changes. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 59 | Baseline target is 100%. Fifty percent of the money budgeted to this milestone category is for an in kind match of network node space contributed by CAI participants. The space value will be reduced due to the timing the space was put into service. The project will make up the difference for the in kind contribution within the Other milestone category. CMS has submitted a revised project budget. Based on the revised budget, the project has spent 85% of the funds allocated to Site Preparation. | 93 | Baseline target is 100%. CMS will have additional spend for customer premise equipment associated with recently approved route changes. | 78 | Baseline target is 100%. The difference between actual and the baseline project schedule is due to late starts and costs for the early construction routes coming in below budget. 99% of the fiber was complete at the end of the quarter. | 3 | Baseline target is 100%. CMS is using in house staff to deploy equipment and does not anticipate any additional spend in this category. CMS has submitted a revised project budget which reallocates the money to other milestones. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2013-08-30 14:13 | 2013-08-30 14:13 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2013 | Q3 | Q3 - 2013 | 11389 | 9503 | TRUE | 86 | Baseline target is 100%. Previous PPR set a target of 95%. 99% of the network is complete; however, CMS is working with the construction vendors on close out paperwork (e.g. lien waivers, stored materials logs, etc.) before issuing final payments and releasing the hold back funds. | 80 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 100%. The original budget included ineligible expenses associated with fiber maintenance costs. Final spend will be less than original budgeted. The remaining funds will be spent in the other milestone categories where expenses have been higher than originally budgeted. | 100 | Actual spend is 123% due to higher engineering costs required to complete EA. | 100 | Actual spend is 101%. All design work for the original scope fiber routes is complete and paid. CMS anticipates some additional charges associated with work recently completed on the expansion routes. | 100 | Actual spend is 129% due to higher engineering costs required to prepare permits. CMS does not anticipate any additional spend in this milestone. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 50 | Baseline target is 100%. Fifty percent of the money budgeted to this milestone category is for an in kind match of network node space contributed by CAI participants. The space value will be reduced due to the timing the space was put into service. The project will make up the difference for the in kind contribution within the Other milestone category. CMS working on a revised project budget. Based on the revised budget, the project has spent 85% of the funds allocated to Site Preparation. Note that the cumulative spend percentage is less than reported in the previous PPR. ISU originally calculated the site valuation match amount based on the date when agreements for space were fully executed. ISU started reporting this amount on the 6/14/12 invoice and the Y2Q4 PPR submitted on 7/12/12. Subsequent to submission of those documents, in emails between NOAA and ISU on 4/10/13 it was determined that the date ISU actually occupied the space should be the date upon which site valuation shoul | 100 | Actual spend is 101%. Baseline target is 100%. CMS will have additional spend for customer premise equipment associated with the approved expansion sites and the approved 100 Gbps optical equipment. | 85 | Baseline target is 100%. 99% of the network is complete; however, CMS is working with the construction vendors on close out paperwork (e.g. lien waivers, stored materials logs, etc.) before issuing the final payment and releasing the retainage. | 3 | Baseline target is 100%. CMS is using in house staff to deploy equipment and will not have any additional spend in this category. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2013-11-26 13:16 | 2013-11-26 13:16 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2013 | Q4 | Q4 - 2013 | 12467 | 10647 | TRUE | 100 | All work is complete and paid. Final costs came in slightly below budget. | 100 | Professional Services such as Project Management, Web Design, Project Engineer | All work is complete. | 100 | All work is complete and paid. The difference represents final costs coming in below budget. | 100 | All design work is complete and paid. | 100 | All right of way work is complete and paid. The difference represents final costs coming in below budget. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 100 | All work is complete. | 100 | All work is complete. | 100 | All work is complete. The difference represents final costs coming in below budget. | 100 | All work is complete and paid. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2014-08-28 17:24 | 2014-08-28 17:24 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570109 | 2010 | Q4 | Q4 - 2010 | 983 | 2027 | TRUE | 1 | N/A |  | N/A | N/A | 50 | N/A | 25 | N/A | 50 | N/A | 25 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-04 17:15 | 2011-02-04 17:15 | 6173 | 6173 | Carver, County of | TRUE
NT10BIX5570109 | 2011 | Q1 | Q1 - 2011 | 1957 | 2724 | TRUE | 0 | Our overall project expenditures for this quarter were less than 1%, which is less than our originally budgeted 3%. This lower amount of expenditure was created by the need to complete an ethnographic report, which has not allowed for our EA to finalized. Once our EA is complete, the EA work expense from our EA vendor will be final billed and thus, expensed in that quarter. Also, due to the EA not being completed, the additional expenditures for engineering dollars were not yet realized, but with the completion of the EA, they will be realized in that quarter. | 0 | N/A | N/A | 75 | With the additional tribal consultations added in February, which included the requirement for an ethnographic report of the area of potential effect, we have not submitted our 2nd draft EA for review. The extra time needed to complete the EA will be made up during the construction phase of our project, by working with our vendor to employ multiple crews to complete the project within budget and schedule. | 50 | N/A | 90 | All rights of way have been established for the project route but with the open tribal consultations the County does not consider rights of way complete until we have a FONSI. | 50 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-05-12 07:57 | 2011-05-12 07:57 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2011 | Q2 | Q2 - 2011 | 3381 | 3454 | TRUE | 1 | Our overall project expenditures for this quarter are at .2%, which is less than our originally budgeted 8%. This lower expenditure was created by two factors, the first being the wait time in receiving our EA approval, which we received at the end of this quarter. The second being the availability of fiber, which affected our construction bid award process, which we also finalized at the end of this quarter. With our EA approved, EA pre-engineering expenses are being billed and will be realized next quarter. Also, with our EA approved, we are able to submit orders for fiber and conduit, which will begin shipping and billing in the next quarter. With conduit shipping early next quarter we look to deploy the resources needed to regain our project timeline. | 0 |  | N/A | 100 | No variance from baseline | 50 | Our network design is at 50%, which is less than our originally stated 100%. This lower percentage was created by the wait time in receiving our EA approval. Now that our EA has been approved, we will be completing site visits at all community anchor institutions (CAI's) to define any specific network design needs that would allow the best and most appropriate use the new fiber infrastructure. | 99 | Our rights of way is at 99%, which is less than our originally stated 100%. This lower percentage was created due to four small route modifications that we are pursuing that will properly place the fiber route in the proper right of way and appropriate utility easements. These four modifications have been submitted as EA addendums and we are awaiting final sign off. | 75 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 0 | Our network build is at 0%, which is less than our originally stated 4%. This lower expenditure was created by two factors, the first being the wait time in receiving our EA approval, which we received at the end of this quarter. The second being the availability of fiber, which affected our construction bid award process, which we also finalized at the end of this quarter. With our EA approved and orders for fiber and conduit placed and conduit shipping next quarter, we look to deploy the resources needed to regain our project timeline. | 0 | No variance from baseline | 0 | No variance from baseline | 2011-08-30 15:07 | 2011-08-30 15:07 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2011 | Q3 | Q3 - 2011 | 3911 | 3794 | TRUE | 19 | Our overall project expenditures for this quarter are 19%, which is less than our originally budgeted 37%. This lower expenditure was created by two factors, the first being that we are now accounting for the project on a cash basis, so there is an approximate $550,000 construction invoice for September that will be accounted for in the next quarter. Second, with the delay in our fiber shipments, we will not expend the funds until next quarter for this approximately $750,000 expense. Combined these amounts if added to this quarters expenditures, would have put us at approxmiately 36%. | 0 |  | N/A | 100 | No variance from baseline | 50 | Our network design is at 50%, which is less than our originally stated 100%. This lower percentage was created by conversations with our community anchor institutions (CAI's) and other interested parties. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. This change has allowed us time to discuss additional connections that CAI's and other interested parties are requesting outside of the original project scope and budget. Based on these discussions we are holding our network design finalization until the spring of 2012, which is when we will be able to begin construction again after the winter. At that time we will finalize our network design to best accommodate any additional outside the original project scope connections in which CAI's would pay for out of their own non ARRA funds. | 100 | No variance from baseline | 75 | Our construction permits and other approvals is at 75%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Many of the required permits for these locations have limited timeframes in which the defined work is able to be completed. So instead, we will be obtaining the remainder of the permits in the spring and summer of 2012 as we are closer to the time in which we will actually be constructing to those locations. | 0 | Our site preparation is at 0%, which is less than our originally stated 25%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the site preparation for our huts will not be needed until the spring/summer of 2012. As such, we will not be doing any site preparation until that time so that we can accommodate any increase in hut size that may be needed from potential out of scope project expansion discussions that may take place over the winter months. | 0 | No variance from baseline | 0 | Our network build is at 0%, which is less than our originally stated 41%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, we will not be completing final network build until the end of the project, at which time we would promptly be at 100%. | 0 | No variance from baseline | 0 | No variance from baseline | 2011-11-07 16:10 | 2011-11-07 16:10 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2011 | Q4 | Q4 - 2011 | 4979 | 4654 | TRUE | 39 | Our overall project expenditures for this quarter are 39%, which is less than our originally budgeted 60%. This lower expenditure was caused by the delay in shipments of our remaining fiber, which is now scheduled to be delivered from January through April of 2012, at which time the costs will be realized. Also, we are running our construction costs on a cash basis versus accrual basis, so there will be approximately $500,000 reported in the first quarter of 2012 that is for work completed in December of 2011. | 0 |  | N/A | 100 | No variance from baseline | 50 | Our network design is at 50%, which is less than our originally stated 100%. This lower percentage was created by conversations with our community anchor institutions (CAI's) and other interested parties. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. This change has allowed us time to discuss additional connections that CAI's and other interested parties are requesting outside of the original project scope and budget. Based on these discussions we are holding our network design finalization until the spring of 2012, which is when we will be able to begin construction again after the winter. At that time we will finalize our network design to best accommodate any additional outside the original project scope connections in which CAI's would pay for out of their own non ARRA funds. | 100 | No variance from baseline | 75 | Our construction permits and other approvals is at 75%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Many of the required permits for these locations have limited timeframes in which the defined work is able to be completed. Due to this factor, we will be obtaining the remainder of the permits in the spring and summer of 2012 as we are closer to the time in which we will actually be constructing to those locations. | 0 | Our site preparation is at 0%, which is less than our originally stated 50%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the site preparation for our huts will not be needed until the spring/summer of 2012. As such, we will not be doing any site preparation until that time so that we can accommodate any increase in hut size that may be needed from potential out of scope project expansion discussions that may take place over the winter months. | 0 | Our equipment procurement is at 0%, which is less than our originally stated 20%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Due to this factor, we will be working on equipment procurement in subsequent quarters, which will allow us to purchase at the most competitive prices for the most currently appropriate equipment. | 0 | Our network build is at 0%, which is less than our originally stated 60%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, we will not be completing final network build until the end of the project, at which time we would promptly be at 100%. | 0 | Our equipment deployment is at 0%, which is less than our originally stated 20%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Due to this factor, we will be working on equipment deployment in subsequent quarters, so that we can deploy the most currently appropriate equipment. | 0 | No variance from baseline | 2012-02-13 15:12 | 2012-02-13 15:12 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2012 | Q1 | Q1 - 2012 | 6265 | 5735 | TRUE | 60 | Our overall project expenditures for this quarter are 60%, which is less than our originally budgeted 63%. This lower expenditure was caused by delays in shipments of our remaining fiber, with the remaining amounts not arriving until the very end of this quarter. Based on the delivery delays we have not been installing fiber at lateral locations, thus our construction costs have not been as significant, which will be made up in the next quarter now that all fiber has arrived. | 0 |  | N/A | 100 | No variance from baseline | 50 | Our network design is at 50%, which is less than our originally stated 100%. This lower percentage was created by conversations with our community anchor institutions (CAI's) and other interested parties. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. This change has allowed us time to discuss additional connections that CAI's and other interested parties are requesting outside of the original project scope and budget. Based on these discussions we are holding our network design finalization until the spring of 2012, which is when we will be able to begin construction again after the winter. At that time we will finalize our network design to best accommodate any additional outside the original project scope connections in which CAI's would pay for out of their own non ARRA funds. | 100 | No variance from baseline | 75 | Our construction permits and other approvals is at 75%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Many of the required permits for these locations have limited timeframes in which the defined work is able to be completed. Due to this factor, we will be obtaining the remainder of the permits in the spring and summer of 2012 as we are closer to the time in which we will actually be constructing to those locations. | 0 | Our site preparation is at 0%, which is less than our originally stated 75%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the site preparation for our huts will not be needed until the spring/summer of 2012. As such, we will not be doing any site preparation until that time so that we can accommodate any increase in hut size that may be needed from potential out of scope project expansion discussions that may take place over the winter months. | 0 | Our equipment procurement is at 0%, which is less than our originally stated 40%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Due to this factor, we will be working on equipment procurement in subsequent quarters, which will allow us to purchase at the most competitive prices for the most currently appropriate equipment. | 0 | Our network build is at 0%, which is less than our originally stated 60%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, we will not be completing considerable network build until the end of our fiber and conduit installation construction. | 0 | Our equipment deployment is at 0%, which is less than our originally stated 40%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Due to this factor, we will be working on equipment deployment in subsequent quarters, so that we can deploy the most currently appropriate equipment. | 0 | No variance from baseline | 2012-05-23 13:51 | 2012-05-23 13:51 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2012 | Q2 | Q2 - 2012 | 7269 | 6262 | TRUE | 71 | Our overall project expenditures for this quarter are 71%, which is less than our originally budgeted 74%. This lower expenditure was caused by the splicing design work we are completing to best configure this new fiber infrastructure to accommodate our anchor entities needs. This work has pushed our equipment expenditure to the 3rd quarter of 2012, which was originally anticipated for this quarter. | 0 |  | N/A | 100 | No variance from baseline | 75 | Our network design is at 75%, which is less than our originally stated 100%. This lower percentage was created by conversations with our community anchor institutions (CAI's) and other interested parties on how to best configure the new fiber infrastructure. Based on these discussions we continue to systematically work on our network design which will be completed in 3rd quarter of 2012. | 100 | No variance from baseline | 95 | Our construction permits and other approvals are at 95%, which is less than our originally stated 100%. This lower percentage was created by conversations with our community anchor institutions (CAI's) and other interested parties on how to best configure the new fiber infrastructure, thus delaying us requesting some specific permits for these respective areas. We look to complete the remaining 5% in 3rd quarter of 2012. | 0 | Our site preparation is at 0%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We are installing fiber to our lateral locations in the late summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the site preparation for our huts will not be needed until the late summer of 2012. As such, we will not be doing any site preparation until that time. Our budget line item for this category is specific to the construction of the three fiber huts that are part of our project, which are slated for construction next quarter. | 0 | Our equipment procurement is at 0%, which is less than our originally stated 60%. This lower percentage was created by conversations with our community anchor institutions (CAI's) and other interested parties on how to best configure the new fiber infrastructure. Based on these discussions we have not begun our process to procure equipment,which we will be completing in 3rd quarter of 2012. | 68 | No variance from baseline | 0 | Our equipment deployment is at 0%, which is less than our originally stated 60%. This lower percentage was created by conversations with our community anchor institutions (CAI's) and other interested parties on how to best configure the new fiber infrastructure. Based on these discussions we have not begun our process to deploy equipment,which we will be working on in 3rd quarter of 2012. | 0 | No variance from baseline | 2012-08-28 17:17 | 2012-08-28 17:17 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2012 | Q3 | Q3 - 2012 | 8011 | 6712 | TRUE | 82 | Our overall project expenditures for this quarter are 82%, which is less than our originally budgeted 90%. This lower expenditure was based on the project not yet expending funds for our equipment, which we will begin acquire in the next quarter and secondly because of not yet paying out a construction retainage fee to our construction contractor as we have not yet finalized our construction. | 0 |  | N/A | 100 | No variance from baseline | 80 | Our network design is at 80%, which is less than our originally stated 100%. This lower percentage was created based on our implementation of a design build approach to our network and equipment planning bid, which will be completed in the next quarter. | 100 | No variance from baseline | 99 | Our construction permits and other approvals are at 99%, which is less than our originally stated 100%. This lower percentage is based on having two remaining railroad permits which will have completed in the first month of the next quarter. | 55 | Our site preparation is at 55%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. Based on this change we did not start to build the three required fiber huts for our project until late this quarter. The remaining is ongoing and will be completed the first part of next quarter. | 0 | Our equipment procurement is at 0%, which is less than our originally stated 80%. This lower percentage was created based on our implementation of a design build approach to our network and equipment planning bid, which will be completed in the next quarter. | 84 | No variance from baseline | 0 | Our equipment procurement is at 0%, which is less than our originally stated 80%. This lower percentage was created based on our implementation of a design build approach to our network and equipment planning bid, which will be completed in the next quarter. | 0 | No variance from baseline | 2012-11-21 10:52 | 2012-11-21 10:52 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2012 | Q4 | Q4 - 2012 | 9081 | 7855 | TRUE | 83 | Our overall project expenditures for this quarter are 83%, which is less than our originally budgeted 99%. This lower expenditure was based on the project not yet expending funds for our equipment, which we will begin paying for in the next quarter. Secondly, we have not yet paid out our construction retainage fee to our construction contractor as they have not yet finalized our all construction requirements. | 0 |  | N/A | 100 | No variance from baseline | 90 | Our network design is at 90%, which is less than our originally stated 100%. This lower percentage was created based on our implementation of a design build approach to our network and equipment planning bid for our equipment RFP that was issued late this quarter. | 100 | No variance from baseline | 100 | No variance from baseline | 55 | Our site preparation is at 55%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We continued construction of the three required fiber huts for during this quarter, with an anticipated completion next quarter. Expenditures will not be paid out until huts are fully completed and fiber splicing and terminations are tested. | 0 | Our equipment procurement is at 0%, which is less than our originally stated 100%. This lower percentage was created based on our implementation of a design build approach to our network and equipment planning bid. The equipment RFP was issued during this quarter and expenditures will be realized in the next quarter as equipment is delivered and installed. | 94 | No variance from baseline | 0 | Our equipment procurement is at 0%, which is less than our originally stated 100%. This lower percentage was created based on our implementation of a design build approach to our network and equipment planning bid. The equipment RFP was issued during this quarter and expenditures will be realized in the next quarter as equipment is delivered and installed. | 0 | No variance from baseline | 2013-02-28 14:29 | 2013-02-28 14:29 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2013 | Q1 | Q1 - 2013 | 9297 | 8102 | TRUE | 89 | Our overall project expenditures for this quarter are 89%, which is less than our originally budgeted 99%. This lower expenditure was based on the project not yet expending funds for our equipment, which will finish deployment in the next quarter. Secondly, we have not yet paid out our construction retainage fee to our construction contractor as they have not yet completed all construction requirements. | 0 |  | N/A | 100 | No variance from baseline | 95 | Our network design is at 95%, which is less than our originally stated 100%. This lower percentage was created based on our implementation of a design build approach to our network deployment. | 100 | No variance from baseline | 100 | No variance from baseline | 75 | Our site preparation is at 75%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We continued construction of the three required fiber huts during this quarter, with an anticipated completion next quarter. Expenditures will not be paid out until huts are fully completed and fiber splicing and terminations are tested. | 6 | Our equipment procurement is at 6%, which is less than our originally stated 100%. This lower percentage was created based on our implementation of a design build approach to our network and equipment planning. All remaining equipment will be deployed next quarter so remaining expenditures will be made at that time. | 100 | No variance from baseline | 50 | Our equipment deployment is at 50%, which is less than our originally stated 100%. This lower percentage was created based on our implementation of a design build approach to our network and equipment planning. We actively deployed equipment this quarter and the remainder will be deployed next quarter. | 50 | No variance from baseline | 2013-04-26 16:28 | 2013-04-26 16:28 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2013 | Q2 | Q2 - 2013 | 10751 | 9041 | TRUE | 92 | Our overall project expenditures for this quarter are 92%, which is less than our originally budgeted 100%. This lower expenditure was based on not yet expending funds for our equipment, which will be expended prior to our required project completion timeline. Secondly, we have not yet paid out our construction retainage fee to our construction contractor as they have not yet completed all construction contract requirements but will also be paid out prior to our required project completion timeline. | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 95 | Our site preparation is at 95%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We neared final completion of the three required fiber huts in our project, which will be completed prior to our required project completion timeline. Expenditures will not be paid out until huts are fully completed and fiber splicing and terminations are tested. | 95 | Our equipment procurement is at 95%, which is less than our originally stated 100%. This lower percentage was created based on our implementation of a design build approach to our network and equipment planning. All remaining equipment will be purchased and paid for prior to our required project completion timeline. | 100 | No variance from baseline | 95 | Our equipment deployment is at 95%, which is less than our originally stated 100%. This lower percentage was created based on our implementation of a design build approach to our network and equipment planning. We actively deployed equipment this quarter and will be finishing up the final equipment deployments prior to our required project completion timeline. | 100 | No variance from baseline | 2013-08-27 09:46 | 2013-08-27 09:46 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2013 | Q3 | Q3 - 2013 | 11601 | 9729 | TRUE | 100 | No variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2014-01-14 10:43 | 2014-01-14 10:43 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570111 | 2010 | Q4 | Q4 - 2010 | 757 | 1792 | TRUE | 1 | Although our Baseline Milestone shows nothing completed based on expenditures towards the project, since we have made progress in other aspects, we believe the project is moving forward and would estimate as 1% complete. | 0 | N/A | N/A | 40 | We began working on this once notified of our award to expedite the process and estimate to be beyond our baseline in this category. | 10 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-01-28 14:07 | 2011-01-28 14:07 | 5529 | 5529 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2011 | Q1 | Q1 - 2011 | 1999 | 2745 | TRUE | 2 | Although expenditures for the project do not reflect the "percent complete" number indicated, significant progress has been made and work is in progress towards meeting the milestones currently lagging the Baseline. | 0 | N/A | N/A | 90 | The Environmental Assessment has been submitted awaiting receipt of Finding of No Significant Impact(FONSI). | 35 | No variance. | 0 | Rights of Way acquisition has not started as was originally called out in our Baseline. Delays in initial acceptance of the award has extended the start of this work. The Project will meet the NTIA metric of two thirds complete by end of year two through aggressive project management. | 0 | Permitting has not yet started, contrary to what was indicated in our Baseline Report. Additional resources have been planned in order to expedite the process once Finding of No Significant Impact (FONSI) is received. The project is anticipated to meet the Baseline projections by end of year two of the timeline. | 0 | Site preparation is pending the receipt of Finding of No Significant Impact (FONSI) and is expected to begin following it's receipt. As FONSI has not yet been received, the project is expected to commence in Q3, with site work caught up with Baseline by end of year two of the project timeline. | 0 | Equipment procurement has not yet been initiated for the project. However, specifications and details surrounding vendor selection are being addressed. Equipment originally planned for purchase in the six month budget was not purchased. Equipment procurement is not expected to start until after FONSI is received. This metric will be met during year two of the project. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 2011-05-13 09:27 | 2011-05-13 09:27 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2011 | Q2 | Q2 - 2011 | 2585 | 3041 | TRUE | 3 | No variance. | 0 | NA | NA | 95 | Work continues on the Environmental process to work towards receipt of Finding of No Significant Impact by end of Quarter 3, 2011. | 45 | No variance. | 15 | Rights of Way acquisition has been initiated with preliminary work taking place. Delays in initial acceptance of the award has extended this portion of the projected progress milestone. The Project will meet the NTIA metric of two thirds complete by end of year two through aggressive project management and bringing in additional resources as may be required. | 20 | Some preliminary work has been initiated in the permitting process and will continue in an aggressive manner to expedite this metric as we work to achieve Finding of No Significant Impact (FONSI). | 10 | Site preparation is lagging Baseline projections while we await Finding of No Significant Impact. Once approval is received and ground disturbing activities are allowed, additional resources will be allocated to staking and Site Preparation. | 20 | Equipment procurement is substantially complete with final design being iterated with the vendor. Equipment purchases originally planned during the initial six months of the project are being allocated to purchases later in the project. Anticipation of meeting the Baseline projections for this metric will be by the end of year two of the project timeline. | 0 | No variance. | 0 | The Baseline projection assumed In Kind Assets would have been approved during this quarter of the project and those assets have yet to receive approval for deployment to the project. | 0 | No variance. | 2011-07-28 11:02 | 2011-07-28 11:02 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2011 | Q3 | Q3 - 2011 | 4219 | 3958 | TRUE | 20 | Currently exceeding Baseline. | 0 |  | N/A | 96 | Finding of No Significant Impact (FONSI) is imminent as we await final approval of the Environmental Assessment (EA). Approval is anticipated in quarter four of 2011. | 60 | No Variance. | 25 | An aggressive Baseline projection along with the longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources will be utilized to bring this metric in line with projections during the final year of the project. | 30 | An aggressive Baseline projection along with the longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources will be utilized to bring this metric in line with projections during the final year of the project. | 15 | See narrative above. Anticipation is to bring this metric in line with the Baseline projections in quarter four of the project's second year. | 30 | Equipment procurement is currently lagging Baseline projections in part due to the anticipated start of construction earlier in the project, will begin to ramp up as we begin to procure equipment in parallel with construction activity. Based on aggressive baseline projections and a prolonged environmental process, this metric will be met in the second quarter of year three in the project life cycle. | 0 | Environmental approval has not been received for the project creating a delay in construction start. This metric will be achieved during the final year of the project in parallel with construction . | 0 | Once the network construction has started and equipment is able to be connected, this metric will be able to meet the baseline projections. Based on aggressive baseline projections and a prolonged environmental process, this metric will be met in the second quarter of year three in the project life cycle. | 0 | Network testing will commence once the network build has started and equipment is connected. This metric will mirror the Network Build schedule timeline with final testing being completed in quarter two of year three of the project. | 2011-11-22 14:42 | 2011-11-22 14:42 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2011 | Q4 | Q4 - 2011 | 5395 | 5079 | TRUE | 21 | Northwest Open Access Network received Finding of No Significant Impact (FONSI) midway through this quarter. Preparatory, non ground disturbing activities took place for construction slated to start in 2012. | 0 |  | N/A | 100 | No Variance. | 75 | No Variance. | 50 | An aggressive Baseline projection along with the longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources will be utilized to bring this metric closer to projections during quarter four of the 2012 calendar year with some remaining and challenging ROW's to be acquired by end of Q1 2013. This schedule still enables completion of the project as outlined in the BTOP Grant guidelines. | 45 | An aggressive Baseline projection along with the longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources will be utilized to bring this metric closer to projections during quarter four of the 2012 calendar year with some permitting still being acquired in quarter one of 2013 for the more difficult segments. This schedule will allow for completion of the project as outlined in the BTOP Grant guidelines. | 25 | See narrative above. Anticipation is to bring this metric in line with the Baseline projections in quarter four of the project's second year. | 26 | Equipment procurement is currently lagging Baseline projections in part due to the anticipated start of construction earlier in the project, will begin to ramp up as we begin to procure equipment in parallel with construction activity. Based on aggressive baseline projections and a prolonged environmental process, this metric will be met in the second quarter of year three in the project life cycle. | 0 | Environmental approval was received for the project this quarter, creating a delay in construction start. This metric will be achieved at the end of calendar year 2012 in parallel with construction . | 0 | Once the network construction has started and equipment is able to be connected, this metric will be able to meet the baseline projections. Based on aggressive baseline projections and a prolonged environmental process, this metric will be met in the second quarter of year three in the project life cycle. | 0 | Network testing will commence once the network build has started and equipment is connected. This metric will mirror the Network Build schedule time line with final testing being completed in quarter two of year three of the project. | 2012-02-29 13:19 | 2012-02-29 13:19 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2012 | Q1 | Q1 - 2012 | 6015 | 5607 | TRUE | 22 | Northwest Open Access Network is busy preparing for construction which is slated to start in Quarter 2 of 2012. With the onset of this activity, the overall project milestone will increase rapidly and continue to shorten the gap in this metric. It is anticipated meeting baseline projections at the end of Q2 2013. | 0 |  | N/A | 100 | No variance. | 85 | No variance. | 60 | An aggressive Baseline projection coupled with a longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources are being utilized to bring this metric closer to projections during quarter four of calendar year 2012 with some remaining and challenging ROW's to be acquired by end of Q1 2013. This schedule will allow completion of the project as outlined in the BTOP Grant Guidelines. | 55 | An aggressive Baseline projection coupled with a longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources are being utilized to bring this metric closer to projections during quarter four of calendar year 2012 with some permitting still being acquired in Q1 2013 for the more difficult segments. This schedule will allow completion of the project as outlined in the BTOP Grant Guidelines. | 35 | See narrative above. Anticipation is to bring this metric in line with the Baseline projections during the fourth quarter of the second year of the project. | 26 | Equipment procurement is currently lagging Baseline projections in part due to the delays in the start of construction and readiness of routes for equipment installations, yet will begin to ramp up in quarters three and four of 2012. It is anticipated meeting baseline projections at the end of Q1 2013. | 0 | This project was only recently granted approval from the environmental perspective creating a delay in construction. The network build is projected to start in quarter two of 2012. Baseline metrics are expected to be met at the end of Q2 2013. | 0 | Once the network construction has started and equipment is able to be connected, this metric will be able to meet the baseline projections. Based on aggressive baseline projections and a prolonged environmental process, this metric will be met in the second quarter of year three of the project life cycle. | 0 | Network testing will commence once the network build has started and equipment is connected. This metric will mirror the Network Build schedule time line with final testing being completed in quarter two of year three of the project. | 2012-05-10 14:01 | 2012-05-10 14:01 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2012 | Q2 | Q2 - 2012 | 6609 | 5922 | TRUE | 25 | With construction kicking off this quarter and additional segments of the project being bid and awarded, this metric will "catch up" by the end of quarter two in 2013. | 0 |  | N/A | 100 | No Variance. | 85 | This metric is nearing completion with final changes and adjustments completed at the end of Q4 2012. | 65 | An aggressive Baseline projection coupled with a longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources are being utilized to bring this metric closer to projections during quarter four of calendar year 2012 with some remaining and challenging ROW's to be acquired by end of Q1 2013. This schedule will allow completion of the project as outlined in the BTOP Grant Guidelines. | 60 | An aggressive Baseline projection coupled with a longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources are being utilized to bring this metric closer to projections during quarter four of calendar year 2012 with some permitting still being acquired in Q1 2013 for the more difficult segments. This schedule will allow completion of the project as outlined in the BTOP Grant Guidelines. | 50 | See narrative above. Anticipation is to bring this metric in line with the Baseline projections during the first quarter of 2013. | 30 | Equipment procurement is currently lagging Baseline projections in part due to the delays in the start of construction and readiness of routes for equipment installations, yet will begin to ramp up as routes are built and available for production projected for quarter four 2012 and the first quarter of 2013. It is anticipated meeting baseline projections at the end of Q1 2013. | 2 | Construction started this quarter with minimal progress being made toward the end of the timeframe. Anticipated completion of the Network Build is slated for the end of Q1 2013. | 25 | Once the network construction has started and equipment is able to be connected, this metric will be able to meet the baseline projections. Route NW-1A is in process and will be in production shortly. Based on aggressive baseline projections and a prolonged environmental process, this metric will be met by the end of the first quarter 2013. | 0 | Network testing will commence once the network build has started and equipment is connected. This metric will mirror the Network Build schedule time line with final testing being completed in Quarter 2 of 2013. | 2012-07-30 11:43 | 2012-07-30 11:43 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2012 | Q3 | Q3 - 2012 | 7927 | 6668 | TRUE | 35 | With construction recently underway and additional routes being bid and awarded, this metric will 'catch up' by the end of the second quarter in 2013. | 0 |  | N/A | 100 | No Variance. | 90 | This metric is nearing completion with final changes and adjustments completed by the end of Q4 2012. | 70 | An aggressive Baseline projection coupled with a longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources are being utilized to bring this metric closer to projections during quarter four of calendar year 2012 with some remaining and challenging ROW's to be acquired by end of Q1 2013. This schedule will allow completion of the project as outlined in the BTOP Grant Guidelines. | 65 | An aggressive Baseline projection coupled with a longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources are being utilized to bring this metric closer to projections during quarter four of calendar year 2012 with some permitting still being acquired in Q1 2013 for the more difficult segments. This schedule will allow completion of the project as outlined in the BTOP Grant Guidelines. | 60 | See narrative above. Anticipation is to bring this metric in line with the Baseline projections during the first quarter of 2013. | 34 | Equipment procurement is currently lagging Baseline projections in part due to the delays in the start of construction and readiness of routes for equipment installations, yet will begin to ramp up as routes are built and available for production projected for quarter four 2012 and the first quarter of 2013. It is anticipated meeting baseline projections at the end of Q1 2013. | 12 | Construction started recently with minimal progress being made toward the end of the timeframe. Anticipated completion of the Network Build is slated for the end of Q1 2013. | 30 | As network construction continues to progress and equipment is able to be connected, this metric will be able to meet the baseline projections. City of Port Angeles Route NW-1A is in process and will be completed by end of Q1 2013. Based on aggressive baseline projections and a prolonged environmental process, this metric will be met by the end of the first quarter 2013. | 13 | Network testing will commence once the network build has started and equipment is connected. This metric will mirror the Network Build schedule time line with final testing being completed in Quarter 2 of 2013. | 2012-11-16 14:41 | 2012-11-16 14:41 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2012 | Q4 | Q4 - 2012 | 8795 | 7592 | TRUE | 55 | With construction well underway, this metric picked up and shortened the gap between actual and projected during the quarter. With the highest cost and most complex route, NE-1, now being substantially complete, this metric resulted in a high increase over the last quarter. It is anticipated that we will reach this metric in the last quarter of the project timeline. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 75 | An aggressive Baseline projection coupled with a longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources were utilized to bring this metric closer to projections during quarter four of calendar year 2012 with some remaining and challenging ROW's to be acquired by end of Q2 2013. This schedule will allow completion of the project as outlined in the BTOP Grant Guidelines. | 75 | An aggressive Baseline projection coupled with a longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources were utilized to bring this metric closer to projections during quarter four of calendar year 2012 with some permitting still being acquired in Q2 2013 for the more difficult segments. This schedule will allow completion of the project as outlined in the BTOP Grant Guidelines. | 70 | See narrative above. Anticipation is to bring this metric in line with the Baseline projections during the second quarter of 2013. | 40 | Equipment procurement is currently lagging Baseline projections in part due to the delays in the start of construction and readiness of routes for equipment installations, yet will begin to ramp up as routes are built and available for production projected for the first quarter of 2013. It is anticipated meeting baseline projections at the end of Q2 2013. | 24 | Construction started in the last half of 2012 with minimal progress being made toward the end of the timeframe. Anticipated completion of the Network Build is slated for the end of Q2 2013. | 35 | As network construction continues to progress and equipment is able to be connected, this metric will be able to meet the baseline projections. City of Port Angeles Route NW-1A is in process and will be completed by end of Q1 2013. Based on aggressive baseline projections and a prolonged environmental process, this metric will be met by the end of the second quarter 2013. | 20 | Network testing has commenced now that the network build has started and equipment is being connected. This metric will mirror the Network Build schedule time line with final testing being completed in Quarter 2 of 2013. | 2013-02-14 23:15 | 2013-02-14 23:15 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2013 | Q1 | Q1 - 2013 | 9909 | 8496 | TRUE | 59 | As construction continues, this metric picked up and shortened the gap between actual and projected during the quarter. It is anticipated that we will reach this metric in the last quarter of the project timeline. | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 80 | An aggressive Baseline projection coupled with a longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources were utilized to bring this metric closer to projections during this past quarter. It is anticipated reaching this metric in the second quarter of 2013. This schedule will allow completion of the project as outlined in the BTOP Grant Guidelines. | 80 | An aggressive Baseline projection coupled with a longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources were utilized to bring this metric closer to projections during this past quarter. It is anticipated reaching this metric in the second quarter of 2013. This schedule will allow completion of the project as outlined in the BTOP Grant Guidelines. | 80 | See narrative above. Anticipation is to bring this metric in line with the Baseline projections during the second quarter of 2013. | 45 | Equipment procurement is currently lagging Baseline projections in part due to the delays in the start of construction and readiness of routes for equipment installations, yet will begin to ramp up as routes are built and available for production projected for the second quarter of 2013. It is anticipated meeting baseline projections in July 2013. With the majority of the equipment being procured, only the payment of the invoices are reflected in this metric. | 32 | Construction is well underway with significant progress being made in the last quarter. Anticipated completion of the Network Build is slated for the end of the project life cycle in July 2013. | 40 | As network construction continues to progress and equipment is able to be connected, this metric will be able to meet the baseline projections. City of Port Angeles Route NW-1A was completed at the end of Q1 2013. Based on aggressive baseline projections and a prolonged environmental process, this metric will be met by the end of the project timeline in July. | 35 | Network testing is well underway with segments already being completed. As routes are built and equipment installed, testing is initiated and will mirror the Network Build schedule time line with final testing being completed in July of 2013. | 2013-05-24 17:08 | 2013-05-24 17:08 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2013 | Q2 | Q2 - 2013 | 10651 | 8986 | TRUE | 63 | As construction continues, this metric picked up and shortened the gap between actual and projected during the quarter. It is anticipated that we will reach this metric in the last quarter of the project timeline. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 90 | An aggressive Baseline projection coupled with a longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources were utilized to bring this metric closer to projections during this past quarter. It is anticipated reaching this metric in the third quarter of 2013. This schedule will allow completion of the project as outlined in the BTOP Grant Guidelines. | 90 | An aggressive Baseline projection coupled with a longer than anticipated Environmental process has created a lag in projections from actual to baseline. Additional resources were utilized to bring this metric closer to projections during this past quarter. It is anticipated reaching this metric in the third quarter of 2013. This schedule will allow completion of the project as outlined in the BTOP Grant Guidelines. | 90 | See narrative above. Anticipation is to bring this metric in line with the Baseline projections during the third quarter of 2013. | 47 | Equipment procurement is currently lagging Baseline projections in part due to the delays in the start of construction and readiness of routes for equipment installations, yet will begin to ramp up as routes are built and available for production projected for the second quarter of 2013. A majority of the equipment is already procured, minor spending is anticipated for CPE and final route completion. | 59 | Construction is well underway with significant progress being made in the last quarter. Anticipated completion of the Network Build is slated for the end of the project life cycle in September 2013. | 42 | As network construction continues to progress and equipment is able to be connected, this metric will be able to meet the baseline projections. Based on aggressive baseline projections and a prolonged environmental process, this metric will be met by the end of the project timeline in September. | 40 | Network testing is well underway with segments already being completed. As routes are built and equipment installed, testing is initiated and will mirror the Network Build schedule time line with final testing being completed in September of 2013. | 2013-08-20 11:23 | 2013-08-20 11:23 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2013 | Q3 | Q3 - 2013 | 12321 | 10496 | TRUE | 100 | Based on Expenditure of Federal Funds, this metric will not reach 100 percent as the budget will not be expended for this project. All construction and related activities have been completed at the close of the project end date. | 0 | N/A | N/A | 100 | Project is Complete. | 100 | Project is Complete. | 100 | Project is Complete. | 100 | Project is Complete. | 100 | Project is Complete. | 100 | Project is Complete. | 100 | Project is Complete. | 100 | Project is Complete. | 100 | Project is Complete. | 2014-07-25 14:45 | 2014-07-25 14:45 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570112 | 2010 | Q4 | Q4 - 2010 | 1197 | 2231 | TRUE | 12 | N/A | 0 | N/A | N/A | 50 | N/A | 20 | Have secured Engineering Consultant to complete Network Design. | 0 | Waiting on award of FONSI | 15 | N/A | 0 | N/A | 30 | Waiting for completion of EA and award of FONSI to purchase additional equipment | 44 | N/A | 30 | Waiting for completion of EA and award of FONSI to purchase/ deploy additional equipment | 30 | N/A | 2011-02-17 11:12 | 2011-02-17 11:12 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2011 | Q1 | Q1 - 2011 | 1893 | 2692 | TRUE | 10 | Waiting on approval of Environmental Assessment and award of FONSI to work on further aspects of project. | 0 |  | N/A | 95 | Draft EA has been submitted, working on follow up to submit final version. | 45 | Waiting on approval of Environmental Assessment and award of FONSI. | 0 | Waiting on approval of Environmental Assessment and award of FONSI. | 25 | We are on target for obtaining necessary construction permits for phase one of our project. | 0 | Waiting on approval of Environmental Assessment and award of FONSI. | 35 | Waiting on award of FONSI for additonal purchases. | 44 | We are on target for our network build in regards to our leases for phase one of our project. | 30 | Waiting on approval of Environmental Assessment and award of FONSI. | 32 | We are on target for network testing in regards to phase one of our project. | 2011-05-05 12:38 | 2011-05-05 12:38 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2011 | Q2 | Q2 - 2011 | 3007 | 3261 | TRUE | 17 | Our project was slightly delayed due to the timeframe in receiving our FONSI. In addition, weather conditions and flooding in our construction area once the FONSI was awarded has delayed our project slightly. We will be working closely with our Engineering Consultant and Contractors with the receipt of our fiber to catch up on the overall project to be closer in line with our baseline plan. We will look into adding additional crews to the contractors work force as well. | 0 |  | Not applicable for our award. | 100 | NebraskaLink's EA was approved this quarter and NebraskaLink was awarded their FONSI. | 55 | NebraskaLink is working closely with our Engineering Consultant on mapping out and staking the remainder of our project plans since the award of our FONSI. | 30 | NebraskaLink is currently behind on this milestone due to the delay in receipt of our FONSI. We are working closely with our Engineering Consultant to bring this milestone closer in line with our baseline plan. | 40 | NebraskaLink continues to work on obtaining the necessary permits in our project cities as well as permits for other needs including railroad crossings. We are working closely with our Engineering Consultant to obtain all necessary permits and approvals as our project progresses. | 20 | NebraskaLink is now ramping up on site preparations since the award of our FONSI. | 55 | We are on target for equipment procurement. | 50 | We are on target for our network build. | 30 | We are delayed on our equipment deployment due to the delay in the award of our FONSI and weather conditions to begin our deployment. | 35 | We are on target for our network testing. | 2011-08-11 08:40 | 2011-08-11 08:40 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2011 | Q3 | Q3 - 2011 | 4133 | 3913 | TRUE | 33 | Our project met a few delays this quarter due to flooding in our contsruction area and a delay in receiving fiber. | 0 |  | N/A | 100 | NebraskaLink received their FONSI. | 65 | NebraskaLink is working closely with our Engineering Consultant on mapping out and staking the remainder of our project plans. | 60 | NebraskaLink is continuing to work with our Engineering Consultant and all applicable parties on this milestone. | 60 | NebraskaLink is continuing to work on obtaining the necessary permits in our project cities as well as permits for other needs including railroad crossings. | 36 | NebraskaLink is on target for our site preparation. | 66 | We are on target for our equipment procurement. | 60 | NebraskaLink is close to their targeted baseline in respects to the Network Build components. With the delivery of fiber, we anticipate being able to be on target with this milestone next quarter. | 50 | We are delayed in our equipment deployment due to the delay in receiving our FONSI and weather conditions. | 45 | We are delayed in our network testing due to the delay in receiving our FONSI, weather conditions and the delay in receipt of fiber from our manufacturer. | 2011-11-18 13:41 | 2011-11-18 13:41 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2011 | Q4 | Q4 - 2011 | 4907 | 4592 | TRUE | 41 | NebraskaLink is behind their baseline projection for this quarter due to the slow construction start due to spring/summer flooding in our construction area and due to the initial delay in receiving fiber. We continue to work closely with all consultants and contractors to align closer with our baseline plan, | 0 |  | N/A | 100 | NebraskaLink received their FONSI. | 75 | NebraskaLink is on target with their baseline plan. | 75 | NebraskaLink is continuing to work with our Engineering Consultant and all applicable parties on this milestone. | 80 | NebraskaLink continues to work with our Engineering Consultant and Construction Contractor in identifying and obtaining all necessary permits for our project. NebraskaLink has completed work during this quarter that will be invoiced after the quarter. | 40 | NebraskaLink is currently on target with our baseline plan for this quarter. | 70 | NebraskaLink is on target with our baseline plan for this quarter. | 65 | NebraskaLink is on target with this milestone. | 70 | NebraskaLink is on target with this milestone. | 55 | NebraskaLink is slightly behind on this milestone due to our miles of constructed fiber. | 2012-02-07 15:28 | 2012-02-07 15:28 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2012 | Q1 | Q1 - 2012 | 5909 | 5554 | TRUE | 50 | NebraskaLink is behind our projected target on this milestone due to our slow construction start in spring /summer due to flooding in our project area and the initial delay in obtaining fiber. We are continuing to work towards aligning this with our baseline projections. | 0 |  | N/A | 100 | NebraskaLink received their FONSI. | 80 | NebrasakLink is on target with our baseline for this quarter. | 85 | NebraskaLink is continuing to work with our Engineering Consultant and all applicable parties on this milestone. | 90 | NebraskaLink continues to work closely with our Contractor and Engineering Consultant to identify and obtain all necessary permits for our project. | 50 | NebraskaLink is currently on target with our baseline for this quarter. | 75 | NebraskaLink is on target with our baseline for this quarter. | 70 | NebraskaLink is slightly behind on this milestone due to the winter season for burying fiber. | 73 | NebraskaLink is on target with our baseline for this quarter. | 63 | NebraskaLink is slightly behind on this milestone due to the winter season. | 2012-05-02 12:12 | 2012-05-02 12:12 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2012 | Q2 | Q2 - 2012 | 7221 | 6238 | TRUE | 66 | NebraskaLink is behind our projected target on this milestone due to our slow construction start in the spring/summer in 2011 due to flooding in our project area and the initial delay in obtaining fiber. We are rapidly approaching the projected milestone with the great stride we have made due to the weather and availability of materials. | 0 |  | N/A | 100 | NebraskaLink received their FONSI. | 85 | NebraskaLink is on target with this milestone. | 90 | NebraskaLink is on target with this milestone. | 95 | NebraskaLink continues to work closely with our Contractor and Engineering Consultant to identify and obtain all necessary permits for our project. | 76 | NebraskaLink is currently on target with our baseline for this milestone. | 80 | NebraskaLink is on target with our baseline for this milestone. | 83 | NebraskaLink is on target with our baseline for this milestone. | 80 | NebraskaLink is on target with our baseline for this milestone. | 71 | NebraskaLink is close to target on this milestone. | 2012-08-23 12:11 | 2012-08-23 12:11 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2012 | Q3 | Q3 - 2012 | 7897 | 6653 | TRUE | 82 | NebraskaLink is behind our projected target on this milestone. We expect to be closer to our target with the close of the next quarter due to invoices for services/ materials that are expected. | 0 |  | N/A | 100 | Completed | 90 | NebraskaLink is on target with this milestone. | 98 | NebraskaLink is close to our target with this milestone. | 98 | NebraskaLink is close to our target with this milestone. | 85 | NebraskaLink is behind on this target with our project plan. We are waiting a reply regarding a possible change to some city builds in our application. | 85 | NebraskaLink is behind on this target with our project plan. | 93 | NebraskaLink is on target with this milestone. | 90 | NebraskaLink is on target with this milestone. | 84 | NebraskaLlink is close to target with our project plan on this milestone. | 2012-11-15 15:21 | 2012-11-15 15:21 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2012 | Q4 | Q4 - 2012 | 8679 | 7496 | TRUE | 86 | NebraskaLink is behind on our projected target on this milestone. We are waiting on a reply to possible changes to CAI builds in our application as well as an addition to our project route. | 0 |  | N/A | 100 | Completed | 95 | NebraskaLink is on target with this milestone. | 100 | Completed | 98 | NebraskaLink is close to target with this milestone. | 90 | NebraskaLink is behind on this target with our project plan. We are waiting a reply regarding a possible change to some city builds in our application. | 86 | NebraskaLink is behind on this target with our project plan. | 97 | NebraskaLink is on target with this milestone. | 93 | NebraskaLink is close to target with this milestone. | 90 | NebraskaLink is close to target with this milestone. | 2013-02-08 13:56 | 2013-02-08 13:56 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2013 | Q1 | Q1 - 2013 | 9353 | 8136 | TRUE | 94 | NebraskaLink is close on this milestone. Our delay was due to the winter build season and waiting on approval for our Award Action Request to swap CAI's in our grant cities. | 0 |  | N/A | 100 | Completed | 98 | NebraskaLink is close to their target on this milestone. | 100 | NebraskaLink has completed this milestone | 100 | NebraskaLink has completed this milestone | 95 | NebraskaLink is close to target on this milestone. NebraskaLink was waiting on approval to swap CAI's in our grant cities before continuing. | 99 | NebraskaLink is close to this milestone. NebraskaLink is requesting a budget modification to reallocate funds. | 97 | NebraskaLink is on target with this milestone. | 98 | NebraskaLink is close to this milestone. | 92 | NebraskaLink is behind on this milestone due to the no construction during this quarter. NebraskaLink was also waiting on approval to swap CAI's in our grant cities before continuing construction. | 2013-04-29 12:51 | 2013-04-29 12:51 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2013 | Q2 | Q2 - 2013 | 10315 | 8775 | TRUE | 97 | NebraskaLink is close to completion on this milestone. Once we receive invoices for final construction in the upcoming weeks, we will be 100 % complete. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 99 | NebraskaLink is close to completion on this project milestone. With the completion of our construction during this quarter, this milestone will be completed early in 3rd quarter 2013. | 2013-07-30 11:51 | 2013-07-30 11:51 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2013 | Q3 | Q3 - 2013 | 11639 | 9761 | TRUE | 100 | Completed | 0 |  | N/A | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2014-01-22 11:41 | 2014-01-22 11:41 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570113 | 2010 | Q4 | Q4 - 2010 | 1011 | 2057 | TRUE | 0 | No variance from Baseline. | 0 |  | N/A | 50 | No variance from Baseline. | 1 | No variance from Baseline. | 0 | N/A | 27 | No variance from Baseline. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 2011-02-09 10:09 | 2011-02-09 10:09 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2011 | Q1 | Q1 - 2011 | 2307 | 2899 | TRUE | 1 | No variance from Baseline. | 0 | None | N/A | 100 | No variance from Baseline. Environmental Assessment (EA) completed and submitted to NTIA. Awaiting Finding Of No Significant Impact (FONSI). Note: this milestone was not budgeted separately so the percent complete is based on completion of the milestone, not on percent of planned expenditure. | 2 | No variance from Baseline. As noted in number 1, the State received responses to Request for Proposals (RFPs) for engineering services and completed reviews of the responses and interviews of the engineering firms. | 0 | N/A | 0 | Variance from baseline. Awaiting Finding Of No Significant Impact (FONSI) on the Environmental Assessment. The State is developing required documents for acquiring needed construction permits, railroad permits and other approvals and will expedite this process with the goal of completing this milestone on schedule. | 0 | N/A | 0 | No variance from Baseline. | 0 | Variance from Baseline. Awaiting Finding Of No Significant Impact (FONSI) on Environmental Assessment. The State is revising internal project plans to expedite the network build in order to complete this milestone on schedule. The State will engage multiple engineering design firms and will divide the project up into 40-50 mini-projects with multiple construction firms and project partners. The State is developing an RFP to purchase all materials (fiber optic cable, conduit, etc.) directly from suppliers. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 2011-05-25 16:24 | 2011-05-25 16:24 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2011 | Q2 | Q2 - 2011 | 2961 | 3238 | TRUE | 6 | Variance from Baseline. The State proceeded on segments of the project while awaiting the Finding Of No Significant Impact (FONSI) on the Environmental Assessment. Critical segments of the project will be expedited - see narratives in 2e and 2h. | 0 | None | N/A | 100 | No variance from Baseline. The State received the Finding of No Significant Impact (FONSI) on April 14, 2011. Note: This milestone was not budgeted separately so the percent complete is based on completion of the milestone, not on percent of planned expenditure. | 3 | No variance from Baseline. As noted in number 1, negotiations have been initiated with the Engineering firms selected from the RFP process for the OCAN project design. | 0 | N/A | 54 | Variance from Baseline due to awaiting the Finding Of No Significant Impact (FONSI) on the Environmental Assessment. The State has proceeded with work on this milestone and has developed required documents for acquiring needed construction permits, railroad permits and other approvals. The State will expedite this process with the goal of completing this milestone on schedule. | 0 | N/A | 0 | No variance from Baseline. | 1 | Variance from Baseline due to awaiting Finding Of No Significant Impact (FONSI) on the Environmental Assessment. The State is revising internal project plans to expedite the network build in order to complete this milestone on schedule. The State will engage multiple engineering design firms and will divide the network build into 40-50 mini-projects with multiple construction firms and project partners. As noted in number 1, the State issued a Request for Proposal (RFP) to solicit and consider proposals from qualified offerors willing to enter into one or multiple agreements for public-private initiative/partnership(s) or shared resources project(s) for the construction of fiber optic cables, conduit and ground boxes along the OCAN Broadband project construction routes. Five offerors submitted responses which are being evaluated. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 2011-08-08 16:21 | 2011-08-08 16:21 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2011 | Q3 | Q3 - 2011 | 3495 | 3518 | TRUE | 15 | Variance from Baseline. As noted in 2g, the State has booked the value of equipment purchased for the OCAN project and the value of leased State fiber donated as State match to the OCAN project. | 0 |  | N/A | 100 | No variance from Baseline. Note: This milestone was not budgeted separately so the percent complete is based on completion of the milestone, not on percent of planned expenditure. | 52 | Variance from Baseline. This milestone is ahead of schedule. As noted in number 1, the engineering design project was divided into 31 sections. 20 sections have been completed and reviewed. All engineering design is due for completion by November 15, 2011. | 100 | NOTE: This milestone was not included in the Baseline as the State is donating Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 81 | Variance from Baseline. The State has continued work on this milestone, developing and submitting the required documents for acquiring needed construction permits, railroad permits and other approvals. Thus far permits have been received from two of the railroads operating in the State. The State is expediting this process with the goal of completing this milestone on schedule. | 0 | N/A | 31 | Variance from Baseline. New network routers and switches have been purchased for the OCAN project as part of the State match. This equipment, valued at $5,000,000, has been booked to the OCAN project. The Indefeasible Right of Use (IRU) agreements on strands of existing State fiber, valued at $3,850,000, are also part of the State match and have been booked to the OCAN project. The total equipment match of $8,850,000 has been posted to Actuals in Row j in the Infrastructure Budget Execution Details. As noted in number 1, the State issued a Request for Proposal (RFP) for Communications Huts for the OCAN project. Bids were received and reviewed, and a recommendation made to award contracts to two bidders. See NOTE in number 1 regarding cost for communications huts and budget adjustments. The State also completed and issued a RFP for Fiber Optic Cable for the OCAN project. The RFP was posted on September 28, 2011 with a close date of October 27, 2011. | 1 | Variance from Baseline. As noted in number 1, item 4, the State completed evaluations of the proposals received from five bidders on the RFP for public-private initiative/partnership(s) or shared resources project(s) for the construction of fiber optic cables, conduit and ground boxes along the OCAN project construction routes, or Indefeasible Right of Use (IRU) Agreements for existing fiber optic strands that will allow the State to meet the purpose of the grant. The State held meetings with three of the bidders to obtain clarifications on their offers and is in process of reviewing proposed IRU Agreements from one of the bidders. Also, the State will begin issuing Request for Proposal (RFP) packages for pure construction upon completion, review and approval of all engineering design. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 2011-10-27 11:36 | 2011-10-27 11:36 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2011 | Q4 | Q4 - 2011 | 4909 | 4594 | TRUE | 17 | Variance from Baseline. The majority of Actual Expenditures are State Match as noted in the Infrastructure Budget Execution Details. | 0 |  | N/A | 100 | No variance from Baseline. Note: This milestone was not budgeted separately so the percent complete is based on completion of the milestone, not on percent of planned expenditure. | 81 | Variance from Baseline. This milestone is ahead of schedule. As noted in number 1, the engineering design project was divided into 31 segments. 25 segments have been completed and reviewed. All engineering design is due for completion in January, 2012. | 100 | NOTE: This milestone was not included in the Baseline as the State is donating Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 90 | Variance from Baseline. The State has continued work on this milestone, developing and submitting the required documents for acquiring needed construction permits, railroad permits and other approvals. As noted in number 1, item 6, the State has received permits from all but a few affected railroads for the OCAN project. Also, as noted in number 1, item 7, the State executed Memorandums of Understanding (MOUs) with Oklahoma communities the OCAN project is passing through. The MOUs grant the OCAN project access to right of way through the communities. The State is expediting this process with the goal of completing this milestone on schedule. | 0 | N/A | 31 | Variance from Baseline. All expenditures to date are State Match as noted in the Infrastructure Budget Execution Details. The State will issue Purchase Orders for Fiber Optic Cable for the OCAN project in early January, 2012. The State will also post a Request for Proposal (RFP) in early January, 2012 for the additional network equipment required for the OCAN project. | 5 | Variance from Baseline. As noted in number 1, item 5, The State completed review of proposed Indefeasible Right of Use (IRU) Agreements for existing fiber optic strands that will allow the State to meet the purpose of the grant. The State submitted an Award Action Request (AAR) to NTIA requesting to execute three separate IRUs that will incorporate ten (10) of the thirty-one OCAN project segments, reducing the number of segments to be constructed from 31 to 21. The State is awaiting NTIA approval of this AAR. Also, as noted in number 1, item 8, the State advertised for bids for construction of the OCAN project. There will be bid lettings in January, February and March, 2012. The State is expediting this process with the goal of completing this milestone on schedule. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 2012-02-07 15:59 | 2012-02-07 15:59 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2012 | Q1 | Q1 - 2012 | 5959 | 5579 | TRUE | 24 | Variance from Baseline. The majority of Actual Expenditures are State Match as noted in the Infrastructure Budget Execution Details. As noted in number 1, construction of the communications huts is well underway, bids for construction of the OCAN route have been awarded and construction is underway on multiple segments of the project. All critical milestones of the project are being expedited to meet the overall 67 percent project completion milestone by the end of year two of the project. | 0 |  | N/A | 100 | No variance from Baseline. Note: This milestone was not budgeted separately so the percent complete is based on completion of the milestone, not on percent of planned expenditure. | 100 | Variance from Baseline. This Milestone has been completed. All engineering design has been completed, reviewed and approved. As noted in the Actuals in Row d in the Infrastructure Budget Execution Details, the cost for engineering design was $4,817,836, all of which is State match. | 100 | NOTE: This milestone was not included in the Baseline as the State is donating Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 98 | Variance from Baseline. The State has acquired all required construction permits and is awaiting the last few railroad permits. As noted in number 1, item 5, the State has received permits from all but a few affected railroads for the OCAN project. Also, as noted in number 1, item 6, the State completed Memorandums of Understanding (MOUs) with Oklahoma communities the OCAN project is passing through. The MOUs grant the OCAN project access to right of way through the communities. | 0 | N/A | 39 | Variance from Baseline. Most expenditures to date are State Match as noted in the Infrastructure Budget Execution Details. As noted in number 1, items 2, 3 and 8, construction of the communications huts and deliveries of fiber optic cable are well underway, and responses on the RFP for network equipment are being evaluated. NOTE: It was determined the communications huts need larger fuel tanks for the backup generators in order to provide backup power for up to 72 hours during a power outage. In order to cover the additional cost, $300,000 has been transferred from the construction (i) category to the structures (b) category in the Infrastructure Budget Execution Details. The structures (b) category was increased from $8,363,120 to $8,663,120 (federal share increased from $3,840,620 to $4,140,620). It also was determined additional fiber optic cable is needed for build-outs to the Community Anchor Institutions (CAIs) in the OCAN project. In order to cover the additional cost, $863,486 | 10 | Variance from Baseline. As noted in number 1, item 4, the State has executed the first IRU for 2 segments of the OCAN project covering 60 miles of the OCAN route and connecting one Community Anchor Institution (CAI). Also, as noted in number 1, item 7, the State has awarded 21 bids for construction of 21 segments of the OCAN project covering 748 miles of the OCAN route. The construction (i) category in the Infrastructure Budget Execution Details is showing zero Actuals as funds were not yet expended in this quarter. | 10 | No variance from Baseline. Equipment donated as match for the OCAN project has been deployed. Also, as noted in number 1, item 8, responses on the RFP for network equipment are being evaluated. | 10 | No variance from Baseline. Network testing has been completed on the network delivered to the OCAN project on the first executed IRU (number 1, item 4). | 2012-05-08 12:11 | 2012-05-08 12:11 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2012 | Q2 | Q2 - 2012 | 6865 | 6059 | TRUE | 51 | Variance from Baseline. As noted in number 1, construction has been completed on the sixteen new communications huts, deliveries of all inside plant and outside plant fiber optic cable have been completed and construction was begun on 12 of 21 segments of the OCAN project with 497 miles of conduit construction completed and 157 miles of fiber optic cable pulled. All critical milestones of the project are being expedited to meet the overall 67 percent project completion milestone by the end of year two of the award. | 0 |  | N/A | 100 | No variance from Baseline. Note: This milestone was not budgeted separately so the percent complete is based on completion of the milestone, not on percent of planned expenditure. | 100 | Variance from Baseline. This Milestone has been completed. All engineering design has been completed, reviewed and approved. As noted in the Actuals in Row d in the Infrastructure Budget Execution Details, the cost for engineering design was $4,817,836, all of which is State match. | 100 | NOTE: This milestone was not included in the Baseline as the State donated Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 98 | Variance from Baseline. The State has acquired all required construction permits and is awaiting the last few railroad permits. As noted in number 1, item 7, the State has received permits from all but a few affected railroads for the OCAN project. Also, as noted in number 1, item 8, the State completed all remaining Memorandums of Understanding (MOUs) with Oklahoma communities the OCAN project is passing through. The MOUs grant the OCAN project access to right of way through the communities. | 0 | N/A | 48 | Variance from Baseline. Most expenditures to date are State Match as noted in the Infrastructure Budget Execution Details. As noted in number 1, item 4, deliveries of all inside plant and outside plant fiber optic cable have been completed. Also, as noted in number 1, item 5, evaluations of the responses to the RFP for network equipment were completed and all network equipment has been ordered. | 22 | Variance from Baseline. The State has executed one IRU for 60 miles of existing infrastructure on the OCAN route and,as noted in number 1, item 9, 497 miles of conduit construction have been completed and 157 miles of fiber optic cable pulled. The percent complete is based on the IRU and miles of completed construction with fiber pulled. | 20 | No variance from Baseline. Equipment donated as match for the OCAN project has been deployed. Also, as noted in number 1, item 5, evaluations of the responses to the RFP for network equipment were completed and all network equipment has been ordered. | 20 | No variance from Baseline. Network testing has been completed on the network delivered to the OCAN project on the first executed IRU and on the 157 constructed miles with fiber optic cable pulled. | 2012-08-06 13:37 | 2012-08-06 13:37 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2012 | Q3 | Q3 - 2012 | 7815 | 6611 | TRUE | 81 | Variance from Baseline. As noted in number 1,item 7, construction continued on 12 of 21 segments and commenced on the remaining 9 segments with 713 miles of conduit construction completed and 471 miles of fiber optic cable pulled. All critical milestones of the project continue to be expedited. The OCAN project met the year two milestone of 67 percent completion with 70.84 percent of Federal funds expended by July 31, 2012. | 0 |  | N/A | 100 | No variance from Baseline. Note: This milestone was not budgeted separately so the percent complete is based on completion of the milestone, not on percent of planned expenditure. | 100 | Variance from Baseline. This Milestone has been completed. All engineering design has been completed, reviewed and approved. As noted in the Actuals in Row d in the Infrastructure Budget Execution Details, the total cost for engineering design was $5,101,568, including $4,817,836 match and $283,732 federal. | 100 | NOTE: This milestone was not included in the Baseline as the State donated Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | The State has acquired all required construction and railroad permits. The total cost for permits of $49,435 came in well under the grant amount of $600,000. | 0 | N/A | 83 | Variance from Baseline. A significant portion of the expenditures to date are State Match as noted in the Infrastructure Budget Execution Details. As noted in number 1, item 5, a majority of the new network equipment has now been delivered. | 72 | Variance from Baseline. As noted in number 1, item 6, the State executed one additional Indefeasible Right of Use (IRU) Agreement for 47 miles of existing infrastructure on the OCAN route. The State now has executed three IRU Agreements for a total of 257 miles of existing infrastructure on the OCAN route. Also, as noted in number 1, item 7, 713 miles of conduit construction has been completed and 471 miles of fiber optic cable pulled. The State continues to expedite construction to meet the 100 percent milestone by Q3 of year 3 of the project. | 40 | No variance from Baseline. Equipment donated as match for the OCAN project has been deployed. Also, as noted in number 1, item 5, a majority of the new network equipment has been delivered and deployment of this equipment has begun. | 55 | Variance from Baseline. Network testing has been completed on the network delivered to the OCAN project on the IRU's and on the 471 constructed miles with fiber optic cable pulled. | 2012-11-09 14:49 | 2012-11-09 14:49 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2012 | Q4 | Q4 - 2012 | 8705 | 7512 | TRUE | 88 | Variance from Baseline. As noted in number 1, item 5, 870 miles of conduit construction has been completed and 700 miles of fiber optic cable pulled. 9 of the 21 project segments were completed as of Year3-Q2, and the State continues to expedite construction on the remaining 12 segments to meet the 100% milestone by Year3-Q3 of the project. All critical milestones of the project continue to be expedited. | 0 |  | N/A | 100 | No variance from Baseline. Note: This milestone was not budgeted separately so the percent complete is based on completion of the milestone, not on percent of planned expenditure. | 100 | No variance from Baseline. | 100 | Note: This milestone was not included in the Baseline as the State donated Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | The State has acquired all required construction and railroad permits. The total cost for permits of $49,435 came in well under the grant amount of $600,000. | 0 | N/A | 83 | Variance from Baseline. A significant portion of the expenditures to date are State Match as noted in the Infrastructure Budget Execution Details. As noted in number 1, item 3, a majority of the new network equipment was installed. | 83 | Variance from Baseline. As noted in number 1, item 5, 870 miles of conduit construction has been completed and 700 miles of fiber optic cable pulled. 9 of the 21 project segments were completed as of Year3-Q2, and the State continues to expedite construction to meet the 100% milestone by Year3-Q3 of the project. | 70 | No variance from Baseline. Equipment donated as match for the OCAN project has been deployed. Also, as noted in number 1, item 3, a majority of the new network equipment has been installed. | 88 | Variance from Baseline. Network testing has been completed on the network delivered to the OCAN project on the IRU's and on the 700 constructed miles with fiber optic cable pulled. | 2013-02-11 15:28 | 2013-02-11 15:28 | 7631 | 7631 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2013 | Q1 | Q1 - 2013 | 9625 | 8344 | TRUE | 88 | Variance from Baseline. As noted in number 1, item 3, 827 miles of conduit construction and fiber optic cable have completed all 21 project segments. The State continues to expedite remaining critical milestones of the project. | 0 |  | N/A | 100 | No variance from Baseline. Note: This milestone was not budgeted separately so the percent complete is based on completion of the milestone, not on percent of planned expenditure. | 100 | No variance from Baseline. | 100 | Note: This milestone was not included in the Baseline as the State donated Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | The State has acquired all required construction and railroad permits. The total cost for permits of $49,435 came in well under the grant amount of $600,000. | 0 | N/A | 86 | Variance from Baseline. A significant portion of the expenditures to date are State Match as noted in the Infrastructure Budget Execution Details. As indicated in number 1, item 5, OCAN pursued approval from NTIA to purchase additional optical equipment and ground vaults to utilize remaining BTOP grant funds. | 84 | Variance from Baseline. As noted in number 1, item 3, 827 miles of conduit construction and fiber optic cable have completed all 21 project segments. The State continues to expedite remaining critical milestones of the project. | 80 | Variance from Baseline. As indicated in number 1, item 5, OCAN pursued approval from NTIA to purchase additional optical equipment and ground vaults to utilize remaining BTOP grant funds. This equipment remains to be installed. | 74 | Variance from Baseline. Network testing has been completed on the network delivered to the OCAN project on the IRU's and continues on the fiber optic cable pulled. Percent complete decreased from last quarter because this is based on expenditures, though testing continues to move towards completion. As noted in number 1, item 6, a portion of previously reported network testing expenditures were also recorded under Architectural and Engineering fees (Line D) on the Infrastructure Budget page of the PPR and have now been removed from the network testing total expenditures. These values are supported by systematic reports. | 2013-05-07 17:23 | 2013-05-07 17:23 | 7631 | 7631 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2013 | Q2 | Q2 - 2013 | 10319 | 8778 | TRUE | 89 | Variance from Baseline. As we neared close-out it became apparent that we needed to initiate change orders for several grant purchase orders to accommodate expenses. The change order process slowed some payments for the grant, causing our percent complete to appear less than actual. The State continues to expedite remaining critical milestones of the project. | 0 |  | N/A | 100 | No variance from Baseline. Note: This milestone was not budgeted separately so the percent complete is based on completion of the milestone, not on percent of planned expenditure. | 100 | No variance from Baseline. | 100 | Note: This milestone was not included in the Baseline as the State donated Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | The State has acquired all required construction and railroad permits. The total cost for permits of $49,435 came in well under the grant amount of $600,000. | 0 | N/A | 86 | Variance from Baseline. As indicated in number 1, item 3, OCAN continues to install additional optical equipment and ground vaults to utilize remaining BTOP grant funds. There was a delay in generator procurement/installation due to local natural disasters affecting our vendor. Also, the change order process slowed payments for equipment, causing our percent complete to appear less than actual (as mentioned in 2a). | 85 | Variance from Baseline. 827 miles of conduit construction and fiber optic cable have completed all 21 project segments. The State continues to expedite remaining critical milestones of the project. Also, the change order process slowed payments for construction causing our percent complete to appear less than actual (as mentioned in 2a). | 86 | Variance from Baseline. As indicated in number 1, item 3, OCAN continues to install additional optical equipment and ground vaults to utilize remaining BTOP grant funds. There was a delay in generator procurement/installation due to local natural disasters affecting our vendor. Also, the change order process slowed payments for equipment, causing our percent complete to appear less than actual (as mentioned in 2a). | 77 | Variance from Baseline. Network testing continues on additional access points (referenced number 1, item 3) with plans to conclude testing by grant end. Since this percent complete is based on expenditures and network testing costs are lower than initially projected, the percent complete appears less than actual. | 2013-07-30 12:25 | 2013-07-30 12:25 | 7631 | 7631 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2013 | Q3 | Q3 - 2013 | 12515 | 10691 | TRUE | 100 | Project complete. | 0 |  | N/A | 100 | Project complete. | 100 | Project complete. | 100 | Note: This milestone was not included in the Baseline as the State donated Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | Project complete. | 0 | N/A | 100 | Project complete. | 100 | Project complete. 827 miles of conduit construction and fiber optic cable have completed all 21 project segments. The State has completed remaining critical construction milestones of the project. | 100 | Project complete. | 100 | Project complete. | 2014-09-22 14:45 | 2014-09-22 14:45 | 7631 | 7631 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570114 | 2010 | Q4 | Q4 - 2010 | 1365 | 2381 | TRUE | 0 | Contract negotiations with engineers and other agencies have put us slightly behind. | 12 | Staffing | None Noted | 75 | None Noted | 10 | None Noted | 5 | Contract negotiations with the engineering firm took longer than anticipated therefore, we were unable to submit the Rights of Way permits but we have identified the agencies. | 0 | Contract negotiations with the engineering firm took longer than anticipated therefore, the engineering firm was not able to complete the permits as we had originally anticipated. | 0 | None Noted | 0 | None Noted | 0 | Merit was unable to secure the Mackinaw Bridge IRU, as originally anticipated, that would have contributed to this category but negotiation are in process to secure a contract. | 0 | None Noted | 0 | None Noted | 2011-02-24 13:47 | 2011-02-24 13:47 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2011 | Q1 | Q1 - 2011 | 2267 | 2879 | TRUE | 1 | Our overall project spending is less than the projected 7% as a result of unexpected delays in the issuance of our FONSI. Merit believed we would be able to begin field engineering and construction this quarter. Once Merit has clearance to move forward with construction, we believe that we will catch up over the next few quarters. | 3 | Staffing | We have not hired staff at the rate originally projected because we overestimated the staffing levels that would be required for this pre-FONSI stage of the project. In addition, staff have not completed budgeted training, and we have not incurred the cost of increased insurance yet. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 364%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the EA, we are considering a revision to the budget to incorporate the latest estimate of the EA cost at completion, which will be at 721%. | 8 | We are waiting for our FONSI to proceed with most of the field engineering, but have attempted to do as much planning as is covered by the revised expenditure plan. Due to weather conditions, pre-construction planning and engineering work wasn't done at the projected pace in the Upper Peninsula and contract renegotiations with our lower peninsula firm are taking longer than anticipated. The number reported in this quarter is lower than last quarter because of the newly issued guidance on percent complete calculations. While our estimate has always been primarily based on cost, previous calculations had also factored in work and progress. | 0 | Permits require an approved engineered route; while we are waiting for the engineering work to be completed and our route to be accepted by the NTIA, we have prepped the Right of Way permits so they can be sent out as soon as the FONSI is received and the route is finalized. | 0 | Permits require an approved engineered route; our ability to move forward depends on having our route accepted by the NTIA so the CAD drawings can be finalized. | 2 | Merit did not receive the FONSI, so we could not begin hut site construction. Sites for the huts have been identified and Merit began to negotiate easements. | 0 | Merit did not include equipment in our revised expenditure plan, so we cannot begin procuring equipment until we receive our FONSI. In addition, we are waiting on a determination on using a sole source justification for equipment vendor selection. However, if the sole source request is approved, we are ready to order optical equipment as soon as the FONSI is received. | 0 | We anticipated having finalized IRU Agreements in place by this point; however, negotiations are underway, and we believe that we will be purchasing the existing infrastructure in the next quarter. | 0 | No variance | 0 | No variance | 2011-05-24 09:31 | 2011-05-24 09:31 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2011 | Q2 | Q2 - 2011 | 3027 | 3271 | TRUE | 1 | Our overall project spending is less than we projected as a result of unexpected delays in the issuance of our Finding of No Significant Impact. Merit believed we would be able to begin field engineering and construction this quarter. Once Merit has clearance to move forward with construction, we believe that we will catch up over the next few quarters. | 7 | Staffing, Misc. | The construction delays have led to a slower staffing ramp up than originally projected. With the hire of a Project Manager, Environmental Assessor, and several clerks pending, we anticipate a gradually aligning with the Baseline Report. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 474%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the Environmental Assessment, we are considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 700%. | 21 | We are waiting for our Finding of No Significant Impact to proceed with most of the field engineering, but have attempted to do as much planning as is covered by the revised expenditure plan. Due to weather conditions, pre-construction planning and engineering work wasn't done at the projected pace in the Upper Peninsula and contract renegotiations with our lower peninsula firm are taking longer than anticipated. | 49 | Many permits require an approved engineered route; while we are waiting for the engineering work to be completed and our route to be accepted by the NTIA, we have prepped many permits so they can be sent out as soon as the Finding of No Significant Impact is received and the route is finalized. | 0 | Many permits require an approved engineered route; while we are waiting for the engineering work to be completed and our route to be accepted by the NTIA, we have prepped many permits so they can be sent out as soon as the Finding of No Significant Impact is received and the route is finalized. | 0 | Merit did not receive the Finding of No Significant Impact, so we could not begin hut site construction. Sites for the huts have been identified and Merit began to negotiate easements. | 0 | Merit did not include equipment in our revised expenditure plan, so we requested a pre-Environmental Assessment budget revision. Our sole source was approved at the end of the quarter, and the order will be placed next quarter. | 0 | We anticipated having finalized Indefeasible Right to Use (IRU) Agreements and the Finding of No Significant Impact in place by this point; however, negotiations are underway, and we believe that we will be purchasing the existing infrastructure and beginning construction in the next quarter. | 0 | We were waiting for our Environmental Assessment budget approval and sole source approval to order equipment. Equipment has been selected, and will be deployed as soon as it is received and tested. | 0 | Network construction has not begun. | 2011-08-11 16:37 | 2011-08-11 16:37 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2011 | Q3 | Q3 - 2011 | 3949 | 3813 | TRUE | 2 | Merit just recently received its notice of our Finding of No Significant Impact and has begun field engineering this quarter. At this point, field engineering is almost complete and permitting has begun so we anticipate a lot of construction work starting next quarter. | 9 |  | With the hire of a Project Manager, Environmental Assessor and several clerks we anticipate a gradual alignment with the Baseline Report. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 565%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the Environmental Assessment, we are considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 600%. | 61 | Since receiving our Finding of No Significant Impact we have proceeded with most of our field engineering. Much of the pre-construction planning has been completed in both the Upper and Lower peninsula but contract negotiations with our lower peninsula firm is taking longer than anticipated. | 9 | Many permits require an approved engineered route; while we are waiting for the last of the engineering work to be completed we have prepped and submitted many permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 15 | We have submitted almost 90% of the permits necessary for Round 2 construction since we received our Finding of No Significant Impact. At this point we are waiting for approval from the various permitting entities. | 2 | Sites for the huts have been identified. We have submitted an RFP for the construction of huts and are also in the process of acquiring easement agreements for the placement of said huts. | 0 | We have had our sole source approved as well as our pre-Environmental Assessment budget revision and have begun placing orders for equipment. | 0 | We have received our Indefeasible Right of Use Agreements as well as our Finding of No Significant Impact and have begun purchasing the existing infrastructure this quarter. | 0 | Equipment has been selected and will be deployed as soon as itâ€™s received and tested. As of this quarter, since receiving the Environmental Assessment budget approval and sole source approval, the process of purchasing this equipment began this quarter. | 0 | Network construction has not begun. | 2011-11-10 08:22 | 2011-11-10 08:22 | 5485 | 5485 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2011 | Q4 | Q4 - 2011 | 5327 | 5000 | TRUE | 9 | Engineering was largely completed, and permitting for Round 2 is in full swing. Construction began on small permitted segments; Merit anticipates having all construction crews working at full capacity next quarter. | 10 |  | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 550%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the Environmental Assessment, we are considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 600%. | 73 | Since receiving our Finding of No Significant Impact we have proceeded with most of our field engineering. While most of the field engineering is complete, we anticipate continued costs for incorporating redlines and doing final CADs, and the project will be at budget at completion. | 52 | We have prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 17 | We have prepped and submitted many permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 4 | Sites for the huts have been identified. We have submitted an RFP for the construction of huts, and are in the final stages of the selection process. Merit is also in the process of acquiring easement agreements for the placement of huts. | 3 | Merit ordered and received equipment, and placed some of it in the field in the Upper Peninsula. As more of the network is completed, we anticipate placing additional orders. | 8 | Materials for construction began arriving at our warehouse this quarter. Construction began in late December. We anticipate construction will ramp up as larger permitted segments are released for construction. | 8 | Merit ordered and received equipment, and placed some of it in the field in the Upper Peninsula. As more of the network is completed, we anticipate placing additional orders. | 0 | Network construction has not begun. | 2012-02-28 07:33 | 2012-02-28 07:33 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2012 | Q1 | Q1 - 2012 | 6243 | 5724 | TRUE | 15 | Permitting for Round 2 is in full swing. Construction began on small permitted segments; Merit anticipates having all construction crews working at full capacity next quarter. | 11 | Staffing, Miscellaneous | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 554%. This is partially due to an underestimate based on RFP responses Merit had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 600%. | 85 | Since receiving Merit's Finding of No Significant Impact, Merit has proceeded with most of the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs, and the project will be at budget at completion. | 88 | Merit has prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving the Finding of No Significant Impact, Merit has finalized the route and completed most of the engineering work necessary. | 46 | Merit has prepped and submitted many permits so they can be approved as Merit starts deploying construction crews. Since receiving the Finding of No Significant Impact, Merit has finalized the route and completed most of the engineering work necessary. | 5 | Sites for the huts have been identified. Merit submitted an RFP for Hut Construction and selected a vendor, and is in final stages of completing the contract with the hut vendor. Merit is also in the process of acquiring easement agreements for the placement of huts. | 3 | Merit ordered and received equipment, and placed some of it in the field in the Upper Peninsula. As more of the network is completed, we anticipate placing additional orders. | 18 | Materials for construction continue to be ordered. Construction began in late December 2011. Merit anticipates construction will ramp up as larger permitted segments are released for construction going forward. | 10 | Merit ordered and received equipment, and placed some of it in the field in the Upper Peninsula. As more of the network is completed, we anticipate placing additional orders. | 0 | Network construction has begun, testing will take place as equipment is placed and operational. | 2012-05-22 07:48 | 2012-05-22 07:48 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2012 | Q2 | Q2 - 2012 | 6947 | 6101 | TRUE | 24 | Construction is in full swing for Round 2 across all segments. Merit anticipates having a significant amount of infrastructure installed over third and fourth quarter. | 28 | Staffing, Miscellaneous | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 556%. This is partially due to an underestimate based on RFP responses Merit had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 600%. | 95 | Since receiving Merit's Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs, and the project will be at budget at completion. | 88 | Merit has prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving the Finding of No Significant Impact, Merit has finalized the route and completed most of the engineering work necessary for permit submission. | 49 | Merit has prepped and submitted many permits so they can be approved as Merit starts deploying construction crews. Since receiving the Finding of No Significant Impact, Merit has finalized the route and completed most of the engineering work necessary for permit submission. | 15 | Sites for the huts have been identified. Merit has completed contracts for hut construction and selected a hut vendor. Merit has acquired the easement agreements for the hut placement. Merit anticipates spending in this category to increase over the coming quarter and beyond. | 5 | Merit ordered and received equipment, and placed some of it in the field in the Upper Peninsula. As more of the network is completed, we anticipate placing additional orders. | 30 | Materials are still being ordered as construction continues. Construction began in late December 2011. Merit has a large number of crews are working across multiple segments each week. Merit anticipates construction will continue at this pace, aiming to place as much infrastructure as possible before weather limitations occur. | 20 | Merit ordered and received equipment, and placed some of it in the field in the Upper Peninsula. As more of the network is completed, we anticipate placing additional orders. | 0 | Network construction has begun, testing will take place as equipment is placed and operational. | 2012-08-09 09:13 | 2012-08-09 09:13 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2012 | Q3 | Q3 - 2012 | 8037 | 6725 | TRUE | 36 | Construction is in full swing for Round 2 across all segments. Merit anticipates having a significant amount of infrastructure installed by the end of the fourth quarter. | 32 | Staffing, Miscellaneous | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 556% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 600%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. | 95 | Merit has prepped and submitted many permits so they can be approved as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed most of the engineering work necessary for permit submission. | 56 | Merit has prepped and submitted many permits so they can be approved as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed most of the engineering work necessary for permit submission. | 16 | Sites for the huts have been identified. Merit has completed the construction contracts and selected a vendor. Merit has also acquired the easement agreements for hut placements. There is an anticipated increase in spending in this category over the coming quarter and beyond. | 8 | Merit ordered and received equipment, and placed some of it in the field in the Upper Peninsula. As more of the network is completed, we anticipate placing additional orders. | 47 | Materials are still being ordered as construction continues. Since construction began in late December 2011, Merit has had a large number of crews working across multiple segments each week. It is anticipated that construction will continue at this pace, aiming to place as much infrastructure as possible before weather limitations occur. | 20 | Merit has managed the equipment deployment by ordering, receiving, and placing it in the Upper Peninsula as needed. As more of the network is completed we will place additional equipment orders. | 0 | Network construction has begun. Testing will take place as equipment is placed and operational. | 2012-11-26 12:39 | 2012-11-26 12:39 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2012 | Q4 | Q4 - 2012 | 9019 | 7792 | TRUE | 50 | Construction is in full swing for Round 2 across all segments. Merit has installed a significant amount of infrastructure and will continue construction during the next quarter. | 35 | Staffing, Miscellaneous | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 610% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 620%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Currently Merit is at 151% of the original budget. A portion of site prep expenses have is included in this category. | 100 | Merit has prepped and submitted many permits so they can be approved as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed most of the engineering work necessary for permit submission. Merit is currently at 115% of its original budget. | 76 | Merit has prepped and submitted many permits so they can be approved as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed most of the engineering work necessary for permit submission. | 16 | Due to the way Merit has been classifying their expenses, these costs are included with Network Design. | 18 | Merit ordered and received equipment, and placed some of it in the field in the Upper Peninsula. As more of the network is completed, we anticipate placing additional orders. | 63 | Materials are still being ordered as construction continues. Since construction began in late December 2011, Merit has had a large number of crews working across multiple segments each week. It is anticipated that construction will continue at this pace, aiming to place as much infrastructure as possible. | 48 | Merit has managed the equipment deployment by ordering, receiving, and placing it in the Upper Peninsula as needed. As more of the network is completed we will place additional equipment orders. | 0 | Network construction has begun. Testing will take place as equipment is placed and operational. | 2013-02-27 14:39 | 2013-02-27 14:39 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2013 | Q1 | Q1 - 2013 | 9953 | 8521 | TRUE | 58 | Construction is in full swing for Round 2 across all segments. Merit has installed a significant amount of infrastructure and will continue construction during the next quarter. | 36 | Staffing, Miscellaneous | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 635% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 641%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Currently Merit is at 170% of the original budget. A portion of site prep expenses have is included in this category. | 100 | Merit has prepped and submitted many permits so they can be approved as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed most of the engineering work necessary for permit submission. Merit is currently at 117% of its original budget. | 78 | Merit has prepped and submitted many permits so they can be approved as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed most of the engineering work necessary for permit submission. | 20 | Due to the way Merit has been classifying their expenses, some of these costs are included with Network Design. | 20 | Merit ordered and received equipment, and placed some of it in the field. As more of the network is completed, weanticipate placing additional orders. | 73 | Materials are still being ordered as construction continues. Since construction began in late December 2011, Merit has had a large number of crews working across multiple segments each week. It is anticipated that construction will continue at this pace. | 48 | Merit has managed the equipment deployment by ordering, receiving, and placing it as needed. As more of the network is completed we will place additional equipment orders and incur more deployment expenses. | 0 | Network construction is taking place. Testing will take place as equipment is placed and operational. | 2013-05-29 06:10 | 2013-05-29 06:10 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2013 | Q2 | Q2 - 2013 | 10731 | 9029 | TRUE | 71 | Construction is in full swing for Round 2. Merit has installed a significant amount of infrastructure and will continue construction during the next quarter with the hope of completing construction. | 38 | Staffing, Miscellaneous | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 637% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 641%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Currently Merit is at 193% of the original budget. A portion of site prep expenses and salary has been included in this category. | 100 | Merit has prepped and submitted many permits so they can be approved as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed most of the engineering work necessary for permit submission. Merit is currently at 136% of its original budget. | 97 | Merit has prepped and submitted many permits so they can be approved as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed most of the engineering work necessary for permit submission. | 21 | Due to the way Merit has been classifying their expenses, some of these costs are included with Network Design. | 24 | Merit ordered and received equipment, and placed some of it in the field. As more of the network is completed, weanticipate placing additional orders. | 92 | Materials are still being ordered as construction continues. Since construction began in late December 2011, Merit has had a large number of crews working across multiple segments each week. It is anticipated that construction will continue at this pace until complete. | 48 | Merit has managed the equipment deployment by ordering, receiving, and placing it as needed. As more of the network is completed we will place additional equipment orders and incur more deployment expenses. | 0 | Network construction is taking place. Testing will take place as equipment is placed and operational. | 2013-08-26 11:00 | 2013-08-26 11:00 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2013 | Q3 | Q3 - 2013 | 11341 | 9471 | TRUE | 88 | Construction is nearly complete for Round 2. Merit has installed almost all infrastructure and will continue construction during the next quarter with the hope of completing all outstanding construction. | 44 | Staffing, Miscellaneous | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. Staffing has mostly been covered in the Network Design category and may re-allocated back to Other. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 643% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur small costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 643%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Currently Merit is at 210% of the original budget. A portion of site prep expenses and salary has been included in this category. | 100 | Merit has prepped and submitted many permits so they can be approved as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed most of the engineering work necessary for permit submission. Merit is currently at 178% of its original budget. | 100 | Merit has prepped and submitted many permits so they can be approved as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed most of the engineering work necessary for permit submission. Merit is currently at 103% of its original budget. | 22 | Due to the way Merit has been classifying their expenses, some of these costs are included with Network Design. | 38 | Merit ordered and received equipment, and the equipment has been placed in the field. Costs originally designed for this category have been placed in other categories resulting in being below budget. This category will be able to absorb overages from other areas. | 100 | Materials are still being ordered as construction continues. Since construction began in late December 2011, Merit has had a large number of crews working across multiple segments each week. Construction is nearing completion and Merit will continue at an aggressive pace until completed. | 100 | Merit has managed the equipment deployment by ordering, receiving, and placing it as needed. Merit is currently at 109% of the budget in this category but with all equipment placed, there will be minimal spending remaining. | 47 | Network construction is taking place. Testing will continue as equipment is placed and operational and there is continuity across the network. | 2013-11-22 09:11 | 2013-11-22 09:11 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2013 | Q4 | Q4 - 2013 | 11897 | 10066 | TRUE | 96 | Construction is nearly complete for Round 2. Merit has installed almost all infrastructure and will continue construction during the next quarter with the hope of completing all outstanding construction. | 49 | Staffing, Miscellaneous | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. Staffing has mostly been covered in the Network Design category and may reallocated back to Other. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 687% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur small costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 690%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Currently Merit is at 230% of the original budget. A portion of site prep expenses and salary has been included in this category. | 100 | Merit has prepped and submitted many permits so they can be approved as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed permit submission. Merit is currently at 180% of its original budget. | 100 | Merit has prepped and submitted many permits so they can be approved as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed permit submission. Merit is currently at 103% of its original budget. | 24 | Due to the way Merit has been classifying their expenses, some of these costs are included with Network Design. Site preparation work has been completed. | 39 | Merit ordered and received equipment, and the equipment has been placed in the field. Costs originally designed for this category have been placed in other categories resulting in being below budget. This category will be able to absorb overages from other areas. | 100 | Construction is near completion. Since construction began in late December 2011, Merit has had a large number of crews working across multiple segments each week. Merit is looking to complete construction in the following quarter. | 100 | Merit has managed the equipment deployment by ordering, receiving, and placing it as needed. Merit is currently at 241% of the budget in this category but with all equipment placed, there will be minimal spending remaining. | 100 | Testing is continuing across the network with almost all infrastructure completed. | 2014-02-26 14:50 | 2014-02-26 14:50 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570115 | 2010 | Q4 | Q4 - 2010 | 1079 | 2116 | TRUE | 0 | Since budget was approved at end of quarter, there wasn't enough time to complete expense reporting. | 0 | Fiscal Compliance and Project Management | Since budget was approved at end of quarter, there wasn't enough time to complete expense reporting. | 0 | See Since budget was approved at end of quarter, there wasn't enough time to complete expense reporting. | 0 | Since budget was approved at end of quarter, there wasn't enough time to complete expense reporting. | 0 | zero variance | 0 | Since budget was approved at end of quarter, there wasn't enough time to complete expense reporting. | 0 | na | 0 | na | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 2011-02-11 13:57 | 2011-02-11 13:57 | 7018 | 7018 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2011 | Q1 | Q1 - 2011 | 1961 | 2726 | TRUE | 1 | Overall, actual recorded federal and match spending for build is delayed while waiting for Finding of No Significant Impact. | 7 | Fiscal Compliance and Project Manager | We are waiting for invoices from subrecipients to be able to record expenses. | 84 | Total spending for assessment is not complete. Additional unplanned assessment will be needed as build proceeds. | 0 | Total spending for build is delayed waiting for Finding of No Significant Impact. Additional engineers will be utilized to ensure design completion. | 0 | na | 0 | Permitting process is 50% completed. We are waiting for invoices from subrecipients to be able to record expenses. | 0 | na | 0 | na | 0 | na | 0 | na | 0 | na | 2011-05-12 11:32 | 2011-05-12 11:32 | 7054 | 7054 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2011 | Q2 | Q2 - 2011 | 3147 | 3334 | TRUE | 4 | Overall, actual recorded federal and match spending for build was delayed while waiting for Finding of No Significant Impact. | 14 | Fiscal compliance and Project Manager | We are waiting for invoices from subrecipients to be able to record expenses. | 100 | Actual spending exceeds budget. Assessment is 95% complete. | 3 | Design activities could not start until after Finding of No Significant Impact was received in late May. | 0 | Spending is delayed until next quarter due to delay from Finding of No Significant Impact. | 0 | Majority of permitting and approval activities could not start until after Finding of No Significant Impact was received in late May. | 0 | na | 0 | na | 3 | With delay of Finding of No Significant Impact, actual network build did not start until end of June. | 0 | Spending is delayed until next quarter due to delay from Finding of No Significant Impact. | 0 | Purchase of network testing equipment was delayed while waiting for Finding of No Significant Impact. | 2011-08-17 11:49 | 2011-08-17 11:49 | 7054 | 7054 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2011 | Q3 | Q3 - 2011 | 4091 | 3889 | TRUE | 18 | Actual recorded federal and match spending for build are lower caused by build delays due to late receipt of the Finding of No Significant Impact. Extra construction crews have been working to get caught up with build. The related spending should occur in the next two quarters. | 25 | Fiscal compliance and Project Manager | We are expecting catch-up invoices from sub-recipients in the next quarter. | 100 | Actual spending exceeds budget. Assessment is 95% complete. | 8 | Design activity is now underway since we have started the build. See 2a above. | 100 | Activity is complete. | 58 | Permitting activities are occurring just ahead of the build. See 2a above. | 0 | na | 0 | na | 17 | See 2a above. | 0 | Now that build has started with receipt of Finding of No Significant Impact, one third of equipment has been ordered. Actual spending will occur next quarter. | 0 | Now that build has started with receipt of Finding of No Significant Impact, approximately half the testing equipment has been ordered. Actual spending will occur next quarter. | 2011-11-16 16:24 | 2011-11-16 16:24 | 7054 | 7054 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2011 | Q4 | Q4 - 2011 | 5275 | 4945 | TRUE | 42 | Actual recorded federal and match spending for build are lower caused by build delays due to late receipt of the Finding of No Significant Impact. Extra construction crews have been working to get caught up with build. The related spending should occur in the next quarter. | 32 | Fiscal and Project Management | Staff did not start in project as early as initially expected so expenses are not likely to equal budget. | 100 | Actual spending exceeds budget. Assessment is 98% complete. | 10 | Design activity is underway. Outside consultants have not been required to the extent originally planned. | 100 | Activity is complete. | 61 | Permitting activity is underway. See 2a above. | 0 | NA | 0 | NA | 40 | Construction is underway. See 2a above. | 41 | Now that construction is underway. Equipment orders for the Chippewa Valley area are now being created. Expense should occur next quarter. | 97 | Purchase of network testing equipment is complete. | 2012-02-27 09:43 | 2012-02-27 09:43 | 7054 | 7054 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2012 | Q1 | Q1 - 2012 | 5945 | 5572 | TRUE | 48 | Actual recorded federal and match spending for network build are lower caused by build delays due to late receipt of the Finding of No Significant Impact. Extra construction crews will be working this year to allow completion of fiber installation this calendar year. Related spending is finalized a quarter later. | 39 | Fiscal and Project Management | Staff expenses did not occur in project as early as anticipated so expenses are not likely to equal budget. | 100 | Actual spending exceeds budget. Initial assessment is complete. | 11 | Design activity is underway. Outside consultants have not been required to the extent originally planned. | 100 | Activity is complete. | 64 | Permitting activity is underway. See 2a above. | 0 | NA | 0 | NA | 47 | Construction is underway. See 2a above. | 44 | Installation of electronic equipment is underway and new equipment is being delivered. The related invoices will not be paid until next quarter. | 97 | Purchase of network testing equipment is complete. | 2012-05-07 16:02 | 2012-05-07 16:02 | 7054 | 7054 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2012 | Q2 | Q2 - 2012 | 7061 | 6158 | TRUE | 55 | Actual recorded federal and match spending for network build are lower caused by build delays due to late receipt of the Finding of No Significant Impact and environmental permitting delays in 2012. | 47 | Fiscal and Project Management | Staff expenses are not likely to meet budget. Early project expenses were not as high as originally planned. | 100 | Actual spending exceeds budget. Initial assessment is complete. | 25 | Design activity is underway. Full budget will not be spent since outside consultants were not utilized to the extent originally planned. | 100 | Activity is complete. | 64 | Permitting is underway. See 2a above. | 0 | NA | 0 | NA | 53 | Construction is underway. See 2a above. | 60 | Much of the new equipment purchases are on hold until tower installation occurs later this year. | 97 | Purchase of network testing equipment is complete. | 2012-08-14 14:46 | 2012-08-14 14:46 | 7054 | 7054 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2012 | Q3 | Q3 - 2012 | 7861 | 6635 | TRUE | 61 | Actual recorded federal and match spending for network build are lower caused by build delays due to late receipt of the Finding of No Significant Impact and environmental permitting delays in 2012. | 64 | Fiscal and Project Management | Staff expenses are not likely to meet budget. Project expenses at the start of project were not as high as originally planned. | 100 | Actual spending exceeds budget. Initial assessment is complete. | 27 | Design activity is underway. Full budget will not be spent since outside consultants were not utilized to the extent originally budgeted. | 100 | Activity is complete. | 71 | Permitting is underway. See 2a above. | 0 | NA | 0 | NA | 59 | Construction is underway. See 2a above. | 62 | Much of the new equipment purchases are on hold until tower installation occurs later this year. | 97 | Purchase of network testing equipment is complete. | 2012-11-14 09:35 | 2012-11-14 09:35 | 7110 | 7110 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2012 | Q4 | Q4 - 2012 | 8729 | 7529 | TRUE | 78 | Actual recorded federal and match spending for network build are lower caused by build delays due to late receipt of the Finding of No Significant Impact and environmental permitting delays in 2012. | 77 | Fiscal and Project Management | Staff expenses are not likely to meet budget. Project expenses at the start of project were not as high as originally planned. | 100 | Actual spending exceeds budget. Initial assessment is complete. | 29 | Design activity is complete. Full budget will not be spent since outside consultants were not utilized to the extent originally budgeted. | 100 | Activity is complete. | 74 | Permitting is underway. See 2a above. | 0 | NA | 0 | NA | 82 | Construction is underway. See 2a above. | 62 | Much of the new equipment purchases are on hold until tower installation occurs next quarter. | 97 | Purchase of network testing equipment is complete. | 2013-02-12 16:02 | 2013-02-12 16:02 | 7110 | 7110 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2013 | Q1 | Q1 - 2013 | 9623 | 8343 | TRUE | 84 | Actual recorded federal and match spending for network build are lower caused by delays due to late receipt of the Finding of No Significant Impact and environmental permitting delays in 2012. | 90 | Fiscal and project management | Staff expenses are not likely to meet budget. Project expenses at start of the project were not as high as originally planned. | 100 | Actual spending exceeds budget. Initial assessment is complete. | 31 | Design activity is complete. Full budget will not be spent since outside consultants were not utilized to the extent originally budgeted. | 100 | Activity is complete. | 74 | Permitting continues. See 2a above. | 0 | NA | 0 | NA | 88 | Limited construction continued this quarter. See 2a above. | 71 | Equipment purchases for towers is underway. Final purchases should occur next quarter. | 97 | Purchase of network testing equipment is complete. | 2013-05-07 15:08 | 2013-05-07 15:08 | 7110 | 7110 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2013 | Q2 | Q2 - 2013 | 10579 | 8946 | TRUE | 92 | Actual recorded federal and match spending for network build are lower caused by delays due to late receipt of the Finding of No Significant Impact at the start of the project, environmental permitting delays in 2012 and weather issues in 2013. | 99 | Fiscal and Project Management | Staff expenses are on target. | 100 | Actual spending exceeds budget. Initial assessment is complete. | 33 | Design activity is complete. Full budget will not be spent since outside consultants were not utilized to the extent originally budgeted. | 100 | Activity is complete. | 75 | Permitting continues. See 2a above. | 0 | NA | 0 | NA | 95 | Construction started in earnest this quarter. See 2a above. | 82 | Almost all equipment has been received. Final invoices will be paid next quarter. | 97 | Purchase of network testing equipment is complete. | 2013-08-14 12:40 | 2013-08-14 12:40 | 7110 | 7110 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2013 | Q3 | Q3 - 2013 | 11949 | 10120 | TRUE | 100 | Activity is complete. Actual recorded federal and match spending equals the grant amounts. | 100 | Fiscal and Project Management | Activity is complete. Staff expenses exceeded budget slightly. | 100 | Actual spending exceeds budget. Initial assessment is complete. | 100 | Design activity is complete. Full budget was not spent since outside consultants were not utilized to the extent originally budgeted. | 100 | Activity is complete. | 100 | Activity is complete. | 0 | NA | 0 | NA | 100 | Actual spending exceeds budget. Construction is complete. | 100 | All equipment has been installed. | 100 | Purchase of network testing equipment is complete. | 2014-03-17 11:43 | 2014-03-17 11:43 | 6687 | 6687 | University of Wisconsin System | TRUE
NT10BIX5570116 | 2010 | Q4 | Q4 - 2010 | 1343 | 2362 | TRUE | 3 | Based on total expenditures, only 1% of the funds were obligated. However, of the activities listed in the baseline report, four were completed by 12/31/2010, and the environmental assessment field work and agency consultation with the exception of the Bureau of Indian affairs was completed. The draft EA is on track for timely submission on January 31. The main route verification, POP location and initial POP design are done. Revised network maps and coordinating meetings with community anchor institutions and last mile providers have been held. The team held meetings with Windstream and ENMR regarding interconnect and infrastructure partnerships (route swaps), US Cable regarding infrastructure partnerships (route swaps), PNM regarding infrastructure partnerships (dark fiber) and pole attachments, and Cisco regarding equipment packages. The team did not develop and release RFP's for construction team, materials suppliers, and equipment vendors, as indicated on the baseline. The c | 6 | Project Management | The baseline report forecast 12%. The variance is due to time involved with finalizing contract terms with Project Management vendor, amount of effort relative to the EA process, and some budgetary savings from more efficient time management. | 75 | All field work was completed by 12/31/2010. Delays in some agency responses to this complex, mulit-agency, multi-jurisdiction project meant that final work on the draft document could not begin. Meetings were scheduled in January and the EA is on track for timely submittal. | 1 | Network design did not meet the baseline benchmark for two reasons. First, approval for the six month budget was not received until January. Although the engineering firm was under contract as of November 4, it was not clear that the project would be able to fully reimburse costs until the six month budget was approved. Second, the Environmental Assessment required more consultation with the engineering team than anticipated. Some route modifications were required to address issues that arose in the EA. Some changes were made to anchor institutions were made that required consultation among the partners, the EA team and the engineer. However, all key milestones are anticipated to be completed within the next quarter, including final engineering design, construction prints, pole review, materials and equipment specifications, in line with the baseline report. | 25 | None | 0 | None | 0 | None | 0 | None | 0 | None | 0 | None | 0 | None | 2011-02-23 15:17 | 2011-02-23 15:17 | 6052 | 6052 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2011 | Q1 | Q1 - 2011 | 1841 | 2664 | TRUE | 3 | Based on total expenditures, only 3.3% of federal funds were obligated. Of the 7 activities listed in the baseline report, 2 (the Environmental Assessment and public meeting) were completed by the end of the quarter, and 3 additional activities (90% engineering, permits and rights-of-way, and contractor selection) are substantially complete. Material procurement and site prep has not occurred as planned because a FONSI has not been issued on the project. Variances from the baseline are due to more time being required for the Environmental Assessment than expected, delays in receiving review comments on the Environmental Assessment, and delays in federal funding permission to spend federal funds (permission was not granted until January 2011). | 18 | Project Management | Variance in percent complete for project management is due to reasons stated in the Quarter 2 report and reiterated here. Additional time was required to finalize contract terms with the Project Management vendor, additional time was required for the Environmental Assessment, and the project realized some costs savings from more efficient time management. | 100 | The draft Environmental Assessment (EA) was submitted on January 27, 2011, in advance of the January 30 deadline. We received comments back from the agency on March 2, 2011 and submitted our revisions to the EA on March 28, 2011. | 45 | 60% engineering design was completed within the quarter (although only 45% of expenditures have been made), fulfilling the 30% and 60% benchmarks. 90% design was not reached due to reasons identified in the Quarter 2 Performance Progress Report, and reiterated here. While the engineering firm was on contract as of November 4, 2010, the six-month budget was not approved until January 2011. As a result, NCNMEDD was unable to pay for engineering services for two months. Also, the Environmental Assessment required more consultation with the engineering team than anticipated, including route modifications to address issues in the EA. | 75 | Rights-of-way through tribal lands were established through the Joint Powers Agreement signed by the project partners in 2010. The Bureau of Indian Affairs reviewed the JPA in Quarter 3, and determined that no BIA rights-of-way or permits will be required. The project manager has met with the New Mexico Department of Transportation (NMDOT) and is preparing rights-of-way applications for the underground portions of the project which will be installed in NMDOT right-of-way. Variance from the baseline is due to the NMDOT permitting process, which requires that a separate permit be submitted for every 90 degree turn in the project. Also, NMDOT does not maintain records of utility locations within its rights-of-way, requiring the project team to undertake independent due diligence on this issue. A right-of-way permit has been submitted to and is under review by the Bureau of Land Management (BLM). The US Department of Energy (DOE) is currently evaluating right-of-way permit options through | 75 | Minor revisions to Jemez Mountains Electric Cooperative's (JMEC) pole attachment agreement have been submitted and are under review by JMEC. Variance from the baseline is due to delays in receiving final approval from these agencies. Approval is reasonably expected in Quarter 4. Pole attachments to DOE infrastructure will be addressed through the agreement referenced in 2d. Construction on BLM lands is covered through the right-of-way permit referenced in 2d. | 0 | The baseline anticipated site preparation for the primary POP and renovations for the secondary POP. Site preparation was not possible in Quarter 3 because a FONSI has not been issued for the project to date. Also, a contractor for the project was not selected in Quarter 3, although the procurement process was fully implemented. Negotiations with finalists are currently in process. The secondary POP site was inspected for renovations needed and design requirements. | 0 | The baseline anticipated procurement of OSP materials and network equipment. Equipment procurement was not possible in Quarter 3 because a FONSI has not been issued for the project to date. Also, a equipment reseller for the project was not selected in Quarter 3, although significant due-diligence was conducted with a vendor on an existing State of New Mexico Purchase Agreement. The network architecture, equipment specifications, bill of materials, and equipment budget is 75% complete. | 0 | None | 0 | None | 0 | None | 2011-05-02 12:43 | 2011-05-02 12:43 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2011 | Q2 | Q2 - 2011 | 2547 | 3022 | TRUE | 7 | Based on total expenditures, 7% of project funds were obligated. Deviances from the baseline are described below, and are associated with delays in receiving the FONSI, which has placed construction expenditures one quarter behind schedule. | 32 | Project Management | Project management work continued as anticipated, directing the procurement processes, construction prep, and general oversight. | 100 | A Finding of No Significant Impact (FONSI) was issued on June 20, 2011. Completion of this milestone was anticipated in Quarter 3. While the Environmental Assessment was completed on time, the federal review, federal comments, and revisions to the EA took longer than expected. | 100 | All engineering design was completed in this quarter as projected in the baseline. | 90 | Rights of way through tribal lands were established through the Joint Powers Agreement signed in Q4 2010. The Bureau of Land Management (BLM) has issued its right-of-way permit for the project. The New Mexico Department of Transportation (NM DOT) has issued 95% of the permits needed for the underground portion of the project, with the remaining 5% in process. There are an additional 86 overhead crossings to be permitted through NM DOT, several of which are already in process. However, the total distance of the aerial crossings represent a very small portion of the overall project. An additional right-of-way amendment is required with the National Nuclear Security Administration (NNSA), for approximately a 5 mile span that crosses San Ildefonso Pueblo land and currently only accommodates electric utility infrastructure. The NNSA permit and the remaining NMDOT permits account for the 10% variance from the baseline, which projected 100% completion of this milestone in this quarter. | 90 | Pole attachment agreements are in place with Jemez Mountains Electric Cooperative and the Public Service Company of New Mexico, and all tribal construction permits have been obtained. Local government construction permits have been submitted, but are still in process. Local government permits account for the variance from the baseline, which projected 100% completion of this milestone in this quarter. | 14 | Pole attachment agreements are in place with Jemez Mountains Electric Cooperative and the Public Service Company of New Mexico, and all tribal construction permits have been obtained. Local government construction permits have been submitted, but are still in process. Local government permits account for the variance from the baseline, which projected 100% completion of this milestone in this quarter. | 0 | The network architecture, equipment specifications, bill of materials, and budget are complete, and a vendor is now under contract through the State of New Mexico Purchase Agreement. The baseline anticipated procurement of OSP materials and network equipment in Quarter 3. Procurement has not occurred to date because equipment has not been needed due to delays with the the FONSI. | 1 | Network construction began on June 27, 2011, immediately following issuance of the FONSI on June 20. Activities included directional drilling, conduit placement, internal building work, and POP prep. The baseline anticipated 36% completion of construction in this quarter, which was clearly not possible given delays with the FONSI. | 0 | N/A | 0 | N/A | 2011-07-27 12:42 | 2011-07-27 12:42 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2011 | Q3 | Q3 - 2011 | 4207 | 3952 | TRUE | 35 | Based on total expenditures, 35% of project funds were obligated through the end of Q3 2011. Deviations from the baseline are described below and are associated with delays in receiving the FONSI, which has placed most construction activities about 3 months behind schedule. However, construction has ramped up considerably since the last quarter--from 1% to 27% complete. Also, the project is on track for completion well before the three-year time frame, with construction slated to conclude in spring/early summer 2012. | 43 | Project Management | Project management work continued as anticipated, providing construction management, procurement, and general oversight. | 100 | A Finding of No Significant Impact (FONSI) was issued on June 20, 2011. Completion of this milestone was anticipated in Quarter 3. While the Environmental Assessment was completed on time, the federal review, federal comments and revisions to the EA took longer than expected. | 100 | All engineering design was completed in Quarter 4 as projected in the baseline. | 95 | There are a few outstanding permits with NM DOT, the National Nuclear Security Administration (NNSA), and San Ildefonso Pueblo which account for the remaining 5%. This is a 5% variance from the baseline, which projected 100% completion. It is anticipated that the ROW permits will be 100% complete by the end of the upcoming reporting period. However, the outstanding permits have not held up construction activities as crews are currently assigned to permitted areas. | 95 | Local government construction permits are submitted and approved within 2-3 days as the construction crews advance closer to specific work sites. There have been no delays using this approach and none are anticipated, as the local governments issuing the permits are all partners in the project. We will continue on this process throughout the remainder of the project. This is a 5% variance from the baseline, which projected 100% completion. | 98 | The only remaining site prep work is being conducted at our Los Alamos County POP location, where an electrical load assessment is underway. This assessment will be completed during Q4 2011, concluding the site prep activities. Therefore, a 2% variance is reserved. | 98 | All major equipment procurement was completed during the current reporting period. However, it is possible that some smaller items, such as additional servers or CPE will be ordered in Q4 2011. Therefore, a 2% variance is reserved. | 27 | Network construction began on June 27, 2011, immediately following issuance of the FONSI on June 20. Activities in the current reporting period include directional drilling, conduit placement, innerduct placement in existing conduit, internal building work, make ready (pole replacements, anchor setting, framing, etc), aerial fiber attachment, and setting the POP foundations. The baseline anticipated 62% completion of the network in this quarter; however, much progress has been made ramping up after the FONSI delays. | 0 | N/A. Equipment deployment will begin in Q4 2011. | 0 | N/A. Configuration testing on network equipment was conducted in a lab environment, but testing of the outside plant has not commenced yet. | 2011-11-21 23:38 | 2011-11-21 23:38 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2011 | Q4 | Q4 - 2011 | 5217 | 4885 | TRUE | 55 | Based on total expenditures, 55% of the project funds were obligated through the end of Q4 2011. Deviations from the baseline are described below and are associated with initial delays in receiving the FONSI, and recent delays involving make-ready. Nevertheless, construction activities have ramped up from 27% to 51% in the last quarter. Also, the project is on track for completion well before the three-year time frame, with construction slated to conclude in fall 2012. | 49 | Project Management | Project management work continued as anticipated, providing construction management, procurement, and general oversight. Baseline forecasted 60% completion in project Q4 2011. The variance is mainly due to identified project savings and greater efficiencies. | 100 | A Finding of No Significant Impact (FONSI) was issued on June 20, 2011. Completion of this milestone was anticipated in Quarter 3, Year 1. While the Environmental Assessment was completed on time, the federal review, federal comments and revisions to the EA took longer than expected. | 100 | All engineering design was completed in project Q4 Y1 as projected in the baseline. | 97 | There are a small number of outstanding permits with NM DOT, US DOE, and San Ildefonso Pueblo which account for the remaining 3%. This is a 3% variance from the baseline, which projected 100% completion. It is anticipated that the ROW permits will be 100% complete by the end of the upcoming reporting period. However, the outstanding permits have not held up construction activities as crews are currently assigned to permitted areas. | 97 | Local government construction permits are submitted and approved within 2-3 days as the construction crews advance closer to specific work sites. There have been no delays using this approach and none are anticipated, as the local governments issuing the permits are all partners in the project. We will continue on this process throughout the remainder of the project. This is a 3% variance from the baseline, which projected 100% completion. | 98 | The only remaining site prep work is being conducted at our Los Alamos County POP location, where an electrical load assessment is still underway. This assessment was to be completed during project Q4 2011 but will carry over into project Q1 2012. Therefore, a 2% variance is reserved. This is not holding up project completion. | 98 | All major equipment procurement was completed during Q3 2011. However, it is possible that some smaller items, such as additional CPE will be ordered in future reporting periods. Therefore, a 2% variance is reserved. This is not holding up project completion. | 51 | Network construction began on June 27, 2011, immediately following issuance of the FONSI on June 20. Activities in the current reporting period include directional drilling, conduit placement, innerduct placement in existing conduit, internal building work, make ready (pole replacements, anchor setting, framing, etc), aerial fiber attachment, underground fiber installation, and setting the POP buildings. The baseline anticipated 82% completion of the network in project Q4 2011. Yet, much progress has been made ramping up after FONSI delays. | 0 | Equipment deployment will begin in Q1 2012. Although baseline assumed 94% completion during Q4 2011, this will not impact project completion and equipment is pre-stagged/pre-configured and ready for installation. | 0 | Configuration testing on network equipment was conducted in a lab environment, but testing of the outside plant has not commenced yet. Although baseline assumed 40% completion of network testing, this is not impacting project delivery. | 2012-02-23 15:25 | 2012-02-23 15:25 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2012 | Q1 | Q1 - 2012 | 6097 | 5651 | TRUE | 60 | Based on total expenditures, 60% of project funds were obligated through the end of Q1 2012. Deviations from the baseline are described below and are associated with initial delays in receiving the FONSI and recent delays involving make-ready. Significant pole replacement activity occurred in Q1 2012, resulting in lower fiber deployment and construction progress for this quarter. | 63 | Project Management | Project management work continued as anticipated, providing construction management, procurement, and general oversight. Baseline forecasted 66% completion in Q1 2012. | 100 | A Finding of No Significant Impact (FONSI) was issued on June 20, 2011. Completion of this milestone was anticipated in Q1 2011. While the Environmental Assessment was completed on time, the federal review, federal comments and revisions to the EA took longer than expected. | 100 | All engineering design was completed in Q2 2011 as projected in the baseline. | 98 | REDI Net has yet to receive a ROW permit from the Pueblo de San Ildefonso. | 100 | All construction permits have been obtained. Please note that some additional permits will be required as a result of the EA Addendum, once approved. | 98 | Site prep is complete for all POP locations, although Certificates of Occupancy are still pending. Please note that changes to the Los Alamos POP location will be requested as part of the EA Addendum. If approved, these changes will require additional site prep work. | 98 | All major equipment procurement was completed during Q3 2011. However, it is possible that some smaller items, such as additional CPE or subscriber aggregation equipment will be ordered in future reporting periods. Therefore, a 2% variance is reserved. This is not holding up project completion. | 54 | Network construction began on June 27, 2011, immediately following issuance of the FONSI on June 20. Activities in the current reporting period include directional drilling, conduit placement, innerduct placement in existing conduit, internal building work, make ready (pole replacements, anchor setting, framing, etc), aerial fiber attachment, underground fiber installation, and POP building preparation. The baseline anticipated 100% completion of the network in Q1 2012. Deviations from the baseline are associated with initial delays in receiving the FONSI and recent delays involving make-ready. Significant pole replacement activity occurred in Q1 2012, resulting in lower fiber deployment and construction progress for this quarter. | 5 | Equipment deployment began during the current reporting period, reflective of the fiber testing completion percentage. Although the baseline assumed 100% completion during Q1 2012, equipment deployment itself will not impact overall project delivery, as it is pre-staged and ready for installation upon completion of fiber testing. | 5 | Configuration testing on network equipment was conducted in a lab environment and testing of the outside plant commenced during the current reporting period. Although baseline assumed 50% completion of network testing in Q1 2012, this is not impacting the project. | 2012-05-15 13:51 | 2012-05-15 13:51 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2012 | Q2 | Q2 - 2012 | 7251 | 6253 | TRUE | 79 | Based on total expenditures, 79% of project funds were obligated through the end of Q2 2012. Deviations from the baseline are described below and are associated with initial delays in receiving the FONSI and recent delays involving make-ready. | 71 | Project Management | Project management work continued as planned, providing construction management, procurement, and general oversight. In-line between previous quarter PPR forecast of 70% completion and 72% in original baseline. | 100 | A Finding of No Significant Impact (FONSI) was issued on June 20, 2011. Completion of this milestone was anticipated in Q1 2011. While the Environmental Assessment was completed on time, the federal review, federal comments and revisions to the EA took longer than expected. | 100 | All engineering design was completed in Q2 2011 as projected in the baseline. | 99 | ROW negotiations with the Pueblo de San Ildefonso will not be resolved during the time constraints of the BTOP grant. Therefore, REDI Net has submitted route changes for an alternative route to connect Los Alamos County. Other route changes proposed in the EA Checklist involve new ROW permits with the Bureau of Land Management (BLM) and New Mexico State Land Office. Both of those ROW permits are in process. | 100 | All construction permits have been obtained. Please note that some additional permits will be required as a result of the EA Addendum, once approved. | 98 | Site prep is complete for all POP locations, although Certificates of Occupancy are still pending. Please note that changes to the Los Alamos POP location will be requested as part of the EA Addendum. If approved, these changes will require additional site prep work. | 100 | All major equipment procurement was completed during project Q3 2011. A smaller order was placed during the current reporting period, completing this aspect of the project. | 69 | Network construction began on June 27, 2011, immediately following issuance of the FONSI on June 20. Activities in the current reporting period include directional drilling, conduit placement, innerduct placement in existing conduit, internal building work, make ready (pole replacements, anchor setting, framing, etc), aerial fiber attachment, underground fiber installation, and POP activities. The baseline anticipated 100% completion of the network in project Q1 2012. Deviations from the baseline are associated with initial delays in receiving the FONSI and recent delays involving make-ready. The approval of route changes submitted in the EA Checklist will be critical for overall project completion. | 50 | Equipment was deployed at the primary POP location and 55 CAIs during the current reporting period. This is reflective of the two-phase approach for turning up network services. Although baseline assumed 100% completion during project Q1 2012, equipment deployment itself will not impact overall project delivery, as it is pre-staged and ready for installation upon completion of fiber testing. | 57 | Testing was completed on approximately 80 of the 140 network miles to be deployed. This is closely in-line with the original baseline, which assumed 60% completion and is not impacting project delivery. | 2012-08-27 13:59 | 2012-08-27 13:59 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2012 | Q3 | Q3 - 2012 | 7909 | 6659 | TRUE | 85 | Based on total expenditures, 85% of project funds were obligated through the end of Q3 2012. Deviations from the baseline are described below and are associated with initial delays in receiving the FONSI and recent delays involving make-ready and the EA Addendum. | 79 | Project Management | Project management work continued as planned, providing construction management, procurement, and general oversight. In-line with previous forecast and original baseline. | 100 | A Finding of No Significant Impact (FONSI) was issued on June 20, 2011. Completion of this milestone was anticipated in Q1 2011. While the Environmental Assessment was completed on time, the federal review, federal comments and revisions to the EA took longer than expected. EA Addendum approved on 10/5/2012. | 100 | All engineering design was completed Q2 2011 as projected in baseline. | 100 | ROW permits with the US Bureau of Land Management (BLM) and New Mexico State Land Office we granted within the current reporting period. | 100 | EA Addendum required additional construction permits with the US Dept of Energy and Los Alamos County, NM, which are in process. | 100 | Site prep was completed during the current reporting period. The Los Alamos County POP was the last remaining site requiring prep work. | 100 | Major equipment procurement was completed during Q3 2011, with smaller supplemental orders during Q2 2012. | 78 | Network construction began on June 27, 2011, immediately following issuance of the FONSI on June 20. Activities in the current reporting period include directional drilling, conduit placement, innerduct placement in existing conduit, internal building work, make ready (pole replacements, anchor setting, framing, etc), aerial fiber attachment, underground fiber installation, and POP activities. The original baseline anticipated 100% completion of the network in Q1 2012. Deviations from the baseline are associated with initial delays in receiving the FONSI, make-ready challenges, and approval of the EA Addendum. | 90 | Equipment installed at the primary POP location and 119 CAIs. 4 CAIs are pending equipment installation, along with the secondary POP. Equipment deployment itself will not impact overall project delivery, as it is pre-staged and ready for installation upon completion of fiber testing. | 70 | Testing was completed on approximately 99 of the 142 new network miles to be deployed, in-line with the original baseline. | 2012-11-15 19:24 | 2012-11-15 19:24 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2012 | Q4 | Q4 - 2012 | 9033 | 7803 | TRUE | 90 | Most construction and development per below description | 86 | Project Management | Project management work continued as planned, providing construction management, procurement, and general oversight. Closely in-line with previous forecast and original baseline. | 100 | A Finding of No Significant Impact (FONSI) was issued on June 20, 2011. Completion of this milestone was anticipated in Q1 2011. While the Environmental Assessment was completed on time, the federal review, federal comments and revisions to the EA took longer than expected. EA Addendum approved on 10/5/2012. | 100 | All engineering design was completed Q2 2011 as projected in baseline. | 100 | ROW permits with the US Bureau of Land Management (BLM) and New Mexico State Land Office we granted within the current reporting period. | 100 | EA Addendum required additional construction permits with the US Dept of Energy and Los Alamos County, NM, which are in process. | 100 | Site prep was completed during the current reporting period. The Los Alamos County POP was the last remaining site requiring prep work. | 100 | Major equipment procurement was completed during Q3 2011, with smaller supplemental orders during Q2-Q3 2012. | 82 | Network construction began on June 27, 2011, immediately following issuance of the FONSI on June 20. Activities in the current reporting period include drilling, conduit placement, innerduct placement in existing conduit, internal building work, aerial fiber attachment, underground fiber installation, and POP activities. The original baseline anticipated 100% completion of the network in calendar Q1 2012. Deviations are associated with initial delays in receiving the FONSI, pole replacement requirements, and approval of the EA Addendum. | 100 | Equipment installation was completed during the current reporting period. Original baseline assumed 100% completion during calendar Q1 2012, variance reflective of staged deployment based on route changes. | 84 | Testing was completed on ~119 miles of the 142 new network miles to be deployed, ahead of the original baseline of 80% | 2013-02-27 16:17 | 2013-02-27 16:17 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2013 | Q1 | Q1 - 2013 | 10045 | 8577 | TRUE | 94 | Most construction and development per description below | 90 | Project Management | Project management work continued as planned, providing construction management, procurement, and general oversight. Equal to baseline. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 86 | Network construction began on June 27, 2011, immediately following issuance of the FONSI on June 20. Activities in the current reporting period include drilling, conduit placement, innerduct placement in existing conduit, internal building work, aerial fiber attachment, underground fiber installation, and POP activities. The original baseline anticipated 100% completion of the network in calendar Q1 2012. Variance is associated with initial delays in receiving the FONSI, pole replacement requirements, and approval of the EA Addendum. | 100 | Complete | 93 | Testing completed on ~132.5 miles of the ~142.6 new miles to be built, ahead of the original baseline of 90%. Original baseline assumed ~149 new miles to be built. The variance between 142.6 and 149 miles is associated with adjustments made via the approved route changes. | 2013-06-03 11:49 | 2013-06-03 11:49 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2013 | Q2 | Q2 - 2013 | 10527 | 8917 | TRUE | 98 | See descriptions below. Total overall based on actual budget and project activities | 94 | Project Management | Project management work continued as planned, providing construction management, procurement, CAI/LMP support, and general oversight. Baseline assumed 100% completion during the reporting period. Remaining work anticipated to be completed in final month of project. Percentage complete based on project activities and reference to budget | 100 | Complete based on project activities | 100 | Complete based on project activities | 100 | Complete based on project activities | 100 | Complete based on project activities | 100 | Complete based on project activities | 100 | Complete based on project activities | 98 | Network construction began on June 27, 2011, immediately following issuance of the FONSI on June 20. Activities in the current reporting period include underground conduit/fiber placement, aerial fiber installation, internal building work, and POP activities. The original baseline anticipated 100% completion of the network in calendar Q1 2012. Variance is associated with initial delays in receiving the FONSI, pole replacement requirements, and approval of the EA Addendum. Baseline assumed 100% completion during the reporting period. Remaining work anticipated to be completed in final month of project. Percentage complete based on project activities and reference to budget | 100 | Complete based on project activities | 96 | Testing completed on ~137.3 miles of the ~142.6 new miles to be built. Original baseline assumed ~149 new miles to be built. The variance between 142.6 and 149 miles is associated with adjustments made via the approved route changes. Baseline assumed 100% completion during the reporting period. Remaining work anticipated to be completed in final month of project. Percentage complete based on project activities. | 2013-08-08 15:14 | 2013-08-08 15:14 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2013 | Q3 | Q3 - 2013 | 12057 | 10217 | TRUE | 100 | The overall project is completed at 100%, The actual spent was 102.95% of the original planned budget as NCNMEDD made additional match contributions. | 100 | Project Management | Based on actual budget and project activities | 100 | Based on actual budget and project activities | 100 | Based on actual budget and project activities | 100 | Based on actual budget and project activities | 100 | Based on actual budget and project activities | 100 | Based on actual budget and project activities | 100 | Based on actual budget and project activities | 100 | Based on actual budget and project activities | 100 | Based on actual budget and project activities | 100 | Based on actual budget and project activities | 2014-04-22 12:23 | 2014-04-22 12:23 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570117 | 2010 | Q4 | Q4 - 2010 | 1317 | 2342 | TRUE | 3 | NA | 0 |  | NA | 25 | NA | 40 |  | 30 | In our baseline report we showed 40% complete by the end of the 4th quarter. We are behind in permitting based upon our decision to rebid fiber installation contract. We should be on target by the end of the first quarter of 2011. | 30 | In our baseline report we showed 40% complete by the end of the 4th quarter. We are behind in permitting based upon our decision to rebid fiber installation contract. We should be on target by the end of the first quarter of 2011. | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 2011-02-22 20:48 | 2011-02-22 20:48 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2011 | Q1 | Q1 - 2011 | 2035 | 2763 | TRUE | 3 | In our baseline we showed 18% complete by the end of the quarter. We are behind due to issues with the bill H3508 and how it could impact our project. We are also behind due to fiber installation contractor being unable to obtain performance bond. We hope to be on target by the end of the second quarter of 2011. | 0 |  | na | 90 | In our baseline we showed 100% complete by the end of the quarter. We are behind due to issues with the bill H3508 and how it could impact our project. We have submitted our Assessment and will be anticipating our FONSI in the next quarter. We hope to be on target by the end of the second quarter of 2011. | 50 | In our baseline we showed 70% complete by the end of the quarter. We are behind due to issues with the bill H3508 and how it could impact our project. We hope to be on target by the end of the second quarter of 2011. | 50 | In our baseline we showed 70% complete by the end of the quarter. We are behind due to issues with the bill H3508 and how it could impact our project. We are also behind due to fiber installation contractor being unable to obtain performance bond. The fiber installation contractor will be completing the drawings of the right of ways for the SCDOT. We hope to be on target by the end of the second quarter of 2011. | 50 | In our baseline we showed 70% complete by the end of the quarter. We are behind due to issues with the bill H3508 and how it could impact our project. We are also behind due to fiber installation contractor being unable to obtain performance bond. We hope to be on target by the end of the second quarter of 2011. | 0 | na | 10 | In our baseline we showed 20% complete by the end of the quarter. We are behind due to issues with the bill H3508 and how it could impact our project. We are also behind due to fiber installation contractor being unable to obtain performance bond. We hope to be on target by the end of the second quarter of 2011. | 0 | In our baseline we showed 10% complete by the end of the quarter. We are behind due to issues with the bill H3508 and how it could impact our project. We are also behind due to fiber installation contractor being unable to obtain performance bond. We hope to be on target by the end of the second quarter of 2011. | 0 | In our baseline we showed 20% complete by the end of the quarter. We are behind due to issues with the bill H3508 and how it could impact our project. We are also behind due to fiber installation contractor being unable to obtain performance bond. We hope to be on target by the end of the second quarter of 2011. | 0 | In our baseline we showed 10% complete by the end of the quarter. We are behind due to issues with the bill H3508 and how it could impact our project. We are also behind due to fiber installation contractor being unable to obtain performance bond. We hope to be on target by the end of the second quarter of 2011. | 2011-05-16 10:39 | 2011-05-16 10:39 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2011 | Q2 | Q2 - 2011 | 3259 | 3392 | TRUE | 3 | We are behind schedule due to the fiber installation RFP being released again. We hope to be on target at the end of the third quarter of 2011. | 0 |  | na | 100 | na | 60 | We are behind schedule due to the fiber installation RFP being released again. We took Engineering and Permitting out of the RFP. In doing this we had to make some changes to the network. We hope to be on target at the end of the third quarter of 2011. | 50 | We are behind schedule due to the fiber installation RFP being released again. We took Engineering and Permitting out of the RFP. During this time we did not have a contractor working on the permits/right of way drawings. We hope to be on target at the end of the third quarter of 2011. | 50 | We are behind schedule due to the fiber installation RFP being released again. We took Engineering and Permitting out of the RFP. During this time we did not have a contractor working on the permits/right of way drawings. We hope to be on target at the end of the third quarter of 2011. | 0 | na | 10 | We are behind schedule due to the fiber installation RFP being released again. During this time of uncertainty we did not purchase any equipment. A purchase order has been issued for the fiber. We were waiting on selection of fiber installer before purchasing a large amount of fiber. We hope to be on target at the end of the third quarter of 2011. | 0 | We are behind schedule due to the fiber installation RFP being released again. We hope to be on target at the end of the third quarter of 2011. | 0 | We are behind schedule due to the fiber installation RFP being released again. We hope to be on target at the end of the third quarter of 2011. | 0 | We are behind schedule due to the fiber installation RFP being released again. We hope to be on target at the end of the third quarter of 2011. | 2011-08-22 14:17 | 2011-08-22 14:17 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2011 | Q3 | Q3 - 2011 | 4193 | 3945 | TRUE | 7 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. | 0 |  | n/a | 100 | na | 70 | We are still a little behind with the network design. In our decision to break the project up into phases, we have had to make a few changes to the network. We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. | 60 | In the decision to break up the project into phases we had to change our focus to phase I only. We are using South Carolina Department of right of ways for our installation. We are acquiring the necessary permits as soon as we turn them into the SCDOT. | 60 | In the decision to break up the project into phases we had to change our focus to phase I only. We are using South Carolina Department of right of ways for our installation. We are acquiring the necessary permits as soon as we turn them into the SCDOT. We are behind schedule due to the fiber installation RFP being released again. We took Engineering and Permitting out of the RFP. During this time we did not have a contractor working on the permits/right of way drawings. | 0 | n/a | 35 | With the changing of phases and our decision to rework the network we have not purchased a lot of equipment. Once the three Network Opertion Centers had been determined the equipment procurement should be on track by the 1st quarter of 2012. | 0 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. With the changing of phases and our decision to rework the network we have not purchased a lot of equipment. | 0 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. With the changing of phases and our decision to rework the network we have not purchased a lot of equipment. | 0 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. With the changing of phases and our decision to rework the network we have not purchased a lot of equipment. | 2011-11-21 16:28 | 2011-11-21 16:28 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2011 | Q4 | Q4 - 2011 | 5389 | 5068 | TRUE | 21 | We are behind schedule. This will be an ongoing problem since we had to re-release the RFP during the 2nd quarter of 2011. We are beginning to receive large shipments of fiber that will help move the project status forward. Railroad permits have taken a little larger than anticipated. The team has worked closely with them and hopefully will have all of the permits needed soon. | 0 |  | na | 100 | na | 95 | na | 70 | We are still utilizing SCDOT right of ways. We are still a little behind due to RFP being released the second time. The railroad permits have delayed us some. The team has been working with them closely to get on track. | 70 | Phase II and III permits and drawings are in the process of being completed. We are working diligently to get all the permits and approvals complete. | 0 | na | 60 | na | 35 | We have received a lot of the equipment but have not set up the network operation centers. After 1st quarter of 2012 we should be on track. | 0 | We are still in the process of setting up our network operation centers. we should have fiber and equipment functioning in the 1st quarter of 2012. | 1 | We are proofing conduit before fiber in installed. Due to the entire project being behind schedule the network testing is not where it should be. | 2012-02-29 11:45 | 2012-02-29 11:45 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2012 | Q1 | Q1 - 2012 | 6049 | 5624 | TRUE | 41 | The broadband team is working very hard to meet the set goals. We have had a few right of way issues this quarter, but all are resolved. The H3508 bill has also delayed our project. The team has spent many days trying to work through the proposed language and how it effects our project which in turn took valuable resource time away from project. | 0 |  | NA | 100 | NA | 95 | NA | 95 | NA | 80 | Due to right of way issues, the permits have been delayed. Should been near completion by 2nd quarter of 2012. | 0 | NA | 70 | NA | 40 | With the above mentioned delays the network build will also be delayed. At this time we presently have 114 miles of conduit and 70 miles of fiber installed. | 30 | We are in the process of receiving most of our electronics. There are a few remaining network electronic items to order and receive. | 10 | Network testing is dependent on construction and electronics. The progress on network testing will be higher next quarter. | 2012-05-14 09:09 | 2012-05-14 09:09 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2012 | Q2 | Q2 - 2012 | 7211 | 6233 | TRUE | 64 | The broadband team has been working very hard to meet our baseline goals. We spent a good bit of time focusing on the House bill again this quarter. A lot of progress has been made. The team will continue to work hard to meet all goals set forth. | 0 |  | na | 100 | na | 95 | na | 95 | na | 95 | na | 0 | na | 80 | na | 65 | With all of our delays network build has been delayed. Hope to be closer to our base line milestone next quarter. | 65 | We continue to have equipment being shipped for our project. A few back orders have caused some delay. Hope to be closer to our base line milestone next quarter. | 65 | na | 2012-08-22 16:01 | 2012-08-22 16:01 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2012 | Q3 | Q3 - 2012 | 8045 | 6729 | TRUE | 72 | The broadband team continues to work hard to meet our goals. The team is getting closer to the baseline goals each quarter. Will continue to work hard to meet all goals set forth. | 0 | true | na | 100 | na | 95 | na | 95 | na | 95 | na | 0 | na | 85 | We have equipment being shipped weekly. Hope to be closer to base line milestone next quarter. | 70 | We have equipment being shipped weekly. Hope to be closer to base line milestone next quarter. | 70 | We have equipment being shipped weekly. Hope to be closer to base line milestone next quarter. | 70 | We have equipment being shipped weekly. Hope to be closer to base line milestone next quarter. | 2012-11-26 15:09 | 2012-11-26 15:09 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2012 | Q4 | Q4 - 2012 | 9121 | 7894 | TRUE | 90 | Very close to our baseline goal. The team continues to work hard to meet the stated goals. | 0 |  | na | 100 | na | 100 | na | 95 | na | 95 | na | 0 | na | 91 | Should be at baseline goal first quarter of 2013. | 85 | Should be at baseline goal first quarter of 2013. | 85 | Should be at baseline goal first quarter of 2013. | 80 | Should be at baseline goal first quarter of 2013. | 2013-03-04 14:02 | 2013-03-04 14:02 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2013 | Q1 | Q1 - 2013 | 9697 | 8382 | TRUE | 96 | Almost there...The team continues to work hard to meet the goals set. | 0 |  | na | 100 | na | 100 | na | 100 | na | 100 | na | 0 | na | 99 | Almost there...The team continues to work hard to meet the goals set. | 99 | Almost there...The team continues to work hard to meet the goals set. | 99 | Almost there...The team continues to work hard to meet the goals set. | 99 | Almost there...The team continues to work hard to meet the goals set. | 2013-05-13 14:57 | 2013-05-13 14:57 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2013 | Q2 | Q2 - 2013 | 10655 | 8988 | TRUE | 98 | Very little left to be done. Will be complete by end of 3rd quarter. | 0 |  | na | 100 | na | 100 | na | 100 | na | 100 | na | 0 | na | 100 | na | 100 | na | 99 | Very little left to be done. Will be complete by end of 3rd quarter. | 99 | Very little left to be done. Will be complete by end of 3rd quarter. | 2013-08-20 12:18 | 2013-08-20 12:18 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2013 | Q3 | Q3 - 2013 | 11509 | 9635 | TRUE | 100 | na | 0 |  | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 0 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 2013-12-20 09:16 | 2013-12-20 09:16 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570118 | 2010 | Q4 | Q4 - 2010 | 793 | 1830 | TRUE | 10 | Engineering delayed slightly due to initial engineering firm withdrawal; new firm is ahead of projected schedule. | 0 | N/A | N/A | 25 | Environmental delayed due to engineering re-assignment, but is projected to be completed in current quarter | 25 | Design is on schedule; bid package due this quarter | 25 | Acquisition is on schedule | 25 | Acquisition is on schedule | 0 | Preparation is on schedule; projected for next quarter | 0 | Acquisition is on schedule; projected for next quarter | 0 | Build is on schedule, bid package due this quarter | 0 | Deployment is on schedule; projected in two quarters | 0 | Testing is on schedule; projected in three quarters | 2011-01-28 15:31 | 2011-01-28 15:31 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2011 | Q1 | Q1 - 2011 | 2341 | 2916 | TRUE | 15 | Engineering and environmental assessment delayed due to initial engineering firm withdrawal; new firm completed major design and environmental's this quarter. The project is shown as 15% complete based on the all initial environmental, engineering, and network design being completed with bidding during the second quarter. Although expenditures are less than 5% at this time, the complex issues involved in the initial design and engineering constitute a very significant part of the overall project. | 0 |  | N/A | 90 | Environmental delayed due to engineering re-assignment; new firm substantially completed draft environmental assessment; draft assessment has been submitted for BTOP review | 90 | Engineering design is substantially complete with bid package projected for 05/15/2011. | 80 | Acquisition is substantially complete at end of quarter | 80 | Acquisition is substantially complete at end of quarter | 20 | Co-location and regeneration sites confirmed with engineering staking of the sites; awaiting bid package for contractor construction | 0 | Acquisition is awaiting construction bid package next quarter | 0 | Build is on schedule | 0 | Deployment is on schedule | 0 | Testing is on schedule | 2011-05-26 12:50 | 2011-05-26 12:50 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2011 | Q2 | Q2 - 2011 | 3209 | 3366 | TRUE | 20 | Engineering and environmental assessment delayed due to initial engineering firm withdrawal; new firm completed major design and environmental's this quarter. The project is shown as 20% complete based on the all initial environmental, engineering, and network design being completed with award of construction contracts during the quarter. Expenditures are less than 5% at this time with these monies expended for the initial design, engineering, and environmental assessment. Significant expenditures are projected in the third quarter reflecting construction contracting costs. | 0 |  | N/A | 100 | Environmental delayed due to engineering re-assignment; new firm completed and obtained approval of environmental assessment. | 90 | Engineering design is substantially complete with minor modifications possible reflecting as-built construction. | 100 | Acquisition is complete at end of quarter | 90 | Acquisition is substantially complete at end of quarter. One railroad is demanding $250,000 for crossing fees in addition to normal permits; these fees are being protested. | 40 | Co-location and regeneration sites confirmed with engineering staking of the sites. Regen sites to be completed during next quarter to coincide with construction schedule. | 80 | Fiber and network equipment is on order at end of quarter | 0 | Build is on schedule. | 0 | Deployment is on schedule. | 0 | Testing is on schedule. | 2011-08-18 17:38 | 2011-08-18 17:38 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2011 | Q3 | Q3 - 2011 | 4325 | 4013 | TRUE | 15 | Percentage completion is based on cost of miles of conduit installed. Although significant construction has been accomplished, Kansas City Southern rail permits are still pending and therefore fiber has not been installed into the conduit yet. Project is still on schedule as projected. | 0 |  | N/A | 100 | Environmental assessment is completed as projected | 90 | Engineering design is substantially complete with minor modifications possible reflecting as-built construction. | 100 | Acquisition is complete | 90 | Kansas City Southern railroad has not issued required permits as of end of quarter, but resolution is expected shortly. | 75 | Co-location sites confirmed, surveys performed, regen buildings acquired and awaiting delivery. Permits to place colo buildings expected within the next 30 days. | 90 | Fiber transmission equipment received. Awaiting delivery of switching/routing equipment during the next quarter. | 50 | Build is ahead of projected schedule. Conduit installation is projected to be completed by January. All fiber has been delivered and is now being installed in conduit. Shelters, equipment, and related electronics are scheduled to be deployed in February. | 0 | Deployment is on schedule. Network equipment has been secured; installation is waiting on completion of fiber deployment. | 0 | Network testing is on schedule for February as equipment is deployed. | 2011-11-29 16:31 | 2011-11-29 16:31 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2011 | Q4 | Q4 - 2011 | 5215 | 4884 | TRUE | 59 | Percentage completion is based on federal funds expended. Significant construction has been completed with the project ahead of construction project schedule. Kansas City Southern rail permits delayed some parts of the construction and delayed installation of fiber overall, but the variances have been overcome. The project is on schedule as projected and will be completed within the grant guidelines | 0 | N/A | N/A | 100 | Environmental assessment is completed as projected | 95 | Engineering design is substantially complete with minor modifications possible reflecting as-build construction in the remaining fiber installation | 100 | Acquisition is complete | 100 | All permits have been obtained | 90 | Co-location sites have been confirmed and foundations begun. Two sites do not have foundations in places as of end of quarter, but will be installed in next quarter. Co-location buildings obtained and scheduled for delivery upon foundation completion | 90 | Fiber transmission equipment received. Delivery scheduled for switching/routing equipment. | 80 | Build is on schedule with fiber installation and equipment placement for first quarter 2012 | 0 | Deployment is on schedule. Fiber equipment received and in test. Switch/routing equipment on schedule for delivery first quarter 2012. | 0 | Network testing is on schedule for first quarter 2012 after fiber placement completion and installation of fiber/switching equipment. | 2012-02-23 15:06 | 2012-02-23 15:06 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2012 | Q1 | Q1 - 2012 | 6281 | 5743 | TRUE | 67 | Percentage completion is based on federal funds expended. Significant construction has been completed with the original primary construction route completed with power, fencing, and similar finishing work being done at this time. The termination point at Pineville is not yet completed as this site is being redesignated a lateral. The site will be completed in the next quarter. The primary construction plan is on schedule and will be completed within grant guidelines. | 0 | N/A | N/A | 100 | Environmental assessment is completed as projected. | 95 | Network design is substantially completed. Modifications are being re-worked due to minor changes in equipment layouts. | 100 | Acquisition is complete. | 100 | All permits have been obtained. | 95 | Co-location sites have foundations and buildings set in Dry Prong, Winnfield, and Jonesboro. Additional construction for power, fencing, and similar finishing is underway. Construction and renovation of the Vienna site is underway and completed except for power additions being installed. The site at Pineville is being changed to terminate in existing structure and will be completed next quarter. | 90 | Fiber transmission equipment received and in testing. Routing/switching equipment is pending awaiting final confirmations of network design. | 90 | Build is on schedule. Change order pending for termination point at Pineville to be a lateral with termination point at AT&T central office. Other components on schedule for second quarter completions. | 0 | Fiber transmission equipment on site and in testing, but not released for deployment. Routing and switching equipment on order. | 0 | Network testing contingent on deployment of fiber transmission equipment and routing/switching equipment. | 2012-05-24 13:47 | 2012-05-24 13:47 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2012 | Q2 | Q2 - 2012 | 7055 | 6155 | TRUE | 76 | Percentage completion is based on federal funds expended. Significant construction has been completed with electrical and utility installations in progress at four co-location and/or repeater sites. The termination at Pineville has not been completed with this site being redesignated as a anchor facility instead of an end point. A program modification request has been submitted to terminate the south end of the network at the AT&T Central Office in Alexandria. Engineering and environmental work is being done at this time to complete this south interconnection point. The same program modification provides for changes at the north end of the project to allow interconnections at Monroe and Shreveport. The primary construction plan is on schedule and all construction including requested program modification will be completed within grant guidelines. | 0 |  | N/A | 95 | Environmental assessment is completed on primary route. Requested program modification may require re-opening environmental for additional review. | 95 | Network design is substantially completed. Changes due to requested program modification will not require significant design changes. | 95 | Right of way permits for primary route are complete. Requested program modification may require additional permit for river crossing. All State highway right of way permits are provided where needed for requested program modification. | 95 | Construction permits for primary route are complete. Requested program modification may require additional permit for river crossing. | 95 | Construction for power, fencing and generator placement is underway. Delays have been encountered due to external utility construction to the sites. | 95 | Fiber and router/switch equipment has been received and is in testing. | 90 | Requested program modification will require additional network build elements as noted above. | 75 | Generator and battery equipment is in place at field sites. Fiber transmission and router switch equipment is being configured for deployment in the next quarter. | 50 | Physical layer testing of the fiber is underway at this time. | 2012-08-14 11:49 | 2012-08-14 11:49 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2012 | Q3 | Q3 - 2012 | 8063 | 6738 | TRUE | 84 | Percentage completion is based on federal funds expended. Significant construction has been completed with electrical and utility installations completed at four co-location and/or repeater sites. The termination at Pineville has not been completed with this site being redesignated as a anchor facility instead of an end point, however engineering and permits are underway. Engineering and permits for pending program modification are underway. The primary construction plan is on schedule and all construction including requested program modification will be completed within grant guidelines. | 0 | N/A | N/A | 95 | Environmental assessment is completed on primary route. Requested program modification has been submitted and is awaiting environmental. | 95 | Network design is substantially completed. Changes due to requested program modification will not require significant design changes. | 95 | Right of way permits for primary route are complete. Requested program modification requires additional permit for river crossing which has been submitted to Core of Engineers and Levy Board. All State highway right of way permits are provided where needed for requested program modification. | 95 | Construction permits for primary route are complete. Requested program modification requires additional permit for river crossing. | 95 | Construction for power, fencing and generator placement is complete for repeater sites. Delays have been encountered due to external utility construction to the sites. | 95 | Fiber and router/switch equipment has been installed and initial 40 Gbps primary link is working. | 90 | Requested program modification will require additional network build elements as noted above. | 85 | Generator and battery equipment is in place at field sites. Fiber transmission and router switch equipment is configured and operating. | 75 | Physical layer testing of the fiber has been completed for the primary path links. | 2012-11-27 09:58 | 2012-11-27 09:58 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2012 | Q4 | Q4 - 2012 | 8929 | 7714 | TRUE | 86 | Percentage completion is based on federal funds expended. Significant construction has been completed with electrical and utility installations completed at four co-location and/or repeater sites. The termination at Pineville has not been completed with this site being redesignated as a anchor facility instead of an end point, however engineering and permits are underway. Engineering and permits for pending program modification are underway. The primary construction plan is on schedule and all construction including requested program modification will be completed within grant guidelines. | 0 | N/A | N/A | 95 | Environmental assessment is completed on primary route. Requested program modification has been submitted and is awaiting environmental approval from NTIA staff. | 95 | Network design is substantially completed. Changes due to requested program modification will not require significant design changes. | 95 | Right of way permits for primary route are complete. Requested program modification requires additional permit for river crossing which has been submitted to Core of Engineers and Levy Board. All State highway right of way permits are provided where needed for requested program modification. | 95 | Construction permits for primary route are complete. Requested program modification requires additional permit for river crossing. | 95 | Construction for power, fencing and generator placement is complete for repeater sites. Delays have been encountered due to external utility construction to the sites. | 95 | Fiber and router/switch equipment has been installed and initial 40 Gbps primary link is working. | 90 | Requested program modification will require additional network build elements as noted above. | 85 | Generator and battery equipment is in place at field sites. Fiber transmission and router switch equipment is configured and operating | 75 | Physical layer testing of the fiber has been completed for the primary path links. | 2013-02-25 11:34 | 2013-02-25 11:34 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2013 | Q1 | Q1 - 2013 | 9857 | 8466 | TRUE | 86 | Percentage completion is based on federal funds expended. Federal funds were not claimed during the current period as the majority of work involved completion of current initiatives during the period the program modification was under review. All construction including requested program modification will be completed within grant guidelines | 0 | N/A | N/A | 100 | Environmental assessment is completed for primary and program modification routes. | 95 | Network design is substantially complete. Minor modifications have been made during the period to reflect connections for CAI sites and program modification. | 100 | Right of way permits for primary route and program modification are completed. | 95 | Construction permits required for ties into Windstream were not completed during the period, but have been completed after period close. | 95 | Site preparation for sites along I20 added during the program modification have not been completed during the period. | 95 | Fiber switch, battery plant, and related equipment for the program modification sites along I20 have not been purchased as of the end of the period. | 90 | Items in the requested program modification have not been completed as of the end of the period. | 85 | Items in the requested program modification have not been completed as of the end of the period. | 85 | Network testing for the original project build has been completed. Network equipment testing for the program modification components has not been completed as of the end of the period. | 2013-05-21 18:42 | 2013-05-21 18:42 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2013 | Q2 | Q2 - 2013 | 10747 | 9038 | TRUE | 94 | Percentage completion is based on federal funds expended. Federal funds claimed during the current period were for equipment and construction required for the approved project modification. All construction including requested program modification will be completed within grant guidelines | 0 | N/A | N/A | 100 | Environmental assessment is completed for primary and program modification routes. | 98 | Network design is substantially complete. Minor modifications have been made during the period to reflect connections for CAI sites and program modification. | 100 | Right of way permits for primary route and program modification are completed. | 100 | Construction permits required for ties into Windstream have been completed; no other permits are anticipated. | 95 | Site preparation for sites (Haughton, Bossier, and Filmore) along I20 added during the program modification have not been completed during the period. Other sites in the program modification have been completed and equipment is being installed in the last three repeater sites. | 98 | All major components for sites in the program has been secured. Minor equipment relating to installation is remaining. | 95 | Not all items in the requested program modification for I20 have been completed as of the end of the period. Since three sites still have equipment installation pending, all network build is not complete. | 95 | Transmission equipment for the I20 program modification has been installed in repeater sites except for Haughton, Bossier, and Filmore. These sites will be competed during the next quarter. | 95 | Network components and segments have been individually tested and end to end network testing will be completed during the next quarter. | 2013-08-26 17:51 | 2013-08-26 17:51 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2013 | Q3 | Q3 - 2013 | 12063 | 10226 | TRUE | 100 | Percentage completion is based on federal funds expended. Federal funds claimed during the current period were for equipment and construction required for the approved project modification. All construction including requested program modification will be completed within grant guidelines | 0 | N/A | N/A | 100 | Environmental assessment is completed for primary and program modification routes. | 100 | Network design is substantially complete. Minor modifications have been made during the period to reflect connections for CAI sites and program modification. | 100 | Right of way permits for primary route and program modification are completed. | 100 | Construction permits required for ties into Windstream have been completed; no other permits were required. | 100 | Site preparation for remaining sites (Haughton, Bossier, and Filmore) along I20 added during the program modification have been completed during the period. Other sites in the program modification have been completed and equipment was installed in the last three repeater sites. | 100 | All major components for sites in the program has been secured and installed. | 100 | Remaining items in the requested program modification for I20 have been completed. | 100 | Transmission equipment for the I20 program modification has been installed in all repeater sites including sites of Haughton, Bossier, and Filmore which were incomplete as of last quarter. | 100 | Network components and segments have been individually tested and end to end network testing is completed. | 2014-04-24 00:18 | 2014-04-24 00:18 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570119 | 2010 | Q4 | Q4 - 2010 | 1017 | 2063 | TRUE | 15 | n/a | 0 |  | n/a | 90 | Draft EA is due Feb. 2, 2011 | 100 | n/a | 25 | n/a | 0 | n/a | 0 | n/a | 20 | Due to complexity and competition the procurement process has not gone as quickly as anticipated. For example, the capability and pricing of respondents to the electronics RFP have been so close that we have had to engage in multiple rounds of elimination to pick a winner. In general, vendors are responding quite aggressively to our RFPs, which is great for the project, but does complicate the process due to the sheer volume of responses and level of competitiveness. | 0 | No build allowed until FONSI is issued | 0 | n/a | 0 | n/a | 2011-02-09 12:21 | 2011-02-09 12:21 | 6072 | 6072 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2011 | Q1 | Q1 - 2011 | 2121 | 2806 | TRUE | 3 | Project expenditures remain low because of continued delays in receiving FONSI that is holding up construction. Procurement has not gone as quickly as projected due to complexity of the RFPs and the large number of responses. | 0 |  | n/a | 90 | Process with SHPO has taken longer than expected, considering that more than 98% of the route is aerial on existing power company rights-of-way. | 6 | Although we have spent approximately 6% of our budgeted amount for architecture and engineering fees, backbone engineering is essentially completed. | 98 | Estimate in baseline project milestones is low. Most ROWs for this project are in utility corridors, where we have permission to build already. | 6 | Permitting was built into network design, of which we have spent 6% of the budgeted amount. Despite the low expenditures, permitting is proceeding ahead of schedule. | 6 | Site preparation and acquisition costs were built into the network engineering budget, of which we have spent 6% of projection. Despite the low expenditures, site preparation is ahead of schedule. | 15 | Equipment procurement has been delayed by the delay in construction. We are reluctant to buy and warehouse equipment that would go unused for months while awaiting a FONSI. | 0 | No build allowed until FONSI is issued. FONSI delayed by ongoing negotiations with the Ohio Historic Preservation Office. Construction represents nearly 70% of projected budget. Miscellaneous line for OARnet IRU represents 5.4% of projected budget. | 0 | No build allowed, so no equipment has been deployed. | 0 | No build allowed, so no construction has taken place. | 2011-05-18 10:24 | 2011-05-18 10:24 | 6072 | 6072 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2011 | Q2 | Q2 - 2011 | 3187 | 3354 | TRUE | 4 | Project expenditures remained low this quarter because the FONSI was not issued until mid-May. | 0 |  | n/a | 98 | Environmental SAC lifted; continuing to assess cultural and historical impact on routes as they are finalized. This work will be ongoing until all routes are finalized. | 18 | Although we have spent approximately 18% of our budgeted amount for architecture and engineering fees, backbone engineering is essentially completed. | 98 | Estimate in baseline project milestones is low. Most ROWs for this project are in utility corridors, where we have permission to build already. | 18 | Permitting was built into network design, of which we have spent 18% of the budgeted amount. Despite the low expenditures, permitting is proceeding ahead of schedule. | 18 | Site preparation and acquisition costs were built into the network engineering budget, of which we have spent 18% of projection. Despite the low expenditures, site preparation is ahead of schedule. | 6 | We purchased a significant amount of fiber and electronics toward the end of the quarter concurrent with the onset of construction. We have not been invoiced for this equipment. Vendor negotiations and subsequent MSA were primarily responsible for variance. We expect to complete this milestone by EOY 2011. | 0 | Construction began in June 2011; by the end of the reporting period, .36% of the construction budget had been spent. The variance is a direct result of the delay in receiving our FONSI. We have accelerated our build schedule and should catch and pass the baseline projections by EOQ4 2011. | 0 | Baseline projected 30%, which is inaccurate. Equipment deployment will run roughly concurrent with network build. | 0 | Baseline projected 30%, which is inaccurate. Testing will run roughly concurrent with network build. | 2011-08-18 11:25 | 2011-08-18 11:25 | 6072 | 6072 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2011 | Q3 | Q3 - 2011 | 4107 | 3897 | TRUE | 11 | This number would have been what we planned were it not for the delayed electronics invoices. The discrepancy with the baseline is due to the delay caused by the Finding of No Significant Impact (FONSI). We will be at least 67% complete by the end of year 2 and 100% by the end of year 3. | 0 |  | n/a | 98 | Assessment will continue as routes are finalized. | 42 | Significant progress was made this quarter. | 98 | We have an agreement with an electric provider which has provided permission for us to use their utility Rights of Way (ROWs) and this has allowed for us to be significantly ahead of baseline projections. | 42 | Included in Network Design budget. | 42 | Included in Network Design budget. | 6 | This is a matter of timing. We received major invoices just after the end of the quarter. Vendor negotiations and subsequent Master Services Agreement (MSA) were primarily responsible for variance from baseline. Equipment Procurement is making significant progress. | 8 | The variance here is a result of the delayed FONSI and a slower ramp-up in construction than was expected. With our accelerated build schedule we should catch and pass baseline projections during the next six months. | 0 | Equipment deployment will run roughly concurrent with the network build. | 0 | Network testing will run fairly concurrent with equipment deployment. | 2011-11-17 12:48 | 2011-11-17 12:48 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2011 | Q4 | Q4 - 2011 | 5269 | 4936 | TRUE | 32 | Horizon's project continues to ramp up. This quarter shows significant improvement and advancement toward our goals. Based on current expenditure rates Horizon expects to reach the 67% point during the second quarter of 2012 and will reach the 100% point during the second quarter 2013. Horizon is behind baseline projections because of the delays caused by the Environmental Assessment. This was not part of the project plan submitted with the application. | 0 | n/a | n/a | 98 | Assessment continues as routes are finalized. | 64 | Network Design is moving along and staying ahead of construction crews. | 98 | Horizon has an agreement with an electric provider which has provided permission for us to use their utility Rights of Way (ROWs). We are experiencing delays from on different utility provider when it is necessary for us to use their poles. We are actively working on this relationship. | 64 | Included in Network Design Budget. | 64 | Included in Network Design Budget. | 72 | Most of our electronics have been delivered. Horizon pays for Points of presence (POPs) when they are up, running and tested. Four complete buildings and electronics, and four electronics only POPs were accepted this quarter. | 20 | Construction is still feeling the effect of delays caused by the Finding of No Significant Impact (FONSI) and issues with permitting. | 10 | Four Points of Presence (POPs) are finished, thirty-six are at various points in the process. Horizon is behind baseline projections because of the delays caused by the Environmental Assessment. This was not part of the project plan submitted with the application. | 10 | Network testing runs fairly concurrent with Equipment Deployment. | 2012-02-26 14:09 | 2012-02-26 14:09 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2012 | Q1 | Q1 - 2012 | 6173 | 5689 | TRUE | 49 | Horizon is on schedule to reach the 67% point for expenditures during this quarter. Horizon is behind baseline projections because of delays caused by the Environmental Assessment, which was not part of the project plan submitted with the application. | 0 | n/a | n/a | 98 | Environmental Assessment continues as routes are finalized. | 87 | Network Design is ahead of construction. | 98 | Horizon's agreement with an electric provider has been very beneficial to the project. Horizon has overcome a hurdle with a different utility provider and the use of their poles. An agreement was signed late in the quarter which will allow progress on many fronts. | 87 | Included in Network Design budget. | 87 | Included in Network Design budget. | 73 | Electronics have been delivered. Eighteen Points of Presence (POPs) have been accepted thus far. We are behind our projection from last quarter of 92% mostly because we are not paying the invoices until our auditor conducts a complete inventory of each POP. 18 of 21 POPs have been placed and 32 of 40 of electronics have been installed (some were placed in existing POPs). | 41 | Construction lags behind projections due primarily to delays caused by the Finding of No Significant Impact (FONSI) and issues with permitting. Permitting made progress this quarter. | 30 | Eighteen Points of Presence (POPs) have been accepted, twenty-two are at various stages of deployment. We are behind our projection from last quarter of 45% primarily because we do not consider it complete until we have audited all equipment as existing and in proper place. | 25 | Network Testing runs close behind Equipment Deployment. | 2012-05-18 10:47 | 2012-05-18 10:47 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2012 | Q2 | Q2 - 2012 | 7121 | 6188 | TRUE | 60 | Horizon is working diligently to overcome the make-ready and permitting difficulties it is facing. Horizon has completed the two-thirds milestone as of the writing of this report as was required by July 31, 2012. | 0 | n/a | n/a | 98 | Environmental Assessment continues as routes are finalized. | 98 | Network Design of distribution laterals has gotten underway. | 98 | Horizon's agreement with an electric provider has been very beneficial to the project. We still face issues with other utilities regarding make-ready and permitting. | 98 | Included in Network Design budget. | 98 | Included in Network Design budget. | 87 | All electronics have been received and installed. Points-of-presence (POPs) have been installed in all county seats. We pay when the electronics have been turned up and tested. Nineteen POPs have been turned up and tested. | 52 | Construction lags baseline projections for a couple of reasons. The first being the delays caused by the Environmental Assessment, as it was not part of the project plan submitted with the application. This delay amounted to virtually ten months. Permitting and make-ready issues have caused a serious slow-down in our build rate. | 48 | Electronics have been installed but are not paid until tested and audited for all pieces of equipment. They cannot be tested until fiber reaches them, so this falls behind due to the delay in the build caused by permitting and make-ready issues. | 25 | The network cannot be tested until fiber is installed, so this falls behind due to the delay in the build caused by permitting and make-ready issues. Processes and procedures have been developed to ensure timely completion of testing as soon as the fiber is available. | 2012-08-17 16:21 | 2012-08-17 16:21 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2012 | Q3 | Q3 - 2012 | 8169 | 6795 | TRUE | 76 | Communications and power make-ready are the primary delays. Railroad permits, while slow, do arrive. An additional factor is the active hurricane season. Power make-ready crews were pulled and loaned to companies in the south in anticipation of storms like Hurricane Isaac. Those crews were gone for about a month. | 0 | n/a | n/a | 98 | Continues as designed. | 92 | Distribution laterals are in the network design phase at this time. *Negative variance from last quarter's report due to correction to budget spreadsheet. | 98 | Continues as designed. | 92 | Included in Network Design. *Negative variance from last quarter's report due to correction to budget spreadsheet. | 92 | Included in Network Design. *Negative variance from last quarter's report due to correction to budget spreadsheet. | 89 | In line with baseline. | 65 | During this quarter delays were caused by permitting and make-ready issues. The loss of crews to assist with storms like Hurricane Isaac delayed power make-ready until they returned. Overall construction delays have been caused by a ten month delay for the Environmental Assessment. Costs are still incurred even with these delays. The primary one being the up-front cost of the fiber optic cable. | 58 | Awaits backbone completion to bring online. | 40 | Awaits backbone completion to bring online. | 2012-11-30 10:30 | 2012-11-30 10:30 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2012 | Q4 | Q4 - 2012 | 8971 | 7752 | TRUE | 87 | Horizon continues to make progress despite continued barriers like make-ready and permitting. | 0 | n/a | n/a | 98 | Horizon will continue the ongoing assessments in coordination with our engineering and environmental assessment consultants. | 93 | Finalizing distribution routes. | 98 | Continues as designed. | 93 | Included in Network Design. | 93 | Included in Network Design. | 90 | In line with baseline. | 70 | Continued delays in permitting and make-ready have negatively affected our total build rate. This quarter had some success and ended up with double the build of the previous quarter. | 60 | Awaits backbone completion to bring online. | 45 | Awaits backbone completion to bring online. | 2013-02-26 13:51 | 2013-02-26 13:51 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2013 | Q1 | Q1 - 2013 | 10011 | 8551 | TRUE | 94 | As instructed at the beginning of the project the percentage complete for milestones has always been based on dollars spent. As a result these numbers are misleading as our project is over budget by as much as 10 percent. | 0 | n/a | n/a | 100 | Horizon continues to consult with its environmental consultants and follow the Performance Agreement. Environmental assessment was not budgeted in project plan. | 100 | Network design is virtually complete. | 100 | Continues as designed. | 100 | Included in Network Design budget. | 100 | Included in Network Design budget. | 100 | Latest forecasts project these costs to be 25% above budget. Currently at 106% of original budget. | 77 | Construction progressed at a decent pace this quarter | 80 | All equipment has been deployed. However it is not turned up until fiber reaches it and is then tested. Payment occurs after testing and equipment audit. | 70 | Runs behind build-out and equipment turn-up. | 2013-05-30 16:22 | 2013-05-30 16:22 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2013 | Q2 | Q2 - 2013 | 10829 | 9087 | TRUE | 100 | As previously instructed, milestones are calculated on dollars spent. Horizon has drawn all of the grant dollars as of this quarter. This result is misleading as our project is expected to be over original budget dollars by approximately 10 percent. | 0 | n/a | n/a | 100 | Horizon continues to follow its Programmatic Agreement as designed. | 100 | Network design is complete. | 100 | Continues as designed. | 100 | Included in Network Design budget. | 100 | Included in Network Design budget. | 100 | Latest forecasts project these costs to be 25% above budget. Currently at just over 106% of original budget. The original budget included six fewer Points-of Presence (POPs). | 97 | Again this number is misleading as it calculated on dollars spent and not actual progress for construction. | 85 | All equipment has been deployed. It is not turned up until fiber reaches it and is tested. | 85 | Runs slightly behind equipment turn-up. | 2013-08-30 16:14 | 2013-08-30 16:14 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2013 | Q3 | Q3 - 2013 | 11361 | 9484 | TRUE | 100 | The project is near completion with only 17.5 miles of fiber left to build which makes construction 98.6% complete. The project is at 105% of budget. | 100 | OARnet | This item is complete. This category is complete at 85% of budget. | 100 | Horizon continues to follow its Programmatic Agreement as designed. | 100 | Network Design is complete. Engineering is complete at 113% of budget. | 0 | n/a | 0 | n/a | 0 | n/a | 100 | All electronics have been received and installed. Points-of-presence (POPs) have been installed in all county seats. We pay when the electronics have been turned up and tested. Thirty-four POPs have been turned up and tested. Electronics is at 107% of budget. | 99 | The vast majority of the network has been completed. All that remains are those small pieces where make-ready, easement, permit, etc issues have blocked sections. Construction is at 104% of budget. | 95 | All equipment has been deployed. It is not turned up until fiber reaches it and is tested. | 0 | n/a | 2013-11-22 17:27 | 2013-11-22 17:27 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2013 | Q4 | Q4 - 2013 | 11913 | 10080 | TRUE | 100 | The project is near completion with construction complete. The project is at 107% of budget. | 100 | OARnet | This item is complete. This category is complete at 85% of budget. | 100 | Horizon continues to follow its Programmatic Agreement as designed. | 100 | Network Design is complete. Engineering is complete at 113% of budget. | 0 | n/a | 0 | n/a | 0 | n/a | 100 | All electronics have been received and installed. Points-of-presence (POPs) have been installed in all county seats. We pay when the electronics have been turned up and tested. Thirty-four POPs have been turned up and tested. Electronics is at 113% of budget. | 100 | Construction is complete at 106% of budget. | 95 | Final testing is being performed. | 0 | n/a | 2014-02-27 17:02 | 2014-02-27 17:02 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570120 | 2010 | Q4 | Q4 - 2010 | 675 | 1705 | TRUE | 6 | N/A | 0 |  | N/A | 60 | All field work has been completed. Tracking to schedule with most of what remains the development of the document and receipt of the FONSI. Due to completion of field work, we're ahead of schedule. | 25 | By end of quarter we had been invoiced for approximately 25% of all new miles to be engineered, slightly ahead of the forecast. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-01-28 08:35 | 2011-01-28 08:35 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2011 | Q1 | Q1 - 2011 | 1885 | 2688 | TRUE | 3 | Baseline % complete for round 2 was calculated based on a percentage of dollars expended. As such, we are behind schedule as only $2M in costs have been submitted thus far. | 0 |  | Not applicable to our project. | 75 | Draft submitted on 2/1/11 as required per SAC. By end of quarter we had received and were responding to comments from NTIA for resubmission to NTIA planned for 4/29/11. With initial comments received prior to end of quarter, we feel we're slightly ahead of where we planned at this point. | 35 | As reported in baseline, the planned network had 1694 miles associated with it. For the purposes of reporting here, we will report on routes actually engineered by our firm, while also adding to it the number of miles where IRU's or existing fibers are confirmed. At the end of the quarter, our firm had completed the engineering design of 2,798,321 feet, or 529 miles. 60 of our planned miles were from the BTOP1 route from Lenoir to Hickory that we would tie in to as well as 37 miles of existing fiber we had previously acquired from Level3. No other IRU's were completely negotiated at this point, so we will not consider them designed until executed. Thus, we consider 589 miles of the 1694 designed, or 35% which is behind schedule by 18%. We are about a quarter behind due to tracking relative to a calendar quarter in our project plan as opposed to realizing that in the Q1 report, we actually only have about 5 weeks of available work time. | 1 | By the end of the quarter we had submitted a right of way package to DOT for one county and approximately 20 railroad crossings. Relative to the number of miles in the entire network this is insignificant, but does amount to 1% of the overall ROW's to be submitted. At this point in the process we are not very far behind the 2% forecasted for this activity. | 0 | While we had forecasted to have 2% of this activity completed, as of the end of the quarter we had not received any formal approval. With our late start for the rights of way process this is not alarming and we anticipate recovering in Y1Q4 and Y2Q1. | 0 | Agreement work with each site has commenced however none are completed as expected, meaning we have missed 2% mark. Additionally with no clearance on the EA, we could not begin ground disturbing events prior to quarter end. | 0 | None had been planned at this point. | 2 | With 37 miles of existing fiber we had acquired designated for the project, we consider 2% complete. BTOP1 fibers designated for the project, while designed, were not fully built, and as such we don't note them here. No IRU's formally signed to transfer title nor had donated conduit been proofed and deployed, but with what's secured and in place, we are slightly ahead of schedule. | 0 | None planned. | 2 | Network testing occurs on fibers as they are built or acquired meaning this matches the network build section and slightly ahead of schedule. | 2011-05-04 13:30 | 2011-05-04 13:30 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2011 | Q2 | Q2 - 2011 | 2947 | 3231 | TRUE | 8 | Our overall project completion forecast was primarily based on miles being completed within the project. Due to not getting started on construction in this quarter as well as not formally completing planned IRU's, we are behind. We're not concerned with making this deficit up over the next 1-2 quarters. | 0 |  | N/A | 100 | FONSI received on 6/23/11. | 75 | Based on feedback from our engineering firm on where they are at in the design process, they have about 65% of the project plans done. Offset that with the planned acquisition of IRU's that were in the project not changing, we feel we are right in line with the 77% forecast we had for this item. | 20 | The permitting process has been challenging with NC DOT, and the permitting process with the railroads is always longer in nature and is expected. The challenges of the NC DOT process relate to the permits having to be approved by the central agency in Raleigh as opposed to the individual districts that normally do them. Because we have a statewide footprint, they have enacted a new policy on us to have them reviewed at the state level as opposed to in the districts where the construction is at. This has caused an increased level of back and forth between the state office, the district office, and our engineering firm. We have now prioritized all the counties where we need permits for our construction firm and DOT and asked them to focus on those that are at the front end of our construction time line. At the end of the quarter we had applied for 45 of 222 expected permits, or about 20%. We are slightly behind schedule. | 1 | We do not have as many permits obtained at the end of the quarter as expected due to a slower approval rate than we had anticipated. We had received only one meaningful permit at the end of the quarter, so are far below where we expected at this point. We expect to recover from this in the second quarter due to a commitment by DOT to help us push the permitting process along now that we have prioritized the counties needed to start construction. | 0 | Slower receipt of FONSI than expected impacted us getting huts deployed. We expect to make some of this difference up in the next reporting quarter. Significant legal work with the locations that are being leveraged has occurred, with agreements in principle for the easement required at about a dozen locations. We anticipate making up this difference over the next 1-2 quarters. | 0 | We had expected to have IRU's finalized and ready when receipt of FONSI so as to order equipment associated with operating those fibers at that time. Without receipt of FONSI and with these agreements not finalized we were not in a position to order the equipment. We expect to make up this reporting difference over the next 1-2 quarters. | 0 | We had expected to have IRU's finalized by end of the quarter and thus received approximately 150 of the miles of the project. These didn't happen, and thus we have no fibers acquired or built. We expect to make up this reporting difference by next quarter. | 0 | We had expected to have IRU's finalized and ready when receipt of FONSI so as to order equipment associated with operating those fibers. Without receipt of FONSI and with these agreements not finalized we were not in a position to order the equipment and thus deploy. We anticipate making up this difference over the next 1-2 quarters. | 0 | As a result of those issues noted with regards to finalizing planned IRU's, and with no construction having commenced, we had no fibers to test. We anticipate making up this reporting difference over the next 1-2 quarters. | 2011-08-08 09:47 | 2011-08-08 09:47 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2011 | Q3 | Q3 - 2011 | 4225 | 3961 | TRUE | 11 | This number for completeness is based on dollars spent. While the planning efforts of the project for engineering and permitting represent a great amount of work, they don't represent a great amount of spend, thus less than the 22% forecasted on the baseline. Over the next 2-3 quarters you will see this number bypass the baseline relative to number of miles deployed and dollars spent. At this point, we are not concerned with meeting expectations of the project and project overall completion of 67% by end of July 2012 and 100% completion by July of 2013. | 0 |  | None | 100 | NA | 81 | With some of the required reroutes of our projects pending, our original baseline for miles in the project is now wrong. We anticipate the final number of miles for the project if all reroutes are approved to be 1674 miles. We show approximately 992 miles fully engineered and 362 miles where IRU's/acquisition are agreed to in principle and working toward finalization, for a total of 1354 miles designed, or 81%. We anticipate making up this delta in the first part of 2012 as the design firm finalizes the designs of the reroutes once the changes have their EA amendment finalized. | 64 | The permitting process continues to be a challenge in such a large project. We asked our engineering firm to prioritize routes that we wanted to start constructing first for permit as opposed to going project wide. This was required due to the back and forth that DOT was going through in this process. By focusing on certain spans, we had a higher probability for finalizing key segments. Thus, all permits have not yet been applied for. At the end of the quarter we had applied for 77 of the required 141 DOT permits; and 54 of the 65 railroad permits for a total of about 64% of the known permits. We are slightly behind where we hoped to be at this point but anticipate being on target next quarter. The change we employed continues to be the best approach knowing that some of the routes not yet applied for are 6-9 months away from commencement of construction. | 37 | We do not have as many permits obtained at the end of the quarter as expected due to a slower approval rate than we had anticipated. Effort has been great, but billings relative to effort are not incurred until the permits are complete and received. We would anticipate 67% completion by end of calendar 2011 and 100% completion by June 2012 at the latest. | 10 | The process to finalize the easements at the universities and community colleges around the state where the huts will be located has been a long process. At the end of the quarter we had finalized (site plans, had surveys, and recorded easements) for about 4 of the 19 locations. All other locations are well along their way with agreements in principle and preliminary work started, but not completed. We expect to recover from this deficit over the next 2 quarters. At this point we have no concern that we are trending behind on this item. As the easements are complete, we will start preparing the sites for the huts. We forecast all complete by summer of 2012. | 1 | We were behind in completion of IRU's that were on the immediate forecast for having equipment ordered to place on them, and thus that equipment has not been ordered. We released an RFP in this quarter to determine equipment for the overall design, and expect to start ordering equipment late in Y1Q4 or Y2Q1 quarter after selecting the vendor after completion of two proof of concept labs with the finalists. We expect to make up this delta by end of Y2Q2. | 8 | This number for 8% completeness if based on dollars spent. Relative to judging our build "completeness", by the end of the quarter our firm fiber total completed within the project stood at 93 miles. Of this, 40 were existing MCNC assets to be placed in to the project from a previously owned route from Level3, 20 from the BTOP1 project used to tie the round 1 and round 2 networks together, 26 from a finalized acquisition with Zayo, and 7 from completed new builds. This is approximately 6% of the expected 1674 miles (after all required reroutes and final engineering are done). If you add the additional miles of conduit constructed, which accounts for the bulk of the time during construction, you would add 60 more miles to the project, for a total of 153 miles, or about 9%. We expect to make up this difference to baseline in the next reporting quarter. Relative to dollars and to miles deployed, we would anticipate 67% complete by end of July 2012 and 100% complete by March 2013. | 0 | Slower than expected deployment of IRU's impacted ordering schedule of equipment and thus deployment. We expect to begin deployment of equipment in earnest by the Y2Q2 quarter, and be back on track no later than Y2Q3 reporting period. | 0 | We did not have significant budget as part of this line item in the budget as these costs were part of the construction line item. Given that no new network testing equipment has been bought to date, this completion percentage is at 0%. However, we test our fibers as we acquire or build, and as such we correspond projection for this line item as 67% by July 2012 and 100% by March 2013. With approximately 6% of project activity done, we stand at 6% on testing relative to the proposed miles in the project but 0% relative to budget line item. | 2011-11-22 15:07 | 2011-11-22 15:07 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2011 | Q4 | Q4 - 2011 | 4971 | 4647 | TRUE | 22 | This number for completeness is based on dollars spent. While the planning efforts of the project for engineering and permitting represent a great amount of work, they don't represent a great amount of spend, thus less than the 25% forecasted on the baseline. We closed this gap significantly during the quarter as all three of our prime contractors had significant portions of the build in process. Over the next 1-2 quarters you will see this number bypass the baseline relative to number of miles deployed and dollars spent. At this point, we are not concerned with meeting expectations of the project and project overall completion of 67% by end of July 2012 and 100% completion by July of 2013. | 0 | NA | NA | 100 | NA | 88 | With some of the required reroutes of our projects pending, our original baseline for miles in the project is now wrong. We anticipate the final number of miles for the project if all reroutes are approved to be 1700 miles. We show approximately 1135 miles fully engineered and 362 miles where IRU's/acquisition are agreed to in principle and working toward finalization, for a total of 1497 miles designed, or 88%. We anticipate by the end of the March quarter if all reroutes are approved that we will virtually be finalized with design, with all design complete by end of June. The variance to baseline relates to those areas where full design has not been completed due to reroutes currently under consideration by NTIA. Percent completeness is based on acquisition and design of miles relative to approved route. | 82 | The permitting process continues to be a challenge in such a large project. We asked our engineering firm to prioritize routes that we wanted to start constructing first for permit as opposed to going project wide. This was required due to the back and forth that DOT was going through in this process. By focusing on certain spans, we had a higher probability for finalizing key segments. Thus, all permits have not yet been applied for. At the end of the quarter we had applied for 150 of the 183 aggregate permits, or 82%. We are slightly behind where we hoped to be at this point but anticipate being on target next quarter. The change we employed continues to be the best approach knowing that some of the routes not yet applied for are 6-9 months away from com mencement of construction. Percent completeness is based on number of permits acquired relative to number of permits required. | 58 | We do not have as many permits obtained at the end of the quarter as expected due to a slower approval rate than anticipated. 107 of 183 required DOT, railroad and municipal permits have been obtained, or 58%. While lower to baseline, because these permits are in areas that are not forecasted for construction until the second half of 2012, this is not a concern. We will be pushing for full permits by end of the March quarter, but realizing that we may slip until the end of June for 100%. Percent completeness is based on number of permits acquired relative to number of permits required. | 7 | At the end of the quarter we had received full easements or right of entry for 18 of the 19 locations around the state. We had begun the actual site work at 4 of these locations, and all 18 known locations had final engineering drawings completed. This represents about 1/2 of the work of the project in aggregate of what has been done. We believe we will fully implement all hut locations by end of the second year. Percent completion is based on dollars spent for construction efforts at site relative to budget and is below baseline due to actual construction being slower. We anticipate catching up in the next 1-2 quarters. | 1 | In December we completed proof of concept laps with two finalists from our RFP process. We expect to make a decision by end of January 2012 on this award and will be procurement in earnest in February. While we are significantly behind in this line item, because no signficant portions of fiber is yet ready, this is not a concern. We expect to be resumed to or exceeding baseline in 1-2 more quarters, or by Y2Q2. Percent complete is based on expenditures relative to budget. | 21 | This number for 21% completeness if based on dollars spent, above our 15% established in baseline. Relative to judging our build "completeness", by the end of the quarter our firm fiber total completed within the project stood at 261 miles. Of this, 40 were existing MCNC assets to be placed in to the project from a previously owned route from Level3, 20 from the BTOP1 project used to tie the round 1 and round 2 networks together, 163 from finalized IRU's, and 38 from completed new builds. This is approximately 15% of the expected 1700 miles (after all required reroutes and final engineering are done). If based on conduit miles constructed, which accounts for the bulk of the time during construction, you would add 329 more miles to the project, for a total of 590 miles, or about 35%. At this point, we are right in line with the baseline established for the project. | 0 | Due to delay in finalizing the selection of the equipment manufacturer, we are thus behind in ordering and deployment. While baseline called for 22%, we believe that our baseline was forecasted too aggressively when it was completed. With the first major span expected to complete in the spring of 2012, as well as finalizing of several IRU's, this number will recover over the next 1-2 reporting quarters. | 10 | We have tested the IRU fibers received but have not yet tested any of the fibers constructed as full segments are not complete. This represents approximately 10%, slightly below baseline. We will recover relative to baseline reporting by the second quarter of 2012. | 2012-02-13 12:41 | 2012-02-13 12:41 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2012 | Q1 | Q1 - 2012 | 6101 | 5653 | TRUE | 38 | This number for completeness is based on dollars spent. We are about 6% behind the baseline presented at the start of the project. We believe the project relative to deployment plan is about where we had hoped to be, but billings received from the contractors has not been as timely as needed at the end of the quarter to meet the baseline. Over the next 1-2 quarters we believe we will see this number begin to be at baseline as we pick up the pace of construction in the summer months. At this point, we are not concerned with meeting expectations of the project and overall completion of 66% by end of July 2012 and 100% completion by July of 2013. | 0 | NA | N/A | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 97 | The permitting process proved to be a challenge in such a large project. We asked our engineering firm to prioritize routes that we wanted to start constructing first for permit as opposed to going project wide. This was required due to the back and forth that existed between our engineering firm and the North Carolina Department of Transportation in processing each individual segment. By focusing on certain spans, we were able to finalize key segments. At the end of the quarter we had applied for 202 of the 208 aggregate permits, or 97%. We are working on the remaining six permits and feel confident that these will be submitted within the next few weeks. We are slightly behind where we hoped to be at this point because we anticipated having applied for all permits but anticipate being on target next quarter. The change we employed continues to be the best approach for our project. | 71 | 148 of 208 (71%) of the required North Carolina Department of Transportation, railroad and municipal permits had been approved/obtained at the end of the quarter. While we pushed for 100% of permits by end of the March quarter, the date slipped due in part to NC DOT and railroad response times. We now project that we should have all permits by the end of June 2012 with the exception of a few railroad permits which can take as long as 9 months to obtain. | 66 | At the end of the quarter we had received full easements or right of entry for nearly all telecommunication hut locations around the state. We had begun the actual site work at 9 of these locations and all design related to the huts has been completed. This represents about 1/2 of the work of the project in aggregate of what has been done, with four of the huts actually now placed. We believe we will fully implement all hut locations by end of the June 2012 reporting period. | 1 | We are significantly behind on procurement of equipment at this point, but will recover in the next quarter. By end of the March quarter we had selected Cisco systems for all equipment. The contract to be signed for delivery commitments was not signed by end of March, so no actual equipment was ordered as anticipated in the March reporting quarter. While we are slightly behind in this line item, it is not a major concern at this time based on our fiber ready status. We will be on target to the baseline by the September 2012 reporting period. | 39 | This number (39% completeness) is based on dollars spent, above our 33% established in baseline. Relative to judging our build "completeness", by the end of the quarter our firm fiber total completed within the project was 652 miles. Of this, 60 miles were existing MCNC fibers to be placed into the project; 272 from finalized IRU's and 321 from completed new builds. This is approximately 38% of the expected 1700 miles of the final as approved network. In analyzing conduit miles constructed, we could reasonably add 338 more miles to the completion rate (as fiber installation doesn't take near the time as conduit), for a total of 990 miles, or about 58% of the project total. At this point, we are ahead of baseline established for the project for dollars and miles. | 0 | The delay in equipment deployment is tied to no complete sections of fiber being built as well as slower than anticipated selection of the equipment vendor. While our baseline called for 22%, we believe that our baseline was forecasted too aggressively when it was completed. With the first major span expected to complete in the spring of 2012, as well as finalizing of several IRU's, this number will recover over the next 1-2 reporting quarters and does not represent a concern to us in being able to complete the project. | 35 | We have tested the IRU fibers received and have tested approximately 300 miles of the completed fiber and all received IRU's. This represents approximately 35% of the network total, slightly ahead of our 33% baseline. | 2012-05-15 14:39 | 2012-05-15 14:39 | 5748 | 5748 | MCNC | TRUE
NT10BIX5570120 | 2012 | Q2 | Q2 - 2012 | 7139 | 6197 | TRUE | 61 | This number for completeness is based on dollars spent. We are about 7% behind the baseline presented at the start of the project. The reason for the variance is due less now to a slower start to construction than planned and more due to timing of billings. We believe the project relative to deployment plan is essentially on track, but billings received from the contractors has not been as timely as needed at the end of the quarter to meet the baseline. Over the next 1-2 quarters we believe we will see this number begin to be at baseline as we pick up the pace of construction in the summer months. At this point, we are not concerned with meeting expectations of the project and overall completion of 66% by end of July 2012 and 100% completion by July of 2013. | 0 | N/A | N/A | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application | 100 | This task is 100% complete for the project as approved in the application | 83 | By the end of the quarter, 15 of the 18 planned telecommunication huts were on the ground and placed. All design work on the others was complete and waiting start dates relative to project needs. The construction cycle of these was a bit slower than anticipated. At this point we are well ahead of baseline and anticipate full completion by end of the December reporting quarter. | 64 | During the quarter we made significant purchases after finalizing selection of the vendor for equipment. At the end of the quarter much of this equipment had started to arrive and we are now ahead of the 51% projected in the baseline. | 60 | This number (60% completeness) is based on dollars spent, slightly ahead of our 58% established in baseline. Relative to judging our build "completeness", by the end of the quarter our firm fiber total completed within the project was 903 miles. Of this, 60 miles were existing MCNC fibers to be placed into the project; 303 from finalized IRU's and 540 from completed new builds. This is approximately 53% of the anticipated 1704 miles of the final network. In analyzing conduit miles constructed, we could reasonably increase this number to a total of 1171 or about 69% of the anticipated project total. At this point, we are slightly ahead of baseline established for the project for dollars and miles and do not have concern with completing the project on time. | 1 | The delay in equipment deployment is tied to no complete sections of fiber being built as well as slower than anticipated selection of the equipment vendor. While our baseline called for 50%, we believe that our baseline was forecasted too aggressively when it was completed. Now that the first span is nearing final acceptance, we anticipate deployment of the equipment to begin in earnest during the September reporting quarter, and we should be near baseline by the end of the December 2012 reporting quarter, however this activity could slip toward the March 2013 reporting quarter to be ahead. | 57 | Slightly below baseline of 58%, but well within schedule. We test fibers as they complete and are spliced, as well as when obtained. We have no concerns with being right at baseline as of this report. | 2012-08-20 07:34 | 2012-08-20 07:34 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2012 | Q3 | Q3 - 2012 | 7925 | 6667 | TRUE | 74 | This number reported for completeness is based on dollars spent, which is 74%, slightly behind baseline of 81% forecasted. Relative to the project miles with conduit miles placed and IRU's executed, we are at 84% complete, which is slightly ahead of the baseline. Contractor billings have delayed by about one month, which means we likely should be at or ahead of baseline by the end of the December reporting quarter. We believe the project relative to deployment plan is essentially on track. At this point, we are not concerned with meeting expectations of the project and overall completion by July of 2013. | 0 |  | N/A | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 89 | By the end of the quarter, 16 of the 18 planned telecommunication huts were on the ground and placed. All design work on the others was complete and start dates in October planned. The construction cycle of these was a bit slower than anticipated, but at this point we are still well ahead of baseline of 71% and anticipate finishing this function by end of the December reporting quarter. | 75 | Most backbone elements related to the project had been ordered and received, prepping for deployment. At the end of the quarter we had bought 75% of the equipment forecasted as part of the project, well above baseline of 66%. | 74 | This number (74% completeness) is based on dollars spent, slightly ahead of our 71% established in baseline. Relative to judging our build "completeness", by the end of the quarter our firm fiber total completed within the project was 1125 miles. Of this, 60 miles were existing MCNC fibers to be placed into the project; 344 from finalized IRU's and 721 from completed new builds. This is approximately 66% of the anticipated network. In analyzing conduit miles constructed, we could reasonably increase this number to a total of 1435 or about 84% of the anticipated project total. At this point, we are slightly ahead of baseline established for the project for dollars and miles and do not have concern with completing the project on time. | 5 | Deployment of backbone equipment is going as planned and had picked up at the end of the quarter. This continued effort in to the December reporting quarter will allow this number to increase closer to baseline in the next 1-2 quarters. CAI deployment and scheduling has to come after the backbone elements are complete and is taking a larger effort for scheduling than anticipated. | 66 | Slightly behind baseline of 71 at this point. We will recover on this in the next reporting quarter. Being behind in this line item is not a concern to us. | 2012-11-16 14:22 | 2012-11-16 14:22 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2012 | Q4 | Q4 - 2012 | 9067 | 7840 | TRUE | 85 | This number reported for completeness is based on dollars spent, which is 85%, which is slightly behind baseline of 90% forecasted. Relative to the project miles when consideration is given to miles of conduit constructed and IRU's executed, we are at 94% complete, which is slightly ahead of the baseline. The variance to baseline can be attributed to the pace of contractor billings and our acceptance of fiber . At this point, we are not concerned with meeting expectations of the project and overall completion by July of 2013. | 0 |  | N/A | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 84 | This task as expected is slightly ahead of baseline and due to quicker order of equipment as engineering requirements finalized. | 87 | This number (87% completeness) is based on dollars spent, slightly below our 88% forecasted in baseline. Relative to judging our build through actual completion in the field, by the end of the quarter our firm fiber total completed within the project was 1406 miles. Of this, 60 miles are existing MCNC fibers to be placed into the project; 336 from finalized IRU's and 1010 from completed new builds. This is approximately 82% of the anticipated network. In analyzing conduit miles constructed, we could reasonably increase this number to a total of 1606 or about 94% of the anticipated project total. We do not have concern with completing the project on time. | 50 | While quite a bit below the projected 80% completion in baseline, this effort continues to go as expected. We are placing equipment in the huts now that they are in place ahead of the fiber completion and this number should be at or ahead of baseline by the end of the March reporting quarter. We have no concerns with our ability to fully meet this criteria by the end of project. | 87 | Nearly at baseline of 88%. We are below simply due to timing of completion of the fiber splicing and acceptance of the fibers. No concerns with this line item from our perspective. | 2013-02-28 12:23 | 2013-02-28 12:23 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2013 | Q1 | Q1 - 2013 | 9751 | 8410 | TRUE | 92 | This number reported for completeness is based on dollars spent, which is 92%, lower to the baseline of 98% forecasted. This is due to a number of factors, the most important being that the most difficult and expensive region for construction has been worked on last, meaning some of the more expensive billings have not yet occurred. We are a bit behind in our construction schedule due to weather during the winter months but are on pace to recover from this by June. Relative to the project miles when consideration is given to miles of conduit constructed and IRU's executed, we are at 98% complete, which is at baseline. At this point, we are not concerned with meeting expectations of the project and overall completion by July of 2013. | 0 |  | NA | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 89 | We are lower to baseline when measured against dollars spent on this line item due to lower costs of equipment procured at this point than expected. All equipment required to complete the project is either already in place, in house for deployment, or queued up for ordering in the next quarter. No concerns on completing this. | 94 | This number (94% completeness) is based on dollars spent, below our 100% forecasted in baseline for completion of fiber. The primary reason for this has been very wet and rainy weather in the winter months of this year that effectively caused us to lose an aggregate of approximately four weeks of work time. Relative to judging our build through actual completion in the field, by the end of the quarter our firm fiber total completed within the project was 1596 miles. Of this, 60 miles are existing MCNC fibers to be placed into the project; 336 from finalized IRU's and 1200 from completed new builds. This is approximately 94% of the anticipated network. We do not have concern with completing the project on time. | 90 | We are below the projected baseline of 95% at this time. This is primarily due to timing of deployment of CPE equipment at CAI's along the completed fiber route. Most backbone related equipment has been deployed and is waiting on final splicing of fiber routes to turn up. We anticipate all deployment work of equipment to be finalized in the June reporting quarter. | 94 | Below baseline of 99%. We are not complete with the fiber build as expected due to slower construction during the winter months with rainy weather. We anticipate this effort will complete by middle of the June quarter in full. | 2013-05-16 07:54 | 2013-05-16 07:54 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2013 | Q2 | Q2 - 2013 | 10541 | 8925 | TRUE | 97 | This number reported for completeness is based on dollars spent, which is 97%, lower to the baseline of 100% forecasted. The primary reason we are not complete as of this quarter is the construction schedule got behind during this past winter due to a particularly rainy/snowy season. Relative to the project miles, when consideration is given to miles of conduit constructed and IRU's executed, we are at 99% complete. We will complete the project by the required deadline of end of July 2013. | 0 |  | N/A | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 98 | This number (98% completeness) is based on dollars spent, below our 100% forecasted in baseline for completion of fiber. The primary reason for this has been very wet and rainy weather in the winter months of this year that effectively caused us to lose an aggregate of approximately four weeks of work time. Relative to judging our build through actual completion in the field, by the end of the quarter our firm fiber total completed within the project was 1690 miles. Of this, 60 miles are existing MCNC fibers to be placed into the project; 336 from finalized IRU's and 1294 from completed new builds. This is approximately 99% of the anticipated network. All required project activity will complete by the end of July 2013 deadline. | 100 | This task is 100% complete for the project as approved in the application. | 98 | We are not complete with the fiber build as expected due to slower construction during the winter months with rainy weather. This effort will complete by the end of July 2013. | 2013-08-09 15:17 | 2013-08-09 15:17 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2013 | Q3 | Q3 - 2013 | 10997 | 9222 | TRUE | 100 | Actual completion based on dollars is 99%, lower to the baseline of 100% forecasted. We were able to achieve some savings on construction due to a couple of IRU's executed during the project in the more difficult areas of construction. The project as outlined in the proposal is complete. | 0 |  | N/A | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 97 | This number (97% completeness) is based on dollars spent, below our 100% forecasted in baseline for completion of fiber. One of the reasons for this has been savings achieved due to fiber acquisitions via IRU's as opposed to builds. The other issue is that the original budget as approved included $2,291,533 or Rights or Ways (ROW) costs, but the actual ROW costs were captured in the Land, structures, ROW, appraisals, etc line. The project as outlined in the application is complete. | 100 | This task is 100% complete for the project as approved in the application. | 100 | This task is 100% complete for the project as approved in the application. | 2013-10-29 11:54 | 2013-10-29 11:54 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570122 | 2010 | Q4 | Q4 - 2010 | 1235 | 2267 | TRUE | 6 | On target for this reporting period. | 15 | IN-KIND | On target for this reporting period. Right of Use agreements for In-Kind assets and master commercial tower license templates are in development. | 0 | N/A. Exempt. | 30 | On target for this reporting period. Site audits have started, and preliminary link engineering is underway. | 0 | N/A. This project does not include this activity. | 0 | On target for this reporting period. We have had preliminary conversations with commercial tower owners to determine certification and application procedures required for contractors and laborers to work at their sites. | 0 | On target for this reporting period. Site audits and assessments are underway however, which include the determination and evaluation of site preparation requirements. | 0 | On target for this reporting period. Equipment RFP development is planned for next quarter. | 0 | On target for this reporting period. IRU negotiations with Level 3 for upstream access have commenced. | 0 | On target for this reporting period. | 0 | On target for this reporting period. | 2011-02-18 19:34 | 2011-02-18 19:34 | 5502 | 5502 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2011 | Q1 | Q1 - 2011 | 2231 | 2861 | TRUE | 5 | Please see Section 1, Item #3 for a more detailed explanation of the project's variance from the Baseline plan and our plans for catching up to the Baseline Plan. In previous Performance Progress Reports, overall project progress was based on pending expenditures and committed costs as determined by work completed instead of actual budget expenditures. From this point forward we will report milestone completion percentages based on budget expenditures in the milestones calculation, incorporating both Federal funds and non-Federal share in-kind contributions where applicable in the milestones calculation, per Additional Guidance instructions. In an effort to catch up to the Baseline Plan and to ensure that the project will be completed within the 3 year period of performance, the General Manager is conducting detailed internal reviews of submitted engineering design documents in order to help identify potential design and deployment issues early on in the process and to ensure that | 0 | In-Kind Capital Leases | Please see Section 1, Item #3 for more details regarding the reasons for variance from our baseline plan. In previous Performance Progress Reports, milestone completion percentages for this category were based on work completed instead of actual budget expenditures. As part of our efforts to catch up to the Baseline Plan, the Florida Rural Broadband Alliance's General Counsel has been working closely with the Grants Office and the Program Office to finalize the format and acceptable language required in all lease documents for the project, including the in-kind leases. The General Manager is also working closely with the Engineer in order to expedite consensus regarding engineering work authorization scopes and associated deliverables, which include a network topology with in-kind asset sites identified. Going forward, progress toward this milestone category will be reported against actual expenditures, incorporating non-Federal share in-kind contributions as applicable per the Ad | 0 | N/A. Categorically exempt from Environmental Assessment. | 5 | Please see Section 1, Item #3 for a more detailed explanation of the project's variance from the Baseline plan. In previous Performance Progress Reports, network design progress was based on pending expenditures and committed costs as determined by work completed instead of actual budget expenditures. From this point forward we will report milestone completion percentages based on budget expenditures in the milestones calculation, per Additional Guidance instructions. The Engineer elected to seek design guidance from a third-party consultant in order to validate the conceptual network design against complex network-to-network integration considerations that are associated with incorporating the Florida Rural Broadband Alliance's two geographically distinct networks into one comprehensive design plan. In an effort to catch up to the Baseline Plan, the General Manager is conducting detailed internal reviews of submitted engineering design documents in order to help identify potent | 0 | N/A | 0 | Please see Section 1, Item #3 for more details regarding the reasons for variance from our baseline plan. In previous Performance Progress Reports, progress toward this milestone category was based on pending expenditures as determined by work completed instead of actual budget expenditures. Progress was also reported against the Baseline Plan quarterly projections for this milestone category as listed in the "Infrastructure Milestone Categories" section in the Baseline Plan. From this point forward we will report milestone completion percentages based on budget expenditures in the milestones calculation, per Additional Guidance instructions. In order to catch up with the Baseline Plan, steps have been taken to identify tower company requirements for site access, and permit acquisition procedures will be determined for each county in the core network footprint as the project transitions into its pre-deployment phase. | 0 | N/A (please see explanation below) In previous Performance Progress Reports, progress toward this milestone category was based on pending expenditures as determined by work completed (in the development of a civil / site prep scope of work template) instead of actual budget expenditures. Progress was also reported against the Baseline Plan quarterly projections for this milestone category as listed in the "Infrastructure Milestone Categories" section in the Baseline Plan. However, per the Additional Guidance instructions, progress is to be reported against actual budgeted expenditures, which we understand to be reflected in the budget categories identified in the "Infrastructure Budget Execution Details" section of this report. As indicated in Item 1g, Site Work and in our SF-424C form, we did not allocate any costs in this budget category. Therefore, in order to comply with Additional Guidance instructions and to be consistent in our current and future reporting, we are indicat | 0 | Please see Section 1, Item #3 for more details regarding the reasons for variance from our baseline plan. In previous Performance Progress Reports, milestone completion percentages for this category were based on pending expenditures as determined by work completed instead of actual budget expenditures. Expenditures for equipment procurement services will not be actualized until next quarter. From this point forward we will report milestone completion percentages based on budget expenditures, incorporating both Federal funds and non-Federal share in-kind contributions where applicable in the milestones calculation, per Additional Guidance instructions. In an effort to catch up to the Baseline Plan, the General Manager is conducting detailed internal reviews of submitted engineering design documents in order to help identify potential design and deployment issues early on in the process and to ensure that the network meets the carrier-class performance requirements of the Florida | 0 | Please see Section 1, Item #3 for more details regarding the reasons for variance from our baseline plan. In previous Performance Progress Reports, milestone completion percentages for this category were based on pending expenditures and committed costs as determined by work completed instead of actual budget expenditures. As part of efforts to catch up to the Baseline Plan, negotiations for our upstream first mile access Indefeasible Right of Use have been successfully completed, and this agreement has been approved and executed by the Florida Rural Broadband Alliance Board of Governors. However, actual expenditures associated with this Indefeasible Right of Use will not be recorded until the next reporting period. In addition, master lease agreement documents have been finalized, and execution of same is pending an internal review and submission to the Florida Rural Broadband Alliance Board of Governors for approval. Actual expenditures for commercial site lease agreements w | 0 | On target for this reporting period. | 0 | On target for this reporting period. | 2011-05-20 19:50 | 2011-05-20 19:50 | 5502 | 5502 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2011 | Q2 | Q2 - 2011 | 3311 | 3418 | TRUE | 20 | The overall project is slightly behind schedule. Completion of the engineering for the South-Central Regional Network and the incremental engineering plan for the North West Regional Network will accelerate the project over the next quarter. The anticipated acceleration will bring the project back to the baseline estimates by the end of the 4th quarter of 2011. | 37 | In-Kind Capital Leases | On target for this reporting period. | 0 | N/A | 70 | On target for this reporting period. | 0 | N/A | 5 | South Central - Ready to start permitting activities after design. | 5 | Site Prep - Ready to start Tampa / Orlando Datacenter upgrades after request for materials bid. | 15 | Equipment Procurement is behind Baseline Plan projections for this past quarter waiting completion of the final engineering plan. The South-Central Regional Network will have a completed bill of materials and ready for a request for bid the 3rd quarter of 2011. A request for bid will be released and equipment will be purchase during the 4th quarter of 2011. | 5 | Level 3 is nearly complete and will be operational by the next quarter for the South-Central Regional Network. | 5 | On target for this reporting period. | 5 | On target for this reporting period. | 2011-08-25 12:45 | 2011-08-25 16:46 | 7164 | 7164 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2011 | Q3 | Q3 - 2011 | 4349 | 4031 | TRUE | 32 | The overall project has been refocused during this period and a new project plan has been put in place. The new plan provides for parallel activities and creates a forward looking approach to managing resources and tasking. Though the overall project is behind its spending baseline it anticipates significant acceleration through the 4th quarter of 2011 and the 1st quarter of 2012. The completion of the equipment procurement and the execution of tower lease agreements during the 4th quarter will enable FRBA to begin new construction efforts beyond the Hardee county network. The previous project reporting metrics were based on percentage of effort/tasks completion and not on actual expenditures. That has been corrected for this reporting period and the percentage of completion now reflects the actual percentage of expenditures. | 38 | In-Kind Capital Leases | On target for this reporting period. | 0 | N/A | 37 | The major effort of completing the overall design and establishing the equipment specifications for the FRBA network has been completed. This will enable FRBA to begin to run parallel tasks on a site by site basis. Even though the expenditures are behind baseline projections the work effort completed will allow FRBA to accelerate the site engineering as site lease agreements and civil site work begin. The previous project reporting metrics were based on percentage of effort/tasks completion and not on actual expenditures. That has been corrected for this reporting period and the percentage of completion now reflects the actual percentage of expenditures. | 0 | N/A | 37 | With the completion of the build out of the Hardee County portion of the network and the completion of the engineering design, FRBA anticipates an acceleration of construction permits, tower lease agreements and other approvals needed to begin construction. Even though this task is behind the baseline for spending it is in alignment with the work effort needed. FRBA expects to run parallel activities which will accelerate the site and tower work that needs to be completed prior to equipment installation. This work is expected to significantly increase towards the end of the 4th quarter of 2011 and accelerate in the 1st quarter of 2012. This should bring the construction expenditures back within baseline by the 2nd quarter of 2012. The previous project reporting metrics were based on percentage of effort/tasks completion and not on actual expenditures. That has been corrected for this reporting period and the percentage of completion now reflects the actual percentage of expenditures. | 14 | Upon the compltion of tower lease agreements and issuance of site permits, FRBA expects to start significant efforts towards the site preparation. FRBA expects civil engineering and site work to remain ahead of the construction/equipment implementation schedule. FRBA expects to be substantially complete with all site prep by the end of the 2nd quarter of 2012. The previous project reporting metrics were based on percentage of effort/tasks completion and not on actual expenditures. That has been corrected for this reporting period and the percentage of completion now reflects the actual percentage of expenditures. | 32 | Six separate Requests for Bids have been prepared for the various types of network equipment. Issuance of the Requests for Bids and vendor selection, contract negotiations and Purchase orders are expected to be completed within the 4th quarter of 2011. This will start the production, shipment and delivery process which is expected to be substantially complete before the end of 2011. The previous project reporting metrics were based on percentage of effort/tasks completion and not on actual expenditures. That has been corrected for this reporting period and the percentage of completion now reflects the actual percentage of expenditures. | 19 | The network build out has resulted in the completion of the Hardee County network and the deployment of the Level 3 fiber. The first of four Points of Presence for the Project has been activated and connected to the FRBA network. Additional network build out will begin once the initial permits and tower lease agreements are completed. It is anticipated that significant progress will be made between the 4th quarter of 2011 and the 2nd quarter of 2012. This should bring the project back within expenditure baseline by the second quarter of 2012. The previous project reporting metrics were based on percentage of effort/tasks completion and not on actual expenditures. That has been corrected for this reporting period and the percentage of completion now reflects the actual percentage of expenditures. | 32 | The equipment is expected to be substantially available for staging and shipment to the sites by the end of the 4th quarter of 2011. Site preparation and tower readiness will be started and equipment will begin to be shipped for installation late 2011. Substantial completion of this effort is not expected until later in the 2nd quarter of 2012.The previous project reporting metrics were based on percentage of effort/tasks completion and not on actual expenditures. That has been corrected for this reporting period and the percentage of completion now reflects the actual percentage of expenditures. | 0 | Hardee County Network Testing was completed at the end of 2010. The continued deployment of the network will being at the end of the 4th quarter of 2011. It is anticipated that the significant testing will not begin until early 2012 and be substantially complete by the end of the second quarter of 2012. The previous project reporting metrics were based on percentage of effort/tasks completion and not on actual expenditures. That has been corrected for this reporting period and the percentage of completion now reflects the actual percentage of expenditures. | 2011-11-30 15:45 | 2011-11-30 15:45 | 7164 | 7164 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2011 | Q4 | Q4 - 2011 | 5375 | 5046 | TRUE | 49 | The new plan provides for parallel activities and creates a forward looking approach to managing resources and tasking. Though the overall project is behind its spending baseline, FRBA has made great progress at accelerating the procurement and initiating its construction efforts that will be kicked-off during the first quarter of 2012. FRBA anticipates significant acceleration through the 1st quarter of 2012. | 73 |  | On target for this reporting period. | 0 | N/A | 43 | The major effort of completing the overall design and establishing the equipment specifications for the FRBA network has been completed. Even though the expenditures are behind baseline projections the work effort completed will allow FRBA to accelerate the site engineering as site lease agreements and civil site work begin during the first quarter of 2012. | 0 | N/A | 43 | Even though this task is behind the baseline for spending it is in alignment with the work effort needed. FRBA expects to run parallel activities which will accelerate the site and tower work that needs to be completed prior to equipment installation. This work is expected to significantly increase during the 1st quarter of 2012. This should bring the construction expenditures back within baseline by the 2nd quarter of 2012. | 18 | Upon the completion of tower lease agreements and issuance of site permits, FRBA expects to start significant efforts towards the site preparation. FRBA expects civil engineering and site work to remain ahead of the construction/equipment implementation schedule. FRBA expects to be substantially complete with all site prep by the end of the 2nd quarter of 2012. | 56 | Procurement began during the 4th quarter of 2011 and equipment is now being received by FRBA. Additional equipment and materials for installation will be received during the 1st quarter of 2012 and bring the equipment procurement back in line with original milestone objectives. | 19 | The network build out has resulted in the completion of the Hardee County network and the deployment of the Level 3 fiber. The first of four Points of Presence for the Project has been activated and connected to the FRBA network. Additional network build out will begin once the initial permits and tower lease agreements are completed. It is anticipated that significant progress will be made between the 1st quarter of 2012 and the 2nd quarter of 2012. This should bring the project back within expenditure baseline by the second quarter of 2012. | 56 | The equipment is expected to be substantially available for staging and shipment to the sites by the end of the 1st quarter of 2012. Site preparation and tower readiness will be started during the 1st quarter. Substantial completion of this effort is not expected until later in the 2nd quarter of 2012. | 0 | Hardee County Network Testing was completed at the end of 2010. It is anticipated that the significant testing will not begin until early 2012 and be substantially complete by the end of the second quarter of 2012. | 2012-02-28 18:44 | 2012-02-28 18:44 | 7164 | 7164 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2012 | Q1 | Q1 - 2012 | 6315 | 5760 | TRUE | 58 | The new plan provides for parallel activities and creates a forward looking approach to managing resources and tasking. Though the overall project is behind its spending baseline, FRBA has made great progress at accelerating the procurement and initiating its construction efforts that were kicked-off during the 1st quarter of 2012. FRBA is bringing the overall program progress back in line with the original milestones. | 73 | In-Kind Capital Leases | On target for this reporting period. | 0 | N/A | 55 | The major effort of completing the overall design and establishing the equipment specifications for the FRBA network has been completed. Even though the expenditures are behind baseline projections the work effort completed will allow FRBA to accelerate the site engineering as site lease agreements and civil site work began in the 1st quarter of 2012. This work will accelerate throughout the second quarter and expected to be back on target during the 2nd half of 2012. | 0 | N/A | 55 | Even though this task is behind the baseline for spending it is in alignment with the work effort needed. FRBA expects to run parallel activities which will accelerate the site and tower work that needs to be completed prior to equipment installation. Over 47 site walk-outs and engineering packages are underway and expected to be completed during the 2nd quarter. This work is expected to significantly increase during the 2nd quarter of 2012. This should bring the construction expenditures back within baseline by the 2nd half of 2012. | 28 | Over 24 commercial and in-kind tower leases have been fully executed and permission to access the physical sites to complete site surveys on an additional 23 tower locations has been granted by the tower owners. Upon the completion of the site engineering and drawings and issuance of site permits, FRBA expects to start significant efforts towards the site preparation. FRBA expects civil engineering and site work to remain ahead of the construction/equipment implementation schedule. FRBA expects to be substantially complete with all site prep for 20 locations by the end of the 2nd quarter of 2012. | 68 | Procurement began during the 4th quarter of 2011 and the equipment has largely been received by FRBA. Equipment cabinets and steel are still being shipped. Additional equipment and materials for installation will be received during the 2nd quarter of 2012 and bring the equipment procurement back in line with original milestone objectives. | 19 | Procurement began during the 4th quarter of 2011 and equipment is now being received by FRBA. Additional equipment and materials for installation will be received during the 1st quarter of 2012 and bring the equipment procurement back in line with original milestone objectives. The commercial leases have largely been complete and waiting on final structural reports, site engineering and drawings. | 68 | The equipment is expected to be substantially available for staging and shipment to the sites by the end of the 1st quarter of 2012. Site preparation and tower readiness will be started during the 1st quarter. Substantial completion of this effort is not expected until later in the 2nd half of 2012. | 0 | Hardee County Network Testing was completed at the end of 2010. It is anticipated that the significant testing will not begin until early 2012 and be substantially complete by the end of the 2nd half of 2012. | 2012-05-29 11:02 | 2012-05-29 11:02 | 7164 | 7164 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2012 | Q2 | Q2 - 2012 | 7283 | 6269 | TRUE | 61 | The new plan provides for parallel activities and creates a forward looking approach to managing resources and tasking. Though the overall project is behind its spending baseline, FRBA has made great progress at accelerating the procurement and initiating its engineering and construction efforts that were kicked-off during the 1st half of 2012. FRBA is bringing the overall program progress back in line with the original milestones. | 76 | In-Kind Capital Leases | All of the critical in-kind leases have been approved enabling FRBA to begin installation. | 0 | N/A | 62 | The major effort of completing the overall design and establishing the equipment specifications for the FRBA network has been completed. Even though the expenditures are behind baseline projections the work effort completed will allow FRBA to accelerate the site engineering as site lease agreements and civil site work during the 3rd quarter of 2012. This work will accelerate throughout the second quarter and expected to be back on target during the 2nd half of 2012. | 0 | N/A | 62 | Even though this task is behind the baseline for spending it is in alignment with the work effort needed. FRBA expects to run parallel activities which will accelerate the site and tower work that needs to be completed prior to equipment installation. Over 47 site walk-outs and engineering packages have been completed during the 2nd quarter. This should bring the construction expenditures back within baseline by the 2nd half of 2012. | 38 | Over 18 commercial and in-kind tower leases have been fully executed and permission to access the physical sites to complete site surveys on an additional 23 tower locations has been granted by the tower owners. Upon the completion of the site engineering and drawings and issuance of site permits, FRBA expects to start significant efforts towards the site preparation. FRBA expects civil engineering and site work to remain ahead of the construction/equipment implementation schedule. FRBA expects to be substantially complete with all site prep for 47 locations by the end of the 3rd quarter of 2012. | 72 | Procurement began during the 4th quarter of 2011 and the equipment has largely been received by FRBA. Equipment cabinets have been received and steel are still being shipped. Additional materials for installation will be received during the deployment process over the 2nd half of 2012 and bring the equipment procurement back in line with original milestone objectives. | 19 | FRBA is in the process of transferring the engineering packages and FCC PCN process to G4S to facilitate the permitting process and the site preparation for tower deployment. The Level 3 IRUs have been executed and plan for Data Center deployment has been put into action ensuring FRBA will be ready to activate services during the 2nd half of 2012. | 72 | The equipment is available for staging and shipment to the sites during the second half of 2012. Site preparation and tower readiness will enable FRBA to begin deployment early in the 2nd half of 2012. Substantial completion of this effort is not expected until later in the 2nd half of 2012. | 0 | Hardee County Network Testing was completed at the end of 2010. It is anticipated that the significant testing will not begin until early in the 2nd half of 2012 and be substantially complete by the end of the 2nd half of 2012. | 2012-08-29 17:57 | 2012-08-29 17:57 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2012 | Q3 | Q3 - 2012 | 8153 | 6787 | TRUE | 56 | The new plan provides for parallel activities and creates a forward looking approach to managing resources and tasking. Though the overall project is behind its spending baseline, FRBA has made great progress at accelerating the procurement and initiating its engineering and construction efforts that were kicked-off during the 1st half of 2012. FRBA is bringing the overall program progress back in line with the original milestones. | 76 | In-Kind Capital Leases | All of the critical in-kind leases have been approved enabling FRBA to begin installation. FRBA continues to execute the in-kind arrangements. | 0 | N/A | 69 | The major effort of completing the overall design and establishing the equipment specifications for the FRBA network has been completed. Even though the expenditures are behind baseline projections the work effort completed will allow FRBA to accelerate the site engineering as site lease agreements and civil site work during the 4th quarters of 2012. This work will accelerate throughout the end of 2012. | 0 | N/A | 69 | Even though this task is behind the baseline for spending it is in alignment with the work effort needed. FRBA expects to run parallel activities which will accelerate the site and tower work that needs to be completed prior to equipment installation. The delayed approval of the PCNs by the FCC has slowed down the process. This is expected to increase during the 4th quarter of 2012. | 44 | Over 87 commercial and in-kind tower leases have been fully executed and permission to access the physical sites to complete site surveys 23 tower locations has been granted by the tower owners. Upon the completion of the site engineering and drawings and issuance of site permits, FRBA expects to start significant efforts towards the site preparation. FRBA expects civil engineering and site work to remain ahead of the construction/equipment implementation schedule. FRBA expects to be substantially complete with all site prep for 47 locations by the end of the 4th quarter of 2012. | 55 | Procurement began during the 4th quarter of 2011 and the equipment has largely been received by FRBA. Equipment cabinets have been received and steel are still being shipped. Additional materials for installation will be received during the deployment process over the 2nd half of 2012 and bring the equipment procurement back in line with original milestone objectives. | 11 | FRBA has transferred the responsibility for the engineering packages and FCC PCN process to G4S to facilitate the permitting process and the site preparation for tower deployment. The Level 3 IRUs have been executed and plan for Data Center deployment has been put into action ensuring FRBA will be ready to activate services during the 1st half of 2013. | 55 | The equipment has been staged by Inspired Technologies and will be shipped to the sites according to the deployment schedule. Site preparation and tower readiness will enable FRBA to begin deployment. Substantial completion of this effort is not expected until 1st quarter of 2013. | 0 | Network testing will begin in the 4th quarter of 2012. | 2012-11-29 16:39 | 2012-11-29 16:39 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2012 | Q4 | Q4 - 2012 | 9135 | 7929 | TRUE | 67 | A network re-design that is physically feasible (i.e. this includes from an engineering and operational perspective) and aligns to the Magellan customer demand set was introduced in the 4th quarter. The result of the re-design enabled contracts with required resources to be executed (i.e. G4S, Inspired, etc.) and for these resources to be aligned to a cohesive deployment plan within the 4th quarter. | 90 | n/a | In-Kind Capital Leases | 0 | N/A | 70 | 100% of the network designs have been completed, but 41% of these designs cannot be finalized until other dependencies are finalized (i.e. structurals, PCNs, leases, etc.). FRBA believes that the majority of these pre-finalized designs will require only minor modifications and will enable the deployment cycle time to be reduced on affected links. | 0 | N/A | 70 | Pre-construction activity was a key area of focus in quarter 4 and will remain a key focus into quarter 1 since this is the enabler to construction. Three key issues were identified in quarter 4 that have and will continue to cause change to the deployment schedule into quarter 1: (1) sites that fail structural, line of sight ("LOS"), etc. approval and must re-enter the design process to be designed around or replaced, (2) sites where lease amendments are needed to accomodate the updated design, and (3) sites where the previous engineering firm did the construction drawings and are being rejected by the permitting municipalities because they were done to the wrong code. The deployment team continues efforts to expedite the identification of these gaps prior to the end of quarter 1. | 69 | Less than 10 site leases are required to complete the core network deployment. FRBA has a high level of confidence that the majority of these can be leased prior to the end of quarter 1. | 60 | FRBA has the 80% of the equipment needed to complete the construction of the network in its warehouses. The remaining equipment to be purchased and delivered is site specific materials that can only be identified after PCNs and structurals are completed. Efforts to expedite the delivery of this equipment once it is identified continues with the vendors. | 0 | Construction activities began in late quarter 4. G4S has different crews doing civil and tower work which will reduce the deployment cycle time since these each have different dependencies. In quarter 1, the North and South networks will each have at least four crews working as the pre-construction activities begin to materialize. The quarter 3 2012 PPR reported 11% completion based on match of $2,446,189 to the project construction and equipment budget, totaling $21,503,295 (2,446,189/21,503,295 = 11.25%). Since Rapid Systems match is no longer being counted in this project budget, we have removed the $2,446,189 from the matching category, resulting in the this Network Build percentage being reduced to 0%, from 11% as reported in the quarter 3 2012 PPR. FRBA will also be address any budget category changes in its budget realignment which is in process during February and will be reported prior to the quarter 1 2013 PPR submission. | 60 | Inspired completed staging microwave and IP equipment in the cabinets at the FRBA warehouses in quarter 4 which will reduce the deployment cycle time since this work will now not have to be done in the field. Also, G4Ss' plan to have separate civil and tower crews will result in equipment being deployed at a faster pace by removing unrelated dependencies between each of these efforts. | 10 | FRBA has engaged Inspired to do individual link and end-to-end network testing after G4S completes construction. This work will include the integration of the links into the data centers and also a quality assurance function to ensure the sites are ready to support customer traffic after construction is complete on each link. | 2013-03-12 16:17 | 2013-03-12 16:17 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2013 | Q1 | Q1 - 2013 | 9977 | 8533 | TRUE | 70 | Project is ahead of 4Q projection of 69%. | 90 | In-Kind Assets | Project is behind 4Q projection of 100%. The variance is attributed to not having leases for In-Kind sites. | 0 | N/A | 70 | Project is behind 4Q projection of 85%. The variance is primarily attributed to delays in completing designs for sites without leases or lease amendments. | 0 | N/A | 70 | Project is ahead of 4Q projection of 69%. | 0 | N/A | 60 | Project is behind 4Q projection of 69%. The variance is primarily attributed to delays in purchasing: (1) site specific equipment for sites without leases/lease amendments, and (2) ancillary data center equipment pending resolution of a legal matter that prevented required negotiations. | 48 | Project is behind 4Q projection of 54%. The variance is primarily attributed to: (1) delays on water tower construction, and (2) resolution of punch-list items at sites where construction has been completed. | 60 | Project is ahead of 4Q projection of 54%. | 10 | Project is behind 4Q projection of 54%. The variance is primarily attributed to delays in water tower construction, which has delayed Quality Assurance and Site Acceptance efforts. | 2013-05-29 17:24 | 2013-05-29 17:24 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2013 | Q2 | Q2 - 2013 | 10777 | 9058 | TRUE | 74 | Project fell behind projected schedule due to: (1) transition of work between sub-contractors for North and South sites, and (2) execution of lease amendments at commercial sites which most were completed late 2Q2013. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 90 | In-Kind Assets | Project is behind 1Q projection of 100%. The variance is attributed to not having several leases for In-Kind sites. | 0 | N/A | 70 | Project is behind 1Q projection of 75%. The variance is primarily attributed to delays in completing designs for sites without leases or lease amendments. | 0 | N/A | 70 | Incremental progress in 2Q2013 for Permits was limited to sites where lease and lease amendments were executed. Permits for sites where lease amendments are executed in later May will be pushed into 3Q2013 pending completion of dependencies listed above. Final Network Design has been submitted at this time. | 0 | N/A | 61 | Project is behind 1Q projection of 62%. The variance is primarily attributed to delays in purchasing: (1) site specific equipment for sites without leases/lease amendments. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 49 | Project is behind 1Q projection of 57%. The variance is primarily attributed to: (1) delays on water tower construction, and (2) resolution of punch-list items at sites where construction has been completed. (3) Intermittent subcontractor turnover (4) Lease and Lease Amendments not being received. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 61 | Project is behind 1Q projection of 62%. Minimal incremental Equipment Purchases were made in 2Q2013 due to slow receipt of lease amendments, Design Work, Permits and finalization of IRU re-configuration negotiations, as described in 2c-f. Purchase of additional equipment will be pushed into 3Q2013 pending completion of dependencies listed above. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 20 | Project is ahead of 1Q projection of 10%. | 2013-08-28 01:21 | 2013-08-28 01:21 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2013 | Q3 | Q3 - 2013 | 11415 | 9528 | TRUE | 79 | Project fell short of quarterly projections by 7%, but made significant gains overall. Original delays continue to effect status as noted: (1) transition of work between sub-contractors for North and South sites, and (2) execution of lease amendments at commercial sites which most were completed late 2Q2013. This percentage compete is actually higher based on FRBA's project tracker but delays in contractor billing is causing a delay in actual draw down of construction grant funds. Construction has nearly been completed in 3Q2013 with only minimal outliers to complete. Focus has transitioned from Construction to Customer Outreach/Fulfillment. | 80 |  | Project is behind quarterly projection of 90%. The variance is attributed to having to request several amendments to leases for In-Kind capital leases. The 80% figure is less than the Q2 PPR reported figure of 90% due to FRBA's project rebudget. The rebudget has been submitted and approved by NTIA. | 0 | N/A | 95 | Project exceeded quarterly projections of 75%. During 3Q2013 final Network Design documentation was submitted and recommended for approval alleviating further effort for additional EHP concerns. No further changes are required for Core Network Build-Out, but a specific service area in Franklin County has required additional review due to reduced altitudes for equipment location at a specific tower. | 0 | N/A | 95 | Project exceeded quarterly projections of 75%. The permitting process was materially completed in 3Q2013. Final Network Design has been submitted at this time pending any mutual agreed upon changes by FRBA and FPO. | 0 | N/A | 90 | Project exceeded quarterly projections of 62%. This percentage complete is saw significant gains as FRBA's budget realignment, submitted to NTIA has been approved. | 74 | Project exceeded quarterly projections of 57%. All facets of the network build have been completed due to additional resources being added to the project and final designs being nailed down. This percentage complete also saw significant gains as FRBA's budget realignment, submitted to NTIA has been approved. | 90 | Project exceeded quarterly projections of 62%. Substantial Equipment Purchases were made in 3Q2013 due to receipt of lease amendments, Design Work, and Permits. Purchase of additional equipment will be pushed into 3Q2013 pending completion of dependencies listed above. | 11 | Project is behind quarterly projection of 50%. An intentional delay in Network Testing has occurred as FRBA on-boards a network operator. Multiple meetings with network operator has yielded a deliberate change in integration and scripting that would had resulted in a re-touch of all field devices if configured and tested prematurely. Testing and integration plans have already been finalized going into 4Q and will undoubtedly be completed prior to to the end of 4Q2013. The 11% percent complete is less than the Q2 PPR reported figure of 20% due to FRBA's project rebudget, which reallocated cost in this category. The rebudget has been submitted and approved by NTIA. | 2013-11-26 20:35 | 2013-11-26 20:35 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2013 | Q4 | Q4 - 2013 | 11917 | 10083 | TRUE | 85 | Project fell short quarterly projections, but continued to make gains in the areas of middle-mile network deployment. | 0 | N/A | In previous quarters, this section described In-Kind. This quarter In-Kind is included in question 2g. | 0 | N/A | 91 | Project fell short of quarterly projections of 100%. During 4Q2013 alternative sites had to be considered in the North and South due to a combination of elevation issues at FRH-024 as well as a failed structural at FRL-063. Alternative sites have been submitted but are pending approval with the NTIA. | 0 | N/A | 81 | Project fell short of quarterly projections of 100%. During 4Q2013 alternative sites had to be considered in the North and South due to a combination of elevation issues at FRH-024 as well as a failed structural at FRL-063. Alternative sites have been submitted but are pending approval with the NTIA. | 0 | N/A | 90 | Project fell short of quarterly projections. Equipment necessary to complete network build has been procured and adequate inventories exist to account for any moderate changes that may occur to middle-mile sites. Remaining percentage exists for miscellaneous equipment and materials that may needed to meet FRBA last mile installation acceptance per the FRBA standard for last mile installations recently created and adopted in 4Q2013. | 81 | Project fell short of quarterly projections of 100%. Network Build is materially complete. Outliers remain to be alternative sites added due to elevation and structural issues. | 81 | Project fell short of quarterly projections of 100%. Network Build is materially complete. Outliers remain to be alternative sites added due to elevation and structural issues. | 46 | Network testing is materially complete. Only the previously mentioned alternative sites remain in the construction schedule. Consequently, the associated links have cannot be tested. | 2014-02-28 10:44 | 2014-02-28 10:44 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570123 | 2010 | Q4 | Q4 - 2010 | 603 | 1622 | TRUE | 5 | Project is on track with Baseline | 50 | Tower site leases on private land | Tower site lease agreements with private landowners (2 sites) are under negotiations | 75 | Winter weather has constrained the Section 106 field review process. The THPO, NTIA, FCC and project development staff are working diligently to develop a Programmatic Agreement to reach an agreed upon process for mitigative actions if necessary to enable the EA process to meet the established time line. | 75 | Microwave network specifications and specific tower site detail under development for site specifications and planning. | 50 | Communication and coordination between network development staff and the Power Utility for line expansion are underway | 50 | Consultations are underway as part of the Environmental Analysis | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-01-27 13:41 | 2011-01-27 13:41 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2011 | Q1 | Q1 - 2011 | 2065 | 2778 | TRUE | 10 | Project is mostly on track with Baseline; power service line rights of way have been delayed due to ongoing negotiations between the Tribe and Private landowners to access TU 71 site. | 100 |  | Land lease agreements for non tribal tower sites have been finalized; and, Collocation agreement language with project partners have been agreed upon. | 100 | Final EA submitted for review; A Programmatic Agreement reached between the Tribe and NTIA regarding Historic & Cultural Resource site surveys. No additional costs or project development issues are expected as a result of site reviews under the Programmatic Agreement. | 100 | Tower locations and network design complete | 90 | Site access agreements and Resolutions in place; Utility corridor rights of way still under negotiation to support line extension to tower sites (Beard and TU 71). The project should be back on track with Baseline for the next reporting Quarter ( Y1Q4) ending 6/30/2011. BIA service line agreement for electrical utility have been initiated. | 50 | Due to timing of applications for County Planning & Zoning the project filing of applications and presenting for Conditional Use permits has been delayed. Filings will be made during the next Quarter to get back on track. | 0 | NA | 1 | Two pick up trucks have been purchased as approved in the project six month budget. Network equipment procurement will get back on track during the next Quarter (ending 6/30/2011); equipment for placement on existing towers will be initiated early during Y1Q4. | 0 | Installation of equipment purchased for existing towers will be installed during the next Quarter, which will get the project back on track with Baseline Y1Q4 milestones. | 0 | Deployment of network equipment for existing towers will be installed during the next Quarter, which will get the project back on track with Baseline Y1Q4 milestones. | 0 | NA | 2011-05-16 19:40 | 2011-05-16 19:40 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2011 | Q2 | Q2 - 2011 | 3331 | 3428 | TRUE | 20 | Cold, wet spring conditions held up cultural resource site surveys, site access for site development and construction activity. During the next quarter the project is expected make great steps forward and should be at 40% of Baseline. Project percent complete and budget expenditures are out of line; staff recently learned that federal funding draw down requests are significantly behind the procurement process, which causes a reporting difference when comparing federal expenditure and project activities. In the budget the funding expenditure reported is in line with the other fiscal reports but the project accomplishments are father along, which results in a disconnect between percentage completion and fund expenditure. | 100 |  | Private land lease agreements and tower collocation agreement language have been approved. | 100 | Completed; and, all sites cleared for development by Tribal Historic Preservation Officer. | 100 | Tower locations and network design complete. | 95 | Final negotiations underway for the Beard and TU 71 sites between private landowners and the Nez Perce Tribe. Negotiations for TU 71 have stopped; the power utility company, after going out on site with construction engineers realized they could not deliver power to the site within the budgetary constraints of the Tribe's BTOP award. Project staff are working to identify an alternative site to TU 71. Negotiations regarding access to the Beard site are moving along well and are expected to be completed early during the next quarter. | 95 | Planning & Zoning Conditional Use permits all issued; waiting on building permits for two towers (Beard, Peck), which are expected to be issued early next quarter. | 10 | NEPA Cultural Resource clearance received this quarter; Request for Bids issued on Site access road work and Utility Service Line Agreements submitted to Bureau of Indian Affairs. On the ground activity will be back on track during the next quarter, weather permitting. | 30 | Purchased to date:Pick up (2); UTV (1); and, Wireless Radio Equipment for thirteen of the fifteen links has been ordered. The remaining links' equipment will be procured following the solution to the network dilemma around TU 71, which appears to be undeveloped. Expected to be on track with baseline by Year 2 Qtr2. | 0 | Wet spring conditions hindered site access so the project is behind baseline projection. Tower construction expected to be underway during next quarter. | 0 | Installation will commence early next quarter; a wet, cold spring held up site access on existing towers. | 0 | NA | 2011-08-26 15:38 | 2011-08-26 15:38 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2011 | Q3 | Q3 - 2011 | 3975 | 3826 | TRUE | 27 | The project got a slow start but is getting back on track with construction contracts awarded and underway. Financial draws are lagging behind project development activities, which results in a difference between programmatic accomplishment reporting and fiscal expenditure amounts. | 100 | Site Lease Agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 90 | Access roads complete; power access underway; five foundations completed. Beard foundation is expected early next Qtr; and the seventh tower site development is likeley during winter (pending modification approval). Site preparation should be in line with Baseline next reporting quarter. | 75 | Space constraints for secure storage of microwave antennae has held back ordering of all the necessary bulky items. Ordering will commence as space becomes available. TO relieve space constrainst a shop building is under construction, expected to be complete early next Qtr. | 1 | Delayed construction of the towers has the project behind baseline for build out. One last mile site is up; on an exiting tower; and collocation agreements for the remaining four partner towers is in negotiations, expected complete early next Qtr. | 1 | Delayed construction of the towers has the project behind baseline for build out. One last mile site is up; on an exiting tower; and collocation agreements for the remaining four partner towers is in negotiations, expected complete early next Qtr. | 1 | Delayed construction of the towers has the project behind baseline for build out. One last mile site is up; on an exiting tower; and collocation agreements for the remaining four partner towers is in negotiations, expected complete early next Qtr. | 2011-11-10 16:57 | 2011-11-10 16:57 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2011 | Q4 | Q4 - 2011 | 5189 | 4856 | TRUE | 52 | Construction contracting was slow to start which set the project back; construction is currently 80% complete with four of the seven tower complete and 2 towers at 90% complete and once modification of the last remaining tower is approved we will be immediately issuing an RFP for construction. We expect to be at 100% early in Q 2 of 2012 Financial draws and payments by the Tribe Finance department are chronically lagging behind project development activities, which results in a difference between programmatic accomplishment reporting and fiscal expenditure amounts. | 100 | Site Lease Agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 90 | Access roads complete; six foundations completed; six towers stacked to highest level; four communications buildings set; four site compound work complete; and power access delivered to four sites. Two sites need communication buildings and power access; the contract is awarded and the pre fab buildings have been back-ordered, expect completion of site work at 6 of the 7 new tower sites to be complete early next quarter. Following approval of modification tower construction request for bids will be advertised. | 95 | completed for the 12 links; Last mile equipment procurement is underway. | 7 | Delayed construction of the towers has the project behind baseline for build out. One last mile site is up; on an exiting tower; and collocation agreements for the remaining four partner towers are complete. Middle mile equipment installation contract has been awarded, expect to have middle mile ring complete early Q1 2012 and last mile equipment installations underway throughout Q1 2012. | 7 | Delayed construction of the towers has the project behind baseline for build out. One last mile site is up; on an exiting tower. All middle mile equipment is procured and configuration complete; a contract for installation is awarded and work will start early 2012. Middle mile is expected to be complete on eleven of the thirteen links in early 2012. | 5 | Delayed construction of the towers has the project behind baseline for build out. Middle mile lab testing complete on 12 links; one last mile site is up; on an exiting tower; and the network testing complete and service being provided. Field network testing is expected to be underway by the end of Q1 2012; and lab testing of the remaining two links, pending modification approval. | 2012-02-22 14:32 | 2012-02-22 14:32 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2012 | Q1 | Q1 - 2012 | 6027 | 5613 | TRUE | 75 | Construction of the network is nearing baseline; eleven of the thirteen middle mile pathways have been completed. The project expects to be have all thirteen middle mile pathways completed in Q2 2012. Currently, three of the ten last mile access sites are up; equipment is on order and last mile access installation at towers should be complete in Q2 2012 and site surveys well underway. Subscriber connections are running two quarters behind the projected baseline. | 100 | Site lease agmts | Complete | 100 | Complete; a modification proposed in Q3 2011 was approved in Q2 2012 | 100 | Complete; however a last mile reeingineering effort was accomplished in Q 2 2012 that will get the project back on track for serving the projected subscriber base. | 100 | Complete | 100 | Complete | 95 | The final tower site development requires access raodway reconstruction and construction; acitivty to begin early Q 2 2012, weather is the only known factor affecting completion. | 97 | Middle mile equipment procurement is complete; Last mile equipment procurement is nearing completion | 60 | Middle mile is 84% complete; Last mile is 27% complete | 60 | Middle mile is 84% complete; Last mile is 27% complete. Delays early on in construction set the whole project back several quarters, we are rapidly catching up and expect to be at 100% by the end of Q2 2012 | 60 | Three pathways to test on the middle mile; and eight last mile sites to configure remain | 2012-05-10 16:37 | 2012-05-10 16:37 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2012 | Q2 | Q2 - 2012 | 7059 | 6157 | TRUE | 81 | For the first project reporting quarter, construction activities are in line with the baseline. | 100 | Site lease agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 99 | Middle mile equipment procurement is complete; there are switch and routers needed to complete two of the last mile sites | 100 | Complete | 90 | Completed wireless radio/antennae installation; there are two sites needing switching equipment | 75 | Middle mile paths are complete adn tested except KIYE-TU64; for some unknown reason when we connect this MM link KIYE looses connection to the rest of the network. This middle mile problem is under investigation. Last mile sites tested and on line: Stoney Pt, Culdesac, TU 17. Crews are working diligently and all LM sites will be tested by early Q3 2012. | 2012-08-14 13:07 | 2012-08-14 13:07 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2012 | Q3 | Q3 - 2012 | 7979 | 6696 | TRUE | 91 | The project is slightly behind the Baseline; a marketing plan will soon be implemented to bolster the awareness of the network to the business community. To date, all site construction is complete; middle mile paths have been established; and, nine last mile sites are on line. | 100 | Site lease agmts | complete | 100 | complete | 100 | complete | 100 | complete | 100 | complete | 100 | complete | 99 | Identifying gap areas where we may need to add equipment onto existing infrastructure to fill in last mile service area gaps. | 100 | complete | 99 | Working to deploy equipment to fill in last mile service area gaps. | 99 | Testing connection strength in gap areas and last mile solutions | 2012-11-20 14:03 | 2012-11-20 14:03 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2012 | Q4 | Q4 - 2012 | 9141 | 7957 | TRUE | 96 | During Q4 the project infrastructure construction became in line with baseline; connections are lagging behind baseline and the last mile delivery interference at KIYE has caused the project to fall behind on end user connections. A marketing plan has been approved by Tribal Council and will be implemented. To date, ten (10) of the eleven (11) last mile sites are on line; two neighborhood solutions (Culdesac & Dumbo Flats) are on line and two will be completed early Q1 2013 (Shenandoah & Clearwater transfer). | 100 | Site lease agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 99 | The KIYE tower last mile shielding devices are under investigation and procurement will be initiated Q1 2013. Identifying gap areas for last mile and developing solutions for service delivery. | 100 | Complete | 99 | Deployment of neighborhood solutions is underway to fill in last mile service gaps. | 99 | Testing is underway on last mile sites; KIYE issues are expected to resolved early Q1 2013. | 2013-03-22 13:38 | 2013-03-22 13:38 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2013 | Q1 | Q1 - 2013 | 9627 | 8346 | TRUE | 99 | The project is within baseline projection; construction of the infrastructure is complete. The KIYE tower problem continues to disrupt last mile access. Staff will implement a possible solution early Q2. | 100 | Site Use Lease Agmt | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 99 | KIYE tower deployment has been delayed with back ordered shielding equipment for the last mile access points. | 99 | Middle mile links testing is complete; final testing of last mile access points are held up at KIYE, all other sites are functioning. | 2013-05-08 13:38 | 2013-05-08 13:38 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2013 | Q2 | Q2 - 2013 | 10715 | 9021 | TRUE | 99 | Construction and network deployment has been completed. There are funds remaining $ 19395.99 or 1%. | 100 | Site Lease Agmt | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-08-23 16:56 | 2013-08-23 16:56 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2013 | Q3 | Q3 - 2013 | 11457 | 9571 | TRUE | 100 | Complete | 100 | Site Use Agmt | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-12-09 19:13 | 2013-12-09 19:13 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570125 | 2010 | Q4 | Q4 - 2010 | 1223 | 2254 | TRUE | 4 | The overall project is on track with the Baseline Project Plan. Some of the actual expenditures are less than the baseline projections of 7%, but the Q3 cumulative results should be more comparable to the milestone projections. | 14 | Administration | The baseline has a 34% milestone due to an error made at time of initial baseline submission. These dollars should have been spread over all the quarters of the project. The overall project milestones/tasks remain on track. | 36 | The project is on track to file the Draft EA on February 1. The dollars will continue to be spent in Q3 so that the expenditures track more closely with the actual project status. We had anticipated being 53% complete but the bulk of the California Environmental Quality Act (CEQA) work did not occur as anticipated in Q2, but will be occurring in Q3. | 19 | The baseline has a 30% milestone. Some of the actual expenditures are less than the baseline projections, but the Q3 cumulative results should be more comparable to the milestone projections. | 0 | The baseline has a 50% milestone. $90,000 was budgeted to be spent on acquiring a site for the fiber node, which is being evaluated and may occur in Q3. | 7 | The 7% is very close to the baseline projection of 8%. | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 2011-02-18 15:40 | 2011-02-18 15:40 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2011 | Q1 | Q1 - 2011 | 2339 | 2915 | TRUE | 7 | The overall project is on track with the Baseline Project Plan. Some of the actual expenditures are tracking behind than the baseline projections of 11%, but the Q4 cumulative results should be more comparable to the milestone projections. | 28 | Administration | The Baseline has a 47% milestone. The majority of the variance is due to dollars that should have been allocated differently in the baseline budget submission. | 70 | The Baseline anticipated 82% complete. The environmental process is on track with the work that is required to be completed, and additional work will continue in Q4 on the California Environmental Quality Act (CEQA). The remainder of the dollars will be spent in Q4. | 37 | The Baseline has a 65% milestone. The specific budget line item where the in-kind contribution has not occurred relates to the pole leased space for the initial attachment. The timing in the initial baseline may have been a quarter too early. Engineering design will also continue into Q4. | 1 | The Baseline has a 61% milestone. The actual percent complete is only 1% as the primary driver of this budget milestone is the acquisition of a node site and the associated permits. Discussions on the site specifics are ongoing. | 13 | The Baseline has a 24% milestone. The focus in Q3 has been the environmental work, and the focus for Q4 and the following quarter will be in obtaining the construction permits and franchise permits. | 0 | None | 0 | None | 0 | None | 0 | None | 0 | None | 2011-05-26 12:33 | 2011-05-26 12:33 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2011 | Q2 | Q2 - 2011 | 3285 | 3405 | TRUE | 10 | The Baseline anticipated 14% overall completion. | 40 | Administration | The Baseline has a 57% milestone. The majority of the variance is due to dollars that should have been allocated differently in the baseline budget submission. | 97 | The Baseline anticipated 88% completion and this milestone is at 97% complete, primarily due to all of the work required for the federal and state environmental approvals. | 56 | The Baseline anticipated 85% completion. The variance is due to not incurring joint pole engineering costs in the quarter previously anticipated and both overhead and underground engineering work is continuing. This milestone will increase next quarter and close the gap on percent complete. | 6 | The Baseline has a milestone of 84% which is a cumulative total in dollars of $150,000 but through this reporting quarter $10,439 has been spent. $110,000 of the dollars not spent relate to a line item for acquiring the site for a fiber node. Fiber node site acquisition evaluation to continue into third quarter of 2011. | 16 | The Baseline has a 59% milestone. Approval of CLEC status in CA will allow for more progress in this area next quarter. | 0 | None | 0 | None | 0 | None | 0 | None | 0 | None | 2011-08-23 17:38 | 2011-08-23 17:38 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2011 | Q3 | Q3 - 2011 | 4041 | 3861 | TRUE | 14 | The baseline anticipated 36% overall completion, variances as described in detail below. | 57 |  | The baseline had projected 66%. The majority of the variance continues to be due to dollars that should have been allocated differently in the baseline budget submission. | 100 | As projected in baseline. | 90 | The baseline projection was 97% Finishing joint pole engineering and overhead and underground design is coming closer to concluding. | 27 | The baseline projected 87% this variance is due to the budgeted $110,000 for nodes site acquisition, which has not yet occurred. Fiber node site acquisition evaluation will continue into the fourth quarter of 2011. | 38 | The baseline had projected 77%. Delays caused in this area due to delay in acquiring FONSI. | 0 | The baseline had projected 100%, delay in construction activities due to FONSI acquisition delay. | 0 | The baseline had projected 18%, delay in procurement purchasing due to delay in acquiring FONSI. RFP's have been continuing in the area of equipment procurement, positioning us to move forward with procurement once FONSI is acquired. | 0 | The baseline had projected 34%. Construction not started as a result of delay in acquiring FONSI. | 0 | None | 0 | The baseline had projected 13%. Construction not started as a result of delay in acquiring FONSI. | 2011-11-14 19:32 | 2011-11-14 19:32 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2011 | Q4 | Q4 - 2011 | 5263 | 4932 | TRUE | 22 | This is a -1% variance from our previous project indicators projection. See below categories to see minor shifting. | 76 | Administration | Variance of +7% due to actual labor coming in higher than projected in the previous project indicators projection. | 100 | No change. | 100 | No change. | 30 | Variance of +3% from our previous project indicators projection with more right of way work being completed. | 48 | Variance of -1% from our previous project indicators projection with invoices coming in slightly under the projections for the quarter. | 0 | No change. | 25 | Variance of -1% from our previous project indicators projection. With a slight variance of invoices coming in over the projections for the quarter. | 2 | Variance of -2%, with the FONSI being acquired at the end of the quarter some network build activities began. | 0 | No change. | 0 | No change. | 2012-02-24 20:07 | 2012-02-24 20:07 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2012 | Q1 | Q1 - 2012 | 6095 | 5650 | TRUE | 33 | This is a +3% variance from our previous project indicators projection. See below categories to see minor shifting. | 90 | Administration | This is a +1% variance from our previous project indicators projection. Project management expenses came in slightly higher than forecast which was primarily driven by increased construction work. | 100 | No change. | 100 | No change. | 35 | This is a -13% variance. The largest line item impacting this category is funds to acquire property for our node placements. This will be addressed with an upcoming budget realignment. | 99 | This is a +26% variance from our previous project indicators projection. More construction permits were acquired during this period than we originally forecast to be finalized. | 0 | No change. | 43 | This is a +2% variance from our previous project indicators projection. Slight underprediction with final costs being slightly higher than forecast. | 11 | This is a +5% variance from our previous project indicators projection. Labor costs came in slightly higher than forecast due to more construction activity occurring then had been predicted. This was due to mild winter weather in our region. | 0 | No change. | 16 | This is a +16% variance from our previous project indicators projection. This was not originally forecast due to the unknown nature of the weather and construction that would be completed. As construction ramped up testing of the fiber ramped up with it. | 2012-05-15 13:37 | 2012-05-15 13:37 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2012 | Q2 | Q2 - 2012 | 7207 | 6231 | TRUE | 60 | 3% increase from our previous project indicators projection. See below categories to see changes. | 100 | Administration | Actual percentage was 105% over budget. Project management costs were slightly higher than anticipated. This line item will be addressed with our upcoming budget realignment. | 100 | No change. | 100 | No change. | 35 | 11% under previous project indicators projection. The largest line item impacting this category is funds to acquire property for our node placements. This will be addressed with an upcoming budget realignment. | 100 | Actual percentage was 114% over budget. This is 14% over the previous project indicators projection. More construction costs were required than we had originally budgeted for and this line item will be addressed with our upcoming budget realignment. | 83 | 11% under previous project indicators. Site preparation of our Node sites was begun and 95% completed. Not all work was completed as planned. | 100 | Actual percentage was 114% over budget. We completed our Fiber cable purchases and have completed approximately 95% of our Hardware purchases. Fiber was more expensive than anticipated plus an additional 13 miles was purchased for a route change that has been approved thru an AAR. This line item will be addressed with our upcoming budget realignment. | 30 | 6% higher than previous project indicators projection. More construction activity occurred due to favorable construction schedules. | 2 | 10% lower than previous project indicators projection. Changes in design and type of equipment caused a delay in anticipated purchasing of equipment. | 20 | 7% lower than previous project indicators projection. This was due to lower than anticipated labor costs and testing not completed. This line item will be addressed with our upcoming budget realignment. | 2012-08-22 13:22 | 2012-08-22 13:22 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2012 | Q3 | Q3 - 2012 | 8163 | 6792 | TRUE | 66 | 15% below our previous project indicators projection. See below categories to see changes. | 100 | Administration | Actual percentage was 123% over budget. Project management costs were slightly higher than anticipated. This line item will be addressed with our upcoming budget realignment. | 100 | No Change | 100 | No Change | 66 | 20% above previous project indicators projection. Unanticipated late billings were paid that were not in the forecast from last quarter. The largest line item impacting this category is budgeted funds to acquire property for our node placements that is not going to expended . This will be addressed with an upcoming budget realignment. | 100 | Actual percentage was 118% over budget. This is 18% over the previous project indicators projection. More construction costs were required than we had originally budgeted for and this line item will be addressed with our upcoming budget realignment. | 100 | Actual percentage was 259% over budget. This is 159% over the previous project indicators projection. More construction costs were required than we had originally budgeted for and this line item will be addressed with our upcoming budget realignment. | 100 | Actual percentage was 115% over budget. Fiber was more expensive than anticipated plus an additional 13 miles was purchased for a route change that has been approved thru an AAR. This line item will be addressed with our upcoming budget realignment. | 35 | 7% lower than previous project indicators projection. Less construction activity occurred due to quicker completion of the majority of Aerial Cable installation. | 9 | 91% lower than previous project indicators projection. Approximately $800,000 in equipment that was anticipated to be purchased in September (3rd Qtr)is not being purchased until November (4th Qtr). | 20 | 10% lower than previous project indicators projection. This was due to lower than anticipated labor costs and testing not completed. This line item will be addressed with our upcoming budget realignment. | 2012-11-29 23:27 | 2012-11-29 23:27 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2012 | Q4 | Q4 - 2012 | 9151 | 7976 | TRUE | 80 | 4% below our previous project indicators projection. Baseline had projected 100% complete. See below categories to see changes. | 100 | Administration | Actual percentage was 141% over budget. Project management costs are higher than anticipated. This line item will be addressed with our upcoming budget realignment. | 100 | No Change. Baseline had projected 100%. | 100 | No Change. Baseline had projected 100%. | 75 | 9% above previous project indicators projection. Unanticipated late billings were paid that were not in forecast form last PPR. Baseline had projected 100%. The largest line item impacting this category is budgeted funds to acquire property for our node placements that is not going to be expended . This will be addressed with an upcoming budget realignment. | 100 | Actual percentage was 121% over budget. More construction costs were required than we had originally budgeted for and this line item will be addressed with our upcoming budget realignment. | 100 | Actual percentage was 259% over budget. More construction costs were required than we had originally budgeted for and this line item will be addressed with our upcoming budget realignment. | 100 | Actual percentage was 118% over budget. Fiber was more expensive than anticipated plus an additional 13 miles was purchased for a route change that has been approved thru an AAR. This line item will be addressed with our upcoming budget realignment. | 40 | 3% lower than previous project indicators projection. Less construction activity occurred due to delays associated with weather and delays related to the Susanville area. Baseline had projected 100%. | 100 | Actual percentage was 104% over budget. More equipment costs were required than we had originally budgeted for and this line item will be addressed with our upcoming budget realignment. | 20 | 15% lower than previous project indicators projection. This was due to lower than anticipated labor costs. This line item will be addressed with our upcoming budget realignment. Baseline had projected 91%. | 2013-03-28 14:00 | 2013-03-28 14:00 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2013 | Q1 | Q1 - 2013 | 9941 | 8514 | TRUE | 85 | 4% below our previous project indicators projection. Baseline had projected 100% complete. See below categories to see changes. | 100 | Administration | Actual percentage was 158% over budget. Project management costs are higher than anticipated. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 100 | No Change. Baseline had projected 100%. | 100 | No Change. Baseline had projected 100%. | 75 | 25% below previous project indicators projection. The largest line item impacting this category is budgeted funds to acquire property for our node placements that is not going to be expended . This will be addressed with an upcoming budget realignment. | 100 | Actual percentage was 131% over budget. More construction costs were required than we had originally budgeted for. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 100 | Actual percentage was 267% over budget. More construction costs were required than we had originally budgeted for. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 100 | Actual percentage was 121% over budget. Fiber was more expensive than anticipated plus an additional 13 miles was purchased for a route change that has been approved thru an AAR. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 44 | On target with previous project indicators projection. Baseline had projected 100%. | 100 | Actual percentage was 113% over budget. More equipment costs were required than we had originally budgeted for. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 20 | 2% lower than previous project indicators projection. This was due to lower than anticipated labor costs. This line item will be addressed with our upcoming budget realignment. Baseline had projected 100%. | 2013-05-28 16:08 | 2013-05-28 16:08 | 6039 | 6039 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2013 | Q2 | Q2 - 2013 | 10629 | 8975 | TRUE | 95 | 1% below our previous project indicators projection. Baseline had projected 100% complete. See below categories to see changes | 100 | Administration | Actual percentage was 177% over budget. Project management costs are higher than anticipated. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 100 | No Change. Baseline had projected 100%. | 100 | No Change. Baseline had projected 100%. | 77 | 2% above previous project indicators projection. The largest line item impacting this category is budgeted funds to acquire property for our node placements that is not going to be expended . This will be addressed with an upcoming budget realignment. | 100 | Actual percentage was 135% over budget. More construction costs were required than we had originally budgeted for. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 100 | Actual percentage was 267% over budget. More construction costs were required than we had originally budgeted for. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 100 | Actual percentage was 135% over budget. Fiber was more expensive than anticipated plus an additional 13 miles was purchased for a route change that has been approved thru an AAR. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 50 | 2% below previous project indicators projection. Baseline had projected 100%. | 100 | Actual percentage was 150% over budget. More equipment costs were required than we had originally budgeted for. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 20 | 28% lower than previous project indicators projection. This was due to lower than anticipated labor costs. This line item will be addressed with our upcoming budget realignment. Baseline had projected 100%. | 2013-08-19 05:04 | 2013-08-19 05:04 | 7691 | 7691 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2013 | Q3 | Q3 - 2013 | 12451 | 10634 | TRUE | 100 | Matches Projections. Baseline had projected 100.% | 100 |  | Matches Projections. Baseline had projected 100.% | 100 | No Change. Baseline had projected 100.% | 100 | No Change. Baseline had projected 100.% | 100 | Matches Projections. Baseline had projected 100.% | 100 | Matches Projections. Baseline had projected 100.% | 100 | Matches Projections. Baseline had projected 100.% | 100 | Matches Projections. Baseline had projected 100.% | 100 | Matches Projections. Baseline had projected 100.% | 100 | Matches Projections. Baseline had projected 100.% | 100 | Matches Projections. Baseline had projected 100.% | 2014-08-22 16:25 | 2014-08-22 16:25 | 6039 | 6039 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570126 | 2010 | Q4 | Q4 - 2010 | 1323 | 2348 | TRUE | 1 | N/A | 0 | N/A | N/A | 80 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-23 10:48 | 2011-02-23 10:48 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2011 | Q1 | Q1 - 2011 | 2155 | 2823 | TRUE | 1 | No change from the baseline plan | 0 | N/A | N/A | 70 | Biological field surveys were slightly delayed due to seasonal weather. At the time CVIN indicated 80% completion in the last quarter, we did not know the full scope of EA costs or the extent of EA work that would be required. The complete EA scope of work was finalized after the previous PPR was submitted. The 70% EA completion is the most accurate estimate to date. The EA cost change is well under 10%. It is expected that EA will be back in line with the baseline in Q2-2011. | 15 | After anticipating an increase in Network Design efforts last quarter, we encountered a slight delay in awarding the Engineering contract. We are now back at the original baseline projection of 15%. It is expected that we will remain in line with the baseline schedule. | 0 | Not yet begun | 0 | Not yet begun | 0 | Not yet begun | 0 | Not yet begun | 0 | Not yet begun | 0 | Not yet begun | 0 | Not yet begun | 2011-05-18 18:37 | 2011-05-18 18:37 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2011 | Q2 | Q2 - 2011 | 2923 | 3219 | TRUE | 3 | Construction could not commence this Quarter since the FONSI was not issued. Construction will commence next Quarter and we anticipate catching up to the baseline during Quarter 4, 2011. | 0 | N/A | N/A | 95 | All biological and habitat studies, maps, and surveys have been provided to the USFWS seeking a letter of concurrence that the project may affect, but is not likely to adversely affect Federally-listed species. It is anticipated that the Environmental Assessment will be completed by the end of July and back in line with the baseline. | 50 | Our Engineering Firm experienced some internal issues which resulted in additional delays. Several segments of the engineering design plans are completed and the remaining are anticipated to be completed by August of 2011 which will put us back in line with the baseline. | 35 | No change from the baseline plan. | 35 | No change from the baseline plan. | 0 | Construction could not commence this Quarter since the FONSI was not issued. Construction will commence next Quarter and we anticipate catching up to the baseline during Quarter 4, 2011. | 0 | Construction could not commence this Quarter since the FONSI was not issued. Construction will commence next Quarter and we anticipate catching up to the baseline during Quarter 4, 2011. | 0 | Construction could not commence this Quarter since the FONSI was not issued. Construction will commence next Quarter and we anticipate catching up to the baseline during Quarter 4, 2011. | 0 | Construction could not commence this Quarter since the FONSI was not issued. Construction will commence next Quarter and we anticipate catching up to the baseline during Quarter 4, 2011. | 0 | No change from the baseline plan. | 2011-08-04 13:06 | 2011-08-04 13:06 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2011 | Q3 | Q3 - 2011 | 3983 | 3830 | TRUE | 5 | Construction could not commence this quarter since the FONSI was not issued until September 30, 2011. Construction will commence next quarter and we anticipate catching up to the baseline during Q1-2012. | 0 |  | N/A | 100 | No change from the baseline. | 85 | Additional delays experienced with engineering firm. We anticipate catching up to the baseline during Q4-2011. | 50 | We are slightly behind schedule due to delays from network design and rights of way authorities. We anticipate catching up to the baseline during Q4-2011. | 50 | We are slightly behind schedule due to delays from network design and permitting authorities. We anticipate catching up to the baseline during Q4-2011. | 0 | Construction could not commence this quarter since the FONSI was not issued until September 30, 2011. Construction will commence next quarter and we anticipate catching up to the baseline during Q1-2012. | 0 | Construction could not commence this quarter since the FONSI was not issued until September 30, 2011. Construction will commence next quarter and we anticipate catching up to the baseline during Q1-2012. | 0 | Construction could not commence this quarter since the FONSI was not issued until September 30, 2011. Construction will commence next quarter and we anticipate catching up to the baseline during Q1-2012. | 0 | Construction could not commence this quarter since the FONSI was not issued until September 30, 2011. Construction will commence next quarter and we anticipate catching up to the baseline during Q1-2012. | 0 | No change from the baseline. | 2011-11-10 19:19 | 2011-11-10 19:19 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2011 | Q4 | Q4 - 2011 | 5369 | 5038 | TRUE | 12 | Behind schedule on construction due to delays in acquiring FONSI and construction permits. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 85 | No change from the baseline. 85% of overall effort is complete though several final approvals are causing delays for other milestones. | 85 | No change from the baseline. 85% of overall effort is complete though several final approvals are causing delays for other milestones. | 20 | Behind schedule on construction due to delays in acquiring FONSI and construction permits. | 0 | Behind schedule on construction due to delays in acquiring FONSI and construction permits. Equipment procurement is delayed until it is needed when network construction progresses. | 10 | Behind schedule on construction due to delays in acquiring FONSI and construction permits. | 0 | Behind schedule on construction due to delays in acquiring FONSI and construction permits. | 0 | Behind schedule on construction due to delays in acquiring FONSI and construction permits. | 2012-02-28 17:15 | 2012-02-28 17:15 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2012 | Q1 | Q1 - 2012 | 6145 | 5675 | TRUE | 29 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No Change from the baseline. | 95 | Slightly behind baseline. 95% of overall effort is complete. California Department of Transportation (Caltrans) permits are one of the outstanding issues. | 95 | Slightly behind baseline. 95% of overall effort is complete. Caltrans permits are one of the outstanding issues. | 20 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 10 | Equipment procurement is delayed until it is needed as network construction progresses. | 30 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 10 | Equipment deployment is delayed until it is needed as network construction progresses. | 5 | Behind schedule on construction and equipment deployment because of initial delays in acquiring FONSI and construction permits. | 2012-05-16 19:57 | 2012-05-16 19:57 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2012 | Q2 | Q2 - 2012 | 7081 | 6168 | TRUE | 43 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 98 | Slightly behind baseline. California Department of Transportation (Caltrans) permits are one of the outstanding issues. | 98 | Slightly behind baseline. California Department of Transportation (Caltrans) permits are one of the outstanding issues. | 30 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 40 | Equipment procurement had been delayed until network construction progressed. Still behind schedule but expect significant progress next quarter and should be complete in Q4-2012. | 45 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. Began installing fiber optic cable this quarter. | 15 | Behind schedule due to construction delays. | 10 | Behind schedule due to construction delays. | 2012-08-15 14:59 | 2012-08-15 14:59 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2012 | Q3 | Q3 - 2012 | 8043 | 6728 | TRUE | 65 | Significant progress was made on underground construction and fiber optic cable installation this quarter. Behind schedule on construction due to initial delays in acquiring FONSI and construction permits. | 0 | N/A | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 99 | Will finalize last few rights-of-way issues next quarter. | 99 | Will finalize last few permit issues next quarter. | 50 | Behind schedule due to construction delays. | 95 | Purchased the bulk of fiber optic network equipment this quarter. Only slightly behind baseline. | 70 | Significant progress was made on underground construction and fiber optic cable installation this quarter. Behind schedule on construction due to initial delays in acquiring FONSI and construction permits. | 20 | Behind schedule due to construction delays. | 20 | Behind schedule due to construction delays. | 2012-11-26 13:03 | 2012-11-26 13:03 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2012 | Q4 | Q4 - 2012 | 8763 | 7559 | TRUE | 74 | Behind schedule due to initial underground construction delays. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 65 | Behind schedule due to initial underground construction delays. | 98 | Only last few items need to be purchased. | 74 | Behind schedule due to initial underground construction delays. | 30 | Behind schedule due to initial underground construction delays. | 30 | Behind schedule due to initial underground construction delays. | 2013-02-13 18:59 | 2013-02-13 18:59 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2013 | Q1 | Q1 - 2013 | 9987 | 8538 | TRUE | 81 | Behind schedule due to initial underground construction delays. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 85 | Behind schedule due to initial underground construction delays. | 100 | No change from the baseline. | 81 | Behind schedule due to initial underground construction delays. | 60 | Behind schedule due to initial underground construction delays. | 60 | Behind schedule due to initial underground construction delays. | 2013-05-29 18:50 | 2013-05-29 18:50 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2013 | Q2 | Q2 - 2013 | 10545 | 8927 | TRUE | 90 | Behind schedule due to initial underground construction delays. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 90 | Behind schedule due to initial underground construction delays. | 100 | No change from the baseline. | 90 | Behind schedule due to initial underground construction delays. | 70 | Behind schedule due to initial underground construction delays. | 70 | Behind schedule due to initial underground construction delays. | 2013-08-09 17:38 | 2013-08-09 17:38 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2013 | Q3 | Q3 - 2013 | 11263 | 9423 | TRUE | 100 | Actual expenditures are 106% of overall budget. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 95 | Behind schedule due to initial underground construction delays. | 85 | Behind schedule due to initial underground construction delays. | 85 | Behind schedule due to initial underground construction delays. | 2013-11-15 12:11 | 2013-11-15 12:11 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2013 | Q4 | Q4 - 2013 | 11827 | 10005 | TRUE | 100 | Actual expenditures are 115% of overall budget. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 96 | Behind schedule due to initial underground construction delays. | 95 | Behind schedule due to initial underground construction delays. | 95 | Behind schedule due to initial underground construction delays. | 2014-02-14 18:52 | 2014-02-14 18:57 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570127 | 2010 | Q4 | Q4 - 2010 | 1037 | 2077 | TRUE | 1 | Less than 1% funds expended as planned. | 0 |  | No Variance | 0 | Physically 75% complete. Cost has not been incurred. 100% cost to obtain a FONSI will be incurred in YR1-Q3 (Q1-2011) | 7 | Milestone baseline variance due to delay in obtaining matching funds. Design Engineering was not issued as planned for Midvale and Orem pending confirmation of match funds availability. Waiver for proportional draw down has been requested and work will be issued in Q1-2011. Matching funds will be available in YR1-Q4 (Q2-2011). | 7 | Milestone baseline variance due to delay in obtaining matching funds. Rights of Way engineering was not issued as planned for Midvale and Orem pending confirmation of match funds availability. Waiver for proportional draw down has been requested and work will be issued in Q1-2011. Matching funds will be available in YR1-Q4 (Q2-2011). | 7 | Milestone baseline variance due to delay in obtaining matching funds. Construction Permits and other approvals work were not issued as planned in Midvale and Orem pending confirmation of match funds availability. Waiver for proportional draw down has been requested and work will be issued in Q1-2011. Matching funds will be available in YR1-Q4 (Q2-2011). | 0 | No Variance | 0 | No Variance | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-02-10 10:19 | 2011-02-10 10:19 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2011 | Q1 | Q1 - 2011 | 2021 | 2756 | TRUE | 1 | It was anticipated the project would be 4% complete. See reason for variance in narratives below. | 0 |  | No Variance | 100 | A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic Structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements, and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities will begin in Q2-2011. | 10 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and Orem. The detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion, key indicators, and initial construction activities. In addition, design engineering was not issued as planned for Midvale and Orem pending confirmation of match funds availability. Waiver for proportional draw down was approved during Q1-2011 and work was issued in Q1-2011. Matching funds will be available in YR1-Q4 (Q2-2011). | 10 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and Orem. The detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion, key indicators, and initial construction activities. In addition, design engineering was not issued as planned for Midvale and Orem pending confirmation of match funds availability. Waiver for proportional draw down was approved during Q1-2011 and work was issued in Q1-2011. Matching funds will be available in YR1-Q4 (Q2-2011). | 10 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and Orem. The detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion, key indicators, and initial construction activities. In addition, design engineering was not issued as planned for Midvale and Orem pending confirmation of match funds availability. Waiver for proportional draw down was approved during Q1-2011 and work was issued in Q1-2011. Matching funds will be available in YR1-Q4 (Q2-2011). | 0 | No Variance | 0 | RFP's were awarded during Q1-2011 for equipment with the first orders being placed in Q1-2011 and the initial planned expenditures related to these orders will be incurred in Q2-2011. The delay in Q4-2010 confirming availability of matching funds to pay for the planned equipment also delayed the initial RFP release and UTOPIA will not actually incur the costs originally planned for the end of Q1-2011 until Q2-2011. A Waiver for proportional draw down was approved to allow the project to continue as planned until matching funds are available. Matching funds will be available sometime during YR1-Q4 (Q2-2011). The milestone baseline for equipment procurement should be fully recovered end of Q3-2011. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-05-13 15:27 | 2011-05-13 15:27 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2011 | Q2 | Q2 - 2011 | 2975 | 3245 | TRUE | 4 | See Narratives below indicating reasons for variance | 8 |  | Milestone baseline variance is due to lower than expected installation costs, extended time frames to actually incur project costs, and challenges in finalizing community anchor institution agreements. Twenty-one community anchor connections were connected during this quarter, but costs were not incurred. This variance will not negatively impact completion of the project. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic Structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements, and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. | 16 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and Orem. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion, key indicators, and initial construction activities. | 16 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and Orem. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion, key indicators, and initial construction activities. | 16 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, Orem, and West Valley. The construction permits and other approvals are dependent on securing these sites, and completing the network design and detailed route engineering. These delays are not expected to significantly impact project completion, key indicators, and initial construction activities. | 0 | Milestone baseline variance is because site preparation for six points of interconnection are still in progress. Costs for these sites will be incurred during the next quarter. | 1 | Milestone baseline variance continued into this quarter. Significant amounts of Equipment have been ordered, but not received. Costs for this equipment will be incurred during the next quarter. | 4 | Milestone baseline variance is due to use of existing conduit resulting in lower costs and extended time frames to incur project costs. Eleven miles of fiber were installed during this quarter and significant amounts of construction activities are in progress, but costs were not incurred. This variance will not negatively impact completion of the project. | 4 | Milestone baseline variance is due to extended time frames to incur project costs. Eleven miles of fiber were deployed during this quarter and significant amounts of construction activities are in progress, but costs were not incurred. This variance will not negatively impact completion of the project. | 4 | Milestone baseline variance is due to extended time frames to incur project costs. Eleven miles of fiber were deployed during this quarter and significant amounts of construction activities are in progress, but costs were not incurred. This variance will not negatively impact completion of the project. | 2011-08-09 13:55 | 2011-08-09 13:55 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2011 | Q3 | Q3 - 2011 | 4315 | 4008 | TRUE | 8 | See Narratives below indicating reasons for variance. It is actually slightly more than 8% complete. | 13 |  | Milestone baseline variance is due to lower than expected installation costs, extended time frames to actually incur project costs, and challenges in finalizing community anchor institution agreements. A primary resource for securing community anchor institution agreements left the organization and will be replaced shortly. Fifty-four community anchor connections are connected , but costs were fully not incurred. This variance will not negatively impact completion of the project. | 100 | No variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for attaching the Broadband Cable to Historic structures provided by NTIA and in concurrence with the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements, and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. | 26 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 26 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to impact project completion. | 26 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Construction Permits and Other Approvals lags slightly behind the completion of the Network Design. These delays are not expected to impact project completion. | 2 | Milestone baseline variance is because site preparation for six points of interconnection that are still in progress or costs have not been incurred. This variance is not expected to impact project completion | 1 | Milestone baseline variance continued into this quarter. Significant amounts of equipment have been ordered but costs have not been incurred to the project. Costs for this equipment will be incurred during the next few quarter as they are received and installed. | 8 | Milestone baseline variance is due to use of existing conduit resulting in lower costs and extended time frames to incur project expenditures and fiber. Seven additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress, but costs were not incurred. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. This variance will not negatively impact completion of the project. | 8 | Milestone baseline variance is due to use of existing conduit resulting in lower costs and extended time frames to incur project costs and fiber. Seven additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress, but costs were not incurred. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Equipment Deployment lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 8 | Milestone baseline variance is due to use of existing conduit resulting in lower costs and extended time frames to incur project costs and fiber. Seven additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress, but costs were not incurred. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Network Testing lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 2011-11-29 13:54 | 2011-11-29 13:54 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2011 | Q4 | Q4 - 2011 | 5223 | 4888 | TRUE | 14 | See Narratives below indicating reasons for variance. It is actually more than 14% complete. | 26 |  | Milestone baseline variance is due to lower than expected installation costs and challenges in finalizing community anchor institution agreements. A primary resource for securing community anchor institution agreements left the organization a few months ago. New resources are now in place. Thirty eight community anchor connections are connected , but costs are fully not incurred. This variance will not negatively impact completion of the project. | 100 | No variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for attaching the Broadband Cable to Historic structures provided by NTIA and in concurrence with the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements, and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. | 38 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem, and a delay in incurring the costs for work performed which would add an additional 10%. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 38 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem, and a delay in incurring the costs for work performed which would add an additional 10%. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to impact project completion. | 38 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem, and a delay in incurring the costs for work performed which would add an additional 10%. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to impact project completion. | 8 | Five points of interconnect are complete. Milestone baseline variance is because site preparation for six points of interconnection that are still in progress or costs have not been fully incurred. This variance is not expected to impact project completion | 16 | Significant progress was made during this Quarter, however milestone baseline variance continued into this quarter. Some equipment has been ordered but costs have not been incurred to the project. Costs for this equipment will be incurred during the next few quarters as they are received and installed. | 13 | Significant progress was made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs. Seven additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. This variance will not negatively impact completion of the project. | 13 | Significant progress was made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs. Seven additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Equipment Deployment lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 13 | Significant progress was made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs. Seven additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Network Testing lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 2012-02-23 16:14 | 2012-02-23 16:14 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2012 | Q1 | Q1 - 2012 | 6031 | 5615 | TRUE | 27 | See Narratives below indicating reasons for variance. It is actually slightly more than 27% complete. | 26 | true | Milestone baseline variance is due to lower than expected installation costs and challenges in finalizing community anchor institution agreements. Thirty eight community anchor connections are connected , but costs are fully not incurred. This variance will not negatively impact completion of the project. | 100 | No variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for attaching the Broadband Cable to Historic structures provided by NTIA and in concurrence with the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements, and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions to the project and required route changes to the project. | 61 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley, and a delay in incurring the costs for work performed which would add an additional 10%. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 61 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley, and a delay in incurring the costs for work performed which would add an additional 10%. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 61 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley, and a delay in incurring the costs for work performed which would add an additional 10%. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 17 | 12 points of interconnect are complete. Milestone baseline variance is because site preparation for six points of interconnection is still in progress or costs have not been fully incurred. This variance is not expected to impact project completion | 20 | Milestone baseline variance continued into this quarter. Some equipment has been ordered but costs have not been incurred to the project. Costs for this equipment will be incurred during the next few quarters as they are received and installed. | 27 | Significant progress was made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs. Eleven additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. This variance will not negatively impact completion of the project. | 27 | Significant progress was made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs. Eleven additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Equipment Deplyment lags slightly behind the completion of the network build. This variance will not negatively impact completion of the project. | 27 | Significant progress was made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs. Eleven additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Network Testing lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 2012-05-10 19:59 | 2012-05-10 19:59 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2012 | Q2 | Q2 - 2012 | 7001 | 6128 | TRUE | 42 | See Narratives below indicating reasons for variance. It is actually slightly more than 42% complete. | 28 |  | Milestone baseline variance is due to lower than expected installation costs and the challenges in finalizing community anchor institution agreements. Forty eight community anchor connections are connected, but costs are fully not incurred. This variance will not negatively impact completion of the project. | 100 | No variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for attaching the Broadband Cable to Historic structures provided by NTIA and in concurrence with the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements, and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 78 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley, and a delay in incurring the costs for work performed which would add an additional 10% to this number. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 78 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley, and a delay in incurring the costs for work performed which would add an additional 10% to this number. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 78 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley, and a delay in incurring the costs for work performed which would add an additional 10% to this number. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 17 | 15 points of interconnect are complete. Milestone baseline variance is because site preparation for 15 additional points of interconnection is still in progress or costs have not been fully incurred. This variance is not expected to impact project completion | 27 | Milestone baseline variance continued into this quarter. Some equipment has been ordered but costs have not been incurred to the project. Costs for this equipment will be incurred during the next two quarters as they are received and installed. | 44 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Ten additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. This variance will not negatively impact completion of the project. | 44 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Ten additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Equipment Deployment lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 44 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Ten additional miles of fiber were installed during this quarter and a significant amount of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Network Testing lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 2012-08-10 12:15 | 2012-08-10 12:15 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2012 | Q3 | Q3 - 2012 | 8077 | 6745 | TRUE | 50 | See Narratives below indicating reasons for variance. | 29 |  | Milestone baseline variance is due to lower than expected installation costs and the challenges in finalizing community anchor institution agreements. Fifty-eight community anchor connections are connected, but costs are fully not incurred. This variance will not negatively impact completion of the project. | 100 | No variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for attaching the Broadband Cable to Historic structures provided by NTIA and in concurrence with the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements, and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 87 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley, and a delay in incurring the costs for work performed which would add an additional 5% to this number. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 87 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley, and a delay in incurring the costs for work performed which would add an additional 5% to this number. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 87 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley, and a delay in incurring the costs for work performed which would add an additional 5% to this number. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 24 | 32 points of interconnect are placed. Milestone baseline variance is because site preparation for 32 additional points of interconnection is still in progress or costs have not been fully incurred. This variance is not expected to impact project completion | 38 | Milestone baseline variance continued into this quarter. Some equipment has been ordered but costs have not been incurred to the project. Costs for this equipment will be incurred during the next quarter as they are received and installed. | 52 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Forty-six additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. This variance will not negatively impact completion of the project. | 52 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Forty-six additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Equipment Deployment lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 52 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Forty-six additional miles of fiber were installed during this quarter and a significant amount of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Network Testing lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 2012-11-27 15:31 | 2012-11-27 15:31 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2012 | Q4 | Q4 - 2012 | 8913 | 7696 | TRUE | 63 | See Narratives below indicating reasons for variance. | 31 |  | Milestone baseline variance is due to lower than expected installation costs and the challenges in finalizing community anchor institution agreements. Sixty-eight community anchor connections are connected, but costs are fully not incurred. This variance will not negatively impact completion of the project. | 100 | No variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for attaching the Broadband Cable to Historic structures provided by NTIA and in concurrence with the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements, and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 95 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley, and a delay in incurring the costs for work performed which would add an additional 5% to this number. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 95 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley, and a delay in incurring the costs for work performed which would add an additional 5% to this number. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 95 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley, and a delay in incurring the costs for work performed which would add an additional 5% to this number. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. These delays are not expected to impact project completion. | 31 | 42 points of interconnect are placed. Milestone baseline variance is because site preparation for 42 points of interconnection is still in progress or costs have not been fully incurred. This variance is not expected to impact project completion | 38 | Milestone baseline variance continued into this quarter. Some equipment has been ordered but costs have not been incurred to the project. Costs for this equipment will be incurred during the next quarter as they are received and installed. | 65 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Forty-nine additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. This variance will not negatively impact completion of the project. | 65 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Forty-nine additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Equipment Deployment lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 65 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Forty-nine additional miles of fiber were installed during this quarter and a significant amount of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Network Testing lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 2013-02-22 15:22 | 2013-02-22 15:22 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2013 | Q1 | Q1 - 2013 | 10039 | 8571 | TRUE | 73 | See Narratives below indicating reasons for variance. | 35 |  | Milestone baseline variance is due to lower than expected installation costs and the challenges in finalizing community anchor institution agreements. Seventy-five community anchor connections are connected, but costs are fully not incurred. This variance will not negatively impact completion of the project. | 100 | No variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for attaching the Broadband Cable to Historic structures provided by NTIA and in concurrence with the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements, and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 100 | The Network Design and detailed route engineering including rights of way have been completed for the project. There are only a few minor route changes that will need approval from NTIA and a route modification request will be submitted for approval. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. | 100 | The Network Design and detailed route engineering including rights of way have been completed for the project. There are only a few minor route changes that will need approval from NTIA and a route modification request will be submitted for approval. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. | 100 | The Network Design and detailed route engineering including rights of way have been completed for the project. There are only a few minor route changes that will need approval from NTIA and a route modification request will be submitted for approval. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. | 39 | 45 points of interconnect are placed. Milestone baseline variance is because site preparation for 45 points of interconnection is still in progress or costs have not been fully incurred. This variance is not expected to impact project completion. | 46 | Milestone baseline variance continued into this quarter. Some equipment has been ordered but costs have not been incurred to the project. Costs for this equipment will be incurred during the next quarter as they are received and installed. | 79 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Twenty-six additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. This variance will not negatively impact completion of the project. | 79 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Twenty-six additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Equipment Deployment lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 79 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Twenty-six additional miles of fiber were installed during this quarter and a significant amount of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Network Testing lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 2013-05-31 18:29 | 2013-05-31 18:29 | 6069 | 6069 | Utopia | TRUE
NT10BIX5570127 | 2013 | Q2 | Q2 - 2013 | 10825 | 9085 | TRUE | 86 | See Narratives below indicating reasons for variance. | 37 |  | Milestone baseline variance is due to lower than expected installation costs and the challenges in finalizing community anchor institution agreements. One hundred and sixteen community anchor connections are connected, but costs are fully not incurred. This variance will not negatively impact completion of the project. | 100 | No variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for attaching the Broadband Cable to Historic structures provided by NTIA and in concurrence with the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements, and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 100 | The Network Design and detailed route engineering including rights of way have been completed for the project. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. | 100 | The Network Design and detailed route engineering including rights of way have been completed for the project. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. | 100 | The Network Design and detailed route engineering including rights of way have been completed for the project. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. | 46 | 59 points of interconnect are placed. Milestone baseline variance is because site preparation for 25 points of interconnection is still in progress or costs have not been fully incurred. This variance will not impact project completion. | 61 | Milestone baseline variance continued into this quarter. Some equipment has been ordered but costs have not been incurred to the project. Costs for this equipment will be incurred during the next quarter as they are received and installed and the project completes | 91 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Fifty additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. This variance will not negatively impact completion of the project. | 91 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Fifty additional miles of fiber were installed during this quarter and significant amounts of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Equipment Deployment lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 91 | Significant progress was also made during this Quarter. The milestone baseline variance is partially due to use of existing conduit resulting in lower costs during the beginning of the project. Fifty additional miles of fiber were installed during this quarter and a significant amount of construction activities are in progress. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Network Testing lags slightly behind the completion of the Network Build. This variance will not negatively impact completion of the project. | 2013-08-30 14:22 | 2013-08-30 14:22 | 6069 | 6069 | Utopia | TRUE
NT10BIX5570127 | 2013 | Q3 | Q3 - 2013 | 12299 | 10474 | TRUE | 100 | See Narratives below indicating reasons for variance. | 100 | NA | The Community Anchor Institutions have all been connected and completed for the project. | 100 | No variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for attaching the Broadband Cable to Historic structures provided by NTIA and in concurrence with the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements, and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 100 | The Network Design and detailed route engineering including rights of way have been completed for the project. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. | 100 | The Network Design and detailed route engineering including rights of way have been completed for the project. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. | 100 | The Network Design and detailed route engineering including rights of way have been completed for the project. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. | 100 | The site prep for 62 sites have been completed. Project has been completed. | 100 | All of the equipment has been purchased and deployed. Project has been completed. | 100 | The Network Build including Equipment Deployment and Network testing have been completed for the project. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. | 100 | The Network Build including Equipment Deployment and Network testing have been completed for the project. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. | 100 | The Network Build including Equipment Deployment and Network testing have been completed for the project. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. | 2014-07-03 11:28 | 2014-07-03 11:28 | 6069 | 6069 | Utopia | TRUE
NT10BIX5570128 | 2010 | Q4 | Q4 - 2010 | 1111 | 2151 | TRUE | 1 | Project team members will continually monitor progress to total project using % complete construction reports along with budget to actual reports to track financial milestones. | 0 |  | N/A | 0 | Our consultant elected not to bill the project until the Environmental Assessment is complete, so the zero % is a little misleading. On December 21st, the first draft of the Environmental Assessment was submitted to NTIA. On January 14th, team members have received comments from NTIA, related to the EA Draft. Our Consultants are currently preparing responses to each comment and plan on submitting a final draft by January 31, 2011. | 3 | Our Engineering Consultants also have elected not to bill the project for work performed through the end of the quarter, so the % complete may be misleading. The engineering Consultants began the mapping the week of November 29th and will continue until complete. | 0 | The project is not allowed to expend any monies in this category until the SAC's are lifted, but Troy Cable currently has agreements with Southeast Alabama Electric Coop, City of Troy, City of Luverne, City of Brundidge and the City of Elba. Once the SAC's are lifted, our plan is to begin construction in areas where agreements exist and request permits and approvals for all other areas at that time. | 0 | The project is not allowed to expend any monies in this category until the SAC's are lifted, but Troy Cable currently has agreements with Southeast Alabama Electric Coop, City of Troy, City of Luverne, City of Brundidge and the City of Elba. Once the SAC's are lifted, our plan is to begin construction in areas where agreements exist and request permits and approvals for all other areas at that time. | 0 | Not yet deployed | 0 | Not yet deployed | 0 | Not yet deployed | 0 | Not yet deployed | 0 | Not yet deployed | 2011-02-11 18:03 | 2011-02-11 18:03 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2011 | Q1 | Q1 - 2011 | 2181 | 2836 | TRUE | 2 | Project Team Members will continually monitor progress of the total Project using % complete construction reports along with budget to actual reports to track financial milestones. | 0 |  | N/A | 86 | The Environmental Assessment has been completed and approved by the National Telecommunications and Information Administration. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 8 | Our Engineering Consultants have elected not to bill the Project for the work performed through the end of the Quarter, so the % complete may be misleading. The Engineering Consultants have completed 90% of the mapping field work and 65% of the AutoCAD work. Troy Cable receives maps from the consultants as the maps are completed. Troy Cable employees have engineered three of the thirty-five project segments or 8.5% of the Project. | 9 | Troy Cable received notification of approval of FONSI on February 24, 2011. Subsequently, Troy Cable has begun requesting the necessary permits for Rights of Way for areas included in Phase 1 of the Build Out Plan. | 9 | Troy Cable received notification of approval of FONSI on February 24, 2011. Subsequently, Troy Cable has begun requesting the necessary permits and have submitted partial permitting documentation to pole owners on fourteen of the thirty-five project segments as of 4/29/11. | 0 | This section is misleading. Based on discussions with the Project's cash match lender, Troy Cable elected to remove land for the hub sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the Project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land which might have created a federal interest. The following activities have been completed by Troy Cable outside of the Project - the purchase of one hub site with an existing building and the purchase of two other parcels of land for hub site locations; with the completion of concrete foundations, ground work and fencing for these two locations. | 1 | The Procurement Team released a RFP for the purchase of an Emergency Alert System (EAS) and awarded the contract. Equipment and Materials have been purchased and installed for the EAS. Project Team Members are continually working to release new RFP's for equipment procurement as outlined in the Baseline Report. | 0 | Not yet deployed. | 0 | Not yet deployed. | 0 | Not yet deployed. | 2011-05-19 16:21 | 2011-05-19 16:21 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2011 | Q2 | Q2 - 2011 | 2937 | 3226 | TRUE | 9 | Project Team Members will continually monitor progress of the total Project using % complete construction reports along with budget to actual reports to measure financial milestones. Overall project was delayed from original Baseline due to Environmental Assessment process delay. Variance from last quarter PPR projection was related to aggressive projection from prior quarter to catch up with Baseline. We have revised this quarterâ€™s projection with a more realistic goal. | 0 |  | N/A | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 40 | Our Engineering Consultants have completed 100 % of the mapping field work. Troy Cable employees have engineered nine of fifty project segments based on maps received from our Consultants. Troy Cable Employees have engineered and produced nine (9) Bill of Materials for current job segments. | 40 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 1 of the Build Out Plan. | 40 | Troy Cable has begun requesting the necessary permits and have submitted partial permitting documentation to pole owners on thirty of fifty project segments as of June 30, 2011. | 0 | This section is misleading. Based on discussions with the Project's cash match lender, Troy Cable elected to remove land for the hub sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the Project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project - the purchase of one hub site with an existing building and the purchase of two other parcels of land for hub site locations; with the completion of concrete foundations, ground work and fencing for these two locations. | 7 | The Procurement Team released numerous Requests for Proposals for the purchase of Equipment, including: Telecom Shelters; OTDR and Fusion Splicing Equipment; Cable Modem Termination System (CMTS); Splicing Trailers; RF Passive Combining/Management; Return Path Receiver; Provisioning; Generators and Batteries for DC Power System; Switches and Routers; Tools; GX2 Chassis; EDFA; 1550 Transmitter and WDM Filters; Edge Decoder and Digital Head end Equipment; and Fire Suppression Units. | 7 | Fiber has been constructed but not yet activated. | 4 | Fiber has been constructed but not yet activated. | 0 | Not yet deployed. | 2011-08-05 16:22 | 2011-08-05 16:22 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2011 | Q3 | Q3 - 2011 | 3913 | 3795 | TRUE | 18 | Project Team Members will continually monitor progress of the total Project using % complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from last quarter PPR projecting was related to aggressive projection from prior quarter with a more realistic goal. Troy Cable has connected to twenty-eight (28) Community Anchor Institutions during the Third Quarter and has turned-up twenty (20) of those. | 0 |  | N/A | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 79 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have engineered twenty-three (23) of the fifty (50) Project segments based on maps received from our consultants. Troy Cable employees have engineered and produced nineteen (19) Bill of Materials for current Project segments. | 79 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 79 | Troy Cable has begun requesting the necessary permits and have submitted partial permitting documentation to pole owners on thirty (30) of the fifty (50) Project segments as of September 30, 2011. | 0 | This section is misleading. Based on discussions with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the hub sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the Project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project - the purchase of one hub site with an existing building and the purchase of two other parcels of land for hub site locations; with the completion of concrete foundations, ground work and fencing for these two locations. Prefabricated Hub Sites have been delivered to Enterprise # 2 and Midland City and the other Hub Site in Enterprise has been secured but none of those sites have been brought on line. | 37 | Procurement Team Members released numerous Request for Proposals during July, August, and September for equipment, including: Business Support Systems ("OSS/BSS"); DC Power System; VOD System; Bucket Truck(s); GPON and Access Equipment; DWDM Network; Installer Truck(s); Switches; and Routers. The Team has awarded contracts and has begun ordering and receiving equipment for Business Support Systems ("OSS/BSS"); DC Power System; Edge Decoder Equipment; Bucket Truck(s). The Team plans to launch various Request for Proposals during the Fourth Quarter for additional Equipment and order additional equipment and materials for Request for Proposals that were released in late September 2011, including: GPON and Access Equipment; DWDM Network; Installer Truck(s); Switches; VOD System; and Routers. | 14 | Troy Cable has constructed 177.57 fiber miles of the total 595 mile Project and has placed 2.43 miles of empty pipe and 2.98 miles of bare strand and has activated certain portions of the constructed job segments. Total fiber miles constructed represents 29.84% of the fiber miles construction. Troy Cable has activated approximately 82.32 miles of fiber. | 32 | Troy Cable has constructed 177.57 fiber miles of the total 595 mile Project and has placed 2.43 miles of empty pipe and 2.98 miles of bare strand and has activated certain portions of the constructed job segments. Total fiber miles constructed represents 29.84% of the fiber miles construction. Troy Cable has activated approximately 82.32 miles of fiber. | 14 | SmartBand has tested 7 of the 50 completed job segments. | 2011-11-07 17:00 | 2011-11-07 17:00 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2011 | Q4 | Q4 - 2011 | 5373 | 5044 | TRUE | 33 | Project Team Members will continually monitor progress of the total Project using % complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters Performance Progress Report projection was related to an aggressive p | 0 |  | N/A | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 85 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have engineered twenty-eight (28) of the fifty-two (52) job segments based on maps received from our consultants. Troy Cable employees have engineered and produced thirty (30) bill of material for current job segments. | 88 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 88 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussions with the Projectâ€™s cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, ground work and fencing for these two locations. Prefabricated Hub Sites have been delivered to the following locations: Enterprise # 2 (North) and Midland City. The following Hub Sites have been brought on line as of December 31, 2011: Enterprise #1 (South) and Enterprise #2 (North). Both Enterprise sites will have the DWDM Network installed next quarter. Next quarter, the following existin | 41 | Troy Cable launched Request for Proposal during the Fourth Quarter for Equipment relevant to the Headend Upgrade for Fiber Distribution System. The Team has awarded contracts and has begun ordering and receiving equipment for Request for Proposals released during previous quarters. Troy Cable has ordered and begun receiving equipment including: Business Support Systems (â€œOSS/BSSâ€); DC Power System; VOD System; DWDM Network; Installer Vans; Bucket Trucks; Routers; Switches; and GPON and Access Equipment. | 26 | Troy Cable has completed 273.21 fiber miles of the total 595 mile Project. Troy Cable has also placed 1.12 miles of empty pipe and 20.09 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 95.64 fiber miles were constructed during the Fourth Quarter. The total fiber miles constructed represents 45.92% completion of the overall fiber construction. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 92.27 miles of fiber as of December 31, 2011 with an additional 40 miles to be activated by January 31, 2012. | 36 | Troy Cable has completed 273.21 fiber miles of the total 595 mile Project. Troy Cable has also placed 1.12 miles of empty pipe and 20.09 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 95.64 fiber miles were constructed during the Fourth Quarter. The total fiber miles constructed represents 45.92% completion of the overall fiber construction. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 92.27 miles of fiber as of December 31, 2011 with an additional 40 miles to be activated by January 31, 2012. | 40 | SmartBand has tested twenty-one (21) of the fifty-two (52) job segments. | 2012-02-28 17:56 | 2012-02-28 17:56 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2012 | Q1 | Q1 - 2012 | 6013 | 5606 | TRUE | 46 | Project Team Members will continually monitor progress of the total Project using % complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters Performance Progress Report projection was related to an aggressive p | 0 |  | N/A | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 85 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have engineered forty-five (45) of the fifty-four (54) job segments based on maps received from our consultants. Troy Cable employees have engineered and produced forty-nine (49) bill of material for current job segments. | 89 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 89 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussions with the Projectâ€™s cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, ground work and fencing for these two locations. Prefabricated Hub Sites have been delivered to the following locations: Enterprise # 2 (North) and Midland City. The following new Hub Sites and co-location facilities have been brought on line as of March 31, 2012: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; and Troy. Next quarter, the following exis | 88 | The Team has awarded contracts and continues to order and receive materials from the awarded Vendors for additional equipment and materials for Request for Proposals released during previous quarters like: DWDM Network; Switches; Routers; Access Gear ("ADTRAN"); Provisioning; Light Meters; Bucket Trucks; and Access Controllers. Troy Cable has ordered and installed equipment for the Headend Upgrade for Fiber Distribution System. The Engineering Team has deployed the following network equipment: Billing Support System ("OSS/BSS"); DWDM Network Equipment; Routers; Switches; and Access Gear. The Billing Support System went live on line March 4, 2012. | 36 | Troy Cable has completed 383.04 fiber miles of the total 595 mile Project. Troy Cable has also placed 4.50 miles of empty pipe and 5.32 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 109.83 fiber miles were constructed during the First Quarter. The total fiber miles constructed represents 64.38% completion of the overall fiber construction. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 193.57 miles of fiber as of March 31, 2012. The Engineering Team has brought on-line a temporary ring to meet co-location requirements in Houston County. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas and has begun negotiating three (3) Interconnection Agreements. | 62 | Troy Cable has completed 383.04 fiber miles of the total 595 mile Project. Troy Cable has also placed 4.50 miles of empty pipe and 5.32 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 109.83 fiber miles were constructed during the First Quarter. The total fiber miles constructed represents 64.38% completion of the overall fiber construction. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 193.57 miles of fiber as of March 31, 2012. The Engineering Team has brought on-line a temporary ring to meet co-location requirements in Houston County. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas and has begun negotiating three (3) Interconnection Agreements. | 56 | SmartBand has tested approximately thirty (30) of the fifty-four (54) job segments. | 2012-05-10 13:27 | 2012-05-10 13:27 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2012 | Q2 | Q2 - 2012 | 6907 | 6080 | TRUE | 58 | Project Team Members will continually monitor progress of the total Project using % complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quartersâ€™ Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. | 0 |  | Not Applicable. | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 85 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have engineered forty-seven (47) of the fifty-five (55) job segments based on maps received from our consultants. Troy Cable employees have engineered and produced forty-nine (49) bills of materials for current job segments. | 90 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 90 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussions with the Projectâ€™s cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and co-location facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and | 88 | Troy Cable has ordered and installed equipment for the following Request for Proposals: Headend Upgrade for Fiber Distribution System; Billing Support System ("OSS/BSS"); DWDM Network Equipment; Routers; Switches; and Access Gear. The following existing Hub Sites and co-location facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and will be connected to the DWDM Network by Third Quarter 2012. The Team has brought online a temporary ring to meet co-location requirements in Houston and Montgomery Counties. Co-location equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed colocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on five (5) Interconnection Agreements. | 44 | Troy Cable has completed 477.79 fiber miles of the total 595 mile Project. Troy Cable has also placed 26.44 miles of empty pipe and 15.52 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 94.75 fiber miles were constructed during the Second Quarter. The total fiber miles constructed represents 80.30% completion of the overall fiber construction. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 336.73 miles of fiber as of June 30, 2012. The Team has brought on line a temporary ring to meet co-location requirements in Houston and Montgomery Counties. Co-location equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on five (5) Interconnection Agreements. | 83 | Troy Cable has completed 477.79 fiber miles of the total 595 mile Project. Troy Cable has also placed 26.44 miles of empty pipe and 15.52 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 94.75 fiber miles were constructed during the Second Quarter. The total fiber miles constructed represents 80.30% completion of the overall fiber construction. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 336.73 miles of fiber as of June 30, 2012. The Team has brought on line a temporary ring to meet co-location requirements in Houston and Montgomery Counties. Co-location equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on five (5) Interconnection Agreements. | 58 | SmartBand has tested approximately thirty-two (32) of the fifty-five (55) job segments. | 2012-08-07 18:42 | 2012-08-07 18:42 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2012 | Q3 | Q3 - 2012 | 7971 | 6692 | TRUE | 66 | Project Team Members will continually monitor progress of the total Project using % complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quartersâ€™ Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable has connected and turned-up fifty-two (52) Community Anchor Institutions. Troy Cable has connected and turned up fifty-eight (58) Businesses. | 0 |  | Not Applicable. | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 92 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced fifty-two (52) bills of materials for current job segments. | 92 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 92 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussions with the Projectâ€™s cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and colocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and will b | 89 | Troy Cable has ordered and installed equipment for the following Request for Proposals: Headend Upgrade for Fiber Distribution System; Billing Support System ("OSS/BSS"); DWDM Network Equipment; Routers; Switches; and Access Gear. The following existing Hub Sites and colocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and will be connected to the DWDM Network by Fourth Quarter 2012. Troy Cable has released and awarded bids on Request for Proposals for Intelligent Policy Management and Firewall. The Team has brought online a temporary ring to meet colocation requirements in Houston and Montgomery Counties. Colocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed colocation with a Carrier Neutral Hotel in At | 53 | Troy Cable has completed 566.73 fiber miles of the total 595 mile Project. Troy Cable has also placed 24.21 miles of empty pipe and 4.02 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 88.94 fiber miles were constructed during the Third Quarter. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 511.12 fiber miles as of September 30, 2012. The Team has brought on line a temporary ring to meet colocation requirements in Houston and Montgomery Counties. Colocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed colocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 84 | Troy Cable has completed 566.73 fiber miles of the total 595 mile Project. Troy Cable has also placed 24.21 miles of empty pipe and 4.02 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 88.94 fiber miles were constructed during the Third Quarter. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 511.12 fiber miles as of September 30, 2012. The Team has brought on line a temporary ring to meet colocation requirements in Houston and Montgomery Counties. Colocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed colocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 88 | SmartBand has tested approximately forty-nine (49) of the fifty-six (56) job segments. | 2012-11-20 11:33 | 2012-11-20 11:33 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2012 | Q4 | Q4 - 2012 | 8851 | 7637 | TRUE | 72 | [REDACTED] | 0 |  | Not Applicable | 87 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task under budget. | 93 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced fifty-four (54) bills of materials for current job segments. | 93 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 95 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussion with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use Cash Match or Grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements. | 93 | The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties with one node remaining offline in Brantley. Troy Cable anticipates the completion of the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier | 61 | Troy Cable has completed 635.96 fiber miles, to include 424.38 route miles of new construction. Troy Cable has also placed 10.95 miles of empty pipe and 3.91 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 635.96 fiber miles, 69.23 fiber miles were constructed during the Fourth Quarter 2012. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated 382.08 fiber miles as of December 31, 2012. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties with one node remaining offline in Brantley. Troy Cable anticipates the completion of the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on one (1) Interconnection Agreement. | 88 | Troy Cable has completed 635.96 fiber miles, to include 424.38 route miles of new construction. Troy Cable has also placed 10.95 miles of empty pipe and 3.91 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 635.96 fiber miles, 69.23 fiber miles were constructed during the Fourth Quarter 2012. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated 382.08 fiber miles as of December 31, 2012. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties with one node remaining offline in Brantley. Troy Cable anticipates the completion of the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on one (1) Interconnection Agreement. | 88 | SmartBand has tested approximately forty-nine (49) of the fifty-six (56) job segments. | 2013-02-19 22:50 | 2013-02-19 22:50 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2013 | Q1 | Q1 - 2013 | 9573 | 8314 | TRUE | 76 | Project Team Members will continually monitor progress of the total Project using # complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters' Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable has connected and turned-up ninety-four (94) Community Anchor Institutions. Troy Cable has connected and turned-up two hundred forty-seven (247) Businesses. | 0 |  | Not Applicable | 88 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task under budget. | 95 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced fifty-six (56) bills of materials for current job segments. | 95 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 97 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussion with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use Cash Match or Grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. | 97 | The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Troy Cable completed the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on two (2) Interconnection Agreements. | 66 | Troy Cable has completed 700.51 fiber miles, to include 458.85 route miles of new construction. Troy Cable has also placed 9.23 miles of empty pipe and .22 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 700.51 fiber miles, 34.47 fiber miles were constructed during the First Quarter. Troy Cable has activated 388.95 route miles as of March 31, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Troy Cable completed the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on two (2) Interconnection Agreements. | 92 | Troy Cable has completed 700.51 fiber miles, to include 458.85 route miles of new construction. Troy Cable has also placed 9.23 miles of empty pipe and .22 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 700.51 fiber miles, 34.47 fiber miles were constructed during the First Quarter. Troy Cable has activated 388.95 route miles as of March 31, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Troy Cable completed the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on two (2) Interconnection Agreements. | 89 | SmartBand has tested approximately fifty (50) of the fifty-six (56) job segments. | 2013-04-30 21:20 | 2013-04-30 21:20 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2013 | Q2 | Q2 - 2013 | 10575 | 8944 | TRUE | 83 | Project Team Members will continually monitor progress of the total Project using # complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters' Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable has connected and turned-up one hundred thirty-nine (139) Community Anchor Institutions. Troy Cable has connected and turned-up three hundred fifty-seven (357) Businesses. | 0 |  | Not Applicable | 88 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task under budget. | 97 | Our Engineering Consultants have completed 99% of the mapping field work. Troy Cable employees have produced fifty-eight (58) bills of materials for current job segments. | 97 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 98 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussion with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use Cash Match or Grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. | 100 | The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 76 | Troy Cable has completed 474.02 route miles of new construction. Troy Cable has activated 474.02 route miles as of June 30, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 95 | Troy Cable has completed 474.02 route miles of new construction. Troy Cable has activated 474.02 route miles as of June 30, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 98 | SmartBand has tested approximately fifty (57) of the fifty-eight (58) job segments. | 2013-08-13 20:10 | 2013-08-13 20:10 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2013 | Q3 | Q3 - 2013 | 11295 | 9446 | TRUE | 88 | Project Team Members will continually monitor progress of the total Project using # complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters' Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. Troy Cable has connected and turned-up one hundred forty-six (146) Community Anchor Institutions. Troy Cable has connected and turned-up four hundred (400) Businesses. | 0 |  | Not Applicable. | 88 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task under budget. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. | 97 | Our Engineering Consultants have completed 97% of the mapping field work. Troy Cable employees have produced approximately eighty (80) bills of materials for current job segments. | 98 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 3 of the Build Out Plan. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. | 99 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 3 of the Build Out Plan. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. | 0 | This section is misleading. Based on discussion with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use Cash Match or Grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. | 100 | The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 83 | Troy Cable has completed 501.00 route miles of new construction. Troy Cable has activated 501.00 route miles as of September 30, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 95 | Troy Cable has completed 501.00 route miles of new construction. Troy Cable has activated 501.00 route miles as of September 30, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 85 | SmartBand has tested approximately sixty-eight (68) of the eighty (80) job segments. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. | 2013-11-19 16:15 | 2013-11-19 16:15 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2013 | Q4 | Q4 - 2013 | 12259 | 10430 | TRUE | 100 | Project Team Members will continually monitor progress of the total Project using # complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters' Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 54.17 route miles. Troy Cable has connected and turned-up one hundred ninety-eight (198) Community Anchor Institutions. Troy Cable has connected and turned-up four hundred eighty-five (485) Businesses. | 0 |  | Not Applicable. | 100 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 54.17 route miles. | 100 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced approximately eighty (80) bills of materials for current job segments. | 100 | Troy Cable continued to request the necessary permits for Rights of Way for areas included in Phase 3 of the Build Out Plan. Troy Cable is still awaiting Railroad Permitting for a .57 mile stretch along a route included in the Route Modification to be completed with non-federal funds due to the ending funds of availability. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 54.17 route miles. | 100 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 3 of the Build Out Plan. Troy Cable is still awaiting Railroad Permitting for a .57 mile stretch along a route included in the Route Modification to be completed with non-federal funds due to the ending funds of availability. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 54.17 route miles. | 0 | This section is misleading. Based on discussion with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use Cash Match or Grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. | 100 | The Engineering Team has continued to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on one (1) Interconnection Agreements. | 100 | Troy Cable has completed 529.12 route miles of new construction. Troy Cable has activated 529.12 route miles as of December 31, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on one (1) Interconnection Agreements. | 100 | Troy Cable has completed 529.12 route miles of new construction. Troy Cable has activated 529.12 route miles as of December 31, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on one (1) Interconnection Agreements. | 100 | SmartBand has tested all eighty (80) job segments. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 54.17 route miles. | 2014-06-02 15:01 | 2014-06-02 15:01 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570129 | 2010 | Q4 | Q4 - 2010 | 1357 | 2373 | TRUE | 1 | Overall Project is listed as 1% complete because no expenditures have occurred, to date. However, work has progressed, as detailed above. The variance between this and the baseline plan, which anticipated 5% completion, is in large part due to the longer than anticipated time frame to sign a project management partner. | 17 | Grant Admin | N/A | 29 | The environmental assessment is on track for submittal of draft EA on due date, January 31, 2011. | 2 | The baseline plan anticipated 6% completion of network design. Similar to the overall project milestone, progress is lower than anticipated due to delayed time to secure project management. No funds have been expended to date, yet the project manager has begun initial work. | 0 | N/A | 0 | The baseline plan anticipated 2% completion of the milestone. No funds have been drawn down to date. The variance, similar to the other impacted milestones, is a result of the longer than anticipated time to sign a project management & engineering firm. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-24 09:26 | 2011-02-24 09:26 | 6108 | 6108 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2011 | Q1 | Q1 - 2011 | 2297 | 2894 | TRUE | 1 | Approximately 0.7% of total funds have been spent through this quarter. However, significant progress was made during the quarter regarding environmental assessment work, route changes, cabinet and data center planning, and lease agreements. Baseline project plan anticipated overall project completeness of 20%. Variance can be largely explained by the fact that equipment procurement was planned to have begun, but did not occur. Additionally, the data center rebid process has delayed related expenditures. | 25 | Grant Administration | N/A | 73 | The draft environmental assessment was submitted on schedule and returned for revisions. Currently, the environmental assessment appears on track for final submittal by next quarter. | 4 | The baseline plan anticipated 38% completion of network design. Due to issues with reroutes, the work on network architecture and technical design was slowed until the proposed route changes were accepted. | 5 | N/A | 9 | N/A | 0 | Baseline Plan anticipated 10% completion of the milestone. Variation in progress is a result of the delayed cabinet process and the rebid of the data center. | 0 | Equipment procurement did not take place as was originally planned. In the baseline it was planned to have 19% of procurement finished by the end of the quarter. Due to the changes to the network route, some additional work on cabinet prepping has pushed back cabinet procurement. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-05-25 13:30 | 2011-05-25 13:30 | 6108 | 6108 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2011 | Q2 | Q2 - 2011 | 3149 | 3335 | TRUE | 4 | The project has spent 4% of total project funds through this quarter. This matches the anticipated progress update provided in the subsequent 2011 Q1 Performance Progress Report update. | 34 | Grant Administration | No variance | 95 | The completion of the environmental assessment was delayed, due to the need to conduct a Phase 1 archaeological survey on the data center site. | 70 | No variance | 15 | Previous Performance Progress Report update anticipated 80% completion of milestone. Negative variance is attributed to delays to the environmental assessment and route engineering. It is likely that Rights of Way will be fully complete by 2011, Q4, only delaying completion of milestone by one quarter. | 18 | Previous Performance Progress Report update anticipated 66% completion of milestone. Due to increased engineering time, the planned completion of route construction permits is to account for the negative variance in completion progress. | 0 | Previous Performance Progress Report anticipated 2% completion of site preparation. Due to delay on the submission of the environmental assessment, no site work took place. | 0 | Previous Performance Progress Report anticipated 3% milestone completion. The procurement of cabinet equipment was delayed. This explains the negative variance between reports. | 0 | No variance | 0 | No variance | 0 | No variance | 2011-08-17 12:23 | 2011-08-17 12:23 | 6108 | 6108 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2011 | Q3 | Q3 - 2011 | 4167 | 3932 | TRUE | 7 | The project has spent a little over 7% of the total project funds through this quarter. This is less than the anticipated progress update provided in the subsequent 2011 Q2 PPR. The delay is due to the delay of submittal and approval of the Environmental assessment and longer route engineering time. | 42 | Grant Adminstration | No variance | 100 | No variance | 100 | No variance | 15 | Previous Performance Progress Report update anticipated 28% completion of milestone. Negative variance is attributed to delays to the environmental assessment and route engineering. It is likely that about 40% of the needed Rights of Way will be gathered by 2011, Q4 with the rest obtained in the first quarter of 2012. The combination of the 15% from the completion of the identification of the easements and 40% of the easements being gathered will make 49% completion of this overall milestone. These agreements will NOT delay the start of construction, as many other network segments require no agreements. | 64 | Baseline plan anticipated 96% completion of milestone by end of the quarter. Completion is approximately 30% lower but very close to previous performance progress report that anticipated 67% completion. Negative variance from baseline plan is attributed to delays in selection of data center design firm and route engineering. All relative permits have been drafted and submitted except the cabinet construction permits, which explains the 3% variance from the previous performance progress report anticipation. | 0 | Previous PPR anticipated 23% completion of site preparation. Due to the delay on the submission and approval of the environmental assessment, no site work took place. | 0 | Previous PPR anticipated 9% milestone completion. The procurement of cabinet equipment was delayed. This explains the negative variance between reports. | 0 | No variance | 0 | No variance | 0 | No variance | 2011-11-21 09:46 | 2011-11-21 09:46 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2011 | Q4 | Q4 - 2011 | 5225 | 4890 | TRUE | 11 | The project has spent a little over 11% of the total project funds through this quarter. This is less than the anticipated progress update provided in the subsequent 2011 Q3 PPR. The delay is due to the delay of submittal and approval of the Environmental assessment, longer route engineering time, and a delay because of negotiations for the Data Center construction contract. | 50 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 70 | Previous Performance Progress Report anticipated 49% completion of this milestone. We have gathered more easements than was anticipated. The County continues to pursue getting the rest of the easements. The easements that are still needed will NOT delay the start of construction, as most of the routes do not require easements or we have already received the easements. | 88 | Baseline plan anticipated 100% completion of this milestone by the end of the quarter. Completion is approximately 10% lower but very close to the previous PPR that anticipated 89% completion. Negative variance from baseline plan is attributed to delays in selection of data center design firm and route engineering. All relative permits have been drafted, submitted and approved except the cabinet construction permits, which explains the 1% variance from the previous PPR anticipation. | 0 | Previous PPR anticipated 23% completion of site preparation. Due to the delay on the submission and approval of the environmental assessment, and the delay in the legal review of the construction bid documents, the publishing of the construction bids was delayed and no site work took place. | 0 | Previous PPR anticipated 22% completion of this milestone. Negative variance is due to the delay in legal review of the three different procurement bid documents. The procurement bids were advertised during this quarter with bids being due back in January. We expect to make an award and begin equipment procurement during 2012 Q1. | 0 | Baseline plan anticipated 33% completion of this milestone and the previous PPR anticipated 2% completion. Negative variance is due to delays with the environmental assessment and data center construction was held up due to contract negotiations. The contract has been signed and data center construction is expected to start early 2012 Q1. | 0 | Baseline plan anticipated 24% completion of this milestone but there is no variance with the anticipated completion from the previous PPR. Due to delays with the environmental assessment and legal review of the bid documents, DSL construction did not begin during this quarter. Equipment for the DSL cabinets and fiber network cabinets was not ordered during this quarter due to delays with legal review of bid documents. DSL equipment (DSLAMs, UPSes, patch panels, etc.) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. This work is expected to begin late 2012 Q1 or early 2012 Q2. The data center is scheduled for completion in 2012 Q2, and fiber equipment will be installed in the data center as soon as all major construction and mechanical work is completed. | 0 | Baseline plan anticipated 22% completion of this milestone but there is no variance with the anticipated completion from the previous PPR. Due to delays with the environmental assessment, construction did not begin during this quarter. Testing cannot take place until the equipment is deployed. Network testing will begin as soon as the data center and the first fiber segments are completed. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2012-02-23 16:23 | 2012-02-23 16:23 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2012 | Q1 | Q1 - 2012 | 6131 | 5668 | TRUE | 15 | The project has spent a little over 15% of the total project funds through this quarter. This is less than the anticipated progress update provided in the subsequent 2011 Q4 PPR. The delay is due to the delay in negotiations for the Data Center construction contract, a delay in the award of the procurement contracts, and a delay in the completion of the Fiber Network and Cabinet construction contracts. | 58 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 76 | Previous PPR anticipated 80% completion of this milestone. Negative variance is due to delays in locating existing Century Link easements around the proposed cabinet locations. We have hired a local firm to look into the location of existing Century Link easements and to get the easements signed. They have been making substantial progress. The easements that are still needed will NOT delay the start of construction, as most of the routes do not require easements or we have already received the easements. | 88 | Baseline plan anticipated 100% completion of this milestone by the end of the quarter and the previous PPR anticipated 96% completion. Negative variance is attributed to delays in the selection of the data center design firm, route engineering, and delays in the writing of the contracts for the DSL cabinet construction and the Fiber network construction. | 0 | Previous PPR anticipated 27% completion of site preparation. Due to the delay in the submission and approval of the environmental assessment, delay in the legal review of the construction bid documents, and the delay in the legal preparation and review of the contracts for the DSL cabinet construction and the Fiber network construction, no site work took place. | 0 | Previous PPR anticipated 28% completion of this milestone. Negative variance is due to the delay in the legal review of the procurement bid documents and of the bids. The review of the bids delayed the award which delayed the delivery of the equipment. Some of the equipment has been delivered and we expect to continue to have equipment delivered during 2012 Q2. | 5 | Baseline plan anticipated 45% completion of this milestone and the previous PPR anticipated 20% completion. Negative variance is due to delays with the environmental assessment and data center construction was held up due to contract negotiations. The contract has been signed and data center construction is underway. The Fiber and DSL network construction awards have been made and we are expecting to have signed contracts during 2012 Q2 and for construction to begin. | 0 | Baseline plan anticipated 37% completion of this milestone but there is no variance with the anticipated completion from the previous PPR. Due to delays with the environmental assessment and legal review of the bid documents, DSL construction did not begin during this quarter. Equipment for the DSL cabinets and fiber network cabinets was not ordered during this quarter due to delays with legal review of bid documents. DSL equipment (DSLAMs, UPSes, patch panels, etc.) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. This work is expected to begin next quarter, 2012 Q2. The DSL equipment is also being analyzed to verify which models will be purchased and installed in the cabinets. That process was started during 2012 Q1 and will continue into 2012 Q2. The data center is scheduled for completion next quarter, 2012 Q2, and fiber equipment will be installed in the data center once all major construction and mechanical work is completed. | 0 | Baseline plan anticipated 35% completion of this milestone but there is no variance with the anticipated completion from the previous PPR. Due to delays with the environmental assessment, construction did not begin during this quarter. Testing cannot take place until the equipment is deployed. Network testing will begin as soon as the date center and the first fiber segments are completed. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2012-05-16 12:19 | 2012-05-16 12:19 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2012 | Q2 | Q2 - 2012 | 7129 | 6192 | TRUE | 27 | The project has spent 27% of the total project funds through this quarter. This is less than the anticipated progress update provided in the subsequent 2012 Q1 PPR. The delay is due to the delay in getting the Rockbridge County-City of Lexington agreement for construction to start in the City, the delay in getting VDOT permits for construction throughout the County, and delay in legal review of the construction contracts. | 66 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 83 | Previous PPR anticipated 90% completion of this milestone. Negative variance is due to delays in locating the existing CenturyLink easements around the proposed cabinet locations. We have a local firm that has been hired to look up the existing CenturyLink easements and to get the easements signed. They are making progress in both those areas. The easements that are still needed will NOT delay construction, as most of the routes do not require easements or we have already received the easements. | 96 | Baseline plan anticipated 100% completion of this milestone by the end of the quarter and the previous PPR anticipated 100% completion. We have all of the permits needed except the VDOT land use permits. We are expected to get those during July 2012. | 10 | Previous PPR anticipated 27% completion of site preparation. Negative variance is due to the delay in the legal review of the construction bid documents, the delay in getting the VDOT permits, and the delay in the legal preparation and review of the contracts for the DSL cabinet construction and the Fiber network construction. Fiber construction has begun and the DSL cabinet construction also began during this quarter. | 17 | Previous PPR anticipated 28% completion of this milestone. Negative variance is due to the delay in getting the Rockbridge County-City of Lexington agreement which has delayed the start of construction. Construction began during this quarter and we expect to continue having equipment delivered during 2012 Q3. | 24 | Baseline plan anticipated 55% completion of this milestone by the end this quarter but there is no variance from the previous PPR anticipated completion. Negative variance from the baseline plan is due to delays with the environmental assessment, data center construction contract negotiations, Fiber and cabinet construction contract legal review delays, and VDOT permits. Data Center construction is close to completion and both the Fiber and cabinet construction have also begun. | 5 | Baseline plan anticipated 50% completion of this milestone but there is no variance with the anticipated completion from the previous PPR. Due to delays with the environmental assessment and legal review of the bid documents, DSL construction did not begin until this quarter. Equipment for the DSL cabinets and fiber network cabinets was not ordered during this quarter. DSL equipment (DSLAMs, UPSes, patch panels, etc.) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. A few of the cabinet sites have been completed with cabinets being placed on site. The DSL equipment is being analyzed to verify which models will be purchased and installed in the cabinets. That process was started during 2012 Q1 and continued into 2012 Q2. The data center is scheduled for completion early next quarter, 2012 Q3, and fiber equipment will be installed in the data center once all major construction and mechanical work is completed. | 0 | Baseline plan anticipated 48% completion of this milestone but there is no variance with the anticipated completion from the previous PPR. Due to delays with the environmental assessment, construction did not begin until this quarter. Testing cannot take place until the equipment is deployed. Network testing will begin as soon as the data center and the first fiber segments are completed. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2012-08-17 16:59 | 2012-08-17 16:59 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2012 | Q3 | Q3 - 2012 | 8133 | 6775 | TRUE | 56 | The project has spent over 56% of the total project funds through this quarter. This is less than the anticipated progress update provided in the subsequent 2012 Q2 PPR. The delay is due to the Data Center contractor finishing up the punch list on Data Center construction. | 75 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 95 | Previous PPR anticipated 90% completion of this milestone. Positive variance is due to landowners along the routes are talking to each other and more landowners are signing than was anticipated. One of the routes where there were easement issues was eliminated and thus that reduced the number of needed easements. | 100 | No variance | 48 | Previous PPR anticipated 30% completion of site preparation. Positive variance is due to the cabinet construction contractors are getting cabinets installed at a faster rate than was previously anticipated. | 48 | Previous PPR anticipated 58% completion of equipment procurement. Most of the equipment bids/quotes have been returned and the difference in completion percentage is because some of the equipment is still in transit and has not been delivered or invoiced for yet. | 55 | Previous PPR anticipated 45% completion of this milestone by the end of this quarter. Positive variance from the previous PPR is due to the construction of the Data Center wrapping up, the fiber contractor is making substantial progress on getting the conduit installed, and the cabinet contractor is getting the cabinet sites constructed faster than anticipated. | 15 | Baseline plan anticipated 62% completion of this milestone but there is no variance with the anticipated completion from the previous PPR. Due to delays with the environmental assessment and legal review of the bid documents, DSL construction did not begin until last quarter. Equipment for the DSL cabinet and fiber network cabinets was ordered during this quarter but none has been placed in the cabinets yet. The equipment being deployed last quarter was the cabinets themselves and racks and some equipment being installed in the Data Center. | 0 | Baseline plan anticipated 61% completion of this milestone but there is no variance with the anticipated completion from the previous PPR. Due to delays with the environmental assessment, construction began last quarter. Testing cannot take place until the equipment is deployed. Network testing will begin as soon as the data center and the first fiber segments are completed. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2012-11-29 11:33 | 2012-11-29 11:33 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2012 | Q4 | Q4 - 2012 | 8943 | 7725 | TRUE | 67 | The project has spent over 67% of the total project funds through this quarter. This is slightly less than the anticipated progress update provided in the subsequent 2012 Q3 PPR. This is due to the delay in invoices for make ready work from the pole owners and CenturyLink cross connect fee invoices. We are expecting those invoices during 2013 Q1. | 83 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 65 | Previous PPR anticipated 62% completion of site preparation. Positive variance is due to nice weather continuing through December and cabinet construction crews continuing to make progress. | 50 | Previous PPR anticipated 67% completion of equipment procurement. Most of the equipment purchase orders have been sent to vendors. The difference in completion percentage is due to the equipment still in staging or in shipment and have not been invoiced for yet. | 60 | Previous PPR anticipated 65% completion of this milestone by the end of this quarter. Negative variance is due to delays from CenturyLink getting invoices back to be paid for collocating inside their easement and due to the holidays, all fiber construction had to stop work for 1.5 weeks until after the New Year. | 25 | Baseline plan anticipated 75% completion of this milestone but there is no variance with the anticipated completion from the previous PPR. Due to delays with the environmental assessment and legal review of the bid document, DSL construction did not begin until 2012 Q2. Equipment for the DSL cabinet and fiber network cabinets has been ordered and is expected to begin installation during 2013 Q1. The equipment being deployed has been primarily the cabinets themselves and the data center equipment. | 5 | Baseline plan anticipated 74% completion of this milestone but there is no variance with the anticipated completion from the previous PPR.. Negative variance is due to the delays with the environmental assessment and legal review of the bid documents. Construction is underway and network equipment installation is scheduled for 2013 Q1 which will result in some network testing taking place. DSL equipment has taken place as the equipment has started arriving. | 2013-02-25 16:18 | 2013-02-25 16:18 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2013 | Q1 | Q1 - 2013 | 9883 | 8480 | TRUE | 78 | The project has spent over 78% of the total project funds through this quarter. This is slightly less than the anticipated progress update provided in the subsequent 2012 Q4 PPR. Negative variance is due to the fact that our drawdown request at the end of this quarter was not reflected in this quarters finances. | 91 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 80 | No variance from the previous PPR. Negative variance from the baseline is explained by the delay in cabinet construction due to the environmental assessment submission and approval delay. It can also be attributed to the delay in the legal review of the cabinet site construction bid documents and the delay in contract preparation. The cabinet construction contract is signed and construction is underway. We are expecting CenturyLink to get back to us on the cabinet placement requirements for the remaining cabinets during the next quarter and for the cabinet contractor to be cleared to work in the remaining cabinet sites. | 100 | No variance | 80 | No variance from the previous PPR. Negative variance from the baseline is due to delays with the environmental assessment, delay with the legal review of the network construction bid documents, delay in the legal preparation and review of the construction contracts, and lengthy data center contract negotiations. The data center construction is now complete. The cabinet and fiber network construction is underway. The fiber contractor has finished construction in downtown Lexington and they are making substantial progress throughout the County. | 60 | No variance from the previous PPR. Negative variance from baseline is due to delays with the environmental assessment and legal reviews of the bid documents and the construction contracts. Cabinet and fiber network construction are underway and both contractors have been making substantial progress towards completion. | 40 | Previous PPR anticipated 50% completion of this milestone by the end of this quarter. Negative variance is due to scheduling issues with equipment vendors for installation and initial configuration of the fiber equipment. That has now been completed and network testing is underway. Negative variance from the baseline is due to delays with the environmental assessment and legal review of the network construction bid documents and preparation of the construction contracts, cabinet construction is underway but no DSL network equipment has been deployed. The data center contract negotiations also delayed the start of the data center construction, which is now complete. | 2013-05-23 11:29 | 2013-05-23 11:29 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2013 | Q2 | Q2 - 2013 | 10735 | 9031 | TRUE | 90 | The project has spent 90% of the total project funds through this quarter. This is less than the anticipated progress update provided in the subsequent 2013 Q1 PPR. Negative variance is due to the fact that our drawdown request at the end of this quarter was not reflected in this quarters finances. | 95 | Grant Administration | No variance from previous PPR. Negative variance from the baseline plan is because the project received an extension until September 30, 2013 and that was not reflected in the baseline plan. | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 95 | Negative variance from the baseline is explained by the delay in cabinet construction due to the environmental assessment submission and approval delay. It can also be attributed to the delay in the legal review of the cabinet site construction bid documents and the delay in contract preparation. The cabinet construction contract is signed and construction is almost finished. We are expecting CenturyLink to get back to us on the cabinet placement requirements for the remaining cabinets during the next quarter and for the cabinet contractor to be cleared to work in the remaining cabinet sites. | 100 | No variance | 95 | No variance from the previous PPR. Negative variance from the baseline is due to delays with the environmental assessment, delay with the legal review of the network construction bid documents, delay in the legal preparation and review of the construction contracts, and lengthy data center contract negotiations. The data center construction is now complete. The cabinet and fiber network construction are almost complete. | 85 | No variance from the previous PPR. Negative variance from baseline is due to delays with the environmental assessment and legal reviews of the bid documents and the construction contracts. Cabinet and fiber network construction are underway and both contractors are almost complete. | 85 | No variance from the previous PPR. Negative variance from the baseline is due to delays with the environmental assessment and legal review of the network construction bid documents and preparation of the construction contracts, cabinet construction is underway and DSL equipment is being deployed and tested. The data center contract negotiations also delayed the start of the data center construction, which is now complete. | 2013-08-26 12:00 | 2013-08-26 12:00 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2013 | Q3 | Q3 - 2013 | 11993 | 10155 | TRUE | 100 | We have spent over 95% of the project funds through 2013 Q3. Previous PPR anticipated 100% completion of this milestone. Negative variance is due to the delay in the environmental assessment approval, the delay in getting legal review of the construction contracts, getting Dept. of Transportation permits for work to begin, and delays in getting signed easements. All that is now completed and the construction of the project is 100% complete. The remaining funds that are to be spent account for work completed in 2013 Q3 but not drawn until 2013 Q4 as well as money left to be invoiced for closeout reporting and documentation work. | 100 | Grant Administration | Negative variance from the baseline plan is because we applied for a grant extension, which was accepted. The baseline plan does not account for that extension. | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2014-03-26 15:36 | 2014-03-26 15:36 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570130 | 2010 | Q4 | Q4 - 2010 | 1291 | 2314 | TRUE | 2 | Construction work awaiting completion of Environmental Assessment | 25 | Project notification | Municipal and Community Stakeholder Notification started January 2011. Phase I End User Connections Notifications to begin February 2011. | 90 | Environmental Assessment Report Completed and prepared for submittal on February 1, 2011. | 100 | Network Design and Systems Specifications Complete. Construction Documents for Permit 10% Complete. | 45 | Terminal placements and right's of way easements identified. Lease agreement negotiations start in February 2011. | 0 | Awaiting completion of Phase I Construction Documents. | 0 | Awaiting FONSI. | 10 | Phase I Equipment acquired and undergoing pre-installation configuration and testing. | 0 | Awaiting FONSI. | 0 | Awaiting FONSI. | 0 | Awaiting FONSI. | 2011-02-22 12:32 | 2011-02-22 12:32 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2011 | Q1 | Q1 - 2011 | 1933 | 2712 | TRUE | 4 | Milestone was not completed due to not receiving FONSI before March 31, 2011. | 15 |  | Municipal and Community Stakeholder Notification started January 2011. Phase I End User Connections Notifications started in February 2011. | 95 | Completed all necessary documents to receive FONSI in May, 2011. | 95 | 100% of Network Design is complete however, 100% of Permit Drawings are not complete due to time required to obtain, digitize and overlay as-build information. | 45 | Ahead of schedule. Terminal placements and right's of way easements identified. Lease agreement notifications started in February 2011. | 5 | Prepared documents to Permit Phase I Rail Road Crossings in Dallas and Lowndes County as well as Alabama DOT right-of-way. Construction Permits are driven by final route design hence is dependent on the Environmental Assessment and FONSI which took longer than anticipated. We expect to catch up to baseline projections within the next 2 quarters. | 2 | Mobilization of construction site to begin staging materials was deferred because we had not received letters of concurrence for EA by March 15th. This caused site preparation activity to be reduced by 2%. We expect to catch up to baseline projections within the next 2 quarters. | 15 | Reviewed and installed test equipment from key manufacturers for Phase I of the network. With the delay in construction noted above, inside plant equipment procurement becomes a secondary need and not critical path. We have procured the necessary equipment needed at this time for beta testing and network setup. We expect to catch up to baseline projections within the next 2 quarters | 0 | Projected during last quarter that FONSI would have been secured by March 2011. Since it was not, construction was deferred to May 2011 which resulted in a reduction in percentage complete | 0 | Projected to deploy equipment to site facilities and terminals by end of March 2011. Due to FONSI not being obtained, percentage had to be reduced. | 0 | Projected to deploy fiber infrastructure in March 2011. However without securing FONSI, construction was deferred to May 2011. | 2011-05-10 19:37 | 2011-05-10 19:37 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2011 | Q2 | Q2 - 2011 | 3343 | 3435 | TRUE | 4 | We are making progress in catching up to baseline. The delay in proceeding with construction stemmed from the effect of the the FONSI delay. | 21 |  | Public Notification is fairly dependant on the final design plan and being able to provide expectation dates. The delay of the FONSI affected our ability to provide this information. Public Notification will be implemented across eight (8) counties in South Central Alabama. The Notification Program is being developed via a collaboration with the Broadband Authority and Stakeholders. Lowndes County Notification in currently in process. We are entering Wave 2 which will have a direct impact to all anchor institutions, businesses, and residences in the last mile FTTP serving area. | 100 | EA is complete | 95 | We are making progress in catching up to baseline. The delay in proceeding with route and fiber design stemmed from the effect of the the FONSI delay. Construction Drawings are being adjusted per specific municipal permit requirements | 45 | We are ahead of baseline. | 10 | We are making progress in catching up to baseline. The delay in proceeding with final construction drawings and submittal of permits stemmed from the effect of the the FONSI delay. Regardless. A2D Signed Lease and opened first construction office. | 10 | We are ahead of baseline | 15 | We are ahead of baseline | 0 | We are making progress in catching up to baseline. The delay in proceeding with construction stemmed from the effect of the the FONSI delay. | 0 | We are making progress in catching up to baseline. The delay in proceeding with construction stemmed from the effect of the the FONSI delay. | 0 | We are making progress in catching up to baseline. The delay in proceeding with construction stemmed from the effect of the the FONSI delay. | 2011-08-29 11:39 | 2011-08-29 11:39 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2011 | Q3 | Q3 - 2011 | 4355 | 4034 | TRUE | 11 | We are making progress in catching up to baseline. We have formulated a construction plan to complete project on schedule | 25 | Project Notification | Notification has an impact on 8 counties in South Central Alabama in collaboration with the Broadband Authority and Stakeholders. Notification in Phase 1 (Lowndes County/Dallas County- Middle Mile Town Hayneville/City of Selma- Last Mile); Lowndes County Notification in currently at 60% complete; The Dallas County Notification program began in Q3, 2011; | 100 | N/A | 99 | Network Design is essentially complete. The remaining tasks fall more in route finalization and permitting. | 50 | We are ahead of baseline | 1 | Submitting first set of permits for phase 1 and are awaiting thier release. | 20 | The impact of the delay of our Finding of No Significant Impact (FONSI) report required us to ramp up construction operations in a short period of time. However, we have not fully caught up with our baseline and anticipate catching up in the next quarter. | 20 | The impact of the delay of our Finding of No Significant Impact (FONSI) report required us to hold back on a significant amount of equipment purchases. We have not fully caught up with our baseline and anticipate catching up in the next quarter. | 1 | The significant delay of our FONSI report impacted actual construction, however we are making progress in catching up to baseline. We have secured the necessary contractors to begin construction. We anticipate an Oct or Nov. groundbreaking and plan to increase simultaneous construction efforts to catch up to baseline. | 15 | We are making progress in catching up to baseline. We anticipate groundbreaking in October or November. | 10 | We have set up a test network, multi-demark environment to pre-troublshoot network. We are making progress in catching up to baseline. | 2011-11-30 16:20 | 2011-11-30 16:20 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2011 | Q4 | Q4 - 2011 | 5085 | 4756 | TRUE | 12 | We are making progress in catching up to the baseline. The delay in obtaining Construction Permits was our largest obstacle this quarter. | 31 | Notification | Delay in the project's construction caused a delay in notification efforts for phase 1 and phase 2 last mile areas. | 100 | N/A | 100 | N/A | 50 | Although behind the baseline, there is no impact to the schedule. Appraisals for all eCommunity Technology Centers (eCTCs)/Network Operation Centers (NOC) facilities are complete and Lease Agreements have been sent out for review by the Lessor. | 10 | The permit process has been significantly slower than expected due to 1) The A2D team being new to Alabama Department of Transportation (ALDOT) inspectors, thereby receiving a higher level of scrutiny, and 2) ALDOT not being able to process the number of permits simultaneously as originally planned. We have set up meetings with ALDOT and State Officials to address this issue and ensure a much more efficient and productive process to get back on schedule. | 33 | Site preparation is directly tied to Construction Activity. The project construction activity is behind the baseline due to the slow pace of the permit approvals process. One of three planned construction management sites fully set up and staffed. | 22 | In relationship with construction activity, there is no need to over purchase equipment until more network is built. We have acquired the equipment for 90% of phase 1. | 4 | The slower than planned permit process slowed network build; however, the installation of fiber conduit did commence in December. | 16 | As discussed in 2g above, We have acquired the equipment for 90% of phase 1. | 12 | Although behind baseline, as an indirect result of the slow permit process, we were able to stand up and begin testing and refining the eCommunity intranet-based platform and customized set-top box. | 2012-02-17 10:44 | 2012-02-17 10:44 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2012 | Q1 | Q1 - 2012 | 6353 | 5779 | TRUE | 14 | The Project's drawdown system was suspended and a stop-work order was put into place pending National Telecommunications and Information Administration (NTIA) review of the Corrective Action Plan (CAP). Overall construction efforts were increased in order to catch up to the baseline prior to the suspension of Federal funds. | 35 | Project/Construction Notification | Project/Construction Notification continued to be a significant effort. The project was in the process of initiating Stakeholder and Community events that were necessary to ensure the area was aware of the construction effort. Meetings continue to be held with Political Oversight Committees, Media Outlets and Broadband Stakeholders. In light of the current suspension of the federal funds and work stoppage, efforts in this area continued due to the importance of keeping the community aware of the status of the project. Additional emphasis was placed on the finalizing any Corrective Action Plan Responses and securing the federal assets. | 100 | N/A | 15 | The original schedule/plan was to complete the Engineering and Design by 'phase". Although the engineering for Phase 1 has been completed, the additional effort to complete the remaining designs for phases 2-9 were postponed due to the suspension of the federal funds. | 55 | Prior to the stop work order, property leases for all Network Operational Centers (NOC) were pending execution. | 15 | Prior to the stop work order, A2D received commitments from Alabama Department of Transportation to reduce permit review time. In addition, A2D obtained proposal for project exclusive utility locate services to help improve permit submission time. | 35 | Prior to the stop work order, the second construction management office and material storage yard was identified in the southern footprint and local hiring advertised. | 13 | In relationship with construction activity, there was no need to exceed the need to purchase additional equipment until more network is built. We have acquired the equipment for 100% of phase 1. | 8 | Installation of the fiber conduit progressed as a result of an increase in Contractor crews. The average production rate of each crew was one (1) mile per day. The Contractor crews ramped up to the following: Two (2) installation/plowing crews and three (3) boring crews. Three (3) additional contractors were scheduled for February to include two (2) more plow crews and one (1) statewide boring company. | 7 | The only Network Equipment deployed is co-located at the Level-3 facility in Dallas County. | 12 | This testing included fiber interoperability testing with service provider(s) from the co-location facility in Dallas County Alabama to the A2D test site in Atlanta GA. "Testing" involved measuring the stability of the design, as well as validating the systemâ€™s architecture. In light of the current funding suspension, minimal testing was performed during this period due to construction schedule and focus on Corrective Action Plan Response. | 2012-05-30 16:56 | 2012-05-30 16:56 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2012 | Q2 | Q2 - 2012 | 7231 | 6243 | TRUE | 15 | The Project's drawdown system was suspended and a stop-work order was put into place pending National Telecommunications and Information Administration (NTIA) review of the Corrective Action Plan (CAP). | 35 | Project/Construction Notification | Project Notification continued to be a significant effort. The Trillion initiated Stakeholder and Community meetings that were necessary to ensure the area was aware of the construction effort. Meetings were held with Alabama Governor's office , Alabama Department of Transportation (ALDOT), Congressmen, Senators and other political leaders to discuss the status of the project and to solicit their support. Trillion continued to schedule meetings with Political Oversight Committees, Media Outlets and Broadband Stakeholders. In light of the current suspension of the federal funds and work stoppage, efforts in this area continued due to the importance of keeping the community aware of the status of the project. Additional emphasis was placed on the finalizing any Corrective Action Plan Responses and securing the federal assets. | 100 | N/A | 15 | The original schedule/plan was to complete the Engineering and Design by 'phase". Although the engineering for Phase 1 has been completed, the additional effort to complete the remaining designs for phases 2-9 were postponed due to the suspension of the federal funds. A Request for Proposal (RFP) will be issued to a select universe of General Contractors (GCs) to solicit a pricing model for a Design/Build solution. | 55 | Prior to the stop work order, property leases for all Network Operational Centers (NOC) were pending execution. | 15 | Prior to the stop work order, Trillion received commitments from Alabama Department of Transportation to minimize permit review time. In addition. ALDOT has agreed to meet with Trillion's newly-acquired General Contractor to discuss methods for ensuring an efficient permitting process. | 35 | As a result of the work stoppage, all construction material have been moved/relocated to a secured warehouse facility. The new facility is gated and monitored via cameras placed throughout the facility. | 14 | As a result of the suspension of the project, no construction activity has occurred since February 9, 2012. There was no need to exceed the requirement to purchase additional equipment until the network construction activity continues. A revised detailed budget forecast and a detailed budget narrative on how Trillion intends to complete the networkâ€™s deployment with the balance of the remaining Federal Grant available are underway. This analysis will be completed by July 13th. | 8 | The Project has been suspended, including Trillion's ability to drawdown funds to obtain components for the build out. A stop-work order was put into place pending National Telecommunications and Information Administration (NTIA) review of the Corrective Action Plan (CAP). | 7 | The only Network Equipment deployed is co-located at a secured facility in Dallas County. No additional equipment has been installed since the Work Stop Notification. All network equipment have been transferred to a secure warehouse facility located in the Hope Hull Alabama vicinity. The equipment was originally staged in an open fenced-in construction yard, in Hayneville Alabama. An inventory of all equipment was taken during the transfer. | 12 | The original testing included fiber interoperability testing with service provider(s) from the co-location facility in Dallas County Alabama to the test site in Atlanta GA. "Testing" involved measuring the stability of the design, as well as validating the systemâ€™s architecture. In light of the current funding suspension, as well as the sub-recipient's removal from the project, no testing was performed during this period and all equipment is being removed from the sub-recipient's office location in Atlanta, GA. | 2012-08-23 14:27 | 2012-08-23 14:27 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2012 | Q3 | Q3 - 2012 | 7717 | 6546 | TRUE | 15 | The Project's drawdown system was suspended and a stop-work order was put into place by the NOAA Grants Office. Trillion was notified by NOAA of the project's termination on September 26, 2012. | 35 |  | The Project has been terminated. Prior to the termination notification, Trillion initiated Stakeholder and Community meetings that were necessary to ensure the area was aware of the planned construction effort. Meetings were held with Alabama Governor's office , Alabama Department of Transportation (ALDOT), Congressmen, Senators and other political leaders to discuss the status of the project and to solicit their support. Trillion continued to schedule meetings with Media Outlets and Broadband Stakeholders. | 100 | N/A | 15 | Trillion was notified by NOAA of the project's termination on September 26, 2012. The original schedule/plan was to complete the Engineering and Design by 'phase". Although the engineering for Phase 1 has been completed, the additional effort to complete the remaining designs for phases 2-9 were postponed due to the suspension of the federal funds. | 55 | Trillion was notified by NOAA of the project's termination on September 26, 2012. Prior to the termination order, property leases for all Network Operational Centers (NOC) were pending execution. ALDOT approved the ROW Valuation. This valuation served as the non-federal match portion of the project. A letter from ALDOT supporting the valuation was provided to NTIA/NOAA via the CAP Responses. | 15 | Trillion was notified by NOAA of the project's termination on September 26, 2012. Prior to the termination order, Trillion received commitments from Alabama Department of Transportation to reduce permit review time. | 35 | As a result of the termination, all construction material remains in a secured warehouse facility. The facility is gated and monitored via cameras placed throughout the facility. | 14 | As a result of the suspension/termination of the project, no construction activity has occurred since February 9, 2012. There was no need to exceed the requirement to purchase additional equipment until the network construction activity continues. Prior to the termination notification, a revised detailed budget forecast and a detailed budget narrative on how Trillion intended to complete the networkâ€™s deployment with the balance of the remaining Federal Grant was performed. | 8 | The Project has been terminated. No additional construction was performed in this quarter. | 7 | No additional equipment has been installed since the Work Stop Notification. All network equipment have been transferred to a secure warehouse facility located in the Hope Hull Alabama vicinity. The equipment was originally staged in an open fenced-in construction yard, in Hayneville Alabama. An inventory of all equipment was taken during the transfer. | 12 | Trillion was notified by NOAA of the project's termination on September 26, 2012. Therefore, no additional testing has been performed. The original testing included fiber interoperability testing with service provider(s) from the co-location facility in Dallas County Alabama to the A2D test site in Atlanta GA. "Testing" involved measuring the stability of the design, as well as validating the systemâ€™s architecture. In light of the current funding suspension, as well as A2D's removal from the project, no testing was performed during this period and all equipment is being removed from A2D's office location in Atlanta, GA. | 2012-10-31 00:19 | 2012-10-31 00:19 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570131 | 2010 | Q4 | Q4 - 2010 | 1259 | 2288 | TRUE | 2 | N/A | 0 | Land Acquisition | Pending approval of our environmental assessment, no land can be acquired. | 26 | N/A | 33 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 9 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-21 16:26 | 2011-02-21 16:26 | 6061 | 6061 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2011 | Q1 | Q1 - 2011 | 2299 | 2895 | TRUE | 2 | N/A | 26 | Land Acquisition | N/A | 43 | N/A | 36 | N/A | 0 | N/A | 19 | N/A | 1 | N/A | 50 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-05-25 13:55 | 2011-05-25 13:55 | 6061 | 6061 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2011 | Q2 | Q2 - 2011 | 3279 | 3402 | TRUE | 5 | No Variance | 2 | Land Acquisition | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 68 | No Variance | 27 | We have experienced environmental delays and have made route changes which negatively affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 0 | No Variance | 19 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 0 | All site preparation expense to date has been allocated to the construction milestone category. | 1 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 2 | No Variance | 2 | Some expenses previously reported under equipment deployment have been allocated to the "miscellaneous" category of expenses, decreasing this percentage. | 2 | No Variance | 2011-08-23 16:01 | 2011-08-23 16:01 | 6061 | 6061 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2011 | Q3 | Q3 - 2011 | 4351 | 4032 | TRUE | 12 | Fiber delays, route changes, and Environmental Assessment changes delayed overall project completion. The 12% project complete reported at the end of September should change significantly by the end of December with the purchase of several shipments of fiber. | 0 | Land Acquisition | To date, we are leasing and using public right-of-way instead of purchasing land so Land Acquisition has not been as high as we predicted it would be at this stage. | 100 | FONZI is complete, thus this milestone is 100% complete. Post-FONZI environmental assessment work will be done under Item 2c, Network Design. | 20 | This is the appropriate percent complete for a project that is 12% complete overall. Additional detail design will be accelerated as project progresses. Post-FONSI budget in the environmental assessment category was added to this category, thereby decreasing percent complete. | 0 | No Variance | 9 | We classified some Construction Permits and Other Approvals expenses in the wrong categories. Re-classifying these dollars in the appropriate categories results in a decrease in percent complete for this category. | 4 | We have found that we are able to utilize cabinets instead of the buildings originally designed and budgeted, thereby incurring less expenses overall by utilizing cabinets instead of incurring land, buildings, and site prep expenses. | 26 | This is the appropriate percent complete for a project that is 12% complete overall. Fiber procurement delays have precluded the purchase of access equipment. | 8 | Fiber delays have caused this category to come up short. You will see a significant increase in network build during 4th quarter, 2011, due to fiber procurement. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2011-11-30 15:50 | 2011-11-30 15:50 | 6061 | 6061 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2011 | Q4 | Q4 - 2011 | 5253 | 4919 | TRUE | 19 | Receipt of fiber resulted in 50% increase in project completion from 3rd Quarter. Expect significant additional progress next quarter. | 0 | Land Acquisition | To date, we are leasing and using public right-of-way instead of purchasing land so Land Acquisition has not been as high as we predicted it would be at this stage. | 100 | FONSI is complete, thus this milestone is 100% complete. Post-FONSI environmental assessment work will be done under item 2c, Network Design. | 27 | Consistent with project progress. | 0 | No variance. | 10 | Approvals procured as needed. Some delay is attributable to delayed receipt of fiber. | 7 | Site preparation performed as needed. Some delay is attributable to delayed receipt of fiber. | 27 | This is the appropriate percent complete for a project that is 19% complete overall. Fiber procurement delays have delayed the purchase of access equipment. | 17 | Receipt of fiber resulted in 50% increase in project completion from 3rd Quarter. Expect significant additional progress next quarter. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2012-02-24 15:24 | 2012-02-24 15:24 | 6061 | 6061 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2012 | Q1 | Q1 - 2012 | 6345 | 5775 | TRUE | 26 | Mainline construction has increased in pace and several potential customers are in negotiation for connection. Variance from plan is still a reflection of fiber shortage and delay in environmental assessment acceptance. Now that we have program income and fiber supply has opened up, we anticipate being on-target with the overall project milestone by first quarter, 2013. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so Land Acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 33 | Network design is evolving and progressing with increased mainline construction pace. Variance from baseline is still primarily due to pace of the project in general. We anticipate being on-target with the network design milestone by first quarter, 2013. | 0 | No variance. | 11 | Approvals procured as needed. Right-of-way cost is less than anticipated but drop and lateral placement is just now beginning to occur due to fiber shortages. We anticipate being closer to target with the construction permits/approvals milestone by first quarter, 2013. | 12 | We have been utilizing public rights-of-way more than planned thereby reducing land acquisition and site preparation. We anticipate being closer to target with the site preparation milestone by first quarter, 2013. | 27 | This is an appropriate percentage complete for current status of overall project. We expect significant increases in equipment deployment as customers connect. However, we have found that the educational community anchor institutions have ERATE timelines they follow rather rigidly. Consequently, we should have our target met by second quarter, 2013. | 25 | Mainline construction has increased in pace and several potential customers are in negotiation for connection. Variance from plan is still a reflection of fiber shortage and delay in environmental assessment acceptance. We anticipate being on-target with the network build milestone by first quarter, 2013. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2012-05-30 11:03 | 2012-05-30 11:03 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2012 | Q2 | Q2 - 2012 | 7077 | 6166 | TRUE | 34 | Mainline construction has increased in pace and several potential customers are in negotiation for connection. Variance from plan is still a reflection of fiber shortage and delay in environmental assessment acceptance. Now that we have program income and fiber supply has opened up, we anticipate being on-target with the overall project milestone by second quarter, 2013. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so Land Acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 41 | Network design is evolving and progressing with increased mainline construction pace. Variance from baseline is still primarily due to paceof the project in general. We anticipate being on-target with the network design milestone by second quarter, 2013. | 0 | No variance. | 12 | Approvals procured as needed. Drop and lateral placement is just now beginning to occur due to fiber shortages. We anticipate being closer to target with the construction permits/approvals milestone by second quarter, 2013. | 12 | We have not been utilizing private land as much as planned thereby reducing land acquisition and site preparation. We anticipate being closer to target with the site preparation milestone by second quarter, 2013. | 33 | This is an approximate percentage complete for current status of overall project. We expect significant increases in equipment deployment as customers connect. However, we have found that the educational community anchor institutions have ERATE timelines they follow rather rigidly. Consequently, we should have our target met by third quarter, 2013. | 34 | Mainline construction has increased in pace and several potential customers are in negotiation for connection. Variance from plan is still a reflection of fiber shortage and delay in environmental assessment acceptance. We anticipate being on-target with the network build milestone by second quarter, 2013. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2012-08-15 14:20 | 2012-08-15 14:20 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2012 | Q3 | Q3 - 2012 | 7827 | 6617 | TRUE | 46 | Mainline construction has increased in pace and several potential customers are in negotiation for connection. Variance from plan is still a reflection of fiber shortage and delay in environmental assessment acceptance. Now that we have program income and fiber supply has opened up, we anticipate being on-target with the overall project milestone by second quarter, 2013. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so Land Acquisition has not been as high as we predicted it would be at this stage. We anticipate using any unused funds in this category for network build. | 100 | No variance. | 53 | Network design is evolving and progressing with increased mainline construction pace. Variance from baseline is partially due to the pace of the project in general but also partially due to improved efficiencies in execution over budgets and plans. Unused funds in this category are planned to be spent in the network build category. | 0 | No variance. | 13 | Approvals procured as needed. Drop and lateral placement just began last quarter due to fiber shortages. We anticipate being closer to target with the construction permits/approvals milestone by second quarter, 2013. However, due to careful use of public rights-of-way, we anticipate that this section will remain under budget and we will be able to use surplus funds for network build. | 12 | We have not been utilizing private land as much as planned thereby reducing land acquisition and site preparation. We anticipate being closer to target with the site preparation milestone by second quarter, 2013. However, due to careful use of public rights-of-way, we anticipate that this section will remain under budget and we will be able to use surplus funds for network build. | 38 | This is an approximate percentage complete for current status of overall project. We expect significant increases in equipment deployment as customers connect. However, we have found that the educational community anchor institutions have ERATE timelines they follow rather rigidly. Consequently, we should have our target met by third quarter, 2013. | 48 | Mainline construction has increased in pace and several potential customers are in negotiation for connection. Variance from plan is still a reflection of fiber shortage and delay in environmental assessment acceptance. We anticipate being on-target with the network build milestone by second quarter, 2013. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. We anticipate using any unused funds in this category for network build. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. We anticipate using any unused funds in this category for network build. | 2012-11-12 13:22 | 2012-11-12 13:22 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2012 | Q4 | Q4 - 2012 | 9101 | 7873 | TRUE | 57 | Mainline construction is still increasing in pace. Variance from plan is still a reflection of fiber shortage and delay in environmental assessment acceptance. We anticipate being on-target with the overall project milestone by second quarter, 2013. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so Land Acquisition has not been as high as we predicted it would be at this stage. We anticipate using any unused funds in this category for network build. | 100 | No variance. | 65 | Network design is evolving and progressing with increased mainline construction pace. Variance from baseline is partially due to the pace of the project in general but also partially due to improved efficiencies in execution over budgets and plans. Unused funds in this category are planned to be spent in the network build category. | 0 | No variance. | 13 | Approvals procured as needed. We anticipate being closer to target with the construction permits/approvals milestone by second quarter, 2013. However, due to careful use of public rights-of-way, we anticipate that this section will remain under budget and we will be able to use surplus funds for network build. | 12 | We have not been utilizing private land as much as planned thereby reducing land acquisition and site preparation. We anticipate being closer to target with the site preparation milestone by second quarter, 2013. However, due to careful use of public rights-of-way, we anticipate that this section will remain under budget and we will be able to use surplus funds for network build. | 44 | This is an approximate percentage complete for current status of overall project. We expect significant increases in equipment deployment as customers connect. However, we have found that the educational community anchor institutions have ERATE timelines they follow rather rigidly. Consequently, we should have our target met by third quarter, 2013. | 59 | Mainline construction has increased in pace. Variance from plan is still a reflection of fiber shortage and delay in environmental assessment acceptance. We anticipate being on-target with the network build milestone by second quarter, 2013. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. We anticipate using any unused funds in this category for network build. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. We anticipate using any unused funds in this category for network build. | 2013-02-28 16:33 | 2013-02-28 16:33 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2013 | Q1 | Q1 - 2013 | 9905 | 8494 | TRUE | 68 | Mainline construction continues to increase in pace. Variance from plan is still a reflection of fiber shortage and delay in environmental assessment acceptance. We anticipate filing for an extension and completing the project by the end of third quarter, 2013. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so Land Acquisition has not been as high as we predicted it would be at this stage. We anticipate using any unused funds in this category for network build. | 100 | No variance. | 74 | Network design is evolving and progressing with increased mainline construction pace. Variance from baseline is partially due to the pace of the project in general but also partially due to improved efficiencies in execution over budgets and plans. Unused funds in this category are planned to be spent in the network build category. | 0 | No variance. | 15 | Approvals procured as needed. We anticipate being closer to target with the construction permits/approvals milestone by second quarter, 2013. However, due to careful use of public rights-of-way, we anticipate that this section will remain under budget and we will be able to use surplus funds for network build. | 12 | We have not been utilizing private land as much as planned thereby reducing land acquisition and site preparation. We anticipate being closer to target with the site preparation milestone by second quarter, 2013. However, due to careful use of public rights-of-way, we anticipate that this section will remain under budget and we will be able to use surplus funds for network build. | 50 | We expect significant increases in equipment deployment as customers connect. However, we have found that the educational community anchor institutions have ERATE timelines they follow rather rigidly. Consequently, we should have our target met by third quarter, 2013. | 72 | Mainline construction has increased in pace. Variance from plan is still a reflection of fiber shortage and delay in environmental assessment acceptance. We anticipate being on-target with the network build milestone by third quarter, 2013. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. We anticipate using any unused funds in this category for network build. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. We anticipate using any unused funds in this category for network build. | 2013-05-24 16:47 | 2013-05-24 16:47 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2013 | Q2 | Q2 - 2013 | 10677 | 9000 | TRUE | 88 | Mainline construction continues to increase in pace. Variance from plan is still a reflection of fiber shortage and delay in environmental assessment acceptance. Construction will be completed by the end of third quarter, 2013. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so Land Acquisition has not been as high as we predicted it would be at this stage. We anticipate using any unused funds in this category for network build. | 100 | No variance. | 79 | Network design is evolving and progressing with increased mainline construction pace. Variance from baseline is partially due to the pace of the project in general but also partially due to improved efficiencies in execution over budgets and plans. Unused funds in this category have been moved to the network build category. | 0 | No variance. | 95 | Approvals procured as needed. Due to careful use of public rights-of-way, this section has remained under budget and we have used surplus funds for network build. | 98 | We have not been utilizing private land as much as planned thereby reducing land acquisition and site preparation. Due to careful use of public rights-of-way, this section has remained under budget and we have used surplus funds for network build. | 99 | We expect significant increases in equipment deployment as we finish the project and customers connect. However, we have found that the educational community anchor institutions have ERATE timelines they follow rather rigidly. Consequently, we should have our target met by third quarter, 2013. | 89 | Mainline construction has increased in pace. Variance from plan is still a reflection of fiber shortage and delay in environmental assessment acceptance. We anticipate being on-target with the network build milestone by third quarter, 2013. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. We anticipate using any unused funds in this category for network build. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. We anticipate using any unused funds in this category for network build. | 2013-08-21 10:51 | 2013-08-21 10:51 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2013 | Q3 | Q3 - 2013 | 12179 | 10365 | TRUE | 100 | Overall project complete. | 0 | Land Acquisition | No Land Acquisition expenses. | 100 | No variance. | 100 | No variance. | 0 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 0 | No equipment deployment expenses. | 0 | No network testing expenses. | 2014-05-12 11:43 | 2014-05-12 11:43 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570132 | 2010 | Q4 | Q4 - 2010 | 1133 | 2171 | TRUE | 0 | Even though the percent complete reflects "0" there is progress being made on the project; this is due to the amount that has been completed at the end of this reporting period being so minute compared to the overall size of the project that it reflects a total percentage completion of less than 1. | 0 | N/A | N/A | 50 | Completion of the draft Environmental Assessment is on schedule. The draft EA is due to be submitted to NTIA by 2/1/11. ENMR-Plateau submitted the draft EA to NTIA on 1/15/11, two and a half weeks ahead of the due date. | 50 | The engineering firm has been diligently working on the network design. The percent completed is an estimate based on the amount of work completed at the end of this reporting period. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 2011-02-14 12:55 | 2011-02-14 15:38 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2011 | Q1 | Q1 - 2011 | 1517 | 2472 | TRUE | 1 | No variance. | 0 | N/A | N/A | 95 | The draft Environmental Assessment was submitted to NTIA on 1/15. ENMR-Plateau's environmental consultant compiled concurrence letters from all related agencies and submitted a final EA on 4/8. Currently waiting on issuance of FONSI by NTIA. | 85 | Approximately 85% of the work related to this milestone has been complete. | 50 | Approximately 50% of the work related to this milestone has been complete. | 50 | Approximately 50% of the work related to this milestone has been complete. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 2011-04-27 11:34 | 2011-04-27 11:34 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2011 | Q2 | Q2 - 2011 | 3251 | 3388 | TRUE | 2 | Please see section #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 75 | Continuing work on rights of way. Expecting completion of this milestone next quarter. | 75 | No variance. | 0 | No variance. | 0 | Please see section #3 below. | 0 | Please see section #3 below. | 0 | Please see section #3 below. | 0 | No variance. | 2011-08-22 10:57 | 2011-08-22 10:57 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2011 | Q3 | Q3 - 2011 | 4189 | 3943 | TRUE | 2 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 70 | Continuing acquisition of rights of way. Expected to be complete by the end of Q2 2012. Rights of way and permits cannot be obtained until construction planning is complete. Since the environmental process took longer than was expected, it resulted in a delay in the construction planning and also the acquisition of the rights of way and permits. Rights of way and permits are requested through government agencies such as the NMDOT. Rights of way and permits are obtained for each location based on the construction schedule so even though all rights of way and permits are not complete at this time there should be no impact to the project schedule. | 40 | Continuing acquisition of rights of way. Expected to be complete by the end of Q2 2012. Rights of way and permits cannot be obtained until construction planning is complete. Since the environmental process took longer than was expected, it resulted in a delay in the construction planning and also the acquisition of the rights of way and permits. Rights of way and permits are requested through government agencies such as the NMDOT. Rights of way and permits are obtained for each location based on the construction schedule so even though all rights of way and permits are not complete at this time there should be no impact to the project schedule. | 66 | Two of the three sites have been acquired. RFP for site construction expected to be finalized and sent out for bid in November. | 0 | Equipment procurement began in Q4 2011. Expect to complete contract negotiations with all vendors and begin installation by the end of Q4. As of now we are projecting to have almost all equipment procured by the end of Q2 2012. | 0 | Construction began on10/10. Expect to catch up to baseline in by the end of Q2 2012. | 0 | No equipment has been purchased. | 0 | No testing has been conducted due to not having equipment deployed. | 2011-11-21 16:01 | 2011-11-21 16:13 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2011 | Q4 | Q4 - 2011 | 4503 | 4152 | TRUE | 6 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 90 | Continuing acquisition of rights of way. Expected to be complete by the end of Q2 2012. Rights of way and permits cannot be obtained until construction planning was complete. Since the environmental process took longer than was expected, it resulted in a delay in the construction planning and also the acquisition of the rights of way and permits. Rights of way and permits are requested through government agencies such as the NMDOT. Rights of way and permits are obtained for each location based on the construction schedule so even though all rights of way and permits are not complete at this time there should be no impact to the project schedule. | 65 | Continuing acquisition of rights of way. Expected to be complete by the end of Q2 2012. Rights of way and permits cannot be obtained until construction planning was complete. Since the environmental process took longer than was expected, it resulted in a delay in the construction planning and also the acquisition of the rights of way and permits. Rights of way and permits are requested through government agencies such as the NMDOT. Rights of way and permits are obtained for each location based on the construction schedule so even though all rights of way and permits are not complete at this time there should be no impact to the project schedule. | 70 | All three sites have been acquired. CO buildings contractor has been selected with construction anticipated to begin in Q1 2012 and end in Q2 2012. | 11 | Equipment procurement and installation began at the end of Q4 2011. Progress is proceeding smoothly. The majority of the equipment is expected to be procured by the end of Q2 2012. | 2 | Construction began on October 10th. We anticipate catching up to baseline projections in subsequent quarters. | 11 | Equipment deployment follows equipment procurement. We anticipate catching up to baseline projections in subsequent quarters. | 5 | Network testing follows network build and equipment deployment. We anticipate catching up to baseline projections in subsequent quarters. | 2012-01-27 11:24 | 2012-01-27 11:24 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2012 | Q1 | Q1 - 2012 | 5979 | 5589 | TRUE | 22 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 80 | Continuing acquisition of rights of way. Expected to be complete by the end of Q2 2012. Rights of way and permits cannot be obtained until construction planning was complete. Since the environmental process took longer than was expected, it resulted in a delay in the construction planning and also the acquisition of rights of way and permits. Rights of way and permits are obtained through government agencies such as the NMDOT. Rights of way and permits are obtained for each location based on the construction schedule so even though all rights of way and permits are not complete at this time there should be no impact to the project schedule. | 75 | CO buildings construction and DC power equipment installation expected to be complete by the end of next quarter. | 44 | Equipment procurement began in Q4 2011. The majority of the equipment is expected to be procured by July 31st 2012. | 13 | Outside plant construction began on October 10th and is progressing quickly. Based on the efficiency of the contractor and the fact that there are currently 12 separate construction crews working on this project simultaneously we are anticipating to catch up to milestones included in the baseline report in subsequent quarters. | 35 | Equipment installation began in Q4 2011. Based on the efficiency of the equipment installers we anticipate catching up to milestones included in the baseline report in subsequent quarters. | 35 | Network testing follows network build and equipment deployment. | 2012-05-08 17:31 | 2012-05-08 17:31 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2012 | Q2 | Q2 - 2012 | 6939 | 6097 | TRUE | 40 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 95 | Continuing acquisition of rights of way. Rights of way and permits cannot be obtained until construction planning was complete. Since the environmental process took longer than was expected, it resulted in a delay in the construction planning and also the acquisition of rights of way and permits. Rights of way and permits are obtained through government agencies such as the NMDOT. Rights of way and permits are obtained for each location based on the construction schedule so even though all rights of way and permits are not complete at this time there should be no impact to the project schedule. | 100 | No variance. | 54 | Equipment procurement began in Q4 2011. The majority of the equipment is expected to be procured by July 31st 2012. | 37 | Outside plant construction began on October 10th and is progressing quickly. Based on the efficiency of the contractor and the fact that there are currently 12 separate construction crews working on this project simultaneously we are anticipating to catch up to milestones included in the baseline report in subsequent quarters. | 45 | Equipment installation began in Q4 2011. Based on the efficiency of the equipment installers we anticipate catching up to milestones included in the baseline report in subsequent quarters. | 45 | Network testing follows network build and equipment deployment. | 2012-08-08 18:07 | 2012-08-08 18:07 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2012 | Q3 | Q3 - 2012 | 7565 | 6441 | TRUE | 63 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 72 | Equipment procurement began in Q4 2011. The majority of the equipment is expected to be procured by 12/31/2012. | 58 | Outside plant construction began on October 10, 2011 and is progressing quickly. Based on the efficiency of the contractor we are anticipating to catch up to milestones included in the baseline report in subsequent quarters. | 65 | Equipment installation began in Q4 2011. Based on the efficiency of the equipment installers we anticipate catching up to milestones included in the baseline report in subsequent quarters. | 65 | Network testing follows network build and equipment deployment. | 2012-10-30 11:57 | 2012-10-30 11:57 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2012 | Q4 | Q4 - 2012 | 9003 | 7779 | TRUE | 70 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 74 | Equipment procurement began in Q4 2011. ENMR anticipates to fully complete equipment procurement by the award end date. | 64 | Outside plant construction began on October 10, 2011 and is progressing quickly. Based on the efficiency of the contractor ENMR anticipates to fully complete construction by the award end date. | 74 | Equipment deployment began in Q4 2011. ENMR anticipates to fully complete equipment deployment by the award end date. | 70 | Network testing follows network build and equipment deployment. | 2013-02-27 11:03 | 2013-02-27 11:03 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2013 | Q1 | Q1 - 2013 | 9967 | 8528 | TRUE | 79 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 74 | Equipment procurement began in Q4 2011. ENMR anticipates to fully complete equipment procurement by the award end date. | 80 | Outside plant construction began on October 10, 2011 and is progressing quickly. Based on the efficiency of the contractor ENMR anticipates to fully complete construction by the award end date. | 74 | Equipment deployment began in Q4 2011. ENMR anticipates to fully complete equipment procurement by the award end date. | 74 | Network testing follows network build and equipment deployment. | 2013-05-29 14:51 | 2013-05-29 14:51 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2013 | Q2 | Q2 - 2013 | 10755 | 9043 | TRUE | 94 | ENMR expects to be fully complete by the award end date of July 31, 2013. Outside plant construction is complete, equipment has been procured and installed. Currently waiting on final invoicing from contractors and equipment vendors in order to process for payment at which point ENMR will draw down grant funds for reimbursement of allowable costs. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 88 | Equipment procurement is complete. Currently waiting on final invoicing from equipment vendors. | 95 | Outside plant fiber construction is complete. Currently waiting on final invoicing from contractor. | 88 | Equipment deployment is complete. Currently waiting on final invoicing from equipment vendors/installers. | 88 | Network testing follows network build and equipment deployment. | 2013-08-27 10:45 | 2013-08-27 10:45 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2013 | Q3 | Q3 - 2013 | 11283 | 9438 | TRUE | 100 | No variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 2013-11-19 10:36 | 2013-11-19 10:36 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570133 | 2010 | Q3 | Q3 - 2010 | 339 | 1436 | TRUE | 3 | Consequent delay in Network Design and Rights of Way work. Actual construction of network will commence in Q4. | 15 | Grant Administration | Due to the long delays in processing our of request for an Entity Transfer of our Grant, and for work on Environmental Assessment requirements, much of our outside consulting for administrative duties were delayed. Now that the Entity Transfer is final, and our Environmental Assessment report has been submitted, we are able to refocus our efforts to the actual construction phases and the administrative resources required for that effort. We expect the need for administrative support to still be at the levels budgeted, and that the 3Q shortfall is only the result of timing. | 100 | Environmental Assessment work took far longer and consumed far more manpower than anticipated. | 43 | We anticipated that the Network Design would be 41.25% complete through 2Q, and 100% complete by 3Q. Through 3Q our actual results for Network Design was 43.14% complete. We estimate to be at 100% complete by 1Q2011. We expect to dedicate an increased amount of outside consultant time to these efforts. This will be possible now that the Environmental Assessment work is complete, and those same resources can be dedicated to Network Design efforts. | 0 | We have not yet completed Rights of Way work by the end of the 3Q. Work will begin in 4Q on these approvals. With the completion of the Environmental Assessment we will move toward this milestone quickly. | 1 | We have not yet completed work on Construction and Other Approvals. Work will begin in 4Q on construction permits and other approvals. With the completion of the Environmental Assessment we will move toward this milestone quickly. | 0 | We anticipate Site Preparation work to begin 4Q of 2010 or 1Q of 2011. With the completion of the Environmental Assessment we will move toward this milestone quickly. | 0 | With the completion of the Environmental Assessment we will move toward this milestone quickly. | 1 | With the completion of the Environmental Assessment we will move toward this milestone quickly. | 0 | N/A | 0 | N/A | 2010-11-17 13:07 | 2010-11-17 13:07 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2010 | Q4 | Q4 - 2010 | 1035 | 2076 | TRUE | 3 | Zero variance | 11 | Grant Administration | Zero variance | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 61 | Baseline 45%;physical construction delayed due to EA process. Redirected resources to Network Design as result to assure that we are ready without delay to begin actual construction as soon as weather permits. | 0 | Baseline 15%; Delayed waiting for issuance of EA FONSI. | 0 | Baseline 11%; Delayed waiting for issuance of EA FONSI. | 0 | Baseline 1%; Delayed waiting for issuance of EA FONSI. | 0 | Baseline 10%; Delayed waiting for issuance of EA FONSI. | 2 | Baseline 1%; physical construction delayed waiting for issuance of EA FONSI. Increased pre-physical construction efforts on additional projects such as staking and preliminary make ready work. | 0 | Zero variance | 0 | Zero variance | 2011-02-10 10:13 | 2011-02-10 10:13 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2011 | Q1 | Q1 - 2011 | 2123 | 2807 | TRUE | 5 | Baseline = 8%; $2,507,018 expended of $4,008,953 budgeted through first quarter 2011. Total budget (Federal and matching funds) is $48,673,735. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Non-Federal matching funds have been fully utilized in the project. | 17 | Grant Administration | Baseline = 19%; $177,581 expended of $198,251 budgeted through first quarter 2011. Total budget (Federal and matching funds) is $1,030,440. Variance is not significant. We expect to catch up to budget during the next quarter. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 49 | Baseline = 100%; $291,285 expended of $596,031 budgeted through first quarter 2011. Total budget (Federal and matching funds) is $596,031. According to the provisions of the Grant, we have been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Network Design. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. Note: Expenditures for Rights of Way and Co | 2 | Baseline = 36%; $11,233 expended of $195,792 budgeted through first quarter 2011. Total budget (Federal and matching funds) is $542,768.According to the provisions of the Grant, we have been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Rights of Way. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. Note: Expenditures for Rights of Way were errone | 27 | Baseline = 35%; $49,531 expended of $63,203 budgeted through first quarter 2011. Total budget (Federal and matching funds) is $180,923.Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Construction Permits. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Note: Expenditures for Construction Permits were erroneously charged to the Network Design category for our 4Q2010 report. They are charged to the proper categories for this report. | 0 | Baseline = 1%; $248 expended of $24,000 budgeted through first quarter 2011. Total budget (Federal and matching funds) is $1,995,501.Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Site Preparation. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. | 4 | Baseline = 10%; $251,784 expended of $558,700 budgeted through first quarter 2011. Total budget (Federal and matching funds) is $5,598,140. Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Equipment Procurement. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. | 5 | Baseline = 6%; $1,725,356 expended of $2,372,975 budgeted through first quarter 2011. Total budget (Federal and matching funds) is $37,980,932. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 0 | Baseline = 0%; No variance. Total budget (Federal and matching funds) is $374,500. | 0 | Baseline = 0%; No variance. Total budget (Federal and matching funds) is $374,500. | 2011-05-18 11:22 | 2011-05-18 11:22 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2011 | Q2 | Q2 - 2011 | 3171 | 3346 | TRUE | 9 | Baseline = 15%; $4,511,748 expended of $7,298,641 budgeted through second quarter 2011. Total budget (Federal and matching funds) is $48,673,735. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Non-Federal matching funds have been fully utilized in the project. | 25 | Grant Administration | Baseline = 27%; $258,137 expended of $281,470 budgeted through second quarter 2011. Total budget (Federal and matching funds) is $1,030,440. Variance is not significant. We expect to catch up to budget during the next quarter. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 66 | Baseline = 100%; $392,544 expended of $596,031 budgeted through second quarter 2011. Total budget (Federal and matching funds) is $596,031. According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Network Design. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. Note: Expenditures for Rights of Way and Constr | 3 | Baseline = 51%; $18,731 expended of $275,341 budgeted through second quarter 2011. Total budget (Federal and matching funds) is $542,768.According to the provisions of the Grant, we have been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Rights of Way. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. Note: Expenditures for Rights of Way were erron | 61 | Baseline = 49%; $111,222 expended of $87,658 budgeted through second quarter 2011. Total budget (Federal and matching funds) is $180,923.Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in actual construction. In order to avoid future delays we have accelerated some up front activities such as Permitting for upcoming projects. Note: Expenditures for Construction Permits were erroneously charged to the Network Design category for our 4Q2010 report. They are charged to the proper categories for this report. | 0 | Baseline = 4%; $248 expended of $72,000 budgeted through second quarter 2011. Total budget (Federal and matching funds) is $1,995,501.Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Site Preparation. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. | 5 | Baseline = 21%; $258,621 expended of $1,187,300 budgeted through second quarter 2011. Total budget (Federal and matching funds) is $5,598,140. Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Equipment Procurement. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. | 9 | Baseline = 12%; $3,472,245 expended of $4,727,007 budgeted through second quarter 2011. Total budget (Federal and matching funds) is $37,980,932. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 0 | Baseline = 11%; $0 expended of $42,333 budgeted through second quarter 2011. Total budget (Federal and matching funds) is $374,500. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 0 | Baseline = 8%; $0 expended of $29,500 budgeted through second quarter 2011. Total budget (Federal and matching funds) is $374,500. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 2011-08-17 18:39 | 2011-08-17 18:39 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2011 | Q3 | Q3 - 2011 | 4283 | 3992 | TRUE | 17 | Baseline = 22%; $8,156,842 expended of $10,679,972 budgeted through third quarter 2011. Total budget (Federal and matching funds) is $48,673,735. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Non-Federal matching funds have been fully utilized in the project. | 32 | Grant Administration | Baseline = 35%; $329,516 expended of $364,689 budgeted through third quarter 2011. Total budget (Federal and matching funds) is $1,030,440. Variance is not significant. We expect to catch up to budget during the next quarter. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | Baseline = 100%; $676,719 expended of $596,031 budgeted through third quarter 2011. Total budget (Federal and matching funds) is $596,031. According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Network Design. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. Note: Expenditures for Rights of Way and Construction | 3 | Baseline =100%; $18,795 expended of $542,768 budgeted through third quarter 2011. Total budget (Federal and matching funds) is $542,768.According to the provisions of the Grant, we have been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Rights of Way. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. Note: Expenditures for Rights of Way were erroneously | 67 | Baseline = 100%; $121,209 expended of $180,923 budgeted through third quarter 2011. Total budget (Federal and matching funds) is $180,923.Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in actual construction. In order to avoid future delays we have accelerated some up front activities such as Permitting for upcoming projects. Note: Expenditures for Construction Permits were erroneously charged to the Network Design category for our 4Q2010 report. They are charged to the proper categories for this report. | 0 | Baseline = 17%; $248 expended of $328,833 budgeted through third quarter 2011. Total budget (Federal and matching funds) is $1,995,501. Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Site Preparation. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. | 7 | Baseline = 24%; $381,335 expended of $1,315,100 budgeted through third quarter 2011. Total budget (Federal and matching funds) is $5,598,140. Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Equipment Procurement. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. | 17 | Baseline = 19%; $6,629,020 expended of $7,251,961 budgeted through third quarter 2011. Total budget (Federal and matching funds) is $37,980,932. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 0 | Baseline = 17%; $0 expended of $62,667 budgeted through third quarter 2011. Total budget (Federal and matching funds) is $374,500. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 0 | Baseline = 10%; $0 expended of $37,000 budgeted through third quarter 2011. Total budget (Federal and matching funds) is $374,500. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 2011-11-28 10:31 | 2011-11-28 10:31 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2011 | Q4 | Q4 - 2011 | 5305 | 4976 | TRUE | 28 | Baseline = 30%; $13,677,397 expended of $14,820,608 budgeted through fourth quarter 2011. Total budget (Federal and matching funds) is $48,673,735. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Non-Federal matching funds have been fully utilized in the project. | 42 | Grant Administration | Baseline = 44%; $431,028 expended of $447,908 budgeted through fourth quarter 2011. Total budget (Federal and matching funds) is $1,030,440. Variance is not significant. We expect to catch up to budget during the next quarter. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | Baseline = 100%; $763,012 expended of $596,031 budgeted through fourth quarter 2011. Total budget (Federal and matching funds) is $596,031. | 4 | Baseline =100%; $24,092 expended of $542,768 budgeted through fourth quarter 2011. Total budget (Federal and matching funds) is $542,768.According to the provisions of the Grant, we have been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Rights of Way. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 79 | Baseline = 100%; $143,396 expended of $180,923 budgeted through fourth quarter 2011. Total budget (Federal and matching funds) is $180,923.Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in actual construction. In order to avoid future delays we have accelerated some up front activities such as Permitting for upcoming projects. | 18 | Baseline = 33%; $355,330 expended of $649,167 budgeted through fourth quarter 2011. Total budget (Federal and matching funds) is $1,995,501. Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Site Preparation. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. | 35 | Baseline = 26%; $1,977,085 expended of $1,454,960 budgeted through fourth quarter 2011. Total budget (Federal and matching funds) is $5,598,140. Ahead of budget to date due to faster than anticipated delivery of equipment. | 26 | Baseline = 28%; $9,972,435 expended of $10,795,851 budgeted through fourth quarter 2011. Total budget (Federal and matching funds) is $37,980,932. | 3 | Baseline = 20%; $11,019 expended of $76,500 budgeted through fourth quarter 2011. Total budget (Federal and matching funds) is $374,500. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 0 | Baseline = 20%; $0 expended of $76,500 budgeted through fourth quarter 2011. Total budget (Federal and matching funds) is $374,500. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 2012-02-27 15:55 | 2012-02-28 17:22 | 6712 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2012 | Q1 | Q1 - 2012 | 5987 | 5593 | TRUE | 39 | Baseline = 37%; $18,816,236 expended of $18,146,910 budgeted through first quarter 2012. Total budget (Federal and matching funds) is $48,673,735. Variance between actual percent complete for overall project compared to baseline is not significant. As shown below, for some categories we are under budget, for some over budget. | 47 |  | Baseline = 52%; $484,377 expended of $531,127 budgeted through first quarter 2012. Total budget (Federal and matching funds) is $1,030,440. Variance is not significant. We expect to catch up to budget during the next one or two quarters. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | Baseline = 100%; $938,274 expended of $596,031 budgeted through first quarter 2012. Total budget (Federal and matching funds) is $596,031. An under-budgeting of this item is indicated and an adjustment to transfer funds between categories of the budget is pending. | 4 | Baseline =100%; $24,092 expended of $542,768 budgeted through first quarter 2012. Total budget (Federal and matching funds) is $542,768.According to the provisions of the Grant, we have been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Rights of Way. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. An over- budgeting of this item is indicated and an | 79 | Baseline = 100%; $143,630 expended of $180,923 budgeted through first quarter 2012. Total budget (Federal and matching funds) is $180,923.Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in actual construction. In order to avoid future delays we have accelerated some up front activities such as Permitting for upcoming projects. | 19 | Baseline = 49%; $387,756 expended of $969,500 budgeted through first quarter 2012. Total budget (Federal and matching funds) is $1,995,501. Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Site Preparation. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. | 50 | Baseline = 35%; $2,819,230 expended of $1,979,960 budgeted through first quarter 2012. Total budget (Federal and matching funds) is $5,598,140. Ahead of budget to date due to faster than anticipated delivery of equipment. | 37 | Baseline = 35%; $13,950,246 expended of $13,133,601 budgeted through first quarter 2012. Total budget (Federal and matching funds) is $37,980,932. Variance between actual percent complete compared to baseline is not significant. | 18 | Baseline = 28%; $68,630 expended of $106,500 budgeted through first quarter 2012. Total budget (Federal and matching funds) is $374,500. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 0 | Baseline = 28%; $0 expended of $106,500 budgeted through first quarter 2012. Total budget (Federal and matching funds) is $374,500. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 2012-05-09 15:13 | 2012-05-09 15:13 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2012 | Q2 | Q2 - 2012 | 7191 | 6223 | TRUE | 50 | Baseline = 61%; $24,102,776 expended of $29,486,391 budgeted through second quarter 2012. Total budget (Federal and matching funds) is $48,673,735. Variance between actual percent complete for overall project compared to baseline is due to timing of expenditures. As shown below, for some categories we are under budget, some over. | 53 | Grant Administration | Baseline = 60%; $548,749 expended of $614,346 budgeted through second quarter 2012. Total budget (Federal and matching funds) is $1,030,440. Variance is not significant. We expect to catch up to budget during the next one or two quarters. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | Baseline = 100%; $1,077,667 expended of $596,031 budgeted through second quarter 2012. Total budget (Federal and matching funds) is$596,031. An under-budgeting of this item is indicated and an adjustment to transfer funds between categories of the budget is pending. | 4 | Baseline =100%; $24,092 expended of $542,768 budgeted through second quarter 2012. Total budget (Federal and matching funds) is $542,768. An over- budgeting of this item is indicated and an adjustment to transfer funds between categories of the budget is pending. | 80 | Baseline = 100%; $144,193 expended of $180,923 budgeted through second quarter 2012. Total budget (Federal and matching funds) is $180,923.Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in actual construction. In order to avoid future delays we have accelerated some up front activities such as Permitting for upcoming projects. | 36 | Baseline = 64%; $718,828 expended of $1,283,501 budgeted through second quarter 2012. Total budget (Federal and matching funds) is $1,995,501.Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Site Preparation. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. | 74 | Baseline = 47%; $4,152,719 expended of $2,620,620 budgeted through second quarter 2012. Total budget (Federal and matching funds) is $5,598,140. Ahead of budget to date due to faster than anticipated delivery of equipment. | 45 | Baseline = 62%; $17,222,670 expended of $23,380,202 budgeted through second quarter 2012. Total budget (Federal and matching funds) is $37,980,932. Variance between actual percent complete compared to baseline is due to timing differences. | 57 | Baseline = 36%; $213,858 expended of $134,000 budgeted through second quarter 2012. Total budget (Federal and matching funds) is $374,500. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 0 | Baseline = 36%; $0 expended of $134,000 budgeted through second quarter 2012. Total budget (Federal and matching funds) is $374,500. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 2012-08-21 15:00 | 2012-08-21 15:00 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2012 | Q3 | Q3 - 2012 | 7839 | 6624 | TRUE | 66 | Baseline = 79%; $32,141,191 expended of $38,471,444 budgeted through third quarter 2012. Total budget (Federal and matching funds) is $48,673,735. Variance between actual percent complete for overall project compared to baseline is due to timing of expenditures. As shown below, for some categories we are under budget, some over. | 64 | Grant Administration | Baseline = 68%; $659,869 expended of $697,564 budgeted through thied quarter 2012. Total budget (Federal and matching funds) is $1,030,440. Variance is not significant. We expect to catch up to budget by the end of the Grant period. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | Baseline = 100%; $1,191,823 expended of $596,031 budgeted through third quarter 2012. Total budget (Federal and matching funds) is$596,031. An under-budgeting of this item is indicated and an adjustment to transfer funds between categories of the budget is pending. | 4 | Baseline =100%; $24,092 expended of $542,768 budgeted through third quarter 2012. Total budget (Federal and matching funds) is $542,768. An over- budgeting of this item is indicated and an adjustment to transfer funds between categories of the budget is pending. | 80 | Baseline = 100%; $145,093 expended of $180,923 budgeted through third quarter 2012. Total budget (Federal and matching funds) is $180,923.Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in actual construction. In order to avoid future delays we have accelerated some up front activities such as Permitting for upcoming projects. | 72 | Baseline = 80%; $1,437,752 expended of $1,597,501 budgeted through third quarter 2012. Total budget (Federal and matching funds) is $1,995,501.Due to unanticipated delays in Environmental Assessment process, and our need to concentrate manpower resources in that process, some delays have been experienced in Site Preparation. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. | 100 | Baseline = 61%; $7,120,560 expended of $3,401,620 budgeted through third quarter 2012. Total budget (Federal and matching funds) is $5,598,140. Ahead of budget to date due to faster than anticipated delivery of equipment. In addition, an under-budgeting of this item is indicated and an adjustment to transfer funds between categories of the budget is pending. | 56 | Baseline = 82%; $21,254,188 expended of $30,985,037 budgeted through third quarter 2012. Total budget (Federal and matching funds) is $37,980,932. Variance between actual percent complete compared to baseline is due to timing differences. | 82 | Baseline = 63%; $307,814 expended of $235,000 budgeted through third quarter 2012. Total budget (Federal and matching funds) is $374,500. Ahead of budget to date due to faster than anticipated delivery of equipment. In addition, an under-budgeting of this item is indicated and an adjustment to transfer funds between categories of the budget is pending. | 0 | Baseline = 63%; $0 expended of $235,000 budgeted through second quarter 2012. Total budget (Federal and matching funds) is $374,500. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. | 2012-11-13 10:01 | 2012-11-13 10:01 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2012 | Q4 | Q4 - 2012 | 8767 | 7563 | TRUE | 73 | $35,591,564 expended through fourth quarter 2012. Total budget (Federal and matching funds) is $48,673,735. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 76 | Grant Administration | $778,074 expended through fourth quarter 2012. Total budget (Federal and matching funds) is $1,023,794. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 87 | $1,489,842 expended through fourth quarter 2012. Total budget (Federal and matching funds) is $1,715,332. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 100 | $87,178 expended through fourth quarter 2012. Total budget (Federal and matching funds) is $24,093. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 100 | $148,586 expended through fourth quarter 2012. Total budget (Federal and matching funds) is $148,584. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 85 | $2,293,591 expended through fourth quarter 2012. Total budget (Federal and matching funds) is $2,705,292. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 89 | $7,328,415 expended through fourth quarter 2012. Total budget (Federal and matching funds) is $8,251,234. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 66 | $22,409,207 expended through fourth quarter 2012. Total budget (Federal and matching funds) is $34,019,486. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 100 | $1,056,672 expended through fourth quarter 2012. Total budget (Federal and matching funds) is $785,918. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 0 | Network Testing costs included in Equipment Deployment. | 2013-02-14 09:07 | 2013-02-14 09:07 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2013 | Q1 | Q1 - 2013 | 9613 | 8338 | TRUE | 85 | $41,393,945 expended through first quarter 2013. Total budget (Federal and matching funds) is $48,673,735. Variance to original Baseline is not relevant due to the approval during the fourth quarter 2012 of a revised budget. | 89 | Grant Administration | $910,736 expended through first quarter 2013. Total budget (Federal and matching funds) is $1,023,794. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | $1,715,332 expended through first quarter 2013. Total budget (Federal and matching funds) is $1,715,332. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 100 | $24,093 expended through first quarter 2013. Total budget (Federal and matching funds) is $24,093. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 100 | $148,586 expended through first quarter 2013. Total budget (Federal and matching funds) is $148,586. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 98 | $2,943,065 expended through first quarter 2013. Total budget (Federal and matching funds) is $2,996,442. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 100 | $7,960,084 expended through first quarter 2013. Total budget (Federal and matching funds) is $7,960,084. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 79 | $26,906,131 expended through first quarter 2013. Total budget (Federal and matching funds) is $34,019,486. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 100 | $785,918 expended through first quarter 2013. Total budget (Federal and matching funds) is $785,918. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 0 | Network Testing costs included in Equipment Deployment. | 2013-05-06 16:06 | 2013-05-06 16:06 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2013 | Q2 | Q2 - 2013 | 10581 | 8948 | TRUE | 91 | $44,385,366 expended through second quarter 2013. Total budget (Federal and matching funds) is $48,673,735. Variance to original Baseline is not relevant due to the approval during the fourth quarter 2012 of a revised budget. | 71 | Grant Administration | $728,794 expended through second quarter 2013. Total budget (Federal and matching funds) is $1,023,794. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 89 | $1,525,332 expended through second quarter 2013. Total budget (Federal and matching funds) is $1,715,332. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 100 | $24,093 expended through second quarter 2013. Total budget (Federal and matching funds) is $24,093. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 100 | $148,586 expended through second quarter 2013. Total budget (Federal and matching funds) is $148,586. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 76 | $2,286,269 expended through second quarter 2013. Total budget (Federal and matching funds) is $2,996,442. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 99 | $7,885,084 expended through second quarter 2013. Total budget (Federal and matching funds) is $7,960,084. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 91 | $31,111,290 expended through second quarter 2013. Total budget (Federal and matching funds) is $34,019,486. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 86 | $675,918 expended through second quarter 2013. Total budget (Federal and matching funds) is $785,918. Variance to original Baseline is not relevant due to the approval during the fourth quarter of a revised budget. | 0 | Network Testing costs included in Equipment Deployment. | 2013-08-14 14:11 | 2013-08-14 14:11 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2013 | Q3 | Q3 - 2013 | 11893 | 10063 | TRUE | 100 | $51,945,538 expended through the end of the Grant. Total budget (Federal and matching funds) is $48,673,735. Variance was funded by additional matching funds. | 100 | Grant Administration | $1,290,178 expended through the end of the Grant. Total budget (Federal and matching funds) is $1,023,794. Variance was funded by additional matching funds. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | $2,382,150 expended through the end of the Grant. Total budget (Federal and matching funds) is $1,715,332. Variance was funded by additional matching funds. | 100 | $31,154 expended through the end of the Grant. Total budget (Federal and matching funds) is $24,093. Variance was funded by additional matching funds. | 100 | $155,417 expended through the end of the Grant. Total budget (Federal and matching funds) is $148,586. Variance was funded by additional matching funds. | 100 | $4,252,590 expended through the end of the Grant. Total budget (Federal and matching funds) is $3,309,658. Variance was funded by additional matching funds. | 100 | $8,631,013 expended through the end of the Grant. Total budget (Federal and matching funds) is $7,960,084. Variance was funded by additional matching funds. | 100 | $33,477,620 expended through the end of the Grant. Total budget (Federal and matching funds) is $34,019,486. Variance was funded by additional matching funds. | 100 | $1,725,415 expended through the end of the Grant. Total budget (Federal and matching funds) is $472,701 . Variance was funded by additional matching funds. | 0 | Network Testing costs included in Equipment Deployment. | 2014-02-26 10:39 | 2014-02-26 10:39 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570135 | 2010 | Q4 | Q4 - 2010 | 1081 | 2118 | TRUE | 0 | .04% is equivalent to the total expenditure of $586,604.00 of both the Federal and Recipient share expenditures. See explanation in section 2k below. | 5 | Administration | Our target was 8% but did not obtain do to timing delays from recruiting and on boarding people during the holiday season. | 40 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-11 14:08 | 2011-02-11 14:08 | 6377 | 6377 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2011 | Q1 | Q1 - 2011 | 1639 | 2541 | TRUE | 1 | The total expenditure of $1,105,572.25 of both the Federal and recipient share expenditures. See explanation in section 2k below. | 16 | Administration | Our target of 19% was not obtained since most of the support staff came onboard over the this reporting quarter due to delays in hiring during the holiday season of the previous quarter. | 100 | N/A | 3 | N/A | 3 | N/A | 0 | Did not meet our 3% this reporting period but many permits are in process. | 0 | Our target of 17% was not met this quarter since we had not yet received the FONSI required for construction. | 0 | Our target of 12% was not met due to delays in the preparation of procurement RFP's, which was necessary to ensure that we follow all Federal Procurement guidelines. We are confident that we are able to cumulatively meet our milestone over the next reporting cycles. | 0 | Our target of 3% was not met this quarter since we had not yet received the FONSI required for construction. | 0 | N/A | 0 | N/A | 2011-04-29 11:04 | 2011-04-29 11:04 | 6377 | 6377 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2011 | Q2 | Q2 - 2011 | 3319 | 3422 | TRUE | 3 | $4,866,522 is being reported. 15% was planned, Please see details below for explanation. | 12 | Administration | Planned was 28%, Delay of the FONSI delayed the need of particular positions at this time (i.e. Inspectors). We anticipate that we wiil obtain our projected goals through the coming quarters as projected in our baseline report. The decrease of reported percentage of Q1 was due to a typo, 16% was reported, however 6% was the actual percentage that should have been reported. | 100 | Completed. | 3 | Planned was 18%. The FONSI came in a month later then expected which delayed our efforts. However a significant amount of engineering is now in process. The decrease in percent complete from Q1 report and Q2 was a rounding error. We rounded up on our Q1 report and rounded down on this report. Reporting rounding standards have been implemented. | 3 | Planned was 18%. The FONSI came in a month later then expected which delayed our efforts. However a significant amount of Right of Way permitting is now in process. The decrease in percent complete from Q1 report and Q2 was a rounding error. We rounded up on our Q1 report and rounded down on this report. Reporting rounding standards have been implemented. | 3 | Planned was 18%. The FONSI came in a month later then expected which delayed out efforts. However a significant amount of environmental, and utility permitting is now in process. | 0 | Planned was 17%. Communication hut procurement is in process and will be awarded next reporting quarter. | 6 | Planned was 16%. Over $1.6M in equipment purchases for network monitoring equipment has been already made. Additional procurement is scheduled for the next reporting quarter. | 1 | Planned was 9%, construction has just begun ramping up. | 0 | Planned was 12%, We anticipate equipment deployment during upcoming quarters. | 0 | Planned was 12%, We anticipate network testing during the upcoming quarters. | 2011-08-26 08:17 | 2011-08-26 08:17 | 6377 | 6377 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2011 | Q3 | Q3 - 2011 | 4005 | 3842 | TRUE | 10 | $16,514,334 is being reported. 27% was planned, Please see details below for explanation. | 23 | Administration | Planned was 38%. As Construction begun ramping up we anticipate that we will obtain our projected goals through the coming quarters. | 100 | Milestone Completed. | 10 | Planned was 34%. A significant amount of engineering is now in process and will catch up in 2012 | 10 | Planned was 34%. Environmental approvals came in a month later than expected which delayed our efforts. However a significant amount of Right of Way permitting is now in process. As the engineering phase of the project is being completed, the number of the permitting submissions and approvals will significantly increase by the next reporting quarter and will catch up in 2012. | 10 | Planned was 34%. Environmental approvals came in a month later than expected which delayed our efforts. However a significant amount of environmental and utility permitting is now in place. As the engineering phase of the project is being completed, the number of the permitting submissions and approvals will significantly be increased by the next reporting quarter and will catch up in 2012 | 0 | Planned was 67%. Communication hut procurement is in process and will be awarded during Q4 2011. | 20 | Planned was 26%. Over $5.7M in equipment purchases have already been made. Additional procurement is scheduled for the next reporting quarter. | 1 | Planned was 22%. Construction will continue ramping up in multiple counties. Contracts have been awarded to 21 construction companies and as work is tasked, construction will increase significantly in 2012. We expect to be in construction in all 24 jurisdictions in 2012. | 6 | Planned was 16%. Network architecture designs are ongoing. We anticipate equipment deployment during upcoming quarters. | 1 | Planned was 16%. We anticipate network testing during the upcoming quarters as the completion of the network architecture is completed. | 2011-11-14 09:54 | 2011-11-14 09:54 | 6377 | 6377 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2011 | Q4 | Q4 - 2011 | 5277 | 4946 | TRUE | 17 | $27,352,153 is being reported, 34% was planned. Please see details below for explanation. | 38 | Administration | Planned was 48% As construction gains momentum during the next reporting quarters, we anticipate that we will obtain our project goals. | 100 | Milestone Completed. | 23 | Planned was 48%. Over 86% of the route is currently in engineering, being permitted or in construction. | 23 | Planned was 48% Over 58% of the route has been submitted to permitting agencies. We have received permits for over 10% of the route mileage so far. As the engineering phase of the project is being completed, the number of permit submissions and approvals will significantly increase through to the next reporting quarter. | 23 | Planned was 48% Over 58% of the route has been submitted to permitting agencies. We have received permits for over 10% of the route mileage so far. As the engineering phase of the project is being completed, the number of permit submissions and approvals will significantly increase through to the next reporting quarter. | 4 | Planned was 67%. The installation schedule will have us ahead of schedule in Q3. Hut orders were completed in December 2012 with the first delivery planned in Q1 and subsequent deliveries in Q2 & final delivery and installation in Q3. | 20 | Planned was 33% Over $7.1M in equipment purchases have already been made. Additional large procurement are currently being solicited, and expected to be awarded in Q1 2012. | 11 | Planned was 28%. Construction will continue ramping up in multiple counties. Contracts have been awarded to 22 construction companies and as work is being tasked, construction is increasing exponentially. Note: last quarter we were at 1% complete. We expect to be in construction in all 24 counties by June 2012. | 10 | Planned was 26%. Network architecture designs are ongoing, equipment deployment and procurement will maintain pace with the network build. | 2 | Planned was 26%. We anticipate network testing during the upcoming quarters as the completion of the network build occurs. | 2012-02-27 10:12 | 2012-02-27 10:12 | 6377 | 6377 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2012 | Q1 | Q1 - 2012 | 6299 | 5752 | TRUE | 26 | $41,858,283 is being reported, 39% was planned. Please see details below for explanation. | 38 | Administration | Planned was 56%. As construction gains momentum during the next reporting quarters, we anticipate that we will obtain our project goals. | 100 | Milestone Completed. | 34 | Planned was 56%. Over 97% of the route is currently in engineering, being permitted or in construction and network logical design is well under way. | 44 | Planned was 56% Over 78% of the route has been submitted to permitting agencies. We have received permits for over 44% of the route mileage so far. As the engineering phase of the project is being completed, the number of permit submissions and approvals will significantly increase through to the next reporting quarter. | 44 | Planned was 56% Over 78% of the route has been submitted to permitting agencies. We have received permits for over 44% of the route mileage so far. As the engineering phase of the project is being completed, the number of permit submissions and approvals will significantly increase through to the next reporting quarter. | 10 | Planned was 70%. Hut orders were completed in December 2011 with its first delivery made in Q1 and subsequent deliveries in Q2 & final delivery and installation in Q3. | 14 | Planned was 38%. Over $4.2M in equipment purchases have already been made. Additionally, $10M of equipment procurements are currently in process (for Q2 2012). Note: in Q4 2011, the program reported 20% complete. Some expenses were reclassified in Q1 2012 resulting in drop in % Complete for Equipment. The expected equipment expenditures are now expected in Q2 2012 and should return the % Complete back to 20%. | 27 | Planned was 32%. Construction is currently occurring in 18 counties. Contracts have been awarded for the remaining 5 counties as work is being tasked, construction is increasing exponentially. Note: last quarter we were at 11% complete. We expect to be in construction in all 24 counties by June 2012. | 11 | Planned was 33%. Network architecture designs are ongoing, equipment deployment and procurement will maintain pace with the network build. | 5 | Planned was 56%. We anticipate network testing during the upcoming quarters as the completion of the network build occurs. Note: last quarter we were at 2% complete. | 2012-05-25 11:48 | 2012-05-25 11:48 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2012 | Q2 | Q2 - 2012 | 7163 | 6209 | TRUE | 45 | $70,859,891 is being reported, 51% was planned. Please see details below for explanation. | 42 | Administration | Planned was 64%. As construction gains traction during the next reporting quarters, we anticipate that we will obtain our project goals. | 100 | Milestone Completed. | 56 | Planned was 70%. Over 98% of the route total has been fully engineered, and is being permitted or in construction. Network logical designs are being completed in conjunction with construction. | 69 | Planned was 70%. Over 89% of the route has been submitted to the permitting agencies. Now that engineering phase of the project is coming to a close the number of permits received will continue to increase through the next quarter. | 69 | Planned was 70%. Over 89% of the route has been submitted to the permitting agencies and permits received for 69% of the route. Now that engineering phase of the project is coming to a close the number of permits received will continue to increase through the next quarter. | 33 | Planned was 81%. All 14 Huts were ordered in December 2011. The first 4 Huts were delivered in Q1. All 4 Huts were installed in Q2 ,with subsequent deliveries and installation of the Huts in Q3 and Q4. Final installation of all Huts are scheduled to be completed in Q1 2013. | 14 | Planned was 49%. A total of $4,678,794 is reported as spent for equipment during 2012 Q2. Orders were placed in Q2 for a total of $7,948,791.43 in network electronics that we expect will be invoiced and included in Q3 reporting. | 54 | Planned was 44%. Currently construction is occurring in all 24 Jurisdictions. | 13 | Planned was 38%. Equipment deployment and procurement is maintaining pace with the network build out. | 6 | Planned was 38%. As buildout of the network occurs, network testing will follow equipment deployment. | 2012-08-20 13:01 | 2012-08-20 13:01 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2012 | Q3 | Q3 - 2012 | 7969 | 6691 | TRUE | 61 | $95,968,567.00 is being reported, 67% was planned. Please see details below for explanation. | 47 | Administration | Planned was 72%. We continue to find efficiencies in our program management allowing us to contain overhead cost. | 100 | Milestone Completed. | 71 | Planned was 82%. Over 99% of the route total has been fully engineered, and is being permitted or in construction. Network logical designs are being completed in conjunction with construction. | 77 | Planned was 82%. Over 97% of the route has been submitted to the permitting agencies. Now that engineering phase of the project is coming to a close the number of permits received will continue to increase through the next quarter. | 77 | Planned was 82%. Over 97% of the route has been submitted to the permitting agencies and permits received for 77% of the route. Now that engineering phase of the project is coming to a close the number of permits received will continue to increase through the next quarter. | 55 | Planned was 81%. All 14 Huts were ordered in December 2011. The first 4 Huts were delivered in Q1. The 4 Huts were installed in Q2 ,with subsequent deliveries and installation of the Huts in Q3 and Q4. Final installation of all Huts are scheduled to be completed in Q1 2013. | 28 | Planned was 61%. A total of $8,136,853 is reported as spent for equipment. We anticipate this figure to increase significantly during our Q1 2013 reporting period. | 54 | Planned was 64%. Currently construction is occurring in 22 Jurisdictions. Two Jurisdictions have been completed. | 16 | Planned was 49%. Equipment deployment and procurement is maintaining pace with the network build out. | 13 | Planned was 49%. As buildout of the network occurs, network testing will follow equipment deployment. | 2012-11-20 10:51 | 2012-11-20 10:51 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2012 | Q4 | Q4 - 2012 | 9143 | 7958 | TRUE | 73 | $115,310,820.00 is being reported, 74% was planned. Please see details below for explanation. | 52 | Administration | Planned was 81%. We continue to find efficiencies in our program management allowing us to contain overhead cost. | 100 | Milestone Completed. | 79 | Planned was 91%. 100% of the route total has been fully engineered, and is being permitted or in construction. Network logical designs are being completed in conjunction with construction. | 87 | Planned was 91%. 100% of the route has been submitted to the permitting agencies. Now that engineering phase of the project has come to a close, we expect all permits will be received next quarter. | 87 | Planned was 91%. 100% of the route has been submitted to the permitting agencies. Now that engineering phase of the project has come to a close, we expect all permits will be received next quarter. | 77 | Planned was 81%. Of the 14 Huts that were ordered in December 2011, 10 have been successfully installed on their sites as of the end of 4Q 2012. Three Huts that were scheduled for 4Q 2012 are now to be installed during Q1 2013. In all three cases, easement delays caused the Hut installation schedule to slip into the first quarter. | 34 | Planned was 70%. A total of $9,968,741 is reported as spent for equipment. We anticipate this figure to increase significantly during our Q2 2013 reporting period. | 73 | Planned was 70%. Currently construction is occurring in 20 Jurisdictions. Four Jurisdictions have been completed. | 28 | Planned was 70%. A significant amount of equipment has been received in our warehouses but not yet deployed. We expect significant deployment in the next quarter. | 29 | Planned was 61%. As buildout of the network occurs, network testing will follow equipment deployment. | 2013-03-22 13:49 | 2013-03-22 13:49 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2013 | Q1 | Q1 - 2013 | 9973 | 8531 | TRUE | 83 | $132,222,532.06 is being reported, 79% was planned. Please see details below for explanation. | 54 | Administration | Planned was 90%. We continue to find efficiencies in our program management allowing us to contain overhead cost. | 100 | Milestone Completed. | 88 | Planned was 95%. Network logical designs are being completed in conjunction with construction. | 94 | Planned was 95%. Now that engineering phase of the project has come to a close, we expect all permits will be received next quarter. | 94 | Planned was 95%. Now that engineering phase of the project has come to a close, we expect all permits will be received next quarter. | 83 | Planned was 87%. Of the 14 Huts that were ordered in December 2011, 12 have been successfully installed on their sites as of the end of 1Q 2013. Of the two Huts that were scheduled for 1Q 2013, 1 was completed and the second/ final Hut is schedule to be installed in Q2 2013. | 76 | Planned was 77%. | 84 | Planned was 74%. Six Jurisdictions have been completed. Currently construction is occurring in the remaining 18 Jurisdictions. | 54 | Planned was 70%. A significant amount of equipment has been received in our warehouses and has been deployed. We expect significant deployment in the next quarter. | 65 | Planned was 70%. Significant resources are now deployed on both fiber and network testing. As the next quarter progresses we will will substantial progress in network testing. | 2013-05-29 16:10 | 2013-05-29 16:10 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2013 | Q2 | Q2 - 2013 | 10701 | 9013 | TRUE | 92 | $145,047,472 is being reported, Please see details below for explanation. | 94 | Administration | We are on target with this milestone. | 100 | Milestone Completed. | 95 | Network logical designs are being completed in conjunction with construction. | 99 | We expect all permits will be received next quarter. | 99 | We expect all permits will be received next quarter. | 100 | Milestone Completed. | 100 | Milestone Completed. | 97 | Five Jurisdictions have been completed. Construction is at its final stage in the remaining 19 Jurisdictions. | 76 | We expect final deployments of the remaining equipment during the next quarter. In the next quarter we will complete Equipment Deployment. | 88 | Significant resources are now deployed on both fiber and network testing. In the next quarter we will complete Network Testing. | 2013-08-22 17:36 | 2013-08-22 17:36 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2013 | Q3 | Q3 - 2013 | 11627 | 9748 | TRUE | 100 | Only activities remaining are close out processes | 100 | Administration | Only activities remaining are close out processes | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 2014-01-20 14:05 | 2014-01-20 14:05 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570136 | 2010 | Q4 | Q4 - 2010 | 1121 | 2161 | TRUE | 1 | n/a | 0 | In-kind IRU Leases | IRU Leases in final legal review; expected complete in Jan 2011. | 50 | Slight variance due to early snowfall and node engineering timing. | 40 | Route changes are being considered; working on node engineering | 24 | n/a | 0 | n/a | 0 | n/a | 0 | Nothing has been purchased; pre-FONSI budget not yet approved. | 0 | n/a | 0 | n/a | 0 | n/a | 2011-02-12 11:32 | 2011-02-12 11:32 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2011 | Q1 | Q1 - 2011 | 1497 | 2462 | TRUE | 10 | No variance from baseline plan. | 16 | in-kind IRU leases | No variance from baseline plan. | 92 | Slightly behind baseline plan. Submitted Draft EA 2/23/2011; revisions and final consultations in progress | 80 | No variance from baseline plan. Completing node engineering, working to finalize the engineering on the backbone. | 30 | Slightly behind baseline plan. Running into difficulties obtaining rights-of-way on BLM and Forest Service lands. | 0 | Slightly behind baseline plan due to to delay of FONSI issuance. | 1 | Slightly ahead of baseline projections. One RFI was released for site surveys and staking out the towers. | 0 | Slightly behind baseline plan. Numerous RFPs are scheduled to be released in early Q2 2011. | 0 | No variance from baseline plan. | 0 | No variance from baseline plan. | 0 | No variance from baseline plan. | 2011-04-26 19:21 | 2011-04-26 19:21 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2011 | Q2 | Q2 - 2011 | 3291 | 3408 | TRUE | 10 | Behind baseline plan due to lack of EA approval, which restricts construction. Submitted two SF-270s in during this reporting period. | 22 | 203 leases | Slightly behind of baseline projections. We made continued progress toward obtaining 203 in-kind leases. | 78 | Behind baseline plan. Submitted Draft EA 2/28/2011, additional requested items and revisions in progress. | 38 | Actual network design is almost complete; behind baseline plan expenditures for finalizing FCC licensing which starts a construction clock. | 22 | Slightly behind baseline plan, due to progress delays in securing federal land leases and annual lease expenses not yet due. | 0 | Slightly behind baseline as directly related to construction timing. | 0 | Behind baseline projections. Surveys are in progress. Construction timeline is behind schedule due to delays with EA/FONSI. | 1 | Behind baseline projections as no delivery yet. Microwave antennas and cable and associated hardware has begun purchase order process. Will begin purchase process of towers and monopoles next quarter. | 17 | Ahead of baseline projections for such expenditures, as network hub sites are being obtained/leased. | 0 | Behind baseline projections. No construction allowed. | 1 | Behind baseline. Some network testing has occurred as part of the equipment procurement process. | 2011-08-24 12:10 | 2011-08-24 12:10 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2011 | Q3 | Q3 - 2011 | 3897 | 3787 | TRUE | 29 | Slightly behind baseline plan due to delay in EA approval. GovNET expects to be back in sync with its Baseline Plan by the end of Y2 Q4. Three SF-270s were submitted during this reporting period. | 50 | 203 leases | Ahead of baseline plan. We made continued progress toward obtaining 203 in-kind leases. | 97 | Slightly behind baseline plan. Awaiting FONSI decision. GovNET will be back in sync with its Baseline Plan for this milestone by next quarter. | 51 | Slightly behind baseline plan. The actual network design is almost complete; waiting on construction to file licenses. Expect to be back in sync with its Baseline Plan by the end of Y2 Q4. | 61 | On track with baseline plan. | 21 | Slightly behind baseline plan due to delay in EA approval. GovNET expects to be back in sync with its Baseline Plan by the end of Y2 Q4. | 1 | Behind baseline plan due to delay in EA approval, which restricts construction. We expect to be back in sync with its Baseline Plan by the end of Y2 Q4. | 7 | Behind baseline plan due to delay in EA approval, which restricts equipment purchases. During next two quarters, significant equipment purchases will be made. | 25 | Ahead of baseline plan due to progress on obtaining leases, rights of way, etc. | 1 | Behind baseline plan due to delay in EA approval, which restricts construction and deployment. In 2012, multiple tower construction crews will have to be utilized to make up for lost time. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 5 | Behind baseline plan due to delay in EA approval, which restricts building and testing. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 2011-11-04 15:52 | 2011-11-04 15:52 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2011 | Q4 | Q4 - 2011 | 4903 | 4590 | TRUE | 33 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be in sync with its Baseline Plan by the end of Q3 2012. Three SF-270s were submitted during this reporting period. | 62 | 203 in-kind IRU leases | No variance from Baseline Plan. GovNET made continued progress toward obtaining 203 in-kind leases. | 73 | GovNET completed its EA and received its FONSI during this reporting period. Additional funding remains in this category to cover any future EA amendments. | 52 | Behind baseline plan due to delay in EA approval, which restricted construction. FCC licenses will be filed as site construction is eminent. | 62 | Behind baseline plan due to delay in school board/board of supervisors approval. | 4 | Behind baseline plan due to delay in EA approval, which restricted construction. | 2 | Behind baseline plan due to delay in EA approval, which restricted construction. | 13 | Behind baseline plan due to delay in EA approval, which restricts construction. GovNET received its FONSI during this reporting period and expects to make significant purchases in the next quarter. | 47 | Slightly ahead of Baseline Plan. We have a significant number of leases secured and equipment purchased. | 2 | Behind baseline plan due to delay in EA approval, which restricts construction. In 2012, multiple tower construction crews will be utilized to make up for lost time. | 10 | Behind baseline plan due to delay in EA approval, which restricted construction. | 2012-02-07 13:06 | 2012-02-07 13:06 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2012 | Q1 | Q1 - 2012 | 6045 | 5622 | TRUE | 32 | Behind baseline plan projections due to delay in EA approval, which restricted construction. GovNET expects to be in sync with its Baseline Plan by the end of Q3 2012. Three SF-270s were submitted during this reporting period. (Note: The percent complete is a decrease from last quarter. The match value decreased due to an appraisal error. As a result, the percent completion was also decreased.) | 46 | 203 in-kind IRU leases | Behind baseline plan projections. GovNET has made significant progress toward securing 203 in-kind leases. (Note: The percent complete is a decrease from last quarter. The match value decreased due to an appraisal error. As a result, the percent completion was also decreased.) | 84 | GovNET received its FONSI in Q4 2011. Additional funding remains in this category to cover any future EA amendments. | 73 | Behind baseline plan due to delay in EA approval, which restricted construction. FCC licenses will be filed as site construction is imminent. | 55 | All in process, but behind baseline plan due to delay in federal agency, library, school board/board of supervisors approvals. (Note: The percent complete is a decrease from last quarter. The match value decreased due to an appraisal error. As a result, the percent completion was also decreased.) | 10 | Behind baseline plan due to delay in EA approval, which restricted construction and is tied to construction spending. GovNET expects to be in sync with its Baseline Plan by the end of Q3 2012. | 10 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET expects to be in sync with its Baseline Plan by the end of Q3 2012. | 23 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET expects to be in sync with its Baseline Plan by the end of Q3 2012. RFPs are done and equipment is ordered as needed. | 38 | Behind Baseline Plan projections. GovNET has secured a significant number of leases, and has made significant equipment purchases. (Note: The percent complete is a decrease from last quarter. The match value decreased due to an appraisal error. As a result, the percent completion was also decreased.) | 6 | Behind baseline plan due to delay in EA approval, which restricts construction. In 2012, multiple tower construction crews will be utilized to make up for lost time. GovNET expects to be in sync with its Baseline Plan by the end of Q3 2012. (Note: The percent complete is a decrease from last quarter. The match value decreased due to an appraisal error. As a result, the percent completion was also decreased.) | 17 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET expects to be in sync with its Baseline Plan by the end of Q3 2012. | 2012-05-11 16:30 | 2012-05-11 16:30 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2012 | Q2 | Q2 - 2012 | 7261 | 6258 | TRUE | 34 | Behind baseline plan projections due to delay of FONSI in Q4 2011 restricting construction, suspension of the project by NTIA in June 2012, and delayed reimbursements reduces expenditure timing for reports. Only one SF-270 was accepted by NTIA during this reporting period. | 46 | 203 in-kind IRU leases | Behind baseline plan projections due to delay in EA approval, which restricted construction, a suspension of the project by NTIA in June 2012. Requesting BTOP Programmatic/EHP approval to 'swap' exempt CAIs (rooftop mounts) in project to ones who have already signed leases, making this close to 100% complete. | 86 | GovNET received its FONSI in Q4 2011. Additional funding remains in this category to cover future EA amendments and/or unforeseen administration costs. | 79 | Slightly behind baseline plan projections due to review of the project by NTIA in Summer 2012. FCC licenses are held in Prior Coordination Notice (PCN) and will be filed as site construction is imminent. | 64 | Remainder of sites in final approval process, but behind baseline plan due to delay in some federal approvals and NTIA review of project. | 25 | Behind baseline plan due to delay in FONSI approval, which restricted construction. Many sites are exempt due to federal land ownership. FCC licenses are held in PCN and filed as site construction is imminent. | 40 | In a wireless network deployment, this milestone precedes site construction and includes site surveys and geo-tech work - which has been completed for almost all new tower sites in the network. Minimal prep activity is required for collocations. | 32 | Significant procurement was in process this quarter in anticipation of continued construction, but not yet reimbursement by BTOP. Majority of RFPs are done and equipment is batch ordered via outstanding purchase orders. | 25 | Behind Baseline Plan projections, and % complete revised to more accurately reflect status for quarter, but still on target for full network completion. GovNET built 10 Backbone sites within 4 months, a significant accomplishment prior to stoppage. | 10 | Significant equipment was ordered and is in warehouse, awaiting deployment. Behind baseline plan projections due to restricted construction time, and a suspension of the project by NTIA June 2012. | 17 | Behind baseline plan projections due to delay in EA approval, which restricted construction, a suspension of the project by NTIA in June 2012. Extensive testing occurs in the labs prior, during construction, and as physical network is turned up. | 2012-08-28 14:53 | 2012-08-28 14:53 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2012 | Q3 | Q3 - 2012 | 8015 | 6714 | TRUE | 39 | Behind baseline plan projections due to less than 6 months of actual construction time from delay in issue of FONSI in November 2011 and suspension of the project by NTIA in May 2012 stopping all work. Only one partial reimbursement request for small vendors was authorized by the NTIA in this quarter. | 46 | 203 in-kind Leases | Behind baseline plan projections due to delay in FONSI approval, which restricted construction, and suspension of the project by NTIA. Still awaiting BTOP Programmatic/EHP approval to 'swap' exempt CAIs (rooftop mounts) in project to ones who have already signed leases, making this close to 100% complete. | 87 | GovNET received its FONSI in Q4 2011. Additional funding remains in this category to cover future EA amendments and administration costs. | 82 | Slightly behind baseline plan projections due to project suspension by NTIA. FCC licenses are held in Prior Coordination Notice (PCN) and will be filed as site construction is imminent. | 64 | Remainder of sites in final approval process, but behind baseline plan due to delay in some federal approvals and NTIA stop work order. | 25 | Behind baseline plan due to delay in FONSI approval, which restricted construction. Many sites are permit exempt due to federal land ownership. FCC licenses filed as site construction is imminent. | 40 | In a wireless network deployment, this milestone precedes site construction and includes site surveys and geo-tech work - which has been completed for almost all new tower sites in the network. Minimal prep activity is required for collocations. | 32 | Significant equipment ordering/procurement was done in March/April/May in anticipation of continued construction. Vendors not yet reimbursement by NTIA, so the % Complete based on spending is lower until reimbursed. Majority of RFPs are done and equipment is batch ordered via outstanding purchase orders. | 25 | Behind Baseline Plan projections, and % Complete revised to more accurately reflect status, but still on target for full network completion. GovNET built 10 Backbone sites within 4 months, a significant accomplishment prior to stoppage. | 10 | Significant equipment was ordered and is in warehouse, awaiting deployment. Behind baseline plan projections due to restricted construction time, and a suspension of the project by NTIA. | 17 | Behind baseline plan projections due to delay in FONSI approval, which restricted construction, and project suspension by NTIA. Extensive testing occurs in the labs prior, during construction, and as physical network is turned up. | 2012-11-21 11:14 | 2012-11-21 11:14 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2012 | Q4 | Q4 - 2012 | 8821 | 7609 | TRUE | 43 | Increase due to outstanding vendor invoices that were processed by NTIA and allowed to be paid. | 46 | In-kind Leases | No change due to no project work allowed. | 87 | GovNET received its FONSI in Q4 2011. Additional funding remains in this category to cover future EA amendments and administration costs. | 82 | No change due to no project work allowed. | 64 | No change due to no project work allowed. | 25 | No change due to no project work allowed. | 40 | No change due to no project work allowed. | 39 | Increase due to payment of outstanding vendor invoices | 25 | No change due to no project work allowed. | 10 | No change due to no project work allowed. | 17 | No change due to no project work allowed. | 2013-02-15 16:31 | 2013-02-15 16:31 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2013 | Q1 | Q1 - 2013 | 9783 | 8426 | TRUE | 44 | Slight increase due to outstanding vendor invoices that were processed by NTIA and allowed to be paid. | 46 |  | No change due to no project work allowed. | 87 | GovNET received its FONSI in Q4 2011. Additional funding remains in this category to cover future EA amendments and administration costs. | 82 | No change due to no project work allowed. | 64 | No change due to no project work allowed. | 25 | No change due to no project work allowed. | 40 | No change due to no project work allowed. | 40 | Slight increase due to outstanding vendor invoice paid. | 25 | No change due to no project work allowed. | 10 | No change due to no project work allowed. | 17 | No change due to no project work allowed. | 2013-05-16 19:49 | 2013-05-16 19:49 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2013 | Q2 | Q2 - 2013 | 10705 | 9015 | TRUE | 47 | Slight increase due to outstanding vendor invoices that were processed by NTIA. | 46 |  | No change due to no project work allowed. | 87 | GovNET received its FONSI in Q4 2011. Additional funding remains in this category to cover future EA amendments and administration costs. | 82 | No change due to no project work allowed. | 64 | No change due to no project work allowed. | 25 | No change due to no project work allowed. | 40 | No change due to no project work allowed. | 46 | Slight increase due to outstanding vendor invoices paid. | 25 | No change due to no project work allowed. | 10 | No change due to no project work allowed. | 17 | No change due to no project work allowed. | 2013-08-22 19:18 | 2013-08-22 19:18 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2013 | Q3 | Q3 - 2013 | 11267 | 9425 | TRUE | 53 | Slight increase due to construction activity and vendor invoices that were processed by NTIA. | 60 | CAI leases | Increase in approved CAI leases due to NTIA approval of Batch 4. | 89 | GovNET received its FONSI in Q4 2011. Additional funding remains in this category to cover future EA amendments and administration costs | 82 | FCC licensing will be held until site construction is imminent. | 65 | Slight increase to resumed activity. | 26 | Slight increase to resumed activity. | 41 | Slight increase to resumed activity. | 47 | Slight increase to resumed activity. | 26 | Slight increase to resumed activity. | 11 | Slight increase to resumed activity. | 17 | Slight increase to resumed activity. | 2013-11-15 13:22 | 2013-11-15 13:22 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2013 | Q4 | Q4 - 2013 | 11817 | 9995 | TRUE | 56 | Increased due to pre-construction activity, planning efforts, and vendor invoices that were reimbursed by NTIA. | 62 |  | Additional in-kind backbone leases received. | 90 | GovNET received its FONSI in Q4 2011. Additional funding remains in this category to cover future EA amendments and administration costs | 82 | FCC licensing will be held until site construction is imminent | 67 | Slight increase to resumed activity | 26 | Slight increase to resumed activity | 42 | Slight increase to resumed activity | 47 | Slight increase to resumed activity | 27 | Slight increase to resumed activity | 11 | Slight increase to resumed activity | 17 | Slight increase to resumed activity | 2014-02-13 23:16 | 2014-02-13 23:16 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570138 | 2010 | Q4 | Q4 - 2010 | 707 | 1744 | TRUE | 2 | no variance from baseline | 50 | (Power Pole Make Ready) | no variance from baseline | 75 | no variance from baseline | 70 | no variance from baseline | 20 | no variance from baseline | 10 | no variance from baseline | 0 | no variance from baseline | 0 | no variance from baseline | 0 | construction has not begun as FONSI not yet received | 0 | no variance from baseline | 0 | no variance from baseline | 2011-01-28 11:57 | 2011-01-28 11:57 | 6339 | 6339 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2011 | Q1 | Q1 - 2011 | 1847 | 2667 | TRUE | 5 | no variance to baseline | 50 |  | 50% variance for Pole Make Ready for Hill Country Telephone. This variance will be eliminated during Q2 2011 upon the issuance of the FONSI. | 90 | We are completing our response to questions on the Draft EA. | 80 | No variance to baseline | 70 | No variance to baseline | 20 | No variance to baseline | 3 | No variance to baseline | 3 | No variance to baseline | 0 | 15% variance to baseline, due to FONSI not being issued. We expect to catch up to baseline projections by the end of Q2 2011 (BTOP Q4 Year 1). | 0 | 1% variance to baseline. This variance will be eliminated during Q2 2011 upon the issuance of the FONSI. | 0 | No variance | 2011-05-02 14:35 | 2011-05-02 14:35 | 6339 | 6339 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2011 | Q2 | Q2 - 2011 | 3073 | 3294 | TRUE | 7 | No variance, Region 18 ESC is tracking % complete based upon actual project completion. We are not tracking our progress based upon $ spent to date. | 50 | Power Pole Make Ready | -50% variance to baseline(Other refers to Pole Make Ready to be performed by Hill Country Telephone). | 100 | No variance, FONSI issued June 2011 | 90 | No variance | 100 | No variance | 10 | Construction permits are only valid for 60 days from grant date. They will be acquired as needed through the construction process. We had Previously reported 20% completion on this task. Due to the fact that construction will not begin until September, permits will not be acquired until August 2011. Permits are only valid for 60 days and as such the previous number reported was incorrect. | 3 | -9% variance to baseline. Delayed due to delay of FONSI | 6 | No variance | 0 | -22% variance to baseline | 0 | -4% variance to baseline | 0 | -5% variance to baseline | 2011-08-15 10:27 | 2011-08-15 10:27 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2011 | Q3 | Q3 - 2011 | 4045 | 3863 | TRUE | 18 | -12% variance to baseline. This is calculated based upon total program $ spent to date. The variance is due to the delay in the start of construction. We anticipate closing this gap over the next two quarters. | 50 |  | -50% variance refers to Pole Make Ready to be performed by Hill Country Telephone | 100 | No variance | 100 | No variance | 100 | No variance | 40 | -35% variance, this is due to the fact that permits are only valid for 60 days and as such must be acquired closer to the start of construction for a given route. | 70 | No variance | 14 | Fiber and equipment have been allocated and purchased in preparation of the start of construction. Still waiting for some delivery and invoicing. | 0 | -35% from baseline. Construction will begin October 1st. Plans in place to complete 2/3 of project by end of year 2 and on track to complete entire project within the three year schedule. | 6 | No variance | 0 | -11% variance from baseline. Construction has not begun by September 30. | 2011-11-15 10:45 | 2011-11-15 10:45 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2011 | Q4 | Q4 - 2011 | 5241 | 4903 | TRUE | 25 | -15% variance to baseline, this is calculated based upon the program $ spent to date. We will continue to narrow this gap in Q1 2012 and expect to be on track with the baseline by the end of the 2nd quarter 2012. The variance is due to our delay in starting construction due to the Environmental Assessment process. | 100 | HCTC Pole Make Ready | No variance | 100 | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 50 | -40 % variance to baseline. Permits are only valid for 60 days. These are being acquired as needed. | 70 | -20 % variance to baseline. Site preparation is on track with regards to construction. We expect to close the variance to baseline by the end of Q3 2012. | 80 | No variance to baseline | 7 | -73% variance to baseline, baseline number was off and the delay in the start of construction has contributed to the variance. We anticipate a rapid reduction in the variance as the project progresses. | 45 | No variance to baseline | 3 | -61.2% variance to baseline, we are working to close this gap and anticipate meeting baseline expectations by the end of Q3 2012. | 2012-02-24 10:32 | 2012-02-24 10:32 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2012 | Q1 | Q1 - 2012 | 6277 | 5741 | TRUE | 43 | -12% variance to baseline. This is calculated based upon the program dollars spent to date. We expect to be on track to baseline by the end of Q2 2012. The variance is due to the delay in starting construction due to the environmental assessment. | 100 | HCTC Pole make ready | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 70 | -30% variance to baseline. Permits are only valid for 60 days. They are being acquired as needed. | 80 | -10 % variance to baseline. Site preparation is on track with regards to construction. We expect to close the variance to baseline by the end of Q3 2012. | 90 | No variance to baseline | 20 | We currently have 5% of CAI's connected and 31% of fiber and aeriel miles completed. This is a -38% variance to baseline. We expect to greatly narrow this gap in Q2 and hope to eliminate the gap by the end of Q3 2012. Dell City expects to connect at least 13 CAI's in Q2 2012 as well as an additional 25 miles of fiber. Poka Lambro and WesTex have completed all construction and connections. Big Bend is progressing as is Hill Country Telephone. | 55 | No variance to baseline | 5 | -60% variance to baseline. We are working to close this gap and anticipate meeting baseline expectations by the end of Q3 2012 | 2012-05-24 10:14 | 2012-05-24 10:14 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2012 | Q2 | Q2 - 2012 | 7095 | 6175 | TRUE | 71 | +4% ahead of baseline. This is calculated based upon the program dollars spent to date. | 100 | HCTC Pole Make Ready | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 80 | -20% variance to baseline. Permits are only valid for 60 days and are being acquired as needed. | 90 | -10% variance to baseline. Site preparation is on track with regards to construction. We expect to close the variance to the baseline by the end of Q3 2012. | 90 | No variance to baseline | 40 | -30% to baseline. As shown above 71% of program $ have been spent and 59.3% of program miles have been constructed. 50% of our interconnection (peering points) have been completed and 6.49% of our CAI's are connected. We anticipate completely closing the gap to baseline in Q3 2012. | 70 | No variance to baseline | 7 | -61% variance to baseline. Actual fiber construction is moving ahead of plan. Final splicing and CAI connections are progressing now with many taking place in Q3 of 2012. Once the CAI's are connected network testing can and will be completed. | 2012-08-15 17:09 | 2012-08-15 17:09 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2012 | Q3 | Q3 - 2012 | 7855 | 6632 | TRUE | 86 | +14% ahead of baseline. This is calculated based upon the program dollars spent to date. | 100 | HCTC Pole Make Ready | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 90 | -10 % variance to baseline. Construction permits are only valid for 60 days. Big Bend is further than 60 days from completing construction. | 95 | -5% to baseline. Big Bend still under construction. | 90 | -10% to baseline. Equipment for two towers constructed by Big Bend still to be purchased. | 60 | -15% to baseline. As shown above 86% of program $ have been spent. 80% of fiber miles have been constructed. | 81 | No variance to baseline | 8 | -62% to baseline. Fiber construction is ahead of schedule. We are working to connect and turn up additional CAI locations. As they are receiving service we will perform network testing. At this point 12 CAI locations have been turned up with service. | 2012-11-13 23:06 | 2012-11-13 23:06 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2012 | Q4 | Q4 - 2012 | 8999 | 7777 | TRUE | 86 | 11% ahead of baseline. This is calculated based upon program dollars spent to date. | 100 | HCTC Pole Make Ready | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 90 | -10% to baseline. Due to Big Bend route changes construction had to be halted. As such permits will expire and need to be obtained again. | 95 | -5% to baseline. Big Bend is still under construction. Two routes have not been completed. | 90 | -10% to baseline. Big Bend still to purchase equipment for two towers. Cannot be purchased during the open route change requests. | 85 | No variance to baseline. 82.7% of program miles have been constructed and 85.7% of program $ have been spent. | 90 | No variance to baseline | 35 | -45% to baseline. CAI's still being connected. Fiber is installed but service connections are ongoing. | 2013-02-27 10:56 | 2013-02-27 10:56 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2013 | Q1 | Q1 - 2013 | 9965 | 8527 | TRUE | 90 | -5% to baseline. This is based upon program dollars spent to date. | 100 | HCTC Pole Make Ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 95 | -5% to baseline. Big Bend will obtain final permits this quarter. | 95 | -5% to baseline. Due to route change requests construction was halted. We are currently working again and plan to bridge the gap this quarter. | 90 | -10% to baseline. Final equipment procurement delayed due to route change requests. Plan to bridge the gap this quarter. | 90 | -5% to baseline. Delay due to route change requests. Plan to bridge the gap in this quarter. | 90 | -10% to baseline. Delay due to route change requests. Plan to bridge the gap this quarter. | 50 | -45% to baseline. Ongoing plan to bridge the gap this quarter. | 2013-05-29 14:34 | 2013-05-29 14:34 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2013 | Q2 | Q2 - 2013 | 10631 | 8976 | TRUE | 90 | -10% variance to baseline | 100 | HCTC Pole make ready | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 100 | No variance to baseline | 90 | -10% variance to baseline | 100 | No variance to baseline | 90 | -10% variance to baseline | 2013-08-19 08:47 | 2013-08-19 08:47 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2013 | Q3 | Q3 - 2013 | 11363 | 9487 | TRUE | 94 | -6% to baseline due to extension for final route. | 100 | HCTC Pole Makeready | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 97 | -3% to baseline due to extension for final route | 100 | no variance | 97 | -3% to baseline due to extension for final route | 2013-11-22 23:16 | 2013-11-22 23:16 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2013 | Q4 | Q4 - 2013 | 12211 | 10384 | TRUE | 100 | No variance | 100 | HCTC Pole Make Ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2014-05-19 15:27 | 2014-05-19 15:27 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570139 | 2010 | Q4 | Q4 - 2010 | 1247 | 2278 | TRUE | 6 | Overall Project percent complete is in line with Baseline plan | 0 |  | N/A | 100 | No variance (completed) | 70 | No variance | 25 | No variance | 15 | No variance (application licenses on plan) | 5 | No variance (make-ready on plan) | 5 | No variance (all major procurements complete, equipment ordered contemporaneously with construction) | 5 | No variance | 0 | N/A - dark fiber network | 1 | Network testing completed for 6 miles | 2011-02-20 20:05 | 2011-02-20 20:05 | 5742 | 5742 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2011 | Q1 | Q1 - 2011 | 2143 | 2817 | TRUE | 13 | Better than expected make-ready completion to date | 0 |  | N/A | 100 | No variance (completed) | 100 | No variance | 35 | No variance | 30 | Better than expected pole licensing activities at the end of February and into March. This result was created by consistent and effective communication between the project team and the pole owners which fostered a productive and efficient work environment. The project team gave specific make-ready schedule priorities to the pole owners who successfully demonstrated their abilities to work with these priorities. | 30 | Better than expected make-ready activities at the end of February and into March. This result was created by consistent and effective communication between the project team and the pole owners which fostered a productive and efficient work environment. The project team gave specific make-ready schedule priorities to the pole owners who successfully demonstrated their abilities to work with these priorities. | 2 | The original baseline listed 10% completion of Equipment Procurement by this quarter's end to match the 10% Overall Project completion also listed. However, the baseline percentage was calculated incorrectly as construction follows significantly behind make-ready completion. The calculation error was only discovered on this quarter's PPR. The Equipment Procurement percentage listed on this quarter's PPR is accurate and will be carried forward as such. | 2 | The original baseline listed 10% completion of Network Build by this quarter's end to match the 10% Overall Project completion also listed. However, the baseline percentage was calculated incorrectly as construction follows significantly behind make-ready completion and equipment procurement. The calculation error was only discovered on this quarter's PPR. In this quarter, Network Build followed close enough behind Equipment Procurement to match percentages. Going forward, Network Build may match Equipment Procurement or follow closely behind. The percentage listed on this PPR is accurate. | 0 | N/A - dark fiber network | 1 | Network testing completed for 6 miles; pending for 20 miles | 2011-05-18 16:16 | 2011-05-18 16:16 | 5742 | 5742 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2011 | Q2 | Q2 - 2011 | 3313 | 3419 | TRUE | 27 | Better than anticipated make-ready survey completion generated more make-ready costs for the project to pay to the pole owners pushing make-ready completion along at a faster pace. | 0 |  | N/A | 100 | No variance (completed) | 100 | No variance | 45 | No variance | 46 | Better than expected make-ready completion generated better than expected pole licenses | 46 | Better than expected make-ready completion | 7 | The original baseline listed 15% completion of Equipment Procurement by this quarter's end. However, the baseline percentage was calculated incorrectly as construction can follow significantly behind make-ready completion. The calculation error was only discovered on last quarter's PPR. The Equipment Procurement percentage listed for next quarter's PPR is an accurate prediction. | 7 | The original baseline listed 15% completion of Network Build by this quarter's end. However, the baseline percentage was calculated incorrectly as construction can follow significantly behind make-ready completion and equipment procurement. The calculation error was only discovered on last quarter's PPR. In this quarter, Network Build followed close enough behind Equipment Procurement to match percentages. Going forward, Network Build may match Equipment Procurement or follow closely behind. The percentage listed for next quarter's PPR is an accurate prediction. | 0 | N/A | 3 | The original baseline listed 10% completion of Network Testing by next quarter's end. However, that calculation is incorrect as there may be a time lag between construction completion and Network Testing. This means that the percentage of Network Testing may track more slowly against the Overall Project rate than the percentages calculated in the original baseline. The calculation error was only discovered on last quarter's PPR. The percentage listed for next quarter's PPR is an accurate prediction. | 2011-08-25 13:14 | 2011-08-25 13:14 | 5742 | 5742 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2011 | Q3 | Q3 - 2011 | 4327 | 4014 | TRUE | 40 | Better than anticipated make-ready survey completion generated more make-ready costs for the project to pay to the pole owners pushing make-ready completion along at a faster pace. | 0 |  | N/A | 100 | No variance (completed). | 100 | No variance | 55 | No variance | 65 | Better than anticipated make-ready completion generated better than expected pole licenses. | 65 | Better than anticipated make-ready completion. | 23 | Better than anticipated make-ready completion allowed for better than anticipated equipment procurement for construction completion. | 23 | Better than anticipated make-ready completion allowed for better than anticipated construction completion. | 0 | N/A | 20 | No variance | 2011-11-29 18:06 | 2011-11-29 18:06 | 5461 | 5461 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2011 | Q4 | Q4 - 2011 | 5075 | 4748 | TRUE | 56 | Better than anticipated make-ready survey completion generated more make-ready costs for the project to pay to the pole owners pushing make-ready completion along at a faster pace. | 0 |  | N/A | 100 | No variance | 100 | No variance | 65 | No variance | 82 | Better than anticipated make-ready completion generated better than expected pole licenses. | 78 | Better than anticipated make-ready completion. | 0 | The RFP for this equipment was awarded in this quarter. The contract negotiations have started with the award winner. | 48 | Better than anticipated make-ready completion allowed for better than anticipated construction completion. | 0 | N/A | 48 | Better than anticipated make-ready completion allowed for better than anticipated construction completion and subsequent testing. | 2012-02-16 19:08 | 2012-02-16 19:08 | 5461 | 5461 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2012 | Q1 | Q1 - 2012 | 6025 | 5612 | TRUE | 64 | Better than anticipated make-ready survey completion generated more make-ready costs for the project to pay the pole owners accelerating make-ready completion. | 0 |  | N/A | 100 | No variance | 100 | No variance | 75 | No variance | 95 | Better than anticipated make-ready completion. | 91 | Better than anticipated make-ready completion generated better than expected pole licenses. | 0 | The RFP award winner has shipped 90% of the equipment. We anticipate them shipping the remaining items early next quarter. The supplier will invoice only after full shipment. We will be ahead of our baseline schedule at that time as all the equipment was ordered at one time. | 56 | Better than anticipated make-ready completion generated better than anticipated construction completion. | 0 | N/A | 50 | Better than anticipated make-ready completion allowed for better than anticipated construction completion and subsequent testing. | 2012-05-10 16:22 | 2012-05-10 16:22 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2012 | Q2 | Q2 - 2012 | 6893 | 6073 | TRUE | 79 | Better than anticipated make-ready survey completion generated more make-ready costs for the project to pay the pole owners accelerating make-ready completion. This also accelerated construction completion and we achieved a better than anticipated rate of construction completion. | 0 |  | N/A | 100 | No variance | 100 | No variance | 90 | Better than anticipated make-ready completion generated better than anticipated rights of way completion. | 98 | Better than anticipated make-ready completion | 96 | Better than anticipated make-ready completion generated better than expected pole licenses. | 100 | 100% of DWDM equipment was shipped and invoiced early in the quarter, ahead of baseline schedule | 94 | Better than anticipated make-ready completion generated better than anticipated construction completion. | 0 | N/A | 86 | Better than anticipated make-ready completion allowed for better than anticipated construction completion and subsequent testing. | 2012-08-07 14:40 | 2012-08-07 14:40 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2012 | Q3 | Q3 - 2012 | 8017 | 6715 | TRUE | 83 | We are ahead of budget because we achieved a better than anticipated rate of construction completion. | 0 |  | N/A | 100 | No variance | 100 | No variance | 98 | Better than anticipated make-ready completion will allow for faster than anticipated complete rights of way. | 99 | Better than anticipated make-ready completion. | 98 | Continued ahead of schedule progress; the site preparation tracks closely with the construction permits and other approvals. | 100 | All DWDM gear has been received | 96 | While the backbone is complete, we are working on finishing up the approved route extension remaining CAI's and regeneration shelters. | 0 | N/A | 98 | Testing only remains on the approved route extension and the remaining CAI's; testing follows construction completion. | 2012-11-21 13:16 | 2012-11-21 13:16 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2012 | Q4 | Q4 - 2012 | 8695 | 7507 | TRUE | 85 | We continue to be ahead of the baseline budget goals due to a better than anticipated rate of construction completion. | 0 |  | N/A | 100 | No variance | 100 | No variance | 100 | All known make-ready work has been complete. | 99 | All known make-ready work has been complete. A small amount of permitting on regeneration shelters remains. | 98 | Site preperation for the fiber backcone, CAIs, Biddeford extension all complete. Site preparation for regeneration shelters still to be complete | 100 | All DWDM gear has been received | 97 | The fiber backbone and route extension are both complete. We have 4 CAIs and the regeneration shelters to complete. | 0 | N/A | 99 | The only testing needing to be complete is on the 4 remaining CAI's. All other testing has been complete. | 2013-02-11 10:30 | 2013-02-11 10:30 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2013 | Q1 | Q1 - 2013 | 9863 | 8469 | TRUE | 88 | With the backbone, CAIs and approved extension now complete, the majority of the remaining funds will be used during Q2 and Q3 2013 to complete the regeneration shelters and the recently approved IRU AAR. | 0 |  | n/a | 100 | No variance | 100 | No variance | 100 | All known Make Ready work has been completed | 100 | All known Make Ready and permitting complete | 98 | Although most the work has been complete, some payments for site preparation for the regeneration shelters will take place in Q2. All other known Site Preparation has been complete. | 100 | All DWDM gear has been received | 91 | While the backbone, CAIs, and extension are all complete and significant progress on the regeneration shelters has been made, the IRU AAR that was approved in Q1 will complete in Q2 (for roughly $2.3M) and caused the percent complete to reduce over Q4 2012. | 0 | n/a | 100 | All known testing has been complete. | 2013-05-22 08:25 | 2013-05-22 08:25 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2013 | Q2 | Q2 - 2013 | 10457 | 8875 | TRUE | 98 | Execution of approved IRU agreements accounted for the jump from Q1 reporting. All other items are substantially complete, as well. | 0 |  | n/a | 100 | No variance | 100 | No variance | 100 | All known Make Ready work has been completed | 100 | All known Make Ready and permitting complete | 100 | All known Site Preparation has been complete. | 100 | All DWDM gear has been received | 99 | Some additional interconnection may occur over the remaining 60 days leading up to Grant Close | 0 | n/a | 100 | All known testing has been complete. | 2013-07-31 12:12 | 2013-07-31 12:12 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2013 | Q3 | Q3 - 2013 | 11613 | 9741 | TRUE | 100 | All activities for the project are complete and all costs are final. | 0 |  | n/a | 100 | No variance | 100 | No variance | 100 | All Make Ready work is complete | 100 | All permitting is complete | 100 | All site prep is complete | 100 | All DWDM gear is received | 100 | All network build is complete | 0 | n/a | 100 | All testing is complete | 2014-01-16 10:06 | 2014-01-16 10:06 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570140 | 2010 | Q4 | Q4 - 2010 | 1167 | 2203 | TRUE | 7 | EA still ongoing, equipment purchases delayed until mid Jan2011 due to budget submission. No fiber build out yet due to EA requirement. | 0 | n/a | N/A | 50 | NTIA letter to Fish and Wildlife was not acted upon by Fish office. EA Consultant was able to move the process forward with Fish. Pending response from Fish. Section 106 with SHPO is in progress. | 100 | Completed per baseline. Network design has been 100% completed. | 0 | n/a | 0 | n/a | 80 | Completed per baseline. All sites have been pre-fielded and most site documentation has been completed. | 0 | Equipment purchases delayed until mid Jan 2011. 6 month budget request and holiday administrative leave contributed to the delay. | 5 | Due to delays in equipment purchases, existing network could not be regroomed as planned. The 5% completion includes sites that have been regroomed using existing network components in preparation for equipment upgrades. | 0 | Equipment purchases delayed until mid Jan 2011. No new equipment has been deployed. | 0 | Equipment purchases delayed until mid Jan 2011. No network testing can be performed on new segments as none are built. | 2011-02-15 21:59 | 2011-02-15 21:59 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2011 | Q1 | Q1 - 2011 | 2233 | 2862 | TRUE | 10 | Draft EA submitted, review in progress. First round equipment purchased, awaiting completion of deliveries. No installation at sites yet as all equipment has not yet arrived. No fiber build out yet due to EA requirement. | 0 |  | n/a | 80 | Draft EA submitted, review of submitted draft in progress with EA reviewer. No expenditures were recorded yet for the EA. | 100 | Completed per baseline. Network design has been 100% completed. | 0 | n/a | 0 | na/a | 100 | Completed per baseline. All sites have been pre-fielded. Site documentation finalized and completed. | 36 | Initial equipment order placed and awaiting delivery of all ordered equipment. Most of the equipment received in this quarter was paid. | 5 | Due to delays in equipment purchases, existing network could not be regroomed as planned. The 5% completion includes sites that have been regroomed using existing network components in preparation for equipment upgrades. No change in status since previous quarter. | 0 | Awaiting equipment delivery | 0 | Fiber build out has not yet begun. No network testing can be performed on new segments as none are built. | 2011-05-20 21:01 | 2011-05-20 21:01 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2011 | Q2 | Q2 - 2011 | 3063 | 3289 | TRUE | 13 | Project is behind the baseline, primarily because the FONSI was not received until the end of the quarter so construction could not actually start during this quarter. Equipment deployment has progressed at a slightly slower pace than anticipated due to delays in receiving equipment and staff changes at the DOE. Overall project percentage is based on actual completion of the project - i.e., deploying fiber, equipment and activation of services. Although closely related, overall project percent completion does not directly correspond to percentage expended and is not expected for this project for a number of reasons including: equipment may be received but not installed in exactly the same quarter, equipment may be received and installed but not paid for or drawn down within the same quarter, work may be done but not yet paid for and drawn down in the same quarter, specific item costs might vary slightly (up or down) from budgeted amounts, etc. | 0 |  | n/a | 100 | EA Submitted and FONSI received | 100 | Completed per baseline. | 0 | n/a | 0 | n/a | 100 | Completed per baseline. All sites have been pre-fielded. | 40 | All equipment on initial order has been received. Equipment Procurement percentage reflects quantities of equipment, not dollar value. Baseline showed 100% of equipment received, however since the FONSI has delayed construction and the deployment has been delayed, we have decided to delay the purchasing of the remainder of equipment until construction has begun and more equipment has been installed. | 8 | Majority of UH sites have been upgraded with new equipment and certain existing fiber segments have been upgraded to new capacity. Some DOE sites have had equipment upgraded as well. This is below the baseline due to the delays in the FONSI and associated impacts. | 10 | Distance Learning equipment has begun, as well as equipment deployment at site. Project is behind baseline, partly due to some delay in receiving equipment and staffing issues at the DOE. | 4 | Links that have been upgraded with improved site access or new access have been tested and are in production. Project is behind baseline due to delay in receiving FONSI and no construction being done. The project has upgraded and tested links over fiber that was already in place. | 2011-08-12 16:31 | 2011-08-12 16:31 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2011 | Q3 | Q3 - 2011 | 4313 | 4007 | TRUE | 18 | Project is behind the baseline, primarily due to the lengthy EA process and delayed FONSI which delayed construction and equipment deployment. Overall project percentage is based on actual completion of the project - i.e. deploying fiber, equipment and activation of services and may not directly correspond to the percentage expended since equipment may not be deployed and work may not be completed in exactly the same quarter as expenditures are recorded. | 0 |  | n/a | 100 | Completed per baseline | 100 | Completed per baseline | 0 | n/a | 0 | n/a | 100 | Completed per baseline. | 45 | All equipment on initial order received. Equipment procurement percentage reflects quantities of equipment, not dollar value. HSPLS has purchased their equipment (as part of their matching) but not all their equipment has been received. Baseline showed 100% of the equipment as received but due to the late EA process, it was not practical to order all of the equipment until construction actually started in this quarter. | 12 | Almost all UH sites have been upgraded with new equipment and certain fiber segments have been upgraded with new capacity. Interisland connections to Molokai and Lanai were completed and Molokai is currently in service. Sites that have existing fiber are in the process of being upgraded as the network allows. This percentage is below baseline due to the delays in the EA process and associated staffing issues. | 15 | Equipment deployment is still in progress. Percentage is less than baseline since the staff of the DOE and Libraries have had to concentrate on other projects during this quarter. Almost all UH sites have been deployed. | 12 | Network testing is in sync with the Network Build percentage - as sites are built or upgraded, the fiber connections or upgraded paths are tested and the put into production. | 2011-11-29 13:34 | 2011-11-29 13:34 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2011 | Q4 | Q4 - 2011 | 4921 | 4602 | TRUE | 30 | Significant progress has been made this quarter. 18 sites have had fiber installed, but due to their location on the network, the optical paths have not yet been built. Project is still behind the baseline due to delay in receiving the EA FONSI. We are working with the DOE and HSPLS to increase staff support to help overcome the initial delays. Overall project percentage is based on actual completion of the project - i.e. deploying fiber, equipment and activation of services and may not directly correspond to the percentage expended since not all equipment may be deployed or work completed in the same quarter as expenditures are recorded. | 0 |  | n/a | 100 | Completed per baseline | 100 | Completed per baseline | 0 | n/a | 0 | n/a | 100 | Completed per baseline | 98 | Almost all equipment has been purchased for the project and is in the process of being received and inventoried. Equipment procurement percentage reflects quantities of equipment, not dollar value. Procurement is less than the Baseline since it is not practical to order the final equipment items until most of the installations are complete. | 17 | Key sites have been upgraded and put into service to allow for further expansion of the network on the neighbor islands. Sites that have existing fiber have been upgraded or installed as the network allows. All interisland circuits have been installed and will be activated as the network allows. 18 sites have had fiber installed this quarter, but the optical network has not yet been built so they have not been counted in the network build but are reflected in the overall project percentage. The network build percentage is below the baseline due to the initial delays in the EA process and DOE and HSPLS staffing issues. | 40 | Project has made considerable progress this quarter and continues to deploy equipment deployment every quarter. The remainder of the equipment to be deployed will be received and inventoried through the next quarter and will be deployed throughout the next few quarters. Deployment continues to lag Baseline due to the initial EA-related delays while the DOE and Libraries continue to find ways to overcome staffing issues, but deployment delays have not impeded overall project progress. | 17 | Network testing is in sync with the Network Build percentage - as sites are built or upgraded, the fiber connections or upgraded paths are tested and put into production. | 2012-02-08 16:54 | 2012-02-08 16:54 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2012 | Q1 | Q1 - 2012 | 6207 | 5706 | TRUE | 38 | An additional 27 sites have had fiber built to them this quarter. None of the sites however have had their optical paths lit yet due to the network topology. Project is still behind the baseline due to the delay in beginning construction. Overall flow of the project is progressing and timely responses from HawaiianTel Joint Pole apps are working in the projects' favor. Overall project percentage is based on actual completion of the project - i.e. deploying fiber, equipment and activation of services and may not directly correspond to the percentage expended since not all equipment may be deployed or work completed in the same quarter as expenditures are recorded. | 0 |  | n/a | 100 | Completed per baseline | 100 | Completed per baseline | 0 | n/a | 0 | n/a | 100 | Completed per baseline | 98 | Almost all equipment has been purchased for the project and is in the process of being received and inventoried. Equipment procurement percentage reflects quantities of equipment, not dollar value. Procurement is less than the Baseline since it is not practical to order the final equipment items until most of the installations are complete. | 36 | Sites that have existing fiber have been upgraded or installed as the network topology allows. Key hub sites have been upgraded and put into service as the network topology allows. 27 sites have had fiber installed this quarter but the optical paths have not yet been built so they have not been counted in the network build but are reflected in the overall project percentage. The network build percentage is below baseline due to initial delays from late receipt of the FONSI. Project timelines have been adversely affected by the additional time it took to process the FONSI approvals. Project participants have been working on improving production rates over the last quarter. Based on projected build rates, the project is estimating that it should reach baseline numbers towards the later quarters of Year 3 | 60 | Equipment continues to be deployed to sites across the state by HSPLS, DOE and UH staff but deployment is below the baseline. Staffing issues are contributing to the delay of installing of equipment but the deployment delays have not impacted the overall project progress. The project is expecting to reach baseline numbers towards the early quarters of Year 3. | 36 | Network testing is in sync with Network Build percentage. As sites are built or upgraded, fiber connections or upgraded paths are tested and then put into production.Project timelines have been adversely affected by the additional time it took to process the FONSI approvals. Project participants have been working on improving production rates over the last quarter. Based on projected build rates, the project is estimating that it should reach baseline numbers towards the later quarters of Year 3 | 2012-05-18 16:50 | 2012-05-18 16:50 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2012 | Q2 | Q2 - 2012 | 7023 | 6139 | TRUE | 38 | Overall Project percentage reported is based on funds expended (Total funds including match). The actual project based on the fiber construction, equipment installation and site activation is 50% completed. An additional 50 sites have had fiber built to them this quarter. Not all of these sites have had their optical paths lit due to the network topology. Additionally not all have had the fiber patch panels installed and the fiber terminated yet. The project is still behind the baseline due to the delay in the start of construction. Overall progress of the project is moving along. We have averaged over 16 sites per month over the last quarter and expect this number to increase. Overall project percentage is based on actual completion of the project - i.e. deploying fiber, equipment and activation of services and may not directly correspond to the percentage of money expended. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is | 0 |  | n/a | 100 | Completed | 100 | Completed | 0 | n/a | 0 | n/a | 100 | Completed | 98 | Almost all equipment has been purchased for the project and is in the process of being received and inventoried. Equipment procurement percentage reflects quantities of equipment, not dollar value. Procurement is less than the Baseline since it is not practical to order the final equipment items until most of the installations are complete. | 38 | Sites that have existing fiber have been upgraded or installed as the network topology allows. Existing sites on the network have been upgraded where the topology allows. 50 new sites have had fiber physically pulled into their wiring closets but not all my have been activated on the network due to topology or fiber termination situations. The network build percentage is still below Baseline due to initial delays from the late receipt of FONSI but project participants have been continuing to work on improving production rates each quarter. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is just slightly behind these revised projections due to delays at the end of june in fiber terminations and the resulting inability to connect sites to the network. | 70 | Equipment continues to be deployed to sites across the state by HSPLS, DOE and UH staff but deployment is below the baseline. Staffing issues are contributing to the delay of installing of equipment but the deployment delays have not impacted the overall project progress. HSPLS is making installations a top priority for the upcoming months. | 38 | Network testing is in sync with Network Build percentage. As sites are built or upgraded, fiber connections or upgraded paths are tested and then put into production. Project timelines were adversely affected by late receipt of the FONSI but project participants have continued to work to increase production rates each quarter. The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is just slightly behind these revised projections. | 2012-08-10 17:41 | 2012-08-10 17:41 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2012 | Q3 | Q3 - 2012 | 7885 | 6647 | TRUE | 38 | Overall project percentage reported is based on funds expended (Total funds including match) but the actual progress, based on the fiber construction, equipment installation and site activation, is 55% complete. Overall project completion is actually much higher than the percentage of money expended this quarter indicates because our major subcontractor is in the process of revising its billing system so some large invoices for work completed have been delayed until next quarter. An additional 54 sites have had fiber built to them this quarter; however, not all of these sites have had their optical paths lit due to the network topology or they are waiting for fiber termination and splicing. The project is still behind the baseline due to the delay in the start of construction. The project has met the 18 site builds per month and is on track to complete the site builds by the end of May 2013 as planned. The project will be tracking the Progress Project Table that was submitted in Jun | 0 | true | n/a | 100 | Completed | 100 | Completed | 0 | n/a | 0 | n/a | 100 | Completed | 98 | Almost all equipment has been purchased for the project and is in the process of being received and inventoried. Equipment procurement percentage reflects quantities of equipment, not dollar value. Procurement is less than the Baseline since it is not practical to order the final equipment items until most of the installations are complete. | 55 | As sites are spliced into the INET rings, they are being activated where the network topology allows. The network build percentage is below baseline due to initial delays from late receipt of the FONSI. The project will be tracking the Progress Project table that was submitted in June 2012. The project is behind that project table due to delays in fiber termination and outside plant splicing and the resulting inability to connect sites to the network. | 80 | Equipment deployment continues across the State by DOE, HSPLS and UH staff. Most of the equipment on Maui and Oahu have been installed. | 55 | Network testing is in sync with the Network Build. | 2012-11-14 20:30 | 2012-11-14 20:30 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2012 | Q4 | Q4 - 2012 | 8753 | 7550 | TRUE | 42 | Overall project percentage reported is based on funds expended (Total funds including match) but the actual progress, based on the fiber construction, equipment installation and site activation, is 68% complete. Our major subcontractor is still behind on billings so funds actually expended during the quarter continue to be much less than the overall completion percentage indicated. An additional 65 sites have had fiber built to them this quarter; however, not all of these sites have had their optical paths lit due to the network topology or they are waiting for fiber termination and splicing. The project is still behind the baseline due to the delay in the start of construction. The project will be tracking the Progress Project Table that was submitted in June 2012 going forward. Based on this revised schedule, construction is on target but site activations are behind. The site activation delays are due to the fiber termination delays and splicing delays due to other planned wor | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 98 | Almost all equipment has been purchased for the project and is in the process of being received and inventoried. Equipment procurement percentage reflects quantities of equipment, not dollar value. Procurement is less than the Baseline since it is not practical to order the final equipment items until most of the installations are complete. | 68 | As sites are spliced into the INET rings, they are being activated where the network topology allows. The network build percentage is below baseline due to initial delays from late receipt of the FONSI. The project will be tracking the Progress Project table that was submitted in June 2012. The project is behind that project table due to delays in fiber termination and outside plant splicing and the resulting inability to connect sites to the network. | 85 | Equipment deployment continues across the State by the DOE, HSPLS and UH Staff. | 68 | Network testing is in sync with the Network Build. | 2013-02-13 14:15 | 2013-02-13 14:15 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2013 | Q1 | Q1 - 2013 | 9805 | 8438 | TRUE | 53 | Overall project percentage reported is based on funds expended (Total funds including match) but the actual progress, based on the fiber construction, equipment installation and site activation, is 75% complete. Our major subcontractor is still behind on billings so funds actually expended during the quarter continue to be much less than the overall completion percentage indicated. An additional 28 sites have had fiber built to them this quarter; however, not all of these sites have had their optical paths lit due to the network topology or they are waiting for fiber termination and splicing. The project is still behind the baseline due to the delay in the start of construction. The project will be tracking the Progress Project Table that was submitted in June 2012 going forward. Based on this revised schedule, construction is on target but site activations are behind. The site activation delays are due to the fiber termination delays and splicing delays due to other planned wor | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 98 | Almost all equipment has been purchased for the project and is in the process of being received and inventoried. Equipment procurement percentage reflects quantities of equipment, not dollar value. Procurement is less than the Baseline since it is not practical to order the final equipment items until most of the installations are complete. | 75 | As sites are spliced into the INET rings, they are being activated where the network topology allows. The network build percentage is below baseline due to initial delays from late receipt of the FONSI. The project will be tracking the Progress Project table that was submitted in June 2012. The project is behind that project table due to delays in fiber termination and outside plant splicing and the resulting inability to connect sites to the network. | 90 | Equipment Deployment continues across the State by the DOE, HSPLS and UH Staff | 75 | Network testing is in sync with the Network b/uild | 2013-05-17 18:00 | 2013-05-17 18:00 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2013 | Q2 | Q2 - 2013 | 10589 | 8952 | TRUE | 71 | Overall project percentage reported is based on funds expended (Total funds including match) but the actual progress, based on the fiber construction, equipment installation and site activation, is 90% complete. Our major subcontractor is still behind on billings so funds actually expended during the quarter continue to be much less than the overall completion percentage indicated. | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 98 | Almost all equipment has been purchased for the project and is in the process of being received and inventoried. Equipment procurement percentage reflects quantities of equipment, not dollar value. Procurement is less than the Baseline since it is not practical to order the final equipment items until most of the installations are complete. | 90 | As sites are spliced into the INET rings they are being activated where the network topology allows. The network build is less than the baseline due the delays encountered at the beginning of the project. | 95 | Equipment Deployment continues across the State by the DOE, HSPLS and UH Staff | 90 | Network testing is tracking the network build. | 2013-08-14 19:54 | 2013-08-14 19:54 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2013 | Q3 | Q3 - 2013 | 11287 | 9441 | TRUE | 95 | Overall project percentage reported is based on funds expended (total funds including match) but the actual progress, based on the fiber construction, equipment installation and site activation is 96% complete. Overall project percentage is now tracking actual progress as the primary contractor has caught up with their billing. | 0 |  | n/a | 100 | Completed | 100 | Completed | 0 | n/a | 0 | n/a | 100 | Completed | 98 | Almost all equipment has been purchased for the project. Equipment procurement percentage reflects quantities of equipment, not dollar value. Procurement is less than the baseline since it is not practical to order the final equipment items until most of the installations are complete. | 96 | As sites are spliced into the INET rings they are being activated where the network topology allows. The network build is less than the baseline due to delays encountered at the beginning of the project. | 95 | Equipment deployment continues across the State by the DOE, HSPLS, and UH Staff. | 96 | Network testing is tracking the network build. | 2013-11-19 12:13 | 2013-11-19 12:13 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2013 | Q4 | Q4 - 2013 | 11901 | 10069 | TRUE | 97 | Overall project percentage reported is based on funds expended (total funds including match) but the actual progress, based on the fiber construction, equipment installation and site activation is 98% complete. Overall project percentage is now tracking actual progress as the primary contractor has caught up with their billing. | 0 | 0 | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 99 | Almost all equpiment has been purchased for the project. Equipment procurement percentage reflects quantities of equipment, not dollar value. | 98 | As sites are spliced into the INET rings they are being activated where the network topology allows. | 98 | Equipment deployment continues across the state as new sites are brought online. | 98 | Network testing is tracking the network build | 2014-02-26 21:15 | 2014-02-26 21:15 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570144 | 2010 | Q4 | Q4 - 2010 | 1255 | 2285 | TRUE | 0 | no variance | 0 |  | n/a | 50 | NIU received notification of award on 9/14/2010. However, NTIA determined the first quarter ended 9/30/2010, just two weeks later. NIU's baseline project plan is based on full quarters. According to our baseline plan, we will be 50% completed with the EA after the first full quarter. Since this report is based on progress 3 months and two weeks after award, there is no variance in our project plan. Our EA was submitted to NTIA on 2/4/2011, less than 5 months after award on 9/14/2010 so we are on target for a completed EA during the second full quarter. We anticipate reaching the overall project target during the grant period. | 0 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | 2011-02-21 13:17 | 2011-02-21 13:17 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2011 | Q1 | Q1 - 2011 | 2397 | 2944 | TRUE | 1 | Variance -9.9% is due to the Shortened First Quarter issue noted in 3. below. According to full project quarters, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to the shortened first quarter within the next two quarters. There were more activities than federal dollars drawn during the report period. | 0 |  | not applicable | 0 | Variance -100% - The environmental assessment was completed and submitted to NTIA on 2/4/2011, less than 5 months after notice of award. While the expense was incurred during the quarter, the initial payment had not yet been drawn down and final invoicing was held until review and approval by NTIA. There were more activities than federal dollars drawn during the report period. | 0 | Variance of -13.9% is due to the Shortened First Quarter issue noted in 3. below. According to full project quarters, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to the shortened first quarter within the next two quarters. There were more activities than federal dollars spent during the report period. The network design is in progress. We are currently meeting with CAIs to finalize organizations and routes. We have hired two employees to expedite this process. | 0 | Variance of -28.5% is due to the Shortened First Quarter issue noted in 3. below. According to full project quarters, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to the shortened first quarter within the next two quarters. There were more activities than federal dollars spent during the report period. Designs have been submitted to Illinois Dept of Transportation Over the next quarter contractors/engineers will be selected and then they can begin rights of way licensing. | 0 | Variance of -28.5% is due to the Shortened First Quarter issue noted in 3. below. According to full project quarters, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to the shortened first quarter within the next two quarters. There were more activities than federal dollars spent during the report period. We have received Army Corp of Engineering approvals for waterway crossings. Over the next quarter contractors/engineers will be selected and then they can begin rights of way licensing. | 0 | no variance | 0 | Variance of -7.9% is due to the Shortened First Quarter issue noted in 3. below. According to full project quarters, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to the shortened first quarter within the next two quarters. Equipment RFPs will be released early during the next quarter. | 0 | Variance of -3.9% is due to the Shortened First Quarter issue noted in 3. below. According to full project quarters, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to the shortened first quarter within the next two quarters. We are currently working on procurement of IRUs and wireless engineering. | 0 | Variance of -2.1% is due to the Shortened First Quarter issue noted in 3. below. According to full project quarters, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to the shortened first quarter within the next two quarters. Contingent upon equipment procurement. | 0 | Variance of -2.1% is due to the Shortened First Quarter issue noted in 3. below. According to full project quarters, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to the shortened first quarter within the next two quarters. Contingent upon completed networks. | 2011-05-31 11:39 | 2011-05-31 11:39 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2011 | Q2 | Q2 - 2011 | 3161 | 3341 | TRUE | 6 | There were more activities than federal dollars drawn during the report period. Variance -16.9% is due to the delay in receiving FONSI and Shortened First Quarter issue noted in 5. below. According to full project quarters, there is less variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress within the next three quarters. Construction will begin in mid July with the first contractor. The second contractor will begin construction in mid August. Two contractors on the project will facilitate progress in the next quarter. | 0 | n/a | not applicable | 100 | no variance | 15 | There were more activities than federal dollars spent during the report period. Variance of -8.8% is due in part to the delayed FONSI and Shortened First Quarter issue noted in 5. below. According to full project quarters, there is positive variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost within the next three quarters. The network design is in progress. We are currently meeting with CAIs to finalize organizations and routes. We have hired two employees to expedite this process in addition to sub recipients. | 0 | There were more activities than federal dollars spent during the report period. Variance of -42.8% is due in part to the delayed FONSI and Shortened First Quarter issue noted in 5. below. We anticipate recovering progress lost within the next three quarters. Permitting and rights of way acquisition began in mid May. Numerous permits had been received as of 6/30 but no expenditures had been processed. | 7 | There were more activities than federal dollars spent during the report period. Variance of -35.4% is due in part to the delayed FONSI and Shortened First Quarter issue noted in 5. below. We anticipate recovering progress lost within the next three quarters. Permitting and rights of way acquisition began in mid May. Numerous permits had been received as of 6/30 but no expenditures had been processed. | 0 | no variance | 0 | Variance of -15.4% is due in part to the delayed FONSI and Shortened First Quarter issue noted in 5. below. We anticipate recovering progress lost within the next two quarters. The Equipment RFP will be released in the next quarter. | 6 | There were more activities than federal dollars drawn during the report period. Variance -4.3% is due in part to the delay in receiving FONSI and Shortened First Quarter issue noted in 5. below. According to full project quarters, there is positive variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress within the next three quarters. Contracts were executed with 2 contractor during the quarter which will facilitate rapid deployment and network build going forward. | 0 | Variance of -11.7% is due in part to the delayed FONSI and Shortened First Quarter issue noted in 5. below. We anticipate recovering progress lost within the next two quarters. The Equipment RFP will be released in the next quarter. | 0 | Variance of -11.7% is due in part to the delayed FONSI and Shortened First Quarter issue noted in 5. below. We anticipate recovering progress lost within the next two quarters. | 2011-08-17 16:53 | 2011-08-17 16:53 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2011 | Q3 | Q3 - 2011 | 3935 | 3806 | TRUE | 11 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. Two construction contractors were hired during the quarter. The first contractor began construction in mid July, the second in early August. To date, 65 miles of duct have been constructed including 60% plowing and 40% boring. Contractors have deployed enough crews to build where existing permits are available but have resources to double the number of crews once sufficient permits are available. See permitting in Q3 below. Contractors will begin SMF fiber installation in early October and will begin network testing during the next quarter. CAI laterals are in progress and many wil | 0 | n/a | not applicable | 100 | no variance | 21 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. The network design is in progress with 40% of the constructed route submitted for permit review of which 18% has been permitted. We are currently meeting with CAIs to finalize organizations and routes. 50% of CAIs have been contacted for which we have secured letters of commitment from 30%. | 4 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. 18% of the constructed route has been permitted. Permitting and rights of way acquisition began in mid May. However resource limitations from the primary permitting agency caused turnaround times to more than double. Additional resources have been deployed at the permitting agency which should allow for increased turnaround times. Construction companies have capacity to significantly increase the number of crews in the field pending availability of permits. | 24 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. 18% of the constructed route has been permitted. Permitting and rights of way acquisition began in mid May. However resource limitations from the primary permitting agency caused turnaround times to more than double. Additional resources have been deployed at the permitting agency which should allow for increased turnaround times. Construction companies have capacity to significantly increase the number of crews in the field pending availability of permits. | 6 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. Increased permits during the quarter should allow contractors to fully deploy the maximum number of crews which will allow the project to move forward rapidly. We are in the final stages of the selection process for a Wireless contractor and anticipate issuing a contract during the next quarter. | 0 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. The CAI Equipment RFP was released in September and we anticipate awarding the contract in mid to late October. The core equipment RFP will be released in December 2011. | 12 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. Contracts were executed with 2 contractor during the quarter which will facilitate rapid deployment and network build going forward. We have construction 65 miles of network construction with fiber installation beginning in early October. Preliminary agreements are in place for IRUs with mutiple providers to solidify the complete route footprint. | 0 | Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. The CAI Equipment RFP was released in September and we anticipate awarding the contract in mid to late October. The core equipment RFP will be released in December 2011. | 0 | Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. Fiber optic cable will begin in early October as will network testing processes. | 2011-11-09 13:39 | 2011-11-09 13:39 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2011 | Q4 | Q4 - 2011 | 5141 | 4808 | TRUE | 20 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. At 12/31/2011, 84% of the network is designed and 34% permitted. over 187 miles of conduit have been installed and 29 miles of fiber blown. Lateral terminations for 6 CAIs have been completed with many more in progress. We have selected both a wireless contractor and CAI equipment vendor and will be executing the final contract in January along with initial purchases. | 0 | N/A | N/A | 100 | no variance | 33 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. At 12/31/2011, over 84% of the network is designed and 34% permitted. We are currently meeting with CAIs to secure organizational commitment and routes. 80% of CAIs have been contacted for which we have secured letters of commitment from 41%. | 20 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. 34% of the constructed route has been permitted. Permitting and rights of way acquisition began in mid May. However resource limitations from the primary permitting agency caused turnaround times to more than double. Additional resources have been deployed at the permitting agency which is improving turnaround times. Construction companies have capacity to significantly increase the number of crews in the field pending availability of permits and good weather. | 44 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. 34% of the constructed route has been permitted. Permitting and rights of way acquisition began in mid May. However resource limitations from the primary permitting agency caused turnaround times to more than double. Additional resources have been deployed at the permitting agency which is improving turnaround times. Construction companies have capacity to significantly increase the number of crews in the field pending availability of permits and good weather. | 17 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. Increased permits during the quarter will allow contractors to fully deploy the maximum number of crews once winter weather clears. We have selected a Wireless contractor and anticipate executing the contract in January. | 0 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. An equipment vendor was selected during the quarter and the final contract is in progress. The initial Purchase Order is ready and will be submitted upon contract execution anticipated in early January 2012. | 23 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. At 12/31/2011, 84% of the network is designed and 34% permitted. over 187 miles of conduit have been installed and 29 miles of fiber blown. Lateral terminations for 6 CAIs have been completed with many more in progress. We have selected both a wireless contractor and CAI equipment vendor and will be executing final contract in January along with initial purchases. | 0 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. An equipment vendor was selected during the quarter and the final contract is in progress. The initial Purchase Order is ready and will be submitted upon contract execution anticipated in early January 2012. | 10 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. Nearly 30 miles of fiber was installed during the quarter and will ramp up over the next quarter. | 2012-02-20 05:56 | 2012-02-20 05:56 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2012 | Q1 | Q1 - 2012 | 6151 | 5678 | TRUE | 40 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. At 3/31/2012, 87% of the network is designed and 61% permitted. Over 305 miles of conduit have been installed and 102 miles of fiber blown. Lateral terminations for 25 CAIs have been completed with dozens more in progress. CAI equipment has been purchased and core equipment is in the final stages of vendor selection. | 0 | N/A | N/A | 100 | no variance | 43 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. At 3/31/2012, over 87% of the network is designed and 61% permitted. We are currently meeting with CAIs to secure organizational commitment and routes. 95% of CAIs have been contacted for which we have secured letters of commitment from 71%. | 63 | no variance | 63 | no variance | 43 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. Increased permits during the quarter will allow contractors to fully deploy the maximum number of crews once winter weather clears. Our Wireless contractor has designed the initial 5 links and will be designing the next 7 links in early Q2 2012. | 9 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. A CAI equipment vendor was secured during the quarter and the initial order of CAI equipment purchased. The core network equipment RFP was released and review of vendors is in progress. We anticipate purchasing the core network equipment during Q2 2012. | 46 | Given the warmer Midwest winter weather and match commitments received, we have exceeded network build expectations during Q1 2012. | 4 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. 45 CAI conduit laterals have been completed. Of those, 25 have fiber blown and are ready for equipment installation which will ramp up during Q2 2012. | 25 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. 102 miles of fiber was installed during the quarter. We anticipate closing the gap on conduit installed during the next quarter. 5 wireless links have been designed and another 7 will be in progress during Q2 2012. | 2012-05-17 11:36 | 2012-05-17 11:36 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2012 | Q2 | Q2 - 2012 | 6927 | 6091 | TRUE | 49 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 6/30/2012, 94% of the network is designed and 77% permitted. Over 432 miles of conduit have been installed and 292 miles of fiber blown. Lateral terminations for 90 CAIs have been completed. CAI equipment has been purchased and core equipment is in the final stages of contract execution. | 0 | NA | not applicable | 100 | no variance | 51 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 6/30/2012, over 94% of the network is designed and 77% permitted. We are currently meeting with CAIs to secure organizational commitment and routes. 95% of CAIs have been contacted for which we have secured letters of commitment from 72%. | 80 | no variance | 85 | no variance | 50 | no variance | 9 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. CAI equipment vendor was selected and equipment is in the process of being programmed for installation. We are in the final stages of contract execution for core network equipment. We anticipate purchasing the core network equipment during Q3 2012. | 58 | no variance | 9 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. 105 CAI conduit laterals have been completed. Of those, 90 have fiber blown and are ready for equipment installation which will occur during Q3 2012. | 32 | There were more activities than federal dollars spent during the report period. Variance is also due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. 190 miles of fiber were installed during the quarter. Five wireless links have been designed and easement agreements for towers are in progress. Another 7 are being designed and easement agreements will begin in Q3 2012. | 2012-08-08 15:04 | 2012-08-21 07:35 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2012 | Q3 | Q3 - 2012 | 7829 | 6618 | TRUE | 62 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 9/30/2012, 98% of the network is designed and 86% permitted. Over 480 miles of conduit have been installed and 365 miles of fiber blown. Lateral terminations connecting 138 CAIs have been completed. CAI and core equipment has been purchased and planning for installation initiated. Several fiber and wireless segments submitted in June 2012 are pending NTIA route modification approval. | 0 | N/A | not applicable | 100 | no variance | 61 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 9/30/2012, over 98% of the network is designed and 86% permitted. We are currently meeting with CAIs to secure organizational commitment and routes. 98% of CAIs have been contacted for which we have secured letters of intent from 72%. | 96 | no variance | 90 | no variance | 90 | no variance | 29 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. CAI and core equipment has been purchased and received and is in the process of being programmed for installation. | 69 | no variance | 23 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. CAI and core equipment has been purchased and received and is in the process of being programmed for installation. | 35 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. To date, 365 miles of fiber have been blown. Five wireless links have been designed and easement agreements for towers are in progress. Another 7 have been designed and easement agreements are in progress. | 2012-11-13 06:22 | 2012-11-13 06:22 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2012 | Q4 | Q4 - 2012 | 9155 | 7982 | TRUE | 70 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 12/31/2012, 99% of the network is designed and 94% permitted. Over 537 miles of conduit have been installed and 473 miles of fiber blown. Lateral terminations connecting 173 CAIs have been completed. CAI and core equipment has been purchased and planning for installation initiated. | 0 | N/A | N/A | 100 | no variance | 94 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 12/31/2012 only 1% of the network remains to be designed, pending permitting agency review and approval of plans. | 96 | no variance | 95 | no variance | 92 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 12/31/2012, the remaining portion of work will be completed once route modifications have been approved and the work completed. | 35 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 12/31/2012, the procurement process is 100% completed, now pending delivery of equipment ordered from vendors. | 74 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 12/31/2012, 87% of conduit representing over 537 miles has been installed and 473 miles of fiber blown. Lateral terminations connecting 173 CAIs have been completed. Most of the remaining portions of the network build is pending NTIA review and approval of project modifications. | 30 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 12/31/2012, the procurement process is 100% completed, now pending delivery of equipment ordered from vendors. Equipment deployment initiated in the current quarter and will ramp up in Q1 2013. | 45 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 12/31/2012, 87% of conduit representing over 537 miles has been installed and 473 miles of fiber blown. Network testing has been completed or is in progress for most of the 473 miles of completed fiber miles. | 2013-03-29 14:31 | 2013-03-29 14:31 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2013 | Q1 | Q1 - 2013 | 9633 | 8349 | TRUE | 76 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 3/31/2013, 100% of the network is designed and 97% permitted. Over 546 miles of conduit have been installed and 516 miles of fiber blown. Lateral terminations connecting 184 CAIs have been completed. CAI and core equipment has been purchased and installation of core and distribution sites are in progress. | 0 | N/A | N/A | 100 | no variance | 100 | no variance | 98 | There were more activities than federal dollars spent during the report period. | 98 | There were more activities than federal dollars spent during the report period. | 95 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 3/31/2013, over 546 miles of conduit have been installed and 516 miles of fiber blown. Lateral terminations connecting 184 CAIs have been completed. The remaining portion of work will be completed once route modifications have been approved. | 39 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 3/31/2013, lateral terminations connecting 184 CAIs have been completed. CAI and core equipment has been purchased and installation of core and distribution sites are in progress. | 81 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 3/31/2013, over 546 miles of conduit have been installed and 516 miles of fiber blown. Lateral terminations connecting 184 CAIs have been completed. The remaining portion of work will be completed once route modifications have been approved. | 50 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 3/31/2013, lateral terminations connecting 184 CAIs have been completed. CAI and core equipment has been purchased and installation of core and distribution sites are in progress. | 52 | There were more activities than federal dollars spent during the report period. Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 3/31/2013, over 546 miles of conduit have been installed and 516 miles of fiber blown. Lateral terminations connecting 184 CAIs have been completed. The remaining portion of work will be completed once route modifications have been approved. | 2013-05-08 16:44 | 2013-05-08 16:44 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2013 | Q2 | Q2 - 2013 | 10493 | 8898 | TRUE | 81 | There were more activities than federal dollars spent during the report period. Variance is also due in part to route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. At 6/30/2013, 100% of the network is designed and 99% permitted. Over 564 miles of conduit have been installed and 520 miles of fiber blown. During the quarter, 1 wireless link was completed representing 8 of 38 wireless miles. Lateral terminations connecting 255 CAIs have been completed. 4 of 5 core network connections were completed. 14 of 28 distribution locations were completed. NTIA approval of all remaining route modifications was received during the quarter which will enable the project move forward. | 0 | N/A | N/A | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 99 | There were more activities than federal dollars spent during the report period. | 46 | There were more activities than federal dollars spent during the report period. Variance is also due in part to route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. At 6/30/2013, lateral terminations connecting 255 CAIs have been completed. CAI and core equipment has been purchased and installation of core and distribution sites is in progress with 4 of 5 core network connections completed and14 of 28 distribution locations completed during the quarter. | 85 | There were more activities than federal dollars spent during the report period. Variance is also due in part to route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. At 6/30/2013, 100% of the network is designed and 99% permitted. Over 564 miles of conduit have been installed and 520 miles of fiber blown. During the quarter, 1 wireless link was completed representing 8 of 38 wireless miles. Lateral terminations connecting 255 CAIs have been completed. 4 of 5 core network connections were completed. 14 of 28 distribution locations were completed. NTIA approval of all remaining route modifications was received during the quarter which will enable the project move forward. | 69 | There were more activities than federal dollars spent during the report period. Variance is also due in part to route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. At 6/30/2013, lateral terminations connecting 255 CAIs have been completed. CAI and core equipment has been purchased and installation of core and distribution sites is in progress with 4 of 5 core network connections completed and14 of 28 distribution locations completed during the quarter. | 73 | There were more activities than federal dollars spent during the report period. Variance is also due in part to route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. At 6/30/2013, 100% of the network is designed and 99% permitted. Over 564 miles of conduit have been installed and 520 miles of fiber blown. NTIA approval of all remaining route modifications was received during the quarter which will enable the project move forward. | 2013-08-06 14:15 | 2013-08-06 14:15 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2013 | Q3 | Q3 - 2013 | 11385 | 9501 | TRUE | 91 | There were more activities than federal dollars spent during the report period. Variance is also due in part to route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. At 9/30/2013, 100% of the network is designed and 100% permitted. 600 miles of conduit have been installed and 600 miles of fiber blown. During the quarter, all remaining wireless links were completed totaling 13 wireless links and 38 wireless miles. Lateral terminations connecting 379 CAIs have been completed. 4 of 5 core network connections were completed. 14 of 28 distribution locations were completed. | 0 | n/a | n/a | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 70 | There were more activities than federal dollars spent during the report period. Variance is also due in part to route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. CAI and core equipment has been purchased and installation of core and distribution sites is in progress with 4 of 5 core network connections completed and14 of 28 distribution locations completed during the quarter. | 100 | no variance | 90 | There were more activities than federal dollars spent during the report period. Variance is also due in part to route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. CAI and core equipment has been purchased and installation of core and distribution sites is in progress with 4 of 5 core network connections completed and14 of 28 distribution locations completed during the quarter. | 95 | There were more activities than federal dollars spent during the report period. Variance is also due in part to route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. At 9/30/2013, 100% of the network is designed and 100% permitted. 600 of 601 fiber miles have been installed and blown. Final network testing is in process. | 2013-11-26 10:00 | 2013-11-26 10:00 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2013 | Q4 | Q4 - 2013 | 12175 | 10359 | TRUE | 100 | no variance | 0 | N/A | N/A | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 2014-05-07 16:46 | 2014-05-07 16:46 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570145 | 2010 | Q4 | Q4 - 2010 | 1013 | 2059 | TRUE | 7 | 7-10 Percent complete | 95 | Grant Prep | Completed | 90 | Waiting for Bureau of Indian Affairs Environmental specialist. | 90 | Mostly Complete | 100 | Tribal Rights of Way have been approved. | 100 | Tribal permits and approvals are completed. | 0 | Haven't started construction because of EA and Weather. | 0 | Haven't started procuring equipment, waiting on EA approval. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-09 10:28 | 2011-02-09 10:28 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2011 | Q1 | Q1 - 2011 | 2353 | 2922 | TRUE | 5 | We feel the 5% is low, it is based on actual dollars spent. | 100 |  | Completed | 100 | Completed. Finding of no Significant Impact. | 90 | Mostly Complete | 100 | Tribal Rights of Way have been approved. | 100 | Tribal permits and approvals are completed. | 0 | Haven't started construction because of EA and Weather. | 0 | Should get back on track by next quarter. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-05-26 14:55 | 2011-05-26 14:55 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2011 | Q2 | Q2 - 2011 | 3107 | 3311 | TRUE | 12 | We will significantly catch up in during the 3rd Quarter of 2011 and plan to completely catch up during the 4th quarter 2011. Originally we had planned to dig part of the path this year and part next. We will dig both parts this year, which will allow us to catch up to our baseline projections. | 100 |  | Completed | 100 | Complete | 90 | Mostly complete | 100 | Complete | 100 | Complete | 0 | Will start to dig 4th quarter 2011 | 0 | Will purchase most of the equipment in 3rd quarter 2011. | 0 | Will begin in the third quarter 2011 with majority coming in the 4th quarter 2011. | 0 | Will begin to deploy equipment in 3rd quarter with majority coming in 4th quarter 2011. | 0 | Network testing will begin during the 3rd quarter and completely caught up in the 4th quarter. | 2011-08-16 10:17 | 2011-08-16 10:17 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2011 | Q3 | Q3 - 2011 | 3891 | 3784 | TRUE | 30 | We have made strides during the 3rd quarter. We will continue with our plan to do the digging during the 4th quarter and this will help us meet our goals. We will catch up to our baseline when the digging is completed. | 100 | N/A | Complete | 100 | Completed | 90 | Mostly complete | 100 | Complete | 100 | Complete | 0 | We will start digging in QRT 4 2011 | 60 | We have purchased the majority of the equipment. | 10 | We have received equipment. The majority will come in the 4th quarter of 2011 | 10 | Since receiving the equipment we have started the deployment and anticipate the majority to happen in the 4th quarter of 2011 | 10 | Testing has been started and will be caught up in the 4th quarter of 2011 | 2011-11-03 21:23 | 2011-11-28 12:38 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2011 | Q4 | Q4 - 2011 | 5017 | 4689 | TRUE | 46 | Unfortunately we were not able to get in the ground before cold weather, but we are on track, according to our last PPR. | 94 | Misc. | Complete | 100 | Completed | 90 | Mostly complete | 100 | Complete | 100 | Complete | 10 | Will start on main fiber loop as soon as weather permits. Have started to dig and place lateral fiber in first leg of project. | 60 | We have purchased the majority of networking equipment. | 30 | We have connected 9 CAI and built the 90% of the wireless network. | 30 | We have made strides in getting the network equipment deployed, with the majority of the deployment being on the 802.11 last mile wireless portion of the project. | 10 | Testing has been started on those section possible. | 2012-02-14 21:49 | 2012-02-14 21:49 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2012 | Q1 | Q1 - 2012 | 6323 | 5764 | TRUE | 53 | We were unable to get in the ground due to the weather, but we are on track, according to our last PPR. | 100 | Misc | Complete | 100 | Completed | 90 | Mostly completed | 100 | Completed | 100 | Completed | 10 | Do to weather we not able to get in the ground this quarter. | 90 | Majority of the equipment has been purchased | 50 | The Majority of the wireless network is built and we have connected 9 CAI. | 90 | We spent a significant portion of our time this quarter on equipment deployment, and were able to deploy almost all the infrastructure equipment required to operate the network. | 50 | We will be testing all the runs and equipment as deployed and thus should be about 50% or greater on the testing phase. | 2012-05-29 13:58 | 2012-05-29 13:58 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2012 | Q2 | Q2 - 2012 | 6931 | 6093 | TRUE | 70 | The project is progressing on schedule | 100 |  | Completed | 100 | Completed | 90 | Mostly completed | 100 | Completed | 100 | Completed | 57 | We made great progess in this quarter on the trenching and laying of conduit and inner duct. Lateral contractor was selected. | 97 | Majority of the equipment has been purchased | 62 | The Majority of the wireless network is built and we have connected 9 CAI. We anticipate adding more CAI's next qrt. | 97 | The majority of the equipment is deployed | 50 | We will be testing all the runs and equipment as deployed. | 2012-08-08 15:40 | 2012-08-08 15:40 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2012 | Q3 | Q3 - 2012 | 8089 | 6751 | TRUE | 93 | The project is progressing on schedule | 100 | n/a | Complete | 100 | Completed | 95 | Mostly Complete | 100 | Completed | 100 | Completed | 90 | We made great progress in this quarter the trenching and laying of conduit and inner duct is complete. The main loop fiber has been blown. Lateral contractor has dug, trenched and layed the conduit. The fiber for the laterals has started. | 100 | Completed | 70 | The majority of the wireless network is built and we have connected 7 CAI. We anticipate that 10 will be added next quarter | 97 | The majority of the equipment is deployed | 65 | We were planning on testing as the project progressed but due to weather concerns we decided to get all the fiber in and then terminate and complete the testing. | 2012-11-27 19:25 | 2012-11-27 19:25 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2012 | Q4 | Q4 - 2012 | 8785 | 7585 | TRUE | 98 | The project is progressing on schedule | 100 | N/A | Complete | 100 | Completed | 98 | Mostly Complete | 100 | Completed | 100 | Completed | 98 | We made great progress in this quarter the trenching and laying of conduit and inner duct is complete. The main loop fiber has been blown. Lateral contractor has been dug, trenched and laid the conduit. The fiber for the laterals is also mostly completed. | 100 | Completed | 98 | The majority of the wireless network is build and we have connected 35 total CAI's, 28 this last quarter. We anticipate connecting the remaining 7 next quarter. | 97 | The majority of the equipment is deployed. | 90 | We were planning on testing as the project progressed but due to weather concerns we decided to get all the fiber in and then terminate and complete the testing. | 2013-02-14 18:19 | 2013-02-14 18:19 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2013 | Q1 | Q1 - 2013 | 9815 | 8444 | TRUE | 100 | The project is progressing on schedule | 100 | N/A | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | The majority of the wireless network is complete and we have connected 43 total CAI's. | 100 | Complete | 100 | Complete | 2013-05-20 10:41 | 2013-05-20 10:41 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2013 | Q2 | Q2 - 2013 | 10083 | 8602 | TRUE | 100 | The project is progressing on schedule | 100 | N/A | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-07-02 12:40 | 2013-07-02 12:40 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2013 | Q3 | Q3 - 2013 | 10859 | 9114 | TRUE | 100 | Complete | 100 | N/A | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-09-28 17:47 | 2013-09-28 17:47 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570146 | 2010 | Q4 | Q4 - 2010 | 1225 | 2255 | TRUE | 1 | Slightly below budget due to lower Legal and Administrative Costs, but project is still on schedule. | 6 |  | Legal and Administrative Costs we're lower than projected for this quarter. Reduced percentage from 18% to 5% | 38 | Ahead of schedule. | 16 | Slightly above budgeted amount due to initial network design planning. Increased from 10% to 12% | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-02-18 15:49 | 2011-02-18 15:49 | 6425 | 6425 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2011 | Q1 | Q1 - 2011 | 1723 | 2590 | TRUE | 1 | Below budget due to ordered equipment invoicing not yet received and slightly delayed EA. | 15 | Admin | Lower due to fewer legal expenses than anticipated and EA delay. | 55 | EA delay, expect to finalize in next quarter. | 24 | No variance. | 1 | Slightly above due to POP site location acquisition process. | 0 | Below budget due to EA delay. | 0 | Below budget due to EA delay. | 0 | Equipment orders submitted to vendors. Lower than projected because invoices not yet received, but expected next quarter. | 1 | Labor expenses for testing started on existing in-kind fiber. | 0 | No variance. | 0 | No variance. | 2011-04-29 17:07 | 2011-04-29 17:07 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2011 | Q2 | Q2 - 2011 | 2959 | 3237 | TRUE | 10 | Slight delay in EA caused delay in Construction and Permitting, but expect catch up to planned schedule by Year End (YE) 2011. | 29 | Admin | Significantly lower Legal expenses than budgeted. | 82 | Below budget, a few additional EA related costs are anticipated in next two quarters. | 34 | Budgeted evenly throughout project, but more time devoted prior to construction and less later in project. | 23 | Lower cost of land for several PoP site locations, last few land purchases pending. | 1 | Slight delay in EA caused delay in Construction and Permitting, but expect catch up to planned schedule by YE 2011. | 23 | Slight delay in EA caused delay in Construction and Permitting, but expect catch up to planned schedule by YE 2011. | 18 | Lower cost of DWDM equipment than budgeted. Fiber ordered but anticipate manufacturer delay in delivery to Q4. | 1 | Slight delay in EA caused delay in Construction and Permitting, but expect catch up to planned schedule by YE 2011. | 7 | Innerduct received, not yet invoiced this quarter. | 0 | N/A | 2011-08-08 15:48 | 2011-08-08 15:48 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2011 | Q3 | Q3 - 2011 | 4255 | 3978 | TRUE | 20 | Below Baseline by 28% mostly due to equipment being received in 4th Qtr 2011 rather than 3rd Qtr as anticipated and fiber delay. However with the contribution of approximately 500 miles of in-kind fiber and the progression of construction, Sho-Me anticipates catching up to near baseline projections in 4th Qtr 2011. | 39 | Legal, Administrative, Pre-Award Expenses | Below Baseline by 8% because Legal expenses are significantly lower than anticipated and are anticipated to continue to be lower than baseline for the remainder of the project. | 82 | Below Baseline by 18%, actual cost of EA below budget, a few additional EA related costs are anticipated through the next couple of quarters. | 50 | Above Baseline by 10% because original budget projected Network Design budgeted evenly throughout project, however more time has been devoted early prior to construction than will be needed later in project. | 42 | Below Baseline by 32% due to prudent site acquisition practices yielding lower than anticipated land costs for several PoP sites, a few land purchases still pending closure next quarter. | 2 | Below Baseline by 30% due to vigilant engineering oversight which moderated Construction and Permitting costs to date. | 70 | Below Baseline by 22% because more has been budgeted in this category due to the Increased cost of NOC Air Handlers. Site Prep is expected to be 100% by 1st Qtr 2012. | 24 | Below Baseline by 35% due to delay in Fiber, however will start paying for in 4th Qtr 2011, DWDM equipment was scheduled to be paid for in Sept., received in Oct will pay for in 4th Qtr 2011 which combined with 4th Qtr fiber delivery will bring Sho-Me closer to baseline projections for 4th Qtr 2011. | 12 | Below Baseline by 27% because the delay of fiber has pushed budgeted costs to future quarters. With the 4th Qtr 2011 fiber delivery; Sho-Me expects to be near baseline projections by the end of 2011. | 66 | Above Baseline by 36% due to the Increased cost of innerduct. The purchase of innerduct is near completion. The increased cost is not anticipated to affect the category budget by more than 10%. | 0 | Below Baseline by 39% because these expenses were moved to another category for budgeting purposes. Sho-Me does not anticipate having any costs in this category for the remainder of the project. | 2011-11-23 13:39 | 2011-11-23 13:39 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2011 | Q4 | Q4 - 2011 | 5103 | 4773 | TRUE | 48 | 8% below Baseline due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. | 46 | Legal, Administrative, Pre-Award Expenses | Below Baseline by 8% due to legal and administrative costs being lower than anticipated. | 84 | Below Baseline by 16% due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 66 | Above Baseline by 16% due to more engineering and design work being performed at the onset of the project than anticipated. | 35 | 48% below Baseline due to lower than anticipated Rights of Way costs. A correction made in Q4 2011 moved expenses out of Rights of Way and into the correct category. This caused the Rights of Way category to show less of a percentage completed than in the previous quarter. | 76 | 28% above Baseline due to Warsaw River Crossing Agreement with MODOT. | 100 | No Variance. | 42 | 26% below Baseline due to lower than anticipated costs relating to DWDM equipment and the delay in fiber cable. | 48 | 2% above Baseline because the more expensive routes were/are being constructed toward the first half of the project. | 88 | 41% above Baseline due to increased costs of innerduct and because Sho-Me chose to buy most of the innerduct up front rather than spreading it throughout the project. | 0 | Below Baseline by 46% because these expenses were moved to another category for budgeting purposes. Sho-Me does not anticipate having any costs in this category for the remainder of the project. | 2012-02-17 15:04 | 2012-02-17 15:04 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2012 | Q1 | Q1 - 2012 | 5927 | 5563 | TRUE | 56 | 12% below baseline due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. Sho-Me anticipates it will meet baseline projections by the end of 2012. | 52 | Legal, Administrative, Pre- Award Expenses | 13% below baseline due to legal and administrative costs being lower than anticipated. | 89 | 11% below baseline due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 74 | 14% above baseline due to more engineering and design work being performed at the onset of the project than anticipated. | 38 | 53% below baseline due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as right of way costs continue to come in under budget. | 76 | 12% above baseline due to Warsaw River Crossing Agreement with MODOT. | 100 | No variance. | 53 | 22% below budget due to lower than anticipated costs relating to DWDM equipment and the delay in fiber cable. Sho-Me anticipates it will meet baseline projections by the end of 2012. | 55 | 6% below budget due to the delay in fiber optic cable. However, Sho-Me anticipates it will meet baseline projections by the end of 2012. | 92 | 28% above baseline due to increased costs of innerduct. Also, Sho-Meâ€™s baseline reflects buying innerduct throughout the project as it is needed, but instead Sho-Me chose to buy most of the innerduct up front in order to secure a lower price per foot. | 0 | Below Baseline by 61% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2012-05-04 11:19 | 2012-05-04 11:19 | 6426 | 6426 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2012 | Q2 | Q2 - 2012 | 6553 | 5891 | TRUE | 61 | Below Baseline by 14% due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. Sho-Me anticipates it will meet baseline projections by the end of 2012. | 61 | Legal, Administrative, Pre- Award Expenses | Below Baseline by 13% due to legal and administrative costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 90 | Below Baseline by 10% due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 79 | Above Baseline by 9% due to more engineering and design work being performed at the onset of the project than anticipated. | 38 | Below Baseline by 62% due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as right of way costs continue to come in under budget. | 76 | Below Baseline by 4% due to costs being lower than anticipated. Sho-Me does anticipate catching up to baseline by the end of 2012 as construction continues. | 100 | No variance. | 55 | Below Baseline by 28% due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 61 | Below Baseline by 7% due to the delay in fiber optic cable. However, Sho-Me anticipates it will meet baseline projections by the end of 2012. | 100 | Above Baseline by 25% due to increased costs of innerduct. Also, Sho-Meâ€™s baseline reflects buying innerduct throughout the project as it is needed, but instead Sho-Me chose to buy most of the innerduct up front in order to secure a lower price per foot. | 0 | Below Baseline by 68% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2012-07-27 18:15 | 2012-07-27 18:15 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2012 | Q3 | Q3 - 2012 | 7907 | 6658 | TRUE | 78 | Below Baseline by 8% due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. Sho-Me anticipates it will meet baseline projections by 1st Quarter 2013. | 68 | Legal, Administrative, Pre-Award Expenses | Below Baseline by 15% due to legal and administrative costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 90 | Below Baseline by 10% due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 84 | Above Baseline by 4% due to more engineering and design work being performed at the onset of the project than anticipated. | 38 | Below Baseline by 62% due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as rights of way costs continue to come in under budget. | 79 | Below Baseline by 21% due to costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project as permitting costs continue to come in under budget. | 100 | No variance. | 76 | Below Baseline by 19% due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 76 | Below Baseline by 2% due to the delay in fiber optic cable. Sho-Me plans to meet the baseline by the end of 2012. | 100 | Above Baseline by 17% due to increased cost of innerduct. | 0 | Below Baseline by 78% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2012-11-15 17:23 | 2012-11-15 17:23 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2012 | Q4 | Q4 - 2012 | 8711 | 7516 | TRUE | 87 | Below Baseline by 5% due to unforeseen fiber availability constraints from manufacturers in 2011, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. Sho-Me anticipates it will meet baseline projections by 1st Quarter 2013. | 75 | Legal, Administrative, Pre- Award Expenses | Below Baseline by 17% due to legal and administrative costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 91 | Below Baseline by 9% due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 89 | Below Baseline by 1% due to fewer engineering hours needed than anticipated. | 38 | Below Baseline by 62% due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as rights of way costs continue to come in under budget. | 80 | Below Baseline by 20% due to costs being lower than anticipated. Sho- Me anticipates this category will remain under budget for the remainder of the project as permitting costs continue to come in under budget. | 100 | No variance. | 79 | Below Baseline by 21% due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 91 | Above Baseline by 7% due to increased cost of construction. | 100 | Above Baseline by 8% due to increased cost of innerduct. | 0 | Below Baseline by 84% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2013-02-11 17:04 | 2013-02-11 17:04 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2013 | Q1 | Q1 - 2013 | 9209 | 8040 | TRUE | 92 | Below Baseline by 7% due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. Sho-Me anticipates it will meet baseline projections by 2nd Qtr 2013. | 75 | Legal, Administrative, Pre- Award Expenses | Below Baseline by 25% due to legal and administrative costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 97 | Below Baseline by 3% due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 91 | Below baseline by 9% due to less engineering hours being needed than expected. | 38 | Below Baseline by 62% due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as rights of way costs continue to come in under budget. | 80 | Below Baseline by 20% due to costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project as permitting costs continue to come in under budget. | 100 | No variance. | 81 | Below Baseline by 19% due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 99 | Above Baseline by 2% due to higher than anticipated construction costs. | 100 | Above Baseline by 3% due to higher than anticipated innerduct costs. | 0 | Below Baseline by 97% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2013-04-22 13:14 | 2013-04-22 13:14 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2013 | Q2 | Q2 - 2013 | 10251 | 8728 | TRUE | 97 | Below Baseline by 3% due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. Sho-Me anticipates it will meet baseline projections by 3rd Qtr 2013. | 84 | Legal, Administrative, Pre- Award Expenses | Below Baseline by 16% due to legal and administrative costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 97 | Below Baseline by 3% due to costs being lower than anticipated. Sho-Me does not anticipate any future expenses in this category. | 93 | Below baseline by 7% due to less engineering hours being needed than expected. | 38 | Below Baseline by 62% due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as rights of way costs continue to come in under budget. Sho-Me does not anticipate any future expenses in this category. | 80 | Below Baseline by 20% due to costs being lower than anticipated. Sho- Me anticipates this category will remain under budget for the remainder of the project as permitting costs continue to come in under budget. Sho-Me does not anticipate any future expenses in this category. | 100 | No variance. | 83 | Below Baseline by 17% due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 100 | No variance. | 100 | No variance. | 0 | Below Baseline by 100% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2013-07-29 17:23 | 2013-07-29 17:23 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2013 | Q3 | Q3 - 2013 | 11625 | 9747 | TRUE | 100 | No Variance. | 100 | Legal, Administrative, Pre- Award Expenses | Actual spend was 94% and below Baseline by 6% due to legal and administrative costs being lower than anticipated. | 100 | Actual spend was 97% and below Baseline by 3% due to costs being lower than anticipated. | 100 | Actual spend was 95% and below baseline by 5% due to less engineering hours being needed than expected. | 100 | Actual spend was 38% and below baseline by 62% due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as rights of way costs came in under budget. | 100 | Actual spend was 80% and below Baseline by 20% due to costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project as permitting costs came in under budget. | 100 | No variance. | 100 | Actual spend was 87% and below Baseline by 13% due to lower than anticipated costs relating to DWDM equipment. | 100 | No variance. | 100 | No variance. | 100 | Actual spend was 0% and below Baseline by 100% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me does not use this baseline category for the remainder of the project. | 2014-01-17 16:22 | 2014-01-17 16:22 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570148 | 2010 | Q4 | Q4 - 2010 | 1209 | 2243 | TRUE | 3 | We projected to be 23% completed by the end of this quarter, mainly on the basis of having procured the equipment and having the crew selection completed. This has been held up by the delay in getting the pre-EA 6-month budget approved and the sub-recipient status for Montana West approved. Once the sub-recipient status is approved, we will catch up quickly. | 8 | Admin and Match | On Target | 14 | On Target | 0 | No Variance | 0 | We projected to have 37% of the rights of way done by this time. We are encountering complexities related to State Department of Transportation rights of way and easements on the Reservations, which is slowing this process down. We are focusing on the rights of way for the first construction segments so that we can get started on schedule for those parts of the project, and continue on the rest of the rights of way while we are putting installation crews to work. | 0 | We projected 8% in the baseline for this quarter...permits and rights of way are taking longer than anticipated. We are making progress and expect to be on target by next quarter. | 0 | No Variance | 0 | We projected to be 94% complete with equipment procurement by this time. We have identified the equipment and have prepared RFP's, however did not proceed until we received approval of Montana West's sub-recipient status...(which we have now received) | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-02-17 18:48 | 2011-02-17 18:48 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2011 | Q1 | Q1 - 2011 | 2059 | 2775 | TRUE | 7 | We projected to be 30% complete by this time, but have delayed equipment purchase and hiring and training of tribal crews, because of the delay associated with completion of the Environmental Assessment. | 8 | admin and Match | Projected 8%..on target. We anticipate additional expenses in this category in 11Q2 relating to legal and administrative costs for rights of way research and correspondence. | 23 | We projected to be 100% done with the EA by this quarter, and we now project completion by the end of May, providing we get timely responses from the Tribes and the State Cultural Preservation offices. | 1 | We are at 1% instead of 0 as we have had some costs for consultants. The main part of this budget will be for electronic equipment for routing, switching, and optical transport hardware. This design is being finalized and we expect to order all electronic equipment by the end of the next quarter. Final decisions regarding transport equipment will be made in 11Q2 and orders will be placed immediately once the specific hardware is identified. | 0 | We projected to have 54% of this done by this quarter. We are still encountering complexities related to easements on the Blackfeet Reservation which is slowing the process down. We are now planning on starting construction on the parts of the fiber route where we can use the existing State and County rights of way, and continuing work with the Tribes to obtain rights of way and easemetnts where necessary. | 0 | Projected 16%...EA delay is causing this effort to slip. | 0 | No Variance..projected 0 for this quarter | 3 | Projected 94%..we have delayed equipment procurement as a result of the EA taking longer than anticipated. All equipment will be obtained once the FONSI is released, which we expect in 11Q2. | 0 | Projected 5%...we have slipped network build as a result of the EA taking longer than anticipated. | 0 | Projected 12%...we have delayed equipment deployment as a result of the EA taking longer than anticipated. | 0 | Projected 12%...we have delayed network testing as a result of the EA taking longer than anticipated. | 2011-05-16 17:46 | 2011-05-16 17:46 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2011 | Q2 | Q2 - 2011 | 3093 | 3304 | TRUE | 15 | Projected 48%--All work delayed until we receive the Fonsi | 20 |  | Projected 24%--Includes In Kind Match which we will report 100% next quarter. | 90 | Projected 100%--all work completed, awaiting notification of FONSI | 80 | Final Staking | 36 | Projected 100%--delayed by EA | 2 | Projected 24%--delayed by EA | 0 | Projected 52%-delayed by EA | 36 | Projected 95%--Purchased Equipment for 2 crews, 3rd crew will not start until the early fall due to negotiations with the Blackfeet Nation, Right of Way issues and the approval of the EA. | 2 | Projected 37%--delayed by EA | 2 | Projected 26%--delayed by EA | 0 | Projected 26%--delayed by EA | 2011-08-15 17:03 | 2011-08-15 17:03 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2011 | Q3 | Q3 - 2011 | 3917 | 3797 | TRUE | 41 | Projected 56% EA delayed the start of the project but we put 100% of the in kind match into the project this quarter. The in kind match is in the ground and fully operational. This includes 105 miles of fiber with segments varying from 8-count to 96-count. | 75 | Admin & Match | Projected 32% Put 100% of In Kind match in project--it is 100% built and operational. | 100 | Projected 100% | 85 | Projected 100% We still have some final engineering to do to before the system can be lit up. | 50 | Projected 100% We are delayed with the right of ways concerning the Blackfeet Tribe but are getting things worked out. | 20 | Projected 32% We are working on permits with the various entities and have the permits we need to keep digging until the ground freezes. We are waiting on the Blackfeet to finish approving the route to preserve historical artifacts. | 0 | Projected 64% The entire project was delayed due to the EA. We are concentrating on getting the fiber buried and will work on the 700 MHZ part of the project next spring. | 54 | Projected 96% Holding off more purchases until the 3rd crew is working on Blackfeet Reservation | 14 | Projected 45% | 18 | Projected 41% | 0 | Projected 41% Delayed by EA--splicer will start next quarter. | 2011-11-07 18:22 | 2011-11-07 18:22 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2011 | Q4 | Q4 - 2011 | 5129 | 4795 | TRUE | 49 | Projected 63% Complete--We have delayed purchasing a large part of the switches and routers until a decision is made on the HIEM fiber IRU purchase. | 34 | Admin & Legal | Projected 40% Now 34%--Projected Milestone change with budget modification. | 80 | Projected 100% Complete Now 81%--We are waiting for the Blackfeet Tribe to complete their Cultural Walk Through. | 30 | Projected 100%--Waiting approval on IRU change to purchase a 10Gb link to Seattle. | 39 | Projected 100% now 40%-- Projected Milestone changed with budget modification. Right of way work remains on the Blackfeet Reservation. | 80 | Projected 40%--Most of the permits have been obtained. The rest of the project is predominately on Montana Department of Transportation right of ways where the fee is minimal or zero. Additional permits remain to be negotiated on the Blackfeet BIA roads. | 11 | Projected 64%--We have started on the site for the Arlee Building. | 70 | Projected 96%--now 94% Projected Milestone changed with budget modification. We have not purchased the equipment for the remote sites yet. | 18 | Projected 53% now 40%--Projected Milestone changed with budget modification. We have not purchased IRU for $662,948 as we are waiting on AAR decision from Washington. We were unable to start our third crew on the Blackfeet Reservation due to delays on permitting and tribal approvals. | 56 | Projected 53% Now 58%--Projected Milestone changed with budget modification. | 0 | Projected 53% Now 0%--Projected Milestone changed with budget modification. 90% of this category was moved to Equipment Deployment as part of the fiber build. We do not need to hire outside inspectors to test the fiber system. We may need to hire consultants to test the wireless systems. | 2012-02-17 18:59 | 2012-02-17 18:59 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2012 | Q1 | Q1 - 2012 | 6099 | 5652 | TRUE | 58 | Projected 66% complete. Purchase of the electronics and upstream IRU were delayed until next quarter | 40 | Admin & Legal | Projected 50% | 86 | Projected 92%. A portion of the cultural walk through is still in progress | 32 | Project 100% The bids for the purchase of the electronic hardware have been received and a decision will be made next quarter. | 44 | Projected 46%. Right of way work remains on the Blackfeet Reservation | 100 | Projected 50% Most of the permits have been obtained. | 31 | Projected 64% The Arlee Building is complete. We are negotiating with a landowner for the Elmo site and will work on the remaining sites later in the summer. | 70 | Projected 94% Most of the required equipment has been purchased for the project. | 24 | Projected 41% Construction is going along as planned but the purchase of the IRU was delayed until next quarter | 70 | Projected 63% We had not projected receiving a majority of the fiber until later in the summer. The manufacturers were able to ship sooner than expected and we have received all of the fiber needed for this construction season. | 0 | Projected 0% This budget item was moved to the main construction line item. The current crew is testing the fiber without hiring an outside contractor. | 2012-05-15 14:05 | 2012-05-15 14:05 | 6343 | 6343 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2012 | Q2 | Q2 - 2012 | 7031 | 6143 | TRUE | 70 | Projected 82% complete. Delays associated with DOT permitting on the Blackfeet have impacted the schedule. | 49 | Admin & Legal | Projected 58% complete. Shortfall is commensurate with overall project minor slippage. | 90 | Projected 100% complete. We still have cultural walk throughs to complete for part of the Blackfeet network. (Heart Butte and St. Mary/Babb) | 56 | Projected 100% complete. Electronics have been ordered but some are not yet received or invoiced. | 66 | Projected 58% complete. Rights of way remain to be obtained for tribally owned land on BIA roads on the Blackfeet. (Heart Butte route) | 100 | Projected 60% complete. Most of the permits have been obtained. | 32 | Projected 76% complete. Site preparation for Browning POP and the wireless locations remains. | 78 | Projected 96% complete. Some additional equipment may be required for the Blackfeet construction season next year. | 55 | Projected 55% complete. | 77 | Projected 88% complete. Permitting issues in Glacier County has delayed construction. | 0 | Projected 25% complete. We are able to do the testing with current employees and have not had to hire an outside contractor. | 2012-08-10 18:28 | 2012-08-10 18:28 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2012 | Q3 | Q3 - 2012 | 8041 | 6727 | TRUE | 75 | Projected 87%--Delays and stoppages on the Blackfeet have negatively impacted the schedule. | 57 | Admin & Legal | Projected 66%--Shortfall is commensurate with overall project minor slippage. | 95 | Projected 100%--We still have cultural pedestrian surveys to complete for part of the Blackfeet network. | 91 | Projected 100%--Some minor networking monitoring and transport electronics have yet to be identified and ordered. | 81 | Projected 70%--Delays and stoppages on the Blackfeet have negatively impacted the schedule. | 100 | Projected 100%--All construction permits have been obtained. | 32 | Projected 88%--Site preparation for the wireless last mile locations remains to be done. | 84 | Projected 98%--Additional wireless equipment will be needed for the final construction season next year. | 60 | Projected 68%--Delays and stoppages on the Blackfeet have negatively impacted the schedule. | 86 | Projected 91%--Delays and stoppages on the Blackfeet have negatively impacted the schedule. | 0 | Projected 38%--We are able to do the testing with current employees and have not had to hire an outside contractor. | 2012-11-26 13:03 | 2012-11-26 13:03 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2012 | Q4 | Q4 - 2012 | 8991 | 7770 | TRUE | 84 | Projected 87%--Delays and stoppages on the Blackfeet have negatively impacted the schedule. | 69 | Admin & Legal | Projected 72%--Legal Fees for the Blackfeet issue are very high | 95 | Projected 100%--Will need EA work on the Blackfeet once we determine our final route. | 99 | Projected 100%-Network design may change if we need to go with microwave at some locations on the Blackfeet due to shortage of time left in the grant period | 88 | Projected 100%--Due to work stoppage on the Blackfeet, rights of way will be needed to complete the project to St. Mary, Babb, and possibly Heart Butte. | 100 | Projected 72%--Due to work stoppage on the Blackfeet, permit applications have been delayed. | 33 | Projected 88%--Site prep for the wireless locations remains to be done. | 86 | Projected 99%-- wireless equipment will be needed for the wireless locations...overall schedule slippage due to contractor delays. | 62 | Projected 85%--Schedule has slipped due to work stoppage on the Blackfeet. | 91 | Projected 90%--No variance | 0 | Projected 90%--Overall schedule has slipped...networks cannot be tested until they are built. | 2013-02-26 17:35 | 2013-02-26 17:35 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2013 | Q1 | Q1 - 2013 | 9735 | 8402 | TRUE | 87 | Projected 93% Schedule was delayed due to negotiations with the Blackfeet Tribal Council. | 72 | Admin & Legal | Projected 80% We moved $50,000 from the Equipment Procurement category to fund the legal fees incurred due to the work stoppage on the Blackfeet Reservation. We have delayed recording any more In-Kind Labor Match to fund the increased legal fees. | 97 | Projected 100% There is still some cultural walk through work anticipated on the Blackfeet Reservation. | 99 | Projected 100% $188,142 was moved from Equipment Procurement to fund additional hardware expenses. | 91 | Projected 94% Schedule delays on the Blackfeet due to negotiations delayed rights of way research. | 100 | Projected 90% | 33 | Projected 88% The wireless sites on the Blackfeet Reservation were delayed. | 92 | Projected 100% The wireless towers and radios have not been received as of yet. We were able to spend less on heavy equipment than was anticipated and were able to move $250,000 to other budget categories. | 63 | Projected 79% A portion of the build was contracted out and we are waiting for the contractor to bill us. | 93 | Projected 95% | 100 | Projected 89% We purchased test equipment to test the fiber ourselves. The labor is in the Network Build category 2h | 2013-05-15 13:58 | 2013-05-15 13:58 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2013 | Q2 | Q2 - 2013 | 10667 | 8995 | TRUE | 89 | Projected 97%, Work stoppage on the Blackfeet impacted the overall schedule | 79 | Admin & Legal | Projected 93%, we anticipate more expense in legal due to ongoing rights of way research. | 99 | Projected 100%, CAI EA review is not complete | 100 | Projected 100% | 95 | Projected 100%, Consents are being obtained for the route to St. Mary and Babb from Browning. | 100 | Projected 100% | 33 | Projected 100%. Most site prep is for the final wireless sites and they are at the end of the project which has slipped due to work stoppage on the Blackfeet | 100 | Projected 100% | 63 | Projected 89%, overall project slippage due to work stoppage on the Blackfeet | 94 | Projected 99%, There will still be equipment deployment on the fiber route to St. Mary and Babb, schedule slipped due to work stoppage on the Blackfeet | 100 | Projected 100% | 2013-08-20 19:03 | 2013-08-20 19:03 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2013 | Q3 | Q3 - 2013 | 11305 | 9452 | TRUE | 91 | Projected 100%. (Based on the pre-extension schedule) Difficulties in obtaining rights of way has impacted the project schedule. | 80 | Admin & Legal | Projected 100%. Holding in Kind Labor Match to Fund with Program Income Match. | 100 | Projected 100%. | 100 | Projected 100%. | 96 | Projected 100%. (Based on the pre-extension schedule) Difficulties in obtaining rights of way has impacted the project schedule. | 100 | Projected 100% | 34 | Projected 100%. (Based on the pre-extension schedule) Site prep is still required for the final wireless sites and the microwave sites above Heart Butte and in East Glacier on the Blackfeet Reservation. | 100 | Projected 100% | 63 | Projected 100%. (Based on the pre-extension schedule) Difficulties in obtaining rights of way has impacted the project schedule. | 96 | Projected 100%. (Based on the pre-extension schedule) Difficulties in obtaining rights of way has impacted final equipment deployment. | 100 | Projected 100% | 2013-11-20 12:02 | 2013-11-20 12:02 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2013 | Q4 | Q4 - 2013 | 11933 | 10102 | TRUE | 92 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. After completion of the microwave to Heart Butte, what will remain is the fiber build to St. Mary/Babb on the Blackfeet Reservation, or the remaining 42.6 miles. | 82 | Admin & Legal | Projected 100%...We still have to pay for signature services and easments on the Blackfeet Reservation. | 100 | Projected 100% | 100 | Projected 100% | 98 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. After completion of the microwave to Heart Butte, what will remain is the fiber build to St. Mary/Babb on the Blackfeet Reservation, or the remaining 42.6 miles, for which we will need to obtain rights of way. | 100 | Projected 100% | 38 | Projected 100%. Overall project slippage has impacted this task. This is the site preparation for the remaining wireless sites, Evaro, Heart Butte, and St. Mary/Babb | 100 | Projected 100% | 63 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. After completion of the microwave to Heart Butte, what will remain is the fiber build to St. Mary/Babb on the Blackfeet Reservation, or the remaining 42.6 miles. | 97 | Projected 100%. Fiber build between Browning and St. Mary/Babb remains on the Blackfeet reservation. | 100 | Projected 100%. Some minor testing will be done at the completion of the last fiber build on the Blackfeet. | 2014-03-06 18:47 | 2014-03-06 18:47 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570150 | 2010 | Q4 | Q4 - 2010 | 553 | 1573 | TRUE | 1 | Zero variance | 3 | Professional Services, Fiber Route Valadation | Work effort is at 13% however not all invoices had been received to pay by end of quarter - will be caught up by next quarter | 0 | Work effort is at 35% however no invoices had been received to pay by end of quarter - will be caught up by next quarter | 0 | Work effort is at 30% however no invoices had been received to pay by end of quarter - will be caught up by next quarter | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Not started due to Environmental Assessment requirements | 0 | Not started due to Environmental Assessment requirements | 0 | Not started due to Environmental Assessment requirements | 0 | Not started due to Environmental Assessment requirements | 2011-01-26 15:35 | 2011-01-26 15:35 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2011 | Q1 | Q1 - 2011 | 1665 | 2554 | TRUE | 5 | Zero Variance | 30 | Professional Services / Fiber Route validation | Work effort at 65% (ahead of plan). Have not received all vendor invoices for payment by end of quarter. Will be included in next reporting period | 90 | Work effort complete. Awaiting final invoice. Will be included in next reporting period | 20 | Work effort at 80%. Have not received all vendor invoices for payment by end of quarter. Will be included in next reporting period | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Not started due to Environmental Assessment requirements | 0 | Not started due to Environmental Assessment requirements | 0 | Not started due to Environmental Assessment requirements | 0 | Not started due to Environmental Assessment requirements | 2011-04-29 13:35 | 2011-04-29 13:35 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2011 | Q2 | Q2 - 2011 | 2919 | 3217 | TRUE | 12 | Later than anticipated receipt of FONSI delayed starting of deployment activities. Additionally, this amount does not include $12M of encumbered amounts for equipment ordered and non-processed invoices due to receipt timing at end of this quarter | 48 | Professional Services, Fiber Route Validation | Later than anticipated receipt of FONSI delayed starting of deployment activities. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 0 | 25% of equipment has been ordered (zero variance from baseline), of which 40% has been received. However, budget execution details do not reflect any expenditures due to vendor invoices not being received in time for processing during this quarter. Will be reflected in next quarter report. | 14 | Later than anticipated receipt of FONSI delayed starting of deployment activities. | 5 | Later than anticipated receipt of FONSI delayed starting of deployment activities. | 5 | Later than anticipated receipt of FONSI delayed starting of deployment activities. | 2011-08-04 08:03 | 2011-08-04 08:03 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2011 | Q3 | Q3 - 2011 | 3957 | 3817 | TRUE | 24 | Later than anticipated start of fiber deployment due to delayed FONSI receipt and longer than anticipated equipment lead times resulted in overall expenditures being less than projected. Additionally, vendor invoice timing reduced reported expenditures. | 4 | Professional Services, Fiber Route Validation | Later than anticipated deployment start resulted in lower than projected expenditures | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 15 | Longer than anticipated equipment delivery lead times and vendor invoice timing delayed overall expenditures. This was not due to equipment shortages from manufactures but rather from overly optimistic order-to-delivery timing estimates presented in original plan. This has been (and will continue to be) adjusted for going forward by placing equipment orders earlier than originally planned. | 31 | Physical network build is on schedule from a mileage perspective however fewer than projected CAI laterals and vendor invoice timing reduced reported expenditures | 18 | Later than anticipated deployment start and longer than anticipated equipment lead times resulted in lower than projected expenditures. This was not due to equipment shortages from manufactures but rather from overly optimistic order-to-delivery timing estimates presented in original plan. This has been addressed by placing equipment orders sooner. | 18 | Later than anticipated deployment start resulted in lower than projected expenditures | 2011-11-10 12:33 | 2011-11-10 12:33 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2011 | Q4 | Q4 - 2011 | 4661 | 4303 | TRUE | 38 | Later than anticipated start of fiber deployment due to delayed FONSI receipt resulted in overall expenditures being less than projected. Additionally, vendor invoice timing reduced total expenditures for this quarter. | 6 | Professional Services | Later than anticipated deployment of equipment delayed expenditures in this category. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 51 | Slightly less than originally projected due to vendor invoice and payment timing. | 35 | Physical network build is slightly ahead of schedule from a mileage perspective. However, vendor invoice timing and payment has reduced reported expenditures for this quarter. | 29 | Later than anticipated deployment start and incomplete installation at sites for this quarter reduced the overall equipment deployment percentages. | 29 | Later than anticipated deployment of equipment delayed network testing | 2012-01-30 12:56 | 2012-01-30 12:56 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2012 | Q1 | Q1 - 2012 | 6017 | 5608 | TRUE | 49 | Later than antcipated start of fiber deployment due to delayed initial FONSI receipt resulted in overall expenditures being less than projected. Additionally, vendor invoice timing has reduced total expenditures reported. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 12 |  | Slightly behind planned schedule. Later than anticipated start of project due to initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion percentage. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. This milestone category includes ongoing professional service activities (equipment installs, site surveys), project management activites, installation mitigation activities and fiber route verifications. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 70 | Sightly ahead of schedule | 42 | Physical build is slightly ahead of schedule but vendor invoice timing and payments has reduced reported expenditures | 53 | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion percentage. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 53 | Slightly behind planned schedule. Later than anticipated start of project due to initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion percentage. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 2012-05-10 14:27 | 2012-05-10 14:27 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2012 | Q2 | Q2 - 2012 | 6877 | 6065 | TRUE | 64 | Later than antcipated start of fiber deployment due to delayed initial FONSI receipt resulted in overall expenditures being less than projected. Additionally, vendor invoice timing has reduced total expenditures reported. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 23 |  | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion percentage. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. This milestone category includes ongoing professional service activities (equipment installs, site surveys), project management activities, installation mitigation activities and fiber route verifications. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 72 | Slightly ahead of schedule | 65 | Physical build is ahead of schedule but vendor invoice timing and reconciliation has delayed payment approval and reduced reported expenditures. | 68 | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion percentage. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 68 | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion percentage. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 2012-08-07 08:37 | 2012-08-07 08:37 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2012 | Q3 | Q3 - 2012 | 7905 | 6657 | TRUE | 74 | Slightly below original plan. This is because of later than anticipated start of fiber deployment due to delayed initial FONSI receipt resulting in overall expenditures being less than projected at this time. It is anticipated that this variance will be corrected by the end of Q4-2012. | 33 |  | Slightly behind schedule. This milestone category includes ongoing project management activities and professional services activities (equipment installations, site surveys, site mitigation activities). Because of invoice timing and acceptance verifications, expenditures are delayed. It is anticipated that this milestone will continue to lag behind schedule until Q2-2013. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 75 | Zero Variance | 77 | Slightly ahead of schedule | 79 | Slightly ahead of schedule | 79 | Slightly ahead of schedule | 2012-11-15 17:06 | 2012-11-15 17:06 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2012 | Q4 | Q4 - 2012 | 9139 | 7940 | TRUE | 87 | Zero Variance | 42 |  | Slightly behind schedule. This milestone category includes ongoing project management activities and professional services activities (equipment installations, site surveys, site mitigation activities). Because of invoice timing and acceptance verifications, expenditures are delayed. It is anticipated that this milestone will continue to lag behind schedule until Q2-2013. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 91 | Slightly ahead of schedule | 90 | Slightly ahead of schedule | 89 | Slightly ahead of schedule | 89 | Slightly ahead of schedule | 2013-03-15 10:16 | 2013-03-15 10:16 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2013 | Q1 | Q1 - 2013 | 9327 | 8120 | TRUE | 90 | Zero Variance | 44 |  | Slightly behind schedule from a budget perspective. This milestone category includes ongoing project management activities and professional services activities (equipment installations, site surveys, site mitigation activities). Because of invoice timing and acceptance verifications, expenditures are delayed. It is anticipated that this milestone will continue to lag behind schedule until Q2-2013. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 92 | Zero Variance | 94 | Slightly ahead of schedule | 92 | Slightly ahead of schedule | 92 | Slightly ahead of schedule | 2013-04-28 20:41 | 2013-04-28 20:41 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2013 | Q2 | Q2 - 2013 | 10303 | 8769 | TRUE | 97 | Zero Variance | 71 | Professional Services | Slightly behind schedule from a budget perspective. This milestone category includes project management and professional services activities (equipment installation, site surveys and site mitigation). Because of invoice timing and acceptance verifications, actual invoice expenditures are delayed. If total encumbrance is included in this calculation, the milestone is at 84%. It is anticipated this milestone will continue to lag behind slightly until project closeout activities are completed. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 96 | Zero Variance | 99 | Zero Variance | 97 | Zero Variance | 97 | Zero Variance | 2013-07-30 11:27 | 2013-07-30 11:27 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2013 | Q3 | Q3 - 2013 | 11641 | 9767 | TRUE | 100 | Zero variance | 100 | Professional Services | Zero variance | 100 | Zero variance | 100 | Zero variance | 0 | N/A | 0 | N/A | 0 | N/A | 100 | Zero variance | 100 | Zero variance | 100 | Zero variance | 100 | Zero variance | 2014-01-23 07:32 | 2014-01-23 07:32 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570153 | 2010 | Q4 | Q4 - 2010 | 733 | 1766 | TRUE | 1 | Detail Below | 0 |  | N/A | 0 | N/A | 30 | Hired Network Design Engineer, Designed 10Gbps Backbone Upgrade, Began Design of Nodes and Community Anchor Institution Sites | 0 | N/A | 0 | N/A | 0 | N/A | 18 | Released Bid for 10Gbps Network Upgrade, Selected Vendor, Ordered Equipment | 14 | Hired Program Manager, Hired Contract Specialist, Issued RFP for Fiber IRU, Provided Tentative Award to Two Vendors - 1. Rhode Island, 2. Massachusetts | 0 | N/A | 0 | N/A | 2011-01-28 13:17 | 2011-01-28 13:17 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2011 | Q1 | Q1 - 2011 | 2287 | 2889 | TRUE | 23 | See Below. | 20 |  | A better valuation of "Other" which includes Community Outreach efforts, audit, etc. has allowed for a proper representation of milestone completion percentages. This has no impact on major milestones required by the grant. | 0 | N/A | 32 | The design for Rhode Island and Massachusetts Nodes has commenced. Due to an effort to increase the Beacon 2.0 Community Anchor Institution connections, an extension to the Network Design period is anticipated. This extension will bear no impact to the Beacon 2.0 Project at large. | 0 | N/A | 0 | N/A | 0 | Site preparation efforts for the Massachusetts and Rhode Island commenced. However, no funds were expended or accrued during this period. | 7 | Because of a delay in IRU execution, equipment procurement was stalled. However, Ocean State Higher Education Economic Development Administrative Network will award the Optical Equipment contract in 2011 Q2, so does not expect this delay will impact the project as a whole. | 26 | Ocean State Higher Education Economic Development Administrative Network awarded its Rhode Island and Massachusetts IRU. At contract execution, a 20% payment was made on each contract as well as a 40% payment for the Providence County, RI segment. No actual installation or miles were completed in this quarter. Based on the final fiber payment schedule, quarterly mileage milestones have been amended to better reflect the actual project plan. This has no impact on major milestones required by the grant. | 5 | The delay in equipment procurement delayed equipment deployment. | 0 | Minimal network testing of the 10Gbps equipment was performed. | 2011-05-24 17:41 | 2011-05-24 17:41 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2011 | Q2 | Q2 - 2011 | 3281 | 3403 | TRUE | 24 | See below. | 27 |  | A better valuation of "Other" which includes Community Outreach efforts, audit, etc. has allowed for a proper representation of milestone completion percentages. This has no impact on major milestones required by the grant. | 0 | N/A | 93 | The core network design for Beacon 2.0 is complete. The only foreseen need for further network design efforts result from any required Change Orders for Community Anchor Institution laterals. | 0 | N/A | 0 | N/A | 0 | Site preparation efforts for the Massachusetts and Rhode Island continue. Efforts thus far have been $0, so no funds were expended or accrued during this period. | 7 | During the quarter, OSHEAN focused its efforts on the defining the Optical Equipment Bill of Materials required for Beacon 2.0, and determining the most efficient and effective phased approach for ordering and installation. This planning delayed the actual equipment order. Optical equipment will ordered during 2011 Q3. This delay will bear no impact on the Beacon 2.0 Project at large. | 27 | Because of the payment structure of the IRUs with Cox Communications and Sidera Networks, few funds were expended on network build this quarter. However, network build efforts are on target, if not ahead of schedule. 40 miles of backbone fiber were installed during this quarter. | 5 | The delay in equipment procurement delayed equipment deployment. | 0 | There was no network testing performed during this quarter. | 2011-08-23 16:38 | 2011-08-23 16:38 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2011 | Q3 | Q3 - 2011 | 4231 | 3964 | TRUE | 33 | See Below. | 42 |  | A better valuation of "Other" which includes Community Outreach efforts, audit, etc. has allowed for a proper representation of milestone completion percentages. This has no impact on major milestones required by the grant. | 0 | N/A | 100 | The core network design for Beacon 2.0 is complete. The only foreseen need for further network design efforts result from any required Change Orders for Community Anchor Institution laterals. | 0 | N/A | 0 | N/A | 1 | Massachusetts site prep efforts are complete. Site prep at four Rhode Island node locations are complete. Two Rhode Island nodes only need racks. Preparation efforts are projected to be under budget overall. | 67 | Phase I DWDM optical equipment for the ten optical node locations was ordered. $2.2M of the order was received and verified. | 34 | One hundred and fifty eight (158) miles of Rhode Island fiber was deployed. Fifteen (15) CAI laterals were deployed. Neither backbone fiber nor CAI laterals were tested or handed over from vendor during this quarter. OSHEAN does not record miles and laterals complete until the 158 miles of fiber and 15 CAI laterals are tested, test results are approved by OSHEAN, and the fiber is handed off by Cox. | 100 | Actual % = 119% Because of an alternate valuation of equipment deployment, over 100% of the baseline projected funds have been expended. However, actual deployment efforts are only approximated at 10% completion. | 0 | There was no network testing performed during this quarter. | 2011-11-22 16:21 | 2011-11-22 16:21 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2011 | Q4 | Q4 - 2011 | 4947 | 4627 | TRUE | 51 | See Below. | 50 |  | A better valuation of "Other" which includes Community Outreach efforts, audit, etc. has allowed for a proper representation of milestone completion percentages. This has no impact on major milestones required by the grant. | 0 | N/A | 100 | The core network design for Beacon 2.0 is complete. The only foreseen need for further network design efforts result from any required Change Orders for Community Anchor Institution laterals. | 0 | N/A | 0 | N/A | 14 | Massachusetts site prep efforts are complete. Site prep at five Rhode Island node locations are complete. One Rhode Island node only requires installation of a power distribution unit. Preparation efforts are projected to be under budget overall. | 99 | The Cisco 15454 and CPT50 optical equipment was ordered; a majority of the equipment was delivered. | 56 | In Rhode Island, two hundred forty six (246) miles of backbone fiber have been installed by Cox Communications. In Providence County, one hundred seventy four (174) miles of the 246 miles were tested and accepted by OSHEAN. The remaining seventy two (72) miles were installed in Kent County. These miles of fiber are expected to be tested and turned over to OSHEAN in 2012 Q1. The fiber for thirty (38) Community Anchor Institution (CAI) laterals has been installed. OSHEAN has tested and accepted the fiber for two (2) of those CAIs. Grounding and testing of the remaining thirty six (36) CAI laterals is scheduled for 2012 Q3. In Massachusetts, Sidera Networks completed the licensing and make-ready work required for the fiber installation. Community Anchor Institution site visits continue in both states. | 100 | Actual % = 179% Because of an increase in professional service expense required to deploy the optical equipment, over 100% of the baseline projected funds have been expended. However, actual deployment efforts are only approximated at 15% completion. | 13 | Network testing of the Providence county Backbone fiber in Rhode Island was performed. | 2012-02-10 14:39 | 2012-02-10 14:39 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2012 | Q1 | Q1 - 2012 | 6251 | 5728 | TRUE | 60 | Per the baseline, the project is ahead of the 56% projected in the baseline, primarily because of the infrastructure installation being ahead of schedule. | 58 |  | While the percent complete is below that projected in the baseline, efforts are still consistent with key milestones, so are of no concern. | 0 | N/A | 100 | The core network design for Beacon 2.0 is complete. | 0 | N/A | 0 | N/A | 38 | All site preparation is complete except for some additional splice and fiber testing required at two of the MA node locations. | 100 | Actual % = 122%. Equipment procurement is greater than budget, but procurement efforts are within the time line projected in the baseline. | 65 | Network build is ahead of schedule primarily because of a mild winter which allowed the crews to continue work throughout the season. | 100 | Actual % = 241% Equipment deployment efforts are greater than budgeted. However, actual deployment efforts are consistent with the project plan. | 26 | Network testing efforts are ahead of the baseline schedule | 2012-05-22 15:28 | 2012-05-22 15:28 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2012 | Q2 | Q2 - 2012 | 7141 | 6198 | TRUE | 64 | Per the baseline, the project is behind the 68% projection due to a modification request pending. This variance will have minimal impact on the overall project time line | 63 |  | While the percent complete is below that projected in the baseline, efforts are still consistent with key milestones. | 0 | N/A | 100 | The core network design for Beacon 2.0 is complete | 0 | N/A | 0 | N/A | 39 | A majority of site preparation work is complete except for some additional splice work and fiber testing at two of the MA node locations | 100 | Actual % = 138%. Equipment procurement is greater than budget, but procurement efforts are within the time line projected in the baseline | 76 | Network build it ahead of schedule primarily because of a mild winter which allowed the crews to work throughout the season. | 100 | Actual % = 347%. Equipment deployment efforts are greater than budgeted. However, actual deployment efforts are consistent with the project plan. | 27 | Network testing is slightly behind schedule due to a modification request pending. This variance will have minimal impact on the overall project time line | 2012-08-20 07:50 | 2012-08-20 07:50 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2012 | Q3 | Q3 - 2012 | 8027 | 6720 | TRUE | 81 | Per the baseline, the project is 2% behind the projected 83% completion due to a pending project modification request. This variance will have minimal impact on the overall project time line. | 65 |  | While the % complete is below that projected in the baseline, efforts are still consistent with key milestones. | 0 | N/A | 100 | The core network design is complete | 0 | N/A | 0 | N/A | 39 | Site Preparation expenses are under budget | 100 | Actual %: 135%. Equipment procurement is greater than budget, but consistent with the time line projected in the baseline. | 76 | Network build expenses are under budget, but the work performed is consistent with the 81% completion indicated in the baseline. | 100 | Actual % = 409%. Equipment deployment is greater than budget, but consistent with the time line projected in the baseline. | 34 | Network testing expenses are under budget, but the work performed is consistent with the 67% completion indicated in the baseline. | 2012-11-26 09:50 | 2012-11-26 09:50 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2012 | Q4 | Q4 - 2012 | 9039 | 7809 | TRUE | 85 | The project is behind the 97% completion projected in the baseline due in large part to a pending route modification request. OSHEAN received approval in December, 2012. We do not expect this variance to have a large impact on the overall project time line. | 69 |  | Other expenses are below those projected in the baseline. Efforts are still consistent with key milestones. | 0 | N/A | 100 | The core network design is complete | 0 | N/A | 0 | N/A | 39 | Site Preparation expenses are under budget | 100 | Actual %: 135%. Equipment procurement is greater than budget, but consistent with the time line projected in the baseline. | 90 | Network build is below the baseline by 4% due to a fiber installation delay from the pending route modification. This is not expected to have an impact on the overall project time line. | 100 | Actual % = 472%. Equipment deployment is greater than budget, but consistent with the time line projected in the baseline. | 41 | Network testing expenses are under budget. Due to a wait on a route modification, testing is slightly behind that projected in the baseline. However, this is not projected to affect the overall project time line. | 2013-02-27 16:53 | 2013-02-27 16:53 | 7671 | 7671 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2013 | Q1 | Q1 - 2013 | 9737 | 8403 | TRUE | 87 | The project is behind the 99% completion projected in the baseline due in large part to a post award modification request that was just approved in December, 2012. We do not expect this variance to have a large impact on the overall project time line. | 64 |  | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. | 0 | N/A | 100 | The core network design is complete | 0 | N/A | 0 | N/A | 97 | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. | 92 | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. | 85 | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. | 100 | Actual % = 102%. Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. Equipment deployment is greater than budget due to implementation delays pending the post award modification approval, but will not impact the overall project budget. | 79 | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. | 2013-05-15 14:15 | 2013-05-15 14:15 | 7671 | 7671 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2013 | Q2 | Q2 - 2013 | 10491 | 8897 | TRUE | 92 | The project is behind the 100% completion projected in the baseline due to the post award modification that was approved in December 2012, and delays in completing pending IRU contracts. We do not expect this variance to impact the overall project time line. | 71 |  | Other (administrative) expenses are projected to be under budget. | 0 | N/A | 100 | The network design is complete. | 0 | N/A | 0 | N/A | 97 | The site preparation is anticipated to be under budget. | 93 | Equipment procurement remains on projected schedule. | 92 | Network build remains on projected schedule. | 100 | Actual % = 105%. Equipment deployment is greater than budget due to implementation delays as a result of the length of the prior post award modification approval. A rebudget in Q3 2013 is anticipated to shift funds between categories as to bring the percentages in this and the other categories line with the baseline. This will not impact the overall project budget. | 85 | Network testing is projected to be under budget. | 2013-08-06 12:28 | 2013-08-06 12:28 | 7671 | 7671 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2013 | Q3 | Q3 - 2013 | 11593 | 9724 | TRUE | 100 | All project installation and testing was completed by the August 31, 2013 project end date. Remaining items are related to project closeout. | 100 |  | Other (administrative) work is complete except for items relating to closeout activities. | 0 | N/A | 100 | The network design is complete. | 0 | N/A | 0 | N/A | 100 | All site preparation is complete. | 100 | All equipment procurement is complete. | 100 | All project network build is complete. | 100 | All equipment deployment is complete. | 100 | All network testing is complete | 2014-01-13 16:53 | 2014-01-13 16:53 | 7671 | 7671 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570156 | 2010 | Q4 | Q4 - 2010 | 1381 | 2394 | TRUE | 0 | As described in #1 above, the Grantee Substitution situation meant that we did not spend any funds during the fourth quarter. We have done all the preliminary groundwork to identify our staff, Environmental and Network Design consultants, and business and operational systems so that once funds are available we can catch up to our planned activities. However, for now we are behind our baseline target of 6% complete. | 0 |  | We have completed all compliance reporting on time, although without our business systems in place we haven't developed a systematic methodology to for standard reporting yet. We also have not begun staging our warehouse. Therefore, we are behind our baseline target of 5 % complete. | 0 | Although we have identified our Environmental Consultant and they are ready to go, we were unable to engage them in the fourth quarter, so we are behind our baseline target of 50% complete. | 0 | Although we have identified our Network Design Consultant and they are ready to go, we were unable to engage them in the fourth quarter, so we are behind our baseline target of 43% complete. | 0 | On track with our baseline target. | 0 | On track with our baseline target. | 0 | Until our Environmental Assessment and Network Design are well underway, we are unable to begin our Site Preparation. Therefore, we are behind our baseline target of 13% complete. | 0 | Until our Network Design is well underway, we are unable to begin our Equipment Procurement. Therefore, we are behind our baseline target of 9% complete. | 0 | Until our Environmental Assessment and Network Design are well underway, we are unable to begin our Network Build. Therefore, we are behind our baseline target of 5% complete. | 0 | Until our Environmental Assessment and Network Design are well underway, we are unable to begin our Equipment Deployment. Therefore, we are behind our baseline target of 7% complete. | 0 | With no Equipment or Network Build, we are unable to begin our Newtwork Testing. Therefore, we are behind our baseline target of 3% complete. | 2011-02-27 16:40 | 2011-02-27 16:40 | 6346 | 6346 | Centennial Board of Cooperative Educational Services | TRUE
NT10BIX5570156 | 2011 | Q1 | Q1 - 2011 | 3885 | 3781 | TRUE | 0 | As described in #1 above, the Grantee Substitution situation meant that we did not spend any funds during the fourth quarter. We have done all the preliminary groundwork to identify our staff, Environmental and Network Design consultants, and business and operational systems so that once funds are available we can catch up to our planned activities. However, for now we are behind our baseline target of 6% complete. | 0 |  | We have completed all compliance reporting on time, although without our business systems in place we haven't developed a systematic methodology to for standard reporting yet. We also have not begun staging our warehouse. Therefore, we are behind our baseline target of 5 % complete. | 0 | Although we have identified our Environmental Consultant and they are ready to go, we were unable to engage them in the fourth quarter, so we are behind our baseline target of 50% complete. | 0 | Although we have identified our Network Design Consultant and they are ready to go, we were unable to engage them in the fourth quarter, so we are behind our baseline target of 43% complete. | 0 | On track with our baseline target. | 0 | On track with our baseline target. | 0 | Until our Environmental Assessment and Network Design are well underway, we are unable to begin our Site Preparation. Therefore, we are behind our baseline target of 13% complete. | 0 | Until our Network Design is well underway, we are unable to begin our Equipment Procurement. Therefore, we are behind our baseline target of 9% complete. | 0 | Until our Environmental Assessment and Network Design are well underway, we are unable to begin our Network Build. Therefore, we are behind our baseline target of 5% complete. | 0 | Until our Environmental Assessment and Network Design are well underway, we are unable to begin our Equipment Deployment. Therefore, we are behind our baseline target of 7% complete. | 0 | With no Equipment or Network Build, we are unable to begin our Newtwork Testing. Therefore, we are behind our baseline target of 3% complete. | 2011-11-01 17:50 | 2011-11-01 17:50 | 6346 | 6346 | Centennial Board of Cooperative Educational Services | TRUE
NT10BIX5570157 | 2010 | Q4 | Q4 - 2010 | 953 | 1999 | TRUE | 3 | N/A | 0 |  | N/A | 30 | N/A | 10 | N/A | 25 | N/A | 30 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-01 11:24 | 2011-02-01 11:24 | 6432 | 6432 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2011 | Q1 | Q1 - 2011 | 1611 | 2527 | TRUE | 5 | N/A | 0 |  | N/A | 100 | N/A | 40 | N/A | 50 | N/A | 80 | N/A | 0 | N/A | 10 | N/A | 0 | We experienced delays in equipment procurement from vendors and access to 3rd party facilities. We have received all equipment and access and anticipate being able to be back on schedule by the end of the next quarter. | 0 | We experienced delays in equipment procurement from vendors and access to 3rd party facilities. We have received all equipment and access and anticipate being able to be back on schedule by the end of the next quarter. | 0 | N/A | 2011-04-28 18:36 | 2011-04-28 18:36 | 6432 | 6432 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2011 | Q2 | Q2 - 2011 | 3061 | 3288 | TRUE | 6 | Delays in the FONSI and the RFP process were the primary cause of schedule delays. With the FONSI now in place we expect to quickly recover the established schedule. | 0 |  | No Variance | 100 | No Variance | 10 | The core network design will not be able to be completed until the LTE vendor is selected. | 60 | We are currently negotiating the final right-of-way for the West Tower fiber run. We have identified the run and are working with the Regional Transportation District to finalize the ROW agreement. We expect to have the ROW issue finalized by next quarter. | 60 | Due to changes in the final site design by the vendor we were not able to identify all permits required. Now that all sites have been finalized we will identify all permits and approvals required and work to acquire them. We expect this category to be on schedule by next quarter. | 0 | Due to delays in the Environmental Assessment (EA) process we were not able to do any site-work that disturbed the surrounding environment. Now that we have received our FONSI we expect this task set to be on schedule by next quarter. | 7 | As negotiations with the LTE vendor were not finalized until late June we were not able to procure the initial set of equipment as expected. The contract will be signed in early July providing the mechanism to procure the LTE equipment and thus be on schedule. | 0 | Due to delays in the EA process we were unable to install equipment at key facilities to begin the fiber network deployment. Now that the FONSI has been received we will be on schedule by next quarter. | 0 | Due to delays in the EA and contractual process we were unable to deploy equipment as anticipated. Both issues have now been resolved and we will be on schedule. | 0 | No Variance | 2011-08-12 16:22 | 2011-08-12 16:22 | 6432 | 6432 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2011 | Q3 | Q3 - 2011 | 4049 | 3868 | TRUE | 26 | No Variance | 0 |  | No Variance | 100 | No Variance | 90 | No Variance | 90 | The right of way agreement for our last fiber-optic installation has been agreed upon in principle and awaits final passage by the appropriate governing bodies. | 80 | Due to the changes in the sites from the initial grant ADCOM has had to work with the various entities to ensure final installation agreements are met. We have completed a majority of these agreements and will be making final submissions to the proper zoning/approval boards during the next quarter. | 20 | Due to the delays in the EA process ADCOM was not able to begin site work as anticipated. Now that the FONSI has been received we are working to catch up on this aspect of the project. We have ordered all required equipment and selected the contractors to perform the required work. We do not expect this work to delay the project and will be ready to install the eNodeB sites beginning in the Spring of 2012. | 19 | Though the dollar amounts do not reflect it, ADCOM has procured almost all equipment required for the network development. In the initial budget, ADCOM was forced to estimate the charge breakdown between equipment and services. Based on the submitted bids, and finalized contract we underestimated the services cost and overestimated the equipment costs. We have submitted a reprogram/rebudget request to correct this issue. | 10 | Due to delays in the EA process and securing the necessary agreements we were unable to begin fiber construction or initialization of existing fiber. All issues have been resolved and we are making progress and do not expect delays to the overall project. | 15 | Due to delays in the EA process we were unable to install equipment at key facilities to begin the fiber network deployment. All issues have been resolved and we are making progress and do not expect delays to the overall project. | 0 | No Variance | 2011-11-15 17:16 | 2011-11-15 17:16 | 6432 | 6432 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2011 | Q4 | Q4 - 2011 | 5001 | 4676 | TRUE | 41 | No Variance | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 80 | Due to the pending route change for our final fiber installation we may need additional permits. We are actively working with both the NTIA and the vendors to finalize this change. | 60 | Due to the delays in the EA process ADCOM 911 was not able to begin site work as anticipated. We are currently focusing our efforts on completing this work and do not anticipate any delays in the overall project. | 38 | A majority of the equipment has actually been received. The only remaining key components to be received are the eNodeB radios which are due to be received in early March. Due to the structure of the prime LTE contract, which is based on key milestones, the expense for the equipment are not in sync with the receipt of the equipment. | 20 | Due to delays in the EA and changes to the network design ADCOM 911 did not begin equipment deployment as anticipated. Large scale equipment deployment will begin in March/April of 2012 and proceed throughout the summer of 2012. ADCOM 911 is still on schedule to have a completed network by the Spring of 2013. | 20 | Due to delays in the EA and changes to the network design ADCOM 911 did not begin equipment deployment as anticipated. Large scale equipment deployment will begin in March/April of 2012 and proceed throughout the summer of 2012. ADCOM 911 is still on schedule to have a completed network by the Spring of 2013. | 10 | No Variance | 2012-02-14 15:37 | 2012-02-14 15:37 | 6432 | 6432 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2012 | Q1 | Q1 - 2012 | 6351 | 5778 | TRUE | 55 | No Variance | 0 | N/A | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 67 | Due to the delays in the EA process ADCOM 911 was not able to begin site work as anticipated. We are currently focusing our efforts on completing this work and do not anticipate any delays in the overall project. In-kind Tower Match was miscalculated on Q6 PPR. This percentage adjusted to reflect actual work completed. | 66 | A majority of the equipment has actually been received. The only remaining key components to be received are the eNodeB radios which are due to be received in early March. Due to the structure of the prime LTE contract, which is based on key milestones, the expense for the equipment are not in sync with the receipt of the equipment. | 30 | Due to delays in the EA and changes to the network design ADCOM 911 did not begin equipment deployment as anticipated. Large scale equipment deployment will begin in March/April of 2012 and proceed throughout the summer of 2012. ADCOM 911 is still on schedule to have a completed network by the Spring of 2013. | 25 | Due to delays in the EA and changes to the network design ADCOM 911 did not begin equipment deployment as anticipated. Large scale equipment deployment will begin in March/April of 2012 and proceed throughout the summer of 2012. ADCOM 911 is still on schedule to have a completed network by the Spring of 2013. | 15 | Due to delays in the EA and changes to the network design ADCOM 911 did not begin equipment deployment as anticipated. Large scale equipment deployment will begin in March/April of 2012 and proceed throughout the summer of 2012. ADCOM 911 is still on schedule to have a completed network by the Spring of 2013. | 2012-05-30 14:19 | 2012-05-30 14:19 | 7504 | 7504 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2012 | Q2 | Q2 - 2012 | 7019 | 6137 | TRUE | 55 | With the partial suspension in effect, ADCOM911 will have to evaluate whether to redirect remaining BTOP funds to network expansion alone, or slow the project progress until a decision is made regarding the FirstNet deployment and spectrum availability. This decision could potentially change the focus of the project, and affect overall percentage of project completed. | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 50 | The revised EA was approved shortly before the suspension notice took effect. As such, no further site preparation took place, as noted above. Some site work performed in the previous quarters took longer than originally anticipated. Therefore, this number is lower than previously reported. | 75 | Additional LTE equipment was received during the quarter. The equipment was purchased prior to receipt of the suspension notice. Due to the structure of the prime LTE contract, which is based on key milestones, the expenses for the equipment are not in sync with the receipt of the equipment. No additional network equipment was procured for backhaul as the revised EA was approved shortly before the suspension notice took effect. | 35 | One additional CAI was lit-up during the quarter, and a second CAI has equipment installed, pending configuration. Due to delays in the EA and changes to the network design ADCOM 911 did not begin further equipment deployment as anticipated. Large scale equipment deployment was scheduled to begin in March/April of 2012 and proceed throughout the summer of 2012. However, the approved EA was received just prior to the suspension notice, temporarily halting further network build efforts. | 30 | One additional CAI was lit-up during the quarter, and a second CAI has equipment installed, pending configuration. Due to delays in the EA and changes to the network design ADCOM 911 did not begin further equipment deployment as anticipated. Large scale equipment deployment was scheduled to begin in March/April of 2012 and proceed throughout the summer of 2012. However, the approved EA was received just prior to the suspension notice, temporarily halting further equipment deployment efforts. | 20 | The fiber transport network has been tested thoroughly to the CAI locations where the work is complete. Those CAI locations are now actively using the transport network. Additional testing is now taking place with the microwave connection to another CAI. The LTE network was set for further expansion to multiple sites during the quarter. The network performance would be tested at each site as the equipment was deployed. However all work related to the LTE system was halted upon receipt of the suspension notice. No further network testing has been performed since that time. | 2012-08-10 16:43 | 2012-08-10 16:43 | 7504 | 7504 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2012 | Q3 | Q3 - 2012 | 7315 | 6287 | TRUE | 60 | Since the partial suspension is still in effect, ADCOM 911 has had to proceed cautiously with our funding. During the third quarter, we only focused on developing the links in the Broadband Network that could be used whether the LTE project moves forward or not. This took some time to assess which links should be prioritized, so as not to waste time or funding on sites prematurely. Because of this our project continued to see progress, but at a slower pace than previous quarters. | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 55 | Site improvement work at Cherokee resumed, and is about 2/3 of the way complete now. At three additional sites, microwave backhaul links were installed and will be ready for use when the network equipment is installed. At one site, the network equipment was installed, and is ready for the microwave link to be installed. At another site, the soil analysis was completed and the parts and materials received for the installation of a monopole. | 78 | We continued to receive some equipment from our original LTE contract during the quarter. All of this equipment was ordered and purchased prior to the suspension notice. We currently have all network equipment necessary to activate some of the core fiber transport sites. We anticipate we will need to purchase additional equipment whether we move forward with LTE or with a Broadband Network only. However, we won't know which equipment until we are advised whether LTE will move forward or not. | 45 | One CAI - Southwest Adams County Fire - had a microwave link installed last quarter, but was pending further network configuration. The network equipment has now been configured, and the site is ready for active use by the CAI. Three additional microwave links were installed, and are pending the installation and configuration of the network equipment. A fourth site has the network equipment installed and configured, and is now pending the installation of the microwave link. A new segment of fiber cabling was installed as the first phase of a larger fiber cable build. | 37 | Three new microwave links were installed and configured, and are ready for network equipment to be installed. One new network switch was installed and configured, and is ready for the microwave link to be installed. | 25 | For the new microwave links that were installed, initial testing of the microwave paths and equipment was completed. Further testing will be completed when those sites have network devices connected. | 2012-10-04 13:27 | 2012-10-04 13:27 | 7504 | 7504 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2012 | Q4 | Q4 - 2012 | 8683 | 7498 | TRUE | 65 | Since the partial suspension is still in effect, ADCOM 911 has had to proceed cautiously with our funding. During the fourth quarter, we only focused on developing the links in the Broadband Network that could be used whether the LTE project moves forward or not. This took some time to assess which links should be prioritized, so as not to waste time or funding on sites prematurely. Because of this our project continued to see progress, but at a slower pace than previous quarters. | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 60 | Site improvement work at Cherokee continued and is about 3/4 of the way complete now. A microwave backhaul link was installed at two additional sites. One microwave link installed during Q3 2012 was configured and placed into production mode. The foundation was poured to support a monopole at another site. | 80 | All LTE equipment ordered under the original contract has now been received. All LTE equipment was ordered and purchased prior to the suspension notice. The remainder of equipment to be purchased will be determined once we know if we can proceed with the LTE project, or re-purpose the funds to general broadband deployment. | 50 | One new microwave link between two sites was installed and is ready for configuration to place into production use. Another microwave installed in Q3 2012 was configured and is now actively providing data services between two major aggregation sites. | 40 | A new microwave was installed at two sites. Network switches were installed at two other sites where the microwaves were installed during Q3 2012. | 30 | For the new microwave links that were installed, initial testing of the microwave paths and equipment was completed. Further testing will be completed when those sites have network devices connected. | 2013-02-08 16:54 | 2013-02-08 16:54 | 7504 | 7504 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2013 | Q1 | Q1 - 2013 | 9667 | 8366 | TRUE | 68 | Since the partial suspension is still in effect, ADCOM 911 has had to proceed cautiously with our funding. During the fourth quarter, we only focused on developing the links in the Broadband Network that could be used whether the LTE project moves forward or not. This took some time to assess which links should be prioritized, so as not to waste time or funding on sites prematurely. Because of this our project continued to see progress, but at a slower pace than previous quarters. | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 65 | Site remodel work at Cherokee completed. The monopole at Station 54 was installed, and the microwave equipment for the link between Sta 54 and the Brighton Water Tank was installed. The generator for our broadband equipment shelter was placed online. | 80 | All LTE equipment ordered under the original contract has now been received. All LTE equipment was ordered and purchased prior to the suspension notice. The remainder of equipment to be purchased will be determined once we know if we can proceed with the LTE project, or re-purpose the funds to general broadband deployment. There were no significant equipment purchases during Q1 of 2013, hence the percentage remaining at 80%. | 55 | Equipment for one new microwave link between Station 54 and the Brighton Water Tank has been installed | 42 | Microwave equipment was deployed at the Station 54 site, as well as the Brighton Water Tank Site. Some of the networking equipment we had anticipated installing has not been deployed, and this is why there is a difference from Q4 2012 to Q1 2013. | 35 | Microwaves at Station 54 and the Brighton Water Tanks were aligned and tested for line of sight. The Jefferson County link has not yet been completed, therefore there is a difference in the values between our Q4 2012 projections, and the percent complete reported this quarter. | 2013-05-09 15:12 | 2013-05-09 15:12 | 7688 | 7688 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2013 | Q2 | Q2 - 2013 | 10257 | 8738 | TRUE | 65 | Since the partial suspension is still in effect, ADCOM 911 has had to proceed cautiously with our funding. During the second quarter, we only focused on developing the links in the Broadband Network that could be used whether the LTE project moves forward or not. This took some time to assess which links should be prioritized, so as not to waste time or funding on sites prematurely. Because of this our project continued to see progress, but at a slower pace than previous quarters. | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 68 | The electrical work for Fire Station 54 was completed, and equipment can now be located and activated at that site. An aggregation router was installed and configured at the Justice Center site, which will interconnect multiple microwave and fiber paths. | 80 | All LTE equipment ordered under the original contract has now been received. All LTE equipment was ordered and purchased prior to the suspension notice. The remainder of equipment to be purchased will be determined once we know if we can proceed with the LTE project, or re-purpose the funds to general broadband deployment. There were no significant equipment purchases during Q2 of 2013, hence the percentage remaining at 80%. | 60 | The aggregation router was installed at the Justice Center site, which will interconnect multiple microwave and fiber paths. | 45 | The aggregation router was installed at the Justice Center site, which will interconnect multiple microwave and fiber paths. | 40 | The aggregation router at the Justice Center site was configured, and we verified connectivity from that router to the existing routers on the network. | 2013-07-29 19:02 | 2013-07-29 19:02 | 7504 | 7504 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2013 | Q3 | Q3 - 2013 | 10917 | 9162 | TRUE | 66 | During the 3rd quarter of 2013 we added 3 new microwave hops to the broadband network. This was the only significant work completed during this time period due to the uncertainty of grant funding. | 0 |  | N/A | 100 | No Variance. If the route modification is approved by the NTIA ADCOM911 may need to perform additional Environmental Assessments and the percent complete may change. | 100 | No Variance. If the route modification is approved by the NTIA the Network Design will be re-visited and the percent complete may change. | 100 | No Variance | 100 | No Variance | 68 | With the uncertainty of grant funding during Q3 of 2013 ADCOM911 did not award a contract to complete the site security measures. | 80 | There were no significant equipment purchases during Q3 of 2013, hence the percentage remaining at 80%. | 62 | Three new microwave paths were installed and the Justice Center, Front Range Airport, and the Hoyt tower. The fiber installation at the Cherokee Site has not been completed due to a lengthy easement process with the City of Northglenn. | 46 | Three new microwave paths were installed and the Justice Center, Front Range Airport, and the Hoyt tower. | 42 | Three new microwave paths were installed, connected and tested at the Justice Center, Front Range Airport, and the Hoyt tower. | 2013-10-23 16:29 | 2013-10-23 16:29 | 7688 | 7688 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2013 | Q4 | Q4 - 2013 | 11899 | 10067 | TRUE | 71 | During the third quarter of 2013 we reached an agreement with FirstNet for use of the LTE spectrum, completed the route modification, and the revised budget. ADCOM also selected a vendor for site security. | 0 |  | N/A | 100 | No Variance. If the route modification is approved by the NTIA ADCOM911 may need to perform additional Environmental Assessments and the percent complete may change. | 100 | No Variance. If the route modification is approved by the NTIA the Network Design will be re-visited and the percent complete may change. | 100 | No Variance | 100 | No Variance | 70 | ADCOM selected a vendor to do the site security work, however the work did not begin until Q1 of 2014. | 80 | There were no significant equipment purchases during Q4 of 2013, hence the percentage remaining at 80%. | 62 | There was no significant progress made on the network during Q4 of 2013. | 46 | There was no significant equipment deployment made during Q4 of 2013. | 42 | There was no significant network testing during Q4 of 2013. | 2014-02-26 15:47 | 2014-02-26 15:47 | 7688 | 7688 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570158 | 2010 | Q4 | Q4 - 2010 | 973 | 2020 | TRUE | 0 | Zero variance. | 0 |  | N/A | 0 | Zero variance. EA procurement completed this quarter. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 2011-02-04 12:00 | 2011-02-04 12:00 | 6478 | 6478 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2011 | Q1 | Q1 - 2011 | 1869 | 2680 | TRUE | 1 | zero variance | 0 |  | N/A | 60 | zero variance | 0 | zero variance | 0 | zero variance | 5 | The Authority has begun outreach to relevant permitting bodies, regulatory agencies, and other stakeholders with oversight responsibilities. However, the Authority will delay formally submitting for most permits and approvals until the conclusion of contract negotiations and the completion of a draft EA. Progress on this milestone will thus be slowed through this calendar year. | 0 | zero variance | 0 | zero variance | 0 | zero variance | 0 | zero variance | 0 | zero variance | 2011-05-02 18:52 | 2011-05-02 18:52 | 6479 | 6479 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2011 | Q2 | Q2 - 2011 | 3019 | 3267 | TRUE | 2 | Towards the end of the quarter, the County Counselâ€™s Office notified the The overall project completion is affected by negotiations being put on hold pending County Counsel's evaluation. | 0 |  | N/A | 80 | Zero variance | 0 | Zero variance | 2 | Progress on securing Rights of Way is pending contract award and design review | 6 | The Authority has continued outreach to relevant permitting bodies, regulatory agencies and other stakeholders with oversight responsibilities. However, the Authority will delay formally submitting for most permits and approvals until the completion of the draft EA. Progress on this milestone will thus be slowed through this calendar year. | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 2011-08-11 14:21 | 2011-08-11 14:21 | 6478 | 6478 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2011 | Q3 | Q3 - 2011 | 3497 | 3519 | TRUE | 2 | Due to canceled procurement. | 0 |  | N/A | 40 | Due to canceled procurement, efforts need to be re-initiated. | 2 | Internal engineering work on system design, variance due to canceled procurement. | 0 | Due to canceled procurement, efforts need to be re-initiated. | 0 | Due to canceled procurement, efforts need to be re-initiated. | 0 | Due to canceled procurement. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 2011-10-27 11:58 | 2011-10-27 11:58 | 6478 | 6478 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2011 | Q4 | Q4 - 2011 | 4705 | 4354 | TRUE | 4 | Due to canceled procurement. | 0 |  | N/A | 40 | Due to canceled procurement. The Authority completed the procurement process for a new environmental firm to analyze the prescriptive site list included in the new RFP. Authority's new site list includes 100 of the sites that were previously included in the prior Environmental Assessment. | 25 | Due to canceled procurement. Authority has developed a new design based on the the prescriptive site list of 255 sites included in the new RFP. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Zero variance. | 2012-01-30 15:27 | 2012-01-30 15:27 | 6478 | 6478 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2012 | Q1 | Q1 - 2012 | 5915 | 5557 | TRUE | 4 | Initiated negotiations for system contract; executed project and construction management contract; executed environmental services contract for the analysis of 255 LTE sites. | 0 |  | N/A | 45 | Completed site visits, drafting technical reports. | 25 | Due to cancelled procurement. | 0 | Due to cancelled procurement. | 1 | Working on site agreements. | 0 | Due to cancelled procurement. | 0 | Due to cancelled procurement. | 0 | Due to cancelled procurement. | 0 | Due to cancelled procurement. | 0 | Zero variance | 2012-05-02 17:19 | 2012-05-02 17:19 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2012 | Q2 | Q2 - 2012 | 6849 | 6051 | TRUE | 5 | Procurement process on hold. Progress made on environmental assessment and site analysis/valuations. | 0 |  | N/A | 48 | Completed and reviewed first draft NEPA environmental assessment/ CEQA initial study document outline, along with all related technical reports. Outreach to key stakeholders, including local land use agencies and conservation groups, continued. The technical team began incorporating the initial environmental findings into the proposed system design in order to reduce or eliminate any potential impacts to environmental resource areas. | 25 | Procurement process on hold. | 5 | Conducted detailed site and land valuation analysis. | 1 | Working with legal counsel to plan for permitting of 255 sites. | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 2012-08-03 12:29 | 2012-08-03 12:29 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2012 | Q3 | Q3 - 2012 | 7823 | 6615 | TRUE | 6 | Procurement has been terminated to be restarted separately for the LTE and LMR systems. | 0 |  | N/A | 55 | Commenced evaluation of the LTE sites for California Environmental Quality Act (CEQ) exemption eligibility under California Assembly Bill 1486 and assess a modified approach to the NEPA and CEQA documenation to provide more clairty. | 25 | Preparation of new RFP for LTE system is underway | 5 | Conducted detailed site and land valuation analysis | 3 | Working with legal counsel to plan for permitting of 255 sites | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 2012-11-09 16:03 | 2012-11-09 16:03 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2012 | Q4 | Q4 - 2012 | 8647 | 7468 | TRUE | 7 | The RFP draft for the LTE system should be substantially complete for FirstNet review by Feb, 2013. The RFP for the LMR system was released in Oct, 2012 and vendor proposals are being evaluated; contract execution is expected by Jun, 2013. | 0 |  | N/A | 58 | Continued evaluation of the LTE sites for California Environmental Quality Act (CEQ) exemption eligibility under California Assembly Bill 1486 and assess a modified approach to the NEPA and CEQA documenation to provide more clairty. | 25 | Preparation of a new RFP for the LTE system is in progress. | 5 | Continuing detailed site and land valuation analysis. | 3 | Working with legal counsel to plan for permitting of 255 sites | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 2013-02-01 12:17 | 2013-02-01 12:17 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2013 | Q1 | Q1 - 2013 | 9705 | 8386 | TRUE | 7 | After obtaining limited statutory exemption from CEQA, LA-RICS requested the NTIA's permission to submit CEQA documents separately from NEPA documents. The modified approach will facilitate the environmental review process while complying with all requirements. LA-RICS continues to wait for approval. Preparation of the RFP for the LTE system could not proceed at full speed until terms and conditions of the spectrum lease agreement are finalized. | 0 |  | N/A | 59 | Continued CEQA exemption eligibility assessment while NTIA reviews proposal to submit documents separately from NEPA. | 26 | Continued preparation of RFP for the LTE system. | 5 | Continued detailed site and land valuation analysis. | 3 | Worked with legal counsel to plan for permitting of 255 sites | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 0 | Procurement process on hold. | 2013-05-13 16:09 | 2013-05-13 16:09 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2013 | Q2 | Q2 - 2013 | 10151 | 8642 | TRUE | 3 | The sites list was reduced to CEQA-compliant sites to avoid further delays that may compromise the project schedule. |  |  |  | 59 | Continue CEQA exemption applicability screening and eligibility assessment including additional field surveys and record research on baseline and replacement sites. Discussed NEPA approach with NTIA and prepared a preliminary draft project narrative description. | 27 | The RFP for the LTE system is almost complete. | 7 | Conducted detailed site and land valuation analysis; will begin site use agreement consultation with cities. | 3 | Working with legal counsel to plan for permitting of LTE sites. | 0 | Pending release of LTE RFP | 0 | Pending release of LTE RFP | 0 | Pending release of LTE RFP | 0 | Pending release of LTE RFP | 0 | Pending release of LTE RFP | 2013-07-24 15:28 | 2013-07-24 15:28 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2013 | Q3 | Q3 - 2013 | 11191 | 9377 | TRUE | 3 | The procurement process for the LTE contractor is well on its way, proposal evaluation to follow soon. Work continues on community outreach to potential LTE sites. Environmental assessment work continues. | 0 |  | N/A | 65 | Completed screening and eligibility assessment of 232 proposed sites for qualified CEQA exemption (Cal. Pub. Res. Code Â§ 21080.25). Developed construction management requirements (CMR) for inclusion in the LTE RFP as project components. Finalized a draft Project Description with NTIA for the initiation of consultation with federal resource agencies. Started National Historic Preservation Act (NHPA) Section 106 consultation coordination with California State Office of Historic Preservation (SHPO). Consulted with State Native American Heritage Commission and contacted state-acknowledged tribes and interested parties about the proposed LTE project. | 27 | Pending contract execution with selected LTE contractor. | 8 | Conducting detailed site and land valuation analysis; continued consultation with cities on site use agreement. | 3 | Working with legal counsel to plan for permitting of LTE sites. | 0 | Pending contract execution with selected LTE contractor. | 0 | Pending contract execution with selected LTE contractor. | 0 | Pending contract execution with selected LTE contractor. | 0 | Pending contract execution with selected LTE contractor. | 0 | Pending contract execution with selected LTE contractor. | 2013-11-05 13:57 | 2013-11-05 13:57 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2013 | Q4 | Q4 - 2013 | 11911 | 10079 | TRUE | 4 | The cancellation of two previous procurements for an LTE contract continued to delay the project's ability to start and meet its milestones. Additional time was lost when the NTIA suspended LTE-related activities in May, 2012 until it was lifted in Aug, 2013. Finally, the project is on the verge of concluding negotiations with the lead bidder. During the quarter, LA-RICS submitted to FirstNet the Key Learning Conditions required by the Spectrum Manager Lease Agreement, as well as continued discussions on how the LA-RICS system would work in concert with the Nationwide Public Safety Broadband Network. | 0 |  | N/A | 78 | Completed preliminary working draft of Chapters 1 and 2 NEPA Environmental Assessment (EA). Continue to prepare the preliminary working draft Environmental Assessment and preliminary working draft Biological Assessment to inform NTIAâ€™s ESA Section 7 informal consultation with the US Fish and Wildlife Service (USFWS). Continue the consultation coordination with federal land-administering agencies for the proposed LTE project sites. | 27 | Pending contract execution with selected LTE system contractor. | 9 | Continued consultation with cities on site use agreement. | 3 | Continued working with legal counsel to plan for permitting of LTE sites. | 0 | Pending contract execution with selected LTE system contractor. | 0 | Pending contract execution with selected LTE system contractor. | 0 | Pending contract execution with selected LTE system contractor. | 0 | Pending contract execution with selected LTE system contractor. | 0 | Pending contract execution with selected LTE system contractor. | 2014-02-27 15:49 | 2014-02-27 15:49 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT11BIX5570001 | 2010 | Q3 | Q3 - 2010 | 2429 | 2960 | TRUE | 0 | n/a | 0 |  | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 2011-06-27 12:06 | 2011-06-27 12:06 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2010 | Q4 | Q4 - 2010 | 2423 | 2957 | TRUE | 0 | As described in #1 above, the Grantee Substitution situation meant that we did not spend any funds during the fourth quarter. We have done all the preliminary groundwork to identify our staff, Environmental and Network Design consultants, and business and operational systems so that once funds are available we can catch up to our planned activities. However, for now we are behind our baseline target of 6% complete. | 0 |  | We have completed all compliance reporting on time, although without our business systems in place we haven't developed a systematic methodology to for standard reporting yet. We also have not begun staging our warehouse. Therefore, we are behind our baseline target of 5 % complete. | 0 | Although we have identified our Environmental Consultant and they are ready to go, we were unable to engage them in the fourth quarter, so we are behind our baseline target of 50% complete. | 0 | Although we have identified our Network Design Consultant and they are ready to go, we were unable to engage them in the fourth quarter, so we are behind our baseline target of 43% complete. | 0 | On track with our baseline target. | 0 | On track with our baseline target. | 0 | Until our Environmental Assessment and Network Design are well underway, we are unable to begin our Site Preparation. Therefore, we are behind our baseline target of 13% complete. | 0 | Until our Network Design is well underway, we are unable to begin our Equipment Procurement. Therefore, we are behind our baseline target of 9% complete. | 0 | Until our Environmental Assessment and Network Design are well underway, we are unable to begin our Network Build. Therefore, we are behind our baseline target of 5% complete. | 0 | Until our Environmental Assessment and Network Design are well underway, we are unable to begin our Equipment Deployment. Therefore, we are behind our baseline target of 7% complete. | 0 | With no Equipment or Network Build, we are unable to begin our Network Testing. Therefore, we are behind our baseline target of 3% complete. | 2011-06-02 10:18 | 2011-06-02 10:18 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2011 | Q1 | Q1 - 2011 | 2039 | 2765 | TRUE | 8 | The 8% is lower than the baseline completion of 14%, but that number is slightly misleading in that it includes 7% of in-kind match which was booked this quarter. The actual spending was about 1%, which is less than anticipated because of the delays in funding described in #3 below. | 0 |  | With no equipment purchases, we have not begun leasing or staging our warehouse. Therefore, we have not achieved our baseline target of 13% complete. | 0 | There was no spending related to the Environmental Assessment this quarter, although the baseline shows that we should be100% complete. We had not yet received the Environmental Consultant's invoice by March 31, but it will be paid in April and May, so it will be 100% complete in the next quarter. | 3 | The baseline report shows 86% complete by this quarter. Because of the described delays, the "logical network design" is significantly complete, but the physical design has not yet been started as a design/build firm has not yet been procured. | 92 | The baseline number for this quarter is 0% because it anticipated booking an in-kind match in future quarters. This match was booked during the current quarter which puts us ahead of the baseline report. | 0 | Consistent with baseline target of 0%. | 0 | Until the Environmental Assessment is complete and Network Design is underway, we are unable to begin our Site Preparation. Therefore, we are behind our baseline target of 23% complete. | 0 | Until our Network Design is well underway, we are unable to begin our Equipment Procurement. Therefore, we did not achieve our baseline target of 18% complete. | 1 | The baseline total was13% for this quarter, which includes project overhead for the build. As we have not begun the actual build phase of the project yet, the 1% shown is the overhead spending for the overall project through this quarter. | 0 | Until Equipment Procurement has started and the Network Design is fundamentally complete, we are unable to begin our Equipment Deployment. Therefore, we did not meet our baseline target of 16% complete. | 0 | With no Equipment or Network Build, we are unable to begin our Network Testing. Therefore, we did not achieve our baseline target of 9% complete. | 2011-05-16 11:53 | 2011-05-16 11:53 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2011 | Q2 | Q2 - 2011 | 2907 | 3211 | TRUE | 10 | The 10% is behind the baseline amount of 27% because of the delays that we've encountered in achieving FONSI (described below). Projected baseline spending included site preparation, network build and equipment deployment costs, etc, none of which we were able to start this quarter without the FONSI. Note that this amount includes the in-kind match that was booked last quarter. | 0 |  | Without the equipment RFP being complete, we have not begun leasing or staging our warehouse. Therefore we did not achieve our baseline target of 23% complete. | 91 | This amount is slightly behind the baseline projected 100% because the Environmental Consultant is withholding their final invoice until the FONSI has been received. | 74 | The projected baseline amount for network design was to be 100% complete this quarter. The 74% shown here is for the design of the "logical network" which is essentially complete. The remaining expense for network design will come from the design/build contractor's physical network design. This was not started this quarter because the design/build contractor had not yet been awarded. | 92 | The baseline number for this quarter was 46% because it anticipated booking this match over two quarters. Instead, the entire match was booked in the prior quarter, which puts us ahead of the baseline target. | 0 | This number is behind the baseline target of 11% because the design/build contractor had not yet been hired during this quarter so final design for permits, etc. was not yet ready. | 0 | This is behind our baseline target of 35%. Until the FONSI has been issued, we are unable to begin site preparation. | 1 | The layer 2/3 equipment RFP was not completed this quarter. Therefore the only equipment purchased was what was required to upgrade the legacy system. This is behind our baseline projection of 29%. | 3 | The baseline target was 23% for this quarter, which includes project overhead for the build. As we have not begun the actual build phase of the project yet, the 3% shown is the overhead spending plus the PMO expense for the overall project through this quarter. | 0 | Until equipment procurement is completed and the network design is fundamentally complete, we are unable to begin our equipment deployment. Therefore, we did not meet our baseline projection of 26%. | 0 | With no network build, we are unable to begin our network testing. Therefore, we did not achieve our baseline target of 18% complete. | 2011-08-01 18:02 | 2011-08-01 18:02 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2011 | Q3 | Q3 - 2011 | 4175 | 3936 | TRUE | 17 | The 17% complete is behind the baseline projection of 41% complete because of the delays encountered with the grant transfer and with the statewide Environmental Assessment process. However, once we received our FONSI, we were allowed to begin post-FONSI expenditures this quarter, as described in the accomplishments above. | 0 |  | The largest projected expense for this category was the leasing of warehouse space for staging fiber and equipment. As no equipment was purchased during this quarter, there is no need yet for leasing space. This expense has not been used and is behind the baseline projection of 35% because of the delays encountered with the grant transfer and in achieving the FONSI. | 100 | The EA was approved, so we received the final invoice from our environmental contractor. The actual amount paid was actually slightly above the projected amount, so this item ended up at 101% based on expenditure. This step is now complete and matches the baseline completion. | 94 | The projected baseline amount for network design was to be 100% complete by this quarter. This logical network and network equipment design is complete, but will be fine-tuned throughout the progression of the design/build process. | 92 | The 92% complete matches the baseline number as we have booked this match amount for rights of way from CDOT. | 0 | The physical design is ongoing, so we have not yet spent any money for construction permits and approvals. This is behind our baseline projection of 25% complete because of the delays encountered with the grant transfer and in achieving the FONSI. | 0 | The physical design is ongoing, so we have not yet spent any money for site preparation. This is behind our baseline projection of 44% complete because of the delays encountered with the grant transfer and in achieving the FONSI. | 1 | This 1% represents the purchase of equipment to upgrade the legacy network. The layer 2-3 equipment contract has been awarded, but as of the end of the quarter, no equipment had actually been purchased. This is behind our baseline projection of 40% complete because of the delays encountered with the grant transfer and in achieving the FONSI. Please note that in the budget categories (last page of this report) layer 2-3 equipment is part of the Construction category. | 12 | The baseline projection was 35% for this quarter, which includes all network build activities in addition to the cost of IRUs, Project Management and overhead costs for the project. Although no physical build was started, we did lease three IRUs in addition to the purchase and upgrade of the legacy Centennial BOCES network. Additional costs were for the PMO, and other related costs. Overall, we are behind the baseline projection this quarter because of the delays encountered with the grant transfer and in achieving the FONSI. | 0 | As no layer 2-3 equipment was purchased by the end of the quarter, there were no costs for equipment deployment. This is behind our baseline projection of 37% because of the delays encountered with the grant transfer and in achieving the FONSI. | 0 | As no layer 2-3 equipment was purchased by the end of the quarter, there were no costs for network testing. This is behind our baseline projection of 37% because of the delays encountered with the grant transfer and in achieving the FONSI. | 2011-11-21 10:31 | 2011-11-21 10:31 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2011 | Q4 | Q4 - 2011 | 5397 | 5080 | TRUE | 27 | The 27% complete is behind the baseline projection of 50% complete because of the delays encountered with the grant transfer and with the statewide Environmental Assessment process. However, significant steps in obtaining new IRUs and our first shipments of equipment and fiber have us ready to move forward with the actual network construction. | 0 |  | The largest projected expense for this category was the leasing of warehouse space for the staging and testing of equipment. This space was identified and negotiated, but the lease doesn't start until January (the next quarter). So, 0% was spent versus our 44% completion due to not needing the space until the equipment arrived. | 100 | The FONSI was obtained and this milestone is complete. | 100 | Although the logical and network equipment design was completed this quarter, it will continue to be fine-tuned throughout the design/build process. | 92 | The 92% complete is slightly behind the baseline projection of 95% as additional rights of way are under negotiation, but have not yet been finalized. | 0 | The 0% is behind our baseline projection of 35% complete because of the delays encountered with the grant transfer and achieving the FONSI. Permit spending has begun, but thus far at a very low dollar amount. | 0 | With the physical design being finalized, no money has yet been spent on site preparation. This is behind our baseline projection of 55% complete because of the delays encountered with the grant transfer and in achieving the FONSI. | 24 | While 24% is behind the baseline projection of 50% complete, our first order of Cisco layer 2 - 3 equipment was ordered and received and is currently being tested. | 21 | The baseline projection was 44% for this quarter, which includes all network build activities in addition to the cost of IRUs, Project Management, and other administrative costs for the project. Although no physical build was started, we did issue 6 major RFPs for statewide infrastructure and signed a major IRU for 511 miles. Overall, we are behind our baseline projections this quarter because of the delays encountered with the grant transfer and in achieving the FONSI. | 6 | The 6% is behind our baseline projection of 47% complete because of the delays encountered with the grant transfer and achieving the FONSI. | 0 | There have been no costs for network testing yet, which is behind the 40% baseline projection because of the delays encountered with the grant transfer and achieving the FONSI. | 2012-02-29 13:22 | 2012-02-29 13:22 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2012 | Q1 | Q1 - 2012 | 6071 | 5635 | TRUE | 32 | The 32% is behind the baseline projection of 60% complete because of the delays encountered with the grant transfer and with the statewide Environmental Assessment process. However, with more IRUs procured and equipment received, our peering ring is almost complete. Preparation for network construction is on target and build will begin in the third week of April. | 9 |  | During this quarter, we did obtain a testing and staging warehouse to begin equipment deployment. This facility is the main component of the "other" category. This is behind our baseline projection of 55% complete. | 100 | The FONSI was obtained and this milestone is complete. | 100 | Although the logical and network equipment design is complete, it will continue to be fine tuned throughout the design/build process | 92 | The 92% complete is slightly behind the baseline projection of 97% complete. However, the final negotiations were completed with CDOT, so this will be complete in the next quarter. | 23 | Although behind the baseline projection of 48% complete, permitting has seen much activity in the last quarter. Permits were obtained by our design/build contractor, G4S Technologies, to enable us to begin construction at five separate statewide locations in April. We should be caught up to the baseline projection by the end of the third quarter of 2012. | 0 | Site preparation activities did begin last quarter, however, invoices were not received in time to book before quarter end. This is behind our baseline projection of 70% complete because of the delays encountered with the grant transfer and in achieving the FONSI. | 34 | Our second order of Cisco Layer 2-3 equipment was ordered and received this quarter, and is currently being tested at our staging warehouse. However, we are behind our baseline projection of 63% complete. | 27 | The baseline projection was 55% this quarter, which includes all network build activities in addition to the cost of IRUs, Project Management and other administrative costs for the project. While no physical build was started (our schedule calls for it to start the during the third week of April), we did procure 593 miles of dark fiber via IRUs for our network peering ring. Overall, we are behind our baseline projections this quarter because of the delays encountered with the grant transfer and in achieving the FONSI. | 12 | The 12% complete is behind our baseline projection of 59% due to the delays encountered with the grant transfer and achieving the FONSI. | 0 | With the peering ring not complete and the laterals not yet under construction, there have been no costs for network testing. This is behind our baseline projection of 51% complete. | 2012-05-14 18:11 | 2012-05-14 18:11 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2012 | Q2 | Q2 - 2012 | 7273 | 6264 | TRUE | 46 | The 46% project completion is behind the baseline projection of 74% complete because of the delays encountered with the grant transfer and with the statewide Environmental Assessment process. However significant progress was made this quarter in the network build. The peering ring was deployed and there was significant construction throughout the state to begin laying conduit and fiber. | 16 |  | The costs of our outside testing and warehouse facilities is behind our baseline projection of 70%. The facilites were just obtained in the last two quarters and at a savings over the original baseline projection. | 100 | The FONSI was obtained and this milestone is complete. | 100 | Although the logical and network equipment design is complete, the design will continue to be fine-tuned throughout the design/build process. | 92 | Rights of way are behind the 99% baseline projection. However, the CDOT agreement that was signed and the rights of way provided had a value that was higher than what was used in the original baseline projection, and this will be reflected in our budget reprogram that will be submitted this quarter. | 100 | Although the permitting process has not yet been completed, based on dollars spent, the original baseline estimate was considerably understated, and we are now at about 164% of that original amount for permitting costs. Costs will continue as not all permits have been obtained, but these costs are offset by lower costs in other categories. | 3 | This is behind our baseline projection of 85% as route construction has just started, so site preparation will begin in earnest in the next quarter. Also, some preparation costs that were originally broken out in this category are now being included in the Network Build category. | 35 | This amount is behind our baseline projection of 78% as the second order for level 2 and 3 equipment has been placed, but the equipment has not yet been received or invoiced. The equipment will be received during the next quarter. Also, because of favorable pricing, the overall cost of the equipment will be about 14% less than originally projected in the baseline report, so we are actually at about 40% complete of what the total invoiced cost will be. | 43 | This amount includes all network build activities in addition to the cost of IRUs, Project Management and other administrative costs for the project. The physical build did begin this quarter, with 151 miles of duct and 12 cable miles installed. The total percent complete is behind the baseline projection of 70% because of the delays encountered with the grant transfer and in achieving the FONSI. | 23 | This amount is behind our baseline projection of 74% complete as the equipment on hand will be mostly deployed during the next quarter. In addition, new equipment will be received and will be deployed during the next few quarters. | 0 | This category is actually being absorbed into the Network Build costs as these expenses are not being specifically broken out. So the roughly $500,000 in total budget will be reallocated to Network Build. | 2012-08-29 14:50 | 2012-08-29 14:50 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2012 | Q3 | Q3 - 2012 | 8121 | 6768 | TRUE | 55 | The 55% completion is behind the baseline projection of 87% complete. In part, this is because actual payments rather than accruals are shown in this calculation. With billing being in arrears, there is actually about $15.5 million in accrued equipment and construction costs at the end of September, which if added to the percent complete calculation would leave us at over 66% complete. Although still behind the baseline amount, this difference was due to the delays encountered with the grant transfer and statewide Environmental Assessment process. | 18 |  | The costs of the outside testing and warehouse facilities is behind our baseline projection of 85%. The facilities were obtained later and are less expensive than our budget, and these dollars were reallocated in our submitted budget reprogram. | 100 | The FONSI was obtained and this milestone is complete. | 100 | Although the logical and network equipment design is complete, the design will continue to be fine-tuned throughout the design/build process. A budget reprogram has been submitted to allow for additional design costs being incurred. | 92 | Rights of way are behind the 100% baseline projection. However, the CDOT agreement that was signed and the rights of way provided had a value that was higher than what was used in the original baseline projection, and this was reflected in our submitted budget reprogram. | 100 | Although the permitting process has not yet been completed, based on dollars spent, the original baseline estimate was considerably understated, and we are now at about 188% of that original permitting cost amount. Costs will continue and we have revised this budget amount in our submitted budget reprogram. | 6 | This amount is lower than our baseline projection of 94% as some costs that were originally in this category are now part of the Network Build category. We have have revised this budget amount in our submitted budget reprogram. | 49 | This amount is behind our baseline projection of 90%, although again if added in our accrued amount for equipment received in the quarter but not yet paid, we'd be at over 60%. The remainder of the level 2 and 3 equipment has been ordered and will start arriving during the fourth quarter. | 53 | This amount, which includes all network build activities in additon to the cost of IRUs, Project Manaagement and other administrative costs for the project is behind our baseline projection of 85%. This is in part due to the delays encountered with the grant transfer and in achieving the FONSI. Also, as noted above, total invoices where work was completed in September but invoices were not received or paid by September 30 drive down the percentage since only paid invoices are included in the percentage calculation. As of September 30, construction is continuing at a good pace, and 543 miles of conduit and 352 miles of fiber have been laid and crews are continuing at a good pace until the winter weather slows down the construction progress. | 26 | Equipment deployment is behind our baseline projection as we are now just beginning the majority of CAI connections. In addition to the accrual issues mentioned about, this is an area where we have changed our overall budget in the submitted budget reprogram. | 0 | This category is actually being absorbed into the Network Build costs as these expenses are not being specifically broken out. The roughly $500,000 budgeted here have been reallocated in our submitted budget reprogram. | 2012-11-28 15:56 | 2012-11-28 15:56 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2012 | Q4 | Q4 - 2012 | 9001 | 7778 | TRUE | 57 | The 57% is behind the baseline projection of 94% complete. This is partially because of the temporary suspension put on construction spending in the last quarter. If accrued construction costs for work performed but not yet paid were included in this spend calculation, the EAGLE-Net network spend would be 76% complete. Although still behind the baseline amount, this difference is due to the initial delays encountered with the grant transfer and the statewide Environmental Assessment Process. Note that construction was suspended on December 6 until a supplemental Environmental Assessment is completed (see #3 below). | 20 |  | The costs of the outside testing and warehouse facilities is behind our baseline projection of 94%. The facilities were obtained later than anticipated and are less expensive than the projected amount, so these dollars were reallocated in our submitted budget reprogram. | 100 | This milestone and the associated spend were completed when the FONSI was obtained. However, there will be additional expenses in this category to complete the supplemental Environmental Assessment. | 100 | Although the logical and network design is complete, the design will continue to be fine-tuned throughout the design/build process. A budget reprogram has been submitted to forecast additional design costs being incurred. | 92 | Rights of way are behind the 100% baseline projection. However, the CDOT agreement that was signed and the rights of way provided had a value that was greater than what was used in the original baseline projection. These adjusted costs were reflected in our submitted budget reprogram. | 100 | Although the permitting process has not yet been completed, based on dollars spent, the original baseline estimate was considerably understated. As of the end of the quarter, actual dollars spent plus accrued costs are substantially higher than the baseline projected amount. These additional costs were reflected in the submitted budget reprogram. | 8 | This amount is lower than the baseline projection of 98% as some costs that were originally in this category are now part of the Network Build category. We have revised this budget amount in our submitted budget reprogram. | 49 | This amount is behind the baseline projection of 96%, although if we added the accrued cost of equipment purchased but not yet paid, we would be at 76% complete. | 56 | This amount, which includes all network build activities in addition to the cost of IRUs, Project Management and other administrative costs for the project is behind our baseline projection of 94%. This is in part due to the delays encountered with the grant transfer and in achieving the FONSI. Also, as noted above, total invoices where work was completed but the invoices are accrued due to the construction suspension are not included in the spend percentage calculation. If these were included, we would be at 76% complete. As of the construction suspension on December 6, we had completed 710 miles of conduit and 660 miles of new fiber construction. | 26 | Equipment deployment is behind our baseline projection of 95% as we only recently began to connect the majority of our CAIs. The accrued amount would increase this percentage to 36%. This is also a category where we have changed the overall budget in the submitted budget reprogram. | 0 | This category is actually being absorbed into the Network Build costs as these expenses are not being specifically broken out. The roughly $500,000 budgeted here has been reallocated in our submitted budget reprogram. | 2013-02-27 10:58 | 2013-02-27 10:58 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2013 | Q1 | Q1 - 2013 | 9985 | 8537 | TRUE | 57 | The 57% is behind the baseline projection of 98% complete. A major part of the lag in the completion percentage is due to the temporary suspension put on construction spending in the last quarter. Not only was EAGLE-Net required to stop all design and construction activities, but there was previously completed work that we were unable to pay for due to the federal funds being frozen during the suspension. With these accrued expenses, we would actually be close to 77% complete. Also, note that the percent complete has decreased by 1% since the last quarter due to the CDOT Rights of Way adjustment described below. | 22 |  | The costs of the outside testing and warehouse facilities is behind our baseline projection of 98%. The facilities were obtained later than anticipated and are less expensive than the projected amount, so these dollars were reallocated in our submitted budget reprogram. | 100 | This milestone and the associated spend were completed when the initial FONSI was obtained. However, there will be additional expenses in this category to complete the supplemental Environmental Assessment. | 100 | Although the logical and network design is complete, the design will continue to be fine-tuned as the design/build process continues. A budget reprogram has been submitted to forecast additional design costs being incurred. | 92 | Rights of way are behind the 100% baseline projection. However, the CDOT agreement that was signed and the rights of way provided had a value that was greater than what was used in the original baseline projection. These adjusted costs were reflected in our submitted budget reprogram. | 100 | Although the permitting process has not yet been completed, based on dollars spent, the original baseline estimate was considerably understated. As of the end of the quarter, actual dollars spent plus accrued costs are substantially higher than the baseline projected amount. These additional costs were reflected in the submitted budget reprogram. | 8 | This amount is lower than the baseline projection of 100% as some costs that were originally in this category are now part of the Network Build category. We have revised this budget amount in our submitted budget reprogram. | 49 | This amount is behind the baseline projection of 99%, although if we added the accrued cost of equipment purchased but not yet paid, we would be at 77% complete. | 56 | This amount, which includes all network build activities in addition to the cost of IRUs, Project Management and other administrative costs for the project is behind our baseline projection of 98% complete. This is in part due to the delays encountered with the grant transfer and in achieving the FONSI, as well as with the temporary construction suspension from December 6. Also, as noted above, total invoices where work was completed but the invoices are accrued due to the construction suspension are not included in the spend percentage calculation. If these were included, we would be at about 77% complete. As of the construction stoppage, we had completed 660 miles of new fiber construction in addition to 1,960 leased miles and 263 upgraded network miles. | 26 | Equipment was deployed only as routes and laterals were completed and CAIs were connected. With the original construction delays and now the temporary construction suspension, we are trailing our baseline projection of 99% complete. However, the accrued amount would increase our completion percentage to 36%. This is also a category where we have changed the overall budget in the submitted budget reprogram. | 0 | This category is actually being absorbed into the Network Build costs as these expenses are not being specifically broken out. The roughly $500,000 budgeted here has been reallocated in our submitted budget reprogram. | 2013-05-29 17:56 | 2013-05-29 17:56 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2013 | Q2 | Q2 - 2013 | 10787 | 9064 | TRUE | 90 | In the baseline report, we had projected that we would be 100% complete with the overall project by the end of this quarter. Although we are behind that estimate, there was a large increase in our percentage complete from last quarter to this one. This was due to the lifting of the temporary suspension giving us the ability to pay our contractors the amounts owed for previously completed work, and the approval to use CDOT rights of way as in-kind match for all construction started along those rights of way. While we did resume construction in June, those invoices won't be received and paid until July. | 25 |  | These costs were for the outside testing and warehouse facilities. These facilities were obtained later than anticipated and are less expensive than projected, so these dollars were reallocated in the recently approved budget reprogram. | 100 | This milestone and the associated spend were completed with both the awarding of the initial FONSI as well as work done for the Supplemental EA. | 100 | Although the logical and network design is complete, the design will continue to be fine-tuned as the design/build process continues. | 100 | The dollar amount in this category is substantially higher than the original baseline projection as in the recently approved budget reprogram, we are now using CDOT rights of way to complete our match percentage. | 100 | The original baseline estimate for this category was substantially understated, and has been adjusted in the recently approved budget reprogram. | 8 | This amount is lower than the baseline projection of 100% as some costs that were originally in this category are now part of the Network Build category. This change has been adjusted in the recently approved budget reprogram. | 96 | Although network type 2 and 3 equipment has been purchased, there will be some additional procurement of wireless equipment. | 70 | This amount, which includes all network build activities in addition to the cost of IRUs, Project Management and other administrative costs for the project, is behind the baseline projection of 100% complete. Although there was a large increase over last quarter due to the ability to pay our contractors for work that had already been performed, and we did resume construction work in June and completed 8.2 new miles, there are still construction activities to be completed. | 30 | This amount is in the original baseline estimate is high, and has been changed in the recently approved budget reprogram. | 0 | This category had been absorbed into the Network Build costs as these expenses have not specifically been broken out. The adjustment has been made in the budget reprogram. | 2013-08-28 11:02 | 2013-08-28 11:02 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2013 | Q3 | Q3 - 2013 | 11345 | 9473 | TRUE | 94 | The Baseline projection was for the network to by completed by August 31, 2013. We fell short of that projection, however, we did receive an approval of our extension request to continue network construction through December 31, 2014. So, construction has continued through this quarter with our percentage complete at 94% | 28 |  | These costs were for the outside testing and warehouse facilities. These facilities were obtained later than anticipated and are less expensive than projected, so these dollars were reallocated in the approved budget reprogram. | 100 | This milestone and the associated spend were completed with both the awarding of the initial FONSI as well as work done for the Supplemental EA. | 100 | Although the logical and network design is complete, the design will continue to be fine-tuned as the design/build process continues. | 100 | The dollar amount in this category is substantially higher than the original baseline projection as in the approved budget reprogram, we are now using CDOT rights of way to complete our total match percentage. | 100 | The original baseline estimate for this category was substantially understated, and has been adjusted in the approved budget reprogram. | 8 | This amount is lower than the baseline projection of 100% as costs that were originally in this category are now part of the Network Build category. This change has been adjusted in the approved budget reprogram. | 96 | Although network type 2 and 3 equipment has been purchased, there will be some additional procurement of wireless equipment as the final stages of the network are constructed. | 74 | This amount, which includes all network build activities in addition to the cost of IRUs, Project Management and other administrative costs for the project, is behind the baseline projection of 100% complete. We did complete construction of 74 new fiber miles, and are continuing to complete previously started routes and laterals this quarter. | 30 | This amount from the original baseline estimate is high, and has been changed in the approved budget reprogram. | 0 | This category had been absorbed into the Network Build costs as these expenses have not specifically been broken out. The adjustment has been made in the budget reprogram. | 2013-11-22 11:06 | 2013-11-22 11:06 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2013 | Q4 | Q4 - 2013 | 11851 | 10024 | TRUE | 96 | The Baseline projection was for the network to by completed by August 31, 2013. We fell short of that projection, however, we did receive an approval of our extension request to continue network construction through December 31, 2014. So, construction has continued through this quarter with our overall percentage complete at 96%. | 30 |  | These costs were for the outside testing and warehouse facilities. These facilities were obtained later than anticipated and are less expensive than projected, so these dollars were reallocated in the approved budget reprogram. | 100 | This milestone and the associated spend were completed with both the awarding of the initial FONSI as well as work done for the Supplemental EA. | 100 | Although the logical and network design is complete, the design will continue to be fine-tuned as the design/build process continues. | 100 | The dollar amount in this category is substantially higher than the original baseline projection as in the approved budget reprogram, we are now using CDOT rights of way to complete our total match percentage. | 100 | The original baseline estimate for this category was substantially understated, and has been adjusted in the approved budget reprogram. | 8 | This amount is lower than the baseline projection of 100% as costs that were originally in this category are now part of the Network Build category. This change has been adjusted in the approved budget reprogram. | 97 | Although network type 2 and 3 equipment has been purchased, there will be some additional procurement of wireless equipment as the final stages of the network are constructed. | 75 | This amount, which includes all network build activities in addition to the cost of IRUs, Project Management and other administrative costs for the project, is behind the baseline projection of 100% complete. We did complete construction of 67 new fiber miles, and are continuing to complete previously started routes and laterals this quarter. | 42 | This amount from the original baseline estimate is high, and has been changed in the approved budget reprogram. | 0 | This category had been absorbed into the Network Build costs as these expenses have not specifically been broken out. The adjustment has been made in the budget reprogram. | 2014-02-20 13:37 | 2014-02-20 13:37 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT12BIX5570001 | 2012 | Q1 | Q1 - 2012 | 6359 | 5782 | TRUE | 30 | This percentage is based on spend based on the total for both awards. This is 60% behind our baseline. Zayo is currently running way under budget. If you look at the numbers above, although we have only spent 30% of our budget, we have ~76% of our total miles built. | 0 |  | N/A | 0 | Zayo did not plan for this in our budget. This was part of our network design. | 95 | This percentage is based on spend based on the total for both awards. This is 5% behind our baseline. Zayo is currently running way under budget. | 0 | Zayo did not plan for this in our budget. This was part of our network design. | 0 | Zayo built this costs into our construction budget. We did not make it a separate line item. Actual permit status is above in section 1. | 52 | This percentage is based on spend based on the total for both awards. This is 48% behind our baseline. Zayo is currently running way under budget. | 94 | This is 16% behind our baseline and has to do with costs savings. | 43 | This percentage is based on spend based on the total for both awards. This is 57% behind our baseline. Zayo is currently running way under budget. If you look at the numbers above, although we have only spent 30% of our budget, we have ~76% of our total miles built. | 0 | This is 100% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. This is 50% behind our baseline and this is because of the way we are building, we are not lighting and testing our network until it is built. | 2012-05-30 19:15 | 2012-05-30 19:15 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570001 | 2012 | Q2 | Q2 - 2012 | 7293 | 6274 | TRUE | 49 | This percentage is based on spend based on the total for both awards. This is 51% behind our baseline. Zayo is currently running way under budget. If you look at the numbers above, although we have only spent 49% of our budget, we have ~76% of our total miles built. | 0 | n/a | This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. This is 50% behind our baseline and this is because of the way we are building, we are not lighting and testing our network until it is built. | 0 | Zayo did not plan for this in our budget. This was part of our network design. | 95 | This percentage is based on spend based on the total for both awards. This is 5% behind our baseline. Zayo is currently running way under budget. | 0 | Zayo did not plan for this in our budget. This was part of our network design. | 0 | Zayo built this costs into our construction budget. We did not make it a separate line item. Actual permit status is above in section 1. | 59 | This percentage is based on spend based on the total for both awards. This is 41% behind our baseline. Zayo is currently running way under budget and this project took less site prep than anticipated. | 84 | This is 16% behind our baseline and has to do with costs savings. | 48 | This percentage is based on spend based on the total for both awards. This is 52% behind our baseline. Zayo is currently running way under budget. If you look at the numbers above, although we have only spent 30% of our budget, we have ~76% of our total miles built. | 0 | This is 100% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. This is 50% behind our baseline and this is because of the way we are building, we are not lighting and testing our network until it is built. | 2012-08-31 12:32 | 2012-08-31 12:32 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570001 | 2012 | Q3 | Q3 - 2012 | 8173 | 6798 | TRUE | 63 | This is based on actual spend. | 0 | 0 | N/A | 0 | Zayo did not plan for this in our detailed budget, this is part of network design. | 100 | Zayo is actually over budget on this and needs to move funds. | 0 | Zayo did not plan for this in our detailed budget, this is part of network design. | 0 | Zayo built this into our construction budget. We did not make it a separate line item. | 54 | This is based on actual spend. | 84 | This is based on actual spend. | 59 | This is based on actual spend. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 2012-11-30 14:50 | 2012-11-30 14:50 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570001 | 2012 | Q4 | Q4 - 2012 | 8969 | 7751 | TRUE | 69 | This is based on actual spend. | 0 | 0 | N/A | 0 | Zayo did not plan for this in our detailed budget, this is part of network design. | 100 | Zayo is actually over budget on this and needs to move funds. | 0 | Zayo did not plan for this in our detailed budget, this is part of network design. | 0 | Zayo built this into our construction budget. We did not make it a separate line item. | 69 | This is based on actual spend. | 96 | This is based on actual spend. | 64 | This is based on actual spend. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 2013-02-26 13:01 | 2013-02-26 13:03 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570001 | 2013 | Q1 | Q1 - 2013 | 10067 | 8592 | TRUE | 73 | This is based on actual spend. | 0 |  | N/A | 0 | Zayo did not plan for this in our detailed budget, this is part of network design. | 92 | This is lower than last quarter because of the movement of funds we requested last quarter between construction to A&E. | 0 | Zayo did not plan for this in our detailed budget, this is part of network design. | 0 | Zayo built this into our construction budget. We did not make it a separate line item. | 73 | This is based on actual spend. | 96 | This is based on actual spend. | 84 | This is based on actual spend. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 2013-06-20 18:19 | 2013-06-20 18:19 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570002 | 2012 | Q1 | Q1 - 2012 | 6357 | 5781 | TRUE | 32 | This percentage is based on spend based on the total for both awards. This is 6.7% ahead of our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 |  | N/A | 100 | This is in line with the detailed budget attached to the original grant. | 60 | This is based on total dollars spent for both awards. | 0 | N/A | 0 | N/A | 0 | This is 23% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget because after review, zayo is not building any hut sites. | 7 | This percentage is based on spend based on the total for both awards. This is 16% behind our baseline. This is because Zayo has not purchased all of our equipment yet. Zayo is waiting until the the spaces are ready before purchasing the equipment to avoid warehousing costs. | 32 | This percentage is based on spend based on the total for both awards. This is 9% ahead our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 | This is 23% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. If you look at the Network Build percentage above, Zayo is 9% ahead. Zayo figures that Build equals deployment. | 0 | N/A | 2012-05-30 19:13 | 2012-05-30 19:13 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570002 | 2012 | Q2 | Q2 - 2012 | 7281 | 6268 | TRUE | 45 | This percentage is based on spend based on the total for both awards. This is 7.2% ahead of our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 | N/A | N/A | 100 | This is in line with the detailed budget attached to the original grant. | 87 | This is based on total dollars spent for both awards. This is 2% ahead of our baseline. | 0 | N/A | 0 | N/A | 0 | This is 38% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget because after review, zayo is not building any hut sites. | 7 | This percentage is based on spend based on the total for both awards. This is 31% behind our baseline. This is because Zayo has not purchased all of our equipment yet. Zayo is waiting until the the spaces are ready before purchasing the equipment to avoid warehousing costs. | 48 | This percentage is based on spend based on the total for both awards. This is 10% ahead our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 | This is 23% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. If you look at the Network Build percentage above, Zayo is 9% ahead. Zayo figures that Build equals deployment. | 0 | N/A | 2012-08-29 17:42 | 2012-08-29 17:42 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570002 | 2012 | Q3 | Q3 - 2012 | 8175 | 6799 | TRUE | 52 | This is based on actual spend. | 0 | 0 | N/A | 100 | This is in line with our detailed budget. | 89 | This is based on actual spend. | 0 | N/A | 0 | N/A | 0 | Zayo included this in our baseline, but did not include this in our detailed budget. | 7 | This is based on actual spend. | 58 | This is based on actual spend. | 0 | Zayo included this in our baseline, but did not include this in our detailed budget. | 0 | N/A | 2012-11-30 14:53 | 2012-11-30 14:53 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570002 | 2012 | Q4 | Q4 - 2012 | 8953 | 7730 | TRUE | 63 | This is based on actual spend. | 0 | 0 | N/A | 100 | This is in line with our detailed budget. | 100 | This is in line with our detailed budget. | 0 | N/A | 0 | N/A | 0 | Zayo included this in our baseline, but did not include this in our detailed budget. | 7 | This is based on actual spend. | 71 | This is based on actual spend. | 0 | Zayo included this in our baseline, but did not include this in our detailed budget. | 0 | N/A | 2013-02-25 18:07 | 2013-02-25 18:07 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570002 | 2013 | Q1 | Q1 - 2013 | 10061 | 8589 | TRUE | 65 | This is based on actual spend. | 0 |  | N/A | 100 | Zayo is actually at 124%, but it will not let us enter this value. Zayo went over budget on this and will need to move funds. | 100 | This is in line with our detailed budget. | 0 | N/A | 0 | N/A | 0 | Zayo included this in our baseline, but did not include this in our detailed budget. | 9 | This is based on actual spend. | 72 | This is based on actual spend. | 0 | Zayo included this in our baseline, but did not include this in our detailed budget. | 0 | N/A | 2013-06-18 16:38 | 2013-06-18 16:38 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570002 | 2013 | Q2 | Q2 - 2013 | 12675 | 10989 | TRUE | 100 | Project completed 12% under budget based on actual spend. | 0 |  | N/A | 100 | Zayo has completed all environmental requirements. | 100 | Completed. This is in line with our detailed budget. | 0 | N/A | 0 | N/A | 0 | Zayo included this in our baseline, but did not include this in our detailed budget. | 100 | Zayo has completed all procurement construction. | 100 | Zayo has completed all construction. | 0 | Zayo included this in our baseline. | 0 | N/A - It is a dark fiber network only. | 2015-02-03 14:13 | 2015-02-03 14:13 | 7919 | 7919 | Zayo Group, LLC | TRUE

## CCI_MileStones_Projected
award_num | Year_Desc | Quarter_Cd | YearQuarter | Milestone_Id | PPRMain_Id | Complete_Ind | ProjOverall_Prcnt_Amt | ProjOverall_Narrtv_Desc | OtherMilstone_Prcnt_Amt | OtherMilstone_Specify_Desc | OtherMilstone_Narrtv_Desc | EnvmntAssessmnt_Prcnt_Amt | EnvmntAssessmnt_Narrtv_Desc | NetworkDesign_Prcnt_Amt | NetworkDesign_Narrtv_Desc | RightsofWay_Prcnt_Amt | RightsofWay_Narrtv_Desc | ConstructPermit_Prcnt_Amt | ConstructPermit_Narrtv_Desc | SitePreprtn_Prcnt_Amt | SitePreprtn_Narrtv_Desc | EquipProcurmnt_Prcnt_Amt | EquipProcurmnt_Narrtv_Desc | NetworkBuild_Prcnt_Amt | NetworkBuild_Narrtv_Desc | EquipDeploy_Prcnt_Amt | EquipDeploy_Narrtv_Desc | NetworkTest_Prcnt_Amt | NetworkTest_Narrtv_Desc | Created_Date | Modified_Date | Created_Person_Id | Modified_Person_Id | Recipient | April 11, 2014 Cutoff Date
NT10BIX5570003 | 2010 | Q2 | Q2 - 2010 | 39 | 1278 | FALSE | 10 |  |  |  |  | 100 |  | 100 |  | 100 |  | 100 |  | 20 |  | 25 |  | 5 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2010 | Q3 | Q3 - 2010 | 434 | 1483 | FALSE | 25 | Equipment originally planned to be purchased in Q4 of calendar year is being pushed back to the first quarter of 2011. | 0 | N/A | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 30 | N/A | 60 | Equipment Procurement is lagging this Q4 of calendar year due to purchases being pushed back into Q1 of 2011. This is a minor gap with us reaching our milestone early in 2011. | 20 | Overall duration of the Environmental Assessment has impeded progress in Network Build by approximately one quarter. | 75 | N/A | 15 | Network Testing will follow the Network Build component above, in that the overall duration of the Environmental Assessment has delayed our Network build and testing by approximately one quarter. | 2010-11-29 11:46 | 2010-11-29 11:46 | 5446 | 5446 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2010 | Q4 | Q4 - 2010 | 1392 | 2407 | FALSE | 35 | N/A | 0 | N/A | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 50 | Site preparation is exceeding baseline as we enter the second year of our project. We will continue at our current pace with the expectations of exceeding our baseline. | 85 | Equipment procurement is ahead of baseline with most major components purchased. | 15 | Limited construction will continue during the first quarter of 2011, however during Q2 and Q3 when the weather is conducive to construction SDN plans to deploy additional crews to bring the project back to baseline projections. | 60 | Equipment purchased in this quarter will not be deployed until the quarter following. | 20 | With the build-out of the network at the current stage and deployment of equipment, testing of the network is behind baseline as originally projected. | 2011-02-28 16:12 | 2011-02-28 16:12 | 5446 | 5446 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2011 | Q1 | Q1 - 2011 | 1960 | 2725 | FALSE | 35 | South Dakota Network will plan on additional resources this quarter to strive to make up the gap from Baseline projections. Equipment purchases are anticipated throughout the remainder of the year. Construction will exceed original projections for this year to close the gap currently created by a shortened construction season last year. | 0 | N/A | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 65 | No variance. | 68 | Equipment originally anticipated as part of the project, not impacting the network, were pushed back pending modifications to the project. These minor changes do not require an amendment or alteration to the Award. | 35 | Construction originally planned for last year was pushed back due to the Environmental process and some additional weather issues late in the season. Additional resources have been deployed to complete the project in the timeframe allowed. | 55 | As indicated in the equipment procurement section, portions of our equipment purchases were extended out in the timeline so a lag occurs in this particular milestone. | 25 | As indicated previously, construction anticipated to start earlier was pushed back due to baseline projections not in line with the Environmental approval timeframe. This causes some variance to Baseline in the Network Testing area from what was originally planned. | 2011-05-12 09:37 | 2011-05-12 09:37 | 5446 | 5446 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2011 | Q2 | Q2 - 2011 | 3002 | 3258 | FALSE | 59 | As previously communicated, Baseline projections were based on an earlier construction start date, therefore the overall project expenditures have lagged the preliminary baseline projections. The anticipation of meeting the Broadband Technology Opportunities Program guidelines are attainable. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 80 | Although lagging Baseline insignificantly, projections are to substantailly complete this milestone by the end of year 2011. Minimal site preparation will remain in 2012. | 90 | Equipment procurement is ahead of schedule. | 50 | Network build has lagged our initial projections as has been indicated earlier. This metric will lag in 2011 and reach projections during the final year of the project. | 75 | Equipment deployment will occur as equipment is received. Equipment deployment lags Baseline as a result of some purchases delayed. Although purchases will be made, some installation will not occur until the following quarter. | 40 | Preliminary Baseline projections anticipated an earlier construction start date. With the delay in the Environmental process, with other milestone categories following construction, testing will lag and be completed as the network is built. | 2011-08-10 17:24 | 2011-08-10 17:24 | 5446 | 5446 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2011 | Q3 | Q3 - 2011 | 4230 | 3963 | FALSE | 76 | An aggressive Baseline projection has left this metric short of forecast by eight percent after the second year of the project. Some of this shortfall will be made up over the next quarter as we originally only projected a minimal increase for the same time period. Additional crews were added to accommodate this lag and construction activities will continue as weather permits . | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance | 90 | No Variance. | 100 | No Variance. | 60 | The Network Build milestone will continue to lag into the final year of the project. Components of this metric will continue to be incorporated into the project as construction activities take place. | 90 | Additional equipment purchases planned will be deployed in the following quarter and allow for a gap in actual versus projection to close. | 50 | Network Testing is currently lagging Baseline projections with the anticipation of making up some of this over the next two quarters. A smaller increase in the Baseline will allow for some 'catch up'. | 2011-11-22 15:39 | 2011-11-22 15:39 | 5445 | 5445 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2011 | Q4 | Q4 - 2011 | 5280 | 4949 | FALSE | 85 | An aggressive Baseline projection has left this metric short of forecast by twelve percent. Some of this shortfall will be made up over the next two quarters as we originally only projected a five percent increase for the same time period. Additional crews were added to accommodate this lag. | 0 |  | N/A | 100 | Meeting Baseline. | 100 | Meeting Baseline. | 100 | Meeting Baseline. | 100 | Meeting Baseline. | 90 | Minimal site preparation will remain going into 2012. This metric will be met during the second quarter of 2012. | 98 | Final Equipment procurement will be taking place with substantial completion | 83 | Network Build metric will be met during the second half of 2012. Additional miles will be minimal in Quarter 1 of 2012 pending warmer weather. | 95 | Exceeding Baseline. | 70 | Exceeding Baseline. Projected completion of this metric will be the end of Quarter 2, 2012. | 2012-02-27 10:37 | 2012-02-27 10:37 | 5445 | 5445 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2012 | Q1 | Q1 - 2012 | 6034 | 5616 | FALSE | 88 | Project expenditures will lag baseline as we finish in the final year of the project. Baseline projections were aggressive in the initial planning phase leading to the lag in actuals versus projections. | 0 |  | N/A | 100 | No Variation | 100 | No Variation | 100 | No Variation | 100 | No Variation | 100 | No Variation | 100 | Exceeding Baseline | 92 | This metric is only slightly behind Baseline projections and will be completed ahead of schedule as we reach the final phase of the project. | 100 | Exceeding Baseline | 75 | No Variance | 2012-05-11 08:32 | 2012-05-11 08:32 | 5445 | 5445 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2012 | Q2 | Q2 - 2012 | 6960 | 6107 | FALSE | 93 | All remaining Construction activity will be completed in this quarter with remaining invoices being paid following completion of the project. Payments will linger into Q4 2012 with the final report showing 100% completion. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance | 100 | No Variance. | 90 | Final Network Testing will be completed in Q4 2012. | 2012-08-09 11:27 | 2012-08-09 11:27 | 5445 | 5445 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2012 | Q3 | Q3 - 2012 | 7852 | 6630 | FALSE | 100 | No Variance. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2012-11-13 17:24 | 2012-11-13 17:24 | 5445 | 5445 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | 2012 | Q4 | Q4 - 2012 | 9038 | 7806 | FALSE | 100 | Project has been completed. | 100 |  | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 2013-02-27 16:34 | 2013-02-27 16:34 | 5445 | 5445 | South Dakota Network, LLC | TRUE
NT10BIX5570004 | 2010 | Q2 | Q2 - 2010 | 40 | 1335 | FALSE | 25 |  | 0 |  |  | 100 |  | 80 |  | 70 |  | 0 |  | 20 |  | 25 |  | 3 |  | 5 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2010 | Q3 | Q3 - 2010 | 300 | 1416 | FALSE | 25 | Project delayed due to pending EA approval | 0 |  | N/A | 100 | N/A | 80 | Middle Mile 80% complete. Last mile 0% complete and can not be completed until middle mile is complete. Middle mile project delayed due to pending EA approval | 80 | Middle Mile 80% complete. Last mile 0% complete and can not be completed until middle mile is complete. Middle mile project delayed due to pending EA approval | 5 | Project delayed due to pending EA approval | 15 | N/A | 15 | Project delayed due to pending EA approval | 0 | Project delayed due to pending EA approval | 0 | Project delayed due to pending EA approval | 0 | Project delayed due to pending EA approval | 2010-11-01 14:35 | 2010-11-01 14:35 | 5444 | 5444 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2010 | Q4 | Q4 - 2010 | 864 | 1898 | FALSE | 28 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 0 | N/A | N/A | 100 | Final approval received January 3, 2011. | 85 | Middle Mile 95% complete. Last mile 0% complete and can not be completed until middle mile is complete. | 85 | Middle Mile 95% complete. Last mile 0% complete and can not be completed until middle mile is complete. | 42 | N/A | 25 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 42 | N/A | 10 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 5 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 5 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 2011-01-28 17:51 | 2011-01-28 17:51 | 5444 | 5444 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2011 | Q1 | Q1 - 2011 | 1940 | 2715 | FALSE | 10 | Fiber construction will continue during the second quarter. Procurement of equipment expected to continue and implementation of equipment should begin during the second quarter. We will continue to develop and implement testing plans and procedures. With the majority of project completion milestone occurring in the third quarter. | 0 | N/A | N/A | 100 | N/A | 85 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts have been started and last mile construction is projected to begin in third quarter 2011. | 90 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts have been started and last mile construction is projected to begin in third quarter 2011. | 50 | N/A | 25 | We do anticipate an increase in site preparation in the third quarter of 2011. | 50 | N/A | 15 | Plan for all core and middle mile fiber construction to be completed by third quarter 2011. IRU negotiations should be completed by end of second quarter 2011. | 10 | Equipment deployment will begin in second quarter 2011 and we are projecting to meet our third quarter 2011 milestone.. | 15 | N/A | 2011-05-11 11:41 | 2011-05-11 11:41 | 5751 | 5751 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2011 | Q2 | Q2 - 2011 | 3032 | 3273 | FALSE | 31 | Fiber construction will continue during the third quarter. Procurement of equipment expected to continue and implementation of major equipment, CPOP and SPOP locations should begin during the third quarter. We will continue to develop and implement testing plans and procedures. Planning and installation of last mile customers and community anchors will begin during third quarter. | 0 | N/A | N/A | 100 | N/A | 85 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts have been started and last mile construction is projected to begin in third quarter 2011. | 90 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts have been started and last mile construction is projected to begin in third quarter 2011. | 58 | Construction Permits and Other Approvals should be 58 percent complete in third quarter 2011 which meets the baseline milestones. | 58 | We do anticipate an increase in site preparation in the third quarter of 2011. | 58 | Last mile construction will increase during the third quarter of 2011. We do anticipate having equipment procurement at 58 percent complete in the third quarter of 2011 which meets the baseline milestones. | 30 | With the increased last mile deployment and core and middle mile construction completed in two of the three areas we anticipate having the network build 35 percent complete which meets the baseline milestones. | 50 | Equipment deployment will increase during the third quarter of 2011 and we are projecting to meet our third quarter 2011 milestones. | 25 | Network Testing is anticipated to be 25 percent complete and we are projecting to meet our third quarter 2011 milestones. | 2011-08-11 18:25 | 2011-08-11 18:25 | 7129 | 7129 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2011 | Q3 | Q3 - 2011 | 4206 | 3951 | FALSE | 67 | Fiber construction will continue during the fourth quarter. Procurement of equipment expected to continue and implementation of major equipment, CPOP and SPOP locations should continue during the fourth quarter. We will continue to develop and implement testing plans and procedures. Planning and installation of last mile customers and community anchors will continue during fourth quarter. We have budget meetings every two weeks to insure that this spend rate will be achieved prior to the November 30, 2011 deadline. | 0 | N/A | N/A | 100 | N/A | 90 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts continued and last mile construction is projected to began the last week of September 2011. | 92 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts continued during the third quarter of 2011 and last mile construction began the last week of September 2011. | 67 | Construction Permits and Other Approvals should be 67 percent complete in fourth quarter 2011 which meets the baseline milestones. | 67 | Site Preparation should be 67 percent complete in fourth quarter 2011 which meets the baseline milestones. | 67 | Last mile construction will increase during the fourth quarter of 2011. We do anticipate having equipment procurement at 67 percent complete in the fourth quarter of 2011 which meets the baseline milestones. | 45 | With the increased last mile deployment and core and middle mile construction completed we anticipate having the network build 45 percent complete which meets the baseline milestones. | 60 | Equipment deployment will continue during the fourth quarter of 2011 and we are projecting to meet our fourth quarter 2011 milestones. | 35 | Network Testing is anticipated to be 35 percent complete and we are projecting to meet our fourth quarter 2011 milestones. | 2011-11-21 21:31 | 2011-11-21 21:31 | 5751 | 5751 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2011 | Q4 | Q4 - 2011 | 5204 | 4874 | FALSE | 75 | Meets first quarter milestones | 0 | N/A | N/A | 100 | N/A | 91 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts continued and last mile construction began the last week of September 2011 and will continue until the end of the project. | 94 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts continued during the fourth quarter of 2011 and will continue until the end of the project. | 75 | Meets first quarter milestones | 75 | Meets first quarter milestones | 75 | Meets first quarter milestones | 55 | Meets first quarter milestones | 75 | Meets first quarter milestones | 45 | Meets first quarter milestones | 2012-02-23 10:23 | 2012-02-23 10:23 | 5751 | 5751 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2012 | Q1 | Q1 - 2012 | 6318 | 5761 | FALSE | 84 | Meets second quarter milestones | 0 | N/A | N/A | 100 | N/A | 94 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts continued and last mile construction began the last week of September 2011 and will continue until the end of the project. | 96 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts will continued during the second quarter of 2012 and will continue until the end of the project. | 83 | Meets second quarter milestones | 83 | Meets second quarter milestones | 83 | Meets second quarter milestones | 75 | Meets second quarter milestones | 80 | Meets second quarter milestones | 55 | Meets second quarter milestones | 2012-05-29 12:11 | 2012-05-29 12:15 | 7129 | 7129 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2012 | Q2 | Q2 - 2012 | 7100 | 6177 | FALSE | 92 | Meets third quarter milestones | 0 | N/A | N/A | 100 | N/A | 97 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts continued and last mile construction began the last week of September 2011 and will continue until the end of the project. | 99 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts will continued during the second quarter of 2012 and will continue until the end of the project. | 92 | Meets third quarter milestones | 92 | Meets third quarter milestones | 92 | Meets third quarter milestones | 85 | Meets third quarter milestones | 90 | Meets third quarter milestones | 75 | Meets third quarter milestones | 2012-08-15 18:51 | 2012-08-15 18:51 | 7129 | 7129 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2012 | Q3 | Q3 - 2012 | 7666 | 6512 | FALSE | 100 | Project on schedule for completion as of 11/30/12 | 0 | N/A | N/A | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 2012-10-30 19:10 | 2012-10-30 19:10 | 7129 | 7129 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | 2012 | Q4 | Q4 - 2012 | 9176 | 8008 | FALSE | 100 | Project was completed on 11/30/12. | 100 | N/A | N/A | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 2013-04-12 14:31 | 2013-04-12 14:31 | 5751 | 5751 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570006 | 2010 | Q2 | Q2 - 2010 | 41 | 1311 | FALSE | 15 |  |  |  |  | 100 |  | 100 |  | 100 |  | 35 |  | 10 |  | 10 |  | 10 |  |  |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Biddeford Internet Corp. | TRUE
NT10BIX5570007 | 2010 | Q2 | Q2 - 2010 | 42 | 1314 | FALSE | 8.47 |  | 53.85 |  |  | 100 |  | 100 |  | 16.72 |  | 12.9 |  | 2.41 |  | 11.23 |  | 3.95 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | ION HOLDCO, LLC | TRUE
NT10BIX5570009 | 2010 | Q2 | Q2 - 2010 | 43 | 1283 | FALSE | 20 |  | 30 |  |  | 99 |  | 60 |  | 60 |  | 20 |  | 10 |  | 30 |  | 2 |  | 5 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2010 | Q3 | Q3 - 2010 | 344 | 1438 | FALSE | 30 | Given the previous quarter's challenges we may not be able to catch up at this point but plan to within the next quarter or the quarter after that. | 40 | Staffing | None Noted | 100 | None Noted | 85 | None Noted | 95 | None Noted | 60 | None Noted | 10 | Site preparation is beginning one quarter later than planned due to delays with obtaining permits in Year 1 Q2. | 10 | Merit will have selected a vendor, but we have changed our purchasing strategy to "just in time". Our baseline plan assumed that equipment would be purchased in advance and warehoused. | 2 | None Noted | 5 | None Noted | 5 | None Noted | 2010-11-18 08:37 | 2010-11-18 08:37 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2010 | Q4 | Q4 - 2010 | 1346 | 2363 | FALSE | 40 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. Merit anticipates that in the following quarter or the quarter after that Merit will be back up to speed considering the construction and equipment procurement will accelerate quickly after the permitting is complete. | 50 | Staffing | None Noted | 100 | None Noted | 95 | None Noted | 95 | None Noted | 55 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. | 30 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. | 30 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. | 2 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. | 5 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. | 5 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. | 2011-02-23 15:52 | 2011-02-23 15:52 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2011 | Q1 | Q1 - 2011 | 2266 | 2878 | FALSE | 12 | The combination of delays in several milestone categories has resulted in significantly less spending than we projected; however, once construction is fully underway, we anticipate closing the gap between our current status and the Baseline Plan. | 59 |  | We are slightly under budget in this category because engineering staff have not completed the installation training. | 100 | Since our Finding of No Significant Impact (FONSI) was issued, we have needed and will continue to need to work with our environmental consulting firm on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the significant overrun (estimated to be approximately 400% next quarter), we do not anticipate revising the budget as reported on Form 424C; the EA is a component of the Engineering budget, and we are significantly under budget in that category at this time. | 20 | Engineering has cost significantly less than originally budgeted. This is offset by the EA subcategory (split out separately for the purpose of reporting), which has cost significant more than anticipated. The percent complete number, when based solely on financials, does not reflect that network design for the fiber optic backbone is complete aside from occasional route changes required by permit kickbacks. The route changes, additional engineering work, and staffing will continue to add between 3% and 5% to the percent complete total on a quarterly basis. | 100 | We have exceeded our budget for rights-of-way permitting (estimated at 173% for next quarter), however, work still remains to be done. There are several municipalities who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution (CAI) builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for rights-of-way permitting (estimated at 173% for next quarter), however, work still remains to be done. There are several municipalities who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution (CAI) builds and route changes necessitated by schedule or engineering. | 0 | We are in the middle of the procurement process for selecting a contractor to perform the site preparation work; we are also still in the process of finalizing central office and CAI routes. We will be catching up by prepping the site prior to the arrival of the backbone fiber to the anchor, allowing us to get more site preparation complete in a short time frame. Wherever possible, we will save time by purchasing existing entrances to the central office facilities. | 18 | Merit does not want to deploy optical equipment until we are closer to the fiber installation date. Due to a lack of storage capacity in our business office, we feel it is wasteful to order more equipment at this time than we are ready to deploy. However, we will acquire some additional equipment in this quarter. | 4 | We are slightly behind on the network build because we are still waiting for the Davis Bacon Act wage determinations to be issued. We have temporarily secured the services of an underground construction firm so that we could begin some construction, but Merit cannot enter into a contract with a construction firm without attaching the applicable wage determinations. We anticipate bringing on several construction crews and beginning aerial construction in the next quarter. | 4 | Merit has just hired an engineer to deploy and test optical equipment; we anticipate being routinely under budget in this category, since it comprises 36 months of salary. | 3 | Merit has just hired an engineer to deploy and test optical equipment; we anticipate being routinely under budget in this category, since it comprises 36 months of salary. We also have not incurred expense for testing equipment at this time. | 2011-05-24 09:26 | 2011-05-24 09:26 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2011 | Q2 | Q2 - 2011 | 3030 | 3272 | FALSE | 29 | The combination of delays in several milestone categories has resulted in significantly less spending than we projected; however, once construction is fully underway, we anticipate closing the gap between our current status and the Baseline Plan. | 75 | Staffing, Misc. | Legal expenses in previous quarters have been signficantly higher than expected. | 100 | Since our Finding of No Significant Impact was issued, we have needed and will continue to need to work with our environmental consulting firm on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the significant overrun (estimated to be approximately 400% next quarter), we do not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and we are significantly under budget in that category at this time. | 41 | Engineering has cost significantly less than originally budgeted. This is offset by the Environmental Assessment subcategory (split out separately for the purpose of reporting), which has cost significant more than anticipated. The percent complete number, when based solely on financials, does not reflect that network design for the fiber optic backbone is complete aside from occasional route changes required by permit kickbacks. The route changes, additional engineering work, and staffing will continue to add between 3% and 5% to the percent complete total on a quarterly basis. | 100 | We have exceeded our budget for rights-of-way permitting (estimated at 196% for next quarter), however, work still remains to be done. There are several municipalities who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for rights-of-way permitting (estimated at 196% for next quarter), however, work still remains to be done. There are several municipalities who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 0 | We have selected a contractor to perform the site preparation work; we are also still in the process of finalizing central office and Community Anchor Institution routes. We will be catching up by prepping the site prior to the arrival of the backbone fiber to the anchor, allowing us to get more site preparation complete in a short time frame. Wherever possible, we will save time by purchasing existing entrances to the central office facilities. | 27 | Merit does not want to deploy optical equipment until we are closer to the fiber installation date. Due to a lack of storage capacity in our business office, we feel it is wasteful to order more equipment at this time than we are ready to deploy. However, we will acquire some additional equipment in this quarter. | 22 | We are slightly behind on the network build because of the wait for the Davis Bacon Act wage determinations to be issued. We have temporarily secured the services of an underground construction firm so that we could begin some construction, but Merit cannot enter into a contract with a construction firm without attaching the applicable wage determinations. We anticipate bringing on several construction crews and beginning aerial construction in the next quarter. | 7 | We will have not incurred significant expense for equipment deployment at this time. We are early in the deployment process, but Merit will be most likely be at or close to budget by completion. | 41 | We have procured test equipment, but less testing has been required due to construction delays. Merit will be most likely be at or close to budget by completion. | 2011-08-11 16:39 | 2011-08-11 16:39 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2011 | Q3 | Q3 - 2011 | 3948 | 3812 | FALSE | 58 | We expect to have the remaining permits approved by the end of the next quarter. We also expect to deploy more segments for construction once the delays in permitting (both construction and environmental) are resolved. We also anticipate having all funded community anchors signed up by the end of next quarter. Once multiple construction deployments commence (which will occur in the very near future) we anticipate closing the gap between our current status and the Baseline Plan. | 84 |  | Legal expenses in previous quarters have been significantly higher than expected. | 100 | Since our Finding of No Significant Impact was issued, we have needed and will continue to need to work with our environmental consulting firm on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the significant overrun (estimated to be approximately 427%), we do not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and we are significantly under budget in that category at this time. | 41 | While the engineering expense cost less than anticipated, we have had significant delays in getting our environmental clearances. While the engineering is less than we anticipated, we have had significant delays in getting our environmental clearances from the State of Michigan. We have received our federal clearances but state regulations are more stringent. The current percent complete does not accurately reflect that network design for fiber optic backbone is complete. Some re-engineering occurred due to changes required by permitting entities. | 100 | We have exceeded our budget for rights-of-way permitting (estimated at 238% for next quarter), however, work still remains to be done. There are several municipalities who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for rights-of-way permitting (estimated at 238% for next quarter), however, work still remains to be done. There are several municipalities who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 25 | We have almost completed the process of finalizing central office and community anchor institution routes. Last quarter we selected a contractor to perform site preparation work and he is diligently conducting site visits. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 30 | We have not incurred expense for equipment deployment at this time. Merit has not completed enough construction to warrant placing equipment in the field. As we are early in the deployment process, Merit will most likely be at or close to budget by completion. | 64 | We have contracts with seven construction firms, each with multiple construction crews and have begun aerial construction in the Southern region. Other areas of aerial construction are planned to start in the very near future as permits are being approved. We are currently over 60% complete on all Round 1 permits, of which there are 1,256 needed. | 50 | We have not incurred expense for equipment deployment at this time. Merit has not completed enough construction to warrant placing equipment in the field. As we are early in the deployment process, Merit will most likely be at or close to budget by completion. | 26 | We have procured test equipment, but testing hasnâ€™t commenced due to construction delays. Merit will most likely be at or close to budget by completion. | 2011-11-10 07:48 | 2011-11-10 07:52 | 5485 | 5485 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2011 | Q4 | Q4 - 2011 | 5320 | 4990 | FALSE | 63 | Permitting (both construction and environmental) delays have resulted in less spending than originally projected for this quarter. While the overall project completion in terms of spending is still behind, significant progress will be made this quarter in eliminating the variance between the percent complete and the baseline plan. Construction crews will be working at capacity, so we anticipate closing the gap between our current status and the Baseline Plan in subsequent quarters. | 94 |  | Spending in this category has evened out, and is now below the Baseline Projection. We anticipate being over budget (114%) by project completion, because we will continue to require administrative staff and incur miscellaneous expenses as long as construction and deployment are underway. | 100 | The Environmental Assessment is at 440% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with our environmental consulting firm and the Michigan Department of Environmental Quality (MDEQ) on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the overrun, we do not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and we are significantly under budget in that category at this time. We are confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 50 | Engineering has so far cost far less than anticipated, and we have had significant delays in getting our environmental clearances. The current percent complete does not accurately reflect that network design for fiber optic backbone is complete. The Engineering teams will continued to work on the route and incorporate redlines. Final CADs cannot be produced until construction is complete, so we anticipate seeing a significant portion of the budget funds expended in the third and fourth quarters of 2012. | 100 | We have exceeded our budget for rights-of-way permitting (273%), however, some work still remains to be done. We estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for rights-of-way permitting (273%), however, some work still remains to be done. We estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 33 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation from one individual to four individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 30 | Most of the dense wave division multiplex (DWDM) equipment will be invoiced this quarter. The procurement process for routers and switches will be completed, and equipment will be ordered. Merit anticipates being at budget by project completion. | 68 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 50 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field deploying equipment, and spending in this category will increase. Merit will be at or close to budget by completion. | 52 | Test equipment has been purchased; once more construction is complete, testing will be performed, and the percent complete is projected to be at budget by project completion. | 2012-02-27 17:13 | 2012-02-27 17:13 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2012 | Q1 | Q1 - 2012 | 6120 | 5662 | FALSE | 64 | Permitting (both construction and environmental) delays have resulted in less spending than originally projected for this quarter. While the overall project completion in terms of spending is still behind, significant progress will be made this quarter in eliminating the variance between the percent complete and the baseline plan. Construction crews will be working at capacity, so we anticipate closing the gap between our current status and the Baseline Plan in subsequent quarters. | 96 |  | Spending in this category has evened out, and is now below the Baseline Projection. We anticipate being over budget (114%) by project completion, because we will continue to require administrative staff and incur miscellaneous expenses as long as construction and deployment are underway. | 100 | The Environmental Assessment is at 440% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with our environmental consulting firm and the Michigan Department of Environmental Quality (MDEQ) on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the overrun, we do not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and we are significantly under budget in that category at this time. We are confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 55 | Engineering has so far cost far less than anticipated, and we have had significant delays in getting our environmental clearances. The current percent complete does not accurately reflect that network design for fiber optic backbone is complete. The Engineering teams will continued to work on the route and incorporate redlines. Final CADs cannot be produced until construction is complete, so we anticipate seeing a significant portion of the budget funds expended in the third and fourth quarters of 2012. | 100 | We have exceeded our budget for rights-of-way permitting (273%), however, some work still remains to be done. We estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for rights-of-way permitting (273%), however, some work still remains to be done. We estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 34 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation from one individual to four individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 64 | Most of the dense wave division multiplex (DWDM) equipment will be invoiced this quarter. The procurement process for routers and switches will be completed, and equipment will be ordered. Merit anticipates being at budget by project completion. | 61 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 33 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field deploying equipment, and spending in this category will increase. Merit will be at or close to budget by completion. | 68 | Test equipment has been purchased; once more construction is complete, testing will be performed, and the percent complete is projected to be at budget by project completion. | 2012-05-16 09:10 | 2012-05-16 09:10 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2012 | Q2 | Q2 - 2012 | 6950 | 6102 | FALSE | 87 | Permitting (both construction and environmental) delays have resulted in less spending than originally projected for this quarter. While the overall project completion in terms of spending is still behind, significant progress will be made this quarter in eliminating the variance between the percent complete and the baseline plan. Additional construction will be complete, allowing equipment deployment, site preparation, and network testing, so we anticipate closing the gap between our current status and the Baseline Plan in subsequent quarters. | 100 | Staffing, Miscellaneous | Spending in this category has evened out, and is now below the Baseline Projection. We anticipate being over budget (114%) by project completion, because we will continue to require administrative staff and incur miscellaneous expenses as long as construction and deployment are underway. Surplus funds from the Network Testing Category will cover the cost overruns for staffing and miscellaneous expenses. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with our environmental consulting firm and the Michigan Department of Environmental Quality (MDEQ) on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the overrun, we do not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and we are significantly under budget in that category at this time. We are confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 78 | Engineering has so far cost far less than anticipated, and we have had significant delays in getting our environmental clearances. The current percent complete does not accurately reflect that network design for fiber optic backbone is complete. The Engineering teams will continued to work on the route and incorporate redlines into Merit's GIS database. Final CADs cannot be produced until construction is complete, so we anticipate seeing a significant portion of the budget funds expended in the fourth quarters of 2012. | 100 | Merit estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, Merit may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | Merit estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, Merit may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 67 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation from one individual to four individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 89 | Most of the dense wave division multiplex (DWDM) equipment will be invoiced this quarter. The procurement process for routers and switches will be completed, and equipment will be ordered. Merit anticipates being at budget by project completion. | 84 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 67 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field deploying equipment, and spending in this category will increase. Merit will be at or close to budget by completion. | 84 | Test equipment has been purchased; once more construction is complete, testing will be performed. However, due to the scheduling and staffing efficiencies achieved by combining deploying equipment, site preparation, and network testing on single runs, this category is projected to be under budget by project completion. | 2012-08-09 09:17 | 2012-08-09 09:17 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2012 | Q3 | Q3 - 2012 | 8036 | 6724 | FALSE | 100 | Construction and environmental permitting delays have resulted in less spending than projected for this quarter. While the overall project completion in terms of spending is still behind, significant progress will be made this quarter in eliminating the variance between the percent complete and the baseline plan. Additional construction will be complete, allowing equipment deployment, site preparation, and network testing, so we anticipate being near budget at the end of the fourth quarter with some funding available to cover administrative expenses associated with closing out the grant. | 100 | Staffing, Miscellaneous | Spending in this category has evened out, and is now below the Baseline Projection. We anticipate being over budget (138%) by project completion. We will continue to require administrative staff and incur miscellaneous expenses as long as construction and deployment are underway. Surplus funds from the Network Testing Company will cover the cost overruns for staffing and miscellaneous expenses. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with the environmental consulting firm and the Michigan Department of Environmental Quality on ways to minimize our projectâ€™s impact and remain in compliance. Despite the overrun Merit does not anticipate revising the budget as reported on Form 424C. The Environmental Assessment is a component of the Engineering budget and Merit is currently under budget in that category. Merit is confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 70 | To date engineering has cost significantly less than anticipated despite delays in getting our environmental clearances. The percentage of completion does not accurately reflect that the network design for fiber optic backbone is complete. The engineering teams will continue to work on the route and incorporate redlines into Meritâ€™s Geographic Information System database. Final CADs cannot be produced until construction is complete, so Merit anticipates seeing a significant portion of the budget funds expended in the fourth quarter of 2012. Because we are still waiting on engineering and construction drawings of the route, our projection for next quarter has come in lower than what our projection was in the third quarter. | 100 | Merit estimates the percentage at completion will be 301%. This overrun will be accounted for in the Construction category. Additionally, Merit may need to submit additional permit applications for Community Anchor Institution. | 100 | Merit estimates the percentage at completion will be 301%. This overrun will be accounted for in the Construction category. Additionally, Merit may need to submit additional permit applications for Community Anchor Institution. | 100 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation form one (1) to four (4) individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 100 | All equipment has been ordered and Merit anticipates paying final invoices during the fourth quarter and finishing at budget upon completion. | 100 | Merit has contracts with seven (7) construction firms. The seven (7) firms have multiple construction crews that are performing aerial and underground construction across the funded network. Merit anticipates being at budget by the end of the fourth quarter. | 100 | Merit has been behind our Baseline Projection due to construction start delays. Now that construction is actively underway our engineers will be out in the field deploying equipment. Spending in this category will increase. Merit will be at or close to budget by completion. | 100 | Test equipment has been purchased. As construction is completed testing will be performed. This category is projected to be under budget by project completion due to the scheduling and staffing efficiencies achieved in deploying equipment, site preparation, and testing the network on single runs. | 2012-11-26 12:38 | 2012-11-26 12:38 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2012 | Q4 | Q4 - 2012 | 8974 | 7754 | FALSE | 100 | Construction and environmental permitting delays have resulted in less spending than projected for this quarter. While the overall project completion in terms of spending is still behind, significant progress was made this quarter in eliminating the variance between the percent complete and the baseline plan. Additional construction will be complete, allowing equipment deployment, site preparation, and network testing, so we anticipate being near budget at the end of the following quarter with some funding available to cover administrative expenses associated with closing out the grant. | 100 |  | Spending in this category has evened out, and is now below the Baseline Projection. We anticipate being over budget (128%) by project completion. We will continue to require administrative staff and incur miscellaneous expenses as long as construction and deployment are underway. Surplus funds from the Network Testing Company will cover the cost overruns for staffing and miscellaneous expenses. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with the environmental consulting firm and the Michigan Department of Environmental Quality on ways to minimize our projectâ€™s impact and remain in compliance. Despite the overrun Merit does not anticipate revising the budget as reported on Form 424C. The Environmental Assessment is a component of the Engineering budget and Merit is currently under budget in that category. Merit is confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 100 | The percentage of completion does not accurately reflect that the network design for fiber optic backbone is complete. Final CADs cannot be produced until construction is complete, so Merit anticipates seeing a significant portion of the budget funds expended as the project wraps up, and will also contain costs relating to site preparation as well as absorb some of the Environmental Assessment costs. | 100 | Merit estimates the percentage at completion will be 288%. This overrun will be accounted for in the Construction category. Additionally, Merit may need to submit additional permit applications for Community Anchor Institution. | 100 | Merit estimates the percentage at completion will be 288%. This overrun will be accounted for in the Construction category. Additionally, Merit may need to submit additional permit applications for Community Anchor Institution. | 0 | Based on the way we have been categorizing expenses, site preperation items have been placed in the Network Design category. | 100 | All equipment has been ordered and Merit anticipates paying final invoices. | 100 | Merit has contracts with seven (7) construction firms. The seven (7) firms have multiple construction crews that are performing aerial and underground construction across the funded network. Merit has almost all construction completed, and will be wrapping up to begin Q1 2013. | 100 | Merit has been behind our Baseline Projection due to construction start delays. Now that construction is actively underway our engineers will be out in the field deploying equipment. Merit is finishing up installing and activating equipment. | 100 | Test equipment has been purchased. As construction is completed testing will be performed. This category is projected to be under budget by project completion due to the scheduling and staffing efficiencies achieved in deploying equipment, site preparation, and testing the network on single runs. | 2013-02-26 14:18 | 2013-02-26 14:18 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2013 | Q1 | Q1 - 2013 | 10002 | 8545 | FALSE | 100 | The construction and environmental permit delays Merit experienced at the outset of the project has resulted in less spending to date than originally projected. Merit has completed construction and is now working on and completing final testing and any repairs that are necessary. Merit anticipates project completion by the end of the quarter. | 100 | Staffing, Miscellaneous | Merit anticipates Spending in this category will reach 126% of the budgeted amount. Merit anticipates that there should be minimal expenses in this category over the remainder of the project. Surplus funds from the Network Testing and Network Design categories will cover this cost overrun. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with the environmental consulting firm and the Michigan Department of Environmental Quality on ways to minimize our projectâ€™s impact and remain in compliance. Merit also needed to do additional work to obtain environmental approval from the National Telecommunications & Information Administration for route changes. Despite the overrun Merit does not anticipate revising the budget as reported on Form 424C. The Environmental Assessment is a component of the Engineering budget and Merit is currently under budget in that category. Merit is confident that the Engineering budget will be able to absorb the current overrun. | 46 | The percentage of completion does not accurately reflect that the network design for fiber optic backbone is complete. Final CADs cannot be produced until construction is complete, so Merit anticipates seeing additional budget funds expended as the project wraps up, and will also contain costs relating to site preparation as well as absorb some of the Environmental Assessment costs and other overrun costs. | 100 | Merit has exceeded our budget for the rights-of-way permitting (288%). However, some work may still remain. Merit estimates the percentage at completion will be under 300%. | 100 | Merit has exceeded our budget for the rights-of-way permitting (288%). However, some work may still remain. Merit estimates the percentage at completion will be under 300%. | 1 | Based on the way we have been categorizing expenses, most site preparation items have been placed in the Network Design category. | 100 | All optical hardware has been procured and invoiced, and the procurement process for routers and switches was completed. Merit anticipates no further spending. | 100 | Merit has contracts with seven (7) construction firms. The seven (7) firms have multiple construction crews that performed aerial and underground construction across the funded network. Merit will receive final invoices and pay them over the next quarter. Merit anticipates being at 112% of this budget category at project end. | 100 | Merit is at 129% of the budget amount in this category but anticipates minimal spending in the following quarter as all equipment has been placed. | 100 | Construction is completed and some testing has occurred so far. Additional testing will take place over the following quarter. Merit anticipates being near budget at completion. | 2013-05-30 07:28 | 2013-05-30 07:28 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2013 | Q2 | Q2 - 2013 | 10524 | 8915 | FALSE | 100 | The construction and environmental permit delays Merit experienced at the outset of the project has resulted in less spending to date than originally projected. Merit has completed construction and is now working on and completing final testing and any repairs that are necessary. Merit anticipates project completion by the end of the quarter. | 100 | Staffing, Miscellaneous | Merit anticipates Spending in this category will reach 187% of the budgeted amount. Merit anticipates that there should be some expenses in this category over the remainder of the project. Surplus funds from the Network Testing and Network Design categories will cover this cost overrun. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with the environmental consulting firm and the Michigan Department of Environmental Quality on ways to minimize our projectâ€™s impact and remain in compliance. Merit also needed to do additional work to obtain environmental approval from the National Telecommunications & Information Administration for route changes. Despite the overrun, Merit is under budget in other areas and should be able to absorb the overage in those categories. | 51 | The percentage of completion does not accurately reflect that the network design for fiber optic backbone is complete. Final CADs cannot be produced until construction is complete, so Merit anticipates seeing additional budget funds expended as the project wraps up, and will also contain costs relating to site preparation as well as absorb some of the Environmental Assessment costs and other overrun costs. | 100 | Merit has exceeded our budget for the rights-of-way permitting (294%). However, some work may still remain. Merit estimates the percentage at completion will be under 300%. | 100 | Merit has exceeded our budget for the rights-of-way permitting (294%). However, some work may still remain. Merit estimates the percentage at completion will be under 300%. | 1 | Based on the way we have been categorizing expenses, most site preparation items have been placed in the Network Design category. | 100 | All optical hardware has been procured and invoiced, and the procurement process for routers and switches was completed. Merit anticipates no further spending. | 100 | Merit has contracts with seven (7) construction firms. The seven (7) firms have multiple construction crews that performed aerial and underground construction across the funded network. Merit will receive final invoices and pay them over the next quarter. Merit anticipates being at 109% of this budget category at project end. | 100 | Merit is at 129% of the budget amount in this category but anticipates minimal spending in the following quarter as all equipment has been placed. | 79 | Construction is completed and some testing has occurred so far. Testing will be completed by the end of this quarter. | 2013-08-08 14:06 | 2013-08-08 14:06 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570009 | 2013 | Q3 | Q3 - 2013 | 12678 | 10991 | FALSE | 100 | Merit has completed the REACH 3MC Project. | 100 | Staffing, Miscellaneous | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 2015-02-04 09:08 | 2015-02-04 09:08 | 7981 | 7981 | Merit Network Inc. | TRUE
NT10BIX5570011 | 2010 | Q2 | Q2 - 2010 | 44 | 1298 | FALSE | 8 |  | 0 |  |  | 100 |  | 100 |  | 25 |  | 25 |  | 0 |  | 15 |  | 10 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | 2010 | Q3 | Q3 - 2010 | 384 | 1458 | FALSE | 15 | Delay in start to construction due to delay in receipt of FONSI has set us back about two months. We expect to make this up over the course of 1-2 months. | 0 |  | N/A | 100 | N/A | 100 | N/A | 50 | Ahead of schedule due to quicker application of permits. | 50 | Ahead of schedule due to quicker application of permits. | 0 | N/A | 15 | N/A | 15 | Delay in start to construction due to delay in receipt of FONSI has set us back about two months. We expect to make this up over the course of 1-2 months. | 10 | Delay in deployment due to delay in receipt of FONSI has set us back about two months. We expect to make this up over the course of 1-2 months. | 20 | Delay in start to construction due to delay in receipt of FONSI has set us back about two months. We expect to make this up over the course of 1-2 months. | 2010-11-23 11:38 | 2010-11-23 11:38 | 5748 | 5748 | MCNC | TRUE
NT10BIX5570011 | 2010 | Q4 | Q4 - 2010 | 1170 | 2204 | FALSE | 35 | N/A | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | Because of our intent to pick up our construction pace, we have changed our approach for permit and encroachment application and expect to submit all before end of next quarter. | 90 | Because of our intent to pick up our construction pace, we have changed our approach for permit and encroachment application and expect to receive a large portion of these approvals back in the quarter and thus ahead of schedule | 0 | N/A | 50 | We will be procuring equipment for two specific spans to correspond with completion of construction efforts to have in hand for when fiber is completed, and thus feel we'll be ahead of pace. | 70 | We have 887 miles of network to deploy as part of the project. As of this quarter we reported 403 complete (7 miles of new, 197 miles of upgrade of existing IRU fibers, 197 miles of newly obtained IRU fibers). We anticipate finalizing IRUâ€™s of new fibers for Balsam West, Plateau LLC, and Morris Broadband within the Y2Q1 quarter that will total 98 miles of the proposed network. We also anticipate building approximately 120 miles of new fiber, amounting to a total of 621 miles of the network out of 887 miles to be deployed. | 40 | N/A | 33 | N/A | 2011-02-16 08:18 | 2011-02-16 08:18 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2011 | Q1 | Q1 - 2011 | 1884 | 2687 | FALSE | 50 | We believe we will begin to be slightly ahead of schedule by end of June quarter and significantly ahead of schedule by end of September quarter due to the pace of construction we're seeing. We're averaging placement of approximately 40 miles of conduit per month. As fiber is ready, equipment will be arriving to be deployed. | 0 | na | N/A to our project | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | No variance | 75 | Due to the fact we're advancing ahead of schedule with miles of conduit placed, coupled with the lead times reported by Cisco currently on the type of equipment we need to deploy, we anticipate ordering equipment about one quarter in advance at a minimum of when we would deploy. Based on that, we will be ahead of pace to the baseline on this line item going forward. | 68 | Based on where we're at now and with a minimum of 100 miles placed, we would expect to be at 68% (conservatively) by end of June, which would be ahead of our baseline estimate. | 40 | Based on the lighting of completed spans, we would anticipate having about 1/2 of the network elements deployed by June, but to remain conservative, will only forecast 40% for now. | 68 | Based on where we're at now and with a minimum of 100 miles placed, we would expect to be at 68% (conservatively) by end of June, which would be ahead of our baseline estimate. | 2011-05-04 13:28 | 2011-05-04 13:28 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2011 | Q2 | Q2 - 2011 | 2946 | 3230 | FALSE | 75 | N/A | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 0 | N/A | 100 | Due to the quicker deployment of the fiber, we anticipate we will have placed orders for all equipment by the end of Y2Q3. | 100 | We are conservatively projecting completion of all fiber builds in the project by end of the quarter unless we experience an unexpected delay. | 50 | We anticipate having all priority segments lit prior to the end of the quarter, which when based on the number of miles in the project, will represent slightly greater than 50% of equipment located in the field. | 100 | Due to quicker than expected construction, we feel we will have all fiber deployed, and thus have all fiber tested. | 2011-08-08 09:45 | 2011-08-08 09:45 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2011 | Q3 | Q3 - 2011 | 4224 | 3960 | FALSE | 81 | We expect to have 95% of the scope of work completed. We expect expenditures by the end of the quarter will be around 81% of the total awarded contract value due to savings realized in executing on the work and timing related to contractor invoices for work completed during the last part of the quarter. | 0 |  | NA | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 80 | We do not anticipate being behind our baseline projection for this quarter. Relative to the number of miles in the project and the amount of equipment deployed to operate that fiber, we feel we will be coming in close to the 60% indication as we are lighting fiber within a close timeframe to completion of the fiber builds. The only thing that may hamper this for completeness in this quarter is lost time due to holiday's and work that we typically do on existing infrastructure during this annual time frame. | 100 | N/A | 2011-11-22 15:05 | 2011-11-22 15:05 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2011 | Q4 | Q4 - 2011 | 4970 | 4645 | FALSE | 78 | We expect to have 100% of the project completed which will correlated to 78% of the original budget. | 0 | NA | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 2012-02-13 12:40 | 2012-02-13 12:40 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2012 | Q1 | Q1 - 2012 | 6228 | 5716 | FALSE | 86 | 100% of the original project plan has been completed. We expect that efforts on the additional proposed infrastructure and expenditures realized during Q22012 will increase the overall spend of the project to 86%. | 0 | NA | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 80 | 100% of the original network build has been completed. We expect that efforts on the additional proposed infrastructure and expenditures related to that will increase the overall spend of the network build to 80%. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 2012-05-21 12:48 | 2012-05-21 12:48 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2012 | Q2 | Q2 - 2012 | 7138 | 6196 | FALSE | 92 | The project as originally funded is 100% complete. This level of completeness forecasted for next quarter represents our estimate of how quickly the remaining builds and deployments will execute over this quarter, and the associated spend to do so. We do not forecast greater than 92% here as we don't believe all equipment associated with the 100G upgrade to the core will have arrived by the end of the September quarter to allow us to show the equipment received and thus accounted for within the project. | 0 | N/A | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 98 | We will be full force in our effort to complete the additional funded infrastructure. At the end of the quarter we would expect to 100% complete with the project as initially funded, and 98% complete as it relates to the percent complete relative to the additions to the scope of work. | 95 | We are 100% complete with the equipment elements of the project as originally funded. With the additions, we will be at 95% completion. | 100 | This task is 100% complete. | 2012-08-20 07:32 | 2012-08-20 07:32 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2012 | Q3 | Q3 - 2012 | 8106 | 6760 | FALSE | 96 | We anticipate this task will complete, but relevant to dollars spent, we will still be under budget and thus complete relative to dollars at 96% | 0 |  | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | We anticipate this task completing. | 95 | We anticipate this task completing during the quarter as awarded, but relevant to budget being under that which was anticipated and thus approved to be at 95% complete based on dollars spent. | 100 | We anticipate this task completing. | 100 | We anticipate this task completing. | 2012-11-28 12:24 | 2012-11-28 12:24 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2012 | Q4 | Q4 - 2012 | 9032 | 7802 | FALSE | 98 | The original project is complete. Due to the extension provided by the NTIA we are exploring adding three additional interconnect colocation point and some 100G infrastructure to Research1 CAI's. Most of the efforts in the next quarter related to this effort will be engineering in nature and have little associated cost. | 0 |  | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task will be 100% complete by the end of the next quarter. | 99 | We anticipate this task completing during the quarter as awarded, but relevant to budget being under that which was anticipated and thus approved to be at 95% complete based on dollars spent. | 95 | While we anticipate the equipment being procured, we do not anticipate having it deployed in the next quarter due to the length of time to receive it. | 100 | This task is 100% complete. | 2013-02-27 16:17 | 2013-02-27 16:17 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2013 | Q1 | Q1 - 2013 | 9904 | 8493 | FALSE | 98 | As originally awarded, we are 100% complete. The balance of work left by end of next quarter would be the placement of the telecommunication huts as part of the project modification. | 0 |  | N/A | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task will be 100% complete next quarter | 100 | This task will be 100% complete next quarter | 100 | This task will be 100% complete next quarter | 100 | This task is 100% complete | 2013-05-24 15:58 | 2013-05-24 15:58 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2013 | Q2 | Q2 - 2013 | 10540 | 8924 | FALSE | 100 | This task will be 100% complete by end of the 9/30/13 quarter. | 0 |  | N/A | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task will be 100% complete by end of the 9/30/13 quarter. | 100 | This task will be 100% complete by end of the 9/30/13 quarter. | 100 | This task is 100% complete | 2013-08-09 15:12 | 2013-08-09 15:12 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570011 | 2013 | Q3 | Q3 - 2013 | 10940 | 9176 | FALSE | 100 | This task is 100% complete | 0 |  | N/A | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 2013-10-25 08:17 | 2013-10-25 08:17 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570016 | 2010 | Q2 | Q2 - 2010 | 45 | 1331 | FALSE | 10 |  |  |  |  | 100 |  | 100 |  | 80 |  | 50 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2010 | Q3 | Q3 - 2010 | 186 | 1359 | FALSE | 20 | No information to add | 0 |  | N/A | 100 | No information to add | 100 | No information to add | 100 | No information to add | 100 | No information to add | 35 | No information to add | 0 | No information to add | 15 | No information to add | 0 | No information to add | 0 | No information to add | 2010-10-28 11:51 | 2010-10-28 11:51 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2010 | Q4 | Q4 - 2010 | 810 | 1845 | FALSE | 20 | Delay in approval of EA & winter weather will hinder construction progress. Plan to add additional construction crews after Y2Q1. | 0 |  | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 35 | Weather will hinder completing site preparation. | 100 | N/A | 15 | Cable construction will be hindered by weather. Electronics & huts will be purchased. | 0 | Zero Variance | 0 | Zero Variance | 2011-01-28 15:52 | 2011-01-28 15:52 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2011 | Q1 | Q1 - 2011 | 2126 | 2808 | FALSE | 24 | Delayed construction start due to lack of approval of final EA and SHPO consultation delay | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 50 | Could not start until EA is approved and RFP prepared to send in May 2011 | 100 | N/A | 24 | Delayed construction start. Additional contractors will "catch up" construction schedule. | 0 | N/A | 0 | N/A | 2011-05-18 12:00 | 2011-05-18 12:00 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2011 | Q2 | Q2 - 2011 | 3066 | 3290 | FALSE | 60 | By adding additional construction crews, we hope to complete 60% of the project by end of Y2Q3. | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 50 | Construction plans are to place approximately 30 miles of cable in Y2Q3. Due to the delay in the start of construction, the network build and equipment deployment dates were shifted forward. MBC is deploying additional crews to "catch up" on the schedule. | 33 | Equipment to be installed in at least one inter-connection point in Y2Q3. Due to the delay in the start of construction, the network build and equipment deployment dates were shifted forward. MBC is deploying additional crews to "catch up" on the schedule. | 25 | Network testing will begin as soon as equipment is installed in at least one node (inter-connection) location. | 2011-08-12 17:32 | 2011-08-12 17:32 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2011 | Q3 | Q3 - 2011 | 4034 | 3857 | FALSE | 61 | Percent completion as projected. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 70 | Construction plans are to place 30 miles of cable in Y2Q4 | 33 | Equipment to be installed in at least one interconnection point. | 33 | Network testing to be completed in at least one location. | 2011-11-14 15:43 | 2011-11-14 15:43 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2011 | Q4 | Q4 - 2011 | 4882 | 4574 | FALSE | 82 | Percent completed projected on PIP (budget spent) | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete remaining 2 site (AC power) | 100 | Complete | 100 | Place additional 19 miles for a total of 105 miles | 100 | Complete remaining 2 interconnection sites | 80 | Completion of final testing in Y3Q2 | 2012-02-06 12:11 | 2012-02-06 12:11 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2012 | Q1 | Q1 - 2012 | 6078 | 5638 | FALSE | 84 | Became evident during Y3Q1, project would be under budget. A budget modification and route modification to be sent in Y3Q2 for approval. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-15 05:23 | 2012-05-15 05:23 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2012 | Q2 | Q2 - 2012 | 6874 | 6063 | FALSE | 90 | Construction of IRU and node to be completed in Y3Q4 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2012-08-06 22:26 | 2012-08-06 22:26 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2012 | Q3 | Q3 - 2012 | 7888 | 6648 | FALSE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2012-11-14 21:12 | 2012-11-14 21:12 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2012 | Q4 | Q4 - 2012 | 8660 | 7483 | FALSE | 98 | Project extended to 6/30/13 as projected completion date | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 98 | Equipment deployment awaiting completion of new node | 98 | Testing awaiting completion equipment installation | 2013-02-06 20:38 | 2013-02-06 20:38 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2013 | Q1 | Q1 - 2013 | 9652 | 8358 | FALSE | 98 | Project Completion scheduled for 6-30-2013 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-05-08 23:58 | 2013-05-08 23:58 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | 2013 | Q2 | Q2 - 2013 | 12440 | 10628 | FALSE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-08-19 15:49 | 2014-08-19 15:49 | 5453 | 5453 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570017 | 2010 | Q2 | Q2 - 2010 | 46 | 1319 | FALSE | 8 |  |  |  |  | 100 |  | 90 |  | 95 |  | 5 |  | 5 |  | 50 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2010 | Q3 | Q3 - 2010 | 390 | 1461 | FALSE | 6 | We expect to have issued all of the purchase orders, with the exception of the wireless links as well as complete two microwave hops (or links) between three sites. Project will be on track with baseline plan in Q3 2011. | 50 | Customer Acquisition, Support and Billing | Workshop to identify interfaces as well as billing design documents is planned for Q1 of 2011. Q4 of 2010 will therefore show much of the research and preparation necessary to be prepared for Q1 of 2011. We have also determined that we plan to begin offering services to customers in July of 2011. | 100 | We expect a favorable response from the secondary investigation previously noted resulting from a request from the Wyandotte Tribe. | 90 | High-level and low-level network switching design will be completed. Remaining 10% contingency for additional design of 43 point to point and point to multi-point connections from the middle-mile backbone to customers. Project will be on track with baseline plan in Q3 2011. | 94 | Contingency for a slower than normal response time due to the holidays. Project will be on track with baseline plan by end Q1 2011 with all site permissions finalized for broadband. | 79 | We are currently determining the need for construction permits and or zoning approvals. Should it be determined that we need either for the new towers and shelters that we will be building and installing as part of this project, three fourths will be secured by close of Q4. | 21 | We expect to complete the site preparation on three sites by close of 2010. | 55 | We expect that we will have ordered all equipment with the exception of the 43 wi-max (wireless) links by the close of Q4. Delivery and acceptance of equipment, other than wi-max, is anticipated to begin in Q4. | 3 | We expect to complete the implementation of three sites to the point that they would be able to sustain the 150 Mbps speeds of broadband; however we also plan to return to these sites at a later date in the project to further upgrade them to allow for the traffic/ high-speed internet to pass through these sites via the path of least resistance. Project will be on track with baseline plan in Q3 2011. | 5 | We expect to deploy the equipment to three of our sites which would allow them to pass traffic that could reach speeds up to 150 Mbps by the end of Q4, 2010. Project will be on track with baseline plan in Q1 2011. | 4 | Network Testing is expected to begin in Q1 of 2011. | 2010-11-23 16:29 | 2010-11-23 16:29 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2010 | Q4 | Q4 - 2010 | 1172 | 2205 | FALSE | 20 | We expect to have the foundations of three of the new towers poured by the close of Q1. We also anticipate the completion of a total of 11 hops of microwave equipment installed. As noted previously, the slight delay that exists in our progress was due to a longer period of time than expected to get all purchase orders through the approval process of the commonwealth. Now that we have issued all of the major procurements, allowing equipment, towers and shelters to be ordered, we expect to catch up to the baseline by Q2 of 2011. | 37 | Customer Acquisition, Support and Billing | By the close of Q1, 2011 we expect to be well on our way to completion of the design of the customer support portion of the system. The asset management final design has already been completed. Training and implementation will follow shortly thereafter and is expected to occur within the 2nd quarter of 2011. | 100 | We have completed this portion of the project. | 90 | Design Documentation for the wireless connections is all that remains at this point. | 76 | The commonwealth is using the Rights of Way milestone indicator to track our completion of "permissions" documents as we currently have "rights-of-way" documents in place for all of our sites as they are pre-existing sites within our network. The permissions that we are seeking vary from site to site but can be anything from a notice that we will be offering broadband services through our equipment already located at that site or a request for permission to add additional equipment/minor modifications to that site. A majority of the permissions that remain outstanding are the type meant to notify the tower owner of our broadband services addition. We expect to complete this milestone within the next few quarters and catch up to the baseline report by Q2 or Q3 of 2011. | 100 | Based upon past experience, we expect to move through the process to obtain all necessary building permits rather quickly and anticipate completing the process within Q1. We are scheduled to begin construction on the towers in late Q1, so this should not cause any delay to the project. | 36 | We expect to have an additional two sites prepared for construction by the close of Q1, 2011. | 75 | While we have ordered all of the equipment deemed necessary for our project prior to the close of Q4 2010, there remains the delivery and invoicing of that equipment for this category to reach 100%. | 8 | We are gaging our network build percentage on the number of sites and hops where equipment is installed as well as the number of towers completed. By close of Q1, we believe that equipment will be deployed to 11 hops (microwave equipment) as well as to 10 sites (MPLS equipment). While no tower builds will be complete within Q1, we expect to have the first towers completed within Q2 of 2011. | 15 | Equipment deployment will begin to ramp up within Q1 of 2011. Within the quarter, we expect to deploy microwave equipment to 11 hops as well as MPLS equipment to 10 sites. | 4 | Network testing is occurring as equipment is deployed and installed. We expect all network testing to be completed within the quarter after each piece is installed, if not sooner. | 2011-02-16 08:29 | 2011-02-16 08:29 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2011 | Q1 | Q1 - 2011 | 2396 | 2943 | FALSE | 16 | According to the guidance from the NTIA and direction from our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 16% According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 38% of completion for this milestone within Q2. During Q2 of 2011, we expect to complete construction on five new equipment shelters as well as two new self-supporting towers within Q2. In order to complete the tower construction we will need to finalize the zoning permit process as well as complete the Federal Aviation Administration (FAA) clearance process which we expect to occur within Q2. We also expect to complete installation of a total of 21 microwave connections as well as completed testing on 11 of those connections. While we will still be slightly behind the baseline for this period of time, we expec | 0 | Customer Acquisition, Support and Billing | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 0%. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 50% of completion for this milestone within Q2. We anticipate the training portion of the asset management system to occur within the second quarter of 2011 as well as the final design of the billing/provisioning systems. The training phase of the billing/provisioning system is expected to occur sometime during the third quarter of the year followed up by implementation of both systems by the end of the quarter. As soon as items are completed to our satisfaction, we will recognize the items as received within the commonwealth's procurement and accounting system and payment will be made to the vendor. | 100 | This milestone has been completed. | 72 | According to the guidance from the NTIA and direction from our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 72% According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 95% of completion for this milestone within Q2. By the close of Q2 of 2011, we will have completed the design of our network to include the high and low level documentation for the switching portion of the network as well as the high level design documentation for the wireless connections. The only portion that will remain at that point will be the final low level design documentation for the wireless connections which will largely depend upon our first customers. With the completion of multiple project design elements we will be in a position to begin showing expenditures for them. | 0 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is not to be tracked due to the lack of expenditures in this category. Following that guidance, our planned percent complete will remain at 0% According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 100% of completion for this milestone within Q2. We anticipate receiving the final permissions documents to be returned around the close of Q2, 2011. | 0 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is not to be tracked due to the lack of expenditures in this category. Following that guidance, our planned percent complete will remain at 0% According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 78% of completion for this milestone within Q2. We are using the Construction Permits and other approvals milestone to represent not only building permits and Federal Aviation Administration (FAA) clearances for our five towers but also the zoning permit process that is necessary at two of the towers. All building permits have been waived at the five sites receiving new towers. We expect to have acquired the remaining FAA clearance within the second quarter as well as to have worked through the process to acquire the two necessary zoning permits. | 0 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 0%. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 50% of completion for this milestone within Q2. During the second quarter of 2011, we expect to install a total of five equipment shelters upon their foundations as well as complete installation of two new self supporting radio towers within the quarter. As a result of the completion of these shelters, we will be able to show expenditures for the costs associated with these shelters bringing us to a status of 50% complete. | 15 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 15%. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 76% of completion for this milestone within Q2. All equipment has been ordered as of the close of Q4; however, due to the Commonwealth's policy, all equipment must be installed, tested and signed off as being complete by our office, the customer, prior to invoicing. We have included delivery and invoicing within this milestone to fully gauge equipment deployment. With that said, we expect to reach 76% of completion of this milestone by the close of Q2, 2011 with the delivery of equipment to complete a total of 21 project connections as well as the invoicing of that equipment. | 0 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 0%. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 30% of completion for this milestone within Q2. By the close of Q2, we expect to have installed 21 of the microwave connections as well as commenced with the installation of switching equipment at ten of the sites. We anticipated the completion of two of our new self supporting radio towers near the end of the second quarter as well. While we are slightly behind the progress predicted by our baseline, we expect to close the gap significantly within the 3rd quarter of 2011 with the build of an additional two towers and five equipment shelters. As the work is completed and connections are quality assurance tested, we will be a | 15 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 15%. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 22% of completion for this milestone within Q2. By the close of the second quarter, we expect to have installed equipment at 21 of the total 71 microwave connections as well as 10 of the 68 sites of switching equipment. Once all quality assurance testing is completed, we will show expenditures for these items bringing us to a status of 22% complete. | 23 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 23%. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 15% of completion for this milestone within Q2. We expect to have fully tested 11 of the 71 network connections by the close of the second quarter. Once this testing is complete, we will show expenditures for these items. | 2011-05-31 08:55 | 2011-05-31 08:55 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2011 | Q2 | Q2 - 2011 | 3130 | 3322 | FALSE | 18 | We expect to see expenditures for the tower and shelters that were completed near the close of the second quarter of 2011. We also expect to be able to show expenditures for the first pieces of microwave equipment as well. This figure varies from the baseline due to our change in method of gauging progress. Prior to the reporting of Q1, 2011, we used a method other than expenditures to determine our percent of progress completed. | 16 | Customer Acquisition, Support and Billing | By the close of the third quarter of 2011, we expect to be near completion on the work required for the billing and provision portions of this milestone with final completion expected early in the fourth quarter. As we have stated previously, all goods and services must be delivered and quality control inspected prior to submission of an invoice by the vendor. With that in mind, in reporting expenditures, it is likely that we will not catch up to our baseline report until early in 2012. | 100 | This milestone is complete. | 72 | We expect to see expenditures for the network design milestone early in the third quarter which should bring our percentage up to 72 percent complete based upon expenditures. One of the remaining items under this milestone is the design of the wireless links which may depend upon the requirements of the first customers which may delay our ability to catch up to the baseline until early in 2012. | 0 | N/A The rights of way milestone has no cost associated with it as part of our project therefore it's progress will not be tracked within the quarterly PPR. | 0 | N/A The construction permits and other approvals milestone has no cost associated with it as part of our project therefore it will not be tracked within the quarterly PPR. | 21 | We expect to have completed the construction of a total of five new towers and ten new shelters by the close of the third quarter of 2011 and are on track with our own internal schedule of progress. Our percent of progress; however, is based upon expenditures (as requested by the NTIA) which trail the completion of project activities. All goods and/or services procured by the Commonwealth of Pennsylvania are required to be completed or installed and quality assurance tested prior to the submission of an invoice by the vendor. We expect to catch the baseline report by the close of the fourth quarter of 2011. | 12 | As of the close of the third quarter of 2011, we expect to be able to show 12% of progress in the Equipment Procurement milestone as we pay for the first few microwave radio upgrades. We expect to continue to receive invoices for the additional equipment upgrades that have been completed to date and expect to catch our baseline report during the second quarter of 2012. | 27 | The network build milestone includes the expenditures for the construction of our new towers and shelters as part of this project. As of the close of the third quarter, we expect to have expenditures for one tower and five shelters. With the planned construction for the third quarter, we expect to be able to catch our baseline in the fourth quarter of this year. | 6 | We expect that the milestone of Equipment Deployment will be able to show expenditures to move the progress to 6% of completion by the close of the third quarter of 2011. The progress in this milestone is slow due to a lack of invoices to pay at this point. We will continue to encourage our vendors to submit invoices as soon as the work is completed. We expect to catch our baseline report in the early quarters of 2012. | 33 | We will continue to test all equipment installations as they happen. By the close of the third quarter of 2011, we expect to have paid all invoices related to the quality control inspections that occurred prior to the third quarter but are being conservative in our estimated expenditures. While this percent of progress slightly trails that of the baseline report, we expect to catch up in the first quarters of 2012. | 2011-08-16 15:53 | 2011-08-16 16:03 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2011 | Q3 | Q3 - 2011 | 4064 | 3875 | FALSE | 36 | By the close of the fourth quarter of 2011, our project will have completed the tower and shelter construction portion of the project and will have installed a total of 41 of the 71 total microwave radio connections included within the project, if not more. Due to the location of our sites and hunting season starting just after Thanksgiving, our teams will take a break from field work and focus their efforts on other activities to keep the project on schedule. Due to our percent of progress being based upon expenditures and our internal requirements prior to payment of invoices, our numbers are not in agreement with the baseline report. As invoices are received for the completed tower and shelter construction as well as the continued equipment installations, our percent of progress should climb significantly at the close of the 2011 4th quarter as well as the 2012 1st quarter. | 16 | Customer Acquisition, Support and Billing | We are nearing completion of the billing and provisioning portion of our project. This portion was temporarily held up by a slight change in hardware configuration in another aspect of the network. Now that we have moved forward with the hardware changes, our vendor can finalize the work on this portion of the project. Our ability to bring customers onto the network and provide an appropriate bill is not continent upon this portion of the project to be functional; however, billing and provisioning will be facilitated by this item. We now expect that this part of the project will be completed around the close of the first quarter of 2012. | 100 | This milestone is complete. | 76 | The main item remaining under our network design is that of the wireless links to connect the last mile providers and/or community anchor institutions to our network. With the planned launch of a pilot project with a last mile service provider in the fourth quarter, and the valuable knowledge we will gain from that project, we anticipated launching this milestone forward in the first quarter of 2012. | 0 | N/A. The rights of way milestone has no cost associated with it as part of our project; therefore, it's progress will not be tracked within the quarterly PPR. | 0 | n/a The construction permits and other approvals milestone has no cost associated with it as part of our project; therefore, it will not be tracked within the quarterly PPR. | 38 | By the close of the fourth quarter, we expect to have completed all of the tower and shelter work as part of this project with the only remaining element in site preparation to be the compound expenses to finish the grading, seeding, fencing etc. at the site compounds. With a majority of this work coming to a close, we expect to be in the early stages of receiving the remainder of the invoices for site preparation by the close of the fourth quarter which should be paid by the close of the first quarter of 2012. | 23 | As our equipment is installed and tested, our vendor(s) are submitting invoices for payment. Unfortunately, the invoices trail the actual installation by multiple months due to the internal procedures that we have in place. Nonetheless, we will have reached 23 percent of this milestone by the close of the fourth quarter and expect to make significant progress as invoices (for work completed in the fourth quarter) are paid by the close of the first quarter in 2012. | 79 | The network build milestone includes the construction of our towers and shelters of which many other elements were dependant upon. A majority of those structures are complete as of the end of the third quarter with the remainder of them expected to be completed early within the fourth quarter. These expenditures, likely realized in the first quarter of 2012, along with expenditures for the radio and switching equipment will help to boost this milestone in early 2012. | 15 | The progress in this milestone is slow due to a network hardware configuration change that effects our entire network. As a result, a few elements of our project schedule were adjusted to allow for that work to be configured. Now that we have made our adjustments, we expect to roll out switching equipment as well as the provisioning portal which will allow our expenditures in this milestone to increase early in 2012. | 40 | We will continue to test all equipment installations as they occur, as we have from the start of the project. By the close of the fourth quarter of 2011, we expect to have paid all invoices related to the quality control inspections that have occurred prior to the fourth quarter but are being conservative in our estimated expenditures. While this percentage of progress slightly trails that of our baseline report, we expect to catch up in the first quarters of 2012. | 2011-11-16 11:59 | 2011-11-16 11:59 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2011 | Q4 | Q4 - 2011 | 5296 | 4965 | FALSE | 48 | The project, when measured by expenditure alone, is anticipated to remain behind the baseline due to the safeguards built into the Commonwealth's payment system. Goods and/or services must be provided and approved, then quality assurance checked and invoiced. Project progress based upon completion of work; however, is expected to remain on schedule at approximately 78% complete. The difference between actual progress and that based upon expenditures accounts for the vendor having not invoiced for the installation and integration of equipment until not only the microwave radios have been installed/integrated but also the MPLS switching equipment as well. | 57 | Customer Acquisition, Support and Billing | The Billing portion of the project remains in progress as we await customers to test the application. It is anticipated that payment for the Reporting Analysis Manager and other elements of the operational support system may be realized. It is anticipated that this milestone will catch up to the expenditure based baseline report in the third quarter of 2012. | 100 | This milestone is complete. | 77 | The only remaining element in the network design milestone is in regard to WiMAX. Once the pilot with a last mile service provider begins and the Request for Information (RFI) is completed, it is expected that the engineering for WiMAX will be completed. | 0 | N/A. This milestone does not apply to our project. | 0 | N/A. This milestone does not apply to our project. | 73 | This milestone is on schedule. | 49 | It is anticipated that 67% of microwave equipment expenditures will have been realized. Engineering and configuration of switching equipment will continue allowing for the deployment in Q2, 2012. | 100 | This milestone is anticipated to be complete. | 9 | On this project, the payments for services at the network sites are contingent upon both microwave and switching equipment to be installed prior to payment; therefore, invoices have not been submitted. The roll-out of switching equipment in Q2, 2012 will bring the first invoices for the services of installation of microwave and switching equipment allowing this milestone to show significant progress at that time. | 64 | This milestone is on schedule. | 2012-02-27 15:35 | 2012-02-27 15:35 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2012 | Q1 | Q1 - 2012 | 6006 | 5602 | FALSE | 53 | When measured by expenditures, the overall project percentage complete is anticipated to be only 53%; however, the project is actually on schedule. Due to the structure of our purchasing documents with the main vendor on the project, microwave radio installations as well as switching equipment installations were quoted together per site. As a result, our vendor is unable to invoice us for services rendered until both the microwave radio and the switching equipment have been installed at each site. According to the current project schedule, a majority of the switching equipment installations are scheduled to be completed within the second and early third quarters, as a result, we expect this percent complete to increase exponentially to show agreement with the baseline in the third quarter of 2012. | 82 | Customer Acquisition, Support and Billing | During Q2, we anticipate reaching 82% completion on the Customer Acquisition, Support and Billing portion of the project with payment of signification portions of this milestone during the second quarter. | 100 | This milestone is complete. | 77 | Our Network Design milestone is anticipated to climb to 77% of completion in the second quarter with the payment of invoicing for tower analyses and path surveys associated with multiple minor route changes. It is also anticipated that our team will have determined some of the final engineering to connect to last mile service providers and community anchor institutions. | 0 | N/A. This milestone does not apply to our project. | 0 | N/A. This milestone does not apply to our project. | 100 | This milestone is expected to reach completion for all site preparation known as of the writing of this report; however, it is anticipated that there may be additional site preparation at one or more of the sites newly added to the project through a series of route changes. | 52 | During Q2, our crews will shift their main focus from microwave radio upgrades to the installation and configuration of switching equipment before moving back to the microwave radio upgrades once again. The installation and configuration of the switching equipment during Q2 will enable invoicing and payment of this equipment likely within Q3. These additional expenditures are anticipated to bring the Equipment Procurement milestone into agreement with the baseline report in Q3. | 100 | This milestone is complete. | 10 | As noted above in the Equipment Procurement milestone, according to schedule, our crews will shift their main focus during Q2 from microwave radio upgrades to the installation and configuration of switching equipment before moving back to the microwave radio upgrades once again. With the shift in focus to switching equipment, our crews will complete the "service" tasks at multiple sites allowing for invoicing of the services rendered. The receipt and payment of these invoices will allow our Equipment Deployment milestone progress to come into agreement with the baseline report within Q3. As noted previously, this milestone has been deficient in progress due to the procurement vessel presented by our vendor which tied the payment of services to completion of both microwave radio upgrades and installation /configuration of the switching equipment. | 72 | This milestone is expected to remain on schedule. | 2012-05-10 11:34 | 2012-05-10 11:34 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2012 | Q2 | Q2 - 2012 | 6936 | 6095 | FALSE | 80 | It is anticipated that our project will reach 80% of overall project completion during the third quarter of 2012 and drastically reduce the gap between the baseline's predicted progress and the actual project progress to date. Much of the gain in progress can be attributed to the roll out of switching equipment upgrades that are scheduled to commence in the third quarter. The completion of this work on a site by site basis will allow our equipment vendor to begin invoicing not only for the equipment that they have installed and configured, but also for the services for equipment installations. | 100 | Customer Acquisition, Support and Billing | We anticipate catching up to our baseline and completing this milestone during the third quarter of 2012 with the payment of invoices for the customer billing solution and provisioning tools. | 100 | This milestone is complete. | 77 | The network design milestone is expected to climb slightly to 77% complete during the third quarter. The remaining elements to complete within this milestone include the design of our connection to last mile and whole sale providers as well as tower analyses and documentation for sites included within a route change that is currently under review. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 90 | It is expected that all site preparation for the current project would be completed in the third quarter; however, due to the submission of an Award Action Request (AAR), we would have a small amount of site preparation to complete at the sites included within this request, which is currently under review. | 83 | With the start of switching equipment installations to occur within the third quarter, it is expected that we will receive invoices for that switching equipment as well as the switching hubs. These expenditures will push the progress of this indicator closer to the baseline's predicted progress. We also expect that the invoices for this work will continue into the fourth quarter where progress for the milestone will come into compliance with the baseline report. | 100 | This milestone is complete. | 60 | We anticipate the equipment deployment milestone to see a large number of expenditures toward the end of the third quarter with the completion of many of the switching equipment upgrades. Completion of this work will allow our equipment vendor to invoice for the services of installing and configuring the microwave radios as well as the MPLS switching equipment on a site by site basis. | 85 | We anticipate this milestone to catch up to the baseline with the payment of invoices for much of the quality assurance work associated with the switching upgrades. | 2012-08-08 16:07 | 2012-08-08 16:07 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2012 | Q3 | Q3 - 2012 | 7822 | 6614 | FALSE | 87 | A large portion of the remaining expenditures on this project remain tied to the completion of our switching equipment upgrades. Those upgrades are expected to wrap up within the fourth quarter of 2012. Once complete, the vendor responsible for installing this equipment as well as the microwave equipment will be able to submit invoices for these deployments since they have quoted the work together on a site by site basis. We believe, by the close of the fourth quarter of 2012, that we will have completed a total of 69 of the 71 microwave radio links. | 99 | Customer Acquisition, Support and Billing | This milestone is expected to be in agreement with our baseline and nearly complete by the close of the fourth quarter. | 100 | This milestone is complete. | 100 | This milestone is complete. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 100 | This milestone is complete. | 99 | This milestone is expected to be in agreement with our baseline and nearly complete by the close of the fourth quarter. | 100 | This milestone is complete. | 80 | With the anticipated completion of our switching equipment upgrades during the fourth quarter, it is expected that a large portion of the invoices for equipment installations will be submitted and paid. With the approval of our most recent award action request (AAR), we anticipate the completion of another four microwave radio links and the invoices that would accompany this accomplishment as well. Knowing that the process to review and accept the vendor's work, document the changes to the site and submit an invoice takes time, it is believed that this category will not be completed until January of 2013 or possibly into our close out period. | 90 | This milestone is expected to be in agreement with our baseline by the close of the fourth quarter. | 2012-11-09 15:24 | 2012-11-09 15:24 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2012 | Q4 | Q4 - 2012 | 8778 | 7574 | FALSE | 92 | Our overall project will make significant progress in the first quarter with the anticipated arrival and payment of invoices for work completed in the fourth quarter. The vendor that is supplying our switching and microwave equipment had quoted the services to install both pieces of equipment together on a site by site basis, making them unable to invoice until the switching equipment had been installed and tested. We completed the assurance testing on those upgrades in mid December allowing the invoicing to begin. We also anticipate the receipt of invoices for equipment and the installation of our customer access platforms. Our percent complete will jump significantly to 92% and come close to agreement with the baseline predictions. | 100 | Customer Acquisition, Billing and Support | This milestone is expected to be in agreement with our baseline report and complete by the close of the first quarter. Completion of this milestone is reliant upon final end to end acceptance of the improved network to include billing and asset management. We are scheduled to complete testing of the network backbone in late January 2013. | 100 | This milestone is complete. | 92 | This milestone is on schedule. The network design that remains to be completed is in regard to the connections to our last mile service providers and Community Anchor Institutions. Due to the Commonwealth's requirement for the vendor to complete all work prior to invoicing, this milestone is expected to be complete just beyond the close of the first quarter of 2013. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 100 | This milestone is complete. | 97 | The equipment procurement milestone will jump to 97% of completion in the first quarter of 2013 with the receipt of invoices for switching equipment as well as a few links of microwave radios. This progress will bring our project into agreement with the baseline report. | 100 | This milestone is complete. | 98 | The equipment deployment milestone will soar to 98% of completion in the first quarter of 2013 with the receipt of invoices for the installation of microwave and switching equipment. This progress will bring our project into agreement with the baseline report. | 87 | The network testing milestone will increase to 87% of completion in the first quarter of 2013 as invoices are paid for much of the testing involved with the upgrades to the switching equipment. This progress trails that of the baseline report; however, we anticipate closing this gap just beyond the close of the first quarter. | 2013-02-14 14:14 | 2013-02-14 14:14 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2013 | Q1 | Q1 - 2013 | 9774 | 8421 | FALSE | 97 | We plan to have this milestone nearly complete within the second quarter of 2013. The only expenditures that we anticipate remaining would be associated with the end to end testing of the network and connections to last mile service providers and community anchor institutions. | 100 | Customer Acquisition, Support and Billing | We plan to complete this milestone within the second quarter of 2013 with the payment of all remaining invoices. | 100 | This milestone is complete. | 100 | We plan to complete this milestone within the second quarter of 2013 with the payment of all remaining invoices. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 100 | We plan to complete this milestone within the second quarter of 2013 with the payment of all remaining invoices. | 99 | We plan to have this milestone nearly complete within the second quarter of 2013. The only expenditures that we anticipate remaining would be associated with the connections to last mile service providers or community anchor institutions. | 100 | This milestone is complete. | 98 | We plan to have this milestone nearly complete within the second quarter of 2013. The only expenditures that we anticipate remaining would be associated with the connections to last mile service providers or community anchor institutions. | 92 | We plan to have this milestone nearly complete within the second quarter of 2013. The only expenditures that we anticipate remaining would be associated with the end to end testing of the network. | 2013-05-16 14:59 | 2013-05-16 14:59 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2013 | Q2 | Q2 - 2013 | 10622 | 8971 | FALSE | 100 | This milestone is expected to be complete. | 100 | Customer Acquisition, Support and Billing | This milestone is complete. | 100 | This milestone is complete. | 100 | This milestone is expected to be complete. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 100 | This milestone is expected to be complete. | 100 | This milestone is expected to be complete. | 100 | This milestone is complete. | 100 | This milestone is expected to be complete. | 100 | This milestone is expected to be complete. | 2013-08-16 14:28 | 2013-08-16 14:28 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | 2013 | Q3 | Q3 - 2013 | 11304 | 9451 | FALSE | 100 | This milestone is expected to be complete. Invoicing during the closeout period will bring this milestone category to 100% completion. | 100 | Customer Acquisition, Support and Billing | This milestone is complete. | 100 | This milestone is complete. | 100 | This milestone is expected to be complete. Invoicing during the closeout period will bring this milestone category to 100% completion. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 100 | This milestone is complete. | 100 | This milestone is expected to be complete. Invoicing during the closeout period will bring this milestone category to 100% completion. | 100 | This milestone is complete. | 100 | This milestone is expected to be complete. Invoicing during the closeout period will bring this milestone category to 100% completion. | 100 | This milestone is expected to be complete. Invoicing during the closeout period will bring this milestone category to 100% completion. | 2013-11-20 10:48 | 2013-11-20 10:48 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570018 | 2010 | Q3 | Q3 - 2010 | 454 | 1493 | FALSE | 85 | No significant variance | 0 | N/A | N/A | 100 | No significant variance | 35 | No significant variance | 16 | No significant variance | 0 | N/A | 22 | No significant variance | 40 | No significant variance | 99 | Completion of acquisition of FAC for Puerto Rico-Florida span. | 7 | No significant variance | 2 | No significant variance | 2010-11-30 11:27 | 2010-11-30 11:27 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2010 | Q4 | Q4 - 2010 | 1354 | 2369 | FALSE | 89 | No significant variance | 0 |  | N/A | 100 | No significant variance | 57 | No significant variance. | 64 | Contract negotiations for towers to be completed but funds won't be disbursed. | 0 | N/A | 67 | Recruitment delays of Network Analyst reflected in expenditures | 47 | Equipment procurement is proceeding as expected. Initial delays were encountered in delivery of core routing/switching equipment as we received defective equipment that had to be returned. While situation has been resolved and we are on track, fund disbursement will be affected which affects the baseline milestones. | 99 | No significant variance | 11 | Recruitment delays of Network Analyst reflected in expenditures. | 6 | Recruitment delays of Network Analyst reflected in expenditures. | 2011-02-24 08:16 | 2011-02-24 08:16 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2011 | Q1 | Q1 - 2011 | 2412 | 2951 | FALSE | 90 | No significant variance | 0 |  | NA | 100 | No variance | 65 | No significant variance | 64 | Due to delays in contract negotiations for tower sites, disbursement for payment not anticipated in this quarter. | 0 | NA | 80 | Recruitment delays of Network Analyst, RF Engineer reflected in expenditures. | 45 | We anticipate completion of procurement selection process for RF equipment, however funds will not be disbursed in this quarter for payment on equipment. | 99 | No significant variance | 18 | Recruitment delays of Network Analyst, RF Engineer reflected in expenditures | 11 | Recruitment delays of Network Analyst, RF Engineer reflected in expenditures | 2011-05-31 16:37 | 2011-05-31 16:37 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2011 | Q2 | Q2 - 2011 | 2442 | 2966 | FALSE | 92 | No significant variance | 0 |  | N/A | 100 | No variance | 74 | No significant variance | 94 | We anticipate completion of contracts and dibursement of payment in this quarter. | 0 | N/A | 81 | Equipment will be received at the end of the quarter. | 47 | We anticipate completion of procurement selection process for RF equipment, however funds will not be disbursed in this quarter for payment on equipment. | 99 | No significant variance | 26 | While recruitment has been completed, original delays in staff recruiting continues to be reflected in expenditures | 16 | While recruitment has been completed, original delays in staff recruiting continues to be reflected in expenditures | 2011-07-11 18:21 | 2011-07-11 18:21 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2011 | Q3 | Q3 - 2011 | 4038 | 3859 | FALSE | 96 | 3% variance as a result of site acquisitions, delayed network equipment arrival. | 0 |  | N/A | 100 | No variance | 79 | No significant variance | 100 | Completion of acquisition of all wireless sites. | 0 | N/A | 95 | No variance | 88 | No variance | 99 | No variance | 35 | Wireless network equipment expected to arrive at the end of the quarter. | 19 | Wireless network equipment expected to arrive at the end of the quarter. | 2011-11-14 16:14 | 2011-11-14 16:14 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2011 | Q4 | Q4 - 2011 | 4962 | 4635 | FALSE | 97 | No variance from baseline | 0 |  | NA | 100 | No variance from baseline | 93 | 6% variance from baseline due to redesign and engineering of network and preparation of route change. | 100 | Actual Milestone Value: 101.78%. Exceeded original budget due to expansion of network route in approved route change and acquisition of additional tower sites. Program Income will be used to fund additional costs. | 0 | NA | 95 | 2% variance from baseline. | 100 | Actual Milestone Value 104%. This milestone has exceeded the original budget because of (a) additional equipment costs due to approved route change and (b) increase in valuation of an in-kind contribution as approved by the grants office and will be booked this quarter. Program Income will be used to fund the necessary equipment for the route change. | 99 | No variance from baseline | 45 | Variance of 17% due to route change approval process. Equipment has been procured, and we anticipate the receipt in middle of quarter, and initiation of deployment at end of quarter. | 38 | 8% variance due to route change and delays in equipment deployment. | 2012-02-13 10:38 | 2012-02-13 10:38 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2012 | Q1 | Q1 - 2012 | 6178 | 5691 | FALSE | 98 | No significant variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 98 | Exceeded baseline due to increased costs associated with route change. | 100 | Actual Milestone Value: 102%. Exceeded original budget due to expansion of network route in approved route change and acquisition of additional tower sites. Program Income will be used to fund additional costs. | 0 | N/A | 96 | Variance of 2% due to delays subject to route change & FCC license delays | 100 | Actual Milestone Value 109%. This milestone has exceeded the original budget because of (a) additional equipment costs due to approved route change and (b) increase in valuation of an in-kind contribution as approved by the grants office and will be booked this quarter. Program Income will be used to fund the necessary equipment for the route change. | 99 | No significant variance from baseline | 54 | 18% variance due to route change, pending FCC licenses | 48 | 9% variance due to route change, pending FCC licenses | 2012-05-18 11:07 | 2012-05-18 11:07 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2012 | Q2 | Q2 - 2012 | 6926 | 6090 | FALSE | 98 | No significant variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 95 | No significant variance from baseline | 100 | No significant variance from baseline | 0 | N/A | 98 | No significant variance from baseline | 92 | Procurement of licensed wireless equipment delayed due to FCC license issuance delays. | 99 | No significant variance from baseline | 65 | Deployment delayed due to FCC license issuance delays | 59 | Testing delayed due to FCC license issuance delays | 2012-08-08 14:34 | 2012-08-08 14:34 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2012 | Q3 | Q3 - 2012 | 7812 | 6609 | FALSE | 99 | No significant variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 95 | No significant variance from baseline | 100 | Actual 101.99% Exceed budget due to approved network route change and acquisition of additional tower sites. | 0 | N/A | 98 | No significant variance from baseline | 98 | Variance due to final procurement of equipment for last POI as submitted under Route Change | 99 | No variance from baseline | 79 | Deployment delayed because of FCC license issuance delays. | 70 | Testing delays due to deployment delays. | 2012-11-09 11:20 | 2012-11-09 11:20 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2012 | Q4 | Q4 - 2012 | 8716 | 7520 | FALSE | 100 | Actual: 99.7%. Variance due to expenditures pending disbursement related to closeout of project, including audit & legal. | 0 |  | NA | 100 | No variance | 100 | No variance | 100 | No variance | 0 | NA | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2013-02-12 08:50 | 2013-02-12 08:50 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2013 | Q1 | Q1 - 2013 | 9880 | 8478 | FALSE | 99 | Extension received in February 2013 to permit expansion of project to include PRBI-TU segment | 0 |  | NA | 100 | NA | 100 | Actual 104%, due to final design work of PRBI-TU segment | 100 | No variance | 0 | NA | 100 | We anticipate this will exceed 100% in next quarter, as we will incur costs related to expanded PRBI-TU segment which was not included in original baseline. | 99 | Variance due to expansion of project. | 99 | Variance due to expansion of project. | 89 | Variance due to expansion of project. | 85 | Variance due to expansion of project. | 2013-05-23 08:42 | 2013-05-23 08:42 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2013 | Q2 | Q2 - 2013 | 10708 | 9017 | FALSE | 100 | Extension approved through September 30, 2013. | 0 |  | NA | 100 | No variance | 100 | Project completion date: September 30, 2013 | 100 | No variance | 0 | NA | 100 | Project completion date: September 30, 2013 | 100 | Project completion date: September 30, 2013 | 100 | Project completion date: September 30, 2013 | 100 | Project completion date: September 30, 2013 | 100 | Project completion date: September 30, 2013 | 2013-08-23 11:19 | 2013-08-23 11:19 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | 2013 | Q3 | Q3 - 2013 | 11632 | 9752 | FALSE | 100 | Project Closeout Period End Date: 12/28/2013 | 0 |  | NA | 100 | Project Closeout Period End Date: 12/28/2013 | 100 | Project Closeout Period End Date: 12/28/2013 | 100 | Project Closeout Period End Date: 12/28/2013 | 0 | NA | 100 | Project Closeout Period End Date: 12/28/2013 | 100 | Project Closeout Period End Date: 12/28/2013 | 100 | Project Closeout Period End Date: 12/28/2013 | 100 | Project Closeout Period End Date: 12/28/2013 | 100 | Project Closeout Period End Date: 12/28/2013 | 2014-01-21 11:27 | 2014-01-21 11:27 | 5487 | 5487 | Critical Hub Networks, Inc | TRUE
NT10BIX5570019 | 2010 | Q2 | Q2 - 2010 | 47 | 1289 | FALSE | 10 |  |  |  |  | 100 |  | 80 |  | 90 |  | 50 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2010 | Q3 | Q3 - 2010 | 298 | 1415 | FALSE | 20 | No Information to add at this time. | 0 |  | N/A | 100 | No Information to add at this time. | 100 | No Information to add at this time. | 100 | No Information to add at this time. | 100 | No Information to add at this time. | 35 | No Information to add at this time. | 0 | N/A | 15 | No Information to add at this time. | 0 | N/A | 0 | N/A | 2010-11-01 11:20 | 2010-11-01 11:20 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2010 | Q4 | Q4 - 2010 | 1130 | 2168 | FALSE | 20 | Construction delayed due to approval of PA. | 0 |  | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 100 | VMRC permit requires fifteen day comment period. Delay possible. | 45 | EA approval 12-7-10. Weather may delay completion of site preparation. | 0 | Delay in construction which delays start of equipment procurement to Y2Q2. | 15 | Weather ill hinder construction activities. | 0 | Delay in construction delays start of equipment deployment to Y2Q2. | 0 | Zero Variance | 2011-02-14 11:43 | 2011-02-14 11:43 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2011 | Q1 | Q1 - 2011 | 2094 | 2792 | FALSE | 30 | Delay in EA and PA delayed construction start date. Adding more contractors will improve productivity. | 0 |  | N/A | 95 | Awaiting design changes | 100 | N/A | 100 | N/A | 100 | N/A | 40 | Bidding Process delayed start of construction | 100 | N/A | 30 | Construction start delayed by PA approval. Equipment to be received in Y2Q2 & Y2Q3 | 15 | Delay in price quotes delayed procurement. While the deployment has been delayed, equipment deployment can be worked in conjunction with the cable construction component once the site work is completed. We should complete the equipment deployment by the time the cable is available. | 0 | N/A | 2011-05-17 15:09 | 2011-05-17 15:09 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2011 | Q2 | Q2 - 2011 | 2990 | 3252 | FALSE | 55 | Construction start delayed until March 2011. Project to be 55% complete by end of Y2Q3. | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 50 | Construction on nodes/site preparation started 7-15-11. Should complete 2 of the 4 sites by end of Y2Q3. | 100 | To receive remainder of transport equipment be end of Y2Q3. | 67 | Construction start delayed until March 2011. Equipment delivery, including fiber optic cable and transport equipment, has been delayed by vendors. We expect to begin equipment installation in 8-11 and to place approximately 120 miles of cable in Y2Q3. | 40 | Remainder of equipment to be received in Y2Q3. Installation to begin 8-11 and complete by 11-2011. | 40 | Will begin network testing as nodes (huts) are completed and as network equipment is received and installed. Both should be completed in Y2Q4. | 2011-08-09 16:54 | 2011-08-09 16:54 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2011 | Q3 | Q3 - 2011 | 4004 | 3841 | FALSE | 55 | Project to be 55% complete in Y2Q4. | 0 |  | N/A | 100 | Timely submission of any feedback questions; SHPO consultation report received by 11-3-11.EA submitted to NTIA by 11-15-11 | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Additional resources to make up for loss time due to inclement weather. | 100 | Ensure all equipment is received from vendor and payment is processed. | 84 | Expect to complete nodes and place 95 miles of fiber in Y2Q4. | 50 | Install equipment in 2 node sites. Complete deployment by Y3Q1. | 60 | Test completed backbone cable and 2 node sites. Complete testing by Y3Q1. | 2011-11-14 09:00 | 2011-11-14 09:00 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2011 | Q4 | Q4 - 2011 | 4866 | 4565 | FALSE | 77 | Will complete remaining construction. Final billing & equipment testing to complete Y3Q3. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 80 | To be completed Y3Q3. Delayed due to site preparation delay. | 75 | To be completed Y3Q3 | 2012-02-03 14:37 | 2012-02-03 14:37 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2012 | Q1 | Q1 - 2012 | 5966 | 5582 | FALSE | 71 | Became evident in Y3Q1 that project would be under budget. Submit a budget modification and route modification for approval in Y3Q2. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete remaining 21 miles in segment 1, 4 & 5 in Y3Q2 | 85 | To be completed Y3Q3. Delayed due to site preparation delay. | 85 | To be completed Y3Q3 | 2012-05-08 14:24 | 2012-05-08 14:24 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2012 | Q2 | Q2 - 2012 | 6952 | 6103 | FALSE | 84 | Submitted route modification to expend the remaining budgeted amount by Y3Q4 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete remaining 8 miles in Y3Q3 | 100 | To be completed in Y3Q3; manpower issues | 100 | To be completed in Y3Q3 | 2012-08-09 09:27 | 2012-08-09 09:27 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2012 | Q3 | Q3 - 2012 | 7754 | 6571 | FALSE | 98 | Project to be completed by end of Y3Q4 | 0 |  | N/A | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 2012-11-01 13:35 | 2012-11-01 13:35 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2012 | Q4 | Q4 - 2012 | 8666 | 7487 | FALSE | 93 | Project extension requested to complete route modification to VSU. Delayed due to easements | 0 | true | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 98 | Cannot complete until all cable is competed | 98 | Cannot complete until all equipment is installed | 2013-02-07 16:14 | 2013-02-07 16:14 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2013 | Q1 | Q1 - 2013 | 9608 | 8335 | FALSE | 96 | Approved route modification to be completed by approved project extension date of 6-30-13 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-05-06 09:59 | 2013-05-06 09:59 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | 2013 | Q2 | Q2 - 2013 | 12310 | 10483 | FALSE | 100 | Complete; 95% of Grant amount spent | 0 |  | N/A | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 2014-07-18 15:24 | 2014-07-18 15:24 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570023 | 2010 | Q3 | Q3 - 2010 | 12014 | 10177 | FALSE | 30 | Final network design (physical layer) complete, equipment procurement and leasing of commercial towers underway. Delay due to engineering re-evaluation has pushed our expectation for negotiation of all leases beyond this quarter. While substantial progress will be made, the percentage complete (based on dollars spent) will be lower than planned in baseline. We will be fully back on schedule in the subsequent quarters. | 35 | In-kind Contributions | On target | 0 | Exempt | 85 | On Target | 0 | N/A | 30 | The Project Management Office will establish permitting procedures for each county and streamline the overall permitting process. However, permitting for deployment of radios and site equipment will only be complete for a limited number of sites. | 30 | Site preparation will remain behind schedule this quarter due to the delays resulting from re-evaluation of engineering design in the previous quarter. Site preparation should be caught up in subsequent quarters. | 50 | RFPs completed, advertised, and distributed, and vendors selected. Evaluation/selection scheduled to be complete by the end of the next quarter. However, contracting (including proof of concept) will not be complete until the following quarter. Again, as a result of engineering delays. | 25 | Slight modification in requirements of Level 3 IRU orders/delivery as a result of revised engineering design have delayed initiation of Level 3 execution of certain orders (by our request). Level 3 will endeavor to accelerate delivery once final design requirements are completed. | 0 | Contracting (including proof of concept) of equipment vendors won't be complete until the following quarter due to delays resulting from revised engineering design as referenced above. | 0 | Network testing follows equipment deployment and has therefore been moved forward to later in the schedule due to delays resulting from revised engineering design as referenced above. | 2014-03-31 22:18 | 2014-03-31 22:18 | 6524 | 6524 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2010 | Q4 | Q4 - 2010 | 1352 | 2367 | FALSE | 50 | As mentioned above, the re-evaluation of the network design approach that began in previous quarters and continued through this reporting quarter resulted in an overall project delay and has impacted most major milestone categories, including site preparation, equipment procurement, network build, equipment deployment, network testing, and in-kind lease agreements, where further progress was originally anticipated according the Baseline Report. While substantial progress continues to be made in regard to network design and equipment deployment, the percentage complete (based on dollars spent) remains lower than planned in the baseline plan for this reporting period. We expect to be fully back on schedule in subsequent quarters, as indicated by the planned completion percentages listed below. | 45 | Commercial Tower Leases | On-target. We will continue the process of checking for previous / duplicate federal funding for targeted in-kind assets, per the Grants Officeâ€™s request. | 0 | Exempt | 88 | Network design is expected to remain on schedule, with final structural assessments completed by next quarter. | 0 | N/A | 50 | Permitting for deployment of radios and site equipment will be complete for a limited number of sites. Tower company certification requirements and application procedures will be established, and the application process is expected to be initiated next quarter. | 50 | It is our expectation that site preparation will get back on track with the baseline reportâ€™s scheduled completion percentages in subsequent quarters upon execution of commercial tower leases, which are pending Grants Office review and approval of the tower lease language. | 93 | Equipment RFPs were released, equipment vendors were selected and approved, and initial equipment purchase orders were executed during this current reporting period. Therefore, we anticipate equipment procurement to be on schedule by the end of next quarter. | 89 | Contract with Level 3 is in place. Upstream design configuration is complete, and circuit delivery is on schedule. Installation of data center equipment at Level 3â€™s Tampa and Orlando co-location facilities is expected to get underway next quarter. | 30 | As noted above, revised engineering design is nearly complete, equipment RFPs were released, equipment vendors were selected and approved, and initial equipment purchase orders were executed during this current reporting period. Therefore, we anticipate that equipment deployment should get back on schedule over the next two quarters, notwithstanding any potential delays from pending Davis-Bacon wage decision requests and the Grants Office review and approval of our tower lease agreement language. | 20 | As network testing is closely tied to equipment deployment, we anticipate that this milestone category will be back on schedule over the next two quarters, notwithstanding any potential delays from pending Davis-Bacon wage decision requests and the Grants Office review and approval of our tower lease agreement language. | 2011-02-24 07:24 | 2011-02-24 07:24 | 5502 | 5502 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2011 | Q1 | Q1 - 2011 | 2216 | 2853 | FALSE | 50 | The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. As we continue to make progress with site acquisition and pre-deployment activities, we anticipate that the overall project completion schedule will be back in line with Baseline Plan projections in subsequent quarters. | 5 | In-Kind Tower Licenses | The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. As part of our efforts to catch up to the Baseline Plan, the North Florida Broadband Authority's General Counsel has been working closely with the Grants Office and the Program Office to finalize the format and acceptable language required in all lease documents for the project, including the in kind leases. | 0 | N/A. Categorically exempt from Environmental Assessment. | 91 | Network design is expected to remain on schedule. | 0 | N/A | 60 | Building permit acquisition is expected to remain on schedule. | 0 | Progress reported for this milestone category in previous Performance Progress Reports was attributed to the progress of work associated with the development of the Request for Quotes procurement document for Civil and Electrical Site Work. As noted in Section 1, Item #3, we are in the process of preparing a budget reallocation Award Action Request to reconcile or adjust our SF-424C budget categories that were originally based on the turnkey link network design project plan. Upon approval of the Award Action Request, the budget amount originally allocated for Site Preparation will be re-allocated to other Cost Classification categories. | 40 | The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. Equipment procurement is currently moving forward with purchase orders and invoices being processed for all network equipment categories. Therefore, we anticipate that this milestone category will be back in line with the Baseline Plan over the next two quarters | 65 | The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. We expect the majority of structural assessments and site license agreements to be complete by the end of the next quarter, and therefore we anticipate that Network Build progress will be back in line with the Baseline Plan by the end of the next quarter. | 20 | The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. We anticipate that Equipment Deployment will be on track with the Baseline Plan over the next two to three quarters. | 15 | The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. As Network Testing is coordinated with Equipment Deployment, we expect that this milestone category will also be be back on track with the Baseline Plan over the next two to three quarters. | 2011-05-20 14:13 | 2011-05-20 14:13 | 6621 | 6621 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2011 | Q2 | Q2 - 2011 | 3216 | 3369 | FALSE | 54 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. As we continue to make progress with ongoing site acquisition and network deployment activities, we anticipate that the overall project completion schedule will be back in line with Baseline Plan projections in subsequent quarters. | 5 | In-Kind Contributions | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. As part of our efforts to catch up to the Baseline Plan, we are re-establishing our efforts to execute in-kind asset leases as lateral site acquisition is being dove-tailed into the beta and early adopter customer acquisition process. | 0 | N/A. Categorically exempt from Environmental Assessment. | 94 | Network design is expected to remain on schedule. | 0 | N/A | 70 | Building and electrical permit acquisition is expected to remain on schedule. | 0 | In previous Performance Progress Reports (submitted prior to the Performance Progress Report for 1st Quarter 2011), progress reported for this milestone category in previous Performance Progress Reports was attributed to the progress of work associated with the development of the Request for Quotes procurement document for Civil and Electrical Site Work. As noted in Section 1, Item #3, we prepared a draft budget reallocation Award Action Request to submit for review and approval to the Program Office to reconcile or adjust our SF-424C budget categories that were originally based on the turnkey link network design project plan. Upon approval of the Award Action Request, the budget amount originally allocated for Site Preparation will be re-allocated to other Cost Classification categories. | 57 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. Equipment procurement continues to move forward as purchase orders for network equipment are being executed, invoiced, and paid on an ongoing basis. Microwave radios and antennas are also currently being purchased, received, inventoried, and staged for deployment. | 57 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. We expect final fiber connections and testing to be completed at our four Point of Presence sites and also our two datacenter locations by the end of the next reporting period. We also expect significant expenditures for tower lease payments that were pending modification of site license agreements that had stemmed fro | 70 | This milestone category is currently scheduled to catch up to Baseline Plan projections by the end of next quarter. | 20 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. As Network Testing is follows in closely behind Equipment Deployment, we expect that this milestone category will also be be back on track with the Baseline Plan over the next two quarters. | 2011-08-18 18:34 | 2011-08-18 18:34 | 5502 | 5502 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2011 | Q3 | Q3 - 2011 | 4358 | 4035 | FALSE | 69 | Prior to the suspension of grant funding, planned project progress was expected to be at 89%, based on our estimated projections for expenditures for 4th quarter of 2011. We would have therefore exceeded our original Baseline Plan projection of 87.13% for overall project completion for the next quarter. | 100 | In-Kind Contributions | We confirmed our inventory of committed in-kind contributions for our Federal match requirement. As Federal funding is fully reinstated, we fully expect to make substantial progress toward booking these assets over the next reporting period. | 0 | N/A. Categorically exempt from Environmental Assessment. | 96 | Network design is expected to be on schedule. | 0 | N/A | 80 | Building and electrical permit acquisition is expected to remain on schedule. | 100 | We prepared a draft budget reallocation Award Action Request to submit for review and approval to the Program Office to reconcile or adjust our SF-424C budget categories that were originally based on the turnkey link network design project plan. Upon approval of the Award Action Request, the budget amount originally allocated for Site Preparation will be reallocated to other Cost Classification categories. | 96 | The anticipated progress referenced here would have been the actual progress made in the 3rd Quarter of 2011 had Federal funds not been suspended. Upon reinstatement of Federal funding (expected to occur in October 2011), we fully expect to reach our Baseline goal for Equipment Procurement by next reporting period. | 94 | Upon reinstatement of Federal funding (expected to occur in October 2011), we fully expect to reach our Baseline goal for this Milestone category by next reporting period. | 80 | Upon reinstatement of Federal funding (expected to occur in late October 2011), we fully expect to reach our Baseline goal for this Milestone category as site-specific equipment installation resumes next reporting period. | 40 | Upon reinstatement of Federal funding (expected to occur in October 2011), we fully expect to make significant progress toward our original Baseline projection for this Milestone category by next reporting period as network testing will follow closely behind equipment deployment. | 2011-11-30 16:32 | 2011-11-30 16:32 | 6621 | 6621 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2011 | Q4 | Q4 - 2011 | 5384 | 5058 | FALSE | 71 | Most efforts during 4th quarter were to execute the transition plan and reinstate project funding. | 71 | In-kind | NFBA will work to memorialize the terms of individual site licenses with the contributing County governments. | 0 | n/a | 100 | Pending budget reallocation, current design evaluation and adjustments are being documented. | 0 | n/a | 85 | Pending Budget Reallocation currently underway, most permits have been obtained and transferred to Engineering. | 100 | Pending Budget Reallocation currently underway, Site preparation against current baseline shows completion. Once Budget reallocation is complete, this number will be adjusted to represent reality. | 96 | Budget Reallocation is currently underway where the budget will be reallocated accordingly. | 95 | Budget Reallocation is currently underway where the budget will be reallocated accordingly. | 70 | Budget Reallocation is currently underway where the budget will be reallocated accordingly. | 40 | Most efforts during the quarter were focused on executing the transition plan and building an organization to provide the necessary project oversight. | 2012-02-29 07:30 | 2012-02-29 07:30 | 7368 | 7368 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2012 | Q1 | Q1 - 2012 | 6076 | 5637 | FALSE | 83 | We are in position to complete core network deployment by the end of next quarter, and we will connect more customers as network sites are activated, tested, and made available for customer access. | 90 | In-Kind Contributions for Recipient Match | We expect to be on target with our baseline projection for this category. We will continue to memorialize the terms of individual site license agreements with our contributing member governments, and we expect to maintain proportionality with federal expenditures as required. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | Our core network design is functionally complete. However, we are continuing to work with demand forecasts in order to incorporate an enhancement plan that will address the original limitations in capacity and meet forecasted demand. We anticipate approval of our Budget Reallocation Award Action Request, which will address the cost impacts associated with this process. | 0 | N/A | 100 | All site permits have been obtained and transferred to our new General Contractor. | 100 | We anticipate approval of our Budget Reallocation Award Action Request, which will allow us to adjust the budget number for this category and establish a more accurate benchmark for measuring cost and schedule performance. | 98 | We expect to be on target with our baseline projection for this category. We also anticipate approval of our Budget Reallocation Award Action Request, which will reallocate any budget surplus in this category to other areas of need. | 98 | We expect to be on target with our baseline projection for this category, as we are in position to make a substantial progress payment on our Indefeasible Right of Use for upstream fiber access in the next reporting period. We also anticipate approval of our Budget Reallocation Award Action Request, which will reallocate any budget surplus in this category to other areas of need. | 90 | We expect to be on target with our baseline projection for this category. | 90 | We expect to be on target with our baseline projection for this category. | 2012-05-14 21:46 | 2012-05-14 21:46 | 6621 | 6621 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2012 | Q2 | Q2 - 2012 | 7190 | 6222 | FALSE | 88 | Variance from the baseline plan is due to challenges faced this reporting period in addition to residual effects from transition-related issues that began in previous quarters. Please see Section 3 above for more details. We remain in position to complete our core network deployment by the end of next quarter, and we will continue to connect more customers as more network sites are activated, tested, and made available for customer access. | 95 | In-Kind Contributions for Recipient Match | We expect to be on target with our baseline projection for this category. We will continue to memorialize the terms of individual site license agreements with our contributing member governments, and we expect to maintain proportionality with federal expenditures as required. | 0 | N/A. Categorically exempt from Environmental Assessment. | 90 | Planned progress is projected against our approved revised budget, resulting in the anticipated completion percentage being decreased for this milestone category in comparison to our previous Performance Progress Report. We will continue to work with demand forecasts to drive our network design enhancement plan, which is being implemented in parallel with network deployment as we move outward from our Fiber Access Points, through the core network, and into the communities that will be served by our network. | 0 | N/A | 99 | Planned progress is projected against our approved revised budget, resulting in the anticipated completion percentage being decreased for this milestone category in comparison to our previous Performance Progress Report. We expect to be on target with our baseline projection for this category. Approval of resubmitted permit applications from local permitting agencies is expected next quarter. Please see section 3 above for more details. | 99 | Planned progress is projected against our approved revised budget, resulting in the anticipated completion percentage being decreased for this milestone category in comparison to our previous Performance Progress Report. We expect to be on target with our baseline projection for this category. | 99 | We expect to be on target with our baseline projection for this category. | 99 | We expect to be on target with our baseline projection for this category. | 95 | We expect to be on target with our baseline projection for this category. | 95 | We expect to be on target with our baseline projection for this category. | 2012-08-21 14:47 | 2012-08-21 14:47 | 7368 | 7368 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2012 | Q3 | Q3 - 2012 | 7952 | 6681 | FALSE | 95 | Our core network will be fully operational by the end of next quarter, and in that regard we are on target with our baseline projection for core network completion. In order to ensure that our network is capable of meeting customer demand according to Service Level Agreement requirements, we anticipate that our current and planned network enhancement activities will continue beyond the end of next quarter through the end of the federal grant period. | 98 | In-Kind Contributions for Recipient Match | We expect to be on target with our baseline projection for this category. We will continue to memorialize the terms of individual site license agreements with our contributing member governments, and we expect to maintain proportionality with federal expenditures as required. | 0 | N/A. Categorically exempt from Environmental Assessment. | 96 | Core network design is functionally complete. However, we are continuing to address the performance and capacity limitations of our pre-transition period network design. We will therefore continue to work with demand forecasts to drive our network design enhancement plan, and will remain engaged with executing concurrent processes of identifying strategic core network locations for enhancement and finalizing network enhancement equipment specifications. | 0 | N/A | 100 | Permitting is complete for our core network tower sites. | 100 | Civil and site electrical work will be complete at our last remaining core network tower site by the end of next quarter. | 100 | Core network equipment procurement is complete. However, we anticipate that procurement activities for network enhancement equipment will continue beyond the end of next quarter through the end of the federal grant period. | 99 | Site acquisition is complete for our core network datacenters, fiber access points, and core tower sites. However, as part of our network enhancement effort, we will continue to explore options and conduct cost/benefit analysis for increasing the quantity of fiber access points at strategic areas of our core network. We expect this activity to continue past the end of next quarter through the end of the federal grant period. | 96 | Core network equipment installation will be complete at our last remaining core network tower site by the end of next quarter. However, the installation of additional licensed microwave radios and antennas at selected core tower sites is planned as part of our network enhancement effort. We expect this activity to continue past the end of next quarter through the end of the federal grant period. | 96 | Core network equipment testing will be complete by the end of next quarter. However, testing of additional licensed microwave radios and antennas at selected core tower sites is planned as part of our network enhancement effort. We expect this activity to continue past the end of next quarter through the end of the federal grant period. | 2012-11-19 10:31 | 2012-11-19 10:31 | 7368 | 7368 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2012 | Q4 | Q4 - 2012 | 9072 | 7846 | FALSE | 100 | Our core network is complete and fully operational. We will continue with our network enhancement activities while building links out from the core network by using our in kind tower sites to create lateral extensions to reach target customers and facilitate connectivity to Community Anchor Institutions. | 100 | In-Kind Contributions for Recipient Match | We will continue to incorporate in-kind assets into our roll-out schedule as lateral extensions of our core network to reach our target customers and connecting Community Anchor Institutions. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | Core network design is complete. We will continue with ongoing link design and engineering activities as necessary to build out from our new Fiber Access Point and to activate lateral network extensions with our in kind towers. | 0 | N/A | 100 | Permitting is complete for our core network tower sites. | 100 | Civil and site electrical work is complete at all of our core network tower sites. | 100 | Core network equipment procurement is complete. We will continue with equipment procurement activities as necessary to build out our in kind tower sites to reach target customers, as well as to ensure that network capacity and performance are aligned with forecasted customer demand. | 100 | Site acquisition is complete for our core network datacenters, original fiber access points, and core tower sites. We will continue to explore options and conduct cost/benefit analysis for integrating additional fiber access points at strategic areas of our core network. | 100 | Core network equipment deployment is complete. We will continue to install additional licensed microwave radios and antennas at selected core tower sites as part of our ongoing network enhancement effort. We will also continue to install equipment as necessary to build out our in kind tower sites to reach our target customers and facilitate connectivity to Community Anchor Institutions. | 100 | Core network equipment testing is complete. We will continue with testing and commissioning activities as additional links are brought online to integrate our new Fiber Access Point and our in-kind towers. | 2013-02-28 13:09 | 2013-02-28 13:09 | 7368 | 7368 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2013 | Q1 | Q1 - 2013 | 9748 | 8408 | FALSE | 99 | We will continue to expand our network by using our in kind tower sites as lateral extensions of our core network to reach target customers and facilitate connectivity to Community Anchor Institutions. As noted above, our Award Action Request to extend our grant period to September 30, 2013 was approved, and therefore, milestone percent complete quantities projected for next quarter may vary from our original baseline plan projections, as these were based on percent complete estimates corresponding to the original January 31, 2013 project completion date. | 100 | In-Kind Contributions for Recipient Match | We will continue to incorporate in-kind assets as lateral extensions of our core network to reach our target customers and to connect Community Anchor Institutions. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | Core network design is complete. We will continue with ongoing link design and engineering activities as necessary to build out from our new fiber access point and to activate lateral network extensions with our in kind towers. | 0 | N/A | 100 | Permitting is complete for our core network tower sites. | 100 | Civil and site electrical work is complete at all of our core network tower sites. | 100 | Core network equipment procurement is complete. We will continue with equipment procurement activities as necessary to build out our in kind tower sites to reach target customers, as well as to ensure that network capacity and performance are aligned with forecasted customer demand. | 100 | Site acquisition is complete for our core network data centers, original fiber access points, our new Palatka fiber access point, and core tower sites. We will continue to explore options for integrating additional fiber access points at strategic areas of our core network as necessary to ensure that network capacity and performance are aligned with forecasted customer demand. | 99 | Core network equipment deployment is complete. We will continue to install additional licensed microwave radios and antennas at selected core tower sites as part of our ongoing network enhancement effort. We will also continue to install equipment as necessary to build out our in kind tower sites to reach our target customers and facilitate connectivity to Community Anchor Institutions. | 99 | Core network equipment testing is complete. We will continue with testing and commissioning activities as additional links are brought online for the integration of our new Fiber Access Point and our in-kind towers. | 2013-05-15 16:39 | 2013-05-15 16:39 | 7368 | 7368 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2013 | Q2 | Q2 - 2013 | 12012 | 10176 | FALSE | 100 | The project will be complete by the end of the next quarter. We will continue to expand our network by building-out in-kind tower infrastructure to reach more customers. We will also continue to develop relationships with last mile providers, utility companies, anchor institutions, and strategic partners to ensure sustainability and growth so that our network will continue to be a source of opportunity for economically distressed businesses in our communities. | 100 | In-Kind Contributions for Recipient Match | We will continue to incorporate in-kind assets as lateral extensions of our core network to reach target customers and to enable connectivity to community anchor institutions. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | Core network design and enhancement strategy activities are complete. | 0 | N/A | 100 | Permitting is complete for our core network tower sites. | 100 | Civil and site electrical work is complete at our core network tower sites and fiber access points. | 100 | Core network equipment procurement is complete. We will continue to reinvest in our network infrastructure and proceed with equipment procurement as necessary to build out our in kind tower sites to reach target customers and to ensure that network capacity and performance are aligned with customer demand forecasts. | 100 | Site acquisition is complete for our core network data centers, fiber access points, and core tower sites. | 100 | Core network equipment deployment is complete. We will continue to reinvest in our network infrastructure and install equipment as necessary to build out our in kind tower sites to reach target customers and facilitate connectivity to community anchor institutions. | 100 | Core network equipment testing is complete. We will continue with testing and commissioning activities as lateral links are brought online through the integration of our in-kind tower infrastructure. | 2014-03-31 22:13 | 2014-03-31 22:13 | 6524 | 6524 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | 2013 | Q3 | Q3 - 2013 | 11446 | 9564 | FALSE | 100 | The project is 100% complete, as determined by total federal expenditures plus allowable in-kind contributions for recipient match. We will continue to reinvest and expand our network and develop relationships with last mile providers, utility companies, anchor institutions, and strategic partners to ensure the sustainability and growth of our network. | 100 | In-Kind Contributions for Recipient Match | We will continue to incorporate in-kind assets as lateral extensions of our core network to reach target customers and enable connectivity to community anchor institutions. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | Core network design and enhancement strategy activities are complete. | 0 | N/A | 100 | Permitting is complete for our core network tower sites. | 100 | Civil site preparation and site electrical work is complete at our core network tower sites and fiber access points. | 100 | Core network equipment procurement is complete. We will continue to reinvest in our network infrastructure and proceed with equipment procurement as necessary to build out our in kind tower sites to reach target customers and enable connectivity to community anchor institutions. | 100 | Site acquisition is complete for our core network data centers, fiber access points, and core tower sites. | 100 | Core network equipment deployment is complete. We will continue to reinvest in our network infrastructure and deploy network access equipment as necessary to build out our in kind tower sites to reach target customers and facilitate connectivity to community anchor institutions. | 100 | Testing is complete for core network equipment. We will continue with testing and commissioning activities as lateral links are brought online through the integration of our in-kind tower infrastructure. | 2013-12-06 14:31 | 2013-12-06 14:31 | 6524 | 6524 | North Florida Broadband Authority | TRUE
NT10BIX5570024 | 2010 | Q2 | Q2 - 2010 | 48 | 1330 | FALSE | 12 |  | 0 |  |  | 100 |  | 100 |  | 40 |  | 40 |  | 20 |  | 30 |  | 10 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570024 | 2010 | Q3 | Q3 - 2010 | 334 | 1433 | FALSE | 36 | No variance to Baseline Report | 0 |  | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 0 | No variance to Baseline Report | 0 | No variance to Baseline Report | 0 | No variance to Baseline Report | 0 | No variance to Baseline Report | 0 | No variance to Baseline Report | 0 | No variance to Baseline Report | 0 | No variance to Baseline Report | 2010-11-17 11:08 | 2010-11-17 11:08 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2010 | Q4 | Q4 - 2010 | 1052 | 2090 | FALSE | 45 | No variance to Baseline Report | 0 |  | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 20 | No variance to Baseline Report | 20 | No variance to Baseline Report | 17 | No variance to Baseline Report | 17 | No variance to Baseline Report | 16 | No variance to Baseline Report | 16 | No variance to Baseline Report | 16 | No variance to Baseline Report | 2011-02-10 14:47 | 2011-02-10 14:47 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2011 | Q1 | Q1 - 2011 | 2074 | 2782 | FALSE | 15 | The U of U/UEN is projecting this milestone will not meet projected percentage of completion for the upcoming quarter. Although significant project progress will be made the amount of funds spent will be less than projected in the Baseline Report. The higher cost project activities, such as those with significant outside plant construction, are not scheduled to begin until the third quarter of this project year. The U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 0 |  | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 40 | No variance to Baseline Report | 40 | No variance to Baseline Report | 15 | The U of U/UEN is projecting this milestone will not meet projected percentage of completion for the upcoming quarter. Although significant project progress will be made the amount of funds spent will be less than projected in the Baseline Report. The higher cost project activities, such as those with significant outside plant construction, are not scheduled to begin until the third quarter of this project year. The U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 34 | This milestone is on schedule. The U of U/UEN will pre-order the equipment and supplies needed to complete site preparations, network build out and CAI testing and turn up for the forty (40) CAI projects scheduled for completion this quarter. | 15 | The U of U/UEN is projecting this milestone will not meet projected percentage of completion for the upcoming quarter. Although significant project progress will be made the amount of funds spent will be less than projected in the Baseline Report. The higher cost project activities, such as those with significant outside plant construction, are not scheduled to begin until the third quarter of this project year. The U of U/UEN's billing policy does not require pre payment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 15 | The U of U/UEN is projecting this milestone will not meet projected percentage of completion for the upcoming quarter. Although significant project progress will be made the amount of funds spent will be less than projected in the Baseline Report. The higher cost project activities, such as those with significant outside plant construction, are not scheduled to begin until the third quarter of this project year. The U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 15 | The U of U/UEN is projecting this milestone will not meet projected percentage of completion for the upcoming quarter. Although significant project progress will be made the amount of funds spent will be less than projected in the Baseline Report. The higher cost project activities, such as those with significant outside plant construction, are not scheduled to begin until the third quarter of this project year. The U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 2011-05-17 10:15 | 2011-05-17 10:15 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2011 | Q2 | Q2 - 2011 | 3300 | 3412 | FALSE | 22 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are ahead of schedule with the network construction and build out, the U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 0 |  | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 60 | No variance to Baseline Report | 60 | No variance to Baseline Report | 22 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are ahead of schedule with the network construction and build out, the U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 51 | This milestone is on schedule. The U of U/UEN will pre-order the equipment and supplies needed to complete site preparations, network build out and CAI installations required to meet project milestones. | 22 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are ahead of schedule with the network construction and build out, the U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 22 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are ahead of schedule with the network construction and build out, the U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 22 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are ahead of schedule with the network construction and build out, the U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 2011-08-24 17:52 | 2011-08-24 17:52 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2011 | Q3 | Q3 - 2011 | 4152 | 3924 | FALSE | 26 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 0 | N/A | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 80 | No variance to Baseline Report | 80 | No variance to Baseline Report | 26 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 68 | This milestone is on schedule. The U of U/UEN will pre-order the equipment and supplies needed to complete the site preparations, network build out and CAI installations required to meet project milestones. | 26 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 26 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 26 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 2011-11-18 17:35 | 2011-11-18 17:35 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2011 | Q4 | Q4 - 2011 | 4950 | 4628 | FALSE | 50 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 0 | N/A | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 50 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 100 | The U of U/UEN is expecting all equipment purchases will be completed during this quarter. | 50 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 50 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 50 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 2012-02-10 16:38 | 2012-02-10 16:38 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2012 | Q1 | Q1 - 2012 | 6332 | 5768 | FALSE | 45 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 0 | N/A | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 45 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 90 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. The Optronics for the Logan Middle Mile segment is the only outstanding equipment to be procured and cannot be ordered until fiber characterization is completed, which is scheduled for the second quarter. This schedule will permit lighting of the fiber for the Logan Middle Mile segment in the third quarter as projected. | 45 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 45 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 45 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 2012-05-29 16:00 | 2012-05-29 16:00 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2012 | Q2 | Q2 - 2012 | 6906 | 6079 | FALSE | 56 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 0 |  | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 56 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 100 | No variance to Baseline Report | 56 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 56 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 56 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 2012-08-07 16:40 | 2012-08-07 16:40 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2012 | Q3 | Q3 - 2012 | 7330 | 6294 | FALSE | 66 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 4th quarter of 2012. Aside from some invoicing and related payments that may carry over into the 1st quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 0 | N/A | N/A | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 66 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 4th quarter of 2012. Aside from some invoicing and related payments that may carry over into the 1st quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 100 | No variance to Baseline Report. | 66 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 4th quarter of 2012. Aside from some invoicing and related payments that may carry over into the 1st quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 66 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 4th quarter of 2012. Aside from some invoicing and related payments that may carry over into the 1st quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 66 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 4th quarter of 2012. Aside from some invoicing and related payments that may carry over into the 1st quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 2012-10-12 15:30 | 2012-10-12 15:30 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2012 | Q4 | Q4 - 2012 | 8656 | 7481 | FALSE | 68 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 1st quarter of 2013. Aside from some invoicing and related payments that may carry over into the close out period, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 0 | N/A | N/A | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 68 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 1st quarter of 2013. Aside from some invoicing and related payments that may carry over into the close out period, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 100 | No variance to Baseline Report. | 68 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 1st quarter of 2013. Aside from some invoicing and related payments that may carry over into the close out period, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 68 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 1st quarter of 2013. Aside from some invoicing and related payments that may carry over into the close out period, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 68 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 1st quarter of 2013. Aside from some invoicing and related payments that may carry over into the close out period, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 2013-02-06 18:01 | 2013-02-06 18:01 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2013 | Q1 | Q1 - 2013 | 10034 | 8567 | FALSE | 93 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 2nd quarter of 2013. Aside from some invoicing and related payments that may carry over into the 3rd quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 0 | N/A | N/A | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 93 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 2nd quarter of 2013. Aside from some invoicing and related payments that may carry over into the 3rd quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 100 | No variance to Baseline Report. | 93 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 2nd quarter of 2013. Aside from some invoicing and related payments that may carry over into the 3rd quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 93 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 2nd quarter of 2013. Aside from some invoicing and related payments that may carry over into the 3rd quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 93 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 2nd quarter of 2013. Aside from some invoicing and related payments that may carry over into the 3rd quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 2013-05-31 15:46 | 2013-05-31 15:46 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570024 | 2013 | Q2 | Q2 - 2013 | 12234 | 10405 | FALSE | 100 | The U of U/UEN completed the Utah's Broadband Technology Opportunities Program project, Utah Anchors: A Community Broadband Project on May 31st, 2013. This percentage for overall completion represents actual expenditures. | 0 | N/A | N/A | 100 | The NTIA approved the U of U/UEN Environmental Assessment and issued a Finding of No Significant Impact (FONSI) in November of 2010. | 100 | All network designs and contracts with Telecommunication Providers have been completed. | 100 | All Rights of Way for this project have been approved and build out is underway. | 100 | All Construction Permits have been granted and build out is completed. | 100 | All Site Preparations for the project are completed. | 100 | All equipment procurement for this project is completed. | 100 | The Network Build Out for the project is completed. | 100 | All project equipment and hardware for the project is installed and in operation. | 100 | All Network Testing was successfully completed prior to production implementation. | 2014-05-23 16:31 | 2014-05-23 16:31 | 5423 | 5423 | University of Utah, The | TRUE
NT10BIX5570025 | 2010 | Q2 | Q2 - 2010 | 49 | 1286 | FALSE | 68 |  |  |  |  | 100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | 2010 | Q3 | Q3 - 2010 | 336 | 1434 | FALSE | 2 | This is a variance from our baseline plan based on the additional EA work that needs to happen. This has delayed the issuance of a FONSI and payment to my subcontractors. Because I need to move money between line items on my award, this has caused a delay in engineering which will delay payments to my subcontractors. | 0 |  | N/A | 100 | N/A | 90 | N/A | 90 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-17 12:17 | 2010-11-17 12:17 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | 2010 | Q4 | Q4 - 2010 | 1136 | 2174 | FALSE | 5 | This has been delayed because of the delay with our Archeological Assessment and the weather. We cannot put shovels in the ground when there is snow. | 0 |  | N/A | 100 | N/A | 45 | N/A | 0 | N/A | 0 | N/A | 50 | This has been delayed because of the delay with our Archeological Assessment and the weather. We cannot put shovels in the ground when there is snow. | 50 | This has been delayed because of the delay with our Archeological Assessment and the weather. | 0 | N/A | 50 | Because of the delays with the equipment procurement above, we cannot deploy equipment. | 0 | N/A | 2011-02-14 15:50 | 2011-02-14 15:50 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | 2011 | Q1 | Q1 - 2011 | 1900 | 2695 | FALSE | 12 | This is 5% below our baseline but we should be able to catch up once our permits come in and we start ordering materials and start construction. We plan to be on track by next quarter. | 0 |  | N/A | 100 | N/A | 85 | We should be a little ahead of schedule the way we are moving. | 15 | This should be a little ahead of schedule based on having engineering and permits. | 15 | This should be a little ahead of schedule based on having engineering and permits. | 50 | This is behind because of permitting and acquisition. | 40 | This is behind because of permitting and acquisiton. | 5 | This is behind because of permitting and acquisiton. | 35 | This is behind because of permitting and acquisiton. | 0 | N/A | 2011-05-05 20:35 | 2011-05-05 20:35 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | 2011 | Q2 | Q2 - 2011 | 3400 | 3463 | FALSE | 50 | This is 18% behind our baseline. This is partially because of our route change approval delays and partially because of our cost savings from competitively bidding out our project. | 0 |  | N/A | 100 | N/A | 100 | N/A | 75 | This is 15% ahead of our baseline. | 75 | This is 15% ahead of our baseline. | 60 | This is 40% behind our baseline. We should have our sites identified, purchased and prepped, but I do not think that we will have all of our huts built and up and running. | 60 | This is 40% behind our baseline, but that is because of our permitting and construction schedule. | 50 | This is 20% behind our baseline, but that is because of the delays in permitting. While some permitting offices have been very responsive, some of the larger ones have caused us some delays along with reroutes and site changes requested by our customer. | 50 | This is 50% behind our baseline, but it lines up with our Network Build above. | 5 | This is 5% ahead of our baseline, this is based on our plan to light some of our sites as we go. | 2011-08-31 16:58 | 2011-08-31 16:58 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | 2011 | Q3 | Q3 - 2011 | 4196 | 3946 | FALSE | 41 | This is 57 percent under our baseline plan. Zayo is projecting coming in under budget. Based on our projections, even though we are only going to be at 41% of our baseline budget, we should be close to 85% actual miles complete. | 0 |  | This is on target with our baseline. | 100 | This is on target with our baseline. | 100 | This is on target with our baseline. | 100 | This is on target with our baseline. | 100 | This is on target with our baseline. | 54 | This is 56% behind our baseline because of delays in site procurement. | 100 | This is on target with our baseline. | 60 | This is 40% behind our baseline. In actuality, Zayo is projecting coming in under budget, so an accurate reflection of actual miles built would be 90% built. | 60 | This is 40% behind our baseline because of delays in site procurement and hut placement. | 0 | This is 70% under our baseline. This is because of permitting and build delays. | 2011-11-21 17:00 | 2011-11-21 17:00 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570026 | 2010 | Q2 | Q2 - 2010 | 50 | 1267 | FALSE | 6 |  | 0 |  |  | 100 |  | 50 |  | 50 |  | 15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2010 | Q3 | Q3 - 2010 | 342 | 1437 | FALSE | 5 | KINBER anticipates completing an RFP process in December 2010 to obtain a new vendor(s) to build the network. This change in Prime Contractor will result in a later construction start date of January 2011. | 0 |  | n/a | 100 | . | 25 | KINBER anticipates completing an RFP process in December 2010 to obtain a new vendor(s) to build the network. This change in Prime Contractor will result in a later construction start date of January 2011. | 0 | KINBER anticipates completing an RFP process in December 2010 to obtain a new vendor(s) to build the network. This change in Prime Contractor will result in a later construction start date of January 2011. | 0 | KINBER anticipates completing an RFP process in December 2010 to obtain a new vendor(s) to build the network. This change in Prime Contractor will result in a later construction start date of January 2011. | 0 | . | 0 | . | 0 | . | 0 | . | 0 | . | 2010-11-17 13:22 | 2010-11-17 13:22 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2010 | Q4 | Q4 - 2010 | 1304 | 2332 | FALSE | 5 | . | 0 | n/a | n/a | 100 | . | 50 | Completing the RFP process in Q3 and selecting a new vendor has resulted in a delay in the network design that will continue in Q1, 2011. Agreements, signed in December 2010, delayed the design process. | 17 | Completing the RFP process in Q3 and selecting a new vendor has resulted in a delay in acquiring ROW on the proposed schedule. ROW for overlash will be completed on approximately 300 miles of planned fiber. | 17 | Completing the RFP process in Q3 and selecting a new vendor has resulted in a delay in acquiring permits and approvals on the proposed schedule. It is anticipated that 300 miles of fiber will receive permits and approvals in Q1, 2011. | 30 | It is anticiapted that sites related to approximately 500 fiber miles will be completed. | 0 | . | 0 | . | 0 | . | 0 | . | 2011-02-22 15:28 | 2011-02-22 15:28 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2011 | Q1 | Q1 - 2011 | 1944 | 2717 | FALSE | 27 | KINBER projects $35M in construction related expenses in the next quarter as new fiber is hung in multiple segments along the network route. | 0 | n/a | n/a | 100 | Complete | 100 | Design will be complete in Q2 2011. | 23 | 400 miles of overlash, ROW recieved. Remaining 77% will be submitted. | 25 | 100% of pole permits submitted, awaiting approvals. | 10 | All engineering will be completed. | 0 | RFP for equipment to be awarded in Q2, 2011; procurement in Q3, 2011. | 2 | 50 miles of fiber will be completed | 0 | Project is on time for equipment deployment to begin in Q4 2011. | 0 | Project is on time for a portion of the network to begin testing in Q4 2011. | 2011-05-11 13:25 | 2011-05-11 13:25 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2011 | Q2 | Q2 - 2011 | 3076 | 3295 | FALSE | 29 | Project is slightly behind proposed baseline scheduling due to the realignment of the deliverable schedule when KINBER entered into a revised construction agreement with their replacement vendor (Sunesys). The construction completion schedule and payment schedule shifted but is expected to catch up to projected baseline in Q4, 2011. The slower than anticipated response for ROW and make ready permits from local utilities has also impacted the completion schedule of the project. | 100 | Fiber Procurement | KINBER has received 1,030 miles of fiber and has dedicated factory time and delivery dates for the remaining fiber necessary to construct the PennREN project. | 100 | Completed, except for unanticipated changes that may be made to the route. | 100 | Project on schedule. | 95 | Progress may be impacted by ROW approvals and/or route changes that arise during the construction process. | 50 | All permits will be submitted, KINBER may be subject to delays in the approval process of the various utilities. | 30 | Project on schedule. | 10 | Contract will be awarded to equipment vendor; purchase agreement will be executed and some equipment may be ordered. | 0 | Project on schedule. | 0 | Project is on time for equipment deployment in Q4, 2011. | 0 | Project is on-time for a portion of the network to begin testing in Q4, 2011. | 2011-08-15 10:53 | 2011-08-15 10:53 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2011 | Q3 | Q3 - 2011 | 4048 | 3866 | FALSE | 57 | Percent complete rate, as reported is estimated to be low because there is a lag in the time that work is done and the time KINBER is billed for the work.. This is due to the nature of the construction contract where the vendor is only paid based on completed milestones instead of work as it is done. KINBER expects to catch up in Q1 2012. | 100 | Fiber procurement | KINBER has received 1,030 miles of NZD fiber and has secured dedicated factory time for the production of the remaining fiber necessary to construct the PennREN project. | 100 | Project is on schedule | 95 | Network design was complete as of Q2, 2011 but KINBER was advsies of a potential overlap with another BTOP funded project (Zito Media). KINBER Is currently waiting for resolution of the overlap with Zito Media in Northwestern, PA. If approved, this change to the route could impact portions of the network design. | 45 | 90% of the ROW requests will be submitted. | 45 | The Verizon strike and weather have impacted the time it takes to get approvals from utility companies. | 65 | 40 of the 62 building entrances will be completed; project is on schedule. | 80 | Project is on schedule. | 0 | Weather and construction related delays have impacted the network completion at this time. | 0 | THE RFP evaluation for equipment took longer than anticipated. KINBER expects to have the equipment ordered and some received for testing in Q4, 2011. | 0 | Network is not yet built to be able to test anything. | 2011-11-15 16:11 | 2011-11-15 16:11 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2011 | Q4 | Q4 - 2011 | 5098 | 4768 | FALSE | 69 | Project is reported as slightly behind schedule due to the deliverable-based billing relationship it has with its construction vendor. Work that is incrementally completed may not be paid in full or reported until the segment has been fully completed and this skews the actual project completion reporting. | 100 | Fiber Procurement | KINBER has received over 1,030 miles of NZD fiber and has secured dedicated factory time to manufacture the remaining fiber necessary to build the network. | 100 | Project is on schedule. | 100 | Project is on schedule. | 100 | Project is on schedule. | 100 | Project is on schedule. | 92 | Project is on schedule. | 95 | Project is on schedule. | 50 | Project is on schedule. | 40 | Project is on schedule. | 40 | Project is on schedule. | 2012-02-17 14:38 | 2012-02-17 14:38 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2012 | Q1 | Q1 - 2012 | 5990 | 5594 | FALSE | 84 | Project is reported as slightly behind schedule due to the deliverable-based billing relationship it has with its construction vendor. Work that is incrementally completed may not be paid in full or reported until the segment has been fully completed and this skews the actual project completion reporting. | 100 | Fiber Procurement | KINBER has received all fiber necessary to build the network. | 100 | Project is on schedule. | 100 | Project is on schedule. | 97 | We anticipate some continuing delays in getting Right of Way approvals. | 97 | We anticipate some delays in getting permits approved. | 95 | Project is on schedule. | 100 | Project is on schedule. | 75 | Project is on schedule. | 70 | Project is on schedule. | 10 | It was decided to hold equipment in intermediary staging facilities rather than deliver it to the various node sites across the state until fiber terminations were available in each location for appropriate setup and testing. Although it has slowed the ability to connect and test equipment on the first few segments, it will allow us to more quickly deploy staff to address multiple segments as they come online. | 2012-05-09 16:18 | 2012-05-09 16:18 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2012 | Q2 | Q2 - 2012 | 6970 | 6112 | FALSE | 85 | This projection is slightly below the targeted baseline of 89% mostly due to anticipated delays in make ready work and the fixed price contract payment schedule. | 100 | Fiber Procurement | KINBER has received all fiber necessary to build the network. | 100 | Milestone complete. | 100 | Milestone complete. | 100 | Milestone complete. | 100 | Milestone complete. | 100 | Milestone complete. | 100 | Milestone complete. | 90 | Milestone is on schedule. | 90 | Milestone is on schedule. | 25 | This milestone is behind schedule due to completion of small portions of fiber segments. Additional crews will be deployed when necessary to ensure the network is complete and tested by the end of the project. | 2012-08-09 13:38 | 2012-08-09 13:38 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2012 | Q3 | Q3 - 2012 | 7800 | 6602 | FALSE | 88 | Project will be slightly behind the baseline schedule, mostly due to lags in payment related to segment completion and payment terms outlined in the fixed price construction contract. | 100 | FIber | KINBER has received all of the fiber cable necessary to complete the project. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 95 | Although project will be slightly behind for completion in Q4; project will finish on time in Q1 2013. | 100 | Milestone is complete. | 50 | Network testing is projected to be behind schedule due to the construction delays related to small pieces of a few segments that may be awiting final approval (bridges and tunnels). | 2012-11-08 10:14 | 2012-11-08 10:14 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2012 | Q4 | Q4 - 2012 | 8692 | 7505 | FALSE | 95 | All fiber and electronics will be in place in Q1 2013. KINBER will use the additional time to complete splicing and network testing activities. | 100 | Fiber Procurement | KINBER has received all of the fiber optic cable necessary to complete the project. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 95 | All fiber and electronics will be in place in Q1 2013. | 100 | Milestone is complete. | 80 | All fiber and electronics will be in place in Q1 2013. K | 2013-02-11 07:44 | 2013-02-11 07:44 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2013 | Q1 | Q1 - 2013 | 9610 | 8336 | FALSE | 100 | Project will be complete. | 100 | Fiber procurement | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 2013-05-06 11:38 | 2013-05-06 11:38 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | 2013 | Q2 | Q2 - 2013 | 11788 | 9954 | FALSE | 100 | Milestone and project are complete. | 100 | Fiber Procurement | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 2014-02-03 17:10 | 2014-02-03 17:10 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570027 | 2010 | Q2 | Q2 - 2010 | 51 | 1328 | FALSE | 1 |  |  |  |  | 100 |  | 100 |  |  |  | 100 |  | 10 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2010 | Q3 | Q3 - 2010 | 222 | 1377 | FALSE | 4 | Based on estimated expenses from inception through the end of the quarter. | 0 | N/A | N/A | 100 | Complete. | 100 | Complete. | 0 | N/A | 100 | Complete. | 10 | Pushed back based on date the FONSI was issued. | 20 | Pushed back based on date the FONSI was issued. | 0 | No new progress. | 0 | Pushed back based on date the FONSI was issued. | 0 | No new progress. | 2010-10-29 12:17 | 2010-10-29 12:17 | 5496 | 5496 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2010 | Q4 | Q4 - 2010 | 566 | 1586 | FALSE | 7 | Based on estimated inception-to-date expenses related to engineering and construction. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 10 | Contractor selection will be completed and work expected to begin by the end of March. | 10 | DWDM and Layer 2/3 equipment vendor selection is expected to be complete with procurement beginning by the end of this quarter or the beginning of the next. | 6 | No variance. | 0 | Pushed back due to equipment procurement schedule. | 0 | Pushed back due to equipment deployment schedule. | 2011-01-26 18:30 | 2011-01-26 18:30 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2011 | Q1 | Q1 - 2011 | 2028 | 2759 | FALSE | 34 | Please see section #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 10 | Construction contractor and Auxiliary Equipment vendor was selected on 4/11. Construction is expected to begin by 6/30. | 25 | Finalized contract negotiations with DWDM vendor and received final signed contract on 4/22. Site visits and planning to begin on deployment of DWDM equipment on 4/25. Continuing work on contract negotiations with Access Equipment vendor. Selected Layer 2/3 Equipment vendor on 4/15 and have begun contract negotiations. | 35 | No variance. Construction is progressing on schedule. | 25 | Pushed back due to equipment procurement schedule. | 9 | Pushed back due to equipment deployment schedule. | 2011-05-13 16:17 | 2011-05-13 16:17 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2011 | Q2 | Q2 - 2011 | 3308 | 3416 | FALSE | 60 | No variance. Please see section #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 50 | Building construction under way and expected to be completed by quarter 4. | 63 | Increasing efforts to catch up this milestone. Equipment is being procured as the installers are ready to proceed with installation. The installation of the equipment is proceeding very quickly and we anticipate catching up to this milestone very soon. | 53 | No variance. Working on catching up to milestones by increasing efforts and deploying multiple crews in each of our fiber construction locations. | 63 | Equipment deployment is proceeding very quickly and we anticipate catching up to this milestone very soon. | 50 | Network testing is conducted as equipment is installed. | 2011-08-25 10:45 | 2011-08-25 10:45 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2011 | Q3 | Q3 - 2011 | 4188 | 3942 | FALSE | 71 | Ahead of baseline projections. Expecting to exceed baseline projections based on completing outside plant construction by the end of Q4 2011. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 75 | Equipment is being procured as we are able to install it. Waiting for completion of buildings in two locations and power equipment upgrades in other locations. Buildings should be complete by the end of Q4 2011, therefore equipment procurement and installation will ramp up and expect to fully complete by Q2 2012. | 69 | No variance. | 75 | Equipment deployment follows equipment procurement. See explanation above. | 75 | Network testing follows equipment deployment. See explanation above. | 2011-11-21 15:54 | 2011-11-21 15:54 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2011 | Q4 | Q4 - 2011 | 4924 | 4604 | FALSE | 92 | Positive variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 95 | All equipment is anticipated to be procured by the end of Q2 2012. | 89 | Positive variance. | 95 | Equipment deployment follows procurement. | 95 | Network testing follows equipment deployment and network build. | 2012-02-09 11:24 | 2012-02-09 11:24 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2012 | Q1 | Q1 - 2012 | 5978 | 5588 | FALSE | 100 | Positive variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | Positive variance. | 100 | Positive variance. | 100 | Positive variance. | 100 | Positive variance. | 2012-05-08 17:26 | 2012-05-08 17:26 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2012 | Q2 | Q2 - 2012 | 6934 | 6094 | FALSE | 100 | Positive variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | Positive variance. | 100 | Positive variance. | 100 | Positive variance. | 100 | Positive variance. | 2012-08-08 15:47 | 2012-08-08 15:47 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2012 | Q3 | Q3 - 2012 | 7562 | 6439 | FALSE | 100 | Positive variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | Positive variance. | 100 | Positive variance. | 100 | Positive variance. | 100 | Positive variance. | 2012-10-30 11:56 | 2012-10-30 11:56 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2012 | Q4 | Q4 - 2012 | 8990 | 7769 | FALSE | 100 | No variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 2013-02-26 16:59 | 2013-02-26 16:59 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | 2013 | Q1 | Q1 - 2013 | 10022 | 8560 | FALSE | 100 | No variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 2013-05-31 11:04 | 2013-05-31 11:07 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570028 | 2010 | Q2 | Q2 - 2010 | 52 | 1313 | FALSE | 2 |  | 0 |  |  | 30 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Administration, Wisconsin Department of | TRUE
NT10BIX5570028 | 2010 | Q3 | Q3 - 2010 | 388 | 1460 | FALSE | 15 | N/A | 0 | N/A | N/A | 100 | N/A | 5 | N/A | 5 | N/A | 5 | N/A | 5 | N/A | 35 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-23 14:36 | 2010-11-23 14:36 | 5375 | 5375 | Administration, Wisconsin Department of | TRUE
NT10BIX5570028 | 2010 | Q4 | Q4 - 2010 | 1022 | 2066 | FALSE | 15 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 0 |  | N/A | 100 | N/A | 5 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 5 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 5 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 5 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 35 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 0 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 0 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 0 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 2011-02-09 14:02 | 2011-02-09 14:02 | 5375 | 5375 | Administration, Wisconsin Department of | TRUE
NT10BIX5570028 | 2011 | Q1 | Q1 - 2011 | 1450 | 2438 | FALSE | 5 | As noted earlier in the report, the project will be terminated for convenience. | 0 |  | N/A | 100 | N/A | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 2011-04-20 11:27 | 2011-04-20 11:27 | 5375 | 5375 | Administration, Wisconsin Department of | TRUE
NT10BIX5570028 | 2011 | Q2 | Q2 - 2011 | 2470 | 2983 | FALSE | 5 | Project was terminated for convenience | 0 |  | :N/A | 100 | : | 0 | project terminated | 0 | project terminated | 0 | project terminated | 0 | project terminated | 0 | project terminated | 0 | project terminated | 0 | project terminated | 0 | project terminated | 2011-07-20 09:41 | 2011-07-20 09:41 | 5373 | 5373 | Administration, Wisconsin Department of | TRUE
NT10BIX5570029 | 2010 | Q2 | Q2 - 2010 | 53 | 1282 | FALSE | 5 | [6 empty] | 35 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Education Networks of America, Inc. | TRUE
NT10BIX5570029 | 2010 | Q3 | Q3 - 2010 | 354 | 1443 | FALSE | 7 | Delay in key vendor contract encountered secondary to new Federal regulations regarding security interest. ENA, vendor and National Telecommunications and Information Administration are currently working to address this issue. | 0 |  | N/A | 0 | N/A | 35 | Vetting Wave 2 sites to verify service need. | 5 | See Item 2a above. | 5 | See Item 2a above. | 5 | See Item 2a above. | 5 | See Item 2a above. | 0 | See Item 2a above. | 0 | See Item 2a above. | 0 | See Item 2a above. | 2010-11-19 13:15 | 2010-11-19 13:15 | 5509 | 5509 | Education Networks of America, Inc. | TRUE
NT10BIX5570029 | 2010 | Q4 | Q4 - 2010 | 820 | 1854 | FALSE | 7 | Delay in securing primary vendor contract because during the fourth quarter our vendor was in the process of undergoing an acquisition and that significantly affected their ability to negotiate or enter into new service contracts. | 0 |  | N/A | 0 | N/A | 35 | Vetting Wave 2 sites to verify service need. | 5 | See item #2a above. | 5 | See item #2a above. | 5 | See item #2a above. | 5 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 2011-01-28 16:07 | 2011-01-28 16:07 | 5509 | 5509 | Education Networks of America, Inc. | TRUE
NT10BIX5570029 | 2011 | Q1 | Q1 - 2011 | 1398 | 2411 | FALSE | 0 | N/A - Grant terminated. | 0 |  | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 2011-03-10 15:57 | 2011-03-10 15:57 | 5508 | 5508 | Education Networks of America, Inc. | TRUE
NT10BIX5570030 | 2010 | Q2 | Q2 - 2010 | 54 | 1269 | FALSE | 18 |  |  |  |  | 100 |  | 100 |  | 75 |  | 85 |  |  |  | 20 |  | 15 |  | 15 |  | 15 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2010 | Q3 | Q3 - 2010 | 446 | 1489 | FALSE | 15 | Significant progress in construction and community anchors is expected in Q4. NIU Outreach will start work on Community Anchor Institutions. DeKalb Fiber Optics will operate second plow crew in beginning in April for three months. This should provide the extra resources to get the overall project on schedule | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed. | 75 | Rights-of-Way are in-place for segments to be constructed in Q4. Schedule allows adequate time for acquisition of ROW for center and south routes as construction is underway on north part of project. Target was 100% at this point but delayed in order to concentrate on agreement preparation. | 75 | Permits are in-place for segments to be constructed in Q4. Schedule allows adequate time for acquisition of ROW for center and south routes as construction is underway on north part of project. Target was 100% at this point but delayed in order to concentrate on agreements preparation. | 0 | N/A | 15 | Northern Illinois University Outreach consulting agreement is expected to be in place early in Q4. Their work includes defining the equipment needs of the community anchors and assisting the County in competitively bidding the purchase of the equipment. First phase of their work will concentrate on community anchors located in north part of route. Network build equipment is available and ready for when construction starts. Target was 40% at this point but delayed in order to work on NIU Outreach agreement. | 8 | Represents completion of three segments in DeKalb and Genoa in Q4. Extra plow crew to be added in April to catch up with IRU schedule which is bulk of project. Target was 30% at this point but delayed due to lack of agreements that would allow construction to start. | 13 | Network build equipment is available when construction starts. Premise participant equipment and core equipment is being purchased by competitive bid. The bids are expected to be awarded in Q5 and will be installed as Community Anchors are brought on-line. Target was 40% at this point but delayed due to lack of agreements are needed in order for construction to start and equipment to be deployed. | 8 | For segments installed in Q4. All segments will be tested as they are completed. Adequate resources are in place to assure testing will keep pace with construction. Target was 40% at this point but delayed due to lack of agreements that are needed in order for construction to start and testing to take place. | 2010-11-29 17:52 | 2010-11-29 17:52 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2010 | Q4 | Q4 - 2010 | 1316 | 2341 | FALSE | 25 | Significant project is projected in Q5. Target was 60% complete at this point but construction delayed due to document preparation. | 0 | N/A | N/A | 100 | Previously completed | 100 | Previously completed | 65 | Finalize rights of way on north part of route. Target was 100% at this point but construction was delayed due to document preparation. | 75 | Obtain three rail crossing permits needed for Q5 construction. Target was 100% at this point but construction was delayed due to document preparation. | 0 | N/A | 33 | Purchase premise switching equipment for 10-15 anchors. Target was 75% by Q5 but construction was delayed due to document preparation. Equipment procurement following Network Build. | 11 | 56,000lf of duct and 60,000lf of fiber to be built in Q5. Target was 60% for Q5 but construction was delayed due to document preparation. Contractor will provide additional resources as weather improves to get project on schedule. | 25 | Premise and node equipment for north community anchors to be deployed in Q5. Target was 50% for Q5. Equipment deployment is following network build. | 9 | For north part of route installed fiber and connected CAI's. Target was 50% for Q5 but delayed due to document preparation. Testing is following network build. | 2011-02-22 17:08 | 2011-02-22 17:08 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2011 | Q1 | Q1 - 2011 | 2072 | 2781 | FALSE | 30 | Baseline predicted 80% complete at this point. The project was behind schedule early due to difficulty getting agreements in place. We project project will reach baseline projection of 80% in Quarter 9. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed. | 70 | Baseline predicted 100% at this point. The project was behind schedule early due to difficulty getting agreements in place. Work will proceed in Q6 to acquire ROW's for Hinckley, Big Rock, Waterman and Shabbona. | 75 | Baseline predicted 100% at this point. The project was behind schedule early due to difficulty getting agreements in place. | 0 | N/A | 40 | Baseline predicted 100% at this point. The project was behind schedule early due to difficulty getting agreements in place. Expect to bid backbone equipment and emergency radio equipment in Q6 | 30 | Baseline predicted 80% at this point. The project was behind schedule early due to difficulty getting agreements in place. Expect to have 36% of duct and 30% of fiber installed by the end of Q6. | 25 | Baseline predicted 85% at this point. The project was behind schedule early due to difficulty getting agreements in place. Expect to place community anchor and backbone equipment for north part of the route in Q6 as well as some 911 tower and repeater equipment. | 12 | Baseline predicted 70% at this point. The project was behind schedule early due to difficulty getting agreement in place. Testing is on schedule and keeping pace with fiber installation. | 2011-05-17 09:18 | 2011-05-17 09:18 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2011 | Q2 | Q2 - 2011 | 2950 | 3232 | FALSE | 53 | Baseline projected 95%. The project was behind schedule early due to difficulty getting agreements in place. Expect to meet baseline in Q10 (10-12 additional months. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed. | 80 | Baseline projected 100%. The project was behind schedule early due to difficulty getting agreements in place. Project will be at 100% in Q9. | 100 | Remaining railroad permits should be received. | 0 | N/A | 15 | Baseline projected 100%. The project was behind schedule early due to difficulty getting agreements in place. Project will be at 100% in Q10. | 53 | Baseline predicted 100%. The project was behind schedule early due to difficulty getting agreements in place. Project will be at 100% in Q10. | 1 | Baseline projected 100%. The project was behind schedule early due to difficulty getting agreements in place. Project will be at baseline in Q11. | 20 | Baseline projected 100%. The project was behind schedule early due to difficulty getting agreements in place. Project will be at baseline in Q10. | 2011-08-08 11:44 | 2011-08-08 11:44 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2011 | Q3 | Q3 - 2011 | 4020 | 3850 | FALSE | 70 | Baseline predicted 98% complete at this point. Expect to meet baseline in Q10 (10-12 additional months). Expect to have 80.2 network miles installed by end of Q8. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed. | 80 | Baseline predicted 100% at this point. We will continue to acquire ROW where we can but the completion of ROW will depend on route change approval. Assuming ROW will not be 100% until Q9. | 100 | All costs associated with permits should be paid by the end of Q8 | 0 | N/A | 60 | Baseline predicted 100% at this point. We will pay for the backbone equipment in Q8. Will meet baseline in Q10. | 70 | Baseline predicted 100%. We will be 67% complete on constructed network and 100% complete on leased and IRU's by the end of Q8. Due the ROW issues, we probably won't meet baseline until Q10. | 25 | Baseline predicted 100%. By the end of Q8, we plan to have 33% of the backbone equipment and 33% of the community anchor switches deployed. Still need to deploy downtown wireless, fiber back haul and GPON, as well as balance of backbone and community anchor switches. Baseline will be met in Q11. | 40 | Baseline predicted 100%. We will continue test the completed segments in Q8. 70% of the build should be completed by the end of the quarter and approximately 80% should be tested. Baseline will be reached in Q10 | 2011-11-14 12:37 | 2011-11-14 12:37 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2011 | Q4 | Q4 - 2011 | 5116 | 4785 | FALSE | 84 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC. Project has been moving well since 1/1/11 showing completion percentages for the last three four quarters of 20, 29, 47, and 62% respectively. The project will be substantially complete by 1/31/12. | 0 | N/A | N/A | 100 | Previously completed. | 100 | Previously completed. | 100 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC. Route change approval will allow row acquisition to proceed. We intend to acquire all row and 13 of 14 municipal utility agreements by the end of Q9. Expenditures in this line item will exceed budget due to payments for previously completed duct and fiber not budgeted here but properly paid from this line item. Some expenditures remain to be paid from this line item, primarily for rail crossing expenses. | 100 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC. Some rail crossing expenses remain to be paid as crossings are made in municipalities with which we are still negotiating utility agreements. | 0 | N/A | 70 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC. Expect to pay for backbone and fiber back haul equipment in Q9. Plan to bid and order City of DeKalb downtown wireless, public library access points and GPON equipment in Q9. | 90 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC. Plan to be 81% built in duct and fiber by end of Q9. All leases and IRU's are in place which adds 9% to the total network build completion. | 25 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC. Backbone equipment will be deployed as telephone central offices become available. Community anchor equipment will be deployed in north and central parts of route. E-911 equipment will be partially deployed. | 25 | Testing will be completed for another 22 miles of fiber from south of Genoa to the network operations center in DeKalb and in the DeKalb-Sycamore area. | 2012-02-17 17:07 | 2012-02-17 17:07 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2012 | Q1 | Q1 - 2012 | 6038 | 5618 | FALSE | 83 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Project has been moving well since 1/1/12 showing completion percentages for the past five quarters of 20, 29, 47, 62 and 70% respectively. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed. | 100 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Remaining municipal utility agreements will either be finalized in Q10 of award or rerouting will be initiated. Expenditures in this line item will exceed budget due to payments for previously completed duct and fiber not budgeted here but properly paid from this line item. | 100 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Some expenditures remain to be paid from this line item for rail crossing expenses for crossings within municipalities from which we currently are negotiating row access. | 0 | N/A | 44 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC.Expect to pay for backbone equipment in Q10 of award. Plan to bid, order and receive wireless access points for libraries. Plan to bid City of DeKalb downtown wireless/ surveillance project in Q10. Plan to complete evaluation of vendor neutral cabinets and start procurement process. | 95 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. If sufficient row issues are resolved by May 1, we plan to be 93% compete with duct and fiber by June 30. All leases and IRU's are completed. | 40 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Plan to deploy one additional collocation site, CAI equipment for 31 additional connections, E-911 fiber back haul equipment should be complete and wireless access point deployment in libraries should start in Q10 of award. | 58 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. We plan to test an additional 30 miles of fiber in Q10 of award which would make the total tested 73.37 miles by the end of Q10. | 2012-05-11 10:17 | 2012-05-11 10:17 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2012 | Q2 | Q2 - 2012 | 7238 | 6246 | FALSE | 90 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Project has been moving well since 1/1/12 showing completion percentages for the past five quarters of 20, 29, 47, 62, 70 and 75% respectively. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed | 100 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. One remaining municipal utility agreements and one remaining right-of-way issue will be finalized in Q11 of award. Expenditures in this line item will exceed budget due to payments for previously completed duct and fiber not budgeted here but properly paid from this line item. | 100 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Some expenditures remain to be paid from this line item for rail crossing expenses for crossings within municipalities from which we currently are negotiating row access. | 0 | N/A | 70 | Essentially will complete equipment procurement. Only minor equipment purchase will remain at end of Q11. | 98 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Since right-of-way issues are sunstantially resolved, we plan to be 95% compete with duct and fiber by September 30. All leases and IRU's are completed. | 75 | Plan to complete the deployment of the node site in Sandwich and additional 30 additional CAI's. Deploy fiber back haul equipment. Backbone equipment would be 100% complete and CAI equipment would be 73% deployed by the end of Q11. | 57 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. We plan to test an additional 30 miles of fiber in Q10 of award which would make the total tested 73.37 miles by the end of Q10. | 2012-08-24 12:50 | 2012-08-24 12:50 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2012 | Q3 | Q3 - 2012 | 7924 | 6666 | FALSE | 95 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. Project has been moving well since 1/1/11 showing completion percentages of 20, 29, 47, 62, 70, 75 and 83 percent respectively. All physical work on the project is expected to be completed by the end of the quarter. We expect final payments to carry over into January, 2013. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All rights-of-way were completed in Q3-12. Costs for rights-of-way are expected to exceed budget due to payment for previously completed duct that was budgeted in "Construction" but was properly paid from "Rights-of-Way" line item. | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. Some expenditures remain to be paid from this line item in Q4-12 as expenses for flag men and railroad supervision are paid after crossings are made in Somonauk and Malta. | 0 | N/A | 100 | All remaining equipment for the project should be received and paid in Q4-12 as 10Gb "ring" equipment and firewalls are received and paid. | 99 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All construction is expected to be complete. However some invoices for completed work may still be unpaid at the end of the quarter. | 100 | Node site in Sandwich will be complete. All Community Anchors locations will be complete for equipment deployment. | 100 | Entire network will be tested by the end of the quarter. | 2012-11-16 14:02 | 2012-11-16 14:02 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2012 | Q4 | Q4 - 2012 | 8742 | 7538 | FALSE | 93 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All approved infrastructure work on the project is completed. Some additional connections will be completed in January and some additional community anchor engineering can be completed and invoices processed for engineering. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously competed. | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All rights-of-way were completed in 2012-Q3. Costs for rights-of-way are expected to exceed budget due to payment for previously completed duct that was budgeted in "Construction" but was properly paid from "Rights-of-Way" line item. In-kind for duct and fiber provided by DeKalb Fiber Optics will exceed budget and be off-set by engineering provided by DeKalb Fiber Optics being less than budgeted. | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. Some expenditures remain to be paid from this line item in 2013-Q1 as railroad invoicing for flag men for crossing are made in Malta is lagging behind actual date of occurance. | 0 | N/A | 100 | All remaining equipment for the project should be received and paid in 2013-Q1. Some additional connection equipment may be needed for the community anchors involved with the route changes. | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All approved construction is complete and invoices are paid. 1.526 miles of additional network will need to be built and 2.965 miles of additional network will be acquired from DeKalb Fiber Optics if the route changes are approved. Construction of the additional network can only take place in 2013Q1 if route change is approved in time to construct it and weather conditional allow it. | 100 | All node sites are complete. All Community Anchors locations will be complete for equipment deployment in January, 2013. Additional equipment will be deployed if route changes are approved. The connection of 17 community anchors remains at the end of 2012-Q4. Of those, one is expected to be connected in January, 2013 and the remaining 16 are dependent on route changes. Of the 16 connections dependent on route changes, seven are dependent on construction and will take up to three months to connect after route changes are approved, making it doubtful these locations can be connected next quarter.. The remaining nine connections need equipment, configuration and lighting only and may be able to be connected late in 2013-Q1 if route changes are received in time to allow the remaining tasks to be complete before the end of the quarter. | 100 | Completed in 2012-Q4. Verification of test results continues into 2013-Q1. | 2013-02-13 10:44 | 2013-02-13 10:44 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2013 | Q1 | Q1 - 2013 | 9818 | 8445 | FALSE | 92 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All approved infrastructure work on the project is completed. One approved additional connection can be completed in 2013-Q2. Remaining connections are dependent on approval of prospective route change approval. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed | 92 | Baseline predicted 100%. All right of way costs are paid; additional in-kind to be received dependent on prospective route change approval but not expected in 2013-Q2. | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All construction permits are received and expenses for construction permits are paid, | 0 | N/A | 87 | Baseline predicted 100%. All equipment that has been ordered has been received and paid. Remaining funds are for 100Gig "ring" being constructed with iFiber project. | 98 | When prospective route changes are approved, an additional 1.26 miles of duct and fiber will be constructed and an additional 1.9 miles of network will be acquired by IRU or bill of sale. Neither of those are expected to be completed in 2013-Q2. | 95 | Seven additional locations will need to be deployed when the prospective route changes are approved. | 98 | Testing for 1.26 miles of additional fiber will need to be completed when the prospective route changes are approved and that additional fiber is installed. Not expected to be completed in 2013-Q2. | 2013-05-20 10:44 | 2013-05-20 10:44 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2013 | Q2 | Q2 - 2013 | 10490 | 8896 | FALSE | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All infrastructure and connections for the project will be completed by end of next quarter. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed. | 100 | Baseline predicted 100%. All right of way costs are paid; all in-kind fiber and duct provided by DeKalb Finer Optics LLC has been received. | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All construction permits will be received and expenses for construction permits will be paid by the end of the next quarter, | 0 | N/A | 100 | Baseline predicted 100%. All major equipment that has been ordered has been received and paid. Some miscellaneous equipment needed to connect remaining locations will be ordered, received and paid by the end of the next quarter. | 100 | There remains a small amount of network build (prospective route changes) to be completed in 2013-Q3. Work on that additional build was started in 2012-Q2 and will be completed by the end of the next quarter. All network to be acquired by bill of sale or IRU has been completed. | 100 | Six additional locations remain to be deployed. Those will be completed by the end in 2013-Q3. All other equipment required for the project has been deployed. | 100 | Testing for 1.28 miles of additional fiber to serve locations authorized by prospective route changes will be completed in 2013-Q3. | 2013-08-06 10:52 | 2013-08-06 10:52 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | 2013 | Q3 | Q3 - 2013 | 11466 | 9580 | FALSE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-12-10 11:08 | 2013-12-10 11:08 | 5512 | 5512 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570031 | 2010 | Q2 | Q2 - 2010 | 55 | 1287 | FALSE | 10 |  |  |  |  | 90 |  | 30 |  | 60 |  | 60 |  | 30 |  | 40 |  | 15 |  | 15 |  | 5 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2010 | Q3 | Q3 - 2010 | 322 | 1427 | FALSE | 35 | N/A | 0 | N/A | N/A | 100 | N/A | 50 | N/A | 60 | N/A | 60 | N/A | 25 | N/A | 45 | N/A | 10 | N/A | 30 | N/A | 15 | N/A | 2010-11-15 16:48 | 2010-11-15 16:48 | 5491 | 5491 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2010 | Q4 | Q4 - 2010 | 1148 | 2186 | FALSE | 40 | The overall project is behind baseline projections because we do not have the FONSI allowing commencement of construction | 0 |  | N/A | 100 | Awaiting FONSI for project kick-off/construction to begin. | 70 | The primary backbone network for the tower, Community Anchor, and Radio Observatory (which is the easiest portion) is nearly complete, causing 70% completion. | 85 | The rights of way are in place, simply awaiting construction approval, making them complete upon receipt of FONSI, effectively leaping forward the planned completion of same. | 85 | The construction permits are ready to go, awaiting a start date to complete the administrative portion, effectively leaping forward the planned completion of same. | 30 | The overall project is behind baseline projections because we do not have the FONSI allowing commencement of construction | 50 | Awaiting FONSI for project kick-off/construction to begin. | 25 | Awaiting FONSI for project kick-off/construction to begin. | 40 | Awaiting FONSI for project kick-off/construction to begin. | 20 | The overall project is behind baseline projections because we do not have the FONSI allowing commencement of construction | 2011-02-15 12:13 | 2011-02-15 12:13 | 5745 | 5745 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2011 | Q1 | Q1 - 2011 | 2118 | 2804 | FALSE | 40 | Variance is due to problems with acquiring FONSI. With the FONSI and PA in place, these percentages will improve each much and be so reflected in the next quarterly report. | 0 |  | N/A | 80 | The EA will be complete; however, with NTIA approval, we may add additional sites due to cost avoidances, and elimination of CAIs. This will have a direct impact on EA. | 55 | As with 2a., portions of design have been on hold, but with release of FONSI and PA, this effort is gaining great momentum. | 70 | While below baseline projections, the release to commence construction and a dynamic construction plan will bring this milestone in line within the next two quarters. | 45 | While below baseline projections, the release to commence construction and a dynamic construction plan will bring this milestone in line within the next two quarters. | 50 | Site preparation for twelve towers is underway. Lewis County as sub-recipient, through an efficient contract is expected to move ahead of schedule within the next six months, making 50% realistic. Site preparation for the CAI sites will account for about 25% of the overall project and will rapidly approach the 50% mark as local communications requests are released. | 50 | Routers for the Community Anchors were ordered and received. Radios and antennae for the tower portion of the grant are ordered. Routers for the Radio Observatory to the West Virginia University link have been ordered. After next quarter, we will be ahead of schedule in this area | 20 | While below baseline projections, the release to commence construction and a dynamic construction plan will bring this milestone in line within the next two quarters. | 40 | During the upcoming quarter, routers for the Community Anchors will be delivered and programmed. Coupled with radio installation, the installed and functioned routers, and other devices will be deployed at a minimum of 40%. | 30 | Network, equipment, functionality, and validation testing will directly remain at about 10% behind equipment deployment. The primary testing portion to be complete next quarter involves the tower and microwave portion of execution. As the radios, routers, and antennae are installed, testing will follow directly behind. | 2011-05-18 10:06 | 2011-05-18 10:06 | 5745 | 5745 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2011 | Q2 | Q2 - 2011 | 2974 | 3244 | FALSE | 60 | Variance is due to delay of FONSI receipt, fiber shortage, invoicing on tower radios, and a wet spring. FONSI has been received and subsequent programmatic agreement is a work in progress, fiber shortage has been mitigated, tower radios will be invoiced in August or September and the summer is hot. During the next two quarters we should rapidly close the gap in this area. | 0 | N/A | N/a | 85 | NTIA may approve addition of community anchors and we may have additional sites or projects due to cost avoidances and elimination of community anchors. This will have a direct impact on environmental. | 75 | As the engineering of the National Radio Astronomy Observatory comes to fruition (likely 3rd quarter), we will close the gap in this area. | 95 | We continue to improve in this area and continuance of a dynamic construction plan will bring this milestone into accord within the next two quarters. | 70 | As with 2nd portions of permits have been on hold; however, as construction commenced, this area gained momentum. | 80 | Site preparation for the twelve towers continues to be ongoing. Through Lewis County as a sub-recipient, our contractor aggressively is working the tower construct. The tower portion will be in line by end of the fiscal year. However, due to noted community anchor delays, mostly due to shortage of fiber, we remain sluggish within the community anchor site preparation, including special construction. Most likely we will be into fiscal year 2012 before this is fully on target. | 60 | The receipt of invoice for the radio towers will rapidly move us to within tolerances within equipment purchased. By end of fiscal year we should be on the mark in this area. | 50 | Although progressing quite nicely, we will remain 5 â€“ 10% behind in this area. After any potential changes and/or new community anchors are identified and approved, this will move to base line goals. The receipt of microwave radios will have an immediate positive impact as they are programmed and installed. | 35 | Network, equipment, functionality, and validation testing will directly remain at 5 â€“ 10% behind equipment deployment. As the noted radios are received and installed, the towers come on line, and the community anchors are installed, proportionally this gap will be removed. | 5 | Network testing remains at 5%. The first large phase of testing/validation begins with the microwave radio testing. Although, the manufacturer indicates they tested radios, the State of WV as directly related to this grant has not started follow on testing. This testing should commence during the week of 8 August 2011 and after complete (about 2 weeks) will move us to approximately 40% complete. Frontier Communications reports six miles of fiber complete with a total subscriber served as 98. Testing is now in process for these sites and will continue as new mileage is complete with new community anchored. When added to the testing of the microwave radios, these new sites as tested will enable compliance with baseline within the next two quarters. | 2011-08-09 13:39 | 2011-08-09 13:39 | 7135 | 7135 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2011 | Q3 | Q3 - 2011 | 3964 | 3820 | FALSE | 50 | This percentage is highly reflective of the tower and engineering portion of the build out, coupled with actual purchases of equipment. However, it remains imperative that Frontier Communications strictly adhere, with strong monitoring by NTIA and State of West Virginia, their proposed mitigation plan. | 0 | N/A | N/A | 95 | Although this moves to 95%, it remains below the baseline of 100% and until the last engineering process is complete, this will likely remain at 95%. However, we remain confident that we will hit the 95% mark during the last quarter. | 90 | This will move to 90% next quarter and lags behind due to some inherent radio problems. | 95 | This goal will be met next quarter; however, the remaining 5% will likely not be met for the next two quarters due to finalization and compliance of mitigation plan. | 95 | This goal will be met next quarter; however, the remaining 5% will likely not be met for the next two quarters due to finalization and compliance of mitigation plan. | 95 | This goal will be met next quarter; however, the remaining 5% will likely not be met for the next two quarters due to finalization and compliance of mitigation plan. | 97 | We are rapidly approaching the actual placement of all purchase orders; however after next quarter there likely will be about 3% remaining for any potential unknowns and NTIA possible approval of additional equipment. | 55 | The tower portion of the project will carry a large portion of this percentage. As Frontier is compliant with the proposed mitigation plan, these numbers will increase, but by the end of December, it likely will not move beyond a total of 55%. | 65 | The tower portion of the project will carry a large portion of this percentage. As Frontier is compliant with the proposed mitigation plan, these numbers will increase, but by the end of December, it likely will not move beyond a total of 55%. | 50 | Testing on towers begins in full; however, we cannot begin complete testing of the fiber portion until it is constructed; therefore, we remain dependant on Frontier to meet or exceed the proposed mitigation plan. | 2011-11-10 14:20 | 2011-11-10 14:20 | 7135 | 7135 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2011 | Q4 | Q4 - 2011 | 5194 | 4861 | FALSE | 58 | Frontier will continue diligently executing their mitigation plan efforts enabling further completion. Tower radios will be 75% installed. We will pay radio invoices of approximately $15,000,000. The fiber build out by sub contractors will be over 50% complete and the National Radio Astronomy Observatory to West Virginia University will be in full construction. | 0 | N/A | N/A | 96 | Environmental Assessments will be complete except for the potential tower replacements. This is necessitated due to structural inhibitors that will delay the environmental progress. However, this will only be minimal delay that will self-correct within six months. | 98 | Network design will be nearly complete. However, there may be glitches that may require revisiting of the overall design. Therefore, we are holding to 98%. | 98 | Rights of way will be virtually complete; however, we may have some minor glitches that require some minor effort. We are on target to meet the overall grant objectives in this area. | 98 | Construction permits will be virtually complete; however, we may have some minor glitches that require some minor effort. We are on target to meet the overall grant objectives in this area. The replacement towers are on existing sites and will require only minimal permitting. | 95 | Site preparation will likely be necessary with the replacement towers and may extend through the next quarter. This will self correct within six months. | 96 | Equipment procurement will be limited only to items that are incidental to the overall project. We expect most, if not all equipment orders to be placed by the end of the first quarter; however, there may be a few items that are â€œhungâ€ within the confines of the purchasing processes. | 60 | As noted within this report, Frontier Communications is behind the overall grant production schedule, but is rapidly increasing the gap by full execution of their approved mitigation plan. We expect this number to decrease dramatically through each quarter enabling satisfactory completion at the end of the grant. | 70 | A major portion of the routers will be delivered/installed as Frontier completes their portion of the mitigation plan (see 2h). As this plan has been jump started, so will the deployment of related equipment. Also, the National Radio Astronomy Observatory to West Virginia University link will have equipment delivered and installed during this quarter. | 60 | In keeping with 2h and 2i, as Frontier develops construction in accord or ahead of their mitigation effort, the testing will be commensurate with construction processes. We are on track to complete | 2012-02-22 15:14 | 2012-02-22 15:14 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2012 | Q1 | Q1 - 2012 | 6320 | 5762 | FALSE | 69 | Frontier continues execution of mitigation plan. We will have factory tested and delivery of all microwave radios. During the next month we will be taking advantage of the summer weather to continue increasing tempo of construction. | 0 | N/A | N/A | 98 | CAI engineering and agency approvals are anticipated to be complete in the 2nd quarter 2012. The remaining 2% represents re-opening of counties for various reasons, or a lagging county approval. | 98 | The remaining 2% allows room for tweaking the network design. | 98 | The remaining 2% allows room for any unknown or not planned efforts in this area. | 96 | Storm water construction inspections for 11 of the 12 towers (92%) has been completed. Then the WVDEP permit can be closed. The remaining 5 tower inspections (0%) will be conducted in 3rd and 4th quarters 2012. Construction inspections for the Community Anchors (2%) will begin in the 2nd quarter 2012 and will continue until end of January 2013. Inspections to close out the WVDEP permits for applicable counties(CIA - 2%) will progress as Frontier completes the construction activities in each county. The last inspections are anticipated to be in January 2013. | 98 | The remaining 2% allows room for tweaking or correcting anything surfacing in this area. | 98 | The remaining 2% allows room for tweaking or correcting anything surfacing in this area. | 85 | As fiber deployment continues, mitigation plan tracker is planned for 85 % completion. | 85 | Most routers will be deployed in this quarter. | 75 | Once all CAI's have routers and all new service is hooked up with fiber. The engineers will be finalizing testing. All CAI's are on schedule to be completed during quarter 4 2012, per Frontiers mitigation plan. | 2012-05-29 12:15 | 2012-05-29 12:15 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2012 | Q2 | Q2 - 2012 | 6998 | 6126 | FALSE | 71 | The difference from the baseline centers on the two significant factors mentioned throughout this and previous reports. First was the time consumed during the environmental assessment process, during which we could not begin construction. Second (coupled with the environmental slowness) was the time required for Frontier Communications to begin construction (much of which was due to a major fiber shortage), but was mitigated by the NTIA approved Frontier Mitigation plan. We are on track to complete the grant by the end of the 3rd year. | 0 | N/A | N/A | 98 | Engineering and agency approvals for the replacement CAI's and FBO's are anticipated to be completed in the 3rd quarter 2012. Anticipated approval of five (5) replacement towers will allow construction to begin. The remaining 5% represents re-opening of counties for FBO's or re-engineering during construction. | 99 | Network design is shown at 99%, leaving 1% for unknown design considerations. We will reach 100% at the end of the upcoming quarter. | 99 | Rights of way are shown at 99%, leaving 1% for unknown design considerations. We will reach 100% at the end of the upcoming quarter. | 98 | The state-wide power outage in early July 2012 caused the inspection process to be behind. Storm water construction inspections for 11 of the 12 towers (92%) will be completed. The remaining tower inspection (0%) will be conducted when the tower is stacked. Then the WVDEP permit can be closed. The five (5) replacement towers (0%) will not involve new ground disturbance and do not require a storm water construction permit. Inspections will be conducted at these five (5) replacement towers as construction progresses. Construction inspections on buried segments for the Community Anchors (another 25% in 3rd quarter) will continue until February 2013. Inspections to close out the WVDEP permits (notice of termination - NOT) for applicable counties (15/30 counties - 50% will progress as Frontier and FBO construction activities are completed in each county. The last inspections are anticipated to be in February 2013. | 98 | Site preparation is shown at 98%. Although virtually complete, the 2% remaining from baseline leaves room for any additional or unforeseen efforts that may surface. | 98 | Equipment procurement is shown at 98%. We will have all approved equipment ordered by end of next quarter. The 2% leaves room for any miscellaneous material that might be required. | 80 | Network Build is shown at 80% for the upcoming quarter. This may be somewhat conservative. We expect Frontier to continue on pace with their mitigation plan; however, the early July 2012 storm caused some delays in projections for catch â€“ up. | 85 | Equipment Deployment at 85% is also somewhat conservative. As the additional radios are received and installed and additional towers are complete, the main effort will parlay to the remaining installations. | 75 | Network Testing will always trail behind equipment deployment. As the deployment develops, the testing will follow proportionally. | 2012-08-10 10:00 | 2012-08-10 10:00 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2012 | Q3 | Q3 - 2012 | 7974 | 6693 | FALSE | 77 | The 77% is including the Match portion of the grant. The Frontier fiber build should be at or near completion, the original twelve towers with associated radios and antenna should be installed, WV NET should be complete and functional, leaving small portions of each of these initiatives for January completion. The five replacement towers are the only activity holding this percent to 77. | 0 | N/A | N/A | 98 | Engineering and agency approvals for the replacement CAIs and FBOs are anticipated to be completed in the 4th quarter 2012. Construction of the 5 replacement towers will begin in 4th Q 2012 with inspection work to follow. The remaining 5% represents re-opening of counties for FBOs or re-engineering during construction. | 99 | Network design remains at 99% due to CAI additions and replacements. Currently, there are two CAI's remaining which require network engineering and design for completion. Once completed, all CAI network designing should be completed. | 99 | With only two CAI's requiring network engineering and design, this remains at 99%. Once completed, this should be finalized by end of the grant period. | 97 | Storm water construction inspections for 11 of the 12 towers (92%) will be completed. The remaining tower inspection (0%) will be conducted when the tower is stacked. The 5 replacement towers (0%) will involve minimal ground disturbance and do not require a storm water construction permit. Inspections will be conducted at these replacement towers as construction is completed and vegetation is up. Then the WVDEP permit can be closed. Construction inspections on buried segments for the Community Anchors (another 25% in 4th quarter) will continue until February 2013. Inspections to close out the WVDEP permits (notice of termination - NOT) for applicable counties (15/30 counties - 50% will progress as Frontier and FBO construction activities are completed in each county. The last inspections are anticipated to be in February 2013. | 98 | Site preparation is shown at 95% which is reduced from last report from 98%. This is solely due to the 5 replacement towers. Site preparation for these towers should be at 100% after 1st quarter 2013. | 98 | The equipment acquisition for the NRAO/WVU portion and K-12 core network upgrade are still pending. This should be completed before January, 2013. | 90 | The 5 replacement towers will hold this number at 90% until such time as the towers are complete. | 90 | Deployment is on-going with a few equipment acquisitions still pending as well as construction and implementation phase still in process. Also, adding CAI replacements/additions requires re-purposing and shipping equipment to their new locations. | 80 | Testing is on-going as CAI locations are completed and verified. This includes fiber termination and router deployments to these locations. This percentage will grow as site locations are completed. Testing has been impacted since there are new CAI replacements/additions to account for. | 2012-11-20 11:58 | 2012-11-20 11:58 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2012 | Q4 | Q4 - 2012 | 8980 | 7758 | FALSE | 80 | The 80% includes the Matching portion of the grant. As the five replacement towers come to fruition, we will begin to see associated vendor construction invoices. Frontier invoicing should increase. As these and other activities begin to come to completion, the actual invoicing and disbursement amounts will grow proportionally. | 0 | N/A | N/A | 99 | As activities begin completion processes and weather improves, actual site validation visits will effectively improve this area to 100. | 99 | Until the grant closes there will remain limited network design and tweaks accounting for the remaining 1%. | 99 | Until the grant closes there will remain limited rights of way initiatives and tweaks accounting for the remaining 1%. | 99 | The five replacement tower permits should be complete and there may remain 1% effort to tweak some areas. | 99 | The five replacement towers should have all site preparation complete; however, there may remain up to 1% effort to finalize some areas. | 99 | We are leaving this percentage at 99% in the event that any equipment is approved to be purchased with residual funding. | 96 | We are leaving this percentage at 96% in the vent to include finalization of the wireless network portion of the five replacement towers. | 90 | This number remains the same. Adding CAI's replacements/additions requires re-purposing and shipping equipment to their new locations. | 95 | As the entire projects begins to come to closure, network testing will be the final stage. We expect this to be about 95% complete by the end of next quarter. | 2013-02-26 14:50 | 2013-02-26 14:50 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2013 | Q1 | Q1 - 2013 | 9934 | 8510 | FALSE | 82 | Billing lags a minimum (specifically fiber build-out) of 90 days. As construction on the grant closes, we will receive invoices accordingly and in two quarters, we should receive and process all construction billing. | 0 | N/A | N/A | 99 | The only remaining environmental effort will be closeout of counties and towers. | 100 | 100 % Complete | 100 | 100 % Complete | 100 | 100 % Complete | 99 | Snow Shoe tower remains problematic and may not be complete next quarter. | 100 | 100 % Complete | 98 | This should be completed by July 2013 for the fiber portion of the grant. The Snow Shoe tower remains problematic and may not be complete next quarter. | 99 | Equipment for Snow Shoe tower may not be deployed by end of next quarter. | 98 | As the entire projects begins to come to closure, network testing will be the final stage. We expect this to be about 98% complete by the end of next quarter. | 2013-05-28 14:15 | 2013-05-28 14:15 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2013 | Q2 | Q2 - 2013 | 10802 | 9073 | FALSE | 92 | Construction will be 100% complete, but we will continue to receive invoices into the last quarter. We will have the last billing by Calendar Year End. | 0 | N/A | N/A | 99 | There will be some environmental validation during the final quarter. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 99 | There will be testing of the wireless links. | 2013-08-29 09:08 | 2013-08-29 09:08 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2013 | Q3 | Q3 - 2013 | 11344 | 9472 | FALSE | 92 | The planned percent completed is based on funding drawn down on ASAP. There remains an inherent administrative delay in payment of Frontier invoices. All of their invoices will be paid either prior to or immediately in the early stages of the close out. When combined with the remaining invoices to receive and the approximately 4% not committed, and approval of a potential residual funds project, we will be at 100% during grant close out. We plan to have spent $146,829,619 of the $159,823,296 by the end of quarter 4. | 0 | N/A | N/A | 100 | Completion of inspections and permit closeout are projected by end of 4Q 2013. closeout documents will be prepared during 1Q 2014. | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2013-11-22 09:21 | 2013-11-22 09:21 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | 2013 | Q4 | Q4 - 2013 | 12366 | 10547 | FALSE | 100 | We will return $1,950,720.85 of unused funds. | 0 | N/A | N/A | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 2014-07-30 13:23 | 2014-07-30 13:23 | 5490 | 5490 | Executive Office State of West Virginia | TRUE
NT10BIX5570032 | 2010 | Q2 | Q2 - 2010 | 56 | 1324 | FALSE | 10 |  | 0 |  |  | 100 |  | 100 |  | 0 |  | 30 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | 2010 | Q3 | Q3 - 2010 | 362 | 1447 | FALSE | 15 | Because the environmental assessment has taken longer to complete, we are starting more slowly than planned. We are, however, working on preparatory actions to allow us to catch up. | 0 | NONE | NA | 100 | NA | 100 | NA | 25 | Concentrating on the environmental assessment has delayed other aspects of the project. In addition, the question of ownership that has not been resolved has caused LCOG to delay acquisition of permissions that may not be necessary. When these issues are resolved, LCOG should be able to move quickly to get the project back on track. | 20 | Concentrating on the environmental assessment has delayed other aspects of the project. In addition, the question of ownership that has not been resolved has caused LCOG to delay permits that may not be necessary. When these issues are resolved, LCOG should be able to move quickly to get the project back on track. | 20 | Concentrating on the environmental assessment has delayed other aspects of the project. In addition, the question of ownership that has not been resolved has caused LCOG to delay the site preparations that may not be necessary. When these issues are resolved, LCOG should be able to move quickly to get the project back on track. | 10 | LCOG expects to complete the selection of one wholesale broadband provider this quarter. As a part of that process, LCOG will determine the equipment to be used on a portion of the network and will initiate, if not complete the equipment procurement. | 75 | LCOG will secure the agreements that will secure the bulk of the network planned during this quarter. | 0 | The delay in completion of the environmental assessment has delayed the start of construction and therefore the deployment of equipment has been delayed. When construction is started, it will be a short time before any equipment deployment is justified. | 10 | LCOG expects to complete this portion of the network testing this quarter. | 2010-11-19 16:37 | 2010-11-19 16:37 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2010 | Q4 | Q4 - 2010 | 1096 | 2137 | FALSE | 15 | Because the environmental assessment has taken longer than expected, construction has been delayed. We anticipate that we will be able to get back on track soon. We may be back on schedule within eight to twelve months. | 0 |  | NA | 100 | Completed | 100 | Completed | 25 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 20 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 20 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 10 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 75 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 0 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 10 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 2011-02-11 16:46 | 2011-02-11 16:46 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2011 | Q1 | Q1 - 2011 | 1952 | 2721 | FALSE | 20 | Construction should begin this quarter. | 0 |  | NA | 100 | This has been completed. | 100 | This should be completed this quarter as construction begins. | 30 | This should proceed ahead of construction. | 30 | This should proceed ahead of construction. | 25 | This should proceed ahead of construction. | 10 | With constructin underway, some equipment can be purchased for installation as construction is completed. | 75 | The completion of the IRU for leased fiber should be done this quarter, which will bring the project back to baseline expectations. | 0 | Deployment will start after construction has moved far enough along so that connections to the internet can be accomplished. | 10 | This will proceed as construction is completed. | 2011-05-11 20:18 | 2011-05-11 20:18 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2011 | Q2 | Q2 - 2011 | 3242 | 3383 | FALSE | 14 | The delays in acquiring fiber have slowed progress, but orders are now being received. | 0 |  | NA | 100 | NA | 100 | This should be completed as construction begins. | 40 | This will proceed ahead of construction. | 40 | This will proceed ahead of construction | 30 | This will proceed ahead of construction | 30 | This will proceed as construction moves forward. | 75 | The completion of the IRUs will establish the largest part fothe network. | 5 | Deploymetn will follow construction. As anchor insitutions are connected, equipment will be deployed. | 30 | With the IRUs completed the testing of the network backbone can commence. | 2011-08-19 16:12 | 2011-08-19 16:12 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2011 | Q3 | Q3 - 2011 | 4258 | 3979 | FALSE | 31 | After completion of the environmental review work has progressed on the time consuming preliminary work of final design, permitting and procurement. |  |  |  | 100 | Completed | 95 | This will proceed as construction moves forward. | 65 | This will proceed as construction moves forward. | 65 | This will proceed as construction moves forward. | 25 | This will proceed as construction moves forward. | 30 | This will proceed as construction moves forward. | 60 | This will proceed as construction moves forward. | 5 | This will proceed as construction moves forward. | 30 | This will proceed as construction moves forward. | 2011-11-23 13:44 | 2011-11-23 13:56 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2011 | Q4 | Q4 - 2011 | 5102 | 4771 | FALSE | 54 | The time consuming elements of the project are mostly completed. The environmental review and fiber availability problems delayed the start but we are getting back on the original timeline. We anticipate getting back to the baseline in third quarter 2012. | 0 |  | NA | 100 | Completed. Pursuant to the new guidelines, some route modifications will be requested Q1 2012. No significant changes to the approved Environmental Assessment is expected. | 100 | Completed this quarter. | 100 | Completed this quarter. | 100 | Completed this quarter. | 70 | This will proceed as construction moves forward. We anticipate getting back to the baseline in second quarter 2012. | 70 | We have identified the equipment to be obtained in many cases, and are proceeding to acquire it in advance of readiness for deployment. We anticipate getting back to the baseline in third quarter 2012. | 75 | We are working to get back on schedule, contracting for construction simultaneously in several areas. We anticipate getting back to the baseline in third quarter 2012. | 15 | We have been making arrangements for equipment deployment, so progress has been made in this area, even though little equipment has been deployed yet. We anticipate getting back to the baseline in third quarter 2012. | 35 | This will proceed as construction moves forward. We anticipate getting back to the baseline in third quarter 2012, when construction is back on schedule. | 2012-02-17 14:47 | 2012-02-17 14:47 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2012 | Q1 | Q1 - 2012 | 5956 | 5577 | FALSE | 70 | The time consuming elements of the project are mostly completed. The environmental review and fiber availability problems delayed the start but we are getting back on the original timeline. We anticipate getting back to the baseline in third quarter 2012. | 0 |  | NA | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 90 | Delays in pole attachment permits and Forest Service permits have delayed this somewhat. Projected completion second quarter 2012. | 65 | We have identified the equipment to be obtained in many cases, and are proceeding to acquire it in advance of readiness for deployment where possible. We anticipate getting back to the baseline in third quarter 2012. | 85 | We are working to get back on schedule, contracting for construction simultaneously in several areas. We anticipate getting back to the baseline in third quarter 2012. | 30 | We have been making arrangements for equipment deployment, so progress has been made in this area, even though little equipment has been deployed yet. We anticipate getting back to the baseline in third quarter 2012. | 50 | This will proceed as construction moves forward. We anticipate getting back to the baseline in third quarter 2012. | 2012-05-08 11:05 | 2012-05-08 11:05 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2012 | Q2 | Q2 - 2012 | 7276 | 6265 | FALSE | 73 | This will bring us nearly back to the intended completion. | 0 |  | NA | 100 | This will be in line with projections | 100 | This is already completed | 100 | This will be in line with projections. | 100 | Completed | 100 | Completed | 75 | This will be back on schedule. | 90 | This includes the route changes | 40 | This will be approaching the intended schedule. | 65 | This will be approaching the intended schedule. | 2012-08-29 15:09 | 2012-08-29 15:09 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2012 | Q3 | Q3 - 2012 | 7934 | 6671 | FALSE | 86 | On Schedule | 0 |  | NA | 100 | On Schedule | 100 | On Schedule | 100 | On Schedule | 100 | On Schedule | 100 | On Schedule | 90 | On Schedule | 100 | On Schedule | 90 | On Schedule | 100 | On Schedule | 2012-11-16 16:46 | 2012-11-16 16:46 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2012 | Q4 | Q4 - 2012 | 8710 | 7515 | FALSE | 90 | On schedule | 0 |  | NA | 100 | On schedule | 100 | On schedule | 100 | On schedule | 100 | On schedule | 100 | On schedule | 95 | On schedule | 99 | On schedule | 85 | On schedule | 100 | On schedule | 2013-02-11 16:54 | 2013-02-11 16:54 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2013 | Q1 | Q1 - 2013 | 10032 | 8566 | FALSE | 98 | We expect that all but a few items will be completed. All eqiupment will be ordered and scheduled for delivery. | 0 |  | NA | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 95 | Some late deliveries may still need to be deployed | 100 | Completed | 2013-05-31 15:45 | 2013-05-31 15:45 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2013 | Q2 | Q2 - 2013 | 10824 | 9084 | FALSE | 100 | Completed | 0 | NA | NA | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed This includes a planned connection of an additional four CAIs building an additional 1.5 miles of fiber. | 100 | Completed | 100 | Completed | 2013-08-30 14:20 | 2013-08-30 14:20 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570032 | 2013 | Q3 | Q3 - 2013 | 12028 | 10191 | FALSE | 100 | This is as planned | 0 | NA | NA | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 2014-04-08 15:49 | 2014-04-08 15:49 | 5521 | 5521 | Lane Council of Government | TRUE
NT10BIX5570033 | 2010 | Q2 | Q2 - 2010 | 57 | 1332 | FALSE | 7 |  |  |  |  | 100 |  | 50 |  | 30 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2010 | Q3 | Q3 - 2010 | 410 | 1471 | FALSE | 10 | Variance of 7%. Completion of EA "Environmental Assessment" held up due to various issues; including design verification and delay in SHPO comments being received. These issues which have been dealt with. | 0 | Administration and Project Management (10%) Federal Grant Expenditures (7%) | Variance of 17%. Completion of EA held up due to various issues; including design verification and delay in SHPO comments being received. These issues have been dealt with. Variance of 10%. Completion of EA held up due to various issues. Major cost expenditures have not occurred since EA Environmental Assessment has to be approved before procurement activities are awarded. | 100 | No variance from baseline. | 100 | No variance from baseline. | 50 | No variance from baseline. | 20 | Variance of 30%. Delay in completing EA has delayed initiation of construction activities. | 10 | Variance of 10%. Delay in completing EA has delayed site preparation activities. | 5 | No variance from baseline. | 5 | No variance from baseline. | 0 | No variance from baseline. | 0 | No variance from baseline. | 2010-11-24 07:07 | 2010-11-24 07:07 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2010 | Q4 | Q4 - 2010 | 1310 | 2336 | FALSE | 5 | Variance of 23%. Completion of EA "Environmental Assessment" held up | 0 | Administration and Project Management (20%) Federal Grant Expenditures (5%) | Variance of 16%. Variance of 23% due to delay in completing EA "Environmental Assessment". | 100 | No variance from baseline. Done; already completed. | 100 | No variance from baseline. Done; already completed. | 65 | Variance of 15% Due to network redesign | 20 | Variance of 60% due to delay in completing EA "Environmental Assessment". | 0 | Variance of 50% due to delay in completing EA "Environmental Assessment". | 0 | Variance of 10%due to delay in completing EA "Environmental Assessment". | 0 | Variance of 10%, due to delay in completing EA "Environmental Assessment". | 0 | Variance of 10%, due to delay in completing EA "Environmental Assessment". | 0 | No variance from baseline. | 2011-02-22 15:58 | 2011-02-22 15:58 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2011 | Q1 | Q1 - 2011 | 1986 | 2738 | FALSE | 8 | Due to time to complete network design update and EA " Environmental Assessment". RFP "Request for Proposals", process in full cycle with all major RFP's being worked on in the quarter. | 38 | Management and Administration 38%. | We are very involved in processing Request for Proposals which have required a lot of preparation, we are now executing the RFP's along a strategy of quadrant priorities which will ensure we meet the expenditures guidelines. | 93 | Received FONSI approval (Finding of No Significant Impact) received on Nov 23, 2010 | 100 | Network redesign update completed. | 5 | Delay in completing network redesign update and EA process. Have signed contracts for land lease for new build towers sites. Received draft leasing contract or letter of intent for all existing tower sites. Will be accelerating payments on leases. | 43 | Delay in completing network redesign update and EA process. Entity selected for Permits Tower Construction will review new build sites, do terrain study and develop pre-design foundation build. Permits applications being worked on for high priority sites. | 5 | Delay in completing network redesign update and EA process. Complete Site Preparation RFP " Request for Proposals", for existing sites; published, receive proposals, evaluation of proposals, selection and signature of contract. | 3 | Delay in completing network redesign update and EA process. Complete Request for Proposals for Telecom Equipment, for 23 Sites (all sites), published, receive proposals, evaluation of proposals initiated , selection,and acquisition of equipment initiated . Complete FCC licencing agreements for all Point to Point links. | 0 | Delay in process for completion of EA and network designs update. Develop New Tower Construction RFP,"Request for Proposals" for Sites New Towers, final edition, publish. | 0 | Delay in completion of EA and network designs update held up procurement process. | 0 | No variance from baseline. | 2011-05-12 16:48 | 2011-05-12 16:48 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2011 | Q2 | Q2 - 2011 | 3394 | 3460 | FALSE | 22 | Due to time to complete network design update and EA " Environmental Assessment". RFP "Request for Proposals", process in full cycle with all major RFP's being worked on in the quarter. | 58 | Management and Administration 58% | We are very involved in processing RFPs which have required a lot of preparation, we are now executing the RFP's along a strategy of quadrant priorities which will ensure we meet the expenditures guidelines. | 93 | Received FONSI approval (Finding of No Significant Impact) received on Nov 23, 2010 | 100 | Network redesign update completed. | 25 | Delay in completing network redesign update and EA process. Have signed contracts for land lease for new build towers sites. Complete leasing contract for all existing tower sites. | 63 | Delay in completing network redesign update and EA process. Entity selected for Permits Tower Construction will review new build sites, do terrain study and develop pre-design foundation build. Permits applications being worked on for high priority sites. | 31 | Delay in completing network redesign update and EA process. Completed Site Preparation RFP " Request for Proposals", for existing sites, contract to be signed and initiation of work on existing sites with eight sites expected to be completed. | 19 | Delay in completing network redesign update and EA process. Sign contract with selected vendor of Request for Proposal for Telecommunications Equipment, initiate acquisition of equipment. Commence Deployment. | 19 | Delay in process for completion of EA and network designs update. Develop New Tower Construction RFP,"Request for Proposal" for New Tower Sites, final edition, publish. | 19 | Delay in completion of EA and network designs update held up start of procurement process. Initiate deployment of equipment on existing tower sites. | 19 | Delay in completion of EA and network designs update. | 2011-08-31 09:40 | 2011-08-31 09:40 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2011 | Q3 | Q3 - 2011 | 4058 | 3872 | FALSE | 41 | Initial delay due to Time to complete network design update and EA " Environmental Assessment". Currently RFP "Request for Proposals", process in full cycle with the fourth RFP , NOC Equipment , in process . | 53 | Management and Administration 53% | We will complete our 4th major RFP, (Request for Proposals) which require a lot of time for preparation and execution. All major proposals for acquisition of network equipment will be completed. A strategy of quadrant priorities was implemented which will ensure we meet the expenditures guidelines. | 93 | Received FONSI approval (Finding of No Significant Impact) received on Nov 23, 2010 | 100 | Network redesign update completed. | 34 | Initial delay due to completing network redesign update and EA process. Will be completing lease contracts for three additional existing tower sites. Lease payments are meeting approved waiver for matching funds. | 77 | Delay in completing network redesign update and EA process. Continue submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency for the construction of three new telecommunications towers to be used by the network in underserved areas. We initially underestimated the time it would take to construct new towers and the time to process the RFPâ€™s for construction permits. | 23 | Delay in completing network redesign update and EA process. Completed RFP " Request for Proposals", Site Preparation , for existing sites, continuation of work in twelve existing sites with ten sites expected to be completed in this quarter. RFP for new tower construction to be issued for towers with approved permits. Quadrant strategy is based on initial two quadrants where existing towers sites are majority of sites. | 45 | Delay in completing network redesign update and EA process. We will receive 50% or more of all equipment for Request for Proposal #3 (Telecommunications Equipment). Implemented system to provide inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of being received, staged and implemented. Request for Proposal #4; ''Acquisition and Implementation of the Central Office Equipment for INTECO'S Broadband Network", will be evaluated, awarded and have contract signed. | 45 | Delay in process for completion of EA and network designs update. | 45 | Delay in completion of EA and network designs update held up start of procurement process. Initiate deployment of equipment on existing tower sites. | 45 | Delay in completion of EA and network designs update. | 2011-11-16 10:05 | 2011-11-16 10:05 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2011 | Q4 | Q4 - 2011 | 5062 | 4734 | FALSE | 70 | Initial delay due to Time to complete network design update and Environmental Assessment. Currently Request for Proposals, process in full cycle with the fifth Request for Proposal, New Tower Construction, in process. | 70 | Management and Administration | We will complete our 5th major Request for Proposals which have required a lot of time for preparation and execution. All major proposals for acquisition of telecommunications equipment and network equipment will be completed and installation initiated with most equipment installed. A strategy of quadrant priorities was implemented which will ensure we meet the expenditures guidelines. We have targeted the summer of 2012 to initiate the two major quadrants in the network. | 100 | Received FONSI approval (Finding of No Significant Impact) received on Nov 23, 2010 | 100 | Network redesign update completed. | 66 | Initial delay due to completing network redesign update and Environmental Assessment process. Will be completing lease contracts for three additional existing tower sites. Lease payments are meeting approved waiver for matching funds. | 89 | Delay in completing network redesign update and Environmental Assessment process. Complete three additional submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency for the construction of three new telecommunications towers to be used by the network in underserved areas. We initially underestimated the time it would take to construct new towers and the time to process the Request for Proposals for construction permits. | 26 | Delay in completing network redesign update and Environmental Assessment process. Complete Request for Proposal;Site Preparation, for existing sites, with a total of fifteen sites expected to be completed in this quarter. Request for Proposal for new tower construction to be issued for towers with approved permits. | 77 | Delay in completing network redesign update and Environmental Assessment process. We will receive 90% or more of all equipment for Request for Proposal #3; Telecommunications Equipment. Request for Proposal #4; Acquisition and Implementation of the Central Office Equipment for INTECO's Broadband Network, all equipment to be received and installed to begin acceptance testing and integration testing. | 77 | Delay in completing network redesign update and Environmental Assessment process. We will receive 90% or more of all equipment for Request for Proposal #3 (Telecommunications Equipment). Request for Proposal #4; Acquisition and Implementation of the Central Office Equipment for INTECO's Broadband Network, all equipment to be received and installed to begin acceptance testing and integration testing. | 77 | Delay in completing network redesign update and Environmental Assessment process. We will receive 90% or more of all equipment for Request for Proposal #3; Telecommunications Equipment. Request for Proposal #4; Acquisition and Implementation of the Central Office Equipment for INTECO's Broadband Network, all equipment to be received and installed to begin acceptance testing and integration testing. | 77 | Delay in completing network redesign update and Environmental Assessment process. Request for Proposal #4; Acquisition and Implementation of the Central Office Equipment for INTECO's Broadband Network, all equipment to be received and installed to begin acceptance testing and integration testing. | 2012-02-16 08:29 | 2012-02-16 08:29 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2012 | Q1 | Q1 - 2012 | 6048 | 5623 | FALSE | 82 | Initial delay due to Time to complete network design update and Environmental Assessment. New tower construction, in process. | 86 | Management and Administration | We met the expenditures guidelines as per SAC with a 72% expenditures of the project to date. All major proposals for acquisition of telecommunications equipment and network equipment will be completed and installation initiated with most equipment installed. A strategy of quadrant priorities was implemented which will ensure we meet the expenditures guidelines. We have targeted the summer of 2012 to initiate the two major quadrants in the network. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 82 | Completed lease contracts for total 16 existing tower sites. Complete land lease contracts for two additional sites. All lease agreements will be completed by Q3 2012. | 83 | Submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency for three additional sites, We expect these three sites to be approved in this quarter. We have authorization granted for the construction of four new telecommunications towers. We initially underestimated the time it would take to get construction permits for new tower construction. All permits for construction will be completed by Q3 2012. | 63 | Will completed Site Preparation & Construction on 16 existing tower sites. Will complete three new tower construction sites and substantially complete a fourth site. All site prep will be concluded by end of Q4 2012. | 85 | The vendor for Request for Proposal #3; Telecommunications Equipment, has completed the purchase of equipment. We developed a system to provide inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of being received, staged and implemented. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was substantially completed. | 84 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 was substantially completed. | 84 | Delay in completing network redesign update and Environmental Assessment process. We will receive 90% or more of all equipment for Request for Proposal #3; Telecommunications Equipment. Request for Proposal #4; Acquisition and Implementation of the Central Office Equipment for INTECO's Broadband Network, all equipment to be received and installed to begin acceptance testing and integration testing. | 84 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 was substantially completed and is now ready for acceptance testing, systems and integration testing. | 2012-05-14 07:11 | 2012-05-14 07:11 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2012 | Q2 | Q2 - 2012 | 7186 | 6220 | FALSE | 91 | Initial delay due to Time to complete network design update and Environmental Assessment. New tower construction, in process. All towers to be completed by Q4 2012. | 89 | Management and Administration | We met the expenditures guidelines as per SAC with a 72% expenditures of the project to date. All major proposals for acquisition of telecommunications equipment and network equipment have been completed and installation initiated with most equipment installed. A strategy of quadrant priorities was implemented which will ensure we meet the expenditures guidelines. We have targeted August 2012 to initiate the largest quadrant in the network. All tower construction will be completed by Q4 2012. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 92 | Completed lease or land lease contracts for 21 sites. All lease agreements will be completed by Q3 2012. | 96 | Submission of permits, including if necessary soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency. We have pending three sites to receive permits for roof-top installation. We initially underestimated the time it would take to get construction permits for new tower construction. All permits for construction will be completed by Q4 2012. | 79 | Completed site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in fifteen tower sites. We will be completing four additional sites in the third quarter, which leaves five sites, mostly roof-tops, to be completed in the fourth quarter. | 92 | The vendor for Request for Proposal #3; Telecommunications Equipment, has completed the purchase of equipment. We developed a system to provide inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of being received, staged and implemented. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was substantially completed. | 92 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 was substantially completed. All network build to be completed by Q4 2012. | 92 | We have received all equipment for Request for Proposal#3; Telecommunications Equipment. Request for Proposal #4; Acquisition and Implementation of the Central Office Equipment for INTECO's Broadband Network, all equipment has been received and installed. Acceptance, systems and integration testing is underway. All equipment deployment to be completed by Q4 2012. | 92 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 was completed and is now in acceptance testing, systems and integration testing. | 2012-08-21 12:22 | 2012-08-21 12:22 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2012 | Q3 | Q3 - 2012 | 7844 | 6626 | FALSE | 97 | New tower construction, in process. All towers to be completed by Q4 2012. | 98 | Management and Administration | All telecommunications equipment and network equipment have been completed and final testing underway. A strategy of quadrant priorities was implemented with the largest quadrant activated in August/September 2012. All major tower construction will be completed by October 2012, with four roof-tops being completed in fourth quarter 2012. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 94 | Completed lease or land lease contracts for 23 sites. All lease agreements will be completed by Q4 2012. | 100 | Submission of permits, including if necessary soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency. We have pending three sites to receive permits for roof-top installation. We initially underestimated the time it would take to get construction permits for new tower construction. All permits for construction will be completed by Q4 2012. | 94 | Completed site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in nineteen tower sites. We will be completing five additional sites, one tower and four roof-tops, in the fourth quarter. | 97 | The vendor for Telecommunications Equipment, has completed the purchase of equipment. We developed a system to provide inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of being received, staged and implemented. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network will be completed in this quarter. | 97 | The vendor for Telecommunications Equipment completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. All network build to be completed by Q4 2012. | 97 | All equipment for INTECO's Broadband Network, all equipment has been received and installed. Acceptance, systems and integration testing and all equipment deployment to be completed in Q4 2012. | 97 | The vendor for Telecommunications Equipment is completing the testing of all microwave radios (integration and acceptance testing). Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. All network build to be completed by Q4 2012. | 2012-11-13 13:18 | 2012-11-13 13:18 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2012 | Q4 | Q4 - 2012 | 9138 | 7936 | FALSE | 99 | All 24 sites to be completed by Q1-2013. | 99 | Management and Administration | All telecommunications equipment and network equipment have been completed and final testing.. A strategy of quadrant priorities was implemented with the largest quadrant activated in August/September 2012. All major tower construction has been completed, with two sites being completed in first quarter 2013. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 100 | Completed lease or land lease contracts for all 24 sites. | 100 | Submission of permits, including if necessary soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency. We initially underestimated the time it would take to get construction permits for new tower construction. All permits for construction will be completed by Q1-2013. | 99 | Completion of all site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in twenty four tower sites. We will be completing two additional sites, in the Q1-2013. | 100 | All Telecommunications Equipment has been acquired. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. | 100 | Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. All network build to be completed by Q1-2013. | 100 | All equipment for INTECO's Broadband Network, all equipment has been received and installed. Acceptance, systems and integration testing and all equipment deployment to be completed in Q1-2013. | 100 | The vendor for Telecommunications Equipment is completing equipment installation in last two sites. Acquisition, installation, testing and verification of the NOC Equipment for INTECO's Broadband Network will be completed in Q1 2013. | 2013-03-14 12:33 | 2013-03-14 12:33 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2013 | Q1 | Q1 - 2013 | 9900 | 8491 | FALSE | 100 | All 24 sites to be completed by Q2-2013. | 100 | Management and Administration | All sites completed and operational. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 100 | Completed lease or land lease contracts for all 24 sites. | 100 | All permits for construction will be completed by Q2-2013. | 100 | Completion of all site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in twenty four tower sites. | 100 | All Telecommunications Equipment completed. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network completed. | 100 | Acquisition and installation of the NOC Equipment for INTECO's Broadband Network completed. All network build to be completed. | 100 | All equipment for INTECO's Broadband Network, all equipment completed. All acceptance, systems and integration testing and all equipment deployment to be completed. | 100 | All acquisition, installation, testing and verification of telecommunications equipment and NOC Equipment for INTECO's Broadband Network completed. | 2013-05-24 11:41 | 2013-05-24 11:41 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2013 | Q2 | Q2 - 2013 | 10694 | 9008 | FALSE | 100 | All 24 sites to be completed by Q3-2013. | 100 | Management and Adminsitration | All sites completed and operational. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 100 | Completed lease or land lease contracts for all 24 sites. | 100 | All permits for construction will be completed by Q3-2013. | 100 | Completion of all site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in twenty four tower sites. | 100 | All Telecommunications Equipment completed. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network completed. | 100 | Acquisition and installation of the NOC Equipment for INTECO's Broadband Network completed. All network build to be completed. | 100 | All equipment for INTECO's Broadband Network, all equipment completed. All acceptance, systems and integration testing and all equipment deployment to be completed. | 100 | All acquisition, installation, testing and verification of telecommunications equipment and NOC Equipment for INTECO's Broadband Network completed. | 2013-08-22 09:41 | 2013-08-22 09:41 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | 2013 | Q3 | Q3 - 2013 | 11634 | 9755 | FALSE | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | Management and Administration | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 2014-01-21 14:38 | 2014-01-21 14:38 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570034 | 2010 | Q2 | Q2 - 2010 | 58 | 1288 | FALSE | 1 |  | 0 |  |  | 100 |  | 34 |  | 0 |  | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2010 | Q3 | Q3 - 2010 | 360 | 1446 | FALSE | 43 | Per Baseline Plan | 0 |  | N/A | 100 | FONSI issued on 09/30/2010.Environmental Assessment was deemed a sole-source procurement and was not approved for funding under the grant. | 56 | Per Baseline Plan | 0 | N/A | 9 | Per Baseline Plan | 100 | Per Baseline Plan | 42 | Per Baseline Plan | 47 | Per Baseline Plan | 22 | Per Baseline Plan | 51 | Per Baseline Plan | 2010-11-19 16:00 | 2010-11-19 16:00 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2010 | Q4 | Q4 - 2010 | 1208 | 2241 | FALSE | 67 | On Schedule | 35 |  | Partial contribution of in kind match assets. | 100 | FONSI issued on 09/30/2010. Professional Services fees incurred related to the Environmental Assessment were deemed a sole-source procurement and were not approved for funding under the grant. | 100 | On Schedule | 0 | NA | 75 | On Schedule | 100 | On Schedule | 77 | On Schedule | 82 | On Schedule | 35 | On Schedule | 51 | On Schedule | 2011-02-17 17:02 | 2011-02-17 17:02 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2011 | Q1 | Q1 - 2011 | 2090 | 2790 | FALSE | 78 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay; however, DeltaCom's project is currently projected to complete in the fourth quarter of 2011, well in advance of the BTOP deadline of January 31, 2013. | 100 |  | Remaining in-kind assets will be dedicated to the project in second quarter 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 100 | On schedule | 0 | N/A | 45 | To date, costs associated with this milestone have under run projected budget expenditures. | 100 | On schedule | 75 | Expenditures for equipment slightly behind schedule due to delayed start. No significant variance to overall baseline budget is anticipated since milestone will be in line with the baseline plan in third quarter 2011. | 78 | DeltaCom anticipates a marginal under run variance against the baseline plan for this milestone. DeltaCom will complete work associated with this milestone category in third quarter 2011. | 48 | The baseline plan over run associated with this milestone is due to invoice payment timing. No significant variance to the overall baseline plan is anticipated. This milestone is expected to be complete in third quarter 2011. | 0 | No expenditures anticipated until third quarter 2011.DeltaCom currently has an under run variance against the baseline plan for this milestone. Funds were budgeted for test equipment that have not been required to date. Funds will be required prior to completion of the project. | 2011-05-17 14:44 | 2011-05-17 14:44 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2011 | Q2 | Q2 - 2011 | 2964 | 3239 | FALSE | 82 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay; however, DeltaCom's project is currently projected to complete in the fourth quarter of 2011, well in advance of the BTOP deadline of January 31, 2013. | 100 |  | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 62 | Network design was completed in the first quarter of 2011. Additional invoices are being processed and scheduled to be paid. This milestone currently has an under run variance against the baseline plan. Finalization of network drawings, for the newly built network, may require future spend in the fourth quarter of 2011. | 0 | N/A | 16 | To date, costs associated with this milestone have under run projected budget expenditures. | 100 | Completed | 69 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan in the fourth quarter 2011. | 95 | DeltaCom will complete work associated with this milestone category in third and fourth quarter 2011. | 97 | Milestone to be completed by fourth quarter 2011. | 0 | DeltaCom currently has an under run variance against the baseline plan for this milestone. Funds were budgeted for test equipment that have not been required to date. Funds may be required prior to completion of the project. | 2011-08-08 16:37 | 2011-08-08 16:37 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2011 | Q3 | Q3 - 2011 | 3968 | 3822 | FALSE | 85 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay; however, DeltaCom's project is currently projected to complete in the first quarter of 2012, well in advance of the BTOP deadline of January 31, 2013. | 100 |  | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | Network design was completed in the first quarter of 2011. Additional invoices are being processed and scheduled to be paid. This milestone currently has an under run variance against the baseline plan. | 0 | N/A | 16 | To date, costs associated with this milestone have under run projected budget expenditures. | 100 | Complete | 74 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan in first quarter 2012. | 96 | DeltaCom anticipates a marginal under run variance against the baseline plan for this milestone. DeltaCom will complete work associated with this milestone category in first quarter 2012. | 80 | Milestone is forecast to be 100% complete in first quarter 2012. | 81 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2011-11-10 15:52 | 2011-11-10 15:52 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2011 | Q4 | Q4 - 2011 | 5072 | 4744 | FALSE | 92 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay; however, DeltaCom's project is currently projected to complete in the third quarter of 2012, well in advance of the BTOP deadline of January 31, 2013. | 100 | In-Kind Assetts | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. Additional cost will be incurred for final as-built drawings. | 0 | N/A | 84 | To date, costs associated with this milestone have under run projected budget expenditures. | 100 | Complete | 78 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan in second quarter 2012. | 100 | Expenditures in this milestone are projected to be at 115% of the baseline category by the end of first quarter 2012. Overall, the project will remain under budget as noted in the SF-424C Budget below. Due to extended negotiations with make-ready and collocation vendors, DeltaCom expects to complete work associated with this milestone category in second quarter 2012. | 82 | Milestone is forecast to be 100% complete in second quarter 2012. | 62 | DeltaCom currently has an under run variance against the baseline plan for this milestone | 2012-02-16 15:14 | 2012-02-16 15:14 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2012 | Q1 | Q1 - 2012 | 6004 | 5601 | FALSE | 93 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay. Additional delays are due to extended negotiations with make-ready and collocation vendors. However, DeltaCom's project is currently projected to complete in the third quarter of 2012, well in advance of the BTOP deadline of January 31, 2013. | 100 | Dark Fiber and Land Assets | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. Additional cost will be incurred for final as-built drawings. | 0 | N/A | 84 | To date, costs associated with this milestone have under run projected budget expenditures. | 100 | Complete | 79 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan by the end of the project. | 100 | Expenditures in this milestone are projected to be at 116% of the baseline category by the end of first quarter 2012. Overall, the project will remain under budget as noted in the SF-424C Budget below. Due to extended negotiations with make-ready and collocation vendors, DeltaCom expects to complete work associated with this milestone category in second quarter 2012. | 82 | Milestone is forecast to be 100% complete by the end of the project. | 67 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2012-05-10 11:34 | 2012-05-10 11:34 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2012 | Q2 | Q2 - 2012 | 7026 | 6140 | FALSE | 93 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay. Additional delays are due to extended negotiations with make-ready and collocation vendors. However, DeltaCom's project is currently projected to complete in the third quarter of 2012, with all expenditures being invoiced by the BTOP deadline of January 31, 2013. | 100 | Dark Fiber and Land Assets | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. Additional cost will be incurred for final as-built drawings. | 0 | N/A | 85 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be incurred and invoiced by the BTOP deadline of January 31, 2013. | 100 | Complete | 79 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan by the end of the project. | 100 | Expenditures in this milestone are projected to be at 115% of the baseline category by the end of first quarter 2012. Overall, the project will remain under budget as noted in the SF-424C Budget below. Due to extended negotiations with make-ready and collocation vendors, DeltaCom expects to complete work associated with this milestone category in second quarter 2012. | 90 | Milestone is forecast to be 100% complete by the end of the project. | 67 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2012-08-10 18:01 | 2012-08-10 18:01 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2012 | Q3 | Q3 - 2012 | 8056 | 6734 | FALSE | 96 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay. Additional delays are due to extended negotiations with make-ready and collocation vendors. However, DeltaCom's project was completed in the third quarter of 2012, and all expenditures will be invoiced by the BTOP deadline of January 31, 2013. | 100 | Dark Fiber and Land Assets | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. | 0 | N/A | 93 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be invoiced by the BTOP deadline of January 31, 2013. | 100 | Complete | 83 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be invoiced by the BTOP deadline of January 31, 2013. | 100 | This milestone is complete and currently expenditures in this milestone are at 118% of the baseline category. Overall, the project remains under budget as noted in the SF-424C Budget below. Any additional expenditures will be invoiced by the BTOP deadline of January 31, 2013. | 89 | This milestone currently has an under run variance against the baseline plan. Equipment deployment was completed in the third quarter of 2012. | 67 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2012-11-26 17:05 | 2012-11-26 17:05 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2012 | Q4 | Q4 - 2012 | 8872 | 7658 | FALSE | 93 | Project expenditures are below the baseline plan due to an under run in the overall project budget. DeltaCom's project was completed in the third quarter of 2012, and all expenditures will be invoiced by the BTOP deadlines. | 100 | Dark Fiber and Land Assets | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. | 0 | N/A | 93 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be invoiced by the BTOP deadlines. | 100 | Complete | 79 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be invoiced by the BTOP deadlines. | 100 | This milestone is complete and currently expenditures in this milestone are at 114% of the baseline category. Overall, the project remains under budget as noted in the SF-424C Budget below. Any additional expenditures will be invoiced by the BTOP deadlines. | 89 | This milestone currently has an under run variance against the baseline plan. Equipment deployment was completed in the third quarter of 2012. | 67 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2013-02-21 11:47 | 2013-02-21 11:47 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | 2013 | Q1 | Q1 - 2013 | 9892 | 8486 | FALSE | 91 | Complete Project expenditures are below the baseline plan due to an under run in the overall project budget. DeltaCom's project was completed in the third quarter of 2012, and all expenditures were invoiced by 05/01/2013. The decrease in this milestone category is the result of a return of funds to ASAP for expenditures not covered by the grant. | 100 | Dark Fiber and Land Assets Close Out Activities | Complete In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. Fees associated with close out activities were expended and reimbursed by 05/01/2013. | 100 | Complete DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | Complete This milestone has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. | 0 | N/A | 93 | Complete This milestone has an under run variance against the baseline plan. | 100 | Complete | 79 | Complete This milestone has an under run variance against the baseline plan. | 100 | Complete Expenditures in this milestone are at 107% of the baseline category. Overall, the project remained under budget as noted in the SF-424C Budget below. The decrease in this milestone category is the result of a return of funds to ASAP for expenditures not covered by the grant. | 89 | Complete This milestone has an under run variance against the baseline plan. Equipment deployment was completed in the third quarter of 2012. | 67 | Complete This milestone has an under run variance against the baseline plan. | 2013-05-23 16:38 | 2013-05-23 16:38 | 5523 | 5523 | DeltaCom, Inc. | TRUE
NT10BIX5570035 | 2010 | Q3 | Q3 - 2010 | 416 | 1474 | FALSE | 10 | Co-first priority security interest confirmed by NTIA as detailed previously. In addition, for site preparation and construction, NTIA grant of limited exclusions to NEPA. | 0 | NA | Same as 2a | 100 | - | 100 | - | 100 | - | 100 | - | 0 | Same as 2a | 0 | Same as 2a | 0 | Same as 2a | 0 | Same as 2a | 0 | Same as 2a | 2010-11-24 12:09 | 2010-11-24 12:09 | 5525 | 5525 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2010 | Q4 | Q4 - 2010 | 1264 | 2290 | FALSE | 42 | Network Deployment will commence in Q2 pending Intercreditor Agreement and Historic Preservation Review. | 0 | N/A | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 12 | Network Deployment will commence in Q2 pending Intercreditor Agreement and Historic Preservation Review. | 16 | Equipment procurement in process. Pending Intercreditor Agreement and Historic Preservation Review. | 20 | Network Deployment and other equipment procurement and installation will commence in Q2 pending Intercreditor Agreement and Historic Preservation Review. | 16 | Equipment procurement in process. Pending Intercreditor Agreement and Historic Preservation Review. | 0 | Network not yet deployed, pending Intercreditor Agreement and Historic Preservation Review. | 2011-02-21 17:36 | 2011-02-21 17:36 | 5525 | 5525 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2011 | Q1 | Q1 - 2011 | 2238 | 2864 | FALSE | 78 | -9% Variance. Delays in Fiber-optic cable order fulfillment lead time. Phase 1 Archaeological Survey and shovel testing for 9.3-mile buried section and building placement site. | 0 | Inspection | -100% Variance. Finding of No Significant Impact required before new construction can begin. Issuance expected in early Q2. Fiber-optic order fulfillment lead times will delay construction. | 100 | 466% Budget Variance. Environmental Assessment completed. Phase 1 Archaeological Survey and shovel testing charged to this account. | 73 | -10% Variance. Results of Phase 1 Archeological Survey and shovel testing may impact network design. | 40 | -60% Variance. Baseline forecast included costs of land, structures and appraisals in the Right of Way budget category. Phase 1 archaeological survey and shovel testing required to discover artifacts in 9.3 mile buried section and land for building placement. | 97 | N/A | 0 | -100% Variance. Land clearing and site preparation not allowable until Phase 1 Archaeological Survey and shovel testing completed. | 60 | -40% Variance. Finding of No Significant Impact required before procurement allowable for other than for Management & Administrative Expenditures. Issuance expected in early Q2 2011 at which time contract negotiations and award will be finalized. | 39 | -61% Variance. Finding of No Significant Impact required before new construction can begin. Issuance expected in early Q2. Fiber-optic order fulfillment lead times will delay construction. Buried Placement of 9.3 miles of line cannot begin until Phase 1 Archeological Survey and shovel testing is completed, but less than 10% of the planned network will be buried cable. | 0 | Baseline forecast included equipment installation & testing in Equipment Procurement budget. | 0 | Same as above | 2011-05-20 23:40 | 2011-05-20 23:40 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2011 | Q2 | Q2 - 2011 | 3244 | 3384 | FALSE | 53 | (41)% Variance. Delays in Intercreditor Agreement, Environmental Assessment review, and completion of Historic and Cultural Preservation Review prevented draw down of funds until April, 2011. | 0 | Inspection | (100%) Variance. Same as Network Build. | 100 | 734% Variance. Cost of environmental assessment and archaeological services ran significantly over budget due to the high number of prehistoric and historic sites in Hardy County, WV and the requirement for a Phase 1 archaeological survey and shovel testing. | 100 | 13% Variance. Resources reallocated to completion of environmental/archaeological assessments. Segments of the network were rerouted and redesigned from buried cable to aerial placement, to avoid identified historic and cultural sites. | 12 | (88)% Variance. The baseline forecast included purchases of land, structures and appraisals, and purchases of land or easements for Rights of Way in this category. Costs associated with obtaining no-cost private Rights of Way were included in Permitting & Other Approvals. Delays in Environmental Assessment review and completion of Historical and Cultural Preservation Review delayed purchases of land for building placement sites and required easements. Phase 1 archaeological survey and shovel testing required to discover artifacts in 9.3 mile buried section and land for building placement. Land has been purchased for one building site, but site prep and building placement may not proceed until the Phase survey is completed and approvals obtained. | 100 | 81% Variance. The baseline forecast included costs of land, structures, appraisals and purchases of land or easements for Rights of Way in the Rights of Way budget category. Costs associated with construction permitting and obtaining no-cost private Rights of Way were included in this category. Network design rerouted in connection with Environmental Assessment and completion of Historical and Cultural Preservation Review due to number of archaeological prehistoric and historic sites in Hardy County. | 0 | (100)% Variance. Site preparation may not proceed until completion of Phase 1 archaeological survey and approval by WV Historic Preservice Office and National Telecommunications & Information Administration. | 12 | (87.7%) Variance. Baseline forecast included Equipment Deployment expenditures in Equipment Procurement budget. Deployment expenditures have been included in this category for consistency. Equipment has been specified and prices negotiated. Delivery dates are established but deferred until two facilities sites are connected over fiber. | 49 | (51)%) Variance. Delays in approval of Intercreditor Agreement and Environmental Assessment prevented procurement of materials and commencement of construction prior to tsecond quarter of 2011. Hardy contributed existing network infrastructure and electronics deployed to Community Anchor Institutions, representing 18% completion. Major materials have been ordered, and construction drawings and requests for proposals documentation completed for all four phases of construction. | 0 | N/A. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | N/A. Same as above. | 2011-08-19 16:23 | 2011-08-19 16:23 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2011 | Q3 | Q3 - 2011 | 4238 | 3967 | FALSE | 93 | (7%) Variance. Delays in Intercreditor Agreement, Environmental Assessment review, and completion of Historic and Cultural Preservation Review prevented draw down of funds until April, 2011. | 100 | Inspection | No variance | 100 | 880% Variance. Cost of environmental assessment and archaeological services ran significantly over budget due to the high number of prehistoric and historic sites in Hardy County, WV and the requirement for a Phase 1 archaeological survey and shovel testing. | 100 | 13% Variance. Resources reallocated to completion of environmental/archaeological assessments. Segments of the network were rerouted and redesigned from buried cable to aerial placement, to avoid identified historic and cultural sites. | 12 | (88%) Variance. The baseline forecast included purchases of land, structures and appraisals, and purchases of land or easements for Rights of Way in this category. Costs associated with obtaining no-cost private Rights of Way were included in Permitting & Other Approvals. Delays in Environmental Assessment review and completion of Historical and Cultural Preservation Review delayed purchases of land for building placement sites and required easements. Phase 1 archaeological survey and shovel testing required to discover artifacts in 9.3 mile buried section and land for building placement. Land has been purchased for one building site, but site prep and building placement may not proceed until the Phase survey is completed and approvals obtained. | 100 | 154% Variance. The baseline forecast included costs of land, structures, appraisals and purchases of land or easements for Rights of Way in the Rights of Way budget category. Costs associated with construction permitting and obtaining no-cost private Rights of Way were included in this category. Network design rerouted in connection with Environmental Assessment and completion of Historical and Cultural Preservation Review due to number of archaeological prehistoric and historic sites in Hardy County. | 0 | (100%) Variance. Site preparation may not proceed until completion of Phase 1 archaeological survey and approval by WV Historic Preservice Office and National Telecommunications & Information Administration. | 28 | (72%) Variance. Baseline forecast included Equipment Deployment expenditures in Equipment Procurement budget. Deployment expenditures have been included in this category for consistency. Delivery dates were deferred until two facilities sites could be connected over fiber. Equipment will be installed in five central office sites in Q4 2011. | 100 | 6% Variance. Delays in obtaining historic preservation approvals for buried construction required aerial construction to commence in advance of buried construction, leading to inefficiencies from deploying the network in portions rather than continuously. Backtracking to buried portions increases resource requirements. Cost of fiber increased by approximately 6.75% due to high demand and limited supply. | 0 | N/A. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | N/A. Same as above. | 2011-11-22 16:57 | 2011-11-22 16:57 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2011 | Q4 | Q4 - 2011 | 5272 | 4940 | FALSE | 77 | (23)% Variance. Delays in Intercreditor Agreement, Environmental Assessment review, and completion of Historic and Cultural Preservation Review prevented draw down of funds until April, 2011. Archaeological shovel testing and Phase 1 Survey report delayed construction until September, 2011. | 100 | Inspection | 66% Variance. Inspection in Network Build but broken out for clarity. Delays in construction expected due to requirement for shovel testing and section 106 review of replacement poles and ground anchors. | 100 | 779% Variance. Cost of environmental assessment and archaeological services ran significantly over budget due to the high number of prehistoric and historic sites in Hardy County, WV and requirement for a Phase 1 archaeological survey and shovel testing. | 100 | 44% Variance. Resources reallocated to completion of environmental/archaeological assessments. Segments of network rerouted and redesigned from buried cable to aerial placement, to avoid identified historic and cultural sites. Route modifications due to R/W acquisition issues. Laterals to anchor institutions will require a Phase 1 survey and shovel testing for buried sections, new poles or replacements, ground anchors and pedestals. | 12 | (88)% variance. The baseline forecast included purchases of land, structures and appraisals, and purchases of land or easements for Rights of Way in this category. Costs associated with obtaining no-cost private Rights of Way were included in Permitting & Other Approvals. | 100 | 141% variance. The baseline forecast included costs of land, structures, appraisals and purchases of land or easements for Rights of Way in the Rights of Way budget category. Costs associated with construction permitting and obtaining no-cost private Rights of Way were included in this category. Network rerouted in some locations due to number of archaeological prehistoric and historic sites in Hardy County. Route modifications required for locations where a private easement could not be obtained. | 0 | (100%) Site prep covered by recipient. | 26 | (74)% variance. Savings obtained through competitive vendor procurements, and purchase of operating equipment from non-award funds. | 70 | (30)% variance. Construction delayed due to delays in intercreditor agreement and archaeological surveys and shovel testing. | 0 | N/A. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | NA. Same as above. | 2012-02-27 01:51 | 2012-02-27 01:51 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2012 | Q1 | Q1 - 2012 | 6242 | 5723 | FALSE | 100 | 0% Variance | 100 | Inspection | 143% Variance. Utilization of multiple contractors and crews to overcome environmental and historic preservation delays to construction commencement. Delays prevented construction prior to third quarter of 2011. | 100 | 949% Variance. 911% Variance. Historic preservation studies and surveys significantly delayed buried construction and materially increased project costs. | 100 | 64% Variance. Network reroutes or changes in deployment methods to avoid potential effects on historic sites; Network redesigned to leverage Hardy AnchorRing Middle Mile backbone network to provide fiber facilities for the Hardy OneNet Last Mile Fiber-to-the-Home ("FTTH") network funded by the Rural Utilities Service ("RUS") of the U.S. Dept. of Agriculture under the Broadband Initiatives Program ("BIP"). | 12 | (88)% Variance. The baseline included costs of land, structures, and appraisals in this category. Private rights of way acquisition costs were included in the Construction Permits and Other Approvals Category. The number of facilities required to transmit services decreased due to the use of long-range optics and availability of fiber-to-the-home in the BIP-funded Hardy OneNet network. | 100 | 157% Variance. Sections of line were rerouted and/or redesigned as aerial placement to avoid potential effects to historic and cultural sites along the route. Private rights of way acquisition costs are included in this category. | 0 | (100)% Variance. Site preparation costs covered by Recipient. | 41 | (59)% Variance. Baseline category included Equipment Deployment. Deployment expenditures have been included for consistency. Equipment deployed in 20 central offices and remote sites. Vendor negotiations produced significant savings on electronics. Use of long-range optics and availability of fiber-to-the-home in the BIP funded Hardy OneNet network reduced the requirement for electronics at all sites. | 94 | (6)% Variance. Variance is due to negotiated savings in construction costs. | 0 | N/A. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | N/A. Same as above | 2012-05-21 22:14 | 2012-05-21 22:14 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2012 | Q2 | Q2 - 2012 | 7088 | 6171 | FALSE | 100 | 0% Variance | 100 |  | 232% Variance. Utilization of multiple contractors and crews to overcome environmental and historic preservation delays to construction commencement. Delays prevented construction prior to third quarter of 2011. | 100 | 856% Variance. Historic preservation studies and surveys significantly delayed buried construction and materially increased project costs. | 100 | 53% Variance. Network reroutes or changes in deployment methods to avoid potential effects on historic sites; Network redesigned to leverage Hardy AnchorRing Middle Mile backbone network to provide fiber facilities for the Hardy OneNet Last Mile Fiber-to-the-Home ("FTTH") network funded by the Rural Utilities Service ("RUS") of the U.S. Dept. of Agriculture under the Broadband Initiatives Program ("BIP"). | 12 | (88)% Variance. The baseline included costs of land, structures, and appraisals in this category. Private rights of way acquisition costs were included in the Construction Permits and Other Approvals Category. The number of facilities required to transmit services decreased due to the use of long-range optics and availability of fiber-to-the-home in the BIP-funded Hardy OneNet network. | 100 | 157% Variance. Sections of line were rerouted and/or redesigned as aerial placement to avoid potential effects to historic and cultural sites along the route. Private rights of way acquisition costs are included in this category. | 0 | (100)% Variance. Site preparation costs covered by Recipient. | 34 | (66)% Variance. Baseline category included Equipment Deployment. Deployment expenditures have been included for consistency. Equipment deployed in 20 central offices and remote sites. Vendor negotiations produced significant savings on electronics. Use of long-range optics and availability of fiber-to-the-home in the BIP funded Hardy OneNet network reduced the requirement for electronics at all sites. | 98 | (2)% Variance. Variance is due to negotiated savings in equipment costs. Use of long-range optics and availability of fiber-to-the-home in the BIP funded Hardy OneNet network reduced requirements for electronics at all sites and facilities construction and upfits. | 0 | N/A. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | Baseline = 0. Testing included in Architectural and Engineering Services. | 2012-08-15 15:46 | 2012-08-15 15:46 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2012 | Q3 | Q3 - 2012 | 7876 | 6642 | FALSE | 100 | No Variance. | 100 | Inspection | 232% Variance as previously noted. No change from Q3-2012 | 100 | 875% Variance as previously noted. No change from Q3-2012. | 100 | 78% Variance as previously noted. No change from Q3-2012. | 12 | (88)% Variance as previously noted. No change from Q3-2012. | 100 | 157% Variance as previously noted. No change from Q3-2012. | 0 | (100)% Variance as previously noted. No change from Q3-2012 | 34 | (66)% Variance as previously noted. No change from Q3-2012 | 100 | 2% Variance. | 0 | Baseline = 0 | 0 | Baseline = 0 | 2012-11-14 14:47 | 2012-11-14 14:47 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | 2012 | Q4 | Q4 - 2012 | 8792 | 7590 | FALSE | 100 | Award completed in 2012 | 100 |  | Awarded completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 2013-02-14 21:31 | 2013-02-14 21:31 | 5526 | 5526 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570036 | 2010 | Q2 | Q2 - 2010 | 59 | 1302 | FALSE | 35 |  | 0 |  |  | 100 |  | 50 |  | 0 |  | 25 |  | 0 |  | 25 |  | 15 |  | 15 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2010 | Q3 | Q3 - 2010 | 398 | 1465 | FALSE | 70 | N/A | 0 |  | N/A | 100 | Complete | 50 | On track | 0 | N/A constructions will be on our own property. | 100 | Complete | 100 | N/A | 75 | Delayed from 3Q | 75 | N/A | 75 | N/A | 50 | N/A | 2010-11-23 17:18 | 2010-11-23 17:18 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2010 | Q4 | Q4 - 2010 | 1156 | 2196 | FALSE | 60 | Variance from baseline due to delay in construction procurement process. | 0 |  | N/A | 100 | Complete | 100 | On Track | 0 | N/A - All construction will be on our own property. | 100 | Complete | 50 | Variance from baseline due to delay in construction procurement process. | 80 | Variance from baseline due to delay in construction procurement process. | 40 | Variance from baseline due to delay in construction procurement process. | 60 | Variance from baseline due to delay in construction procurement process. | 35 | Variance from baseline due to delay in construction procurement process. | 2011-02-15 17:44 | 2011-02-15 17:44 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2011 | Q1 | Q1 - 2011 | 2310 | 2900 | FALSE | 35 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 40 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 37 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 40 | Variance from baseline due to delay in construction procurement process. | 40 | Variance from baseline due to delay in construction procurement process. | 30 | Variance from baseline due to delay in construction procurement process. | 2011-05-25 16:37 | 2011-05-25 16:37 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2011 | Q2 | Q2 - 2011 | 3378 | 3452 | FALSE | 35 | Next quarter we plan to complete all construction, equipment procurement and deployment. The percent complete is based on projected invoiced expenses in 3Q. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 40 | Outside plant construction should be completed. Delays are due to longer construction procurement process than expected. The percent complete is based on projected invoiced expenses in 3Q. | 37 | Most equipment will be purchased by the end of next quarter. The percent complete is based on projected invoiced expenses in 3Q. | 100 | Expected to be completed as there are 4 interconnection points where equipment needs to be installed. | 100 | Expected to be completed as there are 4 interconnection points where equipment needs to be installed. | 95 | Network testing should be completed by early 4Q as there are 4 interconnection points where equipment needs to be tested. | 2011-08-30 13:36 | 2011-08-30 13:36 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2011 | Q3 | Q3 - 2011 | 4334 | 4023 | FALSE | 42 | Next quarter we plan to complete our network build and equipment testing. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 45 | Construction will be completed | 43 | We should have the majority equipment purchased. | 100 | Complete | 100 | Complete | 100 | Complete | 2011-11-30 14:38 | 2011-11-30 14:38 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2011 | Q4 | Q4 - 2011 | 5298 | 4968 | FALSE | 43 | Finalizing construction project and begin working on the project close out. Percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 59 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:43 | 2012-02-27 15:43 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2012 | Q1 | Q1 - 2012 | 6054 | 5626 | FALSE | 43 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 61 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-14 11:59 | 2012-05-14 11:59 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2012 | Q2 | Q2 - 2012 | 6514 | 5871 | FALSE | 43 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 61 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-07-27 12:06 | 2012-07-27 12:06 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2012 | Q3 | Q3 - 2012 | 7692 | 6530 | FALSE | 43 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 61 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 22:57 | 2012-10-30 22:57 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2012 | Q4 | Q4 - 2012 | 8528 | 7254 | FALSE | 45 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 61 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 16:20 | 2013-01-30 16:20 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | 2013 | Q1 | Q1 - 2013 | 11980 | 10138 | FALSE | 100 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2014-03-21 16:00 | 2014-03-21 16:00 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570037 | 2010 | Q2 | Q2 - 2010 | 60 | 1300 | FALSE | 30 |  | 0 |  |  | 100 |  | 45 |  | 50 |  | 50 |  | 10 |  | 20 |  | 5 |  | 5 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Columbia, County of | TRUE
NT10BIX5570037 | 2010 | Q3 | Q3 - 2010 | 146 | 1339 | FALSE | 20 | Construction delayed due to Environmental Assessment taking longer than anticipated | 0 |  | N/A | 100 | Should be completed | 50 | Network Design is based on electronics selected. | 75 | On-schedule | 75 | On-schedule | 50 | On-schedule | 35 | On-schedule | 5 | Environmental Assessment taking longer than anticipated | 15 | Environmental Assessment taking longer than anticipated | 5 | Environmental Assessment taking longer than anticipated | 2010-10-12 10:07 | 2010-10-12 10:07 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2010 | Q4 | Q4 - 2010 | 500 | 1524 | FALSE | 35 | Environmental Assessment and permit process taking longer than anticipated | 0 |  | N/A | 100 | Completed | 75 | On-schedule | 75 | Working with City of Harlem and Grovetown on rights of way issues. | 65 | Permit process taking longer than anticipated | 30 | Site plans are prepared for each construction phase. | 25 | Dependant upon network design to be completed. | 10 | Environmental Assessment and permit process taking longer than anticipated | 0 | Dependant upon network design to be completed and purchase of equipment. | 0 | Dependant upon network design to be completed and purchase of equipment. | 2011-01-21 07:42 | 2011-01-21 07:42 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2011 | Q1 | Q1 - 2011 | 2068 | 2779 | FALSE | 40 | Environmental Assessment and permit process taking longer than anticipated | 0 |  | N/A | 100 | Completed | 75 | Environmental Assessment and permit process taking longer than anticipated | 100 | Working with City of Harlem and Grovetown on rights of way issues. | 100 | On Target | 100 | On Target | 35 | Dependant upon network design to be completed | 20 | Environmental Assessment and permit process taking longer than anticipated | 0 | Dependant upon network design to be completed. | 0 | Dependant upon network design to be completed. | 2011-05-17 06:22 | 2011-05-17 06:22 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2011 | Q2 | Q2 - 2011 | 2918 | 3216 | FALSE | 50 | Environmental, permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 95 | Dependant upon Electronics selected for network | 100 | Our County Attorney is drafting Permanent Easements with the property owners inside the city limits. Once the easements have been completed, our ROW acquisition staff will meet with each property owner to execute the easement. We have identified approximately 25 easements needed in side the cities. | 100 | Working with cities and CSX Transportation on permits and approvals. Our County Attorney is currently reviewing Facility Encroachment Agreements with CSX. We should have all DOT permits and CSX Encroachment Agreements approved by September 30, 2011. We are currently installing broadband infrastructure where we have permits and approvals and these delays should not impact our overall schedule. | 100 | Working with cities and CSX Transportation on permits and approvals to start construction inside the city limits and railroad crossing construction. We are currently installing broadband infrastructure where we have permits and approvals and these delays should not impact our overall schedule. | 53 | Issuing electronics RFP by September 1, 2011. Most of expenses are from Columbia County Board of Education in-kind equipment purchased. | 45 | Environmental, permits, ROW issues, and fiber shipment delays have impacted project schedule. | 2 | Issuing electronics RFP by September 1, 2011. | 0 | Dependant upon electronics purchase | 2011-08-02 07:19 | 2011-08-02 07:19 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2011 | Q3 | Q3 - 2011 | 3930 | 3803 | FALSE | 69 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 95 | dependant upon electronics selected for network. | 98 | Actively acquiring permanent easements from home owners inside the cities. | 100 | We should have all permits for Phase VI construction and one final interstate DOT permit by end of quarter. | 98 | We should have all permits for Phase VI construction and one final interstate DOT permit by end of quarter. We are currently installing broadband infrastructure where we have permits and approvals and these delays should not impact our overall schedule. | 40 | Currently the County is seeking network electronics proposals to provide various broadband middle mile services. Once the proposals are submitted, County staff will evaluate the submitted proposals. County staff should recommend a firm for approval by February 2012. | 65 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 2 | Dependant upon electronics selected and purchased. | 0 | Dependant upon electronics selected and purchased. | 2011-11-09 06:40 | 2011-11-09 06:40 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2011 | Q4 | Q4 - 2011 | 5342 | 5013 | FALSE | 87 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 100 | Fiber splicing plan to be finalized by February 10, 2012 | 100 | Actively working with County Attorney, City of Harlem and Grovetown and Right of Way Acquisition Department to obtain the final 9 easements needed for the routes inside city limits. | 100 | Submitted the final DOT permit for interstate crossing and waiting approval from Georgia State DOT. | 100 | We have all DOT permits except one final interstate permit. We are currently installing infrastructure where we have permits and approvals. These delays should not impact overall project. | 10 | County staff currently reviewing submitted electronic proposals. | 95 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule | 5 | Dependant upon electronics selected and purchased | 0 | Dependant upon construction, electronics selected and purchased | 2012-02-28 13:00 | 2012-02-28 13:00 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2012 | Q1 | Q1 - 2012 | 5924 | 5561 | FALSE | 90 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 99 | Fiber splicing plan completed and minor changes may take place after electronics have been selected. | 100 | Completed | 100 | Completed | 100 | Completed | 25 | Equipment will be selected and on order. | 95 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 5 | Dependent upon electronics selected and purchased. | 5 | Dependent upon electronics selected and purchased. | 2012-05-04 07:46 | 2012-05-04 07:46 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2012 | Q2 | Q2 - 2012 | 7126 | 6190 | FALSE | 95 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule | 0 |  | N/A | 100 | Completed | 99 | Minor changes may take place after electronics are being installed. | 100 | Completed | 100 | Completed | 100 | Completed | 95 | Wireless Access Points to be purchased. | 98 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 50 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 100 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 2012-08-17 16:40 | 2012-08-17 16:40 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2012 | Q3 | Q3 - 2012 | 7846 | 6627 | FALSE | 100 | Completed | 0 |  | N/A | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2012-11-13 13:53 | 2012-11-13 13:53 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2012 | Q4 | Q4 - 2012 | 9130 | 7910 | FALSE | 100 | Completed | 0 |  | N/A | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2013-03-06 15:32 | 2013-03-06 15:32 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570037 | 2013 | Q1 | Q1 - 2013 | 9178 | 8010 | FALSE | 100 | Completed | 0 |  | N/A | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2013-04-15 08:08 | 2013-04-15 08:08 | 5532 | 5532 | Columbia, County of | TRUE
NT10BIX5570038 | 2010 | Q2 | Q2 - 2010 | 61 | 1306 | FALSE | 30 |  | 0 |  |  | 100 |  | 45 |  | 0 |  | 75 |  | 20 |  | 15 |  | 10 |  | 10 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2010 | Q3 | Q3 - 2010 | 396 | 1464 | FALSE | 60 | Ahead | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 70 | On track | 60 | On track | 50 | On track | 50 | On track | 40 | On track | 2010-11-23 17:12 | 2010-11-23 17:12 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2010 | Q4 | Q4 - 2010 | 1102 | 2143 | FALSE | 60 | Variance from baseline due to delay in construction procurement process. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 75 | Variance from baseline due to delay in construction procurement process. | 85 | Ahead | 75 | On track | 65 | Variance from baseline due to delay in construction procurement process. | 50 | Variance from baseline due to delay in construction procurement process. | 2011-02-11 17:24 | 2011-02-11 17:24 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2011 | Q1 | Q1 - 2011 | 1822 | 2654 | FALSE | 27 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 41 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 26 | Variance from baseline due to delay in construction procurement process. Plan to purchase our support and management systems for monitoring. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 40 | Variance from baseline due to delay in construction procurement process. | 35 | Variance from baseline due to delay in construction procurement process. | 25 | Variance from baseline due to delay in construction procurement process. | 2011-05-02 09:40 | 2011-05-02 09:40 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2011 | Q2 | Q2 - 2011 | 3380 | 3453 | FALSE | 28 | The majority of the project will be complete by the end of 3Q. The percent complete is based on projected invoiced expenses in 3Q. Delays are due to longer construction procurement process than expected. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 13 | Majority of work will be completed by end of 3Q. The percent complete is based on projected invoiced expenses in 3Q. Delays are due to longer construction procurement process than expected. | 32 | Most equipment should be purchased by next quarter. The percent complete is based on projected invoiced expenses in 3Q. Delays are due to longer construction procurement process than expected. | 100 | Complete | 100 | Complete | 90 | Network testing should be completed by early 4Q. | 2011-08-30 13:37 | 2011-08-30 13:37 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2011 | Q3 | Q3 - 2011 | 4336 | 4024 | FALSE | 37 | The majority of the project will be complete by the end of 3Q, but the percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 37 | The site preparation will be complete, but the percent complete is strictly based on the budget. | 37 | The equipment procurement will be complete, but the percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2011-11-30 14:40 | 2011-11-30 14:40 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2011 | Q4 | Q4 - 2011 | 5300 | 4970 | FALSE | 39 | Finalizing construction project and begin working on the project close out. Percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 54 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 37 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:46 | 2012-02-27 15:46 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2012 | Q1 | Q1 - 2012 | 6056 | 5627 | FALSE | 39 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 53 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 37 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-14 12:00 | 2012-05-14 12:00 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2012 | Q2 | Q2 - 2012 | 6516 | 5872 | FALSE | 39 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 53 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 37 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-07-27 12:11 | 2012-07-27 12:11 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2012 | Q3 | Q3 - 2012 | 7694 | 6531 | FALSE | 39 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 54 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 37 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 22:59 | 2012-10-30 22:59 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2012 | Q4 | Q4 - 2012 | 8532 | 7257 | FALSE | 40 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 54 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 37 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 16:23 | 2013-01-30 16:23 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | 2013 | Q1 | Q1 - 2013 | 12030 | 10194 | FALSE | 100 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | omplete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2014-04-14 12:10 | 2014-04-14 12:10 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570039 | 2010 | Q2 | Q2 - 2010 | 62 | 1281 | FALSE | 9 |  | 70 |  |  | 100 |  | 100 |  | 45 |  | 30 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2010 | Q3 | Q3 - 2010 | 330 | 1431 | FALSE | 10 | Requirement to issue new RFP has delayed | 75 | Contracts, Audit, Admin. | Requirement to issue new RFPs has delayed | 100 | N/A | 70 | Requirement to issue new RFPs has delayed | 25 | Requirement to issue new RFPs has delayed | 20 | Requirement to issue new RFPs has delayed | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-16 21:38 | 2010-11-16 21:38 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2010 | Q4 | Q4 - 2010 | 1184 | 2217 | FALSE | 15 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 90 |  | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 100 | N/A | 90 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 35 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 35 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 0 | N/A | 5 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 5 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 0 | N/A | 0 | N/A | 2011-02-16 14:54 | 2011-02-16 14:54 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2011 | Q1 | Q1 - 2011 | 2166 | 2828 | FALSE | 19 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. | 100 | contracts etc. | Due to requirement to issue new RFPs and select new contractors this item was delayed but will be complete in this quarter as contracts with contractors are concluded. | 100 | OpenCape has a continual process of review to ensure compliance with its EA FONSI. This process involves OpenCape, its field survey and engineering contractor, and its environmental engineering contractor. Potential deviations from the original EA are identified and will be consolidated into a future submission for amendment of the EA. OpenCape has also engaged the Army Corps of Engineers for the crossing of the Cape Cod Canal and will fulfill the specific EA requirement of their process as stated in the EA and FONSI. | 100 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. The preliminary design of the microwave, fiber optic, transport, and municipal RAN are near complete. Specific design should be completed this quarter. | 60 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. In addition, the slower than anticipated pace of securing Master Agreements from one utility and the slow pace of permitting with Army Corps of Engineers has slowed this category. It is anticipated that significant progress will be achieved in this quarter with regard to pole and conduit license applications, tower access license applications, and the crossing of the Cape Cod Canal. A decision is also anticipated on the best approach to crossing the Taunton River. | 60 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. Significant progress will be made in this category in Y2Q2. A Construction Manager will be selected to begin renovation of the Regional Collocation Center to code and ADA compliance. An RFP will be issued for the construction of the data center within the Collocation Center. Special Permit applications will be submitted to the Massachusetts DOE, DCR, and other agencies for crossings of roads and rail beds, etc. The FCC 700Mhz waiver will be submitted by Barnstable County. | 0 | N/A | 20 | OpenCapeâ€™s contractor has been engaged with vendors of fiber optics, optronics, and other equipment to determine qualified bidders and issue bid documents. Major equipment purchases are anticipated in Y2Q2 and Y2Q3 of fiber and optronics. | 5 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. In addition, the pace of completion of utility pole and conduit owner license application processing and make ready have slowed this category. OpenCape's contractor will engage and select sub-contractors for the installation of fiber optics and microwave systems in this quarter. | 0 | Equipment deployment is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, and construction completion. It is anticipated equipment deployment will follow at expected pace. | 0 | Network testing shall keep pace with the construction of segments of the network. | 2011-05-19 11:30 | 2011-05-19 11:30 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2011 | Q2 | Q2 - 2011 | 2934 | 3224 | FALSE | 25 | The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. OpenCape adjusted to that disruption and established a new normal for its baseline following completion of its contract with CapeNet LLC to design and build the network. Since that time there has been substantial program progress. OpenCape expects to complete the project on time by taking advantage of built in flexibility within its original plan and creating flexibility by compressing certain aspects of the project such as the installation of fiber within a more aggressive timeline. | 100 |  | Complete | 100 | OpenCape has a continual process of review to ensure compliance with its EA FONSI. This process involves OpenCape, its field survey and engineering contractor, and its environmental engineering contractor. Potential deviations from the original EA are identified and will be consolidated into a future submission for amendment of the EA. OpenCape has also engaged the Army Corps of Engineers for the crossing of the Cape Cod Canal and will fulfill the specific EA requirement of their process as stated in the EA and FONSI. | 85 | The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. Apart from the general delay described in Section 3, Network Design specifically has also been delayed by discoveries during site visits and detailed engineering. For example, OpenCape intends to use an existing fire tower on Martha's Vineyard for a microwave link from Cape Cod to the Island. Preliminary analysis indicates this tower is currently overloaded. A detailed engineering evaluation is scheduled to determine if the tower can be altered to accommodate OpenCape equipment while simultaneously evaluating alternative towers. The design of the microwave, fiber optic, transport, and municipal RAN are near complete and expected to be completed well within required parameters to order equipment and perform installation. | 60 | The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. Apart from the general delay described in Section 3, Rights of Way specifically has also been delayed by a far more lengthy process for obtaining rights than was anticipated. OpenCape is fully engaged in the process of submitting special permits, developing the contractual basis of leases to towers to support the microwave component, and applying for access to Verizon Central Offices. The Army Corps of Engineers permitting of critical crossings at the Cape Cod Canal and the Taunton River is very slow and represents a critical element of delay in this category. Obtaining access to towers for the placement of microwave equipment is also a time consuming process because the tower owners must go through a process required by Chapter 30B of the Massachusetts General Laws; however, this process is moving forward at an acceptable pace at this time to | 55 | The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. Apart from the general delay described in Section 3, Construction permits is also delayed by the unexpected slow pace of make ready assessment by utility pole owners with regard to the fiber optic component of the project. OpenCape is focusing on completing make ready work in the NGrid territory where it has more control and confidence in obtaining licenses time coincident with the delivery of fiber. OpenCape is monitoring very closely the performance of NSTAR in performing make ready assessment and requesting improved performance when the pace falls short of requirements. The company has responded to these requests and we will continue to work together to ensure that the pace reaches a level that is acceptable to OpenCape and supportive of its goals. The collocation center portion is progressing appropriately as OpenCape has contracted with Stat | 0 | N/A | 20 | At baseline. OpenCapeâ€™s contractor has engaged vendors of fiber optics, optronics,and other equipment to determine qualified bidders and issue bid documents. The first order of 35 miles of fiber has been placed with an anticipated delivery in September, 2011. The delivery date was 8 weeks after order placement. This is consistent with the timeline of anticipated completed make ready and sub-contractor selection for installation of the fiber beginning in October 2011. | 5 | The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. The Network Build is significantly delayed, but readily recoverable by compressing the installation of fiber within a more aggressive time line. There is a significant dependency in this category on the make ready assessment and make ready work being completed. OpenCape is focusing its initial network build area on the NGrid territory where it has more control and confidence in obtaining licenses time coincident with the delivery of fiber. This will permit the contractor to begin work as early as possible in 20% of the territory with the anticipation that when that work is complete there will be NSTAR licenses forthcoming for work in that territory. | 0 | The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. Equipment deployment is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, and construction completion. It is anticipated equipment deployment will follow at an appropriate pace. OpenCape expects to have equipment available, rights secured, and construction complete in adequate time for network equipment deployment. | 0 | At baseline. The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. Network Testing is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, construction completion, and equipment deployment. It is anticipated that Network Testing will follow at an appropriate pace. OpenCape expects to have equipment available, rights secured, construction complete, and equipment deployed in adequate time for Network Testing to be completed on time. | 2011-08-05 14:21 | 2011-08-05 14:21 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2011 | Q3 | Q3 - 2011 | 3932 | 3804 | FALSE | 31 | OpenCape remains behind its original baseline for reasons described in Sections 2a and 3 above. OpenCape continues to adjust to challenges with innovative solutions and aggressive action. OpenCape expects to complete the project on time by taking advantage of built in flexibility within its original plan and creating flexibility by compressing certain aspects of the project such as the installation of fiber within a more aggressive timeline. OpenCape anticipates expending up to 45% of its funds by January 31, 2012, but anticipates the true project status to be substantially complete at that time based on an assessment of tasks and milestones that will be complete or near complete. | 100 |  | Complete | 100 | OpenCape has a continual process of review to ensure compliance with its EA FONSI. Though the EA Assessment and FONSI are complete,an amendment was necessary to record changes from the original submission. Approval of the EA Amendment is anticipated in the fourth quarter. | 95 | Early delays caused by the transition to a new contractor have been overcome and the design of the microwave, fiber optic, transport, and municipal RAN are near complete. | 65 | Early delays caused by the transition to a new contractor have been overcome and OpenCape has submitted necessary applications to obtain access to two crossings of the Cape Cod Canal. Obtaining access to towers for the placement of microwave equipment is underway but the process is slow as the owners of the towers are public entities that must comply with Commonwealth of Massachusetts procurement laws. | 60 | Early delays caused by the transition to a new contractor have been overcome and OpenCape is fully engaged in the process of submitting applications for and receiving permits locally, with state agencies, railroad owners, and others. Permit applications have been submitted for the renovation of the former Barnstable County Public Safety building with the necessary entities. | 0 | N/A | 30 | OpenCape is on a path for procurement consistent with on time completion of the project. The first fiber delivery of nine reels arrived in September, 2011 and deliveries of 35 miles each month are anticipated. Ciena was selected as the provider of routing and switching equipment and orders will be placed early in the fourth quarter. The completion of the microwave path assessment and start of frequency studies will result in the potential order of radio equipment in the fourth quarter. | 7 | Network Build is greatly dependent on make ready completion. It is therefore delayed. However, sub-contractors for fiber construction have been selected and materials are in hand to begin construction. Make ready has begun in the National Grid territory of the project. Underground work is primed to begin, but awaits a positive Environmental Assessment Amendment review. Microwave construction is dependent on obtaining lease rights from municipal authorities under a complex and slow procurement process required by Commonwealth of Massachusetts Chapter 30B. | 0 | Equipment deployment is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, and construction completion. It is anticipated equipment deployment will follow at an acceptable pace as the vendor has been selected for switching and routing and configuration of DWDM can be achieved in parallel with construction of the fiber. | 5 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber. | 2011-11-09 10:16 | 2011-11-09 10:16 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2011 | Q4 | Q4 - 2011 | 5212 | 4881 | FALSE | 47 | OpenCape remains behind its original baseline for reasons described in Sections 2a and 3 above. However, OpenCape has adjusted and is on target for on time completion based on its revised construction schedule. OpenCape expects to complete the project on time by taking advantage of built in flexibility within its original plan and creating flexibility by compressing certain aspects of the project such as the installation of fiber within a more aggressive timeline. OpenCape anticipates expending in total over 45% of its funds by the end of this quarter, but anticipates the true project to be much higher based on an assessment of tasks and milestones that will be complete or near complete. | 92 |  | Additional contract work was required that has necessitated continued work through the fourth quarter. | 100 | Complete | 95 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps are near complete. | 75 | OpenCape expects to secure underlying rights to the Cape Cod Canal and Taunton RIver crossings this quarter. Obtaining these rights has taken longer than anticipated. OpenCape anticipates obtaining licenses to necessary towers in this quarter and furthering the lease process in parallel. Obtaining access to municipal towers has proven much more difficult and time consuming than anticipated, largely due to Commonwealth of Massachusetts procurement laws. Pole licenses from pole owners are expected to begin flowing in this quarter and maintain a pace consistent with the construction plan. | 85 | Early delays have been overcome and OpenCape is fully engaged in the process of submitting applications for and receiving permits locally, with state agencies, railroad owners, and others. Permit applications have been submitted for the renovation of the former Barnstable County Public Safety building with the necessary entities. | 0 | N/A | 77 | OpenCape is on a path for procurement consistent with on time completion of the project. The first fiber delivery of nine reels arrived in September, 2011 and a total of over 200 miles will be on hand by the end of the first quarter with continued delivery of 35 miles each month until all fiber is in hand by June, 2012. Switching, routing, DWDM, and microwave radio equipment will all be delivered early in the first quarter. | 31 | Network Build is greatly dependent on make ready completion. It is therefore delayed when compared with baseline. Make ready work in National Grid territory will be completed early in this quarter to provide over 40 miles of buildable segments. NSTAR make ready reassessment will be completed early in the quarter, licenses for segments without make ready requirements will be provided early in the quarter. Make ready on the remainder will begin and production will be adequate to support the construction plan. | 25 | All equipment will be on hand in this quarter. As underlying rights to facilities are obtained the equipment will be deployed. It is anticipated that equipment deployment will maintain a pace supportive of fiber build. | 10 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber. | 2012-02-23 14:34 | 2012-02-23 14:34 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2012 | Q1 | Q1 - 2012 | 5530 | 5359 | FALSE | 62 | OpenCape remains behind its original baseline for reasons described in Sections 2a and 3 above. However, OpenCape has adjusted and is on target for on time completion based on its revised construction schedule. OpenCape expects to complete the project on time by taking advantage of built in flexibility within its original plan and creating flexibility by compressing certain aspects of the project such as the installation of fiber within a more aggressive timeline. OpenCape anticipates expending in total over 62% of its funds by the end of this quarter, but anticipates the true project progress to be much higher based on an assessment of tasks and milestones that will be complete or near complete. | 95 |  | Additional contract work was required that has necessitated continued work through the fourth quarter. | 100 | Complete | 99 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps will be nearly completed. | 90 | OpenCape expects to secure underlying rights to the Cape Cod Canal and Taunton RIver crossings this quarter. Obtaining these rights has taken longer than anticipated. OpenCape anticipates obtaining licenses to necessary towers in this quarter. Obtaining access to municipal towers has proven much more difficult and time consuming than anticipated, largely due to Commonwealth of Massachusetts procurement laws. Pole licenses from pole owners are flowing in this quarter and expected to maintain a pace consistent with the construction plan. | 95 | Early delays have been overcome and OpenCape is fully engaged in the process of submitting applications for and receiving permits locally, with state agencies, railroad owners, and others. | 0 | N/A | 97 | OpenCape is on a path for procurement consistent with on time completion of the project. Nearly all fiber is expected to have been delivered by the end of Q2 2012. Switching, routing, DWDM, and microwave radio equipment is on hand to for installation upon receipt of leases for regeneration sites and towers. | 60 | Network Build is greatly dependent on make ready completion. It is therefore delayed when compared with baseline, but fast approaching a pace consistent with the projected construction timeline. A complete make ready reassessment in the NSTAR territory was required, but has been completed, all make ready work orders generated, and all invoices paid for make ready to begin. OpenCape holds weekly conference calls with pole owners to expedite and coordinate on make ready. | 65 | Equipment is on hand to support construction and deployment timelines. As underlying rights to facilities are obtained the equipment will be deployed. It is anticipated that equipment deployment will maintain a pace supportive of fiber build, and as rights to regeneration sites and towers are obtained. | 20 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber. | 2012-04-26 10:27 | 2012-04-26 10:27 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2012 | Q2 | Q2 - 2012 | 6904 | 6078 | FALSE | 77 | OpenCape remains behind its original baseline for reasons described in Sections 2a and 3 above. However, OpenCape has adjusted and is on target for on time completion based on its revised construction schedule. OpenCape expects to complete the project on time by taking advantage of built in flexibility within its original plan and creating flexibility by compressing certain aspects of the project such as the installation of fiber within a more aggressive timeline. OpenCape anticipates expending in total over 77% of its funds by the end of this quarter, but anticipates the true project progress to be much higher based on an assessment of tasks and milestones that will be complete or near complete. | 99 |  | Additional contract work was required that has necessitated continued work through the fourth quarter. | 100 | Complete | 98 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps will be nearly completed. | 99 | OpenCape expects to secure remaining underlying rights to the Taunton River crossing this quarter. Obtaining these rights has taken longer than anticipated. OpenCape anticipates obtaining licenses to all remaining necessary towers in this quarter. Obtaining access to municipal towers has proven much more difficult and time consuming than anticipated, largely due to Commonwealth of Massachusetts procurement laws. Pole licenses from pole owners are flowing in this quarter and expected to maintain a pace consistent with the construction plan. | 99 | Nearly all permits are in hand with the exception of permits associated with installation of antennas on towers. These final remaining permits are anticipated in Q3. | 0 | N/A | 99 | Nearly all equipment will be received by the end of Q3. | 70 | Network Build is greatly dependent on make ready completion. It is therefore delayed when compared with baseline or PIP. A complete make ready reassessment in the NSTAR territory was required, but has been completed, all make ready work orders generated, and all invoices paid for make ready to begin. OpenCape holds weekly conference calls with pole owners to expedite and coordinate on make ready. See section 3. | 55 | Equipment is on hand to support construction and deployment timelines. As underlying rights to facilities are obtained the equipment will be deployed. It is anticipated that equipment deployment will maintain a pace supportive of fiber build, and as rights to regeneration sites and towers are obtained. | 45 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber. | 2012-08-07 15:40 | 2012-08-07 15:40 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2012 | Q3 | Q3 - 2012 | 8166 | 6793 | FALSE | 84 | OpenCape remains behind its original baseline for reasons described in Sections 2a and 3 above. However, OpenCape has adjusted and is on target for on time completion based on its revised construction schedule. OpenCape expects to complete the project on time by taking advantage of built in flexibility within its original plan and creating flexibility by compressing certain aspects of the project such as the installation of fiber within a more aggressive timeline. OpenCape anticipates expending in total over 90% of its funds by the end of this quarter, but anticipates the true project progress to be much higher based on an assessment of tasks and milestones that will be complete or near complete. | 99 |  | Additional contract work was required that has necessitated continued work through the fourth quarter. | 100 | Complete | 99 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps will be nearly completed. | 99 | OpenCape expects to secure remaining underlying rights to the Taunton River crossing this quarter. Obtaining these rights has taken longer than anticipated. OpenCape anticipates obtaining licenses to all remaining necessary towers in this quarter. Obtaining access to municipal towers has proven much more difficult and time consuming than anticipated, largely due to Commonwealth of Massachusetts procurement laws. | 99 | Nearly all permits are in hand with the exception of permits associated with installation of antennas on towers. These final remaining permits are anticipated in Q4. | 9 | N/A | 99 | Nearly all equipment has been received. | 90 | Network Build is greatly dependent on make ready completion and obtaining licenses and permits for microwave construction. It is therefore delayed when compared with baseline or PIP. OpenCape holds weekly conference calls with pole owners to expedite and coordinate on make ready. See section 3. | 75 | Equipment is on hand to support construction and deployment timelines. As underlying rights to facilities are obtained the equipment will be deployed. It is antici | 55 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber.pated that equipment deployment will maintain a pace supportive of fiber build, and as rights to regeneration sites and towers are obtained. | 2012-11-30 08:57 | 2012-11-30 08:57 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2012 | Q4 | Q4 - 2012 | 9014 | 7789 | FALSE | 90 | OpenCape remains behind its original baseline for reasons described in Sections 2a and 3 above. For these reasons, OpenCape has requested a no cost extension to allow project completion. Utility company make ready will continue to be the pacing item. | 99 | Misc contract work | Additional contract work requirements will continue to be adjudicated as required to support the project. | 100 | Complete. | 100 | Additional design details for the municipal regional area network will be completed, as well as completion of as-build drawing at the completion of construction. | 100 | All final permits and licenses for both the fiber and microwave networks will be completed. | 100 | All final permits and licenses for both the fiber and microwave networks will be completed. | 0 | N/A | 98 | Only equipment that may not have been received would be final frequency specific microwave equipment, or ancillary equipment for laser tuning on the fiber network uncovered during testing. | 90 | All fiber construction should be complete. Final data center work may be delayed pending utility company power upgrade discussed above. Final microwave sites may lag depending on local jurisdictional approvals. | 95 | All equipment associated with the fiber network should be deployed. Final microwave sites may lag depending on local jurisdictional approvals. | 60 | Network testing involves a 5-8 week process for final configuration and tuning of electronics, and long duration bit error rate testing. The testing will follow construction completion on a segmented basis to allow incremental acceptance of the network. | 2013-02-27 14:14 | 2013-02-27 14:14 | 5535 | 5535 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2013 | Q1 | Q1 - 2013 | 10054 | 8583 | FALSE | 98 | OpenCape will remain behind its original baseline for reasons described in Sections 2a and 3 above. The network will progress to near completion during this quarter, however. | 95 | Misc contract work | Additional contract work requirements will continue to be adjudicated as required to support the project. | 100 | Complete | 100 | Complete | 96 | All final permits and licenses for the microwave network will have been completed. Rights of way for the additional laterals effectively added new work to this category. | 100 | Construction permits for microwave sites will be in place. These have been delayed by having to work through unique requirements of the 15 individual jurisdictions where the sites are located. | 0 | N/A | 98 | Purchase of equipment for the additional laterals will be substantially completed. | 95 | The initial fiber build will be completed during this period, with the additional laterals representing an increase in work scope that will continue to be worked through this period. | 90 | The delay in microwave system permitting will delay final equipment deployments. | 80 | Network testing can only be accomplished following network completion. As such, it will lag the original schedule for the same reasons that the overall project lags. | 2013-06-05 07:44 | 2013-06-05 07:44 | 7679 | 7679 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2013 | Q2 | Q2 - 2013 | 10360 | 8805 | FALSE | 99 | All network will be operational. Closeout will be underway. | 100 | Misc contract work | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-07-30 15:23 | 2013-07-30 15:23 | 7679 | 7679 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2013 | Q3 | Q3 - 2013 | 11340 | 9470 | FALSE | 100 | Complete | 100 | Misc contract work | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-11-21 19:58 | 2013-11-21 19:58 | 7679 | 7679 | OpenCape Corporation | TRUE
NT10BIX5570039 | 2013 | Q4 | Q4 - 2013 | 12278 | 10448 | FALSE | 100 | Complete | 100 | Misc contract work | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-06-19 15:43 | 2014-06-19 15:43 | 7679 | 7679 | OpenCape Corporation | TRUE
NT10BIX5570040 | 2010 | Q2 | Q2 - 2010 | 63 | 1307 | FALSE | 30 |  | 0 |  |  | 100 |  | 80 |  | 0 |  | 90 |  | 75 |  | 20 |  | 15 |  | 15 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2010 | Q3 | Q3 - 2010 | 400 | 1466 | FALSE | 50 | N/A | 0 |  | N/A | 100 | Complete | 75 | On track | 0 | N/A construction will be on our own property. | 100 | Complete | 100 | N/A | 50 | N/A | 50 | N/A | 50 | N/A | 25 | N/A | 2010-11-23 17:25 | 2010-11-23 17:25 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2010 | Q4 | Q4 - 2010 | 1158 | 2197 | FALSE | 60 | Variance from baseline due to delay in construction procurement process. Plan to be on schedule by the end of Q2. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 60 | Variance from baseline due to delay in construction procurement process.Plan to be on schedule by the end of Q2. | 50 | Variance from baseline due to delay in construction procurement process. Plan to be on schedule by the end of Q2. | 50 | Variance from baseline due to delay in construction procurement process.Plan to be on schedule by the end of Q2. | 50 | Variance from baseline due to delay in construction procurement process. Plan to be on schedule by the end of Q2. | 30 | Variance from baseline due to delay in construction procurement process. Plan to be on schedule by the end of Q2. | 2011-02-15 17:55 | 2011-02-15 17:55 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2011 | Q1 | Q1 - 2011 | 2364 | 2927 | FALSE | 24 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 22 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 25 | Variance from baseline due to delay in construction procurement process. Plan to purchase our support and management systems for monitoring. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 30 | Variance from baseline due to delay in construction procurement process. | 30 | Variance from baseline due to delay in construction procurement process. | 20 | Variance from baseline due to delay in construction procurement process. | 2011-05-27 08:08 | 2011-05-27 08:08 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2011 | Q2 | Q2 - 2011 | 3364 | 3445 | FALSE | 38 | Next quarter we will complete the construction and fiber splicing. The planned percent is strictly based on our budget. | 0 |  | N/A | 100 | Complete. | 100 | Complete. | 0 | N/A - All construction will be on our own property. | 100 | Complete | 31 | Delays are due to longer construction procurement process than expected. The percentage complete is based on projected invoiced expenses in 3Q. | 35 | Delays are due to longer construction procurement process than expected. The percentage complete is based on projected invoiced expenses in 3Q. | 95 | Our network build will be the deployment of transport equipment (2i) at each of our interconnection sites. | 95 | Delays are due to longer construction procurement process than expected. | 90 | Delays are due to longer construction procurement process than expected. | 2011-08-29 23:57 | 2011-08-29 23:57 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2011 | Q3 | Q3 - 2011 | 4304 | 4002 | FALSE | 37 | The majority of the project will be complete by the end of 3Q, but the percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 35 | The site preparation will be complete, but the percent complete is strictly based on the budget. | 38 | The equipment procurement will be complete, but the percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2011-11-29 10:36 | 2011-11-29 10:36 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2011 | Q4 | Q4 - 2011 | 5302 | 4972 | FALSE | 37 | Finalizing construction project and begin working on the project close out. Percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:50 | 2012-02-27 15:50 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2012 | Q1 | Q1 - 2012 | 6058 | 5628 | FALSE | 37 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-14 12:01 | 2012-05-14 12:01 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2012 | Q2 | Q2 - 2012 | 7150 | 6202 | FALSE | 37 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-08-20 10:00 | 2012-08-20 10:00 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2012 | Q3 | Q3 - 2012 | 7696 | 6532 | FALSE | 37 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 23:00 | 2012-10-30 23:00 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2012 | Q4 | Q4 - 2012 | 8540 | 7269 | FALSE | 38 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 16:40 | 2013-01-30 16:40 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | 2013 | Q1 | Q1 - 2013 | 12034 | 10196 | FALSE | 100 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2014-04-14 12:15 | 2014-04-14 12:15 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2010 | Q2 | Q2 - 2010 | 64 | 1308 | FALSE | 35 |  | 0 |  |  | 100 |  | 60 |  | 0 |  | 90 |  | 25 |  | 30 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2010 | Q3 | Q3 - 2010 | 402 | 1467 | FALSE | 35 | N/A | 0 |  | 0 | 100 | Complete | 50 | . | 0 | N/A constructions will be on our own property. | 100 | Complete | 50 | Reprioritized states | 40 | Reprioritized states | 20 | Reprioritized states | 35 | Reprioritized states | 25 | N/A | 2010-11-23 17:33 | 2010-11-23 17:33 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2010 | Q4 | Q4 - 2010 | 908 | 1948 | FALSE | 40 | Slightly behind due to construction RFP. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 35 | Slightly behind due to construction RFP. | 50 | Slightly behind due to construction RFP. | 50 | Slightly behind due to construction RFP. | 50 | Slightly behind due to construction RFP. | 25 | Slightly behind due to construction RFP. | 2011-01-29 17:13 | 2011-01-29 17:13 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2011 | Q1 | Q1 - 2011 | 2366 | 2928 | FALSE | 16 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 32 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 13 | Variance from baseline due to delay in construction procurement process. Plan to purchase the support and management systems for monitoring. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 30 | Variance from baseline due to delay in construction procurement process. | 30 | Variance from baseline due to delay in construction procurement process. | 15 | Variance from baseline due to delay in construction procurement process. | 2011-05-27 08:10 | 2011-05-27 08:10 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2011 | Q2 | Q2 - 2011 | 3366 | 3446 | FALSE | 39 | We plan to complete all construction and the majority of equipment deployments in the 3rd quarter. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 26 | Construction is targeted to be completed by end of 3Q. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 42 | The majority of equipment will be procured. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 80 | Our network build will be the deployment of transport equipment (2i) at each of our interconnection sites. | 80 | Variance from baseline due to delay in construction procurement process. | 75 | Variance from baseline due to delay in construction procurement process. | 2011-08-30 00:11 | 2011-08-30 00:11 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2011 | Q3 | Q3 - 2011 | 4302 | 4001 | FALSE | 44 | The majority of the project will be complete by the end of 3Q, but the percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 68 | The site preparation will be complete, but the percent complete is strictly based on the budget. | 41 | The equipment procurement will be complete, but the percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2011-11-29 10:33 | 2011-11-29 10:33 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2011 | Q4 | Q4 - 2011 | 5304 | 4974 | FALSE | 47 | Finalize construction portion of the project and begin working on the project close out. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 66 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 44 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:52 | 2012-02-27 15:52 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2012 | Q1 | Q1 - 2012 | 6060 | 5629 | FALSE | 47 | Finalize construction portion of the project and begin working on the project close out. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 71 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 44 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-14 12:02 | 2012-05-14 12:02 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2012 | Q2 | Q2 - 2012 | 7152 | 6203 | FALSE | 47 | Finalize construction portion of the project and begin working on the project close out. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 71 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 44 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-08-20 10:08 | 2012-08-20 10:08 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2012 | Q3 | Q3 - 2012 | 7698 | 6533 | FALSE | 47 | Finalize construction portion of the project and begin working on the project close out. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 72 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 44 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 23:00 | 2012-10-30 23:00 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2012 | Q4 | Q4 - 2012 | 8544 | 7276 | FALSE | 48 | Finalize construction portion of the project and begin working on the project close out. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 72 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 44 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 16:51 | 2013-01-30 16:51 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | 2013 | Q1 | Q1 - 2013 | 12032 | 10195 | FALSE | 100 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2014-04-14 12:13 | 2014-04-14 12:13 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2010 | Q2 | Q2 - 2010 | 65 | 1309 | FALSE | 50 |  | 0 |  |  | 75 |  | 75 |  | 0 |  | 75 |  | 25 |  | 50 |  | 10 |  | 10 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2010 | Q3 | Q3 - 2010 | 404 | 1468 | FALSE | 55 | During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. | 0 |  | N/A | 100 | Complete | 50 | See 2a. | 0 | N/A construction will be on our own property. | 100 | Complete | 25 | See 2a. | 40 | See 2a. | 15 | See 2a. | 15 | See 2a. | 10 | See 2a. | 2010-11-23 17:43 | 2010-11-23 17:43 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2010 | Q4 | Q4 - 2010 | 1160 | 2198 | FALSE | 60 | Variance from baseline due to delay in construction procurement process. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 65 | Variance from baseline due to delay in construction procurement process. | 85 | Variance from baseline due to delay in construction procurement process. | 65 | Variance from baseline due to delay in construction procurement process. | 65 | Variance from baseline due to delay in construction procurement process. | 40 | Variance from baseline due to delay in construction procurement process. | 2011-02-15 18:02 | 2011-02-15 18:02 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2011 | Q1 | Q1 - 2011 | 2368 | 2929 | FALSE | 17 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 17 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 18 | Variance from baseline due to delay in construction procurement process. Plan to purchase our ADM and support and management systems for monitoring. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 25 | Variance from baseline due to delay in construction procurement process. | 25 | Variance from baseline due to delay in construction procurement process. | 15 | Variance from baseline due to delay in construction procurement process. | 2011-05-27 08:13 | 2011-05-27 08:13 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2011 | Q2 | Q2 - 2011 | 3370 | 3448 | FALSE | 22 | All construction and fiber splicing will be completed. The majority of equipment deployments should also be completed. Delays are due to longer construction procurement process than expected. The percent complete is based on invoiced expenses in 2Q. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 25 | Delays are due to longer construction procurement process than expected. The percent complete is based on invoiced expenses in 2Q. | 22 | Delays are due to longer construction procurement process than expected. The percent complete is based on invoiced expenses in 2Q. | 90 | Our network build will be the deployment of transport equipment (2i) at each of our interconnection sites. | 90 | Variance from baseline due to delay in construction procurement process. | 80 | Variance from baseline due to delay in construction procurement process. | 2011-08-30 00:19 | 2011-08-30 00:19 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2011 | Q3 | Q3 - 2011 | 4340 | 4026 | FALSE | 30 | The majority of the project will be complete by the end of 3Q, but the percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | The site preparation will be complete, but the percent complete is strictly based on the budget. | 29 | The equipment procurement will be complete, but the percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 95 | Should be very close to completion by the end of next quarter. | 2011-11-30 14:41 | 2011-11-30 14:41 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2011 | Q4 | Q4 - 2011 | 5308 | 4977 | FALSE | 32 | Fiber assignments at three of the sites have taken a bit longer than expected, but plan on having it completed early in the 1st quarter. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 57 | Complete. Percent complete is strictly based on the budget. We expect to be under budget for this line item. | 28 | Complete. Percent complete is strictly based on the budget. We expect to be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:55 | 2012-02-27 15:55 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2012 | Q1 | Q1 - 2012 | 6062 | 5630 | FALSE | 32 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 59 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 28 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-14 12:03 | 2012-05-14 12:03 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2012 | Q2 | Q2 - 2012 | 6522 | 5875 | FALSE | 32 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 59 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 28 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-07-27 12:20 | 2012-07-27 12:20 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2012 | Q3 | Q3 - 2012 | 7700 | 6534 | FALSE | 32 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 60 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 28 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 23:01 | 2012-10-30 23:01 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2012 | Q4 | Q4 - 2012 | 8546 | 7278 | FALSE | 33 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 60 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 28 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 16:54 | 2013-01-30 16:54 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | 2013 | Q1 | Q1 - 2013 | 12036 | 10197 | FALSE | 100 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2014-04-14 12:17 | 2014-04-14 12:17 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2010 | Q2 | Q2 - 2010 | 66 | 1310 | FALSE | 25 |  | 0 |  |  | 100 |  | 50 |  | 0 |  | 75 |  | 0 |  | 25 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2010 | Q3 | Q3 - 2010 | 406 | 1469 | FALSE | 55 | Ahead | 0 |  | 0 | 100 | Complete | 100 | Ahead | 0 | N/A constructions will be on our own property. | 100 | Complete | 100 | Ahead | 50 | N/A | 50 | Ahead | 50 | Ahead | 25 | Ahead | 2010-11-23 17:50 | 2010-11-23 17:50 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2010 | Q4 | Q4 - 2010 | 1162 | 2199 | FALSE | 60 | Variance from baseline due to delay in construction procurement process. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 40 | Variance from baseline due to delay in construction procurement process. | 45 | Variance from baseline due to delay in construction procurement process. | 35 | Variance from baseline due to delay in construction procurement process. | 35 | Variance from baseline due to delay in construction procurement process. | 20 | Variance from baseline due to delay in construction procurement process. | 2011-02-15 18:09 | 2011-02-15 18:09 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2011 | Q1 | Q1 - 2011 | 2370 | 2930 | FALSE | 25 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 25 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 26 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 15 | Variance from baseline due to delay in construction procurement process. | 15 | Variance from baseline due to delay in construction procurement process. | 10 | Variance from baseline due to delay in construction procurement process. | 2011-05-27 08:17 | 2011-05-27 08:17 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2011 | Q2 | Q2 - 2011 | 3372 | 3449 | FALSE | 38 | In the 3rd quarter we expect to complete all equipment deployment and the majority of network testing. The percent complete is based on projected invoiced expenses in 3Q. Delays are due to longer construction procurement process than expected. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 58 | Variance from baseline due to delay in construction procurement process. The percent complete is based on projected invoiced expenses in 3Q. Delays are due to longer construction procurement process than expected. | 37 | Variance from baseline due to delay in construction procurement process. The percent complete is based on projected invoiced expenses in 3Q. Delays are due to longer construction procurement process than expected. | 100 | Complete | 100 | Complete | 85 | Network testing is dependent upon completion of construction and equipment deployment. The testing should be completed by early 4Q. | 2011-08-30 00:36 | 2011-08-30 00:36 | 5516 | 5516 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2011 | Q3 | Q3 - 2011 | 4342 | 4027 | FALSE | 41 | The majority of the project will be complete by the end of 3Q, but the percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 49 | The site preparation will be complete, but the percent complete is strictly based on the budget. | 41 | The equipment procurement will be complete, but the percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2011-11-30 14:43 | 2011-11-30 14:43 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2011 | Q4 | Q4 - 2011 | 5310 | 4979 | FALSE | 45 | Finalize construction portion of the project and begin working on the project close out. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 69 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:57 | 2012-02-27 15:57 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2012 | Q1 | Q1 - 2012 | 6064 | 5631 | FALSE | 44 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 67 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-14 12:05 | 2012-05-14 12:05 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2012 | Q2 | Q2 - 2012 | 6524 | 5876 | FALSE | 44 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 67 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-07-27 12:22 | 2012-07-27 12:22 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2012 | Q3 | Q3 - 2012 | 7702 | 6535 | FALSE | 44 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 67 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 23:02 | 2012-10-30 23:02 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2012 | Q4 | Q4 - 2012 | 8550 | 7285 | FALSE | 46 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 67 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 17:01 | 2013-01-30 17:01 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | 2013 | Q1 | Q1 - 2013 | 11974 | 10135 | FALSE | 100 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2014-03-20 16:23 | 2014-03-20 16:23 | 7224 | 7224 | Level 3 EON, LLC | TRUE
NT10BIX5570044 | 2010 | Q2 | Q2 - 2010 | 67 | 1292 | FALSE | 5 |  | 0 |  |  | 100 |  | 20 |  | 0 |  | 0 |  | 0 |  | 10 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | University of Illinois | TRUE
NT10BIX5570044 | 2010 | Q3 | Q3 - 2010 | 448 | 1490 | FALSE | 3 | This was projected to be at 10%. The length of time needed to complete the Environmental Assessment and hire our engineering firm has put us behind schedule. We are working on ways of expediting the awards of our construction contracts to get us back on schedule. This was projected to be at 10%. | 0 |  | N/A | 100 | Complete | 50 | Projected at 100%. We will have paid some invoices from our engineering firm in the 4th quarter, but most will come in the 1st Quarter of Year 2. The length of time it took to bid and hire the engineering firm put this category behind schedule. | 50 | Projected at 100%. We will have acquired some of our rights of way in this quarter, but this will be completed in the 1st Quarter of Year 2. The length of time it took to bid and hire the engineering firm put this category behind schedule. | 50 | Projected at 100%. This will be completed in the 1st Quarter of Year 2. The length of time it took to bid and hire the engineering firm put this category behind schedule. | 0 | N/A | 0 | Projected at 10%. We will have identified our FTTP vendor, which will easily make this category on schedule from an accomplishment perspective, but we will not have purchased any equipment before the end of the 4th quarter. We do not anticipate purchasing much equipment before the 2nd Quarter of Year 2. | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-29 19:19 | 2010-11-29 19:19 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2010 | Q4 | Q4 - 2010 | 1326 | 2349 | FALSE | 8 | Baseline plan was 15%. At the time this figure was included in the revised project baseline, we thought that we would complete our Environmental Assessment and hire our engineering firm in a shorter period of time than it actually took. We were overly optimistic in predicting that we would have spent 15% of our project budget by the end of the 5th quarter. Based on actual expenditures, it will take until the 4th quarter of 2011 to get back on target, and even that may be difficult. For this category and others below, we were too optimistic that we could move a project of this magnitude through the established processes of the University and two cities as fast as we projected in our revised baseline plan. As mentioned elsewhere, the weatherman has not done us any favors either. | 0 |  | N/A | 100 | Completed | 75 | Baseline plan was 100%.At the time this figure was included in the revised project baseline, we thought that we would complete our Environmental Assessment and hire our engineering firm in a shorter period of time than it actually took. We were overly optimistic in predicting that the engineering would be complete by the end of the 4th quarter. This will be completed in the second quarter of 2011. | 50 | Baseline plan was 100%. At the time this figure was included in the revised project baseline, we thought that we would complete our Environmental Assessment and hire our engineering firm in a shorter period of time than it actually took. We were overly optimistic in predicting that the rights-of-way would be acquired by the end of the 4th quarter. In order to continue to make progress on the construction, an "easement free" design will initially be bid, with the paths that require private easements bid as alternates. That will allow the lengthy process of acquiring the private easements to continue in parallel with the construction bidding. We know that we will have to do some of our construction in 2012, and the areas that will require private easements for rights-of-way will be scheduled for that second year of construction. That should allow a sufficient period of time for the easement negotiation process to be successfully concluded. This milestone may not be completed for yet anot | 50 | Baseline plan was 100%. At the time this figure was included in the revised project baseline, we thought that we would complete our Environmental Assessment and hire our engineering firm in a shorter period of time than it actually took. We were overly optimistic in predicting that the construction permits and other approvals would be complete by the end of the 4th quarter. All permits have been applied for and Shive-Hattery will secure all needed permits prior to the release of the construction bid documents in April of 2011. This will be completed in the second quarter of 2011. | 0 | As planned | 10 | As planned- the FTTP electronics RFP will be awarded. | 0 | As planned | 0 | Baseline Plan was 10%. At the time this figure was included in the revised project baseline, we thought that we would complete our Environmental Assessment and hire our engineering firm in a shorter period of time than it actually took. We were overly optimistic in predicting that the equipment deployment would be 10% complete by the end of the next quarter. The fIber-to-the-premise electronics contract will be voted on by the University of Illinois Board of Trustees at their March 23rd meeting. If they approve the contract, it is unlikely that any purchase orders will be issued before the end of the quarter. Assuming the contract is approved, in early April we will order FTTP equipment to test with. FTTP equipment for deployment will not be ordered until the 3rd quarter. | 0 | As planned | 2011-02-23 11:04 | 2011-02-23 11:04 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2011 | Q1 | Q1 - 2011 | 2258 | 2874 | FALSE | 16 | The baseline plan was 45%. The percentage we have been listing for overall project percentage is directly tied to our expenditures. In the coming quarter we will pay the bulk of our engineering fees and will purchase all of our network core equipment and the first wave of our FTTP electronics. Construction may actually start by the end of the next quarter, but there will be little if any contractor expenses on our books by June 30th. With our original Baseline Plan and with each PPR we have attempted to predict the future as requested by NTIA. What we have consistently shown is that we are not very accurate at predicting the future. We are boldly going into the woods where no one has ever gone before. There are no models for us to study and learn from to help in predicting our future progress. There has never been a project quite like UC2B with its mix of Middle-Mile and Last-Mile components, and with two local municipalities and a major university as partners behind the wheel. We | 0 |  | N/A | 100 | This is consistent with our baseline plan. | 100 | This is consistent with our baseline plan. | 80 | The baseline plan was 100%. We do not expect to complete the negotiations for private easements until the 4th quarter of 2011. | 100 | This is consistent with our baseline plan. | 0 | The baseline plan was 100%. Until we start construction there will not be any site preparation. When we did the baseline plan, we predicted (inaccurately) that we would begin fiber construction in the second quarter. It now appears that we will not begin in earnest until the 3rd quarter. | 50 | Baseline was 60%. The Baseline Plan inaccurately predicted that we would have purchased more equipment in the next quarter than it now looks like we will purchase. As network electronics are constantly being updated and improved by the vendors, within reason, there is value in purchasing the electronics â€œjust-in-timeâ€ for when they will be needed for deployment. We will only purchase network equipment as we need it. There will be significant expenditures in the third quarter as we begin to populate the FTTP neighborhood cabinets. We will purchase our core electronics in the coming quarter, but the bulk of our FTTP electronics will not be purchased until the 3rd quarter. We should be back on target in this area by the end of the 3rd quarter. | 2 | The baseline plan was 30%. We are at least 3 months behind where we predicted we would be in terms of construction. Some of that is attributable to the time and effort that was expended on the Environmental Assessment. Some of that is attributable to the complexity of out project and that it has taken our engineering firm more time than they estimated to compete our drawings. Some of that is attributable to time spent on reviewing the fiber backbone design at the request of one of our municipalities. Some of that is attributable to our poor ability to accurately predict the future. We will make significant progress in this area in the third quarter. | 50 | The baseline plan was 60%. We are at least 3 months behind where we predicted we would be in terms of equipment deployment. Some of that is attributable to the time and effort that was expended on the Environmental Assessment. Some of that is attributable to the complexity of our project and that it has taken our engineering firm more time than they predicted to compete our drawings. Some of that is attributable to time spent on reviewing the fiber backbone design at the request of one of our municipalities. Some of that is attributable to our poor ability to accurately predict the future. We will deploy our core electronics in the coming quarter, but the bulk of our FTTP electronics will not be deployed until the 3rd quarter. We should be back on target by in this area by the end of the 3rd quarter. | 0 | Baseline plan was 25%.With the delay in constriction, there will be no network to test until the 3rd quarter. | 2011-05-23 17:22 | 2011-05-23 17:22 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2011 | Q2 | Q2 - 2011 | 3256 | 3390 | FALSE | 20 | Baseline Projection was 75%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction will begin with a great deal of urgency in the 3rd quarter. The 20% projection is based on the projection of spending 19.94% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 80 | Baseline Projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction will begin with a great deal of urgency in the 3rd quarter. This milestone category will be caught up be the end of the 4th quarter of 2011. | 50 | Baseline Projection was 70%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction will begin with a great deal of urgency in the 3rd quarter. Equipment procurement has been further delayed by a conscious decision to wait until after August 21st when the FTTP electronics vendor will be releasing upgraded software and hardware. We will buy much of this equipment up-front to bring up the core network in the 4th quarter of 2011. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase | 10 | Baseline projection was 69%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction will begin with a great deal of urgency in the 3rd quarter. We expect to conform to the projections in our baseline by the 3rd quarter of 2012. The final Network Build will be completed in January of 2013. | 50 | Baseline projection was 70%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction will begin with a great deal of urgency in the 3rd quarter. Equipment deployment has been further delayed by a conscious decision to wait until after August 21st when the FTTP electronics vendor will be releasing upgraded software and hardware. We do not expect to get back on track with our baseline projections until the 1st quarter of 2013, which is the end of our project. | 0 | Baseline projection was 60%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction will begin with a great deal of urgency in the 3rd quarter. We projected Network testing to be complete by the 2nd quarter of 2012. It now seems likely that the actual date will be late in the 3rd quarter or early in the 4th quarter of 2012 instead. | 2011-08-22 11:40 | 2011-08-22 11:40 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2011 | Q3 | Q3 - 2011 | 4278 | 3989 | FALSE | 22 | Baseline projection was 78%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begin with a great deal of urgency in the 3rd quarter. The 22% projection is based on the projection of spending 22.2% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. There will be significant federal spending in the 4th quarter of 2011 and in the remaining quarters. We believe we can complete the project by our 1/31/2013 end date. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 50 | Baseline projection was 80%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction is progressing with a great deal of urgency in the 4th quarter. Equipment procurement has been further delayed by a conscious decision to wait until after FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We will buy much of this equipment up-front to bring up the core network in the 4th quarter of 2011. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is inst | 10 | Baseline projection was 90%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begin with a great deal of urgency in the 4th quarter. We expect to conform to the projections in our baseline by the 4th quarter of 2012. The final Network Build will be completed in January of 2013. | 50 | Baseline projection was 80%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency in the 4th quarter. Equipment procurement has been further delayed by a conscious decision to wait until after FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We do not expect to get back on track with this baseline projection until the 1st quarter of 2013, which is the end of our project. | 0 | Baseline projection was 70%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency in the 4th quarter. However, our contractors will not receive fiber until the first quarter of 2012, and it may well be the 2nd quarter of 2012 before they have anything ready for testing. We projected Network testing to be complete by the 2nd quarter of 2012. It now seems likely that the actual date will be in the 4th quarter of 2012 instead. | 2011-11-27 22:32 | 2011-11-27 22:32 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2011 | Q4 | Q4 - 2011 | 5082 | 4753 | FALSE | 40 | Baseline projection was 85%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction began with a great deal of urgency in the 3rd quarter. The 40% projection is based on the projection of spending 40% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. There will be significant federal spending in the 1st quarter of 2012 and in the remaining quarters. We believe we can complete the project by our 1/31/2013 end date. | 0 |  | N/A | 100 | Complete | 100 | Complete | 95 | A couple of our "last-minute" ROW issues may not be totally resolved by March 31st. | 100 | Complete | 100 | Complete | 39 | Baseline projection was 90%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction progressed with a great deal of urgency in the 4th quarter. Equipment procurement has been further delayed by a conscious decision to wait until after FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We will buy much of this equipment up-front to bring up the core network in the 1st quarter of 2012. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installe | 36 | Baseline projection was 92%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction began with a great deal of urgency in the 4th quarter. We will receive our fiber during this next quarter and will get a small amount installed this coming quarter. We expect to conform to the projections in our baseline by the 4th quarter of 2012. The final network build will be completed in January of 2013. | 50 | Baseline projection was 90%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency in the 4th quarter. Equipment procurement has been further delayed by a conscious decision to wait until after our FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We do not expect to get back on track with this baseline projection until the 1st quarter of 2013, which is the end of our project. All of the core network and most of the core FTTP equipment will be deployed by the end of next quarter. | 5 | Baseline projection was 80%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency in the 4th quarter. However, our contractors will not receive fiber until the first quarter of 2012, and it may well be the 2nd quarter of 2012 before they have anything ready for testing. We projected network testing to be complete by the 2nd quarter of 2012. It now seems likely that the actual date will be in the 4th quarter of 2012 instead. | 2012-02-16 23:14 | 2012-02-16 23:14 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2012 | Q1 | Q1 - 2012 | 5932 | 5565 | FALSE | 68 | Baseline projection was 85%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction began with a great deal of urgency in the 3rd quarter. The 68% projection is based on the projection of spending 68% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. There will be significant federal spending in the 2nd quarter of 2012 and in the remaining quarters. We believe we can complete the project by our 1/31/2013 end date. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 70 | Baseline projection was 90%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction progressed with a great deal of urgency in the 4th quarter. Equipment procurement has been further delayed by a conscious decision to wait until after FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We will buy much of this equipment up-front to bring up the core network in the 1st quarter of 2012. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installe | 71 | Baseline projection was 92%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction began with a great deal of urgency in the 4th quarter. We will receive our fiber during this next quarter and will get a small amount installed this coming quarter. We expect to conform to the projections in our baseline by the 4th quarter of 2012. The final network build will be completed in January of 2013. | 60 | Baseline projection was 90%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency in the 4th quarter. Equipment procurement has been further delayed by a conscious decision to wait until after our FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We do not expect to get back on track with this baseline projection until the 1st quarter of 2013, which is the end of our project. All of the core network and most of the core FTTP equipment will be deployed by the end of next quarter. | 50 | Baseline projection was 80%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency in the 4th quarter. However, our contractors will not receive fiber until the first quarter of 2012, and it may well be the 2nd quarter of 2012 before they have anything ready for testing. We projected network testing to be complete by the 2nd quarter of 2012. It now seems likely that the actual date will be in the 4th quarter of 2012 instead. | 2012-05-06 14:50 | 2012-05-06 14:50 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2012 | Q2 | Q2 - 2012 | 6902 | 6077 | FALSE | 72 | Baseline projection was 100%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction began with a great deal of urgency in the 3rd quarter of 2011. The 72% projection is based on the projection of spending 72% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. There will be significant federal spending in the 3rd quarter of 2012 and in the remaining quarters. We believe we can complete the project by our 1/31/2013 end date. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 85 | Baseline projection was 90%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has progressed with a great deal of urgency. Equipment procurement has been further delayed by a conscious decision to wait until after FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. The core network equipment will all have been purchased. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase the customer equipment too far ahead of t | 90 | Baseline projection was 96%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency. We expect to conform to the projections in our baseline by the 1st quarter of 2013. The final network build will be completed in January of 2013. | 80 | Baseline projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency. Equipment procurement has been further delayed by a conscious decision to wait until after our FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We do not expect to get back on track with this baseline projection until the 1st quarter of 2013, which is the end of our project. All of the core network and most of the core FTTP equipment will be deployed by the end of next quarter. | 90 | Baseline projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency. We projected network testing to be complete by the 2nd quarter of 2012. It now seems likely that the actual date will be in the 4th quarter of 2012 instead. | 2012-08-07 15:29 | 2012-08-07 15:29 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2012 | Q3 | Q3 - 2012 | 8060 | 6736 | FALSE | 73 | Baseline projection was 100%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and middle-mile construction will be compete by the end of the 4th quarter. Last-mile construction will continue as long as weather permits. The 73% projection is based on the projection of spending 73% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. There will be significant federal spending in the 4th quarter of 2012 as the contractors process their invoices for work completed in the 3rd and 4th quarters. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 85 | Baseline projection was 100%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has progressed with a great deal of urgency. The core network equipment has all been purchased. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase the customer equipment too far ahead of time, we use up too much of the warranty before it is ever deployed. We expect to purchase the last of this customer-specific equipment in January of 2013. | 85 | Baseline projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency. We expect to to complete all of our middle-mile construction in the 4th quarter. We are concerned that we will not be able to complete all of our last-mile construction by February 1st. | 70 | Baseline projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and middle mile construction will be complete by the end of the 4th quarter. All of the core network equipment will be deployed, but the customer premise equipment will be deployed one location at a time as the customers are connected. | 100 | Complete | 2012-11-26 18:07 | 2012-11-26 18:07 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2012 | Q4 | Q4 - 2012 | 8736 | 7534 | FALSE | 70 | Baseline projection was 100%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and middle-mile construction will be compete by the end of the 4th quarter. Last-mile construction will continue as long as weather permits. The 70% projection is based on the projection of spending 70% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. We will get caught up with pay requests in the next quarter as the contractors process their invoices for work completed in the 3rd and 4th quarters of 2013. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 80 | Baseline projection was 100%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has progressed with a great deal of urgency. The core network equipment has all been purchased. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase the customer equipment too far ahead of time, we use up too much of the warranty before it is ever deployed. We expect to purchase the last of this customer-specific equipment in September of 2013. | 85 | Baseline projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We expect to to complete all of our middle-mile construction in the 1st quarter of 2013. Last mile Fiber-to-the-Premise (FTTP) construction will continue through September of2013. | 70 | Baseline projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and middle mile construction will be complete by the end of the 1st quarter of 2013. All of the core network equipment is deployed, but the customer premise equipment will be deployed one location at a time as the customers are connected through 9/30/13. | 100 | Complete | 2013-02-12 23:56 | 2013-02-12 23:56 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2013 | Q1 | Q1 - 2013 | 9808 | 8439 | FALSE | 80 | This is consistent with our Extension projections. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 95 | We will accquire the remaining equipment we will need to deliver services. There may be a few cables and smaller items that we pick up in the following quarter as needed. | 92 | We will add some ROW fiber and some FTTP fiber drops in June, but the bulk of the remaining work to be done will happen in the 3rd quarter. | 90 | We will continue to deploy equipment as customers are built to there will still be customers to connect in the 3rd quarter of 2013. | 95 | We will continue to test the network as it is expanded to provide service to the 61 additional Anchor Institutions. | 2013-05-19 18:15 | 2013-05-19 18:15 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2013 | Q2 | Q2 - 2013 | 10722 | 9024 | FALSE | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 0 | N/A | N/A | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 2013-08-23 18:02 | 2013-08-23 18:02 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570044 | 2013 | Q3 | Q3 - 2013 | 12078 | 10240 | FALSE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-04-25 15:18 | 2014-04-25 15:18 | 5400 | 5400 | University of Illinois | TRUE
NT10BIX5570045 | 2010 | Q2 | Q2 - 2010 | 68 | 1327 | FALSE | 11.1 |  | 0 |  |  | 100 |  | 100 |  | 25 |  | 15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2010 | Q3 | Q3 - 2010 | 464 | 1498 | FALSE | 20 | Expect to acquire materials for 3 of 6 service areas which comprise 40% of total project. Anticipate FONSI approximately 11/17 leaving 15-30 days (maximum) of fiber construction before winter sets. | 0 | N/A | N/A | 100 | N/A | 100 | Finalizing slack and splice locations in engineering plans for 3 service areas | 25 | N/A | 15 | Didn't receive FONSI such that we are not permitted to take out permits yet | 100 | N/A | 0 | Expecting FONSI in 4Q2010 such that final ordering, receipt and installation will be delayed to 1Q2011 | 0 | N/A | 0 | N/A | 0 | N/A | 2010-12-01 11:50 | 2010-12-01 11:50 | 5201 | 5201 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2010 | Q4 | Q4 - 2010 | 1262 | 2289 | FALSE | 20 | Expect to acquire materials for 3 of 6 service areas which comprise 40% of total project. FONSI received on 12/23/10 therefore, no fiber construction during 4Q2010. | 0 |  | N/A | 100 | N/A | 100 | N/A | 25 | N/A | 15 | Since we received the FONSI on 12/23/10, there were no permits initiated | 100 | N/A | 10 | FONSI received on 12/23/10. As such, the final ordering, receipt and installation will be delayed to 2Q2011. We have completed an initial design for the first of 2 fiber rings on the East side of Madison. However, we do not have the procurement details worked out yet nor do we have a final design and are not ready to order just yet. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-21 17:12 | 2011-02-21 17:12 | 5201 | 5201 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2011 | Q1 | Q1 - 2011 | 2024 | 2757 | FALSE | 6 | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. We expect to catch up in 4Q2011. | 0 |  | N/A | 95 | Monona Drive service area (Phase 3) will not begin until 2Q2012. Expect to catch in 2Q2012. | 100 | Our baseline assumed network engineering design could be completed in phases. However, the EA required us to complete all engineering before proceeding with construction. | 50 | Delaying Monona Drive service area until summer 2012 due to significant road construction. | 38 | Phase 1 permits expected 5/4/11. We plan to submit Phase 2 permits in May 2011 and go before the City of Madison Board of Public Works on 6/8/11. We are also meeting with WisDOT (Wisconsin Department of Transportation) in May 2011 to finalize a permit request. FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. We expect to catch up in 2Q2011. | 0 | FONSI timing and engineering resources were used to complete network design. We expect to catch up 3Q2011. | 0 | FONSI timing. Also, we were conducting CAI needs assessments before procuring hardware which we did not include in our baseline. We expect to complete 40% of this in 4Q2011 and catch up in 4Q2012. Significant delay is due to construction delays in Monona Drive service area due to road construction schedule changes. | 14 | Received Environmental Assessment late 4Q2010 | 0 | FONSI timing. Also, are conducting CAI needs assessments before procuring hardware which we did not include in our baseline. | 0 | FONSI timing and weather. We expect to be substantially caught up in 4Q2011. | 2011-05-13 16:08 | 2011-05-13 16:08 | 5201 | 5201 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2011 | Q2 | Q2 - 2011 | 2968 | 3241 | FALSE | 49 | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. We expect to catch up in 4Q2011. | 0 |  | N/A | 95 | FONSI was received in 4Q2010. We have used funds from SF-424C's architectural and engineering fees to cover the cost of the EA. We expect to expend approximately $1,500 to cover the cost of an on-site archeologist as required during the Monona Drive Service area in Spring 2012. | 100 | Our baseline assumed network engineering design could be completed in phases. However, the EA required us to complete all engineering before proceeding with construction. | 69 | Expect to finalize right-of-way with City of Middleton and Dane County | 46 | Anticipate to receive permits in City of Middleton, Town of Madison, Town of Middleton, Dane County and from the WI Dept of Transportation in 3Q2011. | 100 | Expect to complete site prep activities at 525 Science Dr, Madison, WI | 0 | Expect to procure equipment in 4Q2011 once consortium network designs are finalized | 46 | We expect to be one quarter behind our baseline at the end of 3Q2011. This is due to late start due to FONSI and weather. | 0 | FONSI timing. Also, we were conducting CAI needs assessments before procuring hardware which we did not include in our baseline. | 0 | FONSI timing. Also, we were conducting CAI needs assessments before procuring hardware which we did not include in our baseline. | 2011-08-09 11:44 | 2011-08-09 11:44 | 5201 | 5201 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2011 | Q3 | Q3 - 2011 | 4018 | 3849 | FALSE | 54 | MUFN is catching up from 1yr loss due to EA delays. Our 4Q2011 progress will meet our 2Q2011 progress plan. Due to weather, we won't be able to fully catch up with our baseline until 4Q2012. We expect to expend 67% of funds by the end of 2Q2012. | 0 |  | N/A | 95 | FONSI was received in 4Q2010. We were not aware that an EA was required. We have used funds from SF-424C's architectural and engineering fees to cover the cost of the EA. We expect to expend approximately $1,500 to cover the cost of an on-site archeologist as required during the Monona Drive Service area in 3Q2012. | 100 | Expect to have optical design work completed by end of 4Q2011. | 75 | Have right-of-ways for all but Monona Drive service area (remaining 25% difference from our baseline with completion (100%) by end of 1Q2012. | 69 | Did not know about EA so plan is 1yr behind. Expect to meet baseline in 2Q2012 | 0 | Filed and (expect to) receive SF-1444 conformance in 4Q2011 and meet 100% baseline in 1Q2012 | 0 | We are redesigning optical transport system due to unexpected CAI demands for redundancy. Will begin procuring hardware in late 4Q2011 after optical network (re)design is complete which we did not include in our baseline as we believed this was already completed. We expect to purchase hardware in 1Q2012 (expend funds). Will be on track with baseline in 1Q2012. | 57 | At the end of 4Q2011, we will be exceeding our baseline at 2Q2011 (46%) but will not be able to catch up to our 4Q2011 projection until 4Q2012 due to weather and road construction delays causing some builds to be delayed to late summer 2012. | 0 | We expected to immediately deploy "North ring" but delayed due to network assessment meetings with CAIs and resulting surprise in demand. Redesigning optical system now with anticipated 1Q2012 deployment to catch up to baseline. Will not catch up to final 100% baseline until 4Q2012 as Monona Drive service area was delayed by 1yr due to road construction (orig. deployment was 1Q2012). | 71 | Lagging 3Q2011 baseline due to dropped sites and road construction delays which we can't resolve until 4Q2012. | 2011-11-14 11:56 | 2011-11-14 11:56 | 5201 | 5201 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2011 | Q4 | Q4 - 2011 | 5392 | 5071 | FALSE | 64 | MUFN is catching up from 1yr loss due to EA delays. Our 1Q2012 progress will be between our 2Q2011 and 3Q2011 progress plan. Due to weather, we won't be able to fully catch up with our baseline until 4Q2012. We expect to expend 67% of funds by the end of 2Q2012. | 0 |  | N/A | 95 | FONSI was received in 4Q2010. We were not aware that an EA was required. We have used funds from SF-424C's architectural and engineering fees to cover the cost of the EA. We expect to expend approximately $1,500 to cover the cost of an on-site archeologist as required during the Monona Drive Service area in 3Q2012. | 100 | EA required us to complete all engineering ahead of time such that we had 100% completed - including optical engineering. However, after network design mtgs with CAIs, we determined MUFN must redesign the optical transport as ALL entities want redundancy. This began in 3Q2011 and will complete by end of 1Q2012. | 100 | N/A | 79 | We are just past 1Q2010 baseline plan but will not catch up with our baseline of 100% completed until 2Q2012 due to road construction changes in University Ave, Monona Dr, Mineral Point and East Washington service areas (can not obtain permits in construction areas until work is nearly complete) | 0 | Expect work to commence in 1Q2012 but not to receive invoice from contractor until 2Q2012. | 0 | Expect to complete optical hardware procurement by 2Q2012. | 77 | Will catch up at 4Q2012. Expect to hit 3Q2011 baseline projection. | 0 | Expect to deploy optical hardware in 2Q2012. | 77 | Will catch up at 4Q2012. Expect to surpass 3Q2011 baseline projection. | 2012-02-29 12:24 | 2012-02-29 12:24 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2012 | Q1 | Q1 - 2012 | 5984 | 5591 | FALSE | 66 | MUFN is catching up from 1yr loss due to EA delays. Our 2Q2012 progress will be between our 2Q2011 and 3Q2011 progress plan. We won't be able to fully catch up with our baseline until 4Q2012. | 0 |  | N/A | 97 | We expect to complete 2 route change submission EA work by the end of 2Q2012 with exception of hiring archaeologist to monitor 1 lateral located in phase 3 (Monona Dr service area) | 100 | N/A | 100 | Expect to have all right-of-way though MG&E route change right-of-way will be tight to end of 2nd quarter. | 100 | Expect to have all construction permits. | 0 | Received Davis-Bacon Wage conformance for site preparation at 525 Science Dr on 12/20/12. Expect contractor to begin in 2Q2012 but not finish/invoice for work until 3Q2012. We will meet our baseline in 3Q2012. | 0 | Expect to begin procurement in 2nd quarter but not complete it or place order until 3Q2012 - assuming NTIA programmatic/grants office approval is received. | 77 | We met our planned 3Q2011 baseline but are behind our 1Q2012 due to delayed EA and unanticipated road construction plan changes. Will catch up to at 4Q2012. | 0 | We expected to immediately deploy "North ring" but delayed due to network assessment meetings with CAIs and resulting surprise in demand. Anticipate 3Q2012 deployment to catch up to baseline. Will not catch up to final 100% baseline until 4Q2012 as Monona Drive service area was delayed by 1yr due to road construction (orig. deployment was 1Q2012); can't deploy equipment on fiber until fiber is installed. | 80 | Tested completed laterals in 1Q2011 though due to EA, road construction delays, we will not catch up to baseline until 4Q2012 due to road construction delays delaying fiber installation in Monona Dr service area and 3 in E. Washington Ave and University Ave Service Areas. | 2012-05-09 12:52 | 2012-05-09 12:52 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2012 | Q2 | Q2 - 2012 | 6994 | 6124 | FALSE | 67 | MUFN is catching up from 1yr loss due to EA delays. Our 2Q2012 progress will be between our 2Q2011 and 3Q2011 progress plan. We won't be able to fully catch up with our baseline until 4Q2012. | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | Anticipate phase 2 (Watts Rd) and phase 3 (Monona Dr) route change approval | 100 | Anticipate approvals from NTIA and expedient permitting. | 100 | Expect 525 Science Dr to be completed. | 100 | Expect optical procurement to be completed | 85 | Anticipate continued construction on road-construction delayed areas as well as finalizing UWHC fiber lease. | 0 | Expect to perform this work in 4Q2012 assuming NTIA approval of rebudget request. | 92 | Will catch up to baseline in 4Q2012 | 2012-08-09 18:32 | 2012-08-09 18:32 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2012 | Q3 | Q3 - 2012 | 7832 | 6619 | FALSE | 99 | Expect to have all fiber and network equipment installation completed by end of 4Q2012. Some invoicing and project closeout work will occur in January 2013. | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | Anticipate phase 2 (Watts Rd) and phase 3 (Monona Dr) route change approval | 100 | Anticipate approvals from NTIA | 100 | Expect completion in early November | 100 | Will be done with procurements for optical hardware and DC power systems in early 4Q2012 | 100 | Expect to finalize UWHC fiber lease once consortium agreement is completed and complete all fiber construction | 100 | Expect all DC power and optical equipment installed in 4Q2012 | 100 | Expect to complete in 4Q2012 | 2012-11-13 08:15 | 2012-11-13 08:15 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2012 | Q4 | Q4 - 2012 | 8770 | 7564 | FALSE | 100 | Anticipate completion by 1/31/13 though MUFN has requested an extension from NTIA due to potential delays from Wisconsin winter weather. | 0 |  | N/A | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Anticipate completion by 1/31/13 | 100 | Expect completion by 1/16/13 | 100 | Anticipate completion by 1/31/13 | 2013-02-14 09:10 | 2013-02-14 09:10 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2013 | Q1 | Q1 - 2013 | 9712 | 8389 | FALSE | 100 | Anticipate completion by 6/7/13. | 0 |  | N/A | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Anticipate completion by 6/7/13 | 100 | Completed in 1Q2013 | 100 | Anticipate completion by 6/7/13 | 2013-05-14 09:02 | 2013-05-14 09:02 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570045 | 2013 | Q2 | Q2 - 2013 | 10844 | 9097 | FALSE | 100 | Grant completed | 0 |  | N/A | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 2013-09-12 15:23 | 2013-09-12 15:23 | 5183 | 5183 | University of Wisconsin System | TRUE
NT10BIX5570046 | 2010 | Q2 | Q2 - 2010 | 69 | 1293 | FALSE | 3 |  |  |  |  | 10 |  | 8 |  | 10 |  | 0 |  | 0 |  | 2 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | 2010 | Q3 | Q3 - 2010 | 438 | 1485 | FALSE | 3 | The engineering and combined environment assessment is now under the direction of the State Facility Planning and Control (FP&C). The Board of Regents/LONI is the user agency providing specifications, requirements and needs to FP&C. | 0 |  | N/A | 75 | The contracted firm will be in position to submit the draft EA by 1/31/10. | 8 | Consult with Cisco Systems and other potential vendors on the best technology to deliver the anticipated transport services. | 10 | The contracted firm will have finalized the fiber route in order to process the final right-of-way permits with DOTD and railroads, US FWS, SHPO and US Army Corp of Engineers. | 0 | N/A | 0 | N/A | 2 | It is our intention to follow state procurement statutes, guidelines and guidance and issue a public competitive RFP for equipment purchases above $250,000. For equipment purchases below $250,000 we will utilize existing state contracts and/or other short-term bid response vehicles. | 0 | N/A | 0 | N/A | 1 | Working with our testing vendor, EXFO, in developing a hardware, software and testing methodoloy. | 2010-11-29 14:08 | 2010-11-29 14:08 | 5537 | 5537 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | 2010 | Q4 | Q4 - 2010 | 1376 | 2388 | FALSE | 8 | With the EA submitted 1/31 and FONSI received, GEC will be in full strength to finish the design for the end of March 2011. | 0 | N/A | N/A | 90 | Work on the research and data collection for the Existing Environment section of the EA willcontinue. Several sub-sections, including, geology and soils, air quality, water quality, biological resources,land use, aesthetics, cultural resources, infrastructure, noise, socioeconomics, and human health& safety will be finalized. Office coordination with the LA SHPO will continue. Coordination with the U.S. Fish and Wildlife and the U.S. Army Corps of Engineers (New Orleans and Vicksburg Districts) will continue. Draft EA will be submitted on January 31, 2011. | 65 | Communications field crews will survey each project segment (both rural and urban areas) for the purpose of finalizing the OSP route and will identify the placement of conduit (HDD, trench,structure), handholes, and interconnect points. In addition, required permits for construction will be solidified. Field inspection data will be delivered to design personnel for review and incorporation into routemaps. Specification preparation and design details will commence. | 65 | Required permits will be identified as part of the EA document preparation as well as field inspections. ROW issues, if any, are and will continue to be discovered during the final inspections of the OSP route and interconnect point locations. | 0 | Construction anticipated to start within the 3rd quarter of 2011. | 0 | Construction anticipated to start within the 3rd quarter of 2011. | 0 | 0 variance | 0 | Construction anticipated to start within the 3rd quarter of 2011. | 0 | 0 variance | 50 | We intent to purchase some of the hardware and software needed to facilitate this phase. | 2011-02-25 14:22 | 2011-02-25 14:22 | 5537 | 5537 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | 2011 | Q1 | Q1 - 2011 | 2314 | 2902 | FALSE | 13 | GEC will have submitted the final Environmental Assessment. In addition, GEC will have completed five of their five contracted submittals to advertise for the fiber and interconnect point construction. | 0 | N/A | N/A | 100 | STATEMENT PROVIDED BY GEC. Coordination, for the EA effort, with the U.S. Army Corps of Engineers - Vicksburg District, the Louisiana State Historic Preservation Office (LASHPO), and the United States Forest Service (USFS) will be completed. Final draft EA will be submitted. Coordination, for construction and permitting, with the U.S. Fish and Wildlife Service (USFWS), the U.S. Army Corps of Engineers - New Orleans and Vicksburg Districts, the Louisiana State Historic Preservation Office (LASHPO), the Louisiana Department of Natural Resources (LDNR), and the United States Forest Service (USFS) will continue. | 85 | STATEMENT PROVIDED BY GEC. Communications field crews will complete the survey of each project segment (both rural and urban areas) for the purpose of finalizing the OSP route and identifying the placement of conduit (HDD, trench, structure), handholes, and interconnect points. Identification of permits for construction will be completed. Field inspection / survey data will be delivered to design personnel for review and for Coordination for placement of interconnect points (new standalone building or within existing building) and development of installation details will be completed. Specifics will be incorporated into construction documents. Route maps will be finalized and incorporated into construction documents. Coordination for placement of interconnect points (new standalone pre-fab buildings or with existing buildings) and development of installation details will be completed. Specifics will be incorporated into construction documents. Construction documents suitable for bi | 75 | STATEMENT PROVIDED BY GEC. Required permits will continue to be identified as part of the EA document preparation as well as field inspections. ROW issues, if any, are and will continue to be discovered during the final inspections of the OSP route and interconnect point locations. Permits identified include the United States Army Corps of Engineers - New Orleans and Vicksburg Districts, Louisiana State Historic Preservation Office (LASHPO), Louisiana Department of Natural Resources (LDNR), United States Forest Service (USFS), United States Fish and Wildlife Service (USFWS), Louisiana Department of Transportation and Development (LADOTD), railroads, pipelines, levee districts, and cities / municipalities. Assembly of forms, permit preparation, and coordination with permitting entities will continue. | 0 | STATEMENT PROVIDED BY GEC. Construction anticipated to begin 3rd quarter of 2011. | 0 | STATEMENT PROVIDED BY GEC. Construction anticipated to begin 3rd quarter of 2011. | 1 | STATEMENT PROVIDED BY GEC. Construction anticipated to begin 3rd quarter of 2011. | 0 | STATEMENT PROVIDED BY GEC. Construction anticipated to begin 3rd quarter of 2011. | 0 | 0 variance | 0 | 0 variance | 2011-05-25 17:02 | 2011-05-25 17:02 | 5537 | 5537 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | 2011 | Q2 | Q2 - 2011 | 3156 | 3338 | FALSE | 7 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 0 | N/A | N/A | 100 | STATEMENTS PROVIDED BY GEC: Finding of No Significant Impact (FONSI) was issued by NTIA on June 3, 2011. Preparation of a supplemental EA will be required once the project is complete. This supplemental EA will address route changes subsequent to submission of the draft and final EA documents as well as any route changes that may be required during construction. Documentation for the supplemental EA will be gathered as the project moves forward. | 55 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 35 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 0 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 0 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 1 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 0 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 0 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 0 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 2011-08-17 14:37 | 2011-08-17 14:37 | 5537 | 5537 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | 2011 | Q3 | Q3 - 2011 | 4142 | 3917 | FALSE | 7 | 0 variance | 0 | N/A | N/A | 100 | 0 variance | 55 | 0 variance | 35 | 0 variance | 0 | 0 variance | 0 | 0 variance | 1 | 0 variance | 0 | 0 variance | 0 | 0 variance | 0 | 0 variance | 2011-11-18 15:00 | 2011-11-18 15:00 | 5537 | 5537 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | 2011 | Q4 | Q4 - 2011 | 5192 | 4859 | FALSE | 7 | 0 variance | 0 | N/A | N/A | 100 | 0 variance | 55 | 0 variance | 35 | 0 variance | 0 | 0 variance | 0 | 0 variance | 1 | 0 variance | 0 | 0 variance | 0 | 0 variance | 0 | 0 variance | 2012-02-22 14:58 | 2012-02-22 14:58 | 5537 | 5537 | Louisiana Board of Regents | TRUE
NT10BIX5570047 | 2010 | Q2 | Q2 - 2010 | 70 | 1320 | FALSE | 5 |  |  |  |  | 100 |  | 35 |  | 25 |  | 5 |  | 5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2010 | Q3 | Q3 - 2010 | 366 | 1449 | FALSE | 5 | Delay in completion of the Environmental Assessment (EA) and subsequent receipt of Finding of No Significant Impact (FONSI) has extended the current overall project timeline into future quarters. Construction is planned to begin in Q4. In addition, permitting issues have hindered progress of some select routes. | 0 | N/A | N/A | 100 | N/A | 40 | See narrative in 2a above describing overall project delay from initial projections. | 20 | See narrative in 2a above describing overall project delay from initial projections. | 25 | See narrative in 2a above describing overall project delay from initial projections. | 20 | See narrative in 2a above describing overall project delay from initial projections. | 20 | See narrative in 2a above describing overall project delay from initial projections. | 1 | See narrative in 2a above describing overall project delay from initial projections. | 10 | N/A | 0 | See narrative in 2a above describing overall project delay from initial projections. | 2010-11-19 17:22 | 2010-11-19 17:22 | 5529 | 5529 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2010 | Q4 | Q4 - 2010 | 754 | 1787 | FALSE | 10 | Delay in completing the Environmental Assessment and subsequent receipt of finding of No Significant Impact (FONSI) has extended the current overall project timeline into future quarters. Construction is now targeted to begin in the first quarter of 2011. Some permitting issues have hindered progress on select routes but are anticipated to be resolved this quarter as well. Weather has impacted some select routes for preparation, but again hopeful to resolve this quarter. | 0 | N/A | N/A | 100 | N/A | 70 | N/A | 50 | See 2a. above. | 40 | See 2a. above. | 30 | See 2a. above. | 40 | See 2a. above. | 5 | See 2a. above. | 15 | See 2a. above. | 5 | See 2a. above. | 2011-01-28 13:55 | 2011-01-28 13:55 | 5529 | 5529 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2011 | Q1 | Q1 - 2011 | 2264 | 2877 | FALSE | 11 | Expenditures are lagging planned milestones, as construction activities were originally forecasted well ahead of current levels. Additional resources are being deployed to meet the three year plan as outlined by the Broadband Technology Opportunities Program guidelines. | 0 | N/A | N/A | 100 | No variance. | 85 | No variance. | 70 | Right of Way acquisition, although progressing against the current milestone gap, should be completed by year end. | 60 | Acquisition of permits continues by acquiring all necessary Federal,State and Local permits. This metric to be completed by the end of calendar year 2011. | 50 | Additional resources have been allocated to this task and its anticipated there will be no gap in this milestone by year end. | 25 | A significant amount of equipment is in the form of In Kind contribution dependant upon acceptance into the project by the Grants Officer. Once approved and 'booked' to the project, this gap will narrow and be brought closer to initial projections. Projection is to meet our Baseline by the end of Quarter 1, 2012. | 10 | Network build will accelerate as weather will hopefully allow us to move forward and all necessary contracts and pre-construction activities have been completed. This metric will be accelerated throughout the year to insure gaps in Baseline are eliminated by end of the year. | 15 | Equipment will be deployed as allowed per the network build progress and procurement process. It is projected to meet our Baseline metric by Quarter 1; 2012. | 10 | Network testing will commence with portions of the network build being completed and brought on line. This metric will be brought up to Baseline projections by the end of Quarter 1, 2012. | 2011-05-24 09:07 | 2011-05-24 09:07 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2011 | Q2 | Q2 - 2011 | 3092 | 3303 | FALSE | 33 | Expenditures are lagging Baseline projections as construction activities were originally forecasted much earlier in the project time line. In Kind assets were included in this calculation and their approval date is not yet known. | 0 | N/A | N/A | 100 | No variance. | 95 | No variance. | 90 | Right of Way acquisition is progressing against the current milestone and should be completed by year end. Minimal acquisition will remain going into the final year of the project. | 80 | Permitting at all levels continues with a completion date of December 31, 2011 anticipated. | 65 | No variance. | 77 | A significant amount of Equipment for this project is in the form of In Kind assets currently under review for acceptance by the Program Office. Once approved we will meet the baseline by the end of this quarter. | 15 | Network build, although currently lagging the milestone compared to the Baseline, this metric will be met by the end of the project. Additional resources as required will added to insure compliance with the guidelines. | 70 | This metric will be exceeded as a result of adding the In Kind assets in this quarter. | 15 | Network testing is anticipated to continue as the Network Build is taking place. | 2011-08-15 16:57 | 2011-08-15 16:57 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2011 | Q3 | Q3 - 2011 | 4218 | 3957 | FALSE | 48 | Expenditures are lagging baseline projections as an aggressive original forecast had construction beginning in year one of the project. This metric will lag into year three of the project life cycle. All available resources along with an expedited construction schedule will allow for an on time completion. | 0 |  | N/A | 100 | 0-98-No Variance. | 100 | No Variance. | 90 | Rights of Way acquisition and permitting near completion as we approach the final year of the project life cycle. Any remaining rights of way and construction permits will be acquired in quarter one of 2012. | 85 | Rights of Way acquisition and permitting near completion as we approach the final year of the project life cycle. Any remaining rights of way and construction permits will be acquired in quarter one of 2012. | 70 | Currently lagging Baseline projections as we enter in the final year of the project. Some additional site preparation is scheduled for projects slated for construction next year. This metric will be met in quarter two of 2012 as routes are being completed. | 85 | No Variance. | 30 | The Network Build metric, although lagging significantly compared to original Baseline projections, will be met as required by the Broadband Technology Opportunities Program guidelines. Additional resources will be deployed to meet the projections during the final year of the project. Northwest Open Access is taking an aggressive approach to installing conduit so that when the February arrival of fiber is received, it can be expeditiously installed. | 45 | Equipment is being deployed as fiber routes are completed. Delayed fiber delivery forces equipment deployment to follow final fiber splicing projected in quarter three of 2012. | 20 | Network testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter three of year three of the project. This metric will again mirror the Network Build schedule. | 2011-11-22 14:19 | 2011-11-22 14:19 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2011 | Q4 | Q4 - 2011 | 5388 | 5064 | FALSE | 64 | Expenditures are lagging baseline projections as an aggressive original forecast had construction beginning in year one of the project. This metric will lag into year three of the project life cycle. All available resources along with an expedited construction schedule will allow for an on time completion. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 95 | Based on the necessity to make changes or to rescope segments of the project scheduled for construction in 2012, pending right of way acquisition may be necessary in the final stages of the project. | 95 | See 'Rights of Way' narrative above. | 75 | Currently lagging Baseline projections as we enter the final year o the project. Some additional site preparation will linger into 2012 as final route preparation is performed prior to construction. | 95 | No Variance. | 50 | Northwest Open Access Network has found it necessary to initiate several route changes or rescopes of segments within the project for a variety of reasons. Pending review and approval has taken additional time and added delays to an already compressed schedule. The Network Build metric, although lagging significantly compared to original Baseline projections, will be met as required by the Broadband Technology Opportunities Program guidelines. Additional resources will be deployed to meet the projections during the final year of the project. Northwest Open Access is taking an aggressive approach to installing conduit so that when the February arrival of fiber is received, it can be expeditiously installed. | 70 | Equipment is being deployed as fiber routes are completed. Delays in Fiber shipment has forced equipment deployment to follow final fiber splicing projected in quarter three of 2012. | 30 | Network testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter three of year three of the project. This metric will mirror the Network Build schedule. | 2012-02-29 11:00 | 2012-02-29 11:00 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2012 | Q1 | Q1 - 2012 | 6186 | 5695 | FALSE | 65 | Although lagging for the entire project, this metric continues to keep stride with the current gap. Significant progress is occurring in the construction phase as we surpass our second year of the project. Current projections are to attain the baseline projection for this category in quarter four of 2012. | 0 |  | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 98 | The majority of permitting will be completed with minimal approvals remaining for projects that required modifications to the originally designed routes. This metric will attain baseline projections in Q3 2012. | 90 | We are currently lagging Baseline projections as we enter the final year of the project. Some additional site preparation will linger into the second half of 2012 as final route preparation is performed prior to construction. This metric will achieve baseline in Q3 2012. | 95 | Equipment procurement will lag into the final stages of the project with minimal purchasing yet to be completed. We are anticipating finalizing purchases in Q3 2012. | 76 | The Network Build will continue to lag as construction was scheduled to start much earlier in the project time line. All available resources will continue to be utilized to bring this metric to baseline projections by Q4 2012. | 80 | Equipment is being deployed as fiber routes are completed. Delays in fiber shipment has forced equipment deployment to follow final fiber splicing projected in quarter four of 2012. | 40 | Network testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter three of 2012 and follow the same metric as Network Build. | 2012-05-18 12:29 | 2012-05-18 12:29 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2012 | Q2 | Q2 - 2012 | 6828 | 6040 | FALSE | 74 | Although lagging for the entire project, this metric continues to keep stride with the current gap. Significant progress is occurring in the construction phase as we surpass our second year of the project. Current projections are to attain the baseline projection for this category in quarter four of 2012. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 96 | Equipment procurement is anticipated to be completed as we approach the end of Q3 2012. Some minimal purchases are expected to be finalized in this quarter. | 86 | The Network Build will continue to lag as construction was scheduled to start much earlier in the project time line. All available resources will continue to be utilized to bring this metric to baseline projections by Q4 2012. | 85 | Equipment deployment will slightly lag procurement with final placement occurring in Q4 2012. | 70 | Network testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter three of 2012 and follow the same metric as Network Build. | 2012-08-01 15:00 | 2012-08-01 15:00 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2012 | Q3 | Q3 - 2012 | 7936 | 6672 | FALSE | 84 | Although lagging for the entire project and nearing completion of the project in this quarter, remaining expenses and invoices will continue into the following month. This metric will not show 100 percent completion as a result of these expenditures. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 97 | A few final clean up and completion of minor lengths of segments will occur during the final month of the project leaving this metric short until the final report is completed. | 95 | Minimal equipment will be deployed as final testing and routes are completed in January. | 90 | Testing will be done in the final month of the project schedule allowing for all remaining segments to be tested. | 2012-11-16 17:01 | 2012-11-16 17:01 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2012 | Q4 | Q4 - 2012 | 8794 | 7591 | FALSE | 92 | This metric will not be reached as we will not be expending 100% of the Budgeted amount. | 0 | N/A | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2013-02-14 23:12 | 2013-02-14 23:12 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2013 | Q1 | Q1 - 2013 | 9908 | 8495 | FALSE | 98 | Minimal activities remain pertaining primarily to closeout activities. Final invoices for activity still remain to be approved and will continue into the third quarter. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2013-05-24 17:06 | 2013-05-24 17:06 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2013 | Q2 | Q2 - 2013 | 10690 | 9006 | FALSE | 96 | Final expenditures and invoices are still pending approvals and reimbursement for the project. Originally forecasted to be completed by last quarter, final invoices will be received and paid in Quarter 3 with the exception of closeout costs and any late or disputed invoices for the project. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2013-08-21 17:22 | 2013-08-21 17:22 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570047 | 2013 | Q3 | Q3 - 2013 | 12184 | 10367 | FALSE | 100 | Project is complete. | 0 | N/A | N/A | 100 | Project is complete | 100 | Project is complete | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 2014-05-12 17:42 | 2014-05-12 17:42 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570049 | 2010 | Q2 | Q2 - 2010 | 71 | 1325 | FALSE | 7 |  |  |  |  | 100 |  | 12 |  | 15 |  | 5 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570049 | 2010 | Q3 | Q3 - 2010 | 148 | 1340 | FALSE | 15 | No change - project expected to catch up to baseline estimate | 0 | N/A | N/A | 100 | No change | 60 | No change | 75 | No change | 85 | No change | 0 | N/A | 0 | No change | 0 | No change | 0 | No change | 0 | No change | 2010-10-13 10:53 | 2010-10-13 10:53 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2010 | Q4 | Q4 - 2010 | 818 | 1852 | FALSE | 25 | No change | 0 |  | N/A | 100 | No change | 85 | No change | 100 | No change | 60 | Anticipate all applications for permits submitted, but VDOT review (up to 45 days) may delay completion percentage initially estimated. | 0 | N/A | 25 | No change | 0 | No change | 0 | No change | 0 | No change | 2011-01-28 15:58 | 2011-01-28 15:58 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2011 | Q1 | Q1 - 2011 | 1908 | 2699 | FALSE | 40 | Slight variance due to delay in starting make ready work and VDOT permitting. | 0 |  | No variance | 100 | No variance | 95 | Anticipate the potential for minor changes to final design based on network operator selection or changes requested by the department of transportation. | 100 | No variance | 90 | Anticipate all approvals for fiber construction to be secured; tower permitting will not be completed but will be in progress. | 0 | No variance | 40 | Materials for construction will have been ordered but anticipate longer than normal delivery times. Towers will not have been ordered and expect they will not until 2012. | 0 | The construction contractor is expected to have been selected, but due to delays in finalizing VDOT permitting and make ready the construction is expected to start near the beginning of the 3rd quarter. | 0 | No variance | 0 | No variance | 2011-05-06 14:58 | 2011-05-06 14:58 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2011 | Q2 | Q2 - 2011 | 3246 | 3385 | FALSE | 40 | Construction expected to be underway on middle mile fiber, but delayed start. Towers will not be constructed but will be in development for bidding. | 0 |  | N/A | 100 | May have to reconsult if changes to construction method but do not anticipate any problems with receiving approval. | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 50 | All outside plant materials will have been ordered but not anchor or network operating equipment. | 15 | Construction expected to have just begun on fiber network but not on towers. | 0 | Equipment for anchor institutions and network operations will be ordered but not deployed since construction just beginning. | 0 | No variance | 2011-08-19 18:19 | 2011-08-19 18:19 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2011 | Q3 | Q3 - 2011 | 4172 | 3934 | FALSE | 37 | Variance due to delayed construction start. By the end of Qtr 4 approximately 4 miles of fiber is anticipated to have been deployed. The project has been broken into five segments and the contractor will be in process of construction on two segments. VDOT requirements for stop work during holiday periods include the day before, the holiday, and the day following; the Thanksgiving and Christmas holidays will limit construction progress in Qtr 4. Payments for work completed on this project will always lag grant expenditures by approximately one month due to required Board of Supervisor approval prior to issuing payment to contractors and vendors. | 0 |  | N/A | 100 | No variance; expect to have received EA amendment approval. | 100 | No variance | 100 | No variance, VDOT permitting complete | 100 | No variance, expect to receive final water permits and environmental sign off by end of October. | 0 | N/A | 44 | Variance anticipated due to delay in selecting network operator and wholesale providers, and delay in fiber construction. 44% of equipment budget is anticipated to be expended for construction materials by the end of Qtr 4, with an additional $33,000 of materials received but payment not expended until January. Expect specifications and bid documents to be in process in Qtr 4 for bid release and purchase of equipment 1st Qtr of 2012. | 0 | Variance due to delay in construction start. Construction is scheduled to be in progress in November, but expenditures not made until January based on the County's payment process contractual agreement with contractor. | 0 | Variance due to delay in selecting network operator and wholesale providers. Expect to begin deploying equipment approximately 2nd Qtr 2012 when fiber network is completing. | 0 | Variance expected, network testing will not commence until completion approximately 2nd Qtr 2012. | 2011-11-21 09:56 | 2011-11-21 09:56 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2011 | Q4 | Q4 - 2011 | 4412 | 4071 | FALSE | 76 | Construction start delayed approximately 6 months, but contractor working additional crews to complete fiber construction in Qtr 2 2012. | 0 | N/A | N/A | 100 | No variance, but we expect to submit a request for an environmental assessment addendum to deploy additional fiber underground to a revised tower location. | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 78 | Variance due to delayed construction start as well as the delay in fund expenditure. It is anticipated that all outside plant materials will have been purchased by the end of next quarter as well as some of the key network electronics. | 54 | Delayed construction start by approximately 6 months. Expect the majority of the fiber network to be constructed but towers will not be under construction and equipment will not have been deployed. | 0 | Delayed construction start. Network operating and end user equipment will not be deployed until fiber construction complete, anticipated in Qtr 2 of 2012. | 25 | Expect to begin some testing of network circuits | 2012-01-24 13:55 | 2012-01-24 13:55 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2012 | Q1 | Q1 - 2012 | 6130 | 5667 | FALSE | 66 | Expect fiber construction to be 85% complete with testing and equipment deployment in progress. Tower construction firm will have been chosen for Avon and Afton towers with pre-construction tasks prior to tower erection in progress. | 0 |  | N/A | 100 | No variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 0 | N/A | 90 | Expect the majority of electronics to have been ordered with installation in progress. Miscellaneous server equipment and last minute orders will be pending. | 65 | Construction of the fiber network will be 85% complete with an additional 13 miles constructed by the end of the quarter. Two towers will be nearing construction and planning for construction of the third tower will be underway. | 65 | Expect to have begun deployment of equipment cabinets and interconnection facilities as fiber circuits are complete. | 65 | Testing will begin following construction and turn up of all interconnection points and network operating center equipment. Private provider collocated at network operating center will be testing connection. | 2012-05-16 11:43 | 2012-05-16 11:43 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2012 | Q2 | Q2 - 2012 | 7042 | 6148 | FALSE | 85 | Expect fiber construction to be nearly complete with testing and equipment deployment in progress. Two towers will be under construction. Payments lag completion in accordance with contracts requiring hold back and compliance testing prior to final payments. | 0 | N/A | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 75 | Expected to have ordered the majority of equipment but payments to lag into the following quarter in accordance with contract and compliance testing. | 80 | Construction of the fiber network will be nearly complete and testing in process. Two towers will be under construction and planning for construction of the third tower will be underway. | 65 | Expect to have begun deployment of equipment cabinets and interconnection facilities as fiber circuits are complete. | 65 | Testing will begin following construction and turn up of all interconnection points and network operating center equipment. Private providers collocated at network operating center will be testing connections. | 2012-08-13 09:13 | 2012-08-13 09:13 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2012 | Q3 | Q3 - 2012 | 7788 | 6595 | FALSE | 96 | Variance due to network construction delayed by approximately six months and difficulty in securing a third tower site in the Massies Mill area. All of the fiber network and operating equipment will have been installed and community anchor institutions receiving services over the new middle mile fiber network. Only the Massies Mill tower construction will remain to be completed in this project by the end of the following quarter, and work well in progress for local approvals and construction procurement. | 0 | N/A | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 100 | No variance | 96 | Variance due to network construction delayed by approximately six months and difficulty in securing a third tower site in the Massies Mill area. Construction of the fiber network will be complete and all equipment deployed in the operating center and in the community anchor institutions. Two towers will have been fully constructed and the third in process of securing local approvals and construction procurement. | 100 | No variance | 100 | No variance | 2012-11-07 16:02 | 2012-11-07 16:02 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2012 | Q4 | Q4 - 2012 | 8890 | 7678 | FALSE | 99 | Variance due to delayed construction start, difficulties in securing an optimum tower location in Massie's Mill, and significant weather events that impacted resources and ground conditions. The backbone fiber is complete, turn up and testing will have been completed but deployment of the final tower will be in progress. | 0 |  | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 100 | No variance | 99 | Variance due to delayed construction start, difficulties in securing an optimum tower location in Massie's Mill, and significant weather events that impacted resources and ground conditions. The backbone fiber is complete, turn up and testing will have been completed but deployment of the final tower will be in progress. | 99 | Variance due to delayed construction start and difficulties in securing an optimum tower location in Massie's Mill. The microwave backhaul equipment will have been received with installation on scheduled following erection of the tower. | 99 | Variance due to a delayed construction start, difficulties in securing an optimum tower location in Massie's Mill, and significant weather events that impacted resources and ground conditions. The backbone fiber construction and community anchor connections are complete, and splicing and close out testing of the fiber network will be completed in this quarter. Testing of the microwave equipment and the microwave to fiber interconnection will follow tower erection and microwave equipment installation. | 2013-02-21 16:51 | 2013-02-21 16:51 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2013 | Q1 | Q1 - 2013 | 9714 | 8391 | FALSE | 100 | No variance | 0 | 0 | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2013-05-14 13:37 | 2013-05-14 13:37 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570049 | 2013 | Q2 | Q2 - 2013 | 11986 | 10147 | FALSE | 100 | Project complete. | 0 | N/A | N/A | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 0 | N/A | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 2014-03-25 11:12 | 2014-03-25 11:12 | 5488 | 5488 | Nelson, County of | TRUE
NT10BIX5570050 | 2010 | Q2 | Q2 - 2010 | 72 | 1284 | FALSE | 5 |  | 0 |  |  | 100 |  | 60 |  | 15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2010 | Q3 | Q3 - 2010 | 194 | 1363 | FALSE | 11 | Due to fiber purchase and make planning ahead of schedule. | 0 |  | N/A | 100 | No Variance from Baseline Report | 90 | Due to fiber purchase and make planning ahead of schedule. | 25 | Due to fiber purchase and make planning ahead of schedule. | 0 | N/A | 10 | No Variance from Baseline Report | 25 | Purchase dark fiber from Conneaut Telephone Company | 0 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 2010-10-28 14:47 | 2010-10-28 14:47 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2010 | Q4 | Q4 - 2010 | 1056 | 2094 | FALSE | 45 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 0 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 95 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 60 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 0 | No Variance from Baseline Report | 30 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.No Variance from Baseline Report | 50 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 20 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 20 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 2011-02-10 16:03 | 2011-02-10 16:03 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2011 | Q1 | Q1 - 2011 | 2200 | 2845 | FALSE | 43 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 0 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 50 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 0 | No Variance from Baseline Report | 70 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 29 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 30 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 40 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 20 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito expects to be back on schedule by the end of the September 2011 quarter. | 2011-05-20 10:52 | 2011-05-20 10:52 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2011 | Q2 | Q2 - 2011 | 3132 | 3323 | FALSE | 42 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. In addition, percentage is based off of projected expenditures. | 0 | N/A | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 63 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 0 | No Variance from baseline | 85 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 13 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 15 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 40 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 20 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 2011-08-16 17:03 | 2011-08-16 17:03 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2011 | Q3 | Q3 - 2011 | 4086 | 3886 | FALSE | 74 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. In addition, percentage is based off of projected expenditures. | 0 | N/A | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 87 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 0 | No Variance from Baseline | 85 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 61 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 50 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 50 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 25 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 2011-11-16 16:12 | 2011-11-16 16:12 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2011 | Q4 | Q4 - 2011 | 5064 | 4735 | FALSE | 89 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 0 | N/A | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 97 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 0 | No Variance from Baseline | 95 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 72 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 65 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 50 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 30 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 2012-02-16 09:08 | 2012-02-16 09:08 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2012 | Q1 | Q1 - 2012 | 6112 | 5658 | FALSE | 87 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 0 |  | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 0 | No Variance from Baseline | 98 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 84 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 70 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 60 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 45 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 2012-05-15 15:54 | 2012-05-15 15:54 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2012 | Q2 | Q2 - 2012 | 7072 | 6163 | FALSE | 99 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | 0 | n/a | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 0 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 96 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | 70 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | 55 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | 2012-08-15 10:04 | 2012-08-15 10:04 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2012 | Q3 | Q3 - 2012 | 7872 | 6640 | FALSE | 99 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | 0 |  | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 0 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 99 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | 95 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | 95 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | 2012-11-14 14:05 | 2012-11-14 14:05 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2012 | Q4 | Q4 - 2012 | 8776 | 7569 | FALSE | 100 | No Variance from Baseline | 0 |  | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 0 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 2013-02-14 12:05 | 2013-02-14 12:05 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2013 | Q1 | Q1 - 2013 | 9240 | 8059 | FALSE | 100 | No Variance from Baseline | 100 |  | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 0 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 2013-04-24 12:28 | 2013-04-24 12:28 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2013 | Q2 | Q2 - 2013 | 10684 | 9003 | FALSE | 100 | No Variance from Baseline Report | 100 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 2013-08-21 15:19 | 2013-08-21 15:19 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | 2013 | Q3 | Q3 - 2013 | 11294 | 9444 | FALSE | 100 | No Variance from Baseline Report | 0 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 2013-11-19 14:25 | 2013-11-19 14:25 | 5542 | 5542 | Zito Media Communications II, LLC | TRUE
NT10BIX5570051 | 2010 | Q2 | Q2 - 2010 | 73 | 1312 | FALSE | 37 |  | 0 |  |  | 100 |  | 100 |  | 0 |  | 90 |  | 25 |  | 40 |  | 10 |  | 10 |  | 10 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2010 | Q3 | Q3 - 2010 | 346 | 1439 | FALSE | 58 | delayed due to Environmental Assessment/Finding of No Significant Impact | 0 |  | n/a | 100 | completed with Finding of No Significant Impact issued | 100 | completed | 0 | n/a | 100 | all permits and approval acquired | 50 | site and tower work underway | 75 | purchasing occurring in accordance with project progress | 30 | network builds occur as towers come online. | 30 | begins with network build | 30 | as deployed | 2010-11-18 10:47 | 2010-11-18 10:47 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2010 | Q4 | Q4 - 2010 | 1138 | 2176 | FALSE | 25 | winter weather and the Environmental assessment slowed the started of the project. First Step should be able to resume procurement and begin construction late Q1. | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | all permits and approval acquired | 10 | winter weather has slowed the start of the project | 25 | winter weather has slowed the start of the project | 25 | network builds occur as towers are built and commissioned | 25 | begins with network build | 25 | as deployed | 2011-02-14 16:09 | 2011-02-14 16:09 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2011 | Q1 | Q1 - 2011 | 1990 | 2740 | FALSE | 25 | Late winter weather continue to provide delays in the beginning of the construction process. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | all permits and approvals acquired | 10 | winter weather delayed start of construction | 25 | tower and communication hut purchases completed. | 25 | network build begins with tower construction | 25 | begins with network build | 25 | as deployed | 2011-05-12 17:59 | 2011-05-12 17:59 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2011 | Q2 | Q2 - 2011 | 3068 | 3291 | FALSE | 48 | winter weather delayed construction start. Additional staff has been trained and deployed to bring the project back in line with estimates | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | all permits and approvals acquired | 50 | 5 major tower sites will be prepped and ready for construction of towers | 50 | Phase two radios will be purchased along with networking equipment necessary | 27 | 150 new microwave miles built out of a total planned 550 | 30 | 21 of 69 new paths built | 30 | 21 of 69 newly built paths tested | 2011-08-12 17:41 | 2011-08-12 17:41 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2011 | Q3 | Q3 - 2011 | 4068 | 3877 | FALSE | 52 | Winter weather and the Environmental requirements slowed the start of the project. With the additional staff on board, we are working towards bringing the project back in line with projections. First Step has added additional staff to bring the project in line with the baseline indicators. First Step is working directly with NTIA on a Project Improvement Plan to address the initial project delays. Our project timeline shows that the project will have ~77% of the construction completed by the 2 year project award date. | 0 | n/a | n/a | 100 | Completed | 100 | Completed | 0 | n/a | 100 | all permits and approvals acquired | 100 | Completed | 55 | Phase 3 radios will be acquired. The equipment procurement is occurring along with the construction schedule. With the proposed construction schedule, the equipment procurement schedule will match the construction completed. | 55 | 36 of 69 microwave paths will be installed. | 55 | 36 paths will be deployed along with switching and routing equipment | 55 | testing of the deployed radios and network will be completed | 2011-11-16 13:36 | 2011-11-16 13:36 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2011 | Q4 | Q4 - 2011 | 5404 | 5084 | FALSE | 60 | Winter weather and the Environmental requirements slowed the start of the project. With the additional staff on board, we are working towards bringing the project back in line with projections. First Step has added additional staff to bring the project in line with the baseline indicators. First Step is working directly with NTIA on a Project Improvement Plan to address the initial project delays. Our project timeline shows that the project will have ~77% of the construction completed by the 2 year project award date. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | all permits and approvals acquired | 100 | completed | 85 | Phase 4 radios will be acquired. The equipment procurement occurs along with the construction schedule. With the proposed construction schedule, the equipment procurement schedule will match the construction completed. | 80 | Continued winter weather combined with the remoteness of many of the remaining paths will slow the deployment through Q1 2012. | 80 | Continued winter weather combined with the remoteness of many of the remaining paths will slow the deployment through Q1 2012. | 80 | testing of the deployed radios and network will be completed | 2012-02-29 13:58 | 2012-02-29 13:58 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2012 | Q1 | Q1 - 2012 | 5914 | 5556 | FALSE | 60 | Winter weather and the Environmental requirements slowed the start of the project. With the additional staff on board, we are working towards bringing the project back in line with projections. First Step has added additional staff to bring the project in line with the baseline indicators. First Step is working directly with NTIA on a Project Improvement Plan to address the initial project delays. Our project timeline shows that the project will have ~77% of the construction completed by the 2 year project award date. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | all permits and approvals acquired | 100 | completed | 90 | Phase 4 radios will be acquired. The equipment procurement occurs along with the construction schedule. With the proposed construction schedule, the equipment procurement schedule will match the construction completed. | 86 | Spring weather will allow First Step to begin the construction of the planned paths once again. 6 new paths will be completed in Q2, 2012. | 86 | Spring weather will allow First Step to begin the construction of the planned paths once again. 6 new paths will be completed in Q2, 2012. | 86 | Spring weather will allow First Step to begin the construction of the planned paths once again. 6 new paths will be completed in Q2, 2012. The network testing occurs along with the network deployment. | 2012-05-02 16:42 | 2012-05-02 16:42 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2012 | Q2 | Q2 - 2012 | 7288 | 6271 | FALSE | 68 | Our project timeline shows that the project will have ~95% of the construction completed by Q1 of 2013. That projection was based on a shovel ready start date of Q1 2010 with a 2 year window to completion of construction. Due to the project start delays concerning the EA, First Step has only been under construction for 2 actual years, even though we are in the 10th quarter of the 12 quarter project. First Step will still complete the project on time and on budget. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | completed | 100 | completed | 95 | all major equipment will be acquired. The remaining will be miscellaneous and additional concerning the new tower construction. | 95 | Spring weather will allow First Step to begin the construction of the planned paths once again. 16 new paths will be completed in Q3, 2012. | 100 | Spring weather will allow First Step to begin the construction of the planned paths once again. 16 new paths will be completed in Q3, 2012. | 95 | Spring weather will allow First Step to begin the construction of the planned paths once again. 16 new paths will be completed in Q3, 2012. The network testing occurs along with the network deployment. | 2012-08-29 23:39 | 2012-08-29 23:39 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2012 | Q3 | Q3 - 2012 | 8020 | 6716 | FALSE | 72 | Our project timeline shows that the project will have ~95% of the construction completed by Q1 of 2013. That projection was based on a shovel ready start date of Q1 2010 with a 2 year window to completion of construction. Due to the project start delays concerning the EA, First Step has only been under construction for 2 actual years, even though we are in the 11th quarter of the 12 quarter project. First Step will still complete the project on time and on budget. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | completed | 100 | completed | 95 | all major equipment will be acquired. The remaining will be miscellaneous and additional concerning the new tower construction. | 95 | final permit release by the US Forest Service will allow First Step to complete the final network building requirements. The remaining 5% will be the final network testing and final turn up of the CAI's. | 100 | final permit release by the US Forest Service will allow First Step to complete the final network building requirements. | 95 | final permit release by the US Forest Service will allow First Step to complete the final network building requirements. Network testing occurs along with the network building and equipment deployment. | 2012-11-21 14:27 | 2012-11-21 14:27 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2012 | Q4 | Q4 - 2012 | 8752 | 7548 | FALSE | 75 | First Step anticipates that they will be 100% completed with all key project indicators and planned construction activities. First Step anticipates being under budget with all key project indicators met. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 2013-02-13 13:46 | 2013-02-13 13:46 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2013 | Q1 | Q1 - 2013 | 9226 | 8051 | FALSE | 82 | First Step anticipates the final approvals to move forward with the pending AAR for route modifications / additions. If this approval is giving timely, work on the additional paths should be completed within the quarter. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 2013-04-23 14:10 | 2013-04-23 14:10 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2013 | Q2 | Q2 - 2013 | 10586 | 8950 | FALSE | 83 | First Step anticipates the final approvals to move forward with the pending AAR for route modifications / additions. If this approval is giving timely, work on the additional paths should be completed within the quarter. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 2013-08-14 17:38 | 2013-08-14 17:38 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2013 | Q3 | Q3 - 2013 | 11320 | 9460 | FALSE | 92 | First Step anticipates the final approvals to move forward with the pending AAR for route modifications / additions. | 0 | n/a | n/a | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 2013-11-21 10:29 | 2013-11-21 10:29 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | 2013 | Q4 | Q4 - 2013 | 11816 | 9994 | FALSE | 92 | First Step anticipates the final approvals to move forward with the pending AAR for route modifications / additions. | 0 | n/a | n/a | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 2014-02-13 17:22 | 2014-02-13 17:22 | 5543 | 5543 | First Step Internet, L.L.C. | TRUE
NT10BIX5570053 | 2010 | Q2 | Q2 - 2010 | 74 | 1299 | FALSE | 3 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 1.77 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2010 | Q3 | Q3 - 2010 | 462 | 1497 | FALSE | 45 | Project Implementation begins for two projects. | 17 | Travel/Training/Conversion Strategy | Inter-island travel due to site inspection and project implementation. | 0 | IT&E has received a Categorical Exclusion. | 74 | Network Design for other projects will continue. | 0 | IT&E has received a Categorical Exclusion. No work will be done in the Rights of Way. | 50 | FCC License is anticipated to be completed. | 57 | Site preparation work will continue. | 38 | Equipment and Materials for other projects will be procured. | 3 | Project Implementation begins. | 0 | N/A | 0 | N/A | 2010-11-30 18:53 | 2010-11-30 18:53 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2010 | Q4 | Q4 - 2010 | 1064 | 2099 | FALSE | 57 | Project Implementation continues for two projects. | 20 | TRAVEL/TRAINING/CONVERSION STRATEGY | Inter-island travel due to project implementation and site survey will continue. | 0 | IT&E has received a Categorical Exclusion. | 95 | Network Design will continue. | 0 | IT&E has received a Categorical Exclusion. No work will be done in the Rights of Way. | 37 | FCC License applications will be submitted for approval. | 40 | Site preparation will commence for two projects. | 45 | Equipment is expected to arrive for two projects. | 26 | Project Implementation continues. | 29 | Equipment Deployment will continue. | 12 | Testing of equipment will continue. | 2011-02-10 18:27 | 2011-02-10 18:27 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2011 | Q1 | Q1 - 2011 | 1996 | 2743 | FALSE | 88 | Project implementation will begin for the 29 Hops Project and the Inter-island Microwave Upgrade. | 41 | Training and Conversion Strategy | Inter-island travel due to project implementation will continue. Off-island training and on-site training will be conducted for different projects. | 0 | IT&E has received a Categorical Exclusion. | 97 | Prepaid Billing System Configuration will begin in June and should be completed by September. | 0 | IT&E has received a Categorical Exclusion. No work will be done in the Rights of Way. | 100 | FCC license approvals are expected to be received within three months. | 52 | Site preparation will continue for the 29 Hops Project and the Inter-island Microwave Project. | 100 | Remaining equipment for NOC and MPLS will be procured Q2 2011 | 29 | Build of 29 Hops Project and Inter-Island Microwave Upgrade will begin Q2 2011 | 30 | Equipment for 29 Hops Project and Inter-Island Microwave Upgrade will start Q2 2011 | 30 | Network testing will begin for 29 Hops Project and Inter-Island Microwave Upgrade as soon as equipment is installed. | 2011-05-13 03:52 | 2011-05-13 03:52 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2011 | Q2 | Q2 - 2011 | 3222 | 3372 | FALSE | 91 | Project Implementation will begin for the Prepaid Billing System. 29 Hops Project is expected to be completed this quarter. Inter-island Microwave Upgrade is anticipated to be at 80% complete. We hope to meet the 91% completion with our actual expenditures by the end of next quarter, but this is not expected since the Prepaid Billing project will not be completed until the end of December. We expect the 29 Hops to be 100% complete and the interisland Microwave Upgrade to be 90% complete by the end of the 3rd quarter, and the Prepaid Billing project to be 50% complete by this date. | 44 |  | Inter-island travel due to project implementation will continue. | 0 | IT&E has a Categorical Exclusion. | 97 | Prepaid Billing System Configuration continues. Postpaid Billing will begin. | 0 | IT&E has received a Categorical Exclusion. No work will be done in the Rights of Way. | 100 | All FCC License will be received. | 57 | Site preparation work will be completed for the Inter-Island Microwave Upgrade. | 100 | Postpaid Billing System RFP is expected to be issued. | 96 | Network Build continues is expected to be completed for the 29 Hops and the Inter-island Microwave Upgrade will be close to completion. | 57 | Equipment Deployment will continue for the 29 Hops and the Inter-island Microwave Upgrade. | 30 | Network Testing will continue for the 29 Hops and Inter-island Microwave Upgrade Projects. | 2011-08-18 23:20 | 2011-08-18 23:20 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2011 | Q3 | Q3 - 2011 | 4114 | 3900 | FALSE | 99 | Award of Postpaid Billing Project will be made. Testing of Prepaid Billing Project will begin late this quarter. These are the two remaining subprojects under this grant. | 89 |  | Interisland travel due to project implementation of the two remaining projects. | 0 | IT&E received a categorical exclusion. | 98 | Kick off of Postpaid Billing Project. | 0 | No work will be done in the Rights of Way. | 100 | FCC Licenses received. | 100 | Postpaid Billing Project will commence. | 100 | All equipment procurement is expected to be initiated. | 100 | Postpaid Billing Project will commence. | 100 | Postpaid Billing Project will commence. | 80 | Network Testing will be conducted for the Prepaid Billing Project. | 2011-11-17 14:57 | 2011-11-17 14:57 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2011 | Q4 | Q4 - 2011 | 4720 | 4369 | FALSE | 96 | Postpaid Billing Project will commence. | 93 |  | Travel inter-island will continue for Postpaid Billing Project and training. | 0 | IT&E received a categorical exclusion. | 98 | Postpaid Billing will commence. | 0 | No work will be done in ROW. | 100 | FCC licenses have been received. | 100 | All Site preparation work is expected to be completed. | 95 | Postpaid Billing Project Equipment required is expected to be procured. | 80 | Postpaid Billing Project will commence. | 95 | Prepaid Triggers expected to be installed. | 81 | Network testing expected to be completed for Prepaid Billing System this quarter. | 2012-01-30 16:13 | 2012-01-30 16:13 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2012 | Q1 | Q1 - 2012 | 5908 | 5553 | FALSE | 96 | Postpaid Billing Project will continue. | 85 |  | User Training will continue for Prepaid Billing Project. | 0 | IT&E received a categorical exclusion. | 100 | Network Design has been completed. | 0 | No work will be done in the ROW. | 100 | FCC licenses applied for have been received. | 100 | Site Preparation has been completed. | 100 | Equipment Procurement has been completed. | 90 | Postpaid Billing project will continue. | 97 | Hardware for Postpaid Billing will be installed. | 87 | User Testing continues for Prepaid Billing Project. | 2012-05-02 01:01 | 2012-05-02 01:01 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2012 | Q2 | Q2 - 2012 | 6844 | 6048 | FALSE | 98 | Postpaid Billing Project will continue. | 90 |  | Training (on-site support) will end this quarter for the Prepaid Billing Project. Travel for Postpaid Billing Projects between the islands. | 0 | IT&E received a categorical exclusion. | 100 | Systems Requirements Specifications will be completed. | 0 | No work will be done in the Rights of Way. | 100 | FCC licenses applied for have been received. | 100 | All Site Preparation work has been completed. | 100 | All Equipment has been procured. | 95 | Software Development and customization will continue based on the Systems Requirements Specifications (SRS). | 100 | Hardware for Postpaid Billing Project will be delivered to IT&E and installed at Data Network Operations Center (NOC). | 90 | Postpaid Billing Project software development will continue. | 2012-08-02 21:59 | 2012-08-02 21:59 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2012 | Q3 | Q3 - 2012 | 7854 | 6631 | FALSE | 99 | Postpaid Billing Project will continue. | 99 |  | Training (on-site support) will end this quarter for the Prepaid Billing Project. Travel for Postpaid Billing Projects between the islands. Training will commence. | 0 | IT&E received a categorical exclusion. | 100 | Systems Requirements Specifications completed. | 0 | No work will be done in the Rights of Way. | 100 | FCC licenses applied for have been received. | 100 | All Site Preparation work has been completed. | 100 | All Equipment has been procured. | 99 | Software Development and customization will continue based on the Systems Requirements Specifications (SRS). Data migration will continue. | 100 | All equipment deployed. | 99 | ATP Testing will commence. | 2012-11-13 23:02 | 2012-11-13 23:02 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2012 | Q4 | Q4 - 2012 | 8690 | 7504 | FALSE | 100 | Postpaid Billing Project completed. | 100 |  | Training completed. | 0 | IT&E received a categorical exclusion. | 100 | Network design completed. | 0 | No work done in the rights of way. | 100 | All FCC licenses approved and received. | 100 | Site Preparation completed. | 100 | All Equipment Procured. | 100 | Build completed. | 100 | All Equipment Deployed. | 100 | Testing Completed. | 2013-02-11 01:55 | 2013-02-11 01:55 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | 2013 | Q1 | Q1 - 2013 | 11392 | 9504 | FALSE | 100 | Project Completed. Grant Award expired 2/28/13. | 100 |  | Project Completed. Grant Award expired 2/28/13. | 0 | n/a | 100 | Project Completed. Grant Award expired 2/28/13. | 0 | n/a | 100 | Project Completed. Grant Award expired 2/28/13. | 100 | Project Completed. Grant Award expired 2/28/13. | 100 | Project Completed. Grant Award expired 2/28/13. | 100 | Project Completed. Grant Award expired 2/28/13. | 100 | Project Completed. Grant Award expired 2/28/13. | 100 | Project Completed. Grant Award expired 2/28/13. | 2013-11-26 13:24 | 2013-11-26 13:24 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570054 | 2010 | Q2 | Q2 - 2010 | 75 | 1321 | FALSE | [23 empty] | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2010 | Q3 | Q3 - 2010 | 226 | 1379 | FALSE | 5 | See comments in #3 below | 0 |  | NA | 98 | See comments in #3 below | 2 | See comments in #3 below | 1 | See comments in #3 below | 0 | See comments in #3 below | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-10-29 12:49 | 2010-10-29 12:49 | 5552 | 5552 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2010 | Q4 | Q4 - 2010 | 1386 | 2397 | FALSE | 15 | N/A | 0 |  | N/A | 100 | N/A | 25 | N/A | 30 | N/A | 35 | N/A | 0 | N/A | 15 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-28 13:37 | 2011-02-28 13:37 | 5552 | 5552 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2011 | Q1 | Q1 - 2011 | 1460 | 2443 | FALSE | 25 | Will not have received permissions from SVEC, Centurylink and VMRC nor railroads. | 0 | NA | NA | 100 | NA | 50 | No variance to baseline anticipated at this time, pending make ready operations in progress and no need for any changes in design. Point of Presence locations will have been approved. | 75 | no variance | 70 | Railroad permits will still be outstanding as well as VMRC permits. | 0 | NA | 40 | no variance | 20 | Will not have permissions to attach or construct anything other than one remote site POP. | 0 | no variance | 0 | no variance | 2011-04-22 14:35 | 2011-04-22 14:35 | 5552 | 5552 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2011 | Q2 | Q2 - 2011 | 3232 | 3377 | FALSE | 30 | Extremely high make ready costs will require change in deployment to an estimated 50% underground. Network redesign in progress as well as changes to permitting and environmental assessment. | 0 |  | N/A | 90 | Reinitiation of environmental consultations for areas changed to underground construction, amendment to EA in progress. Anticipated completion of the new EA is anticpated by the end of Q4 (Dec. 31, 2011). | 50 | Redesign of portions of network changing from aerial to underground construction. No change to route or route miles to be deployed. | 75 | Work will be in progress for solidifying pole agreement with electric cooperative and VDOT ROW due to a deployment modification. Anticipated completion of these agreements by the end of Q4. | 60 | Permitting in progress with VDOT for areas changed to underground deployment. | 0 | No Variance | 15 | Will not procure any more materials or equipment until design is finalized. | 0 | Redesign and permitting in progress, construction will not have started. | 0 | Equipment deployment delayed until after construction of fiber which will not have started in this quarter. | 0 | No Variance | 2011-08-19 13:25 | 2011-08-19 13:25 | 7118 | 7118 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2011 | Q3 | Q3 - 2011 | 4236 | 3966 | FALSE | 10 | Variance expected: The original baseline projected 95% completion in Qtr 4. During the next quarter it is anticipated that a revised design will be approved by NTIA and reconsultation for an environmental assessment amendment will be underway along with final construction design by the construction contractor Shentel. | 0 |  | N/A | 100 | Variance expected: This project's environmental assessment will be amended to remove tower construction, replace fiber backhaul with microwave, and move some areas of fiber construction from aerial to underground. No historic buildings will be modified, no new CAI last mile construction is proposed, and the underground construction will occur within department of transportation or town rights of way. During this quarter reinitiation of environmental consultations will be in progress. Anticipated completion of the new EA is anticipated before the end of Q1 2012. | 100 | No variance anticipated. Pending timely approval by NTIA of the project modification, redesign of portions of network changing from aerial to underground construction will be completed as significant portions of the design completed to date will not change. | 100 | No variance. Work will be in progress for solidifying pole agreement with electric cooperative and VDOT ROW due to a deployment modification. Anticipated completion of these agreements by the end of Q4. | 100 | No variance: Permitting in progress with VDOT for areas changed to underground deployment, and two railroad crossing permits will be complete. | 0 | No Variance | 0 | The baseline projections were developed prior to entering into contract for construction. Variance expected as the current contract for design and construction stipulate payments to contractor to be made at significant construction completion points. Some materials have already been procured by the contractor that would not be affected by the proposed modification. No further equipment will be procured by the contractor until design is complete, anticipate final equipment and materials to be procured by the contractor during Qtr 1 2012. | 1 | Variance: expected: The current unliquidated obligation in the amount of $30,745.91 for the Luray interconnection facility already constructed is expected to be expended in the next quarter. All other preconstruction activities and including reinitiation of consultation for an environmental assessment amendment will be in progress pending timely approval of project design modification. Further construction of network facilities not anticipated until Qtr 1 2012. | 0 | Variance expected: No deployment of equipment or materials will be in progress in the next quarter as preconstruction activities will be in progress pending timely approval of project design modification. | 0 | Variance expected; No network construction anticipated during this quarter due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, the PCBA was requested to submit a project modification to NTIA in October 2011 and anticipates only having the design complete by the end of Q4-2011 with construction slated to begin in Q1-2012. | 2011-11-22 16:56 | 2011-11-22 16:56 | 7118 | 7118 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2011 | Q4 | Q4 - 2011 | 5394 | 5077 | FALSE | 29 | Variance: During the next quarter it in anticipated that a revised design will be approved by NTIA and reconsultation for an environmental assessment amendment will be complete with final construction design by the construction contractor Shentel. | 0 |  | N/A | 100 | Variance expected: This project's environmental assessment will be amended to remove tower construction, replace fiber backhaul with microwave, and move some areas of fiber construction from aerial to underground. No historic buildings will be modified, no new CAI last mile construction is proposed, and the underground construction will occur within department of transportation or town rights of way. During this quarter reinitiation of environmental consultations will be in progress. Anticipated completion of the new EA is anticipated before the end of Q1 2012. | 100 | Variance: Baseline predicted original design at 100% completion by end of Qtr 4. Pending timely approval by NTIA of the project modification, redesign of portions of network changing from aerial to underground construction will be completed as significant portions of the design completed to date will not change. | 100 | No variance. Work will be in progress for solidifying pole agreement with electric cooperative and VDOT ROW due to a deployment modification. Anticipated completion of these agreements by the end of Q1-2012. | 100 | No variance: Permitting in progress with VDOT for areas changed to underground deployment, and two railroad crossing permits will be complete. | 0 | No Variance | 50 | Variance: Some materials have already been procured by the contractor that would not be affected by the proposed modification. No further equipment will be purchased until design is complete, anticipate final procurement to occur Qtr 2 2012. | 1 | Variance: No construction can be started until approval received, anticipate receiving Qtr 1 2012. | 0 | Variance in baseline due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, the PCBA was requested to submit a final project modification to NTIA in December 2011. | 0 | Variance: no network construction anticipated during this quarter due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, the PCBA was requested to submit a final project modification to NTIA in December 2011 and anticipates only having the design complete by the end of Q1-2012 with construction slated to begin in Q2-2012. | 2012-02-29 12:54 | 2012-02-29 12:54 | 7118 | 7118 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2012 | Q1 | Q1 - 2012 | 6268 | 5736 | FALSE | 50 | Variance: During the next quarter it is anticipated that a revised design will be complete and the reconsultation for an environmental assessment amendment will be approved with final construction design by the construction contractor Shentel. | 0 |  | N/A | 100 | We anticipate NTIA will approve the supplemental EA. | 100 | Baseline predicted original design at 100% completion by end of Qtr 4. Redesign of portions of network changing from aerial to underground construction will be completed. The microwave design and engineering will also be complete. | 100 | No Variance. Work will be in progress for solidifying pole agreement with electric cooperative and VDOT Right-of-Way (ROW) due to a deployment modification. Anticipated completion of these agreements by the end of Q2-2012. | 100 | No Variance: Permitting complete with VDOT for areas changed to underground deployment, and two railroad crossing permits will be complete. | 0 | No Variance | 75 | Some materials have already been procured by the contractor that would not be affected by the proposed modification approved in January 2012 by NTIA and the NOAA Grants Office. No further equipment will be purchased until design is complete, anticipate procurement to occur Qtr 2 and Qtr 3 2012. | 1 | Variance: No construction can be started until approval of EA amendment and final design is complete. Anticipated completion of these tasks is Q2-2012. Only the facility in Luray has been constructed (facility only no equipment). | 0 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. | 0 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012.The PCBA anticipates only having the design complete by the end of Q2-2012 with construction slated to begin in Q3-2012. | 2012-05-23 14:01 | 2012-05-23 14:01 | 7118 | 7118 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2012 | Q2 | Q2 - 2012 | 7144 | 6199 | FALSE | 85 | Variance: During the next quarter it is anticipated that a revised design will be approved, permits secured and rights of way and easements acquired. It is also anticipated that construction and make-ready work will be underway. | 0 |  | N/A | 90 | NTIA and the NOAA Grants Office approved the supplemental EA for the project modification approved in January 2012. A second proposed modification for Segment 4 in the Town of Shenandoah, including the EHP Checklist, will be submitted to NTIA with expected approval in Q3-2012. | 100 | The baseline predicted original design at 100% completion by end of Qtr 2. Redesign of portions of network changing from aerial to underground construction are completed. The microwave design and engineering is also complete. Segments 1-3 and 5 are complete and approved by the PCBA. Design for Segment 4 will be complete during the next quarter. | 100 | No Variance. Work will be complete for VDOT and other necessary Rights-of-Way (ROW). Additional easements are also being secured. Anticipated completion of these agreements by the end of July 2012. | 100 | No Variance: Permitting activities will be complete. | 0 | No Variance. | 100 | Some materials have already been procured by the contractor that would not be affected by the proposed modification approved in January 2012 by NTIA and the NOAA Grants Office. Further equipment will be purchased now that the design is complete, anticipate procurement complete in Qtr 3-2012. | 50 | Variance: Only the facility in Luray has been constructed (facility only no equipment) to date. The PCBA anticipates the network build to get underway in Qtr 3-2012. | 75 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. The PCBA anticipates equipment deployment to begin in Qtr 3-2012. | 0 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012.The PCBA anticipates only having the design approved with initial construction started in Q3-2012. Network testing expected to initiate in Q4-2012. | 2012-08-20 08:57 | 2012-08-20 08:57 | 7393 | 7393 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2012 | Q3 | Q3 - 2012 | 8136 | 6776 | FALSE | 89 | Variance: During the next quarter it is anticipated that construction will complete and make-ready work will be complete. Network testing will also be underway. | 0 |  | No Variance | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 0 | No Variance | 100 | Some materials have already been procured by the contractor that would not be affected by the proposed modification approved in January 2012 by NTIA and the NOAA Grants Office. 7 Anticipate procurement complete in Qtr 4-2012. | 95 | Variance: Only the facility in Luray has been constructed (facility only no equipment) to date. Construction and make-ready work are currently underway. The PCBA anticipates the network build to have substantial completion in Q4-2012. | 100 | No Variance. | 50 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. Network testing expected to initiate in Q4-2012 and be complete in Q1-2013. | 2012-11-29 11:33 | 2012-11-29 11:33 | 7393 | 7393 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2012 | Q4 | Q4 - 2012 | 9146 | 7962 | FALSE | 95 | Variance due to project modification. High make ready estimate from incumbent electric cooperative forcing redesign to reduce fiber deployment and move to microwave connectivity and to move some areas of construction from aerial to underground. Project modification approval in January 2012 by NTIA and NOAA Grants Office and work restarted to implement the project. | 0 | N/A | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2013-03-25 13:25 | 2013-03-25 13:25 | 7393 | 7393 | Page County Broadband Authority | TRUE
NT10BIX5570054 | 2013 | Q1 | Q1 - 2013 | 12154 | 10337 | FALSE | 83 | Variance due to project modification and left over funds. High make ready estimate from incumbent electric cooperative forcing redesign to reduce fiber deployment and move to microwave connectivity and to move some areas of construction from aerial to underground. Project modification approval in January 2012 by NTIA and NOAA Grants Office and work restarted to implement the project. Project was completed on February 28, 2013. | 0 | N/A | N/A | 59 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 45 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 10 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 23 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 100 | No Variance. | 47 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 100 | No Variance. Actuals from project inception through end of the current reporting period are 200% of the budget figures. Activity complete. | 100 | No Variance. Actuals from project inception through end of the current reporting period are 200% of the budget figures. Activity complete. | 45 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. . | 2014-05-01 09:03 | 2014-05-01 09:03 | 7393 | 7393 | Page County Broadband Authority | TRUE
NT10BIX5570055 | 2010 | Q2 | Q2 - 2010 | 76 | 1336 | FALSE | 15 |  | 0 |  |  | 100 |  | 100 |  | 75 |  | 75 |  | 5 |  | 25 |  | 5 |  | 0 |  | 0 |  | 2010-09-16 11:02 | 2010-09-16 11:02 | 0 | 0 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2010 | Q3 | Q3 - 2010 | 266 | 1399 | FALSE | 18 | Original projection was set at 15%. Expected construction start date moved ahead of schedule | 0 |  | No Variance | 100 | No Variation | 100 | No Variation | 75 | Projecting completion by next quarter | 100 | Projecting completion by next quarter | 10 | Projecting to begin construction this quarter | 50 | No Variance | 10 | Projecting to begin construction this quarter | 25 | Projecting to begin equipment deployment in conjunction with construction | 0 | No Variance | 2010-10-29 18:18 | 2010-10-29 18:18 | 5554 | 5554 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2010 | Q4 | Q4 - 2010 | 1176 | 2209 | FALSE | 20 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 75 | 100% of ROW has been completed for the Fiber Optic Backbone, Projecting completion of ROW for laterals and towers by end of quarter. | 100 | No Variance | 25 | No Variance | 75 | No Variance | 21 | No Variance | 10 | No Variance | 5 | No Variance | 2011-02-16 11:09 | 2011-02-16 11:09 | 5554 | 5554 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2011 | Q1 | Q1 - 2011 | 2190 | 2840 | FALSE | 18 | Reasons for the variance include the following: 1. Delays in make ready. To expedite the make ready work, NTUA will add crews from within NTUA or from contractors. 2. Additional RUS requirements for OPGW construction. To expedite the RUS approval, NTUA has worked with the RUS to complete the first span and created a model for subsequent spans. 3. Delays in obtaining state road crossing permits. To avoid work stoppage and further delays, the NTUA has instructed the contractor to continue with the build out and dead-end the fibers in areas where they have not obtained the permits. 4. Delays in obtaining all materials for fiber optic build out. To expedite the process, NTUA has instructed the vendors to deliver all hardware and cable in a lump sum rather than a phased approach. | 0 |  | No Variance | 95 | Variance is due to changes in the fiber optic route or tower locations which may require an additional environmental assessment | 100 | No Variance | 75 | Variance is due to the potential route changes that may require additional ROW assessment. | 75 | NTUA anticipated 100% completion of permits & approvals however variance will occur due to the delay in obtaining road crossing permits and Indian Allotment issues. In order to remedy the issues, NTUA has hired T&D Surveyors to expedite the road crossing permits and NTUA has hired a consultant to approach the land owners directly for Indian Allotment consent. | 50 | No Variance | 100 | No Variance | 18 | Reasons for the variance include the following: 1. Delays in make ready. To expedite the make ready work, NTUA will add crews from within NTUA or from contractors. 2. Additional RUS requirements for OPGW construction. To expedite the RUS approval, NTUA has worked with the RUS to complete the first span and created a model for subsequent spans. 3. Delays in obtaining state road crossing permits. To avoid work stoppage and further delays, the NTUA has instructed the contractor to continue with the build out and dead-end the fibers in areas where they have not obtained the permits. 4. Delays in obtaining all materials for fiber optic build out. To expedite the process, NTUA has instructed the vendors to deliver all hardware and cable in a lump sum rather than a phased approach. | 10 | Variance is due to previous delays in RFP process & finalizing service line agreements. | 10 | Variance is due to the previous construction and service line delays. | 2011-05-19 16:41 | 2011-05-19 16:41 | 5554 | 5554 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2011 | Q2 | Q2 - 2011 | 2972 | 3243 | FALSE | 26 | Variance is due to subsequent delays in Make Ready production as well as delays in tower construction. NTUA has acquired additional crews to assist with Make Ready and streamlined the tower RFP process to expedite build out. | 0 |  | - | 95 | Reasons for variance in the EA are due to changes in the location of towers that are outside the original EA. To start construction on the sites the following steps are required. 1. Further environment and cultural studies and final assessment 2. Acquire approvals from Fish & Wildlife 3. Submit changes to the NTIA for approval Formal environmental and cultural studies are currently under way and NTUA anticipates submitting an action award request for NTIA approval once NTUA obtain final results of the studies and approval from U.S. Fish and wildlife. | 100 | No Variance | 75 | Variance is due to changes in original network design which require additional ROW approvals. | 70 | Variance in construction permit approvals is due to delays in the submittal process. NTUA has submitted all permit applications required for New Mexico. Furthermore, NTUA hired T&D Contractors to expedite the development of profiles required for permit application in Arizona. NTUA will submit permit applications to the Arizona Department of Transportation in piecemeal fashion as they receive profiles for individual areas from T&D contractors. | 75 | No Variance | 75 | Variance is due to delays in network build out. | 30 | Variance is due to previous delays trickling down to the next quarter. NTUA has developed a process to increase production. | 15 | Variance is due to a lack of signed agreements. NTUA anticipates completion of critical agreements prior to the end of the quarter at which time equipment will be deployed in a phased approach. | 15 | Variance is due to delays in network build out and a lack of signed agreements. NTUA anticipates testing to begin during this quarter. | 2011-08-09 13:10 | 2011-08-09 13:10 | 5554 | 5554 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2011 | Q3 | Q3 - 2011 | 4354 | 4033 | FALSE | 45 | Reasons for variance from the baseline are as follows: 1. Delays in the overall project are due to subsequent delays in Make Ready production. To alleviate the delay, NTUA has hired additional contractors to assist. 2. Delays in obtaining Rural Utilities Service (RUS) approvals for transmission line work. NTUA in conjunction with their consultants are working directly with RUS to expedite the RUS approval process. 3. Delays in acquiring Indian Allotments approvals and Rights of Way. NTUA has taken a proactive approach to resolving the Indian Allotment issue including the various alternatives such as route change, gigabit laser, and utilizing existing microwave system as a temporary measure until approval is obtained. 4. Weather Delays |  |  | - | 95 | NTUA is currently in the process of performing an environmental assessment on 4 tower locations that were not covered in the original Findings of No Significant Impact (FONSI). NTUA anticipates completion of the assessment and submittal of Award Action Request to the NTIA by the end of the quarter. | 100 | No Variance | 75 | Variance in obtaining Rights of Way (ROW) is due to changes in Navajo Nation ROW process. To alleviate the problem, NTUA ROW agents / Government liaisons are working directly with the Navajo Nation & Arizona Department of Transportation to expedite approvals. | 75 | Variance in obtaining construction permits is due to delays in the submittal process. NTUA has submitted all permit applications required for New Mexico. Profiles required for Arizona permits are currently being developed. To expedite the process, NTUA hired T&D Contractors to assist in the development of profiles. T&D is currently working on the crucial, time-sensitive profiles and will submit to NTUA on a piecemeal basis for submission to the Arizona department of transportation. | 90 | No Variance | 85 | Variance is due to delays in microwave equipment deployment. Also, due to rapid changes in technology, NTUA has decided to delay purchase of laptops. | 45 | Variance is due to previous delays in fiber optic construction caused by sluggish Make Ready progress and lack of RUS approvals. | 35 | Variance is due to NTUA decision to delay procurement of last mile customer premise equipment due to technology changes | 40 | Variance is a consequence of previous delays in construction and microwave deployment | 2011-11-30 16:02 | 2011-11-30 16:02 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2011 | Q4 | Q4 - 2011 | 5286 | 4955 | FALSE | 74 | No Variance |  |  | - | 100 | No Variance | 100 | No Variance | 80 | Variance is due to the elongated process for obtaining easement rights for traversing Indian Allotments. NTUA has taken steps to expedite the allotment process including hiring additional consultants to approach the allottees. | 100 | No Variance | 100 | No Variance | 90 | Variance is due to the rapid changes in technology which has prompted NTUA to delay purchases of Netbooks. | 70 | No Variance | 65 | Variance is due to delays in procuring Microwave equipment and last mile customer premise equipment (CPE). | 70 | Variance is a consequence of previous delays in construction and the IRU agreement. | 2012-02-27 13:21 | 2012-02-27 13:21 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2012 | Q1 | Q1 - 2012 | 6314 | 5759 | FALSE | 74 | Variance will be due to the Indian Allotment issues. NTUA has hired a consultant to address the issue. |  |  | N/A | 100 | No Variance | 100 | No Variance | 85 | Variance is due to the elongated process for obtaining easement rights for traversing Indian Allotments. NTUA has taken steps to expedite the allotment process including hiring additional consultants to approach the allottees. | 100 | No Variance | 100 | No Variance | 90 | Variance will be due to delays in procuring the last mile dongles | 85 | Variance will be due to previous delays and potential delays in build out due to Indian Allotments. | 85 | Variance will be due to previous delays and potential delays in build out due to Indian Allotments. Deployment of the wireless links have a potential for delay depending on remaining tower construction. | 85 | Variance is a consequence of previous delays in construction | 2012-05-29 10:27 | 2012-05-29 10:27 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2012 | Q2 | Q2 - 2012 | 6864 | 6058 | FALSE | 90 | Variance might occur due to Indian Allotment Issues and tower construction. NTUA has developed a contingency plan regarding the allotments. |  |  | - | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 95 | Variance might occur due to Indian Allotment Issues and tower construction. NTUA has developed a contingency plan regarding the allotments. | 95 | Variance might occur due to Indian Allotment Issues and tower construction. NTUA has developed a contingency plan regarding the allotments. | 90 | Variance might occur as a consequence of previous delays in construction. | 2012-08-06 13:36 | 2012-08-06 13:36 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2012 | Q3 | Q3 - 2012 | 8120 | 6767 | FALSE | 97 | NTUA anticipates all construction and testing to be complete. A slight variance may occur due to weather related issues or a protracted approval process for the three towers that require NTIA approval. NTUA plans of utilizing the last quarter for auditing and close out procedures. |  |  |  | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 95 | Variance is due a couple of events including the following: 1. WESODI lost several employees due to the clean up efforts for Hurricane Sandy. 2. The accident at the Little Water Tower site will cause a delay of up to six weeks because a new piece of the tower had to be ordered. 3. Approval for the three remaining tower sites has not been acquired: Blue Gap, Houck, and Hole in the Rock. NTUA will require a minimum of 4 weeks to complete each tower. | 90 | Variance is due to delays in the network build. Equipment can not be deployed on towers that are incomplete. Furthermore, NTUA will require time for testing and configuration of the equipment once the network build is complete. | 100 | No Variance | 2012-11-28 15:51 | 2012-11-28 15:51 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2012 | Q4 | Q4 - 2012 | 8908 | 7691 | FALSE | 92 | Variance is due to previous delays in weather and tower construction which lead to delays in microwave link and 4G LTE installation and testing. |  |  | - | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 97 | Variance is due to previous delays in weather and tower construction which lead to delays in microwave link and 4G LTE installation and testing. | 96 | Variance is due to previous delays in weather and tower construction which lead to delays in microwave link and 4G LTE installation and testing. | 85 | Variance is due to delays in the equipment deployment | 2013-02-22 14:34 | 2013-02-22 14:34 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2013 | Q1 | Q1 - 2013 | 9940 | 8513 | FALSE | 99 | Variance due to the following: 1. Clean up process 2. Remaining Microwave Link installation at Escrito Mesa. 3. Close out process. |  |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 98 | Variance is anticipated due to an anticipated delay in the Escrito Mesa microwave link. The Escrito Mesa tower is a state funded project however the microwave equipment to be installed on the tower is funded by NTIA. NTUA anticipates the tower to be compete in August with the MW to be installed thereafter. | 100 | No Variance | 98 | Variance due to delayed LTE commissioning | 2013-05-28 15:28 | 2013-05-28 15:28 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2013 | Q2 | Q2 - 2013 | 10512 | 8908 | FALSE | 100 | No Variance |  |  |  | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-08-07 14:03 | 2013-08-07 14:03 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2013 | Q3 | Q3 - 2013 | 11370 | 9490 | FALSE | 100 | No Variance |  |  |  | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-11-25 10:46 | 2013-11-25 10:46 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | 2013 | Q4 | Q4 - 2013 | 12652 | 10935 | FALSE | 100 | No Variance | 100 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2015-01-29 11:43 | 2015-01-29 11:43 | 7302 | 7302 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570056 | 2010 | Q3 | Q3 - 2010 | 456 | 1494 | FALSE | 70 | N/A | 30 |  | Outreach to local libraries and other anchor institutions. | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 70 | N/A | 0 | N/A | 30 | N/A | 30 | N/A | 0 | N/A | 2010-11-30 15:38 | 2010-11-30 15:38 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | 2010 | Q4 | Q4 - 2010 | 1098 | 2138 | FALSE | 60 | Awaiting approval for tower/route change and winter weather delays--project will not be completed by March 31 as planned. | 30 |  | Awaiting approval for tower/route change and winter weather delays | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 70 | Awaiting approval for tower/route change and winter weather delays | 50 | Awaiting approval for tower/route change and winter weather delays | 50 | Awaiting approval for tower/route change and winter weather delays | 0 | Awaiting approval for tower/route change and winter weather delays | 2011-02-11 17:07 | 2011-02-11 17:07 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | 2011 | Q1 | Q1 - 2011 | 1876 | 2683 | FALSE | 1 | Previous Quarter miscalculated | 30 |  | Project on hold until asset sale completed | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-05-02 22:58 | 2011-05-02 22:58 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | 2011 | Q2 | Q2 - 2011 | 3102 | 3308 | FALSE | 1 | Asset Sale in process | 35 |  | Project on hold until asset sale completed | 100 | N/A | 100 | No Variance from Baseline | 35 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-08-15 21:55 | 2011-08-15 21:55 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | 2011 | Q3 | Q3 - 2011 | 3566 | 3557 | FALSE | 1 | Asset Sale in process | 35 |  | Project on hold until asset sale completed | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-10-28 00:54 | 2011-10-28 00:54 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | 2011 | Q4 | Q4 - 2011 | 5330 | 5002 | FALSE | 1 | Project on hold pending review of progress. | 35 |  | Project on hold pending review of progress. | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold pending review of progress. | 0 | Project on hold pending review of progress. | 0 | N/A | 0 | Project on hold pending review of progress. | 0 | Project on hold pending review of progress. | 0 | Project on hold pending review of progress. | 2012-02-28 08:50 | 2012-02-28 08:50 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | 2012 | Q1 | Q1 - 2012 | 5712 | 5453 | FALSE | 1 | Project has been terminated | 35 |  | Project has been termianted | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project has been termianted | 0 | Project has been termianted | 0 | N/A | 0 | Project has been termianted | 0 | Project has been termianted | 0 | Project has been termianted | 2012-04-29 21:49 | 2012-04-29 21:49 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2010 | Q3 | Q3 - 2010 | 458 | 1495 | FALSE | 30 | N/A | 30 |  | Outreach to local libraries and other anchor institutions | 100 | N/A | 30 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 20 | N/A | 20 | N/A | 0 | N/A | 2010-11-30 15:56 | 2010-11-30 15:56 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2010 | Q4 | Q4 - 2010 | 1114 | 2152 | FALSE | 60 | Will complete network design, rights of way, permitting, and equipment procurement. | 30 | Library outreach | Will continue library outreach and RFP response. | 100 | N/A | 100 | Will complete tower site logistics. | 100 | Will determine and request permits for rights of way. | 100 | Will request necessary permits. | 70 | Will finalize tower sites for construction. | 100 | Will order all equipment necessary for deployment. | 30 | Will commence network build. | 30 | Will commence equipment deployment. | 0 | N/A | 2011-02-11 18:03 | 2011-02-11 18:03 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2011 | Q1 | Q1 - 2011 | 1878 | 2684 | FALSE | 1 | Previous Quarter miscalculated | 30 |  | Will continue library outreach and RFP reponse | 100 | N/A | 100 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-05-02 23:01 | 2011-05-02 23:01 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2011 | Q2 | Q2 - 2011 | 3270 | 3397 | FALSE | 2 | Asset Sale in process | 35 |  | Project on hold until asset sale completed | 100 | N/A | 100 | No Variance from Baseline | 35 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-08-23 00:10 | 2011-08-23 00:10 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2011 | Q3 | Q3 - 2011 | 4320 | 4010 | FALSE | 1 | Asset Sale in process | 35 |  | Project on hold until asset sale completed | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-11-29 15:20 | 2011-11-29 15:20 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2011 | Q4 | Q4 - 2011 | 5332 | 5004 | FALSE | 1 | Project on hold pending progress review. | 35 |  | Project on hold pending progress review. | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | N/A | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 2012-02-28 08:58 | 2012-02-28 08:58 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | 2012 | Q1 | Q1 - 2012 | 5714 | 5454 | FALSE | 1 | Project has been terminated | 35 |  | Project has been terminated | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project has been terminated | 0 | Project has been terminated | 0 | Project has been terminated | 0 | Project has been terminated | 0 | Project has been terminated | 0 | Project has been terminated | 2012-04-29 21:51 | 2012-04-29 21:51 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570058 | 2010 | Q3 | Q3 - 2010 | 374 | 1453 | FALSE | 25 | Delay in drafting of engineering and construction projects have delayed RFQs and other bidding documents. Anticipate holidays to also influence delay in time-lines. | 0 | None | No Variance from baseline | 0 | N/A | 100 | No Variance from baseline | 100 | No Variance from baseline | 100 | No Variance from baseline | 0 | N/A | 100 | No Variance from baseline | 10 | Delay in engineering and construction documents have delayed project as a whole. Anticipate construction and equipment awards by the end of 3rd quarter, however also anticipate holidays to slow mobilization of contractor and delivery of equipment. | 0 | No Variance from baseline | 0 | No Variance from baseline | 2010-11-22 12:33 | 2010-11-22 12:33 | 5557 | 5557 | City of Williamstown | TRUE
NT10BIX5570058 | 2010 | Q4 | Q4 - 2010 | 1284 | 2309 | FALSE | 60 | Projection was estimate of project time line. Previous engineering, contract draft delays, and winter weather have created delays in overall project. Project is expected to proceed quickly, meeting projections as spring weather arrives. | 0 |  | No Variance from Baseline | 0 | N/A | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 0 | N/A | 95 | Projection was estimate of project time line. Previous engineering, contract draft delays, and winter weather have created delays in overall project. Project is expected to proceed quickly, meeting projections as spring weather arrives. | 60 | Projection was estimate of project time line. Previous engineering, contract draft delays, and winter weather have created delays in overall project. Project is expected to proceed quickly, meeting projections as spring weather arrives. | 50 | Projection was estimate of project time line. Previous engineering, contract draft delays, and winter weather have created delays in overall project. Project is expected to proceed quickly, meeting projections as spring weather arrives. | 0 | No Variance from Baseline | 2011-02-22 11:30 | 2011-02-22 11:30 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2011 | Q1 | Q1 - 2011 | 1964 | 2727 | FALSE | 99 | No variance from baseline | 0 |  | N/A | 0 | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 0 | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 70 | No variance from baseline | 2011-05-12 11:48 | 2011-05-12 11:54 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2011 | Q2 | Q2 - 2011 | 3346 | 3436 | FALSE | 100 | No variance from baseline. | 100 |  | By the end of quarter three of 2011 we should be 100 percent complete with the construction and testing, which will leave the customer installs and we should not have any problems meeting the baseline numbers for those. | 0 | n/a | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 0 | n/a | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2011-08-29 11:47 | 2011-08-29 11:47 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2011 | Q3 | Q3 - 2011 | 3990 | 3833 | FALSE | 100 | No variance from baseline. | 100 |  | Ahead of baseline, all equipment for customer registration/installs are purchased and paid for. We are still installing customers. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2011-11-11 12:05 | 2011-11-11 12:05 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2011 | Q4 | Q4 - 2011 | 5412 | 5096 | FALSE | 100 | No variance from baseline. | 100 |  | Slightly ahead of baseline due to being ready to install in earlier quarters that what was projected. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2012-02-29 15:35 | 2012-02-29 15:35 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2012 | Q1 | Q1 - 2012 | 6104 | 5654 | FALSE | 100 | No variance from base line. | 83 |  | Had 86 customers of the 103 in baseline at the end of reporting period, believe the economy has to do with the lower number. | 0 | N/A | 100 | No variance from base line. | 100 | No variance from base line. | 100 | No variance from base line. | 0 | N/A | 100 | No variance from base line. | 100 | No variance from base line. | 100 | No variance from base line. | 100 | No variance from base line. | 2012-05-15 15:09 | 2012-05-15 15:09 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2012 | Q2 | Q2 - 2012 | 6988 | 6121 | FALSE | 100 | No variance from baseline. | 83 | Subscribers | We still are at 86 subscribers however we have added subscribers this quarter the number is unchanged from last quarter due to people moving etc. Plus we feel it has to do with a poor economy and this being a very rural community. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2012-08-09 17:28 | 2012-08-09 17:28 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570058 | 2012 | Q3 | Q3 - 2012 | 7784 | 6593 | FALSE | 100 | No variance from baseline. | 100 | Subscribers | No variance from baseline. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2012-11-07 13:26 | 2012-11-07 13:26 | 6960 | 6960 | City of Williamstown | TRUE
NT10BIX5570059 | 2010 | Q3 | Q3 - 2010 | 424 | 1478 | FALSE | 2 | Based on grant expenditures for the project, baseline projections were estimated at 5%. Pend Oreille believes the project will be closer to 2% complete based on expenditures only. Expenditures in equipment and Network Build will not occur as anticipated. | 2 | Sales Tax | See narrative for 2a. above. | 100 | N/A | 80 | N/A | 40 | N/A | 70 | N/A | 0 | N/A | 0 | N/A | 0 | Based on potential weather delays, awarding of contracts, and anticipated FONSI receipt late in the quarter, it is not expected that any portion of the Network will be started in the 4th Q of 2010. | 0 | N/A | 0 | N/A | 2010-11-24 15:09 | 2010-11-24 15:09 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2010 | Q4 | Q4 - 2010 | 982 | 2025 | FALSE | 5 | No variance. | 5 | Sales Tax | No variance. | 100 | No variance. | 90 | Network design is near completion with finalization ahead of schedule. | 90 | No variance. | 60 | Some State and county permitting will need to be resolved with outstanding issues currently being completed. Additionally, the State Environmental Protection Act for Washington is currently being addressed for approval, which has extended the permitting process. | 40 | Staking and site preparation is on schedule according to our Baseline Report. | 20 | Equipment purchases, although in process, will be staggered to arrive as needed for project completion. | 2 | Network build may initiate this quarter, but minimally at best scenario. | 0 | No variance. | 0 | No variance. | 2011-02-04 15:49 | 2011-02-04 15:49 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2011 | Q1 | Q1 - 2011 | 2160 | 2825 | FALSE | 13 | 35-Overall expenditures lag baseline as a result of aggressive forecasting on our part when projecting out the anticipated process. | 0 | Sales Tax | 35-Sales tax will be incorporated into the expenditure detail at a future date. | 98 | 100-Environmental process is completed. | 40 | 80-This metric may not meet the expenditures as planned as the process and work appears to be on target. | 95 | 80-Rights of way acquistion process is substantially completed. Some minimal work may be necessary as we progress through the construction phase. | 50 | 95-Permitting work will continue as additional resources are utilized. This category may have been potentially over budgeted and may not meet the expenditures originally called out. | 30 | 40-Site preparation continues to lag as are deploying additional resources, thus expenditures, towards making up some of the lag in this particular metric. | 45 | 80-Preliminary equipment procurement budgets anticipated expenditures earlier in the project timeline, but will not occur until later in this calendar year. Expectations are to meet this metric by end of 2011. | 15 | 35-Network build was originally anticipated beginning earlier on in the project life cycle, and an original forecast of 30% being done over this past quarter. Although we are currently behind the baseline projections, we feel confident that this will be made up and the project completion will occur within the Broadband Technology Opportunities Program timeline. | 10 | 10-No variance. | 0 | 0-No variance. | 2011-05-19 09:44 | 2011-05-19 09:44 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2011 | Q2 | Q2 - 2011 | 2932 | 3223 | FALSE | 17 | Baseline 49-Overall expenditures lag baseline as a result of aggressive forecasting when doing the Baseline Report. A delay in the environmental process and Network design has led to a shortfall versus forecast in expenditures. | 0 | Sales Tax | 49-Sales tax will be incorporated into the expenditure detail at a future date. | 98 | 100- The Environmental process is complete. | 50 | 80-This category may not expend all that was budgeted as design of the network is near completion. | 95 | 80-Right of Way acquisition will be substantially complete by the end of Quarter 3, 2011. | 75 | 95-Permitting for the project will be close to completion by end of year 2011. Budgeted amounts may not be met, as minimal activity will be required next year. | 50 | 60-Site work continues as work towards completion of this metric will be completed by second quarter of 2012. | 9 | 80-Equipment Procurement will lag baseline projections as most equipment will be ordered and arriving late in 2011 or early in 2012. | 20 | 49-An aggressive Baseline projection and later than anticipated constructions start has created the variance in this metric. | 9 | 25-Baseline projections had indicated earlier arrival of equipment than is actually occurring. Equipment will be deployed upon arrival and slightly behind the procurement metric as we progress through the project time line. | 5 | 15- Network testing will commence once the Build is up and operational. As evidenced by the 5% forecast, some testing will occur in this period. | 2011-08-05 12:39 | 2011-08-05 12:39 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2011 | Q3 | Q3 - 2011 | 4062 | 3874 | FALSE | 30 | Baseline 62-LQ 20-The original Baseline projections called for over half of the project completed in first three quarters of year two of the project. Realistically, this was not attainable and current projections show us meeting Baseline at the end of year two. An adjusted project plan has been incorporated to include additional crews being added as necessitated by unforeseen circumstances. | 0 |  | 62-0-Sales tax will be implemented and segregated out at a future date. | 100 | 100-100-No Variance. | 80 | 80-50-No Variance. | 90 | 80-85-Exceeding Baseline. | 75 | 95-70-Permiting continues into the final year of the project with Baseline metrics met during quarter three of 2012. The permitting schedule was extended into year three to accomodate for the underground build section of the project. | 70 | 60-60-Exceeding Baseline. | 10 | 80-7- Original Baseline projections were inaccurate when depicting the timeline for Equipment Procurement. This process will continue into the final year of the project and lag Baseline until quarter two year three of the project. | 35 | 62-20-An aggressive initial start date from the Baseline has caused a lag in this metric. Projections now indicate meeting Baseline during the first half of 2012. Additional crews as well as favorable weather and conditions have allowed for expeditious construction. The current project plan anticipates requiring additional crews and completion on time. | 7 | 40-7-Equipment originally forecasted to be put in service will not be required until 2012. This metric will be attained during the final year of the project as equipment necessary for the project is utilized closer towards the end of the project life cycle. The revised project plan has this incorporated to this new timeframe. | 0 | 25-0-Network testing will occur once equipment is connected to the network and services are turned up. Attaining this metric will occur sometime during the final phase of the project. This is included as part of a revised project plan. | 2011-11-16 11:51 | 2011-11-16 11:51 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2011 | Q4 | Q4 - 2011 | 4642 | 4286 | FALSE | 36 | Baseline-69-LQ 29 The original Baseline projections called for over half of the project completed in first three quarters of year two of the project. Realistically, this was not attainable and current projections show us meeting Baseline at the end of year two. An adjusted project plan has been incorporated to include additional crews being added as necessitated by unforeseen circumstances. | 10 |  | 69-0 Sales tax is being implemented into the project as a seperate tracking metric. | 100 | 100-100 No Variance. | 90 | 90-65 No Variance. | 90 | 90-90 No Variance. | 85 | 95-80 Permiting continues into the final year of the project with Baseline metrics met during quarter three of 2012. The permitting schedule was extended into year three to accomodate for the underground build section of the project. | 75 | 60-70 Exceeding Baseline. | 15 | 90-10 Original Baseline projections were inaccurate when depicting the timeline for Equipment Procurement. This process will continue into the final year of the project and lag Baseline until quarter two year three of the project. | 55 | 69-30 An aggressive initial start date from the Baseline has caused a lag in this metric. Projections now indicate meeting Baseline during the first half of 2012. Additional crews as well as favorable weather and conditions have allowed for expeditious construction. The current project plan anticipates requiring additional crews and completion on time. | 15 | 50-10 Equipment originally forecasted to be put in service will not be required until 2012. This metric will be attained during the final year of the project as equipment necessary for the project is utilized closer towards the end of the project life cycle. The revised project plan has this incorporated to this new timeframe. | 0 | 30-0 Network testing will occur once equipment is connected to the network and services are turned up. Attaining this metric will occur sometime during the final phase of the project. This is included as part of a revised project plan. | 2012-01-30 11:54 | 2012-01-30 11:54 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2012 | Q1 | Q1 - 2012 | 6114 | 5659 | FALSE | 45 | LQ 32 Baseline 87 By design the last and most costly phase of the project, the underground portion, will be completed in the last three quarters of 2012. Original Baseline projections did not account for this or the equipment purchases late in the project timeline. | 2 |  | 1-87 Sales tax will be incorporated as additional equipment is purchased and | 100 | 100-100 No Variation. | 80 | 70-90 Final design changes or completions will be left at the end of the second quartr of 2012. Minimal design work will remain that needs to be accomplished. | 98 | 95-90 Exceeding Baseline. | 95 | 90-95 No Variance. | 90 | 85-80 Exceeding Baseline. | 20 | 10-90 Equipment projections were inaccurate when depicting the timeline for equipment procurement. This process will continue throughout the 2012 calendar year and likely miss this metric until the final reporting period. | 60 | 45-87 Earlier projections had construction starting earlier than actually occurred. With the delays experienced along the way, the network build has ultimately been delayed and compressed into a shorter time frame. This metric will be met as we approach the final months of the project. | 15 | 10-60 Equipment deployment was originally forecasted to take place much earlier. Due to network and system designs, it wasn't necessary to deploy until the final year of the project time frame. This metric will be attained in the final months of the project. | 0 | 0-40 Network testing will occur once equipment is installed and connected to the network. Services will be offered once this is completed and is part of the revised plan. | 2012-05-15 17:16 | 2012-05-15 17:16 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2012 | Q2 | Q2 - 2012 | 6834 | 6043 | FALSE | 72 | LQ40-BL94 By design the last and most costly phase of the project, the underground build, is in full production now as we approach the quarter of the year 2012. | 1 | Sales Tax | 1-94 Sales tax will be incorporated as additional equipment is purchase | 100 | 100-100 No Variance. | 90 | 90-90 No Variance. | 100 | 98-90 No Variance. | 100 | 95-95 Exceeding Baseline | 95 | 90-90 Exceeding Baseline. | 75 | 40-90 Equipment procurement was intentionally delayed until the final year of the project life cycle. Purchases will not meet this metric until the final reporting quarter for this metric. | 80 | 70-94 Earlier projections had estimated an earlier start to construction, but a prolonged environmental process and fiber shipments has extended out the project completion rate. The aerial build will near completion this quarter as well as the make ready work. Underground construction will forge ahead with completion scheduled for the first quarter of 2013. | 40 | 15-70 Equipment orders placed are scheduled for arrival during the third and fourth quarters of 2012. Equipment will be installed upon arrival and as the network build allows. this metric will be attained in the first quarter of 2013. | 10 | 0-60 Network testing is scheduled to begin as soon as equipment is installed and is anticipated to reach Baseline projections in the fourth quarter of 2012. | 2012-08-02 10:30 | 2012-08-02 10:30 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2012 | Q3 | Q3 - 2012 | 8058 | 6735 | FALSE | 80 | LQ-65 BL-97 By design the last and most costly phase of the project, the underground build, is in full production now as we approach the final quarter of the year 2012. This metric will be attained in Q1 2013. | 1 | Taxes | 1-97 Sales tax will be incorporated as Equipment purchases are booked to the project. | 100 | 100-100 No Variance. | 100 | 100-100 No Variance. | 100 | 100-90 No Variance. | 100 | 98-100 No Variance. | 100 | 95-100 No Variance. | 81 | 40-95 Equipment procurement was intentionally delayed until the final year of the project life cycle. This metric will be attained in Q1 2013. | 90 | 70-97 Earlier projections had estimated an earlier start to construction, but a prolonged environmental process and fiber shipments has extended out the project completion rate. The aerial build will near completion this quarter as well as the make ready work. Underground construction will forge ahead with completion scheduled for the first quarter of 2013. | 75 | 70-80 Equipment orders placed are scheduled for arrival during the third and fourth quarters of 2012. Equipment will be installed upon arrival and as the network build allows. This metric will be attained in the first quarter of 2013. | 75 | 70-80 Network testing is scheduled to begin as soon as equipment is installed and is anticipated to reach Baseline projections in the first quarter of 2013. | 2012-11-26 17:52 | 2012-11-26 17:52 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2012 | Q4 | Q4 - 2012 | 8774 | 7567 | FALSE | 95 | LQ-90- BL-100 Lagging in expenditures for the final phase of the project as it is anticipated to hit this metric by the end of Q2 2013. | 1 | Sales Tax | 1-100 Sales tax has been included in the line item in which it pertains to in the above categories. | 100 | 100-100 No Variance. | 100 | 100-100 No Variance. | 100 | 100-100 No Variance. | 100 | 99-100 No Variance. | 100 | 98-100 No Variance. | 100 | 91-100 No Variance. | 90 | 85-100 The network build will continue as weather has hampered the underground construction phase this past quarter. It is anticipated to complete end of Q2 2013. | 80 | 65-100 Final equipment deployment is anticipated to be installed during the Q2 2013 timeframe. | 80 | 40-100 Final Network Testing will be completed as we progress through the remaining sections of the Network Build and as remaining equipment is installed. It is anticipated to complete this by the end of Q2 2013. | 2013-02-14 10:33 | 2013-02-14 10:33 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2013 | Q1 | Q1 - 2013 | 9842 | 8457 | FALSE | 98 | With the project extension now in place, the project is anticipated to complete construction well before the end of the third quarter. Final expenditures will be anticipated in quarter 3 of 2013. Closeout activities will be finalized during the fourth quarter of 2013. | 1 |  | 1-100 Sales tax has been included in the line item in which it pertains to in the above categories. | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 98 | 85-100 The network build will continue as weather has hampered the underground construction phase this past quarter. It is anticipated to complete all construction by the end of July. | 90 | 65-100 Final equipment deployment is anticipated to be installed during the Q2 2013 timeframe. | 60 | 40-100 Final Network Testing will be completed as we progress through the remaining sections of the Network Build and as remaining equipment is installed. It is anticipated to complete this by the end of Q2 2013. | 2013-05-21 10:02 | 2013-05-21 10:02 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2013 | Q2 | Q2 - 2013 | 10764 | 9047 | FALSE | 100 | No Variance. | 0 | N/A | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2013-08-27 14:21 | 2013-08-27 14:21 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | 2013 | Q3 | Q3 - 2013 | 12080 | 10241 | FALSE | 100 | Project is completed. | 0 | N/A | N/A | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 2014-04-25 16:49 | 2014-04-25 16:49 | 5560 | 5560 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570060 | 2010 | Q3 | Q3 - 2010 | 324 | 1428 | FALSE | 13 | - | 0 |  | N/A | 100 | Completed and submitted. | 100 | - | 0 | N/A | 100 | - | 13 | - | 56 | - | 13 | - | 13 | - | 13 | - | 2010-11-16 10:29 | 2010-11-16 10:29 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2010 | Q4 | Q4 - 2010 | 1216 | 2247 | FALSE | 18 | Project was significantly delayed while waiting for FONSI approval | 0 | 0 | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed & approved | 20 | Project was significantly delayed while waiting for FONSI approval | 30 | In Q4, our intention was to order and invoice all the equipment at once. In the 1st Q of 2011, the ordering of all equipment will continue as planned, but it will be invoiced and shipped only as needed, instead of being invoiced and shipped all at once. Therefore, only 30% will be completed next quarter. | 18 | Project was significantly delayed while waiting for FONSI approval | 13 | Project was significantly delayed while waiting for FONSI approval | 13 | Project was significantly delayed while waiting for FONSI approval | 2011-02-18 11:18 | 2011-02-18 11:18 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2011 | Q1 | Q1 - 2011 | 2012 | 2751 | FALSE | 35 | Project was significantly delayed while waiting for FONSI approval | 0 |  | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 40 | Project was significantly delayed while waiting for FONSI approval | 30 | Pine Telephone company plans to have 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 20 | Pine Telephone company plans to have 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 15 | Pine Telephone company plans to have 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 10 | Pine Telephone company plans to have 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 2011-05-13 13:35 | 2011-05-13 13:35 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2011 | Q2 | Q2 - 2011 | 3054 | 3284 | FALSE | 25 | The method of calculating next quarter's project completion is based on overall expenditures. Some payment terms with vendors will occur after the system is up and running which will show project completion to be lower than actual completion. | 0 |  | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 75 | - | 30 | Pine Telephone Company has 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 25 | Pine Telephone Company has 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 15 | Pine Telephone Company has 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 15 | Pine Telephone Company has 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 2011-08-12 15:33 | 2011-08-12 15:33 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2011 | Q3 | Q3 - 2011 | 3954 | 3815 | FALSE | 60 | - | 0 |  | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 90 | - | 65 | - | 60 | - | 45 | - | 40 | - | 2011-11-10 11:18 | 2011-11-10 11:18 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2011 | Q4 | Q4 - 2011 | 4968 | 4642 | FALSE | 74 | The reason for overall completion lagging behind milestone completion is because Pine Telephone Company will not pay equipment vendors until after it is up and running. | 0 | true | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 95 | - | 90 | - | 80 | - | 80 | - | 80 | - | 2012-02-13 12:20 | 2012-02-13 12:20 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2012 | Q1 | Q1 - 2012 | 5998 | 5598 | FALSE | 80 | Pine Telephone Company (PTC) expects to be complete, but is running under budget and is seeking permission to add new sites within the proposed funded service areas (PFSAs) to improve service. | 0 |  | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 100 | Completed | 90 | - | 95 | - | 90 | - | 80 | - | 2012-05-09 17:28 | 2012-05-09 17:28 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2012 | Q2 | Q2 - 2012 | 7064 | 6159 | FALSE | 80 | Pine Telephone Company (PTC) expects to be complete, but is running under budget and is seeking permission to add new sites within the proposed funded service areas (PFSAs) to improve service. | 0 |  | N/A | 100 | Completed and submitted | 100 | Complete | 0 | N/A | 100 | Completed and approved | 100 | Completed | 90 | - | 95 | - | 95 | - | 90 | - | 2012-08-14 16:23 | 2012-08-14 16:23 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2012 | Q3 | Q3 - 2012 | 7838 | 6623 | FALSE | 80 | Pine Telephone Company (PTC) expects to be complete, but is running under budget and is seeking permission to add new sites within the proposed funded service areas (PFSAs) to improve service. | 0 |  | N/A | 100 | Completed and submitted | 100 | Complete | 0 | N/A | 100 | Completed and approved | 100 | Complete | 90 | - | 95 | - | 95 | - | 90 | - | 2012-11-13 09:48 | 2012-11-13 09:48 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2012 | Q4 | Q4 - 2012 | 8440 | 7144 | FALSE | 87 | Pine Telephone Company (PTC) is running under budget and is seeking permission to add new sites within the proposed funded service areas (PFSAs) to improve service. | 0 |  | N/A | 100 | Completed and submitted | 100 | Complete | 0 | N/A | 100 | Completed and approved | 100 | Complete | 90 | N/A | 95 | N/A | 95 | N/A | 90 | N/A | 2013-01-30 11:57 | 2013-01-30 11:57 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2013 | Q1 | Q1 - 2013 | 9756 | 8412 | FALSE | 100 | Pine Telephone Company has just received approval to add new sites within the proposed funded service areas (PFSAs) for improved service. | 0 |  | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2013-05-16 09:33 | 2013-05-16 09:33 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | 2013 | Q2 | Q2 - 2013 | 12048 | 10206 | FALSE | 100 | Completed | 0 | true | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2014-04-18 13:22 | 2014-04-18 13:22 | 5564 | 5564 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570062 | 2010 | Q3 | Q3 - 2010 | 460 | 1496 | FALSE | 30 | N/A | 30 |  | Outreach to local libraries and other anchor institutions | 100 | N/A | 30 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 20 | N/A | 20 | N/A | 0 | N/A | 2010-11-30 15:58 | 2010-11-30 15:58 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | 2010 | Q4 | Q4 - 2010 | 1108 | 2147 | FALSE | 60 | Will complete network design, rights of way, permitting, and equipment procurement. | 30 | Library outreach | Will continue library outreach and RFP responses. | 100 | N/A | 100 | Will finalize tower site logistics. | 100 | Will determine and request permits for rights of way. | 100 | Will request necessary permits. | 70 | Will finalize tower sites for construction. | 100 | Will order all equipment necessary for deployment. | 30 | Will commence network build. | 30 | Will commence equipment deployment. | 0 | N/A | 2011-02-11 17:44 | 2011-02-11 17:44 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | 2011 | Q1 | Q1 - 2011 | 2394 | 2942 | FALSE | 1 | Previous Quarter miscalculated | 30 |  | Will continue library outreach and RFP reponse | 100 | N/A | 100 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-05-30 22:26 | 2011-05-30 22:26 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | 2011 | Q2 | Q2 - 2011 | 3104 | 3309 | FALSE | 1 | Asset Sale in process | 35 |  | Project on hold until asset sale completed | 100 | N/A | 100 | No Variance from Baseline | 35 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-08-15 21:57 | 2011-08-15 21:57 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | 2011 | Q3 | Q3 - 2011 | 4322 | 4011 | FALSE | 1 | Asset Sale in process | 35 |  | Project on hold until asset sale completed | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-11-29 15:23 | 2011-11-29 15:23 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | 2011 | Q4 | Q4 - 2011 | 5334 | 5007 | FALSE | 1 | Project on hold pending progress review. | 35 |  | Project on hold pending progress review. | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | N/A | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 2012-02-28 09:01 | 2012-02-28 09:01 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | 2012 | Q1 | Q1 - 2012 | 5716 | 5455 | FALSE | 1 | Project has been terminated | 35 |  | Project has been terminated | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project has been terminated | 0 | Project has been terminated | 0 | N/A | 0 | Project has been terminated | 0 | Project has been terminated | 0 | Project has been terminated | 2012-04-29 21:52 | 2012-04-29 21:52 | 5559 | 5559 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570065 | 2010 | Q3 | Q3 - 2010 | 160 | 1346 | FALSE | 19 | No variance | 0 | N/A | N/A | 60 | No variance | 100 | No variance | 0 | N/A | 25 | No variance | 0 | No variance | 80 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2010-10-27 09:05 | 2010-10-27 09:05 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2010 | Q4 | Q4 - 2010 | 1320 | 2344 | FALSE | 35 | No variance | 0 | N/A | N/A | 0 | No variance | 84 | No variance | 0 | N/A | 0 | No variance | 48 | No variance | 100 | No variance | 0 | No variance | 6 | No variance | 39 | No variance | 2011-02-23 07:27 | 2011-02-23 07:27 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2011 | Q1 | Q1 - 2011 | 1542 | 2488 | FALSE | 57 | No variance | 0 |  | N/A | 100 | No variance | 100 | No variance | 0 | N/A | 0 | No variance | 66 | No variance | 100 | No variance | 44 | No variance | 10 | No variance | 39 | No variance | 2011-04-27 16:44 | 2011-04-27 16:44 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2011 | Q2 | Q2 - 2011 | 3358 | 3442 | FALSE | 32 | The overall project percentage completion has changed due to the reasons stated below. | 0 |  | N/A | 100 | No variance | 32 | There is a variance in this category for next quarter. Airspan, the WiMax vendor procured by BIT for this project has created a propagation map and has completed the site surveys for all of the 35 towers. During the surveys it became apparent that some of the sites are structurally inadequate. BIT is therefore, in the process of changing these five (5) tower locations and securing approval for this change. | 0 | N/A | 0 | There is a variance in this category for next quarter. BIT is currently working on the permits and approvals for the tower sites. The site surveys have been completed by our vendor, Airspan, and BIT has finalized the sites for the WiMax equipment. Until the sites were cleared after the site surveys BIT did not want to begin the permitting process. | 0 | There is a variance in this category for next quarter. BIT is currently working on the site preparation for the tower sites. The site surveys have been completed by our vendor, Airspan, and BIT has finalized the sites for the WiMax equipment. Until the sites were cleared after the site surveys BIT did not want to begin the site preparation. | 100 | No variance | 16 | The equipment BIT originally anticipated receiving in quarter 3, 2011 will be sent to BIT's facilities in quarter 4, 2011. Therefore, the percentage completion for this category has been changed for quarter 4, 2011. | 1 | The equipment BIT originally anticipated receiving in quarter 3, 2011 will be sent to BIT's facilities in quarter 4, 2011. Therefore, the percentage completion for this category has been changed for quarter 4, 2011. | 3 | The equipment BIT originally anticipated receiving in quarter 3, 2011 will be sent to BIT's facilities in quarter 4, 2011. Therefore, the percentage completion for this category has been changed for quarter 4, 2011. | 2011-08-29 16:26 | 2011-08-29 16:26 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2011 | Q3 | Q3 - 2011 | 4090 | 3888 | FALSE | 42 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance | 22 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This has not been completed due to the fact that some of the towers are structurally inadequate to hold the WiMax equipment. BIT has submitted a request for approval of the sites identified as alternates, but has not yet received approval from NTIA from the Environmental Division. As soon as approval for the alternate sites is granted work will resume on the propagation maps. BIT anticipates receiving approval during this quarter, but the work on the propagation map has been postponed until the approval is obtained. Therefore, the map completion is scheduled for the first quarter in 2012. The percent complete is based on total dollars spent, and therefore won't increase until the maps have been updated. | 0 | N/A | 64 | There is only a slight variance anticipated for construction permits, but this category is expected to meet the baseline projections for quarter one 2012. | 48 | The percent complete per category is based on total dollars spent. However, the billing of the site preparation work will be billed after the work has been completed. BIT anticipates receiving invoices for these services late next quarter, which will be paid early the following quarter. Therefore, the category will not change next quarter since the dollars will not be spent until the first quarter of 2012. | 100 | No variance | 47 | Since BIT is waiting for environmental approval on the towers that are being switched out this category will be slightly behind next quarter, but will catch up by the first quarter in 2012. BIT has already discussed an expedited process for the network build-out with their contractors, who, in turn, have identified multiple crews that can be pulled in to expedite the build process. | 2 | The percent complete per category is based on total dollars spent. This category is comprised of project management services as well as training, maintenance and installation services. Most of this is invoiced after each of the sites has been commissioned and tested. Since BIT's build-out will begin during this quarter, expenses for this category are not anticipated until the first quarter of 2012. Therefore, the category will not change next quarter since the dollars will not be spent until the first quarter of 2012. | 6 | The percent complete per category is based on total dollars spent. Since BIT's build-out will begin during this quarter, expenses for this category are not anticipated until the first quarter of 2012. Therefore, the category will not change next quarter since the dollars will not be spent until the first quarter of 2012. | 2011-11-16 16:15 | 2011-11-18 13:37 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2011 | Q4 | Q4 - 2011 | 5180 | 4843 | FALSE | 67 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance. | 45 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This map has not been complete due to the fact that some of the towers are structurally inadequate to hold the WiMax equipment. BIT submitted a request for approval of the sites identified as alternates, but did not receive approval through the Environmental Assessment process until December 27, 2011. Now that the alternative sites are approved work will continue on the propagation maps. Additionally, the As Built drawings will be prepared once each tower has been completed. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of the quarter. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 72 | BIT anticipates completing 24 of the total 35 towers by the end of next quarter. | 30 | BIT anticipates completing 24 of the total 35 towers by the end of next quarter. | 6 | BIT anticipates completing 24 of the total 35 towers by the end of next quarter. Network testing will begin as each tower is completed. | 2012-02-21 17:34 | 2012-02-21 17:34 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2012 | Q1 | Q1 - 2012 | 5962 | 5580 | FALSE | 79 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance. | 45 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This map has been completed for the portion of the network that has been deployed. These maps will not be complete until the remaining sites are installed at the end of 2012 and will be billed together at that time. Until it is invoiced and paid there will be a variance for this category. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of the quarter. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 75 | Buggs Island Telephone has completed the installation of WiMax equipment on 24 of the 35 towers. The remaining 10 sites will be constructed starting in quarter 3 of 2012. | 89 | Buggs Island Telephone has completed the installation of WiMax equipment on 24 of the 35 towers. The remaining 10 sites will be constructed starting in quarter 3 of 2012. | 54 | Buggs Island Telephone has completed the installation of WiMax equipment on 24 of the 35 towers. The remaining 10 sites will be constructed starting in quarter 3 of 2012. Once that equipment is installed testing will begin on the last 10 sites. | 2012-05-08 12:46 | 2012-05-08 12:46 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2012 | Q2 | Q2 - 2012 | 7118 | 6186 | FALSE | 80 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance. | 45 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This map has been completed for the portion of the network that has been deployed. These maps will not be complete until the remaining sites are installed at the end of 2012 and will be billed together at that time. Until it is invoiced and paid there will be a variance for this category. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of the quarter. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 78 | Buggs Island Telephone completed the installation of WiMax equipment on 24 of the 35 towers at the end of quarter one, 2012. The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter three, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter four, 2012 equipment will be installed on the remaining 11 sites. | 80 | Buggs Island Telephone completed the installation of WiMax equipment on 24 of the 35 towers at the end of quarter one, 2012. The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter three, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter four, 2012 equipment will be installed on the remaining 11 sites. | 6 | Buggs Island Telephone completed the installation of WiMax equipment on 24 of the 35 towers at the end of quarter one, 2012. The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter three, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter four, 2012 equipment will be installed on the remaining 11 sites. | 2012-08-17 16:13 | 2012-08-17 16:13 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2012 | Q3 | Q3 - 2012 | 7342 | 6304 | FALSE | 80 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance. | 63 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This map has been completed for the portion of the network that has been deployed. These maps will not be complete until the remaining sites are installed at the end of 2012 and will be billed together at that time. Until it is invoiced and paid there will be a variance for this category. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of the quarter. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 78 | Buggs Island Telephone completed the installation of WiMax equipment on 24 of the 35 towers at the end of quarter one, 2012. The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter four, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter one, 2013 equipment will be installed on the remaining 11 sites. | 79 | Buggs Island Telephone completed the installation of WiMax equipment on 24 of the 35 towers at the end of quarter one, 2012. The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter four, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter one, 2013 equipment will be installed on the remaining 11 sites. | 54 | Buggs Island Telephone completed the installation of WiMax equipment on 24 of the 35 towers at the end of quarter one, 2012. The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter four, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter one, 2013 equipment will be installed on the remaining 11 sites. | 2012-10-23 08:55 | 2012-10-23 08:55 | 5566 | 5566 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2012 | Q4 | Q4 - 2012 | 9092 | 7864 | FALSE | 80 | Projection of commercially ready to market service and final build-out of the additional 11 sites is undetermined. | 0 |  | N/A | 100 | No Variance | 80 | 3.65 network will be tested and accepted and 700 network will be re-designed. | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 80 | 3.65 network build completed and 700 network optimized. | 80 | 3.65 network build completed and 700 network optimized. | 56 | 3.65 network virtually tested and 700 network being re-configured. | 2013-02-28 15:45 | 2013-02-28 15:45 | 5565 | 5565 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2013 | Q1 | Q1 - 2013 | 10070 | 8593 | FALSE | 82 | WiMAX equipment was installed on 24 tower sites and tested. Extreme interference issues with neighboring companies using LTE technology resulted in Buggs Island Telephone, in coordination with the grant funding agencies, to abandon the WiMAX system and convert to a compatible LTE system if approved by NTIA. Due to limited grant funds remaining, the LTE build-out will cover a 5-county service area versus the original plans to cover a 15-county service area. Construction is projected to begin in Q3 of 2013. The project completion date was extended as a result of WiMAX interference and the need for additional time to deploy LTE. Costs to date reflect actual expenses incurred in constructing the WiMAX and 3.65 networks. The 3.65 network, consisting of six towers, is fully operational with testing and commercial launch to be implemented in Q2 of 2013. | 58 |  | The costs included in this category include 1) Admin and Legal, 2) Engineering -Project Management, 3) Project Inspection, 4) Monthly Tower Lease Payments, and 5) Monthly Backhaul Fees. The remaining funds in this category will be expended as the project proceeds over the next 6 to 8 months and these activities are implemented. | 100 | The Environmental Assessment is complete. | 77 | The 700 network is being re-designed due to interference issues. The 3.65 network is complete. The remaining funds will be used to design the LTE build-out in the 5-county service area if approved by NTIA. | 0 | Not Applicable | 100 | All construction permits have been acquired for the project. | 100 | It is expected that all costs associated with tower modifications to install the WiMAX equipment will be fully paid in Q2 of 2013. | 85 | Activities associated with the procurement of LTE equipment will be initiated in Q2 of 2013. | 0 | Not Applicable | 84 | The purchase and installation of LTE equipment will begin in Q3 of 2013. | 26 | Network testing was implemented on the WiMAX and 3.65 network. As noted previously, the WiMAX system will be abandoned and replaced with a LTE system if approved by NTIA. The 3.65 testing resulted in a successfully installed system that can be commercially launched. Additional costs are expected in this category to cover costs associated with the WiMAX and 3.65 testing and upcoming LTE testing once deployed. | 2013-06-21 14:50 | 2013-06-21 14:50 | 7685 | 7685 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2013 | Q2 | Q2 - 2013 | 10784 | 9061 | FALSE | 83 | WiMAX equipment was installed on 24 tower sites and tested. Extreme interference issues with neighboring companies using LTE technology resulted in Buggs Island Telephone, pending grant funding agency approval, developing plans to abandon the WiMAX system and converting to a compatible LTE system. Due to limited grant funds remaining, the LTE build-out will cover a 5-county service area versus the original plan to cover a 15-county service area. Construction is projected to begin in Q3-2013. The project completion date was extended as a result of WiMAX interference and the need for additional time to deploy LTE. Costs to date reflect actual expenses incurred in constructing the WiMAX and 3.65 networks. | 80 |  | The costs included in this category include 1) Admin and Legal, 2) Engineering -Project Management, 3) Project Inspection, 4) Monthly Tower Lease Payments, and 5) Monthly Backhaul Fees. The remaining funds in this category will be expended as the project proceeds over the next 6 months and these activities are implemented. | 100 | The Environmental Assessment is complete | 81 | The 700 network is being re-designed due to interference issues. The 3.65 network is complete. The remaining funds will be used to design the LTE build-out in the reduced 5-county service area pending NTIA approval. | 0 | Not Applicable | 100 | All construction permits have been acquired for this project. | 100 | No additional site work is anticipated for this project. | 90 | Activities associated with the procurement of LTE equipment have been initiated and a vendor will be selected after receiving authorization from NTIA to proceed. | 0 | Not Applicable | 83 | The purchase and installation of LTE equipment will begin in Q3-2013. | 70 | Network testing was implemented on the WiMAX and 3.65 network. As noted previously, the WiMAX system will be abandoned and replaced with a LTE system, contingent upon NTIA approval. The 3.65 testing resulted in a successfully installed system that has been commercially launched. Additional costs are expected in this category to cover expenses associated with the proposed LTE testing once deployed. | 2013-08-28 10:00 | 2013-08-28 10:00 | 7685 | 7685 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2013 | Q3 | Q3 - 2013 | 11336 | 9468 | FALSE | 86 | LTE contracts will be signed with vendors and the equipment order will be placed. The deployment of LTE equipment is projected to begin in Q1 2014 and will not be commercially launched until Q2 or Q3 2014. Decommissioning the WiMAX equipment from the terminated 24 tower sites continue and will be completed in Q4 2013. WiMAX equipment will continue to be put on the market for sale by the consignment company. | 58 | Legal/Admin/Tower Backhaul/Tower Lease/ Engineering Manaagament | Next quarter costs include the removal of WiMAX equipment, legal fees associated with contract reviews, ongoing monthly backhaul & lease fees, and general administrative and engineering activities. | 100 | The Environmental Assessment is complete. | 81 | The remaining funds will be used to design the LTE build-out in the 5-county service area. | 0 | Not Applicable | 99 | Additional permits will need to obtained for the installation of LTE equipment. | 100 | No additional site work is anticipated for this project. | 98 | The percentage increased due to the costs associated with procuring an LTE equipment vendor. | 0 | Not Applicable | 89 | Costs for LTE equipment is expected to occur in Q4-2013, thus the slight increase in percent complete. | 70 | Additional costs are expected in this category to cover expenses associated with LTE testing once deployed. Testing should begin in Q2 2014. | 2013-11-21 16:49 | 2013-11-21 16:49 | 7685 | 7685 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | 2013 | Q4 | Q4 - 2013 | 11794 | 9963 | FALSE | 87 | BIT originally projected that the deployment of the LTE network would be 100% completed by Q1 2014 but lengthy equipment vendor procurement and contract negotiations delayed the build-out time line. The deployment of LTE equipment is now projected to begin in Q2 2014. Because of this delay BIT's projection of signing up and installing beta testers will not begin until early Q3 2014 and will not be commercially launched until late Q3 2014. BIT will start marketing efforts in Q1 2014 in order to do customer pre-sales. | 54 |  | Next quarter costs include the removal of WiMAX equipment from the 10 tower sites, ongoing monthly back haul & lease fees, and general administration, management, and inspection fees. | 100 | BIT anticipates an environmental assessment for a new tower site that will be needed to replace one of the ten existing sites. Q4 2013 showed remaining funds in this category. | 83 | Engineering design fees continue as LTE build-out proceeds in the 5-county service area. | 0 | Not Applicable | 99 | Additional permits will need to obtained for the installation of LTE equipment. | 100 | Actual site preparation was 100% complete by the end of Q4 2013. BIT will have to do a structural analysis for a new tower site that will be needed to replace one of the ten existing sites. No funds remain in this category but a budget modification will be submitted during Q1 2014 where funds will be reallocated to this category. | 90 | Equipment procurement is complete. A budget amendment will be submitted prior to the next reporting period. | 0 | Not Applicable | 90 | Costs for LTE equipment purchase and deployment is expected to occur in Q1-2014. | 70 | Additional costs are expected in this category to cover expenses associated with LTE testing once deployed. | 2014-02-05 13:35 | 2014-02-05 13:35 | 7685 | 7685 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570066 | 2010 | Q4 | Q4 - 2010 | 1128 | 2167 | FALSE | 6 | No variance | 100 | Grant Prep | No variance | 100 | No variance | 23 | No variance | 15 | No variance | 100 | No variance | 7 | No variance | 20 | No variance | 4 | No variance | 15 | No variance | 1 | No variance | 2011-02-14 09:54 | 2011-02-14 09:59 | 5930 | 5930 | BVU Authority | TRUE
NT10BIX5570066 | 2011 | Q1 | Q1 - 2011 | 2168 | 2829 | FALSE | 33 | This percent complete is based on weighted amounts for each category, as shown in BVU's baseline report. | 100 | Grant Preparation | N/A | 100 | N/A | 30 | Lag during previous quarter | 65 | Based on changes in engineering, BVU does not expect that any PoP locations will have begun to be constructed by the end of Q2-2011; thus, this category will not change from the current reporting quarter. | 30 | All will be applied for, but not all will be received based on standard wait time and agency delays. National Forest Permits will have begun biological studies, and will hopefully have necessary studies completed by 6/30/2011. As noted in the current quarter's percentages, this category has decreased in percentage complete because of the way BVU is now tracking it. BVU had been tracking by activities complete; however, this does not match with expended dollars. To account for the difference in the two, BVU has decided to allocate 5% of total engineering dollars spent to permitting, since actual work performed by the engineering firm cannot be tracked by hours specifically to permitting. | 32 | Allocation of 0.5% of Construction dollars to Site Prep. | 50 | Lag during previous quarter. Since all money during the previous quarter was in-kind money, progression of this category will be at a slower pace from here on out as NTIA and BVU match funds are charged to it. | 32 | N/A | 46 | Lag in previous quarter. Based on changes in engineering, BVU does not expect that any PoP locations will have begun to be constructed by the end of Q2-2011. | 2 | Based on review of the schedule changes in the project, BVU expects Network Testing to fall behind Network Build by a little more than originally anticipated. | 2011-05-19 11:35 | 2011-05-19 11:35 | 5930 | 5930 | BVU Authority | TRUE
NT10BIX5570066 | 2011 | Q2 | Q2 - 2011 | 3402 | 3464 | FALSE | 45 | BVU Authority's project modifications are currently under review by NTIA. While current quarter percentages complete track by the amounts in each budget category as of 6/30/2011, the amounts in some of those categories will change for next quarter. Therefore, our projections for next quarter use the modified amounts. Please see attached baseline tracking spreadsheet for more info on current and projected percent(s) complete. | 98 |  | Since BVU cannot incur any more dollars to grant preparation, this category will remain at 98% complete, unless BVU later decides to transfer its remaining dollars to EA/mapping/Davis Bacon compliance. | 82 | This category will experience an increase in $5,000 budgeted, so the percentage complete will decrease, even after new charges incurred. This category will have $18,281 in it after project modifications are approved. However, since this category was approved at 100% federally-funded, we cannot add in another $5,000 at the same breakdown. Therefore, everything expended in this category after 6/30/2011 will follow the 80% federal/20% match breakdown like the rest of the budget, to keep federal and match dollars the same for the overall budget. | 47 | While this category is slightly below baseline predictions, it is expected to incur about the same amount as it did in Q2-2011. It will still be on track, as its percentage complete is still ahead of construction. This category will have $1,325,417 in it after project modifications are approved. | 68 | This category will not incur any expenses because PoP construction is not expected to start by the end of Q3-2011. However, since the amount in the category will have changed to a lower amount, the planned percentage complete increases. This category will have $938,279 in it after project modifications are approved. | 47 | This category is an allocated 5% of OMB category 4, and will incur proportionately the same amount as Network Design. This category will have $69,759 in it after project modifications are approved. | 45 | This category is an allocated 0.5% of OMB category 9, and will incur proportionately the same amount as Network Build. This category will have $156,832 in it after project modifications are approved. | 52 | After project modifications are approved in July 2011, PoP engineering should begin, as well as equipment procurement. This category will have $908,616 in it after project modifications are approved. | 45 | Network build will continue to remain ahead of schedule in Q3-2011. This category will have $31,209,666 in it after project modifications are approved. | 49 | As of the end of Q3-2011, PoP construction is not expected to have started. However, since project modifications decrease the amount in this category, the percentage complete will still increase. This category will have $908,616 in it after project modifications are approved. | 2 | Network testing will begin in Q3-2011. | 2011-08-31 17:38 | 2011-08-31 17:38 | 5930 | 5930 | BVU Authority | TRUE
NT10BIX5570066 | 2011 | Q3 | Q3 - 2011 | 4332 | 4021 | FALSE | 64 | Projections for next quarter contain the modified in-kind amounts mentioned previously. This will jump the percentages due to the influx of in-kind dollars.Percentage shown takes this into account. | 100 | Grant Prep | Completed. | 100 | Complete | 58 | Projections for next quarter contain the modified in-kind amounts mentioned previously. This will jump the percentages due to the influx of in-kind dollars.Percentage shown takes this into account. | 70 | No actual dollars are expected to be expended to this category during next period, but as noted in last quarter's report, the percentage was expected to increase slightly due to budget changes discussed previously. | 58 | This category is an allocated 5% of OMB category 4, and will incur proportionately the same amount as Network Design. | 65 | This category is an allocated 0.5% of OMB category 9, and will incur proportionately the same amount as Network Build. Projections for next quarter contain the modified in-kind amounts mentioned previously. This will jump the percentages due to the influx of in-kind dollars. Percentage shown takes this into account. | 60 | No actual dollars are expected to be expended to this category during next period, but as noted in last quarter's report, the percentage was expected to increase slightly due to budget changes discussed previously. | 65 | Network build experienced slow down, but is still on original schedule. Projections for next quarter contain the modified in-kind amounts mentioned previously. This will jump the percentages due to the influx of in-kind dollars. Percentage shown takes this into account. | 60 | No actual dollars are expected to be expended to this category during next period, but as noted in last quarter's report, the percentage was expected to increase slightly due to budget changes discussed previously. | 0 | Network testing will begin in Q4-2011. | 2011-11-30 12:05 | 2011-11-30 12:05 | 5930 | 5930 | BVU Authority | TRUE
NT10BIX5570066 | 2011 | Q4 | Q4 - 2011 | 5036 | 4708 | FALSE | 55 | Percentage reflects change to in-kind utilization reporting. Also, plan is to bring on more construction resources over the next two quarters to hit the 2/3 complete goal at end of second year. | 100 | Grant Prep | Completed | 100 | Complete. | 75 | Expect that 3/4 of the routes will be fully engineered by end of quarter. | 75 | This category is an allocated in relation to Network Design, and will incur proportionately. | 75 | This category is an allocated 0.5% of Network Design, and will incur proportionately. | 51 | This category is an allocated 0.5% of Network Build, and will incur proportionately. | 23 | As routes are being completed and lit during this quarter, equipment will start to be procured and deployed, as well as, in-kind utilization per miles build out. | 51 | Plan is to bring on more construction resources over the next two quarters to hit the 2/3 complete goal at end of second year. | 3 | First route planned to be lit in quarter | 3 | First route planned to be lit in quarter | 2012-02-15 15:07 | 2012-02-15 15:07 | 5930 | 5930 | BVU Authority | TRUE
NT10BIX5570066 | 2012 | Q1 | Q1 - 2012 | 5940 | 5569 | FALSE | 59 | Projected an estimated 55 miles to be build out. | 100 | Grant Prep | Complete | 100 | Complete. | 81 | All routes have had preliminary designs completed. Will continue to finalize routes. | 77 | Based on mileage completed. | 81 | Correlated with Network Design so percentage will concur with that category. | 59 | Correlated with Network Build so percentage will concur with that category. | 49 | Expect multiple routes to be completed and lit in 2012-Q2 with an effect that equipment based procurement and deployment will increase significantly. | 59 | Slightly ahead of schedule. | 49 | Expect multiple routes to be completed and lit in 2012-Q2 with an effect that equipment based procurement and deployment will increase significantly. | 22 | Expect multiple routes to be completed and lit in 2012-Q2 with an effect that network testing will increase significantly. | 2012-05-07 11:15 | 2012-05-07 11:15 | 5930 | 5930 | BVU Authority | TRUE
NT10BIX5570066 | 2012 | Q2 | Q2 - 2012 | 6958 | 6106 | FALSE | 81 | Project an estimated 49 miles to be build out. | 100 | Grant management | Complete | 100 | All current route environmental assessments complete. | 100 | All current route network design complete. | 79 | Based on mileage completed. | 98 | Based on expensed vs project dollars. Has been done in conjunction with Network Design on assumption was that permits and easements would be received as design built. This is no longer true due to easement issues. | 79 | Correlated with Network Build so percentage will concur with that category. | 57 | Expect 17 routes to be completed and lit by end of 2012-Q3. | 79 | Slightly ahead of baseline schedule. Baseline estimated at 78% at end of Q3-2012 | 57 | Allocation done in conjunction with Equipment Procurement, so percentage is consistent with Equipment Procurement percentage. | 34 | Expect multiple routes to be completed and lit in 2012-Q3 with an effect that network testing will increase significantly. | 2012-08-09 10:41 | 2012-08-09 10:42 | 7556 | 7556 | BVU Authority | TRUE