## Summary
Financial Information Summary
1. Overall Budget
Project Budget Element (1) | Federal Funds Awarded (2) | Approved Matching Funds (3) | Total Budget (4) | Federal Funds Expended (5) | Approved Matching Funds Expended (6) | Total Funds Expended (7)
Personnel Salaries | 1243667 | 480700 | 1724367 | 1117872.45 | 480700 | 1598572.45
Personnel Fringe Benefits | 223113 | 120159 | 343272 | 185768.89 | 120159 | 305927.89
Travel | 262805 | 0 | 262805 | 118069.35 | 0 | 118069.35
Equipment | 1203214 | 0 | 1203214 | 23152 | 0 | 23152
Materials/Supplies | 26270 | 0 | 26270 | 1109725.42 | 0 | 1109725.42
Subcontracts Total | 2369699 | 243455 | 2613154 | 1619884.99 | 243455 | 1863339.99
Construction | 0 | 0 | 0 | 0 | 0 | 0
Other | 400647 | 588027 | 988674 | 314748.99 | 588027 | 902775.99
Total Direct Costs | 5729415 | 1432341 | 7161756 | 4489222.09 | 1432341 | 5921563.09
Total Indirect Costs | 0 | 0 | 0 | 0 | 0 | 0
Total Costs | 5729415 | 1432341 | 7161756 | 4489222.09 | 1432341 | 5921563.09
% of Total | 80% | 20% | 100% | 75.81% | 24.19% | 100%
2. Budget by Project Type
Project Type (1) | Federal Funds Awarded (2) | Approved Matching Funds (3) | Total Budget (4) | Federal Funds Expended (5) | Approved Matching Funds Expended (6) | Total Funds Expended (7)
Data Collection | 2283882 | 831482 | 3115364 | 2038781.33 | 831482 | 2870263.33
Original Planning Grant | 0 | 0 | 0 | 0 | 0 | 0
Capacity Building | 1054616 | 0 | 1054616 | 779908.03 | 0 | 779908.03
Technical Assistance | 767180 | 600859 | 1368039 | 481491.52 | 600859 | 1082350.52
Planning Teams | 0 | 0 | 0 | 0 | 0 | 0
Address File | 623737 | 0 | 623737 | 162249.16 | 0 | 162249.16
Application Usage and Development | 0 | 0 | 0 | 0 | 0 | 0
Ownership and Adoption | 1000000 | 0 | 1000000 | 1026792.05 | 0 | 1026792.05
Leading Practices | 0 | 0 | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0 | 0 | 0
Total Costs across all Project Types | 5729415 | 1432341 | 7161756 | 4489222.09 | 1432341 | 5921563.09

## DataCollection
Project Title: | Data Collection
1. Budget
Project Budget Element (1) | Federal Funds Awarded (2) | Approved Matching Funds (3) | Total Budget (4) | Federal Funds Expended (5) | Approved Matching Funds Expended (6) | Total Funds Expended (7) | Expended Matching Funds Description (Ex. Staff salary for project manager and GIS specialist) | Q3 Fed Exp | Difference | Q3 Match | Difference
Personnel Salaries | 407392 | 0 | 407392 | 267488.83 | 0 | 267488.83 |  | 259585.36 | 7903.47 | 0 | 0
Personnel Fringe Benefits | 68847 | 0 | 68847 | 44451.5 | 0 | 44451.5 |  | 43138.1 | 1313.4 | 0 | 0
Travel | 37685 | 0 | 37685 | 37331.42 | 0 | 37331.42 |  | 36578.32 | 753.1 | 0 | 0
Equipment | 151613 | 0 | 151613 | 23152 | 0 | 23152 | Software products for broaband mapping were moved from equipment to other at the recommendation of the NTIA staff. This suggestion came up during closeout discussions with Brian Gibbons. | 23152 | 0 | 0 | 0
Materials/Supplies | 1000 | 0 | 1000 | 58442.12 | 0 | 58442.12 | Expenditures are greater than budgeted. Expenditures/budget will be realigned with budget amendment. | 58442.12 | 0 | 0 | 0
Subcontracts Total | 1472473 | 243455 | 1715928 | 1434205.96 | 243455 | 1677660.96 |  | 1387516.96 | 46689 | 243455 | 0
Construction | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Other | 144872 | 588027 | 732899 | 173709.5 | 588027 | 761736.5 | Software products for broadband mapping were moved from equipment to other at the recommendation of the NTIA staff. This suggestion came up during closeout discussions with Brian Gibbons. | 170595.54 | 3113.96 | 588027 | 0
Total Direct Costs | 2283882 | 831482 | 3115364 | 2038781.33 | 831482 | 2870263.33 |  | 1979008.4 | 59772.93 | 831482 | 0
Total Indirect Costs | 0 |  | 0 | 0 |  | 0 |  | 0 | 59772.93
Total Costs | 2283882 | 831482 | 3115364 | 2038781.33 | 831482 | 2870263.33
% of Total | 73.31% | 26.69% | 100% | 71.03% | 28.97% | 100%
2. Describe any additional project milestones that have been accomplished over this reporting period (Ex. Updates to state broadband maps and websites, map outreach activities)
•Completed the 10th NTIA data submission on 09/25/14 with 57 providers submitting data. Follow-ups for CAI updates were submitted at NTIA request. •Six providers were non-responsive for the 10th submission, and three responded to our outreach but did not supply data (one becoming non-cooperative and unwilling to participate in the program anymore). •Received CAI extract and ingested into files for the 10th data submission (2,021 CAI's). Worked with SDTA to better synchronize data between FCC and NTIA data collection efforts in October to resubmit and align with FCC. •Static maps have been updated with October submission data. •Speed test tile caches have been updated for our interactive map. •Speed tests as of 12/31/14: Driven 80,189 miles testing cellular signal and speeds, collected over 110,000 cellular speed tests and 1.97 million signal tests during road testing. We have a combined total of 723,080 speed tests from wireless/cellular and wireline services, collected and licensed. Our crowdsourcing tool has gathered 32,782 speed tests from our portal at speedtest.sd.gov, which is now shut down with the end of the project. •The state broadband.sd.gov website has been updated with: • 1) TPCO grant applications have been taken offline • 2) TPCO references for assessment registration have been modified to indicate the end of the project • 3) Will work on updating the survey pages in January • 4) Since our Ookla speed test license was not renewed, pointed users to other Ookla servers in the area including Midco and SDN • 5) Twitter and Facebook updates have slowed • 6) Other forms may be updated in January including CAI verification, report unserved area, public wifi, and share your story •Attended SBI closeout webinars to understand upcoming procedures and expectations. •Continue working through our list of activities to close out the project, including website updates indicating the closure of the project. •Suspended provider portal synchronization scripts and processes due to program activities coming to an end. They can be restarted if needed. •Data collection, verification, speed tests have concluded. All test devices were turned off by 12/15/2014, and all verification data archived. •Received additional analysis graphs / data from BroadMap for all of our broadband mapping data. Have included results of the analysis in a report to the SD Public Utilities Commission, and will include in our end of year / project reports.
3. Provide number of unique visitors for your state broadband website:
| Current Quarter | Cumulative (since website launch)
Unique Visitors | 43421 | 270506
Avg. Number Pages per Visit | 1.85 | 3.13
4. Provide any other information or statistics that you think would be useful to NTIA as it assesses your broadband data collection, Validation and publication activites.
none

## Original Planning Grant
Project Title: | Original Planning Grant
1. Budget
Project Budget Element (1) | Federal Funds Awarded (2) | Approved Matching Funds (3) | Total Budget (4) | Federal Funds Expended (5) | Approved Matching Funds Expended (6) | Total Funds Expended (7) | Expended Matching Funds Description (Ex. Staff salary for project manager and GIS specialist)
Personnel Salaries |  |  | 0 |  |  | 0
Personnel Fringe Benefits |  |  | 0 |  |  | 0
Travel |  |  | 0 |  |  | 0
Equipment |  |  | 0 |  |  | 0
Materials/Supplies |  |  | 0 |  |  | 0
Subcontracts Total |  |  | 0 |  |  | 0
Construction |  |  | 0 |  |  | 0
Other |  |  | 0 |  |  | 0
Total Direct Costs | 0 | 0 | 0 | 0 | 0 | 0
Total Indirect Costs |  |  | 0 |  |  | 0
Total Costs | 0 | 0 | 0 | 0 | 0 | 0
% of Total | 0% | 0% | 0% | 0% | 0% | 0%
2. Describe your progress meeting each major activity/milestone approved in the Project Plan for this project; any challenges or obstacles encountered and mitigation strategies you have employed; planned major activities for the next quarter; and any additional project milestones or information.
3. If the project team anticipates requesting any changes to the approved project plan in the next quarter, describe these below. Note that any substantive changes to the project plan must be approved by the Department of Commerce before implementation.
4. Provide any other information that you think would be useful to NTIA as it assesses this project's progress.
5. Attach as a separate document any success stories or best practices you have identified. Please be as specific as possible.

## Capacity Building
Project Title: | Capacity Building
1. Budget
Project Budget Element (1) | Federal Funds Awarded (2) | Approved Matching Funds (3) | Total Budget (4) | Federal Funds Expended (5) | Approved Matching Funds Expended (6) | Total Funds Expended (7) | Expended Matching Funds Description (Ex. Staff salary for project manager and GIS specialist) | Q3 Fed Exp | Difference | Q3 Match | Difference
Personnel Salaries | 445169 | 0 | 445169 | 475812.38 | 0 | 475812.38 |  | 454723.69 | 21088.69 | 0 | 0
Personnel Fringe Benefits | 87942 | 0 | 87942 | 79070.86 | 0 | 79070.86 |  | 75566.33 | 3504.53 | 0 | 0
Travel | 25000 | 0 | 25000 | 22455.76 | 0 | 22455.76 |  | 21918.81 | 536.95 | 0 | 0
Equipment | 12303 | 0 | 12303 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Materials/Supplies | 10178 | 0 | 10178 | 12559.83 | 0 | 12559.83 | Expenditures are less than reported in Q3 - reimbursement of $15,000 received from Telogical Systems - contract cancelled. Expenditures/budget will be realigned with budget amendment. | 12559.83 | 0 | 0 | 0
Subcontracts Total | 458989 | 0 | 458989 | 166497.03 | 0 | 166497.03 |  | 166497.03 | 0 | 0 | 0
Construction | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Other | 15035 | 0 | 15035 | 23512.17 | 0 | 23512.17 | Expenditures are greater than budgeted. Expenditures/budget will be realigned with budget amendment. | 22864.98 | 647.19 | 0 | 0
Total Direct Costs | 1054616 | 0 | 1054616 | 779908.03 | 0 | 779908.03 |  | 754130.67 | 25777.36 | 0 | 0
Total Indirect Costs | 0 | 0 | 0 | 0 | 0 | 0
Total Costs | 1054616 | 0 | 1054616 | 779908.03 | 0 | 779908.03
% of Total | 100% | 0% | 100% | 100% | 0% | 100%
2. Describe your progress meeting each major activity/milestone approved in the Project Plan for this project; any challenges or obstacles encountered and mitigation strategies you have employed; planned major activities for the next quarter; and any additional project milestones or information.
•Continue to share information with Broadband Advisory Team members via email. Will send any final, closeout related items/notes before closure. •The 2014 Ag Survey report is nearly finalized, entering the final draft. •Reduced daily / frequent Facebook and Twittering, but will monitor sites until removed. Undetermined when/if our social media will be maintained. •Received additional analysis graphs/data from BroadMap for all of our broadband mapping data. Have included results of the analysis in a report to the PUC and will include in our end of year / project reports. •Final project report is being reviewed. •Attended SBI close-out webinars •Held a team broadband project review with BIT directors and staff as part of completing the project. •Responded to Danielle Natz, of Booz Allen Hamilton, regarding clarification of a team member's quote during a NTIA on-site interview in summer 2014. •Spoke with Gini Grannes, SDTA (SD Telecommunications Association) regarding whether there has been any measurement of increased usage since the broadband initiative began. We will provide her with the 2014 Ag Survey, point her to maps and data that depict availability speeds. We are not privy to providers' "usage data." •Continue speaking with representatives from other states, most recently Maine and Minnesota, on the subject of continued/ongoing mapping efforts.
3. If the project team anticipates requesting any changes to the approved project plan in the next quarter, describe these below. Note that any substantive changes to the project plan must be approved by the Department of Commerce before implementation.
No project plan changes anticipated.
4. Provide any other information that you think would be useful to NTIA as it assesses this project's progress.
none
5. Attach as a separate document any success stories or best practices you have identified. Please be as specific as possible.
See attachment: Q4 2014 Supplemental Answers - Questions 14B - Capacity Building - Ownership and Adoption.doc

## Technical Assistance
Project Title: | Technical Assistance
1. Budget
Project Budget Element (1) | Federal Funds Awarded (2) | Approved Matching Funds (3) | Total Budget (4) | Federal Funds Expended (5) | Approved Matching Funds Expended (6) | Total Funds Expended (7) | Expended Matching Funds Description (Ex. Staff salary for project manager and GIS specialist) | Q3 Fed Exp | Difference | Q3 Match | Difference
Personnel Salaries | 356106 | 480700 | 836806 | 349592.01 | 480700 | 830292.01 | Staff salaries for State Department of Education technologists providing technical assistance to education CAIs | 340791.28 | 8800.73 | 480700 | 0
Personnel Fringe Benefits | 60324 | 120159 | 180483 | 58095.46 | 120159 | 178254.46 | Staff salaries for State Department of Education technologists providing technical assistance to education CAIs | 56632.95 | 1462.51 | 120159 | 0
Travel | 145120 | 0 | 145120 | 37901.75 | 0 | 37901.75 |  | 35952.31 | 1949.44 | 0 | 0
Equipment | 29298 | 0 | 29298 | 0 | 0 | 0 | Expenditures associated with equipment previously are now shown in Materials/Suppplies to properly account for expenditures under the $5,000 equipment limitation. | 0 | 0 | 0 | 0
Materials/Supplies | 15092 | 0 | 15092 | 11427 | 0 | 11427 |  | 11427 | 0 | 0 | 0
Subcontracts Total | 153000 | 0 | 153000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Construction | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Other | 8240 | 0 | 8240 | 24475.3 | 0 | 24475.3 | Expenditures are greater than budgeted. Expenditures/budget will be realigned with budget amendment. | 23713.46 | 761.84 | 0 | 0
Total Direct Costs | 767180 | 600859 | 1368039 | 481491.52 | 600859 | 1082350.52 |  | 468517 | 12974.52 | 600859 | 0
Total Indirect Costs | 0 | 0 | 0 | 0 | 0 | 0
Total Costs | 767180 | 600859 | 1368039 | 481491.52 | 600859 | 1082350.52
% of Total | 56.08% | 43.92% | 100% | 44.49% | 55.51% | 100%
2. Describe your progress meeting each major activity/milestone approved in the Project Plan for this project; any challenges or obstacles encountered and mitigation strategies you have employed; planned major activities for the next quarter; and any additional project milestones or information.
•The overall total assessments conducted in 2011 - 2014 totaled 233 (32 were performed in 2014). •Assessment reports continue to be valuable assets to CAI's as a result of the assessments. •Even though subgrant funding for equipment has been exhausted, CAI's have still been very active in procuring necessary equipment for improvements through still active contracts at no cost to the program.
3. If the project team anticipates requesting any changes to the approved project plan in the next quarter, describe these below. Note that any substantive changes to the project plan must be approved by the Department of Commerce before implementation.
No project plan changes anticipated.
4. Provide any other information that you think would be useful to NTIA as it assesses this project's progress.
none
5. Attach as a separate document any success stories or best practices you have identified. Please be as specific as possible.
none

## Planning Teams
Project Title: | Planning Teams
1. Budget
Project Budget Element (1) | Federal Funds Awarded (2) | Approved Matching Funds (3) | Total Budget (4) | Federal Funds Expended (5) | Approved Matching Funds Expended (6) | Total Funds Expended (7) | Expended Matching Funds Description (Ex. Staff salary for project manager and GIS specialist)
Personnel Salaries |  |  | 0 |  |  | 0
Personnel Fringe Benefits |  |  | 0 |  |  | 0
Travel |  |  | 0 |  |  | 0
Equipment |  |  | 0 |  |  | 0
Materials/Supplies |  |  | 0 |  |  | 0
Subcontracts Total |  |  | 0 |  |  | 0
Construction |  |  | 0 |  |  | 0
Other |  |  | 0 |  |  | 0
Total Direct Costs | 0 | 0 | 0 | 0 | 0 | 0
Total Indirect Costs |  |  | 0 |  |  | 0
Total Costs | 0 | 0 | 0 | 0 | 0 | 0
% of Total | 0% | 0% | 0% | 0% | 0% | 0%
2. Describe your progress meeting each major activity/milestone approved in the Project Plan for this project; any challenges or obstacles encountered and mitigation strategies you have employed; planned major activities for the next quarter; and any additional project milestones or information.
3. If the project team anticipates requesting any changes to the approved project plan in the next quarter, describe these below. Note that any substantive changes to the project plan must be approved by the Department of Commerce before implementation.
4. Provide any other information that you think would be useful to NTIA as it assesses this project's progress.
5. Attach as a separate document any success stories or best practices you have identified. Please be as specific as possible.

## Address File
Project Title: | Address File
1. Budget
Project Budget Element (1) | Federal Funds Awarded (2) | Approved Matching Funds (3) | Total Budget (4) | Federal Funds Expended (5) | Approved Matching Funds Expended (6) | Total Funds Expended (7) | Expended Matching Funds Description (Ex. Staff salary for project manager and GIS specialist) | Q3 Fed Exp | Difference | Q3 Match | Difference
Personnel Salaries | 35000 | 0 | 35000 | 24979.23 | 0 | 24979.23 |  | 24979.23 | 0 | 0 | 0
Personnel Fringe Benefits | 6000 | 0 | 6000 | 4151.07 | 0 | 4151.07 |  | 4151.07 | 0 | 0 | 0
Travel | 55000 | 0 | 55000 | 20380.42 | 0 | 20380.42 |  | 20294.02 | 86.4 | 0 | 0
Equipment | 10000 | 0 | 10000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Materials/Supplies | 0 | 0 | 0 | 504.42 | 0 | 504.42 | Expenditures are greater than budgeted. Expenditures/budget will be realigned with budget amendment. | 504.42 | 0 | 0 | 0
Subcontracts Total | 285237 | 0 | 285237 | 19182 | 0 | 19182 |  | 19182 | 0 | 0 | 0
Construction | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Other | 232500 | 0 | 232500 | 93052.02 | 0 | 93052.02 |  | 91552.02 | 1500 | 0 | 0
Total Direct Costs | 623737 | 0 | 623737 | 162249.16 | 0 | 162249.16 |  | 160662.76 | 1586.4 | 0 | 0
Total Indirect Costs | 0 | 0 | 0 | 0 | 0 | 0
Total Costs | 623737 | 0 | 623737 | 162249.16 | 0 | 162249.16
% of Total | 100% | 0% | 100% | 100% | 0% | 100%
2. Describe your progress meeting each major activity/milestone approved in the Project Plan for this project; any challenges or obstacles encountered and mitigation strategies you have employed; planned major activities for the next quarter; and any additional project milestones or information.
•Completed this part of the program and turned it over to the GIS team. •Total number of address points collected and or verified in 2014 was approximately 40,000. •Delivered address file dataset to NG911 GIS contractor. •With the NG911 GIS project officially off the ground, this data is being reviewed for inclusion in our statewide NG911 dataset, and should significantly bolster the efforts with 48 counties worth of data. We are excited to see another large project making use of this data. •All address data collected to-date is ingested in the locator service. •Created a map of the 66 South Dakota counties to indicate the counties we have data for: No data (9 counties); Data point is in front of house on road (3 counties); Data point is on rooftop (45 counties); Data purchased from counties but not verified (9 counties). •Outreach efforts to the 9 counties without addressing data produced nothing more. Most do not have GIS capabilities. They were not interested in participating.
3. If the project team anticipates requesting any changes to the approved project plan in the next quarter, describe these below. Note that any substantive changes to the project plan must be approved by the Department of Commerce before implementation.
No project plan changes anticipated.
4. Provide any other information that you think would be useful to NTIA as it assesses this project's progress.
none
5. Attach as a separate document any success stories or best practices you have identified. Please be as specific as possible.
none

## Application Usage
Project Title: | Application Usage and Development
1. Budget
Project Budget Element (1) | Federal Funds Awarded (2) | Approved Matching Funds (3) | Total Budget (4) | Federal Funds Expended (5) | Approved Matching Funds Expended (6) | Total Funds Expended (7) | Expended Matching Funds Description (Ex. Staff salary for project manager and GIS specialist)
Personnel Salaries |  |  | 0 |  |  | 0
Personnel Fringe Benefits |  |  | 0 |  |  | 0
Travel |  |  | 0 |  |  | 0
Equipment |  |  | 0 |  |  | 0
Materials/Supplies |  |  | 0 |  |  | 0
Subcontracts Total |  |  | 0 |  |  | 0
Construction |  |  | 0 |  |  | 0
Other |  |  | 0 |  |  | 0
Total Direct Costs | 0 | 0 | 0 | 0 | 0 | 0
Total Indirect Costs |  |  | 0 |  |  | 0
Total Costs | 0 | 0 | 0 | 0 | 0 | 0
% of Total | 0% | 0% | 0% | 0% | 0% | 0%
2. Describe your progress meeting each major activity/milestone approved in the Project Plan for this project; any challenges or obstacles encountered and mitigation strategies you have employed; planned major activities for the next quarter; and any additional project milestones or information.
3. If the project team anticipates requesting any changes to the approved project plan in the next quarter, describe these below. Note that any substantive changes to the project plan must be approved by the Department of Commerce before implementation.
4. Provide any other information that you think would be useful to NTIA as it assesses this project's progress.
5. Attach as a separate document any success stories or best practices you have identified. Please be as specific as possible.

## Ownership Adoption
Project Title: | Ownership and Adoption
1. Budget
Project Budget Element (1) | Federal Funds Awarded (2) | Approved Matching Funds (3) | Total Budget (4) | Federal Funds Expended (5) | Approved Matching Funds Expended (6) | Total Funds Expended (7) | Expended Matching Funds Description (Ex. Staff salary for project manager and GIS specialist) | Q3 Fed Exp | Difference | Q3 Match | Difference
Personnel Salaries | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Personnel Fringe Benefits | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Travel | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Equipment | 1000000 | 0 | 1000000 | 0 | 0 | 0 | Expenditures/budget will be realigned with budget amendment. | 0 | 0 | 0 | 0
Materials/Supplies | 0 | 0 | 0 | 1026792.05 | 0 | 1026792.05 | Expenditures are greater than budgeted. Expenditures/budget will be realigned with budget amendment. | 1021608.85 | 5183.2 | 0 | 0
Subcontracts Total | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Construction | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Direct Costs | 1000000 | 0 | 1000000 | 1026792.05 | 0 | 1026792.05 |  | 1021608.85 | 5183.2 | 0 | 0
Total Indirect Costs | 0 | 0 | 0 | 0 | 0 | 0
Total Costs | 1000000 | 0 | 1000000 | 1026792.05 | 0 | 1026792.05
% of Total | 100% | 0% | 100% | 100% | 0% | 100%
2. Describe your progress meeting each major activity/milestone approved in the Project Plan for this project; any challenges or obstacles encountered and mitigation strategies you have employed; planned major activities for the next quarter; and any additional project milestones or information.
•Resolved issues / questions with grant recipients from grant round 6. •Keloland TV, the state's largest television network, produced a news story on the improvements of our program, on television and online, featuring grant recipient South Dakota Moody County Sherriff's Office.
3. If the project team anticipates requesting any changes to the approved project plan in the next quarter, describe these below. Note that any substantive changes to the project plan must be approved by the Department of Commerce before implementation.
No project plan changes anticipated.
4. Provide any other information that you think would be useful to NTIA as it assesses this project's progress.
none
5. Attach as a separate document any success stories or best practices you have identified. Please be as specific as possible.
See attachment: Q4 2014 Supplemental Answers - Questions 14B - Capacity Building - Ownership and Adoption.doc

## Leading Practices
Project Title: | Leading Practices
1. Budget
Project Budget Element (1) | Federal Funds Awarded (2) | Approved Matching Funds (3) | Total Budget (4) | Federal Funds Expended (5) | Approved Matching Funds Expended (6) | Total Funds Expended (7) | Expended Matching Funds Description (Ex. Staff salary for project manager and GIS specialist)
Personnel Salaries |  |  | 0 |  |  | 0
Personnel Fringe Benefits |  |  | 0 |  |  | 0
Travel |  |  | 0 |  |  | 0
Equipment |  |  | 0 |  |  | 0
Materials/Supplies |  |  | 0 |  |  | 0
Subcontracts Total |  |  | 0 |  |  | 0
Construction |  |  | 0 |  |  | 0
Other |  |  | 0 |  |  | 0
Total Direct Costs | 0 | 0 | 0 | 0 | 0 | 0
Total Indirect Costs |  |  | 0 |  |  | 0
Total Costs | 0 | 0 | 0 | 0 | 0 | 0
% of Total | 0% | 0% | 0% | 0% | 0% | 0%
2. Describe your progress meeting each major activity/milestone approved in the Project Plan for this project; any challenges or obstacles encountered and mitigation strategies you have employed; planned major activities for the next quarter; and any additional project milestones or information.
3. If the project team anticipates requesting any changes to the approved project plan in the next quarter, describe these below. Note that any substantive changes to the project plan must be approved by the Department of Commerce before implementation.
4. Provide any other information that you think would be useful to NTIA as it assesses this project's progress.
5. Attach as a separate document any success stories or best practices you have identified. Please be as specific as possible.

## Other
Project Title: | Other
1. Budget
Project Budget Element (1) | Federal Funds Awarded (2) | Approved Matching Funds (3) | Total Budget (4) | Federal Funds Expended (5) | Approved Matching Funds Expended (6) | Total Funds Expended (7) | Expended Matching Funds Description (Ex. Staff salary for project manager and GIS specialist)
Personnel Salaries |  |  | 0 |  |  | 0
Personnel Fringe Benefits |  |  | 0 |  |  | 0
Travel |  |  | 0 |  |  | 0
Equipment |  |  | 0 |  |  | 0
Materials/Supplies |  |  | 0 |  |  | 0
Subcontracts Total |  |  | 0 |  |  | 0
Construction |  |  | 0 |  |  | 0
Other |  |  | 0 |  |  | 0
Total Direct Costs | 0 | 0 | 0 | 0 | 0 | 0
Total Indirect Costs |  |  | 0 |  |  | 0
Total Costs | 0 | 0 | 0 | 0 | 0 | 0
% of Total | 0% | 0% | 0% | 0% | 0% | 0%
2. Describe your progress meeting each major activity/milestone approved in the Project Plan for this project; any challenges or obstacles encountered and mitigation strategies you have employed; planned major activities for the next quarter; and any additional project milestones or information.
3. If the project team anticipates requesting any changes to the approved project plan in the next quarter, describe these below. Note that any substantive changes to the project plan must be approved by the Department of Commerce before implementation.
4. Provide any other information that you think would be useful to NTIA as it assesses this project's progress.
5. Attach as a separate document any success stories or best practices you have identified. Please be as specific as possible.